## Project Model
Input scroll bar
Average
| Bid | 900
| Finish in Months |  | 18 | Cost in $000s |  | 800 | Penalty | 0 | Profit | 100
| Average Finish |  | 19.8704 | Average Cost |  | 800 | Avg. Penalty | 101.7107 | Avg. Profit | -1.7107
Penalty Parameters
[9 empty] | Deadline (Months) | 18
[9 empty] | Daily Penalty 000s | 1
[9 empty] | Profit Level | -130
[9 empty] | Chance of Profit Below this Level | 26.6%
[9 empty] | Percentile Scroll Bar |  | © Copyright 2013, ProbabilityManagement.org
Calculations Below
|  |  |  | GANTT Chart Calculations | [6 empty] | Penalty Calculations
47
|  | Durations |  |  |  | Start |  |  | Finish |  |  | -1.7186e-08
0 | House | 12 |  | Remodel_2 |  | 12 | 6 | 6 | 18 | 19.8704 |  | 0
| Remodel_1 | 6 |  | Remodel_1 |  | 12 | 6
| Remodel_2 | 6 |  | House |  | 0 | 12
[5 empty] | House_Cost |  | Remodel_1_Cost |  | Remodel_2_Cost
[5 empty] | 400 |  | 200 |  | 200
Model accompanying The Flaw of Averages in Project Management.
by Philip Fahringer, John Hinton, Marc Thibault and Sam Savage. (2011)
http://probabilitymanagement.org/Library/PMI%20FOA%20in%20Projects.pdf

## SIP Library
Trials | 1000 | Average | 1001
|  | House Cost | House Duration | Remodel 1 Cost | Remodel 1 Duration | Remodel 2 Cost | Remodel 2 Duration | MN | MR1 | MR2
|  | 243.253 | 28.3877 | 103.8232 | 3.6098 | 125.6241 | 2.4732 | 28.3877 | 3.6098 | 2.4732
|  | 449.1913 | 20.4134 | 157.3343 | 10.8987 | 277.2604 | 4.3843 | 20.4134 | 10.8987 | 4.3843
|  | 342.9409 | 12.0166 | 379.5599 | 7.8765 | 117.7809 | 3.1843 | 12.0166 | 7.8765 | 3.1843
|  | 371.1637 | 8.3585 | 132.4973 | 2.3654 | 247.1946 | 3.9843 | 8.3585 | 2.3654 | 3.9843
|  | 396.0661 | 8.3585 | 315.5067 | 7.8765 | 172.6837 | 11.8797 | 8.3585 | 7.8765 | 11.8797
|  | 391.0856 | 8.3585 | 166.4848 | 7.8765 | 247.1946 | 3.9843 | 8.3585 | 7.8765 | 3.9843
|  | 391.0856 | 8.3585 | 123.3469 | 0.54638 | 183.1413 | 8.9621 | 8.3585 | 0.54638 | 8.9621
|  | 256.6124 | 9.6056 | 204.3939 | 3.6098 | 308.6335 | 7.9843 | 9.6056 | 3.6098 | 7.9843
|  | 449.1913 | 20.4134 | 201.7794 | 7.8765 | 159.6116 | 7.9843 | 20.4134 | 7.8765 | 7.9843
|  | 256.6124 | 9.6056 | 132.4973 | 2.3654 | 103.8232 | 3.7177 | 9.6056 | 2.3654 | 3.7177
|  | 391.0856 | 8.3585 | 201.7794 | 7.8765 | 156.9972 | 1.9843 | 8.3585 | 7.8765 | 1.9843
|  | 243.253 | 28.3877 | 201.7794 | 7.8765 | 173.9909 | 4.5621 | 28.3877 | 7.8765 | 4.5621
|  | 362.8629 | 7.1877 | 163.8704 | 1.8765 | 197.5206 | 3.1843 | 7.1877 | 1.8765 | 3.1843
|  | 362.8629 | 7.1877 | 379.5599 | 7.8765 | 218.436 | 11.8797 | 7.1877 | 7.8765 | 11.8797
|  | 243.253 | 28.3877 | 225.3092 | 11.8797 | 143.9251 | 9.4954 | 28.3877 | 11.8797 | 9.4954
|  | 342.9409 | 12.0166 | 103.8232 | 3.6098 | 116.4737 | 0.54638 | 12.0166 | 3.6098 | 0.54638
|  | 391.0856 | 8.3585 | 201.7794 | 4.2765 | 197.5206 | 3.1843 | 8.3585 | 4.2765 | 3.1843
|  | 256.6124 | 9.6056 | 201.7794 | 4.2765 | 194.9062 | 4.3843 | 9.6056 | 4.2765 | 4.3843
|  | 362.8629 | 7.1877 | 133.8045 | 3.6098 | 249.809 | 11.8797 | 7.1877 | 3.6098 | 11.8797
|  | 362.8629 | 7.1877 | 103.8232 | 3.6098 | 194.9062 | 7.9843 | 7.1877 | 3.6098 | 7.9843
|  | 362.8629 | 7.1877 | 150.7983 | 9.3876 | 183.1413 | 8.9621 | 7.1877 | 9.3876 | 8.9621
|  | 243.253 | 28.3877 | 152.1055 | 3.0765 | 119.0881 | 1.9843 | 28.3877 | 3.0765 | 1.9843
|  | 243.253 | 28.3877 | 204.3939 | 3.6098 | 172.6837 | 11.8797 | 28.3877 | 3.6098 | 11.8797
|  | 256.6124 | 9.6056 | 188.7073 | 7.8765 | 218.436 | 11.8797 | 9.6056 | 7.8765 | 11.8797
|  | 449.1913 | 20.4134 | 190.0146 | 8.8543 | 218.436 | 11.8797 | 20.4134 | 8.8543 | 11.8797
|  | 500.6564 | 12.9311 | 179.5569 | 11.8797 | 159.6116 | 7.9843 | 12.9311 | 11.8797 | 7.9843
|  | 666.5945 | 8.3585 | 315.5067 | 7.8765 | 159.6116 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 666.5945 | 8.3585 | 201.7794 | 4.2765 | 117.7809 | 3.1843 | 8.3585 | 4.2765 | 3.1843
|  | 243.253 | 28.3877 | 166.4848 | 7.8765 | 247.1946 | 3.9843 | 28.3877 | 7.8765 | 3.9843
|  | 342.9409 | 12.0166 | 125.9613 | 1.8765 | 308.6335 | 7.9843 | 12.0166 | 1.8765 | 7.9843
|  | 371.1637 | 8.3585 | 201.7794 | 4.2765 | 119.0881 | 1.9843 | 8.3585 | 4.2765 | 1.9843
|  | 666.5945 | 8.3585 | 256.6822 | 11.8797 | 194.9062 | 4.3843 | 8.3585 | 11.8797 | 4.3843
|  | 391.0856 | 8.3585 | 133.8045 | 3.6098 | 197.5206 | 3.7177 | 8.3585 | 3.6098 | 3.7177
|  | 449.1913 | 20.4134 | 180.8641 | 4.4543 | 181.8341 | 7.9843 | 20.4134 | 4.4543 | 7.9843
|  | 256.6124 | 9.6056 | 150.7983 | 9.3876 | 156.9972 | 1.9843 | 9.6056 | 9.3876 | 1.9843
|  | 243.253 | 28.3877 | 157.3343 | 10.8987 | 249.809 | 11.8797 | 28.3877 | 10.8987 | 11.8797
|  | 371.1637 | 8.3585 | 190.0146 | 8.8543 | 116.4737 | 0.54638 | 8.3585 | 8.8543 | 0.54638
|  | 362.8629 | 7.1877 | 190.0146 | 8.8543 | 249.809 | 11.8797 | 7.1877 | 8.8543 | 11.8797
|  | 243.253 | 28.3877 | 225.3092 | 11.8797 | 159.6116 | 7.9843 | 28.3877 | 11.8797 | 7.9843
|  | 243.253 | 28.3877 | 204.3939 | 3.6098 | 143.9251 | 9.4954 | 28.3877 | 3.6098 | 9.4954
|  | 256.6124 | 9.6056 | 225.3092 | 11.8797 | 173.9909 | 4.5621 | 9.6056 | 11.8797 | 4.5621
|  | 256.6124 | 9.6056 | 166.4848 | 7.8765 | 119.0881 | 1.9843 | 9.6056 | 7.8765 | 1.9843
|  | 371.1637 | 8.3585 | 180.8641 | 4.4543 | 125.6241 | 2.4732 | 8.3585 | 4.4543 | 2.4732
|  | 362.8629 | 7.1877 | 124.6541 | 3.0765 | 103.8232 | 3.7177 | 7.1877 | 3.0765 | 3.7177
|  | 243.253 | 28.3877 | 179.5569 | 5.4765 | 143.9251 | 9.4954 | 28.3877 | 5.4765 | 9.4954
|  | 371.1637 | 8.3585 | 132.4973 | 2.3654 | 159.6116 | 7.9843 | 8.3585 | 2.3654 | 7.9843
|  | 391.0856 | 8.3585 | 201.7794 | 7.8765 | 143.9251 | 9.4954 | 8.3585 | 7.8765 | 9.4954
|  | 371.1637 | 8.3585 | 179.5569 | 11.8797 | 181.8341 | 7.9843 | 8.3585 | 11.8797 | 7.9843
|  | 342.9409 | 12.0166 | 180.8641 | 4.4543 | 126.9313 | 3.7177 | 12.0166 | 4.4543 | 3.7177
|  | 500.6564 | 12.9311 | 188.7073 | 7.8765 | 172.6837 | 11.8797 | 12.9311 | 7.8765 | 11.8797
|  | 449.1913 | 20.4134 | 133.8045 | 3.6098 | 145.2323 | 3.1843 | 20.4134 | 3.6098 | 3.1843
|  | 371.1637 | 8.3585 | 204.3939 | 3.6098 | 218.436 | 11.8797 | 8.3585 | 3.6098 | 11.8797
|  | 449.1913 | 20.4134 | 201.7794 | 4.2765 | 159.6116 | 7.9843 | 20.4134 | 4.2765 | 7.9843
|  | 256.6124 | 9.6056 | 225.3092 | 11.8797 | 125.6241 | 2.4732 | 9.6056 | 11.8797 | 2.4732
|  | 342.9409 | 12.0166 | 204.3939 | 3.0765 | 308.6335 | 7.9843 | 12.0166 | 3.0765 | 7.9843
|  | 666.5945 | 8.3585 | 225.3092 | 11.8797 | 437.1616 | 3.4954 | 8.3585 | 11.8797 | 3.4954
|  | 371.1637 | 8.3585 | 125.9613 | 1.8765 | 372.6867 | 7.9843 | 8.3585 | 1.8765 | 7.9843
|  | 342.9409 | 12.0166 | 133.8045 | 3.6098 | 437.1616 | 3.4954 | 12.0166 | 3.6098 | 3.4954
|  | 449.1913 | 20.4134 | 123.3469 | 0.54638 | 119.0881 | 1.9843 | 20.4134 | 0.54638 | 1.9843
|  | 342.9409 | 12.0166 | 254.0678 | 3.8765 | 194.9062 | 4.3843 | 12.0166 | 3.8765 | 4.3843
|  | 256.6124 | 9.6056 | 190.0146 | 8.8543 | 277.2604 | 4.3843 | 9.6056 | 8.8543 | 4.3843
|  | 342.9409 | 12.0166 | 152.1055 | 3.0765 | 119.0881 | 1.9843 | 12.0166 | 3.0765 | 1.9843
|  | 396.0661 | 8.3585 | 150.7983 | 9.3876 | 103.8232 | 3.7177 | 8.3585 | 9.3876 | 3.7177
|  | 396.0661 | 8.3585 | 188.7073 | 7.8765 | 145.2323 | 3.1843 | 8.3585 | 7.8765 | 3.1843
|  | 362.8629 | 7.1877 | 152.1055 | 3.0765 | 234.1225 | 6.7843 | 7.1877 | 3.0765 | 6.7843
|  | 391.0856 | 8.3585 | 157.3343 | 10.8987 | 119.0881 | 1.9843 | 8.3585 | 10.8987 | 1.9843
|  | 243.253 | 28.3877 | 379.5599 | 7.8765 | 277.2604 | 4.3843 | 28.3877 | 7.8765 | 4.3843
|  | 256.6124 | 9.6056 | 157.3343 | 10.8987 | 173.9909 | 4.5621 | 9.6056 | 10.8987 | 4.5621
|  | 342.9409 | 12.0166 | 125.9613 | 1.8765 | 173.9909 | 4.5621 | 12.0166 | 1.8765 | 4.5621
|  | 243.253 | 28.3877 | 204.3939 | 3.0765 | 183.1413 | 8.9621 | 28.3877 | 3.0765 | 8.9621
|  | 342.9409 | 12.0166 | 180.8641 | 4.4543 | 156.9972 | 1.9843 | 12.0166 | 4.4543 | 1.9843
|  | 500.6564 | 12.9311 | 285.4409 | 7.8765 | 103.8232 | 3.7177 | 12.9311 | 7.8765 | 3.7177
|  | 449.1913 | 20.4134 | 379.5599 | 7.8765 | 172.6837 | 5.5843 | 20.4134 | 7.8765 | 5.5843
|  | 371.1637 | 8.3585 | 152.1055 | 3.0765 | 197.5206 | 3.7177 | 8.3585 | 3.0765 | 3.7177
|  | 391.0856 | 8.3585 | 315.5067 | 7.8765 | 194.9062 | 4.3843 | 8.3585 | 7.8765 | 4.3843
|  | 391.0856 | 8.3585 | 179.5569 | 11.8797 | 125.6241 | 2.4732 | 8.3585 | 11.8797 | 2.4732
|  | 371.1637 | 8.3585 | 150.7983 | 9.3876 | 150.4611 | 11.0066 | 8.3585 | 9.3876 | 11.0066
|  | 449.1913 | 20.4134 | 285.4409 | 7.8765 | 150.4611 | 11.0066 | 20.4134 | 7.8765 | 11.0066
|  | 391.0856 | 8.3585 | 152.1055 | 3.0765 | 172.6837 | 5.5843 | 8.3585 | 3.0765 | 5.5843
|  | 500.6564 | 12.9311 | 190.0146 | 8.8543 | 247.1946 | 3.9843 | 12.9311 | 8.8543 | 3.9843
|  | 371.1637 | 8.3585 | 285.4409 | 7.8765 | 172.6837 | 11.8797 | 8.3585 | 7.8765 | 11.8797
|  | 391.0856 | 8.3585 | 204.3939 | 3.6098 | 143.9251 | 9.4954 | 8.3585 | 3.6098 | 9.4954
|  | 666.5945 | 8.3585 | 256.6822 | 11.8797 | 247.1946 | 3.9843 | 8.3585 | 11.8797 | 3.9843
|  | 666.5945 | 8.3585 | 315.5067 | 7.8765 | 194.9062 | 4.3843 | 8.3585 | 7.8765 | 4.3843
|  | 243.253 | 28.3877 | 133.8045 | 3.6098 | 308.6335 | 7.9843 | 28.3877 | 3.6098 | 7.9843
|  | 500.6564 | 12.9311 | 285.4409 | 7.8765 | 249.809 | 11.8797 | 12.9311 | 7.8765 | 11.8797
|  | 449.1913 | 20.4134 | 103.8232 | 3.6098 | 116.4737 | 0.54638 | 20.4134 | 3.6098 | 0.54638
|  | 396.0661 | 8.3585 | 133.8045 | 3.6098 | 173.9909 | 4.5621 | 8.3585 | 3.6098 | 4.5621
|  | 396.0661 | 8.3585 | 180.8641 | 4.4543 | 117.7809 | 3.1843 | 8.3585 | 4.4543 | 3.1843
|  | 391.0856 | 8.3585 | 166.4848 | 7.8765 | 183.1413 | 8.9621 | 8.3585 | 7.8765 | 8.9621
|  | 342.9409 | 12.0166 | 103.8232 | 3.6098 | 173.9909 | 4.5621 | 12.0166 | 3.6098 | 4.5621
|  | 666.5945 | 8.3585 | 179.5569 | 5.4765 | 247.1946 | 3.9843 | 8.3585 | 5.4765 | 3.9843
|  | 666.5945 | 8.3585 | 240.9957 | 6.6765 | 197.5206 | 3.1843 | 8.3585 | 6.6765 | 3.1843
|  | 396.0661 | 8.3585 | 166.4848 | 7.8765 | 172.6837 | 5.5843 | 8.3585 | 7.8765 | 5.5843
|  | 362.8629 | 7.1877 | 152.1055 | 3.0765 | 437.1616 | 3.4954 | 7.1877 | 3.0765 | 3.4954
|  | 362.8629 | 7.1877 | 125.9613 | 1.8765 | 197.5206 | 3.1843 | 7.1877 | 1.8765 | 3.1843
|  | 342.9409 | 12.0166 | 201.7794 | 4.2765 | 277.2604 | 4.3843 | 12.0166 | 4.2765 | 4.3843
|  | 362.8629 | 7.1877 | 180.8641 | 4.4543 | 437.1616 | 3.4954 | 7.1877 | 4.4543 | 3.4954
|  | 391.0856 | 8.3585 | 180.8641 | 4.4543 | 437.1616 | 3.4954 | 8.3585 | 4.4543 | 3.4954
|  | 243.253 | 28.3877 | 125.9613 | 1.8765 | 181.8341 | 7.9843 | 28.3877 | 1.8765 | 7.9843
|  | 449.1913 | 20.4134 | 315.5067 | 7.8765 | 125.6241 | 2.4732 | 20.4134 | 7.8765 | 2.4732
|  | 371.1637 | 8.3585 | 179.5569 | 5.4765 | 249.809 | 11.8797 | 8.3585 | 5.4765 | 11.8797
|  | 666.5945 | 8.3585 | 225.3092 | 11.8797 | 126.9313 | 3.7177 | 8.3585 | 11.8797 | 3.7177
|  | 371.1637 | 8.3585 | 166.4848 | 7.8765 | 143.9251 | 9.4954 | 8.3585 | 7.8765 | 9.4954
|  | 243.253 | 28.3877 | 150.7983 | 9.3876 | 218.436 | 11.8797 | 28.3877 | 9.3876 | 11.8797
|  | 666.5945 | 8.3585 | 225.3092 | 11.8797 | 234.1225 | 6.7843 | 8.3585 | 11.8797 | 6.7843
|  | 362.8629 | 7.1877 | 204.3939 | 3.6098 | 247.1946 | 3.9843 | 7.1877 | 3.6098 | 3.9843
|  | 666.5945 | 8.3585 | 201.7794 | 4.2765 | 145.2323 | 3.1843 | 8.3585 | 4.2765 | 3.1843
|  | 396.0661 | 8.3585 | 204.3939 | 3.0765 | 372.6867 | 7.9843 | 8.3585 | 3.0765 | 7.9843
|  | 449.1913 | 20.4134 | 180.8641 | 4.4543 | 372.6867 | 7.9843 | 20.4134 | 4.4543 | 7.9843
|  | 666.5945 | 8.3585 | 103.8232 | 3.6098 | 197.5206 | 3.7177 | 8.3585 | 3.6098 | 3.7177
|  | 391.0856 | 8.3585 | 166.4848 | 7.8765 | 172.6837 | 11.8797 | 8.3585 | 7.8765 | 11.8797
|  | 342.9409 | 12.0166 | 379.5599 | 7.8765 | 372.6867 | 7.9843 | 12.0166 | 7.8765 | 7.9843
|  | 449.1913 | 20.4134 | 133.8045 | 3.6098 | 278.5676 | 7.9843 | 20.4134 | 3.6098 | 7.9843
|  | 342.9409 | 12.0166 | 240.9957 | 6.6765 | 172.6837 | 11.8797 | 12.0166 | 6.6765 | 11.8797
|  | 342.9409 | 12.0166 | 437.1616 | 3.3876 | 116.4737 | 0.54638 | 12.0166 | 3.3876 | 0.54638
|  | 449.1913 | 20.4134 | 201.7794 | 4.2765 | 173.9909 | 4.5621 | 20.4134 | 4.2765 | 4.5621
|  | 396.0661 | 8.3585 | 179.5569 | 11.8797 | 116.4737 | 0.54638 | 8.3585 | 11.8797 | 0.54638
|  | 342.9409 | 12.0166 | 284.1336 | 4.2765 | 125.6241 | 2.4732 | 12.0166 | 4.2765 | 2.4732
|  | 243.253 | 28.3877 | 315.5067 | 7.8765 | 234.1225 | 6.7843 | 28.3877 | 7.8765 | 6.7843
|  | 391.0856 | 8.3585 | 157.3343 | 10.8987 | 159.6116 | 7.9843 | 8.3585 | 10.8987 | 7.9843
|  | 362.8629 | 7.1877 | 179.5569 | 5.4765 | 181.8341 | 7.9843 | 7.1877 | 5.4765 | 7.9843
|  | 391.0856 | 8.3585 | 152.1055 | 3.0765 | 181.8341 | 7.9843 | 8.3585 | 3.0765 | 7.9843
|  | 500.6564 | 12.9311 | 284.1336 | 4.2765 | 234.1225 | 6.7843 | 12.9311 | 4.2765 | 6.7843
|  | 500.6564 | 12.9311 | 124.6541 | 3.0765 | 197.5206 | 3.7177 | 12.9311 | 3.0765 | 3.7177
|  | 396.0661 | 8.3585 | 240.9957 | 6.6765 | 150.4611 | 11.0066 | 8.3585 | 6.6765 | 11.0066
|  | 362.8629 | 7.1877 | 284.1336 | 4.2765 | 218.436 | 11.8797 | 7.1877 | 4.2765 | 11.8797
|  | 500.6564 | 12.9311 | 256.6822 | 11.8797 | 145.2323 | 3.1843 | 12.9311 | 11.8797 | 3.1843
|  | 500.6564 | 12.9311 | 123.3469 | 0.54638 | 181.8341 | 7.9843 | 12.9311 | 0.54638 | 7.9843
|  | 362.8629 | 7.1877 | 254.0678 | 3.8765 | 116.4737 | 0.54638 | 7.1877 | 3.8765 | 0.54638
|  | 371.1637 | 8.3585 | 179.5569 | 11.8797 | 145.2323 | 3.1843 | 8.3585 | 11.8797 | 3.1843
|  | 666.5945 | 8.3585 | 254.0678 | 3.8765 | 125.6241 | 2.4732 | 8.3585 | 3.8765 | 2.4732
|  | 371.1637 | 8.3585 | 179.5569 | 11.8797 | 372.6867 | 7.9843 | 8.3585 | 11.8797 | 7.9843
|  | 342.9409 | 12.0166 | 152.1055 | 3.0765 | 119.0881 | 1.9843 | 12.0166 | 3.0765 | 1.9843
|  | 500.6564 | 12.9311 | 204.3939 | 3.0765 | 277.2604 | 4.3843 | 12.9311 | 3.0765 | 4.3843
|  | 256.6124 | 9.6056 | 125.9613 | 1.8765 | 372.6867 | 7.9843 | 9.6056 | 1.8765 | 7.9843
|  | 396.0661 | 8.3585 | 179.5569 | 5.4765 | 277.2604 | 4.3843 | 8.3585 | 5.4765 | 4.3843
|  | 342.9409 | 12.0166 | 254.0678 | 3.8765 | 197.5206 | 3.7177 | 12.0166 | 3.8765 | 3.7177
|  | 500.6564 | 12.9311 | 254.0678 | 3.8765 | 143.9251 | 9.4954 | 12.9311 | 3.8765 | 9.4954
|  | 371.1637 | 8.3585 | 133.8045 | 3.6098 | 218.436 | 11.8797 | 8.3585 | 3.6098 | 11.8797
|  | 666.5945 | 8.3585 | 188.7073 | 7.8765 | 150.4611 | 11.0066 | 8.3585 | 7.8765 | 11.0066
|  | 243.253 | 28.3877 | 180.8641 | 4.4543 | 181.8341 | 7.9843 | 28.3877 | 4.4543 | 7.9843
|  | 391.0856 | 8.3585 | 180.8641 | 4.4543 | 194.9062 | 7.9843 | 8.3585 | 4.4543 | 7.9843
|  | 342.9409 | 12.0166 | 133.8045 | 3.6098 | 437.1616 | 3.4954 | 12.0166 | 3.6098 | 3.4954
|  | 371.1637 | 8.3585 | 133.8045 | 3.6098 | 234.1225 | 6.7843 | 8.3585 | 3.6098 | 6.7843
|  | 391.0856 | 8.3585 | 124.6541 | 3.0765 | 156.9972 | 1.9843 | 8.3585 | 3.0765 | 1.9843
|  | 342.9409 | 12.0166 | 204.3939 | 3.6098 | 145.2323 | 3.1843 | 12.0166 | 3.6098 | 3.1843
|  | 500.6564 | 12.9311 | 190.0146 | 8.8543 | 308.6335 | 7.9843 | 12.9311 | 8.8543 | 7.9843
|  | 371.1637 | 8.3585 | 254.0678 | 3.8765 | 278.5676 | 7.9843 | 8.3585 | 3.8765 | 7.9843
|  | 391.0856 | 8.3585 | 240.9957 | 6.6765 | 372.6867 | 7.9843 | 8.3585 | 6.6765 | 7.9843
|  | 500.6564 | 12.9311 | 132.4973 | 2.3654 | 145.2323 | 3.1843 | 12.9311 | 2.3654 | 3.1843
|  | 391.0856 | 8.3585 | 188.7073 | 7.8765 | 278.5676 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 396.0661 | 8.3585 | 166.4848 | 7.8765 | 116.4737 | 0.54638 | 8.3585 | 7.8765 | 0.54638
|  | 342.9409 | 12.0166 | 379.5599 | 7.8765 | 277.2604 | 4.3843 | 12.0166 | 7.8765 | 4.3843
|  | 243.253 | 28.3877 | 163.8704 | 1.8765 | 126.9313 | 3.7177 | 28.3877 | 1.8765 | 3.7177
|  | 666.5945 | 8.3585 | 132.4973 | 2.3654 | 116.4737 | 0.54638 | 8.3585 | 2.3654 | 0.54638
|  | 342.9409 | 12.0166 | 285.4409 | 7.8765 | 172.6837 | 11.8797 | 12.0166 | 7.8765 | 11.8797
|  | 256.6124 | 9.6056 | 180.8641 | 4.4543 | 103.8232 | 3.7177 | 9.6056 | 4.4543 | 3.7177
|  | 449.1913 | 20.4134 | 124.6541 | 3.0765 | 197.5206 | 3.1843 | 20.4134 | 3.0765 | 3.1843
|  | 391.0856 | 8.3585 | 179.5569 | 5.4765 | 159.6116 | 7.9843 | 8.3585 | 5.4765 | 7.9843
|  | 500.6564 | 12.9311 | 152.1055 | 3.0765 | 437.1616 | 3.4954 | 12.9311 | 3.0765 | 3.4954
|  | 391.0856 | 8.3585 | 179.5569 | 5.4765 | 249.809 | 11.8797 | 8.3585 | 5.4765 | 11.8797
|  | 243.253 | 28.3877 | 315.5067 | 7.8765 | 156.9972 | 1.9843 | 28.3877 | 7.8765 | 1.9843
|  | 362.8629 | 7.1877 | 123.3469 | 0.54638 | 150.4611 | 11.0066 | 7.1877 | 0.54638 | 11.0066
|  | 500.6564 | 12.9311 | 284.1336 | 4.2765 | 249.809 | 11.8797 | 12.9311 | 4.2765 | 11.8797
|  | 391.0856 | 8.3585 | 240.9957 | 6.6765 | 372.6867 | 7.9843 | 8.3585 | 6.6765 | 7.9843
|  | 362.8629 | 7.1877 | 240.9957 | 6.6765 | 145.2323 | 3.1843 | 7.1877 | 6.6765 | 3.1843
|  | 371.1637 | 8.3585 | 225.3092 | 11.8797 | 437.1616 | 3.4954 | 8.3585 | 11.8797 | 3.4954
|  | 391.0856 | 8.3585 | 179.5569 | 5.4765 | 181.8341 | 7.9843 | 8.3585 | 5.4765 | 7.9843
|  | 396.0661 | 8.3585 | 179.5569 | 5.4765 | 372.6867 | 7.9843 | 8.3585 | 5.4765 | 7.9843
|  | 371.1637 | 8.3585 | 201.7794 | 4.2765 | 277.2604 | 4.3843 | 8.3585 | 4.2765 | 4.3843
|  | 362.8629 | 7.1877 | 103.8232 | 3.6098 | 173.9909 | 4.5621 | 7.1877 | 3.6098 | 4.5621
|  | 449.1913 | 20.4134 | 240.9957 | 6.6765 | 372.6867 | 7.9843 | 20.4134 | 6.6765 | 7.9843
|  | 666.5945 | 8.3585 | 132.4973 | 2.3654 | 234.1225 | 6.7843 | 8.3585 | 2.3654 | 6.7843
|  | 256.6124 | 9.6056 | 157.3343 | 10.8987 | 159.6116 | 7.9843 | 9.6056 | 10.8987 | 7.9843
|  | 342.9409 | 12.0166 | 157.3343 | 10.8987 | 247.1946 | 3.9843 | 12.0166 | 10.8987 | 3.9843
|  | 449.1913 | 20.4134 | 190.0146 | 8.8543 | 143.9251 | 9.4954 | 20.4134 | 8.8543 | 9.4954
|  | 500.6564 | 12.9311 | 284.1336 | 4.2765 | 159.6116 | 7.9843 | 12.9311 | 4.2765 | 7.9843
|  | 666.5945 | 8.3585 | 133.8045 | 3.6098 | 116.4737 | 0.54638 | 8.3585 | 3.6098 | 0.54638
|  | 449.1913 | 20.4134 | 132.4973 | 2.3654 | 234.1225 | 6.7843 | 20.4134 | 2.3654 | 6.7843
|  | 500.6564 | 12.9311 | 284.1336 | 4.2765 | 194.9062 | 7.9843 | 12.9311 | 4.2765 | 7.9843
|  | 391.0856 | 8.3585 | 437.1616 | 3.3876 | 173.9909 | 4.5621 | 8.3585 | 3.3876 | 4.5621
|  | 342.9409 | 12.0166 | 179.5569 | 11.8797 | 194.9062 | 7.9843 | 12.0166 | 11.8797 | 7.9843
|  | 396.0661 | 8.3585 | 152.1055 | 3.0765 | 247.1946 | 3.9843 | 8.3585 | 3.0765 | 3.9843
|  | 500.6564 | 12.9311 | 190.0146 | 8.8543 | 126.9313 | 3.7177 | 12.9311 | 8.8543 | 3.7177
|  | 391.0856 | 8.3585 | 103.8232 | 3.6098 | 197.5206 | 3.7177 | 8.3585 | 3.6098 | 3.7177
|  | 256.6124 | 9.6056 | 379.5599 | 7.8765 | 183.1413 | 8.9621 | 9.6056 | 7.8765 | 8.9621
|  | 500.6564 | 12.9311 | 166.4848 | 7.8765 | 159.6116 | 7.9843 | 12.9311 | 7.8765 | 7.9843
|  | 500.6564 | 12.9311 | 437.1616 | 3.3876 | 181.8341 | 7.9843 | 12.9311 | 3.3876 | 7.9843
|  | 256.6124 | 9.6056 | 240.9957 | 6.6765 | 234.1225 | 6.7843 | 9.6056 | 6.6765 | 6.7843
|  | 362.8629 | 7.1877 | 204.3939 | 3.0765 | 249.809 | 11.8797 | 7.1877 | 3.0765 | 11.8797
|  | 342.9409 | 12.0166 | 284.1336 | 4.2765 | 234.1225 | 6.7843 | 12.0166 | 4.2765 | 6.7843
|  | 256.6124 | 9.6056 | 315.5067 | 7.8765 | 119.0881 | 1.9843 | 9.6056 | 7.8765 | 1.9843
|  | 371.1637 | 8.3585 | 124.6541 | 3.0765 | 247.1946 | 3.9843 | 8.3585 | 3.0765 | 3.9843
|  | 391.0856 | 8.3585 | 133.8045 | 3.6098 | 172.6837 | 11.8797 | 8.3585 | 3.6098 | 11.8797
|  | 256.6124 | 9.6056 | 166.4848 | 7.8765 | 218.436 | 11.8797 | 9.6056 | 7.8765 | 11.8797
|  | 666.5945 | 8.3585 | 103.8232 | 3.6098 | 437.1616 | 3.4954 | 8.3585 | 3.6098 | 3.4954
|  | 256.6124 | 9.6056 | 225.3092 | 11.8797 | 197.5206 | 3.7177 | 9.6056 | 11.8797 | 3.7177
|  | 362.8629 | 7.1877 | 437.1616 | 3.3876 | 197.5206 | 3.7177 | 7.1877 | 3.3876 | 3.7177
|  | 396.0661 | 8.3585 | 123.3469 | 0.54638 | 218.436 | 11.8797 | 8.3585 | 0.54638 | 11.8797
|  | 396.0661 | 8.3585 | 256.6822 | 11.8797 | 117.7809 | 3.1843 | 8.3585 | 11.8797 | 3.1843
|  | 243.253 | 28.3877 | 150.7983 | 9.3876 | 197.5206 | 3.7177 | 28.3877 | 9.3876 | 3.7177
|  | 256.6124 | 9.6056 | 132.4973 | 2.3654 | 156.9972 | 1.9843 | 9.6056 | 2.3654 | 1.9843
|  | 342.9409 | 12.0166 | 204.3939 | 3.6098 | 103.8232 | 3.7177 | 12.0166 | 3.6098 | 3.7177
|  | 500.6564 | 12.9311 | 150.7983 | 9.3876 | 117.7809 | 3.1843 | 12.9311 | 9.3876 | 3.1843
|  | 449.1913 | 20.4134 | 132.4973 | 2.3654 | 116.4737 | 0.54638 | 20.4134 | 2.3654 | 0.54638
|  | 500.6564 | 12.9311 | 285.4409 | 7.8765 | 156.9972 | 1.9843 | 12.9311 | 7.8765 | 1.9843
|  | 371.1637 | 8.3585 | 157.3343 | 10.8987 | 278.5676 | 7.9843 | 8.3585 | 10.8987 | 7.9843
|  | 362.8629 | 7.1877 | 133.8045 | 3.6098 | 159.6116 | 7.9843 | 7.1877 | 3.6098 | 7.9843
|  | 362.8629 | 7.1877 | 166.4848 | 7.8765 | 119.0881 | 1.9843 | 7.1877 | 7.8765 | 1.9843
|  | 449.1913 | 20.4134 | 188.7073 | 7.8765 | 234.1225 | 6.7843 | 20.4134 | 7.8765 | 6.7843
|  | 449.1913 | 20.4134 | 254.0678 | 3.8765 | 218.436 | 11.8797 | 20.4134 | 3.8765 | 11.8797
|  | 371.1637 | 8.3585 | 133.8045 | 3.6098 | 197.5206 | 3.1843 | 8.3585 | 3.6098 | 3.1843
|  | 396.0661 | 8.3585 | 157.3343 | 10.8987 | 234.1225 | 6.7843 | 8.3585 | 10.8987 | 6.7843
|  | 449.1913 | 20.4134 | 150.7983 | 9.3876 | 103.8232 | 3.7177 | 20.4134 | 9.3876 | 3.7177
|  | 256.6124 | 9.6056 | 201.7794 | 7.8765 | 143.9251 | 9.4954 | 9.6056 | 7.8765 | 9.4954
|  | 371.1637 | 8.3585 | 179.5569 | 5.4765 | 194.9062 | 7.9843 | 8.3585 | 5.4765 | 7.9843
|  | 500.6564 | 12.9311 | 225.3092 | 11.8797 | 218.436 | 11.8797 | 12.9311 | 11.8797 | 11.8797
|  | 449.1913 | 20.4134 | 132.4973 | 2.3654 | 116.4737 | 0.54638 | 20.4134 | 2.3654 | 0.54638
|  | 371.1637 | 8.3585 | 225.3092 | 11.8797 | 117.7809 | 3.1843 | 8.3585 | 11.8797 | 3.1843
|  | 371.1637 | 8.3585 | 152.1055 | 3.0765 | 103.8232 | 3.7177 | 8.3585 | 3.0765 | 3.7177
|  | 500.6564 | 12.9311 | 180.8641 | 4.4543 | 194.9062 | 7.9843 | 12.9311 | 4.4543 | 7.9843
|  | 362.8629 | 7.1877 | 180.8641 | 4.4543 | 172.6837 | 11.8797 | 7.1877 | 4.4543 | 11.8797
|  | 256.6124 | 9.6056 | 284.1336 | 4.2765 | 159.6116 | 7.9843 | 9.6056 | 4.2765 | 7.9843
|  | 371.1637 | 8.3585 | 225.3092 | 11.8797 | 117.7809 | 3.1843 | 8.3585 | 11.8797 | 3.1843
|  | 500.6564 | 12.9311 | 133.8045 | 3.6098 | 126.9313 | 3.7177 | 12.9311 | 3.6098 | 3.7177
|  | 449.1913 | 20.4134 | 254.0678 | 3.8765 | 197.5206 | 3.7177 | 20.4134 | 3.8765 | 3.7177
|  | 666.5945 | 8.3585 | 240.9957 | 6.6765 | 437.1616 | 3.4954 | 8.3585 | 6.6765 | 3.4954
|  | 500.6564 | 12.9311 | 201.7794 | 4.2765 | 172.6837 | 11.8797 | 12.9311 | 4.2765 | 11.8797
|  | 449.1913 | 20.4134 | 132.4973 | 2.3654 | 234.1225 | 6.7843 | 20.4134 | 2.3654 | 6.7843
|  | 342.9409 | 12.0166 | 103.8232 | 3.6098 | 181.8341 | 7.9843 | 12.0166 | 3.6098 | 7.9843
|  | 256.6124 | 9.6056 | 166.4848 | 7.8765 | 437.1616 | 3.4954 | 9.6056 | 7.8765 | 3.4954
|  | 243.253 | 28.3877 | 188.7073 | 7.8765 | 103.8232 | 3.7177 | 28.3877 | 7.8765 | 3.7177
|  | 371.1637 | 8.3585 | 132.4973 | 2.3654 | 234.1225 | 6.7843 | 8.3585 | 2.3654 | 6.7843
|  | 256.6124 | 9.6056 | 285.4409 | 7.8765 | 143.9251 | 9.4954 | 9.6056 | 7.8765 | 9.4954
|  | 449.1913 | 20.4134 | 240.9957 | 6.6765 | 173.9909 | 4.5621 | 20.4134 | 6.6765 | 4.5621
|  | 256.6124 | 9.6056 | 103.8232 | 3.6098 | 181.8341 | 7.9843 | 9.6056 | 3.6098 | 7.9843
|  | 362.8629 | 7.1877 | 180.8641 | 4.4543 | 249.809 | 11.8797 | 7.1877 | 4.4543 | 11.8797
|  | 256.6124 | 9.6056 | 180.8641 | 4.4543 | 372.6867 | 7.9843 | 9.6056 | 4.4543 | 7.9843
|  | 371.1637 | 8.3585 | 204.3939 | 3.0765 | 197.5206 | 3.7177 | 8.3585 | 3.0765 | 3.7177
|  | 396.0661 | 8.3585 | 285.4409 | 7.8765 | 308.6335 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 371.1637 | 8.3585 | 254.0678 | 3.8765 | 277.2604 | 4.3843 | 8.3585 | 3.8765 | 4.3843
|  | 449.1913 | 20.4134 | 133.8045 | 3.6098 | 197.5206 | 3.1843 | 20.4134 | 3.6098 | 3.1843
|  | 362.8629 | 7.1877 | 103.8232 | 3.6098 | 172.6837 | 5.5843 | 7.1877 | 3.6098 | 5.5843
|  | 500.6564 | 12.9311 | 201.7794 | 4.2765 | 249.809 | 11.8797 | 12.9311 | 4.2765 | 11.8797
|  | 396.0661 | 8.3585 | 284.1336 | 4.2765 | 119.0881 | 1.9843 | 8.3585 | 4.2765 | 1.9843
|  | 342.9409 | 12.0166 | 132.4973 | 2.3654 | 172.6837 | 5.5843 | 12.0166 | 2.3654 | 5.5843
|  | 449.1913 | 20.4134 | 166.4848 | 7.8765 | 172.6837 | 11.8797 | 20.4134 | 7.8765 | 11.8797
|  | 500.6564 | 12.9311 | 240.9957 | 6.6765 | 172.6837 | 5.5843 | 12.9311 | 6.6765 | 5.5843
|  | 342.9409 | 12.0166 | 163.8704 | 1.8765 | 194.9062 | 7.9843 | 12.0166 | 1.8765 | 7.9843
|  | 666.5945 | 8.3585 | 163.8704 | 1.8765 | 143.9251 | 9.4954 | 8.3585 | 1.8765 | 9.4954
|  | 342.9409 | 12.0166 | 285.4409 | 7.8765 | 172.6837 | 5.5843 | 12.0166 | 7.8765 | 5.5843
|  | 449.1913 | 20.4134 | 256.6822 | 11.8797 | 194.9062 | 7.9843 | 20.4134 | 11.8797 | 7.9843
|  | 500.6564 | 12.9311 | 152.1055 | 3.0765 | 278.5676 | 7.9843 | 12.9311 | 3.0765 | 7.9843
|  | 371.1637 | 8.3585 | 225.3092 | 11.8797 | 218.436 | 11.8797 | 8.3585 | 11.8797 | 11.8797
|  | 243.253 | 28.3877 | 256.6822 | 11.8797 | 247.1946 | 3.9843 | 28.3877 | 11.8797 | 3.9843
|  | 391.0856 | 8.3585 | 285.4409 | 7.8765 | 183.1413 | 8.9621 | 8.3585 | 7.8765 | 8.9621
|  | 666.5945 | 8.3585 | 157.3343 | 10.8987 | 172.6837 | 5.5843 | 8.3585 | 10.8987 | 5.5843
|  | 396.0661 | 8.3585 | 254.0678 | 3.8765 | 197.5206 | 3.1843 | 8.3585 | 3.8765 | 3.1843
|  | 449.1913 | 20.4134 | 157.3343 | 10.8987 | 277.2604 | 4.3843 | 20.4134 | 10.8987 | 4.3843
|  | 371.1637 | 8.3585 | 225.3092 | 11.8797 | 173.9909 | 4.5621 | 8.3585 | 11.8797 | 4.5621
|  | 396.0661 | 8.3585 | 124.6541 | 3.0765 | 183.1413 | 8.9621 | 8.3585 | 3.0765 | 8.9621
|  | 362.8629 | 7.1877 | 240.9957 | 6.6765 | 234.1225 | 6.7843 | 7.1877 | 6.6765 | 6.7843
|  | 396.0661 | 8.3585 | 201.7794 | 7.8765 | 119.0881 | 1.9843 | 8.3585 | 7.8765 | 1.9843
|  | 256.6124 | 9.6056 | 190.0146 | 8.8543 | 156.9972 | 1.9843 | 9.6056 | 8.8543 | 1.9843
|  | 342.9409 | 12.0166 | 188.7073 | 7.8765 | 197.5206 | 3.7177 | 12.0166 | 7.8765 | 3.7177
|  | 396.0661 | 8.3585 | 437.1616 | 3.3876 | 218.436 | 11.8797 | 8.3585 | 3.3876 | 11.8797
|  | 256.6124 | 9.6056 | 188.7073 | 7.8765 | 197.5206 | 3.7177 | 9.6056 | 7.8765 | 3.7177
|  | 362.8629 | 7.1877 | 225.3092 | 11.8797 | 197.5206 | 3.7177 | 7.1877 | 11.8797 | 3.7177
|  | 243.253 | 28.3877 | 188.7073 | 7.8765 | 197.5206 | 3.1843 | 28.3877 | 7.8765 | 3.1843
|  | 362.8629 | 7.1877 | 285.4409 | 7.8765 | 159.6116 | 7.9843 | 7.1877 | 7.8765 | 7.9843
|  | 243.253 | 28.3877 | 157.3343 | 10.8987 | 278.5676 | 7.9843 | 28.3877 | 10.8987 | 7.9843
|  | 396.0661 | 8.3585 | 437.1616 | 3.3876 | 234.1225 | 6.7843 | 8.3585 | 3.3876 | 6.7843
|  | 666.5945 | 8.3585 | 180.8641 | 4.4543 | 247.1946 | 3.9843 | 8.3585 | 4.4543 | 3.9843
|  | 391.0856 | 8.3585 | 152.1055 | 3.0765 | 172.6837 | 11.8797 | 8.3585 | 3.0765 | 11.8797
|  | 666.5945 | 8.3585 | 201.7794 | 4.2765 | 126.9313 | 3.7177 | 8.3585 | 4.2765 | 3.7177
|  | 243.253 | 28.3877 | 190.0146 | 8.8543 | 277.2604 | 4.3843 | 28.3877 | 8.8543 | 4.3843
|  | 391.0856 | 8.3585 | 379.5599 | 7.8765 | 119.0881 | 1.9843 | 8.3585 | 7.8765 | 1.9843
|  | 371.1637 | 8.3585 | 152.1055 | 3.0765 | 181.8341 | 7.9843 | 8.3585 | 3.0765 | 7.9843
|  | 500.6564 | 12.9311 | 124.6541 | 3.0765 | 172.6837 | 11.8797 | 12.9311 | 3.0765 | 11.8797
|  | 371.1637 | 8.3585 | 315.5067 | 7.8765 | 172.6837 | 11.8797 | 8.3585 | 7.8765 | 11.8797
|  | 243.253 | 28.3877 | 125.9613 | 1.8765 | 145.2323 | 3.1843 | 28.3877 | 1.8765 | 3.1843
|  | 371.1637 | 8.3585 | 123.3469 | 0.54638 | 437.1616 | 3.4954 | 8.3585 | 0.54638 | 3.4954
|  | 371.1637 | 8.3585 | 179.5569 | 11.8797 | 194.9062 | 4.3843 | 8.3585 | 11.8797 | 4.3843
|  | 666.5945 | 8.3585 | 254.0678 | 3.8765 | 172.6837 | 11.8797 | 8.3585 | 3.8765 | 11.8797
|  | 256.6124 | 9.6056 | 180.8641 | 4.4543 | 194.9062 | 4.3843 | 9.6056 | 4.4543 | 4.3843
|  | 362.8629 | 7.1877 | 166.4848 | 7.8765 | 156.9972 | 1.9843 | 7.1877 | 7.8765 | 1.9843
|  | 500.6564 | 12.9311 | 201.7794 | 7.8765 | 234.1225 | 6.7843 | 12.9311 | 7.8765 | 6.7843
|  | 362.8629 | 7.1877 | 190.0146 | 8.8543 | 194.9062 | 7.9843 | 7.1877 | 8.8543 | 7.9843
|  | 362.8629 | 7.1877 | 180.8641 | 4.4543 | 277.2604 | 4.3843 | 7.1877 | 4.4543 | 4.3843
|  | 396.0661 | 8.3585 | 103.8232 | 3.6098 | 194.9062 | 7.9843 | 8.3585 | 3.6098 | 7.9843
|  | 391.0856 | 8.3585 | 379.5599 | 7.8765 | 197.5206 | 3.7177 | 8.3585 | 7.8765 | 3.7177
|  | 371.1637 | 8.3585 | 123.3469 | 0.54638 | 197.5206 | 3.7177 | 8.3585 | 0.54638 | 3.7177
|  | 342.9409 | 12.0166 | 152.1055 | 3.0765 | 103.8232 | 3.7177 | 12.0166 | 3.0765 | 3.7177
|  | 362.8629 | 7.1877 | 201.7794 | 7.8765 | 150.4611 | 11.0066 | 7.1877 | 7.8765 | 11.0066
|  | 362.8629 | 7.1877 | 163.8704 | 1.8765 | 119.0881 | 1.9843 | 7.1877 | 1.8765 | 1.9843
|  | 391.0856 | 8.3585 | 379.5599 | 7.8765 | 372.6867 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 342.9409 | 12.0166 | 379.5599 | 7.8765 | 145.2323 | 3.1843 | 12.0166 | 7.8765 | 3.1843
|  | 391.0856 | 8.3585 | 152.1055 | 3.0765 | 103.8232 | 3.7177 | 8.3585 | 3.0765 | 3.7177
|  | 362.8629 | 7.1877 | 225.3092 | 11.8797 | 308.6335 | 7.9843 | 7.1877 | 11.8797 | 7.9843
|  | 666.5945 | 8.3585 | 204.3939 | 3.0765 | 234.1225 | 6.7843 | 8.3585 | 3.0765 | 6.7843
|  | 500.6564 | 12.9311 | 379.5599 | 7.8765 | 173.9909 | 4.5621 | 12.9311 | 7.8765 | 4.5621
|  | 500.6564 | 12.9311 | 204.3939 | 3.0765 | 197.5206 | 3.1843 | 12.9311 | 3.0765 | 3.1843
|  | 256.6124 | 9.6056 | 204.3939 | 3.6098 | 181.8341 | 7.9843 | 9.6056 | 3.6098 | 7.9843
|  | 391.0856 | 8.3585 | 166.4848 | 7.8765 | 126.9313 | 3.7177 | 8.3585 | 7.8765 | 3.7177
|  | 256.6124 | 9.6056 | 125.9613 | 1.8765 | 173.9909 | 4.5621 | 9.6056 | 1.8765 | 4.5621
|  | 396.0661 | 8.3585 | 163.8704 | 1.8765 | 197.5206 | 3.1843 | 8.3585 | 1.8765 | 3.1843
|  | 371.1637 | 8.3585 | 132.4973 | 2.3654 | 156.9972 | 1.9843 | 8.3585 | 2.3654 | 1.9843
|  | 449.1913 | 20.4134 | 163.8704 | 1.8765 | 150.4611 | 11.0066 | 20.4134 | 1.8765 | 11.0066
|  | 666.5945 | 8.3585 | 204.3939 | 3.6098 | 197.5206 | 3.7177 | 8.3585 | 3.6098 | 3.7177
|  | 371.1637 | 8.3585 | 284.1336 | 4.2765 | 116.4737 | 0.54638 | 8.3585 | 4.2765 | 0.54638
|  | 500.6564 | 12.9311 | 179.5569 | 11.8797 | 308.6335 | 7.9843 | 12.9311 | 11.8797 | 7.9843
|  | 391.0856 | 8.3585 | 123.3469 | 0.54638 | 159.6116 | 7.9843 | 8.3585 | 0.54638 | 7.9843
|  | 449.1913 | 20.4134 | 179.5569 | 11.8797 | 116.4737 | 0.54638 | 20.4134 | 11.8797 | 0.54638
|  | 243.253 | 28.3877 | 133.8045 | 3.6098 | 156.9972 | 1.9843 | 28.3877 | 3.6098 | 1.9843
|  | 500.6564 | 12.9311 | 152.1055 | 3.0765 | 119.0881 | 1.9843 | 12.9311 | 3.0765 | 1.9843
|  | 666.5945 | 8.3585 | 133.8045 | 3.6098 | 249.809 | 11.8797 | 8.3585 | 3.6098 | 11.8797
|  | 666.5945 | 8.3585 | 103.8232 | 3.6098 | 117.7809 | 3.1843 | 8.3585 | 3.6098 | 3.1843
|  | 396.0661 | 8.3585 | 150.7983 | 9.3876 | 249.809 | 11.8797 | 8.3585 | 9.3876 | 11.8797
|  | 396.0661 | 8.3585 | 379.5599 | 7.8765 | 278.5676 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 256.6124 | 9.6056 | 152.1055 | 3.0765 | 194.9062 | 4.3843 | 9.6056 | 3.0765 | 4.3843
|  | 666.5945 | 8.3585 | 284.1336 | 4.2765 | 183.1413 | 8.9621 | 8.3585 | 4.2765 | 8.9621
|  | 500.6564 | 12.9311 | 315.5067 | 7.8765 | 278.5676 | 7.9843 | 12.9311 | 7.8765 | 7.9843
|  | 666.5945 | 8.3585 | 133.8045 | 3.6098 | 249.809 | 11.8797 | 8.3585 | 3.6098 | 11.8797
|  | 396.0661 | 8.3585 | 133.8045 | 3.6098 | 218.436 | 11.8797 | 8.3585 | 3.6098 | 11.8797
|  | 371.1637 | 8.3585 | 179.5569 | 5.4765 | 181.8341 | 7.9843 | 8.3585 | 5.4765 | 7.9843
|  | 243.253 | 28.3877 | 201.7794 | 4.2765 | 172.6837 | 11.8797 | 28.3877 | 4.2765 | 11.8797
|  | 256.6124 | 9.6056 | 124.6541 | 3.0765 | 172.6837 | 11.8797 | 9.6056 | 3.0765 | 11.8797
|  | 371.1637 | 8.3585 | 201.7794 | 7.8765 | 308.6335 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 500.6564 | 12.9311 | 201.7794 | 7.8765 | 126.9313 | 3.7177 | 12.9311 | 7.8765 | 3.7177
|  | 371.1637 | 8.3585 | 163.8704 | 1.8765 | 159.6116 | 7.9843 | 8.3585 | 1.8765 | 7.9843
|  | 449.1913 | 20.4134 | 180.8641 | 4.4543 | 247.1946 | 3.9843 | 20.4134 | 4.4543 | 3.9843
|  | 256.6124 | 9.6056 | 240.9957 | 6.6765 | 116.4737 | 0.54638 | 9.6056 | 6.6765 | 0.54638
|  | 449.1913 | 20.4134 | 204.3939 | 3.6098 | 125.6241 | 2.4732 | 20.4134 | 3.6098 | 2.4732
|  | 500.6564 | 12.9311 | 204.3939 | 3.6098 | 218.436 | 11.8797 | 12.9311 | 3.6098 | 11.8797
|  | 391.0856 | 8.3585 | 103.8232 | 3.6098 | 150.4611 | 11.0066 | 8.3585 | 3.6098 | 11.0066
|  | 243.253 | 28.3877 | 132.4973 | 2.3654 | 145.2323 | 3.1843 | 28.3877 | 2.3654 | 3.1843
|  | 362.8629 | 7.1877 | 379.5599 | 7.8765 | 173.9909 | 4.5621 | 7.1877 | 7.8765 | 4.5621
|  | 449.1913 | 20.4134 | 188.7073 | 7.8765 | 218.436 | 11.8797 | 20.4134 | 7.8765 | 11.8797
|  | 243.253 | 28.3877 | 225.3092 | 11.8797 | 116.4737 | 0.54638 | 28.3877 | 11.8797 | 0.54638
|  | 342.9409 | 12.0166 | 201.7794 | 4.2765 | 308.6335 | 7.9843 | 12.0166 | 4.2765 | 7.9843
|  | 362.8629 | 7.1877 | 284.1336 | 4.2765 | 117.7809 | 3.1843 | 7.1877 | 4.2765 | 3.1843
|  | 362.8629 | 7.1877 | 315.5067 | 7.8765 | 183.1413 | 8.9621 | 7.1877 | 7.8765 | 8.9621
|  | 243.253 | 28.3877 | 315.5067 | 7.8765 | 145.2323 | 3.1843 | 28.3877 | 7.8765 | 3.1843
|  | 396.0661 | 8.3585 | 256.6822 | 11.8797 | 172.6837 | 11.8797 | 8.3585 | 11.8797 | 11.8797
|  | 256.6124 | 9.6056 | 204.3939 | 3.0765 | 125.6241 | 2.4732 | 9.6056 | 3.0765 | 2.4732
|  | 362.8629 | 7.1877 | 179.5569 | 11.8797 | 172.6837 | 11.8797 | 7.1877 | 11.8797 | 11.8797
|  | 371.1637 | 8.3585 | 285.4409 | 7.8765 | 194.9062 | 4.3843 | 8.3585 | 7.8765 | 4.3843
|  | 342.9409 | 12.0166 | 188.7073 | 7.8765 | 125.6241 | 2.4732 | 12.0166 | 7.8765 | 2.4732
|  | 243.253 | 28.3877 | 225.3092 | 11.8797 | 145.2323 | 3.1843 | 28.3877 | 11.8797 | 3.1843
|  | 666.5945 | 8.3585 | 285.4409 | 7.8765 | 247.1946 | 3.9843 | 8.3585 | 7.8765 | 3.9843
|  | 391.0856 | 8.3585 | 180.8641 | 4.4543 | 172.6837 | 11.8797 | 8.3585 | 4.4543 | 11.8797
|  | 666.5945 | 8.3585 | 437.1616 | 3.3876 | 308.6335 | 7.9843 | 8.3585 | 3.3876 | 7.9843
|  | 243.253 | 28.3877 | 225.3092 | 11.8797 | 308.6335 | 7.9843 | 28.3877 | 11.8797 | 7.9843
|  | 371.1637 | 8.3585 | 179.5569 | 11.8797 | 125.6241 | 2.4732 | 8.3585 | 11.8797 | 2.4732
|  | 243.253 | 28.3877 | 379.5599 | 7.8765 | 372.6867 | 7.9843 | 28.3877 | 7.8765 | 7.9843
|  | 256.6124 | 9.6056 | 201.7794 | 4.2765 | 197.5206 | 3.1843 | 9.6056 | 4.2765 | 3.1843
|  | 243.253 | 28.3877 | 379.5599 | 7.8765 | 218.436 | 11.8797 | 28.3877 | 7.8765 | 11.8797
|  | 391.0856 | 8.3585 | 163.8704 | 1.8765 | 145.2323 | 3.1843 | 8.3585 | 1.8765 | 3.1843
|  | 362.8629 | 7.1877 | 204.3939 | 3.0765 | 150.4611 | 11.0066 | 7.1877 | 3.0765 | 11.0066
|  | 342.9409 | 12.0166 | 152.1055 | 3.0765 | 197.5206 | 3.1843 | 12.0166 | 3.0765 | 3.1843
|  | 362.8629 | 7.1877 | 123.3469 | 0.54638 | 277.2604 | 4.3843 | 7.1877 | 0.54638 | 4.3843
|  | 666.5945 | 8.3585 | 166.4848 | 7.8765 | 173.9909 | 4.5621 | 8.3585 | 7.8765 | 4.5621
|  | 342.9409 | 12.0166 | 179.5569 | 5.4765 | 172.6837 | 11.8797 | 12.0166 | 5.4765 | 11.8797
|  | 391.0856 | 8.3585 | 157.3343 | 10.8987 | 249.809 | 11.8797 | 8.3585 | 10.8987 | 11.8797
|  | 362.8629 | 7.1877 | 201.7794 | 4.2765 | 145.2323 | 3.1843 | 7.1877 | 4.2765 | 3.1843
|  | 362.8629 | 7.1877 | 201.7794 | 7.8765 | 145.2323 | 3.1843 | 7.1877 | 7.8765 | 3.1843
|  | 243.253 | 28.3877 | 125.9613 | 1.8765 | 197.5206 | 3.1843 | 28.3877 | 1.8765 | 3.1843
|  | 243.253 | 28.3877 | 150.7983 | 9.3876 | 172.6837 | 11.8797 | 28.3877 | 9.3876 | 11.8797
|  | 342.9409 | 12.0166 | 225.3092 | 11.8797 | 218.436 | 11.8797 | 12.0166 | 11.8797 | 11.8797
|  | 500.6564 | 12.9311 | 315.5067 | 7.8765 | 103.8232 | 3.7177 | 12.9311 | 7.8765 | 3.7177
|  | 666.5945 | 8.3585 | 132.4973 | 2.3654 | 145.2323 | 3.1843 | 8.3585 | 2.3654 | 3.1843
|  | 243.253 | 28.3877 | 133.8045 | 3.6098 | 197.5206 | 3.1843 | 28.3877 | 3.6098 | 3.1843
|  | 391.0856 | 8.3585 | 285.4409 | 7.8765 | 159.6116 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 666.5945 | 8.3585 | 201.7794 | 7.8765 | 278.5676 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 666.5945 | 8.3585 | 163.8704 | 1.8765 | 234.1225 | 6.7843 | 8.3585 | 1.8765 | 6.7843
|  | 391.0856 | 8.3585 | 201.7794 | 4.2765 | 172.6837 | 11.8797 | 8.3585 | 4.2765 | 11.8797
|  | 666.5945 | 8.3585 | 254.0678 | 3.8765 | 278.5676 | 7.9843 | 8.3585 | 3.8765 | 7.9843
|  | 362.8629 | 7.1877 | 240.9957 | 6.6765 | 117.7809 | 3.1843 | 7.1877 | 6.6765 | 3.1843
|  | 449.1913 | 20.4134 | 254.0678 | 3.8765 | 218.436 | 11.8797 | 20.4134 | 3.8765 | 11.8797
|  | 391.0856 | 8.3585 | 379.5599 | 7.8765 | 116.4737 | 0.54638 | 8.3585 | 7.8765 | 0.54638
|  | 391.0856 | 8.3585 | 254.0678 | 3.8765 | 183.1413 | 8.9621 | 8.3585 | 3.8765 | 8.9621
|  | 666.5945 | 8.3585 | 150.7983 | 9.3876 | 197.5206 | 3.1843 | 8.3585 | 9.3876 | 3.1843
|  | 362.8629 | 7.1877 | 150.7983 | 9.3876 | 150.4611 | 11.0066 | 7.1877 | 9.3876 | 11.0066
|  | 243.253 | 28.3877 | 150.7983 | 9.3876 | 116.4737 | 0.54638 | 28.3877 | 9.3876 | 0.54638
|  | 449.1913 | 20.4134 | 179.5569 | 11.8797 | 173.9909 | 4.5621 | 20.4134 | 11.8797 | 4.5621
|  | 391.0856 | 8.3585 | 201.7794 | 7.8765 | 181.8341 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 666.5945 | 8.3585 | 225.3092 | 11.8797 | 119.0881 | 1.9843 | 8.3585 | 11.8797 | 1.9843
|  | 256.6124 | 9.6056 | 125.9613 | 1.8765 | 150.4611 | 11.0066 | 9.6056 | 1.8765 | 11.0066
|  | 362.8629 | 7.1877 | 240.9957 | 6.6765 | 173.9909 | 4.5621 | 7.1877 | 6.6765 | 4.5621
|  | 391.0856 | 8.3585 | 225.3092 | 11.8797 | 218.436 | 11.8797 | 8.3585 | 11.8797 | 11.8797
|  | 362.8629 | 7.1877 | 150.7983 | 9.3876 | 156.9972 | 1.9843 | 7.1877 | 9.3876 | 1.9843
|  | 362.8629 | 7.1877 | 132.4973 | 2.3654 | 194.9062 | 7.9843 | 7.1877 | 2.3654 | 7.9843
|  | 256.6124 | 9.6056 | 123.3469 | 0.54638 | 183.1413 | 8.9621 | 9.6056 | 0.54638 | 8.9621
|  | 243.253 | 28.3877 | 157.3343 | 10.8987 | 249.809 | 11.8797 | 28.3877 | 10.8987 | 11.8797
|  | 371.1637 | 8.3585 | 188.7073 | 7.8765 | 437.1616 | 3.4954 | 8.3585 | 7.8765 | 3.4954
|  | 243.253 | 28.3877 | 103.8232 | 3.6098 | 277.2604 | 4.3843 | 28.3877 | 3.6098 | 4.3843
|  | 666.5945 | 8.3585 | 190.0146 | 8.8543 | 117.7809 | 3.1843 | 8.3585 | 8.8543 | 3.1843
|  | 666.5945 | 8.3585 | 180.8641 | 4.4543 | 172.6837 | 5.5843 | 8.3585 | 4.4543 | 5.5843
|  | 371.1637 | 8.3585 | 166.4848 | 7.8765 | 117.7809 | 3.1843 | 8.3585 | 7.8765 | 3.1843
|  | 666.5945 | 8.3585 | 256.6822 | 11.8797 | 181.8341 | 7.9843 | 8.3585 | 11.8797 | 7.9843
|  | 342.9409 | 12.0166 | 124.6541 | 3.0765 | 197.5206 | 3.7177 | 12.0166 | 3.0765 | 3.7177
|  | 371.1637 | 8.3585 | 132.4973 | 2.3654 | 156.9972 | 1.9843 | 8.3585 | 2.3654 | 1.9843
|  | 666.5945 | 8.3585 | 150.7983 | 9.3876 | 116.4737 | 0.54638 | 8.3585 | 9.3876 | 0.54638
|  | 256.6124 | 9.6056 | 124.6541 | 3.0765 | 117.7809 | 3.1843 | 9.6056 | 3.0765 | 3.1843
|  | 449.1913 | 20.4134 | 379.5599 | 7.8765 | 249.809 | 11.8797 | 20.4134 | 7.8765 | 11.8797
|  | 500.6564 | 12.9311 | 124.6541 | 3.0765 | 156.9972 | 1.9843 | 12.9311 | 3.0765 | 1.9843
|  | 256.6124 | 9.6056 | 179.5569 | 5.4765 | 172.6837 | 11.8797 | 9.6056 | 5.4765 | 11.8797
|  | 243.253 | 28.3877 | 179.5569 | 11.8797 | 116.4737 | 0.54638 | 28.3877 | 11.8797 | 0.54638
|  | 449.1913 | 20.4134 | 179.5569 | 5.4765 | 197.5206 | 3.1843 | 20.4134 | 5.4765 | 3.1843
|  | 342.9409 | 12.0166 | 179.5569 | 5.4765 | 277.2604 | 4.3843 | 12.0166 | 5.4765 | 4.3843
|  | 391.0856 | 8.3585 | 133.8045 | 3.6098 | 172.6837 | 11.8797 | 8.3585 | 3.6098 | 11.8797
|  | 371.1637 | 8.3585 | 284.1336 | 4.2765 | 194.9062 | 7.9843 | 8.3585 | 4.2765 | 7.9843
|  | 396.0661 | 8.3585 | 179.5569 | 11.8797 | 119.0881 | 1.9843 | 8.3585 | 11.8797 | 1.9843
|  | 371.1637 | 8.3585 | 132.4973 | 2.3654 | 218.436 | 11.8797 | 8.3585 | 2.3654 | 11.8797
|  | 396.0661 | 8.3585 | 437.1616 | 3.3876 | 117.7809 | 3.1843 | 8.3585 | 3.3876 | 3.1843
|  | 396.0661 | 8.3585 | 201.7794 | 7.8765 | 372.6867 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 500.6564 | 12.9311 | 285.4409 | 7.8765 | 172.6837 | 11.8797 | 12.9311 | 7.8765 | 11.8797
|  | 371.1637 | 8.3585 | 379.5599 | 7.8765 | 103.8232 | 3.7177 | 8.3585 | 7.8765 | 3.7177
|  | 371.1637 | 8.3585 | 179.5569 | 11.8797 | 372.6867 | 7.9843 | 8.3585 | 11.8797 | 7.9843
|  | 449.1913 | 20.4134 | 179.5569 | 5.4765 | 197.5206 | 3.7177 | 20.4134 | 5.4765 | 3.7177
|  | 500.6564 | 12.9311 | 256.6822 | 11.8797 | 372.6867 | 7.9843 | 12.9311 | 11.8797 | 7.9843
|  | 362.8629 | 7.1877 | 254.0678 | 3.8765 | 437.1616 | 3.4954 | 7.1877 | 3.8765 | 3.4954
|  | 371.1637 | 8.3585 | 166.4848 | 7.8765 | 194.9062 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 666.5945 | 8.3585 | 225.3092 | 11.8797 | 183.1413 | 8.9621 | 8.3585 | 11.8797 | 8.9621
|  | 391.0856 | 8.3585 | 157.3343 | 10.8987 | 145.2323 | 3.1843 | 8.3585 | 10.8987 | 3.1843
|  | 362.8629 | 7.1877 | 125.9613 | 1.8765 | 126.9313 | 3.7177 | 7.1877 | 1.8765 | 3.7177
|  | 256.6124 | 9.6056 | 133.8045 | 3.6098 | 278.5676 | 7.9843 | 9.6056 | 3.6098 | 7.9843
|  | 371.1637 | 8.3585 | 179.5569 | 5.4765 | 372.6867 | 7.9843 | 8.3585 | 5.4765 | 7.9843
|  | 243.253 | 28.3877 | 150.7983 | 9.3876 | 116.4737 | 0.54638 | 28.3877 | 9.3876 | 0.54638
|  | 371.1637 | 8.3585 | 204.3939 | 3.0765 | 103.8232 | 3.7177 | 8.3585 | 3.0765 | 3.7177
|  | 500.6564 | 12.9311 | 284.1336 | 4.2765 | 125.6241 | 2.4732 | 12.9311 | 4.2765 | 2.4732
|  | 362.8629 | 7.1877 | 124.6541 | 3.0765 | 218.436 | 11.8797 | 7.1877 | 3.0765 | 11.8797
|  | 449.1913 | 20.4134 | 256.6822 | 11.8797 | 156.9972 | 1.9843 | 20.4134 | 11.8797 | 1.9843
|  | 500.6564 | 12.9311 | 284.1336 | 4.2765 | 125.6241 | 2.4732 | 12.9311 | 4.2765 | 2.4732
|  | 371.1637 | 8.3585 | 284.1336 | 4.2765 | 150.4611 | 11.0066 | 8.3585 | 4.2765 | 11.0066
|  | 500.6564 | 12.9311 | 204.3939 | 3.0765 | 278.5676 | 7.9843 | 12.9311 | 3.0765 | 7.9843
|  | 449.1913 | 20.4134 | 133.8045 | 3.6098 | 159.6116 | 7.9843 | 20.4134 | 3.6098 | 7.9843
|  | 256.6124 | 9.6056 | 124.6541 | 3.0765 | 194.9062 | 4.3843 | 9.6056 | 3.0765 | 4.3843
|  | 243.253 | 28.3877 | 285.4409 | 7.8765 | 143.9251 | 9.4954 | 28.3877 | 7.8765 | 9.4954
|  | 391.0856 | 8.3585 | 125.9613 | 1.8765 | 181.8341 | 7.9843 | 8.3585 | 1.8765 | 7.9843
|  | 396.0661 | 8.3585 | 150.7983 | 9.3876 | 156.9972 | 1.9843 | 8.3585 | 9.3876 | 1.9843
|  | 362.8629 | 7.1877 | 179.5569 | 11.8797 | 194.9062 | 4.3843 | 7.1877 | 11.8797 | 4.3843
|  | 500.6564 | 12.9311 | 179.5569 | 5.4765 | 150.4611 | 11.0066 | 12.9311 | 5.4765 | 11.0066
|  | 371.1637 | 8.3585 | 132.4973 | 2.3654 | 119.0881 | 1.9843 | 8.3585 | 2.3654 | 1.9843
|  | 449.1913 | 20.4134 | 204.3939 | 3.0765 | 145.2323 | 3.1843 | 20.4134 | 3.0765 | 3.1843
|  | 342.9409 | 12.0166 | 437.1616 | 3.3876 | 183.1413 | 8.9621 | 12.0166 | 3.3876 | 8.9621
|  | 243.253 | 28.3877 | 254.0678 | 3.8765 | 437.1616 | 3.4954 | 28.3877 | 3.8765 | 3.4954
|  | 500.6564 | 12.9311 | 225.3092 | 11.8797 | 116.4737 | 0.54638 | 12.9311 | 11.8797 | 0.54638
|  | 342.9409 | 12.0166 | 315.5067 | 7.8765 | 172.6837 | 11.8797 | 12.0166 | 7.8765 | 11.8797
|  | 666.5945 | 8.3585 | 163.8704 | 1.8765 | 181.8341 | 7.9843 | 8.3585 | 1.8765 | 7.9843
|  | 500.6564 | 12.9311 | 190.0146 | 8.8543 | 277.2604 | 4.3843 | 12.9311 | 8.8543 | 4.3843
|  | 256.6124 | 9.6056 | 379.5599 | 7.8765 | 173.9909 | 4.5621 | 9.6056 | 7.8765 | 4.5621
|  | 391.0856 | 8.3585 | 103.8232 | 3.6098 | 437.1616 | 3.4954 | 8.3585 | 3.6098 | 3.4954
|  | 342.9409 | 12.0166 | 201.7794 | 4.2765 | 218.436 | 11.8797 | 12.0166 | 4.2765 | 11.8797
|  | 396.0661 | 8.3585 | 284.1336 | 4.2765 | 172.6837 | 5.5843 | 8.3585 | 4.2765 | 5.5843
|  | 500.6564 | 12.9311 | 256.6822 | 11.8797 | 172.6837 | 11.8797 | 12.9311 | 11.8797 | 11.8797
|  | 666.5945 | 8.3585 | 437.1616 | 3.3876 | 278.5676 | 7.9843 | 8.3585 | 3.3876 | 7.9843
|  | 666.5945 | 8.3585 | 133.8045 | 3.6098 | 125.6241 | 2.4732 | 8.3585 | 3.6098 | 2.4732
|  | 371.1637 | 8.3585 | 188.7073 | 7.8765 | 308.6335 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 391.0856 | 8.3585 | 163.8704 | 1.8765 | 249.809 | 11.8797 | 8.3585 | 1.8765 | 11.8797
|  | 243.253 | 28.3877 | 150.7983 | 9.3876 | 218.436 | 11.8797 | 28.3877 | 9.3876 | 11.8797
|  | 449.1913 | 20.4134 | 150.7983 | 9.3876 | 277.2604 | 4.3843 | 20.4134 | 9.3876 | 4.3843
|  | 371.1637 | 8.3585 | 150.7983 | 9.3876 | 143.9251 | 9.4954 | 8.3585 | 9.3876 | 9.4954
|  | 362.8629 | 7.1877 | 179.5569 | 11.8797 | 125.6241 | 2.4732 | 7.1877 | 11.8797 | 2.4732
|  | 342.9409 | 12.0166 | 225.3092 | 11.8797 | 150.4611 | 11.0066 | 12.0166 | 11.8797 | 11.0066
|  | 391.0856 | 8.3585 | 124.6541 | 3.0765 | 172.6837 | 5.5843 | 8.3585 | 3.0765 | 5.5843
|  | 666.5945 | 8.3585 | 201.7794 | 7.8765 | 308.6335 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 449.1913 | 20.4134 | 201.7794 | 4.2765 | 150.4611 | 11.0066 | 20.4134 | 4.2765 | 11.0066
|  | 243.253 | 28.3877 | 254.0678 | 3.8765 | 277.2604 | 4.3843 | 28.3877 | 3.8765 | 4.3843
|  | 396.0661 | 8.3585 | 150.7983 | 9.3876 | 247.1946 | 3.9843 | 8.3585 | 9.3876 | 3.9843
|  | 362.8629 | 7.1877 | 157.3343 | 10.8987 | 181.8341 | 7.9843 | 7.1877 | 10.8987 | 7.9843
|  | 362.8629 | 7.1877 | 103.8232 | 3.6098 | 234.1225 | 6.7843 | 7.1877 | 3.6098 | 6.7843
|  | 342.9409 | 12.0166 | 240.9957 | 6.6765 | 150.4611 | 11.0066 | 12.0166 | 6.6765 | 11.0066
|  | 243.253 | 28.3877 | 103.8232 | 3.6098 | 194.9062 | 7.9843 | 28.3877 | 3.6098 | 7.9843
|  | 449.1913 | 20.4134 | 256.6822 | 11.8797 | 159.6116 | 7.9843 | 20.4134 | 11.8797 | 7.9843
|  | 243.253 | 28.3877 | 437.1616 | 3.3876 | 156.9972 | 1.9843 | 28.3877 | 3.3876 | 1.9843
|  | 391.0856 | 8.3585 | 133.8045 | 3.6098 | 159.6116 | 7.9843 | 8.3585 | 3.6098 | 7.9843
|  | 342.9409 | 12.0166 | 150.7983 | 9.3876 | 181.8341 | 7.9843 | 12.0166 | 9.3876 | 7.9843
|  | 342.9409 | 12.0166 | 180.8641 | 4.4543 | 143.9251 | 9.4954 | 12.0166 | 4.4543 | 9.4954
|  | 666.5945 | 8.3585 | 123.3469 | 0.54638 | 194.9062 | 4.3843 | 8.3585 | 0.54638 | 4.3843
|  | 396.0661 | 8.3585 | 240.9957 | 6.6765 | 437.1616 | 3.4954 | 8.3585 | 6.6765 | 3.4954
|  | 243.253 | 28.3877 | 179.5569 | 11.8797 | 218.436 | 11.8797 | 28.3877 | 11.8797 | 11.8797
|  | 666.5945 | 8.3585 | 124.6541 | 3.0765 | 437.1616 | 3.4954 | 8.3585 | 3.0765 | 3.4954
|  | 391.0856 | 8.3585 | 152.1055 | 3.0765 | 249.809 | 11.8797 | 8.3585 | 3.0765 | 11.8797
|  | 362.8629 | 7.1877 | 201.7794 | 7.8765 | 159.6116 | 7.9843 | 7.1877 | 7.8765 | 7.9843
|  | 396.0661 | 8.3585 | 201.7794 | 7.8765 | 103.8232 | 3.7177 | 8.3585 | 7.8765 | 3.7177
|  | 391.0856 | 8.3585 | 132.4973 | 2.3654 | 372.6867 | 7.9843 | 8.3585 | 2.3654 | 7.9843
|  | 666.5945 | 8.3585 | 315.5067 | 7.8765 | 278.5676 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 256.6124 | 9.6056 | 152.1055 | 3.0765 | 126.9313 | 3.7177 | 9.6056 | 3.0765 | 3.7177
|  | 256.6124 | 9.6056 | 254.0678 | 3.8765 | 308.6335 | 7.9843 | 9.6056 | 3.8765 | 7.9843
|  | 500.6564 | 12.9311 | 132.4973 | 2.3654 | 249.809 | 11.8797 | 12.9311 | 2.3654 | 11.8797
|  | 256.6124 | 9.6056 | 225.3092 | 11.8797 | 172.6837 | 11.8797 | 9.6056 | 11.8797 | 11.8797
|  | 342.9409 | 12.0166 | 152.1055 | 3.0765 | 172.6837 | 5.5843 | 12.0166 | 3.0765 | 5.5843
|  | 342.9409 | 12.0166 | 157.3343 | 10.8987 | 194.9062 | 4.3843 | 12.0166 | 10.8987 | 4.3843
|  | 391.0856 | 8.3585 | 204.3939 | 3.6098 | 150.4611 | 11.0066 | 8.3585 | 3.6098 | 11.0066
|  | 449.1913 | 20.4134 | 125.9613 | 1.8765 | 103.8232 | 3.7177 | 20.4134 | 1.8765 | 3.7177
|  | 449.1913 | 20.4134 | 204.3939 | 3.0765 | 197.5206 | 3.7177 | 20.4134 | 3.0765 | 3.7177
|  | 342.9409 | 12.0166 | 256.6822 | 11.8797 | 116.4737 | 0.54638 | 12.0166 | 11.8797 | 0.54638
|  | 449.1913 | 20.4134 | 103.8232 | 3.6098 | 197.5206 | 3.7177 | 20.4134 | 3.6098 | 3.7177
|  | 256.6124 | 9.6056 | 133.8045 | 3.6098 | 437.1616 | 3.4954 | 9.6056 | 3.6098 | 3.4954
|  | 449.1913 | 20.4134 | 201.7794 | 4.2765 | 125.6241 | 2.4732 | 20.4134 | 4.2765 | 2.4732
|  | 500.6564 | 12.9311 | 188.7073 | 7.8765 | 126.9313 | 3.7177 | 12.9311 | 7.8765 | 3.7177
|  | 362.8629 | 7.1877 | 133.8045 | 3.6098 | 247.1946 | 3.9843 | 7.1877 | 3.6098 | 3.9843
|  | 396.0661 | 8.3585 | 152.1055 | 3.0765 | 247.1946 | 3.9843 | 8.3585 | 3.0765 | 3.9843
|  | 243.253 | 28.3877 | 437.1616 | 3.3876 | 234.1225 | 6.7843 | 28.3877 | 3.3876 | 6.7843
|  | 449.1913 | 20.4134 | 201.7794 | 7.8765 | 156.9972 | 1.9843 | 20.4134 | 7.8765 | 1.9843
|  | 362.8629 | 7.1877 | 166.4848 | 7.8765 | 372.6867 | 7.9843 | 7.1877 | 7.8765 | 7.9843
|  | 396.0661 | 8.3585 | 315.5067 | 7.8765 | 116.4737 | 0.54638 | 8.3585 | 7.8765 | 0.54638
|  | 391.0856 | 8.3585 | 179.5569 | 5.4765 | 437.1616 | 3.4954 | 8.3585 | 5.4765 | 3.4954
|  | 666.5945 | 8.3585 | 166.4848 | 7.8765 | 116.4737 | 0.54638 | 8.3585 | 7.8765 | 0.54638
|  | 449.1913 | 20.4134 | 103.8232 | 3.6098 | 117.7809 | 3.1843 | 20.4134 | 3.6098 | 3.1843
|  | 396.0661 | 8.3585 | 225.3092 | 11.8797 | 218.436 | 11.8797 | 8.3585 | 11.8797 | 11.8797
|  | 371.1637 | 8.3585 | 315.5067 | 7.8765 | 247.1946 | 3.9843 | 8.3585 | 7.8765 | 3.9843
|  | 396.0661 | 8.3585 | 123.3469 | 0.54638 | 218.436 | 11.8797 | 8.3585 | 0.54638 | 11.8797
|  | 449.1913 | 20.4134 | 240.9957 | 6.6765 | 143.9251 | 9.4954 | 20.4134 | 6.6765 | 9.4954
|  | 342.9409 | 12.0166 | 103.8232 | 3.6098 | 197.5206 | 3.1843 | 12.0166 | 3.6098 | 3.1843
|  | 396.0661 | 8.3585 | 150.7983 | 9.3876 | 159.6116 | 7.9843 | 8.3585 | 9.3876 | 7.9843
|  | 362.8629 | 7.1877 | 163.8704 | 1.8765 | 234.1225 | 6.7843 | 7.1877 | 1.8765 | 6.7843
|  | 362.8629 | 7.1877 | 157.3343 | 10.8987 | 437.1616 | 3.4954 | 7.1877 | 10.8987 | 3.4954
|  | 500.6564 | 12.9311 | 163.8704 | 1.8765 | 172.6837 | 5.5843 | 12.9311 | 1.8765 | 5.5843
|  | 500.6564 | 12.9311 | 204.3939 | 3.6098 | 234.1225 | 6.7843 | 12.9311 | 3.6098 | 6.7843
|  | 500.6564 | 12.9311 | 225.3092 | 11.8797 | 194.9062 | 7.9843 | 12.9311 | 11.8797 | 7.9843
|  | 371.1637 | 8.3585 | 240.9957 | 6.6765 | 247.1946 | 3.9843 | 8.3585 | 6.6765 | 3.9843
|  | 449.1913 | 20.4134 | 163.8704 | 1.8765 | 277.2604 | 4.3843 | 20.4134 | 1.8765 | 4.3843
|  | 371.1637 | 8.3585 | 125.9613 | 1.8765 | 116.4737 | 0.54638 | 8.3585 | 1.8765 | 0.54638
|  | 371.1637 | 8.3585 | 240.9957 | 6.6765 | 172.6837 | 11.8797 | 8.3585 | 6.6765 | 11.8797
|  | 243.253 | 28.3877 | 163.8704 | 1.8765 | 156.9972 | 1.9843 | 28.3877 | 1.8765 | 1.9843
|  | 362.8629 | 7.1877 | 132.4973 | 2.3654 | 194.9062 | 4.3843 | 7.1877 | 2.3654 | 4.3843
|  | 243.253 | 28.3877 | 152.1055 | 3.0765 | 143.9251 | 9.4954 | 28.3877 | 3.0765 | 9.4954
|  | 342.9409 | 12.0166 | 240.9957 | 6.6765 | 156.9972 | 1.9843 | 12.0166 | 6.6765 | 1.9843
|  | 666.5945 | 8.3585 | 256.6822 | 11.8797 | 150.4611 | 11.0066 | 8.3585 | 11.8797 | 11.0066
|  | 256.6124 | 9.6056 | 179.5569 | 5.4765 | 181.8341 | 7.9843 | 9.6056 | 5.4765 | 7.9843
|  | 500.6564 | 12.9311 | 240.9957 | 6.6765 | 172.6837 | 5.5843 | 12.9311 | 6.6765 | 5.5843
|  | 449.1913 | 20.4134 | 201.7794 | 7.8765 | 197.5206 | 3.7177 | 20.4134 | 7.8765 | 3.7177
|  | 396.0661 | 8.3585 | 125.9613 | 1.8765 | 278.5676 | 7.9843 | 8.3585 | 1.8765 | 7.9843
|  | 500.6564 | 12.9311 | 204.3939 | 3.0765 | 372.6867 | 7.9843 | 12.9311 | 3.0765 | 7.9843
|  | 256.6124 | 9.6056 | 125.9613 | 1.8765 | 249.809 | 11.8797 | 9.6056 | 1.8765 | 11.8797
|  | 362.8629 | 7.1877 | 284.1336 | 4.2765 | 172.6837 | 5.5843 | 7.1877 | 4.2765 | 5.5843
|  | 391.0856 | 8.3585 | 125.9613 | 1.8765 | 437.1616 | 3.4954 | 8.3585 | 1.8765 | 3.4954
|  | 371.1637 | 8.3585 | 190.0146 | 8.8543 | 197.5206 | 3.7177 | 8.3585 | 8.8543 | 3.7177
|  | 362.8629 | 7.1877 | 179.5569 | 5.4765 | 278.5676 | 7.9843 | 7.1877 | 5.4765 | 7.9843
|  | 500.6564 | 12.9311 | 125.9613 | 1.8765 | 247.1946 | 3.9843 | 12.9311 | 1.8765 | 3.9843
|  | 391.0856 | 8.3585 | 188.7073 | 7.8765 | 277.2604 | 4.3843 | 8.3585 | 7.8765 | 4.3843
|  | 342.9409 | 12.0166 | 179.5569 | 11.8797 | 197.5206 | 3.1843 | 12.0166 | 11.8797 | 3.1843
|  | 500.6564 | 12.9311 | 103.8232 | 3.6098 | 150.4611 | 11.0066 | 12.9311 | 3.6098 | 11.0066
|  | 666.5945 | 8.3585 | 124.6541 | 3.0765 | 181.8341 | 7.9843 | 8.3585 | 3.0765 | 7.9843
|  | 396.0661 | 8.3585 | 204.3939 | 3.0765 | 194.9062 | 7.9843 | 8.3585 | 3.0765 | 7.9843
|  | 396.0661 | 8.3585 | 201.7794 | 7.8765 | 126.9313 | 3.7177 | 8.3585 | 7.8765 | 3.7177
|  | 371.1637 | 8.3585 | 157.3343 | 10.8987 | 172.6837 | 5.5843 | 8.3585 | 10.8987 | 5.5843
|  | 362.8629 | 7.1877 | 103.8232 | 3.6098 | 119.0881 | 1.9843 | 7.1877 | 3.6098 | 1.9843
|  | 500.6564 | 12.9311 | 437.1616 | 3.3876 | 116.4737 | 0.54638 | 12.9311 | 3.3876 | 0.54638
|  | 449.1913 | 20.4134 | 315.5067 | 7.8765 | 437.1616 | 3.4954 | 20.4134 | 7.8765 | 3.4954
|  | 396.0661 | 8.3585 | 254.0678 | 3.8765 | 172.6837 | 5.5843 | 8.3585 | 3.8765 | 5.5843
|  | 449.1913 | 20.4134 | 201.7794 | 4.2765 | 172.6837 | 5.5843 | 20.4134 | 4.2765 | 5.5843
|  | 396.0661 | 8.3585 | 179.5569 | 5.4765 | 197.5206 | 3.7177 | 8.3585 | 5.4765 | 3.7177
|  | 362.8629 | 7.1877 | 163.8704 | 1.8765 | 173.9909 | 4.5621 | 7.1877 | 1.8765 | 4.5621
|  | 362.8629 | 7.1877 | 204.3939 | 3.6098 | 145.2323 | 3.1843 | 7.1877 | 3.6098 | 3.1843
|  | 391.0856 | 8.3585 | 179.5569 | 11.8797 | 277.2604 | 4.3843 | 8.3585 | 11.8797 | 4.3843
|  | 666.5945 | 8.3585 | 204.3939 | 3.0765 | 103.8232 | 3.7177 | 8.3585 | 3.0765 | 3.7177
|  | 666.5945 | 8.3585 | 157.3343 | 10.8987 | 173.9909 | 4.5621 | 8.3585 | 10.8987 | 4.5621
|  | 342.9409 | 12.0166 | 437.1616 | 3.3876 | 277.2604 | 4.3843 | 12.0166 | 3.3876 | 4.3843
|  | 256.6124 | 9.6056 | 204.3939 | 3.6098 | 249.809 | 11.8797 | 9.6056 | 3.6098 | 11.8797
|  | 396.0661 | 8.3585 | 179.5569 | 5.4765 | 277.2604 | 4.3843 | 8.3585 | 5.4765 | 4.3843
|  | 396.0661 | 8.3585 | 256.6822 | 11.8797 | 308.6335 | 7.9843 | 8.3585 | 11.8797 | 7.9843
|  | 371.1637 | 8.3585 | 132.4973 | 2.3654 | 372.6867 | 7.9843 | 8.3585 | 2.3654 | 7.9843
|  | 371.1637 | 8.3585 | 256.6822 | 11.8797 | 145.2323 | 3.1843 | 8.3585 | 11.8797 | 3.1843
|  | 342.9409 | 12.0166 | 284.1336 | 4.2765 | 437.1616 | 3.4954 | 12.0166 | 4.2765 | 3.4954
|  | 396.0661 | 8.3585 | 240.9957 | 6.6765 | 437.1616 | 3.4954 | 8.3585 | 6.6765 | 3.4954
|  | 396.0661 | 8.3585 | 254.0678 | 3.8765 | 277.2604 | 4.3843 | 8.3585 | 3.8765 | 4.3843
|  | 396.0661 | 8.3585 | 204.3939 | 3.0765 | 308.6335 | 7.9843 | 8.3585 | 3.0765 | 7.9843
|  | 256.6124 | 9.6056 | 201.7794 | 7.8765 | 247.1946 | 3.9843 | 9.6056 | 7.8765 | 3.9843
|  | 391.0856 | 8.3585 | 190.0146 | 8.8543 | 197.5206 | 3.7177 | 8.3585 | 8.8543 | 3.7177
|  | 391.0856 | 8.3585 | 190.0146 | 8.8543 | 197.5206 | 3.7177 | 8.3585 | 8.8543 | 3.7177
|  | 449.1913 | 20.4134 | 315.5067 | 7.8765 | 117.7809 | 3.1843 | 20.4134 | 7.8765 | 3.1843
|  | 666.5945 | 8.3585 | 204.3939 | 3.6098 | 197.5206 | 3.1843 | 8.3585 | 3.6098 | 3.1843
|  | 391.0856 | 8.3585 | 163.8704 | 1.8765 | 103.8232 | 3.7177 | 8.3585 | 1.8765 | 3.7177
|  | 449.1913 | 20.4134 | 437.1616 | 3.3876 | 197.5206 | 3.7177 | 20.4134 | 3.3876 | 3.7177
|  | 391.0856 | 8.3585 | 285.4409 | 7.8765 | 277.2604 | 4.3843 | 8.3585 | 7.8765 | 4.3843
|  | 243.253 | 28.3877 | 240.9957 | 6.6765 | 278.5676 | 7.9843 | 28.3877 | 6.6765 | 7.9843
|  | 500.6564 | 12.9311 | 201.7794 | 7.8765 | 197.5206 | 3.7177 | 12.9311 | 7.8765 | 3.7177
|  | 391.0856 | 8.3585 | 166.4848 | 7.8765 | 197.5206 | 3.1843 | 8.3585 | 7.8765 | 3.1843
|  | 449.1913 | 20.4134 | 204.3939 | 3.6098 | 172.6837 | 11.8797 | 20.4134 | 3.6098 | 11.8797
|  | 449.1913 | 20.4134 | 190.0146 | 8.8543 | 143.9251 | 9.4954 | 20.4134 | 8.8543 | 9.4954
|  | 391.0856 | 8.3585 | 315.5067 | 7.8765 | 197.5206 | 3.7177 | 8.3585 | 7.8765 | 3.7177
|  | 243.253 | 28.3877 | 163.8704 | 1.8765 | 194.9062 | 4.3843 | 28.3877 | 1.8765 | 4.3843
|  | 362.8629 | 7.1877 | 180.8641 | 4.4543 | 181.8341 | 7.9843 | 7.1877 | 4.4543 | 7.9843
|  | 396.0661 | 8.3585 | 379.5599 | 7.8765 | 218.436 | 11.8797 | 8.3585 | 7.8765 | 11.8797
|  | 371.1637 | 8.3585 | 152.1055 | 3.0765 | 234.1225 | 6.7843 | 8.3585 | 3.0765 | 6.7843
|  | 371.1637 | 8.3585 | 180.8641 | 4.4543 | 181.8341 | 7.9843 | 8.3585 | 4.4543 | 7.9843
|  | 666.5945 | 8.3585 | 179.5569 | 5.4765 | 278.5676 | 7.9843 | 8.3585 | 5.4765 | 7.9843
|  | 449.1913 | 20.4134 | 180.8641 | 4.4543 | 156.9972 | 1.9843 | 20.4134 | 4.4543 | 1.9843
|  | 371.1637 | 8.3585 | 179.5569 | 11.8797 | 181.8341 | 7.9843 | 8.3585 | 11.8797 | 7.9843
|  | 391.0856 | 8.3585 | 123.3469 | 0.54638 | 234.1225 | 6.7843 | 8.3585 | 0.54638 | 6.7843
|  | 362.8629 | 7.1877 | 201.7794 | 7.8765 | 116.4737 | 0.54638 | 7.1877 | 7.8765 | 0.54638
|  | 371.1637 | 8.3585 | 201.7794 | 7.8765 | 156.9972 | 1.9843 | 8.3585 | 7.8765 | 1.9843
|  | 666.5945 | 8.3585 | 190.0146 | 8.8543 | 277.2604 | 4.3843 | 8.3585 | 8.8543 | 4.3843
|  | 362.8629 | 7.1877 | 133.8045 | 3.6098 | 234.1225 | 6.7843 | 7.1877 | 3.6098 | 6.7843
|  | 342.9409 | 12.0166 | 150.7983 | 9.3876 | 145.2323 | 3.1843 | 12.0166 | 9.3876 | 3.1843
|  | 396.0661 | 8.3585 | 225.3092 | 11.8797 | 159.6116 | 7.9843 | 8.3585 | 11.8797 | 7.9843
|  | 391.0856 | 8.3585 | 256.6822 | 11.8797 | 249.809 | 11.8797 | 8.3585 | 11.8797 | 11.8797
|  | 396.0661 | 8.3585 | 225.3092 | 11.8797 | 234.1225 | 6.7843 | 8.3585 | 11.8797 | 6.7843
|  | 243.253 | 28.3877 | 201.7794 | 7.8765 | 437.1616 | 3.4954 | 28.3877 | 7.8765 | 3.4954
|  | 500.6564 | 12.9311 | 124.6541 | 3.0765 | 172.6837 | 5.5843 | 12.9311 | 3.0765 | 5.5843
|  | 342.9409 | 12.0166 | 166.4848 | 7.8765 | 234.1225 | 6.7843 | 12.0166 | 7.8765 | 6.7843
|  | 362.8629 | 7.1877 | 204.3939 | 3.0765 | 159.6116 | 7.9843 | 7.1877 | 3.0765 | 7.9843
|  | 500.6564 | 12.9311 | 240.9957 | 6.6765 | 150.4611 | 11.0066 | 12.9311 | 6.6765 | 11.0066
|  | 342.9409 | 12.0166 | 179.5569 | 11.8797 | 308.6335 | 7.9843 | 12.0166 | 11.8797 | 7.9843
|  | 500.6564 | 12.9311 | 240.9957 | 6.6765 | 308.6335 | 7.9843 | 12.9311 | 6.6765 | 7.9843
|  | 371.1637 | 8.3585 | 179.5569 | 11.8797 | 159.6116 | 7.9843 | 8.3585 | 11.8797 | 7.9843
|  | 500.6564 | 12.9311 | 240.9957 | 6.6765 | 277.2604 | 4.3843 | 12.9311 | 6.6765 | 4.3843
|  | 391.0856 | 8.3585 | 188.7073 | 7.8765 | 197.5206 | 3.7177 | 8.3585 | 7.8765 | 3.7177
|  | 391.0856 | 8.3585 | 133.8045 | 3.6098 | 277.2604 | 4.3843 | 8.3585 | 3.6098 | 4.3843
|  | 391.0856 | 8.3585 | 201.7794 | 4.2765 | 247.1946 | 3.9843 | 8.3585 | 4.2765 | 3.9843
|  | 256.6124 | 9.6056 | 179.5569 | 11.8797 | 247.1946 | 3.9843 | 9.6056 | 11.8797 | 3.9843
|  | 449.1913 | 20.4134 | 201.7794 | 7.8765 | 173.9909 | 4.5621 | 20.4134 | 7.8765 | 4.5621
|  | 500.6564 | 12.9311 | 132.4973 | 2.3654 | 194.9062 | 7.9843 | 12.9311 | 2.3654 | 7.9843
|  | 342.9409 | 12.0166 | 157.3343 | 10.8987 | 143.9251 | 9.4954 | 12.0166 | 10.8987 | 9.4954
|  | 396.0661 | 8.3585 | 179.5569 | 11.8797 | 181.8341 | 7.9843 | 8.3585 | 11.8797 | 7.9843
|  | 500.6564 | 12.9311 | 188.7073 | 7.8765 | 277.2604 | 4.3843 | 12.9311 | 7.8765 | 4.3843
|  | 256.6124 | 9.6056 | 284.1336 | 4.2765 | 194.9062 | 4.3843 | 9.6056 | 4.2765 | 4.3843
|  | 666.5945 | 8.3585 | 315.5067 | 7.8765 | 234.1225 | 6.7843 | 8.3585 | 7.8765 | 6.7843
|  | 243.253 | 28.3877 | 163.8704 | 1.8765 | 116.4737 | 0.54638 | 28.3877 | 1.8765 | 0.54638
|  | 243.253 | 28.3877 | 179.5569 | 5.4765 | 234.1225 | 6.7843 | 28.3877 | 5.4765 | 6.7843
|  | 256.6124 | 9.6056 | 123.3469 | 0.54638 | 437.1616 | 3.4954 | 9.6056 | 0.54638 | 3.4954
|  | 391.0856 | 8.3585 | 179.5569 | 5.4765 | 150.4611 | 11.0066 | 8.3585 | 5.4765 | 11.0066
|  | 396.0661 | 8.3585 | 166.4848 | 7.8765 | 437.1616 | 3.4954 | 8.3585 | 7.8765 | 3.4954
|  | 391.0856 | 8.3585 | 179.5569 | 11.8797 | 156.9972 | 1.9843 | 8.3585 | 11.8797 | 1.9843
|  | 362.8629 | 7.1877 | 315.5067 | 7.8765 | 119.0881 | 1.9843 | 7.1877 | 7.8765 | 1.9843
|  | 362.8629 | 7.1877 | 179.5569 | 5.4765 | 125.6241 | 2.4732 | 7.1877 | 5.4765 | 2.4732
|  | 666.5945 | 8.3585 | 254.0678 | 3.8765 | 172.6837 | 11.8797 | 8.3585 | 3.8765 | 11.8797
|  | 256.6124 | 9.6056 | 179.5569 | 11.8797 | 197.5206 | 3.7177 | 9.6056 | 11.8797 | 3.7177
|  | 342.9409 | 12.0166 | 204.3939 | 3.6098 | 194.9062 | 4.3843 | 12.0166 | 3.6098 | 4.3843
|  | 342.9409 | 12.0166 | 150.7983 | 9.3876 | 172.6837 | 5.5843 | 12.0166 | 9.3876 | 5.5843
|  | 391.0856 | 8.3585 | 123.3469 | 0.54638 | 159.6116 | 7.9843 | 8.3585 | 0.54638 | 7.9843
|  | 391.0856 | 8.3585 | 152.1055 | 3.0765 | 197.5206 | 3.7177 | 8.3585 | 3.0765 | 3.7177
|  | 500.6564 | 12.9311 | 133.8045 | 3.6098 | 197.5206 | 3.7177 | 12.9311 | 3.6098 | 3.7177
|  | 371.1637 | 8.3585 | 166.4848 | 7.8765 | 150.4611 | 11.0066 | 8.3585 | 7.8765 | 11.0066
|  | 500.6564 | 12.9311 | 124.6541 | 3.0765 | 172.6837 | 5.5843 | 12.9311 | 3.0765 | 5.5843
|  | 449.1913 | 20.4134 | 285.4409 | 7.8765 | 197.5206 | 3.7177 | 20.4134 | 7.8765 | 3.7177
|  | 666.5945 | 8.3585 | 201.7794 | 4.2765 | 278.5676 | 7.9843 | 8.3585 | 4.2765 | 7.9843
|  | 449.1913 | 20.4134 | 201.7794 | 7.8765 | 156.9972 | 1.9843 | 20.4134 | 7.8765 | 1.9843
|  | 500.6564 | 12.9311 | 179.5569 | 5.4765 | 197.5206 | 3.1843 | 12.9311 | 5.4765 | 3.1843
|  | 371.1637 | 8.3585 | 204.3939 | 3.0765 | 234.1225 | 6.7843 | 8.3585 | 3.0765 | 6.7843
|  | 342.9409 | 12.0166 | 204.3939 | 3.0765 | 159.6116 | 7.9843 | 12.0166 | 3.0765 | 7.9843
|  | 362.8629 | 7.1877 | 379.5599 | 7.8765 | 218.436 | 11.8797 | 7.1877 | 7.8765 | 11.8797
|  | 396.0661 | 8.3585 | 123.3469 | 0.54638 | 156.9972 | 1.9843 | 8.3585 | 0.54638 | 1.9843
|  | 391.0856 | 8.3585 | 123.3469 | 0.54638 | 156.9972 | 1.9843 | 8.3585 | 0.54638 | 1.9843
|  | 396.0661 | 8.3585 | 123.3469 | 0.54638 | 218.436 | 11.8797 | 8.3585 | 0.54638 | 11.8797
|  | 256.6124 | 9.6056 | 157.3343 | 10.8987 | 159.6116 | 7.9843 | 9.6056 | 10.8987 | 7.9843
|  | 371.1637 | 8.3585 | 379.5599 | 7.8765 | 119.0881 | 1.9843 | 8.3585 | 7.8765 | 1.9843
|  | 396.0661 | 8.3585 | 285.4409 | 7.8765 | 172.6837 | 11.8797 | 8.3585 | 7.8765 | 11.8797
|  | 666.5945 | 8.3585 | 437.1616 | 3.3876 | 103.8232 | 3.7177 | 8.3585 | 3.3876 | 3.7177
|  | 396.0661 | 8.3585 | 123.3469 | 0.54638 | 143.9251 | 9.4954 | 8.3585 | 0.54638 | 9.4954
|  | 396.0661 | 8.3585 | 150.7983 | 9.3876 | 249.809 | 11.8797 | 8.3585 | 9.3876 | 11.8797
|  | 362.8629 | 7.1877 | 125.9613 | 1.8765 | 277.2604 | 4.3843 | 7.1877 | 1.8765 | 4.3843
|  | 500.6564 | 12.9311 | 103.8232 | 3.6098 | 172.6837 | 5.5843 | 12.9311 | 3.6098 | 5.5843
|  | 666.5945 | 8.3585 | 201.7794 | 7.8765 | 194.9062 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 500.6564 | 12.9311 | 180.8641 | 4.4543 | 117.7809 | 3.1843 | 12.9311 | 4.4543 | 3.1843
|  | 256.6124 | 9.6056 | 190.0146 | 8.8543 | 145.2323 | 3.1843 | 9.6056 | 8.8543 | 3.1843
|  | 243.253 | 28.3877 | 315.5067 | 7.8765 | 172.6837 | 11.8797 | 28.3877 | 7.8765 | 11.8797
|  | 500.6564 | 12.9311 | 163.8704 | 1.8765 | 234.1225 | 6.7843 | 12.9311 | 1.8765 | 6.7843
|  | 500.6564 | 12.9311 | 133.8045 | 3.6098 | 145.2323 | 3.1843 | 12.9311 | 3.6098 | 3.1843
|  | 243.253 | 28.3877 | 256.6822 | 11.8797 | 194.9062 | 7.9843 | 28.3877 | 11.8797 | 7.9843
|  | 256.6124 | 9.6056 | 315.5067 | 7.8765 | 372.6867 | 7.9843 | 9.6056 | 7.8765 | 7.9843
|  | 371.1637 | 8.3585 | 180.8641 | 4.4543 | 125.6241 | 2.4732 | 8.3585 | 4.4543 | 2.4732
|  | 362.8629 | 7.1877 | 180.8641 | 4.4543 | 126.9313 | 3.7177 | 7.1877 | 4.4543 | 3.7177
|  | 449.1913 | 20.4134 | 133.8045 | 3.6098 | 194.9062 | 4.3843 | 20.4134 | 3.6098 | 4.3843
|  | 342.9409 | 12.0166 | 204.3939 | 3.6098 | 234.1225 | 6.7843 | 12.0166 | 3.6098 | 6.7843
|  | 449.1913 | 20.4134 | 188.7073 | 7.8765 | 247.1946 | 3.9843 | 20.4134 | 7.8765 | 3.9843
|  | 391.0856 | 8.3585 | 201.7794 | 7.8765 | 172.6837 | 5.5843 | 8.3585 | 7.8765 | 5.5843
|  | 396.0661 | 8.3585 | 201.7794 | 4.2765 | 119.0881 | 1.9843 | 8.3585 | 4.2765 | 1.9843
|  | 256.6124 | 9.6056 | 240.9957 | 6.6765 | 117.7809 | 3.1843 | 9.6056 | 6.6765 | 3.1843
|  | 371.1637 | 8.3585 | 256.6822 | 11.8797 | 119.0881 | 1.9843 | 8.3585 | 11.8797 | 1.9843
|  | 391.0856 | 8.3585 | 225.3092 | 11.8797 | 234.1225 | 6.7843 | 8.3585 | 11.8797 | 6.7843
|  | 362.8629 | 7.1877 | 256.6822 | 11.8797 | 117.7809 | 3.1843 | 7.1877 | 11.8797 | 3.1843
|  | 500.6564 | 12.9311 | 240.9957 | 6.6765 | 308.6335 | 7.9843 | 12.9311 | 6.6765 | 7.9843
|  | 391.0856 | 8.3585 | 133.8045 | 3.6098 | 143.9251 | 9.4954 | 8.3585 | 3.6098 | 9.4954
|  | 256.6124 | 9.6056 | 179.5569 | 5.4765 | 156.9972 | 1.9843 | 9.6056 | 5.4765 | 1.9843
|  | 500.6564 | 12.9311 | 285.4409 | 7.8765 | 234.1225 | 6.7843 | 12.9311 | 7.8765 | 6.7843
|  | 342.9409 | 12.0166 | 123.3469 | 0.54638 | 249.809 | 11.8797 | 12.0166 | 0.54638 | 11.8797
|  | 396.0661 | 8.3585 | 180.8641 | 4.4543 | 197.5206 | 3.7177 | 8.3585 | 4.4543 | 3.7177
|  | 666.5945 | 8.3585 | 163.8704 | 1.8765 | 197.5206 | 3.7177 | 8.3585 | 1.8765 | 3.7177
|  | 500.6564 | 12.9311 | 157.3343 | 10.8987 | 183.1413 | 8.9621 | 12.9311 | 10.8987 | 8.9621
|  | 362.8629 | 7.1877 | 190.0146 | 8.8543 | 194.9062 | 7.9843 | 7.1877 | 8.8543 | 7.9843
|  | 396.0661 | 8.3585 | 315.5067 | 7.8765 | 172.6837 | 11.8797 | 8.3585 | 7.8765 | 11.8797
|  | 371.1637 | 8.3585 | 179.5569 | 5.4765 | 372.6867 | 7.9843 | 8.3585 | 5.4765 | 7.9843
|  | 371.1637 | 8.3585 | 240.9957 | 6.6765 | 278.5676 | 7.9843 | 8.3585 | 6.6765 | 7.9843
|  | 371.1637 | 8.3585 | 179.5569 | 11.8797 | 308.6335 | 7.9843 | 8.3585 | 11.8797 | 7.9843
|  | 391.0856 | 8.3585 | 180.8641 | 4.4543 | 197.5206 | 3.1843 | 8.3585 | 4.4543 | 3.1843
|  | 256.6124 | 9.6056 | 166.4848 | 7.8765 | 194.9062 | 4.3843 | 9.6056 | 7.8765 | 4.3843
|  | 243.253 | 28.3877 | 225.3092 | 11.8797 | 218.436 | 11.8797 | 28.3877 | 11.8797 | 11.8797
|  | 342.9409 | 12.0166 | 254.0678 | 3.8765 | 218.436 | 11.8797 | 12.0166 | 3.8765 | 11.8797
|  | 500.6564 | 12.9311 | 125.9613 | 1.8765 | 145.2323 | 3.1843 | 12.9311 | 1.8765 | 3.1843
|  | 500.6564 | 12.9311 | 132.4973 | 2.3654 | 126.9313 | 3.7177 | 12.9311 | 2.3654 | 3.7177
|  | 449.1913 | 20.4134 | 379.5599 | 7.8765 | 119.0881 | 1.9843 | 20.4134 | 7.8765 | 1.9843
|  | 396.0661 | 8.3585 | 201.7794 | 7.8765 | 437.1616 | 3.4954 | 8.3585 | 7.8765 | 3.4954
|  | 371.1637 | 8.3585 | 437.1616 | 3.3876 | 278.5676 | 7.9843 | 8.3585 | 3.3876 | 7.9843
|  | 243.253 | 28.3877 | 124.6541 | 3.0765 | 172.6837 | 11.8797 | 28.3877 | 3.0765 | 11.8797
|  | 256.6124 | 9.6056 | 190.0146 | 8.8543 | 156.9972 | 1.9843 | 9.6056 | 8.8543 | 1.9843
|  | 362.8629 | 7.1877 | 188.7073 | 7.8765 | 117.7809 | 3.1843 | 7.1877 | 7.8765 | 3.1843
|  | 500.6564 | 12.9311 | 188.7073 | 7.8765 | 249.809 | 11.8797 | 12.9311 | 7.8765 | 11.8797
|  | 362.8629 | 7.1877 | 285.4409 | 7.8765 | 194.9062 | 7.9843 | 7.1877 | 7.8765 | 7.9843
|  | 243.253 | 28.3877 | 133.8045 | 3.6098 | 159.6116 | 7.9843 | 28.3877 | 3.6098 | 7.9843
|  | 666.5945 | 8.3585 | 240.9957 | 6.6765 | 103.8232 | 3.7177 | 8.3585 | 6.6765 | 3.7177
|  | 391.0856 | 8.3585 | 179.5569 | 11.8797 | 183.1413 | 8.9621 | 8.3585 | 11.8797 | 8.9621
|  | 243.253 | 28.3877 | 125.9613 | 1.8765 | 145.2323 | 3.1843 | 28.3877 | 1.8765 | 3.1843
|  | 243.253 | 28.3877 | 123.3469 | 0.54638 | 194.9062 | 7.9843 | 28.3877 | 0.54638 | 7.9843
|  | 391.0856 | 8.3585 | 103.8232 | 3.6098 | 173.9909 | 4.5621 | 8.3585 | 3.6098 | 4.5621
|  | 396.0661 | 8.3585 | 103.8232 | 3.6098 | 197.5206 | 3.7177 | 8.3585 | 3.6098 | 3.7177
|  | 371.1637 | 8.3585 | 132.4973 | 2.3654 | 125.6241 | 2.4732 | 8.3585 | 2.3654 | 2.4732
|  | 449.1913 | 20.4134 | 132.4973 | 2.3654 | 277.2604 | 4.3843 | 20.4134 | 2.3654 | 4.3843
|  | 500.6564 | 12.9311 | 190.0146 | 8.8543 | 119.0881 | 1.9843 | 12.9311 | 8.8543 | 1.9843
|  | 362.8629 | 7.1877 | 179.5569 | 11.8797 | 143.9251 | 9.4954 | 7.1877 | 11.8797 | 9.4954
|  | 500.6564 | 12.9311 | 166.4848 | 7.8765 | 194.9062 | 4.3843 | 12.9311 | 7.8765 | 4.3843
|  | 256.6124 | 9.6056 | 188.7073 | 7.8765 | 125.6241 | 2.4732 | 9.6056 | 7.8765 | 2.4732
|  | 449.1913 | 20.4134 | 150.7983 | 9.3876 | 156.9972 | 1.9843 | 20.4134 | 9.3876 | 1.9843
|  | 256.6124 | 9.6056 | 163.8704 | 1.8765 | 119.0881 | 1.9843 | 9.6056 | 1.8765 | 1.9843
|  | 256.6124 | 9.6056 | 254.0678 | 3.8765 | 194.9062 | 7.9843 | 9.6056 | 3.8765 | 7.9843
|  | 449.1913 | 20.4134 | 204.3939 | 3.0765 | 194.9062 | 7.9843 | 20.4134 | 3.0765 | 7.9843
|  | 243.253 | 28.3877 | 152.1055 | 3.0765 | 197.5206 | 3.7177 | 28.3877 | 3.0765 | 3.7177
|  | 391.0856 | 8.3585 | 284.1336 | 4.2765 | 172.6837 | 11.8797 | 8.3585 | 4.2765 | 11.8797
|  | 256.6124 | 9.6056 | 179.5569 | 11.8797 | 145.2323 | 3.1843 | 9.6056 | 11.8797 | 3.1843
|  | 666.5945 | 8.3585 | 379.5599 | 7.8765 | 194.9062 | 4.3843 | 8.3585 | 7.8765 | 4.3843
|  | 396.0661 | 8.3585 | 152.1055 | 3.0765 | 172.6837 | 5.5843 | 8.3585 | 3.0765 | 5.5843
|  | 342.9409 | 12.0166 | 157.3343 | 10.8987 | 145.2323 | 3.1843 | 12.0166 | 10.8987 | 3.1843
|  | 391.0856 | 8.3585 | 315.5067 | 7.8765 | 116.4737 | 0.54638 | 8.3585 | 7.8765 | 0.54638
|  | 371.1637 | 8.3585 | 125.9613 | 1.8765 | 234.1225 | 6.7843 | 8.3585 | 1.8765 | 6.7843
|  | 342.9409 | 12.0166 | 285.4409 | 7.8765 | 247.1946 | 3.9843 | 12.0166 | 7.8765 | 3.9843
|  | 666.5945 | 8.3585 | 204.3939 | 3.0765 | 197.5206 | 3.7177 | 8.3585 | 3.0765 | 3.7177
|  | 342.9409 | 12.0166 | 133.8045 | 3.6098 | 156.9972 | 1.9843 | 12.0166 | 3.6098 | 1.9843
|  | 500.6564 | 12.9311 | 179.5569 | 5.4765 | 117.7809 | 3.1843 | 12.9311 | 5.4765 | 3.1843
|  | 371.1637 | 8.3585 | 188.7073 | 7.8765 | 247.1946 | 3.9843 | 8.3585 | 7.8765 | 3.9843
|  | 256.6124 | 9.6056 | 437.1616 | 3.3876 | 116.4737 | 0.54638 | 9.6056 | 3.3876 | 0.54638
|  | 256.6124 | 9.6056 | 315.5067 | 7.8765 | 218.436 | 11.8797 | 9.6056 | 7.8765 | 11.8797
|  | 371.1637 | 8.3585 | 201.7794 | 4.2765 | 372.6867 | 7.9843 | 8.3585 | 4.2765 | 7.9843
|  | 362.8629 | 7.1877 | 132.4973 | 2.3654 | 181.8341 | 7.9843 | 7.1877 | 2.3654 | 7.9843
|  | 391.0856 | 8.3585 | 240.9957 | 6.6765 | 156.9972 | 1.9843 | 8.3585 | 6.6765 | 1.9843
|  | 391.0856 | 8.3585 | 254.0678 | 3.8765 | 218.436 | 11.8797 | 8.3585 | 3.8765 | 11.8797
|  | 396.0661 | 8.3585 | 133.8045 | 3.6098 | 159.6116 | 7.9843 | 8.3585 | 3.6098 | 7.9843
|  | 391.0856 | 8.3585 | 152.1055 | 3.0765 | 125.6241 | 2.4732 | 8.3585 | 3.0765 | 2.4732
|  | 371.1637 | 8.3585 | 133.8045 | 3.6098 | 194.9062 | 4.3843 | 8.3585 | 3.6098 | 4.3843
|  | 500.6564 | 12.9311 | 103.8232 | 3.6098 | 125.6241 | 2.4732 | 12.9311 | 3.6098 | 2.4732
|  | 362.8629 | 7.1877 | 133.8045 | 3.6098 | 172.6837 | 11.8797 | 7.1877 | 3.6098 | 11.8797
|  | 396.0661 | 8.3585 | 125.9613 | 1.8765 | 159.6116 | 7.9843 | 8.3585 | 1.8765 | 7.9843
|  | 500.6564 | 12.9311 | 125.9613 | 1.8765 | 277.2604 | 4.3843 | 12.9311 | 1.8765 | 4.3843
|  | 256.6124 | 9.6056 | 133.8045 | 3.6098 | 234.1225 | 6.7843 | 9.6056 | 3.6098 | 6.7843
|  | 362.8629 | 7.1877 | 285.4409 | 7.8765 | 117.7809 | 3.1843 | 7.1877 | 7.8765 | 3.1843
|  | 371.1637 | 8.3585 | 254.0678 | 3.8765 | 156.9972 | 1.9843 | 8.3585 | 3.8765 | 1.9843
|  | 243.253 | 28.3877 | 179.5569 | 5.4765 | 143.9251 | 9.4954 | 28.3877 | 5.4765 | 9.4954
|  | 500.6564 | 12.9311 | 157.3343 | 10.8987 | 116.4737 | 0.54638 | 12.9311 | 10.8987 | 0.54638
|  | 342.9409 | 12.0166 | 315.5067 | 7.8765 | 103.8232 | 3.7177 | 12.0166 | 7.8765 | 3.7177
|  | 500.6564 | 12.9311 | 285.4409 | 7.8765 | 156.9972 | 1.9843 | 12.9311 | 7.8765 | 1.9843
|  | 243.253 | 28.3877 | 152.1055 | 3.0765 | 143.9251 | 9.4954 | 28.3877 | 3.0765 | 9.4954
|  | 256.6124 | 9.6056 | 157.3343 | 10.8987 | 173.9909 | 4.5621 | 9.6056 | 10.8987 | 4.5621
|  | 342.9409 | 12.0166 | 240.9957 | 6.6765 | 150.4611 | 11.0066 | 12.0166 | 6.6765 | 11.0066
|  | 666.5945 | 8.3585 | 179.5569 | 11.8797 | 183.1413 | 8.9621 | 8.3585 | 11.8797 | 8.9621
|  | 342.9409 | 12.0166 | 166.4848 | 7.8765 | 117.7809 | 3.1843 | 12.0166 | 7.8765 | 3.1843
|  | 362.8629 | 7.1877 | 103.8232 | 3.6098 | 372.6867 | 7.9843 | 7.1877 | 3.6098 | 7.9843
|  | 256.6124 | 9.6056 | 150.7983 | 9.3876 | 437.1616 | 3.4954 | 9.6056 | 9.3876 | 3.4954
|  | 391.0856 | 8.3585 | 315.5067 | 7.8765 | 172.6837 | 11.8797 | 8.3585 | 7.8765 | 11.8797
|  | 500.6564 | 12.9311 | 201.7794 | 7.8765 | 156.9972 | 1.9843 | 12.9311 | 7.8765 | 1.9843
|  | 371.1637 | 8.3585 | 204.3939 | 3.6098 | 159.6116 | 7.9843 | 8.3585 | 3.6098 | 7.9843
|  | 500.6564 | 12.9311 | 188.7073 | 7.8765 | 126.9313 | 3.7177 | 12.9311 | 7.8765 | 3.7177
|  | 342.9409 | 12.0166 | 256.6822 | 11.8797 | 194.9062 | 4.3843 | 12.0166 | 11.8797 | 4.3843
|  | 371.1637 | 8.3585 | 133.8045 | 3.6098 | 437.1616 | 3.4954 | 8.3585 | 3.6098 | 3.4954
|  | 449.1913 | 20.4134 | 150.7983 | 9.3876 | 156.9972 | 1.9843 | 20.4134 | 9.3876 | 1.9843
|  | 500.6564 | 12.9311 | 190.0146 | 8.8543 | 126.9313 | 3.7177 | 12.9311 | 8.8543 | 3.7177
|  | 342.9409 | 12.0166 | 315.5067 | 7.8765 | 172.6837 | 5.5843 | 12.0166 | 7.8765 | 5.5843
|  | 256.6124 | 9.6056 | 285.4409 | 7.8765 | 116.4737 | 0.54638 | 9.6056 | 7.8765 | 0.54638
|  | 666.5945 | 8.3585 | 124.6541 | 3.0765 | 117.7809 | 3.1843 | 8.3585 | 3.0765 | 3.1843
|  | 243.253 | 28.3877 | 201.7794 | 4.2765 | 117.7809 | 3.1843 | 28.3877 | 4.2765 | 3.1843
|  | 256.6124 | 9.6056 | 152.1055 | 3.0765 | 194.9062 | 4.3843 | 9.6056 | 3.0765 | 4.3843
|  | 500.6564 | 12.9311 | 285.4409 | 7.8765 | 249.809 | 11.8797 | 12.9311 | 7.8765 | 11.8797
|  | 449.1913 | 20.4134 | 240.9957 | 6.6765 | 197.5206 | 3.1843 | 20.4134 | 6.6765 | 3.1843
|  | 362.8629 | 7.1877 | 124.6541 | 3.0765 | 278.5676 | 7.9843 | 7.1877 | 3.0765 | 7.9843
|  | 500.6564 | 12.9311 | 284.1336 | 4.2765 | 372.6867 | 7.9843 | 12.9311 | 4.2765 | 7.9843
|  | 256.6124 | 9.6056 | 133.8045 | 3.6098 | 194.9062 | 4.3843 | 9.6056 | 3.6098 | 4.3843
|  | 396.0661 | 8.3585 | 133.8045 | 3.6098 | 143.9251 | 9.4954 | 8.3585 | 3.6098 | 9.4954
|  | 391.0856 | 8.3585 | 125.9613 | 1.8765 | 172.6837 | 5.5843 | 8.3585 | 1.8765 | 5.5843
|  | 342.9409 | 12.0166 | 315.5067 | 7.8765 | 278.5676 | 7.9843 | 12.0166 | 7.8765 | 7.9843
|  | 500.6564 | 12.9311 | 201.7794 | 4.2765 | 277.2604 | 4.3843 | 12.9311 | 4.2765 | 4.3843
|  | 396.0661 | 8.3585 | 201.7794 | 4.2765 | 437.1616 | 3.4954 | 8.3585 | 4.2765 | 3.4954
|  | 396.0661 | 8.3585 | 133.8045 | 3.6098 | 150.4611 | 11.0066 | 8.3585 | 3.6098 | 11.0066
|  | 371.1637 | 8.3585 | 285.4409 | 7.8765 | 125.6241 | 2.4732 | 8.3585 | 7.8765 | 2.4732
|  | 371.1637 | 8.3585 | 150.7983 | 9.3876 | 119.0881 | 1.9843 | 8.3585 | 9.3876 | 1.9843
|  | 371.1637 | 8.3585 | 157.3343 | 10.8987 | 437.1616 | 3.4954 | 8.3585 | 10.8987 | 3.4954
|  | 391.0856 | 8.3585 | 285.4409 | 7.8765 | 172.6837 | 11.8797 | 8.3585 | 7.8765 | 11.8797
|  | 449.1913 | 20.4134 | 285.4409 | 7.8765 | 247.1946 | 3.9843 | 20.4134 | 7.8765 | 3.9843
|  | 666.5945 | 8.3585 | 179.5569 | 11.8797 | 308.6335 | 7.9843 | 8.3585 | 11.8797 | 7.9843
|  | 362.8629 | 7.1877 | 150.7983 | 9.3876 | 234.1225 | 6.7843 | 7.1877 | 9.3876 | 6.7843
|  | 500.6564 | 12.9311 | 201.7794 | 4.2765 | 150.4611 | 11.0066 | 12.9311 | 4.2765 | 11.0066
|  | 391.0856 | 8.3585 | 103.8232 | 3.6098 | 116.4737 | 0.54638 | 8.3585 | 3.6098 | 0.54638
|  | 342.9409 | 12.0166 | 150.7983 | 9.3876 | 247.1946 | 3.9843 | 12.0166 | 9.3876 | 3.9843
|  | 396.0661 | 8.3585 | 133.8045 | 3.6098 | 308.6335 | 7.9843 | 8.3585 | 3.6098 | 7.9843
|  | 362.8629 | 7.1877 | 166.4848 | 7.8765 | 194.9062 | 7.9843 | 7.1877 | 7.8765 | 7.9843
|  | 391.0856 | 8.3585 | 254.0678 | 3.8765 | 183.1413 | 8.9621 | 8.3585 | 3.8765 | 8.9621
|  | 449.1913 | 20.4134 | 201.7794 | 7.8765 | 308.6335 | 7.9843 | 20.4134 | 7.8765 | 7.9843
|  | 666.5945 | 8.3585 | 150.7983 | 9.3876 | 247.1946 | 3.9843 | 8.3585 | 9.3876 | 3.9843
|  | 342.9409 | 12.0166 | 163.8704 | 1.8765 | 150.4611 | 11.0066 | 12.0166 | 1.8765 | 11.0066
|  | 371.1637 | 8.3585 | 132.4973 | 2.3654 | 125.6241 | 2.4732 | 8.3585 | 2.3654 | 2.4732
|  | 449.1913 | 20.4134 | 201.7794 | 7.8765 | 119.0881 | 1.9843 | 20.4134 | 7.8765 | 1.9843
|  | 362.8629 | 7.1877 | 204.3939 | 3.0765 | 156.9972 | 1.9843 | 7.1877 | 3.0765 | 1.9843
|  | 362.8629 | 7.1877 | 124.6541 | 3.0765 | 172.6837 | 11.8797 | 7.1877 | 3.0765 | 11.8797
|  | 243.253 | 28.3877 | 163.8704 | 1.8765 | 197.5206 | 3.1843 | 28.3877 | 1.8765 | 3.1843
|  | 500.6564 | 12.9311 | 437.1616 | 3.3876 | 103.8232 | 3.7177 | 12.9311 | 3.3876 | 3.7177
|  | 666.5945 | 8.3585 | 166.4848 | 7.8765 | 197.5206 | 3.7177 | 8.3585 | 7.8765 | 3.7177
|  | 371.1637 | 8.3585 | 180.8641 | 4.4543 | 173.9909 | 4.5621 | 8.3585 | 4.4543 | 4.5621
|  | 362.8629 | 7.1877 | 166.4848 | 7.8765 | 197.5206 | 3.7177 | 7.1877 | 7.8765 | 3.7177
|  | 243.253 | 28.3877 | 152.1055 | 3.0765 | 194.9062 | 4.3843 | 28.3877 | 3.0765 | 4.3843
|  | 256.6124 | 9.6056 | 152.1055 | 3.0765 | 194.9062 | 7.9843 | 9.6056 | 3.0765 | 7.9843
|  | 243.253 | 28.3877 | 132.4973 | 2.3654 | 117.7809 | 3.1843 | 28.3877 | 2.3654 | 3.1843
|  | 243.253 | 28.3877 | 315.5067 | 7.8765 | 159.6116 | 7.9843 | 28.3877 | 7.8765 | 7.9843
|  | 362.8629 | 7.1877 | 150.7983 | 9.3876 | 437.1616 | 3.4954 | 7.1877 | 9.3876 | 3.4954
|  | 666.5945 | 8.3585 | 123.3469 | 0.54638 | 197.5206 | 3.7177 | 8.3585 | 0.54638 | 3.7177
|  | 342.9409 | 12.0166 | 204.3939 | 3.6098 | 372.6867 | 7.9843 | 12.0166 | 3.6098 | 7.9843
|  | 371.1637 | 8.3585 | 157.3343 | 10.8987 | 143.9251 | 9.4954 | 8.3585 | 10.8987 | 9.4954
|  | 500.6564 | 12.9311 | 315.5067 | 7.8765 | 125.6241 | 2.4732 | 12.9311 | 7.8765 | 2.4732
|  | 362.8629 | 7.1877 | 256.6822 | 11.8797 | 173.9909 | 4.5621 | 7.1877 | 11.8797 | 4.5621
|  | 666.5945 | 8.3585 | 125.9613 | 1.8765 | 172.6837 | 5.5843 | 8.3585 | 1.8765 | 5.5843
|  | 449.1913 | 20.4134 | 201.7794 | 4.2765 | 126.9313 | 3.7177 | 20.4134 | 4.2765 | 3.7177
|  | 396.0661 | 8.3585 | 240.9957 | 6.6765 | 172.6837 | 11.8797 | 8.3585 | 6.6765 | 11.8797
|  | 666.5945 | 8.3585 | 123.3469 | 0.54638 | 247.1946 | 3.9843 | 8.3585 | 0.54638 | 3.9843
|  | 371.1637 | 8.3585 | 124.6541 | 3.0765 | 172.6837 | 11.8797 | 8.3585 | 3.0765 | 11.8797
|  | 666.5945 | 8.3585 | 204.3939 | 3.6098 | 125.6241 | 2.4732 | 8.3585 | 3.6098 | 2.4732
|  | 256.6124 | 9.6056 | 179.5569 | 11.8797 | 277.2604 | 4.3843 | 9.6056 | 11.8797 | 4.3843
|  | 371.1637 | 8.3585 | 179.5569 | 5.4765 | 159.6116 | 7.9843 | 8.3585 | 5.4765 | 7.9843
|  | 256.6124 | 9.6056 | 240.9957 | 6.6765 | 159.6116 | 7.9843 | 9.6056 | 6.6765 | 7.9843
|  | 449.1913 | 20.4134 | 256.6822 | 11.8797 | 247.1946 | 3.9843 | 20.4134 | 11.8797 | 3.9843
|  | 396.0661 | 8.3585 | 125.9613 | 1.8765 | 197.5206 | 3.1843 | 8.3585 | 1.8765 | 3.1843
|  | 500.6564 | 12.9311 | 132.4973 | 2.3654 | 278.5676 | 7.9843 | 12.9311 | 2.3654 | 7.9843
|  | 342.9409 | 12.0166 | 179.5569 | 5.4765 | 156.9972 | 1.9843 | 12.0166 | 5.4765 | 1.9843
|  | 342.9409 | 12.0166 | 284.1336 | 4.2765 | 145.2323 | 3.1843 | 12.0166 | 4.2765 | 3.1843
|  | 256.6124 | 9.6056 | 254.0678 | 3.8765 | 103.8232 | 3.7177 | 9.6056 | 3.8765 | 3.7177
|  | 396.0661 | 8.3585 | 315.5067 | 7.8765 | 197.5206 | 3.7177 | 8.3585 | 7.8765 | 3.7177
|  | 396.0661 | 8.3585 | 166.4848 | 7.8765 | 277.2604 | 4.3843 | 8.3585 | 7.8765 | 4.3843
|  | 362.8629 | 7.1877 | 157.3343 | 10.8987 | 119.0881 | 1.9843 | 7.1877 | 10.8987 | 1.9843
|  | 362.8629 | 7.1877 | 240.9957 | 6.6765 | 116.4737 | 0.54638 | 7.1877 | 6.6765 | 0.54638
|  | 362.8629 | 7.1877 | 201.7794 | 4.2765 | 194.9062 | 4.3843 | 7.1877 | 4.2765 | 4.3843
|  | 342.9409 | 12.0166 | 152.1055 | 3.0765 | 172.6837 | 11.8797 | 12.0166 | 3.0765 | 11.8797
|  | 391.0856 | 8.3585 | 150.7983 | 9.3876 | 150.4611 | 11.0066 | 8.3585 | 9.3876 | 11.0066
|  | 256.6124 | 9.6056 | 125.9613 | 1.8765 | 150.4611 | 11.0066 | 9.6056 | 1.8765 | 11.0066
|  | 256.6124 | 9.6056 | 201.7794 | 7.8765 | 125.6241 | 2.4732 | 9.6056 | 7.8765 | 2.4732
|  | 362.8629 | 7.1877 | 103.8232 | 3.6098 | 143.9251 | 9.4954 | 7.1877 | 3.6098 | 9.4954
|  | 666.5945 | 8.3585 | 437.1616 | 3.3876 | 143.9251 | 9.4954 | 8.3585 | 3.3876 | 9.4954
|  | 362.8629 | 7.1877 | 152.1055 | 3.0765 | 126.9313 | 3.7177 | 7.1877 | 3.0765 | 3.7177
|  | 500.6564 | 12.9311 | 157.3343 | 10.8987 | 183.1413 | 8.9621 | 12.9311 | 10.8987 | 8.9621
|  | 391.0856 | 8.3585 | 204.3939 | 3.6098 | 172.6837 | 11.8797 | 8.3585 | 3.6098 | 11.8797
|  | 449.1913 | 20.4134 | 180.8641 | 4.4543 | 197.5206 | 3.1843 | 20.4134 | 4.4543 | 3.1843
|  | 371.1637 | 8.3585 | 125.9613 | 1.8765 | 145.2323 | 3.1843 | 8.3585 | 1.8765 | 3.1843
|  | 391.0856 | 8.3585 | 284.1336 | 4.2765 | 172.6837 | 5.5843 | 8.3585 | 4.2765 | 5.5843
|  | 371.1637 | 8.3585 | 179.5569 | 5.4765 | 247.1946 | 3.9843 | 8.3585 | 5.4765 | 3.9843
|  | 371.1637 | 8.3585 | 240.9957 | 6.6765 | 181.8341 | 7.9843 | 8.3585 | 6.6765 | 7.9843
|  | 391.0856 | 8.3585 | 201.7794 | 7.8765 | 116.4737 | 0.54638 | 8.3585 | 7.8765 | 0.54638
|  | 362.8629 | 7.1877 | 437.1616 | 3.3876 | 308.6335 | 7.9843 | 7.1877 | 3.3876 | 7.9843
|  | 666.5945 | 8.3585 | 284.1336 | 4.2765 | 159.6116 | 7.9843 | 8.3585 | 4.2765 | 7.9843
|  | 666.5945 | 8.3585 | 152.1055 | 3.0765 | 194.9062 | 7.9843 | 8.3585 | 3.0765 | 7.9843
|  | 342.9409 | 12.0166 | 256.6822 | 11.8797 | 150.4611 | 11.0066 | 12.0166 | 11.8797 | 11.0066
|  | 342.9409 | 12.0166 | 284.1336 | 4.2765 | 194.9062 | 4.3843 | 12.0166 | 4.2765 | 4.3843
|  | 342.9409 | 12.0166 | 254.0678 | 3.8765 | 181.8341 | 7.9843 | 12.0166 | 3.8765 | 7.9843
|  | 396.0661 | 8.3585 | 157.3343 | 10.8987 | 119.0881 | 1.9843 | 8.3585 | 10.8987 | 1.9843
|  | 243.253 | 28.3877 | 157.3343 | 10.8987 | 145.2323 | 3.1843 | 28.3877 | 10.8987 | 3.1843
|  | 362.8629 | 7.1877 | 152.1055 | 3.0765 | 181.8341 | 7.9843 | 7.1877 | 3.0765 | 7.9843
|  | 666.5945 | 8.3585 | 256.6822 | 11.8797 | 156.9972 | 1.9843 | 8.3585 | 11.8797 | 1.9843
|  | 391.0856 | 8.3585 | 103.8232 | 3.6098 | 308.6335 | 7.9843 | 8.3585 | 3.6098 | 7.9843
|  | 396.0661 | 8.3585 | 379.5599 | 7.8765 | 119.0881 | 1.9843 | 8.3585 | 7.8765 | 1.9843
|  | 362.8629 | 7.1877 | 315.5067 | 7.8765 | 249.809 | 11.8797 | 7.1877 | 7.8765 | 11.8797
|  | 342.9409 | 12.0166 | 190.0146 | 8.8543 | 277.2604 | 4.3843 | 12.0166 | 8.8543 | 4.3843
|  | 371.1637 | 8.3585 | 188.7073 | 7.8765 | 172.6837 | 11.8797 | 8.3585 | 7.8765 | 11.8797
|  | 243.253 | 28.3877 | 163.8704 | 1.8765 | 194.9062 | 7.9843 | 28.3877 | 1.8765 | 7.9843
|  | 256.6124 | 9.6056 | 437.1616 | 3.3876 | 125.6241 | 2.4732 | 9.6056 | 3.3876 | 2.4732
|  | 256.6124 | 9.6056 | 166.4848 | 7.8765 | 181.8341 | 7.9843 | 9.6056 | 7.8765 | 7.9843
|  | 666.5945 | 8.3585 | 179.5569 | 5.4765 | 173.9909 | 4.5621 | 8.3585 | 5.4765 | 4.5621
|  | 666.5945 | 8.3585 | 225.3092 | 11.8797 | 119.0881 | 1.9843 | 8.3585 | 11.8797 | 1.9843
|  | 396.0661 | 8.3585 | 152.1055 | 3.0765 | 103.8232 | 3.7177 | 8.3585 | 3.0765 | 3.7177
|  | 371.1637 | 8.3585 | 225.3092 | 11.8797 | 437.1616 | 3.4954 | 8.3585 | 11.8797 | 3.4954
|  | 391.0856 | 8.3585 | 315.5067 | 7.8765 | 103.8232 | 3.7177 | 8.3585 | 7.8765 | 3.7177
|  | 342.9409 | 12.0166 | 204.3939 | 3.0765 | 308.6335 | 7.9843 | 12.0166 | 3.0765 | 7.9843
|  | 500.6564 | 12.9311 | 133.8045 | 3.6098 | 218.436 | 11.8797 | 12.9311 | 3.6098 | 11.8797
|  | 243.253 | 28.3877 | 201.7794 | 7.8765 | 125.6241 | 2.4732 | 28.3877 | 7.8765 | 2.4732
|  | 371.1637 | 8.3585 | 190.0146 | 8.8543 | 183.1413 | 8.9621 | 8.3585 | 8.8543 | 8.9621
|  | 449.1913 | 20.4134 | 201.7794 | 4.2765 | 372.6867 | 7.9843 | 20.4134 | 4.2765 | 7.9843
|  | 391.0856 | 8.3585 | 132.4973 | 2.3654 | 143.9251 | 9.4954 | 8.3585 | 2.3654 | 9.4954
|  | 362.8629 | 7.1877 | 204.3939 | 3.0765 | 277.2604 | 4.3843 | 7.1877 | 3.0765 | 4.3843
|  | 256.6124 | 9.6056 | 190.0146 | 8.8543 | 126.9313 | 3.7177 | 9.6056 | 8.8543 | 3.7177
|  | 342.9409 | 12.0166 | 180.8641 | 4.4543 | 159.6116 | 7.9843 | 12.0166 | 4.4543 | 7.9843
|  | 342.9409 | 12.0166 | 437.1616 | 3.3876 | 437.1616 | 3.4954 | 12.0166 | 3.3876 | 3.4954
|  | 666.5945 | 8.3585 | 201.7794 | 7.8765 | 194.9062 | 4.3843 | 8.3585 | 7.8765 | 4.3843
|  | 371.1637 | 8.3585 | 201.7794 | 7.8765 | 173.9909 | 4.5621 | 8.3585 | 7.8765 | 4.5621
|  | 449.1913 | 20.4134 | 152.1055 | 3.0765 | 145.2323 | 3.1843 | 20.4134 | 3.0765 | 3.1843
|  | 449.1913 | 20.4134 | 225.3092 | 11.8797 | 308.6335 | 7.9843 | 20.4134 | 11.8797 | 7.9843
|  | 449.1913 | 20.4134 | 152.1055 | 3.0765 | 194.9062 | 4.3843 | 20.4134 | 3.0765 | 4.3843
|  | 243.253 | 28.3877 | 240.9957 | 6.6765 | 247.1946 | 3.9843 | 28.3877 | 6.6765 | 3.9843
|  | 449.1913 | 20.4134 | 180.8641 | 4.4543 | 173.9909 | 4.5621 | 20.4134 | 4.4543 | 4.5621
|  | 342.9409 | 12.0166 | 204.3939 | 3.0765 | 372.6867 | 7.9843 | 12.0166 | 3.0765 | 7.9843
|  | 243.253 | 28.3877 | 190.0146 | 8.8543 | 197.5206 | 3.1843 | 28.3877 | 8.8543 | 3.1843
|  | 500.6564 | 12.9311 | 204.3939 | 3.6098 | 159.6116 | 7.9843 | 12.9311 | 3.6098 | 7.9843
|  | 342.9409 | 12.0166 | 133.8045 | 3.6098 | 181.8341 | 7.9843 | 12.0166 | 3.6098 | 7.9843
|  | 391.0856 | 8.3585 | 188.7073 | 7.8765 | 156.9972 | 1.9843 | 8.3585 | 7.8765 | 1.9843
|  | 396.0661 | 8.3585 | 190.0146 | 8.8543 | 156.9972 | 1.9843 | 8.3585 | 8.8543 | 1.9843
|  | 256.6124 | 9.6056 | 225.3092 | 11.8797 | 234.1225 | 6.7843 | 9.6056 | 11.8797 | 6.7843
|  | 449.1913 | 20.4134 | 204.3939 | 3.6098 | 218.436 | 11.8797 | 20.4134 | 3.6098 | 11.8797
|  | 391.0856 | 8.3585 | 225.3092 | 11.8797 | 172.6837 | 5.5843 | 8.3585 | 11.8797 | 5.5843
|  | 256.6124 | 9.6056 | 163.8704 | 1.8765 | 159.6116 | 7.9843 | 9.6056 | 1.8765 | 7.9843
|  | 391.0856 | 8.3585 | 204.3939 | 3.0765 | 197.5206 | 3.1843 | 8.3585 | 3.0765 | 3.1843
|  | 243.253 | 28.3877 | 150.7983 | 9.3876 | 143.9251 | 9.4954 | 28.3877 | 9.3876 | 9.4954
|  | 391.0856 | 8.3585 | 284.1336 | 4.2765 | 159.6116 | 7.9843 | 8.3585 | 4.2765 | 7.9843
|  | 362.8629 | 7.1877 | 152.1055 | 3.0765 | 150.4611 | 11.0066 | 7.1877 | 3.0765 | 11.0066
|  | 256.6124 | 9.6056 | 225.3092 | 11.8797 | 197.5206 | 3.7177 | 9.6056 | 11.8797 | 3.7177
|  | 500.6564 | 12.9311 | 163.8704 | 1.8765 | 172.6837 | 11.8797 | 12.9311 | 1.8765 | 11.8797
|  | 666.5945 | 8.3585 | 256.6822 | 11.8797 | 145.2323 | 3.1843 | 8.3585 | 11.8797 | 3.1843
|  | 256.6124 | 9.6056 | 125.9613 | 1.8765 | 172.6837 | 11.8797 | 9.6056 | 1.8765 | 11.8797
|  | 342.9409 | 12.0166 | 315.5067 | 7.8765 | 150.4611 | 11.0066 | 12.0166 | 7.8765 | 11.0066
|  | 500.6564 | 12.9311 | 123.3469 | 0.54638 | 172.6837 | 5.5843 | 12.9311 | 0.54638 | 5.5843
|  | 500.6564 | 12.9311 | 225.3092 | 11.8797 | 249.809 | 11.8797 | 12.9311 | 11.8797 | 11.8797
|  | 391.0856 | 8.3585 | 133.8045 | 3.6098 | 126.9313 | 3.7177 | 8.3585 | 3.6098 | 3.7177
|  | 243.253 | 28.3877 | 190.0146 | 8.8543 | 172.6837 | 5.5843 | 28.3877 | 8.8543 | 5.5843
|  | 396.0661 | 8.3585 | 132.4973 | 2.3654 | 172.6837 | 11.8797 | 8.3585 | 2.3654 | 11.8797
|  | 256.6124 | 9.6056 | 284.1336 | 4.2765 | 249.809 | 11.8797 | 9.6056 | 4.2765 | 11.8797
|  | 666.5945 | 8.3585 | 225.3092 | 11.8797 | 117.7809 | 3.1843 | 8.3585 | 11.8797 | 3.1843
|  | 342.9409 | 12.0166 | 150.7983 | 9.3876 | 372.6867 | 7.9843 | 12.0166 | 9.3876 | 7.9843
|  | 256.6124 | 9.6056 | 201.7794 | 7.8765 | 277.2604 | 4.3843 | 9.6056 | 7.8765 | 4.3843
|  | 666.5945 | 8.3585 | 315.5067 | 7.8765 | 372.6867 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 371.1637 | 8.3585 | 166.4848 | 7.8765 | 181.8341 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 362.8629 | 7.1877 | 125.9613 | 1.8765 | 249.809 | 11.8797 | 7.1877 | 1.8765 | 11.8797
|  | 391.0856 | 8.3585 | 437.1616 | 3.3876 | 156.9972 | 1.9843 | 8.3585 | 3.3876 | 1.9843
|  | 362.8629 | 7.1877 | 132.4973 | 2.3654 | 119.0881 | 1.9843 | 7.1877 | 2.3654 | 1.9843
|  | 666.5945 | 8.3585 | 125.9613 | 1.8765 | 173.9909 | 4.5621 | 8.3585 | 1.8765 | 4.5621
|  | 396.0661 | 8.3585 | 125.9613 | 1.8765 | 197.5206 | 3.7177 | 8.3585 | 1.8765 | 3.7177
|  | 449.1913 | 20.4134 | 188.7073 | 7.8765 | 218.436 | 11.8797 | 20.4134 | 7.8765 | 11.8797
|  | 396.0661 | 8.3585 | 180.8641 | 4.4543 | 247.1946 | 3.9843 | 8.3585 | 4.4543 | 3.9843
|  | 396.0661 | 8.3585 | 157.3343 | 10.8987 | 249.809 | 11.8797 | 8.3585 | 10.8987 | 11.8797
|  | 362.8629 | 7.1877 | 132.4973 | 2.3654 | 125.6241 | 2.4732 | 7.1877 | 2.3654 | 2.4732
|  | 449.1913 | 20.4134 | 201.7794 | 4.2765 | 125.6241 | 2.4732 | 20.4134 | 4.2765 | 2.4732
|  | 256.6124 | 9.6056 | 180.8641 | 4.4543 | 172.6837 | 5.5843 | 9.6056 | 4.4543 | 5.5843
|  | 500.6564 | 12.9311 | 150.7983 | 9.3876 | 372.6867 | 7.9843 | 12.9311 | 9.3876 | 7.9843
|  | 391.0856 | 8.3585 | 180.8641 | 4.4543 | 125.6241 | 2.4732 | 8.3585 | 4.4543 | 2.4732
|  | 500.6564 | 12.9311 | 284.1336 | 4.2765 | 308.6335 | 7.9843 | 12.9311 | 4.2765 | 7.9843
|  | 342.9409 | 12.0166 | 133.8045 | 3.6098 | 116.4737 | 0.54638 | 12.0166 | 3.6098 | 0.54638
|  | 449.1913 | 20.4134 | 315.5067 | 7.8765 | 247.1946 | 3.9843 | 20.4134 | 7.8765 | 3.9843
|  | 500.6564 | 12.9311 | 152.1055 | 3.0765 | 194.9062 | 7.9843 | 12.9311 | 3.0765 | 7.9843
|  | 371.1637 | 8.3585 | 204.3939 | 3.6098 | 197.5206 | 3.7177 | 8.3585 | 3.6098 | 3.7177
|  | 666.5945 | 8.3585 | 103.8232 | 3.6098 | 197.5206 | 3.1843 | 8.3585 | 3.6098 | 3.1843
|  | 396.0661 | 8.3585 | 152.1055 | 3.0765 | 234.1225 | 6.7843 | 8.3585 | 3.0765 | 6.7843
|  | 243.253 | 28.3877 | 132.4973 | 2.3654 | 143.9251 | 9.4954 | 28.3877 | 2.3654 | 9.4954
|  | 362.8629 | 7.1877 | 133.8045 | 3.6098 | 372.6867 | 7.9843 | 7.1877 | 3.6098 | 7.9843
|  | 449.1913 | 20.4134 | 240.9957 | 6.6765 | 197.5206 | 3.1843 | 20.4134 | 6.6765 | 3.1843
|  | 342.9409 | 12.0166 | 254.0678 | 3.8765 | 197.5206 | 3.7177 | 12.0166 | 3.8765 | 3.7177
|  | 342.9409 | 12.0166 | 152.1055 | 3.0765 | 172.6837 | 11.8797 | 12.0166 | 3.0765 | 11.8797
|  | 396.0661 | 8.3585 | 124.6541 | 3.0765 | 194.9062 | 7.9843 | 8.3585 | 3.0765 | 7.9843
|  | 500.6564 | 12.9311 | 152.1055 | 3.0765 | 156.9972 | 1.9843 | 12.9311 | 3.0765 | 1.9843
|  | 342.9409 | 12.0166 | 179.5569 | 11.8797 | 172.6837 | 5.5843 | 12.0166 | 11.8797 | 5.5843
|  | 243.253 | 28.3877 | 240.9957 | 6.6765 | 183.1413 | 8.9621 | 28.3877 | 6.6765 | 8.9621
|  | 371.1637 | 8.3585 | 225.3092 | 11.8797 | 150.4611 | 11.0066 | 8.3585 | 11.8797 | 11.0066
|  | 362.8629 | 7.1877 | 315.5067 | 7.8765 | 117.7809 | 3.1843 | 7.1877 | 7.8765 | 3.1843
|  | 256.6124 | 9.6056 | 133.8045 | 3.6098 | 278.5676 | 7.9843 | 9.6056 | 3.6098 | 7.9843
|  | 396.0661 | 8.3585 | 315.5067 | 7.8765 | 249.809 | 11.8797 | 8.3585 | 7.8765 | 11.8797
|  | 666.5945 | 8.3585 | 190.0146 | 8.8543 | 277.2604 | 4.3843 | 8.3585 | 8.8543 | 4.3843
|  | 500.6564 | 12.9311 | 254.0678 | 3.8765 | 159.6116 | 7.9843 | 12.9311 | 3.8765 | 7.9843
|  | 342.9409 | 12.0166 | 152.1055 | 3.0765 | 156.9972 | 1.9843 | 12.0166 | 3.0765 | 1.9843
|  | 500.6564 | 12.9311 | 157.3343 | 10.8987 | 150.4611 | 11.0066 | 12.9311 | 10.8987 | 11.0066
|  | 666.5945 | 8.3585 | 188.7073 | 7.8765 | 172.6837 | 5.5843 | 8.3585 | 7.8765 | 5.5843
|  | 371.1637 | 8.3585 | 190.0146 | 8.8543 | 308.6335 | 7.9843 | 8.3585 | 8.8543 | 7.9843
|  | 362.8629 | 7.1877 | 240.9957 | 6.6765 | 159.6116 | 7.9843 | 7.1877 | 6.6765 | 7.9843
|  | 256.6124 | 9.6056 | 132.4973 | 2.3654 | 156.9972 | 1.9843 | 9.6056 | 2.3654 | 1.9843
|  | 500.6564 | 12.9311 | 166.4848 | 7.8765 | 277.2604 | 4.3843 | 12.9311 | 7.8765 | 4.3843
|  | 396.0661 | 8.3585 | 123.3469 | 0.54638 | 372.6867 | 7.9843 | 8.3585 | 0.54638 | 7.9843
|  | 243.253 | 28.3877 | 190.0146 | 8.8543 | 145.2323 | 3.1843 | 28.3877 | 8.8543 | 3.1843
|  | 666.5945 | 8.3585 | 225.3092 | 11.8797 | 117.7809 | 3.1843 | 8.3585 | 11.8797 | 3.1843
|  | 256.6124 | 9.6056 | 180.8641 | 4.4543 | 159.6116 | 7.9843 | 9.6056 | 4.4543 | 7.9843
|  | 362.8629 | 7.1877 | 163.8704 | 1.8765 | 117.7809 | 3.1843 | 7.1877 | 1.8765 | 3.1843
|  | 449.1913 | 20.4134 | 204.3939 | 3.0765 | 156.9972 | 1.9843 | 20.4134 | 3.0765 | 1.9843
|  | 391.0856 | 8.3585 | 150.7983 | 9.3876 | 197.5206 | 3.1843 | 8.3585 | 9.3876 | 3.1843
|  | 256.6124 | 9.6056 | 132.4973 | 2.3654 | 277.2604 | 4.3843 | 9.6056 | 2.3654 | 4.3843
|  | 500.6564 | 12.9311 | 180.8641 | 4.4543 | 156.9972 | 1.9843 | 12.9311 | 4.4543 | 1.9843
|  | 666.5945 | 8.3585 | 103.8232 | 3.6098 | 159.6116 | 7.9843 | 8.3585 | 3.6098 | 7.9843
|  | 396.0661 | 8.3585 | 225.3092 | 11.8797 | 125.6241 | 2.4732 | 8.3585 | 11.8797 | 2.4732
|  | 243.253 | 28.3877 | 256.6822 | 11.8797 | 194.9062 | 7.9843 | 28.3877 | 11.8797 | 7.9843
|  | 256.6124 | 9.6056 | 123.3469 | 0.54638 | 172.6837 | 11.8797 | 9.6056 | 0.54638 | 11.8797
|  | 500.6564 | 12.9311 | 163.8704 | 1.8765 | 247.1946 | 3.9843 | 12.9311 | 1.8765 | 3.9843
|  | 391.0856 | 8.3585 | 204.3939 | 3.0765 | 119.0881 | 1.9843 | 8.3585 | 3.0765 | 1.9843
|  | 500.6564 | 12.9311 | 180.8641 | 4.4543 | 197.5206 | 3.1843 | 12.9311 | 4.4543 | 3.1843
|  | 391.0856 | 8.3585 | 201.7794 | 4.2765 | 156.9972 | 1.9843 | 8.3585 | 4.2765 | 1.9843
|  | 256.6124 | 9.6056 | 240.9957 | 6.6765 | 277.2604 | 4.3843 | 9.6056 | 6.6765 | 4.3843
|  | 256.6124 | 9.6056 | 152.1055 | 3.0765 | 277.2604 | 4.3843 | 9.6056 | 3.0765 | 4.3843
|  | 371.1637 | 8.3585 | 150.7983 | 9.3876 | 125.6241 | 2.4732 | 8.3585 | 9.3876 | 2.4732
|  | 500.6564 | 12.9311 | 201.7794 | 4.2765 | 197.5206 | 3.1843 | 12.9311 | 4.2765 | 3.1843
|  | 666.5945 | 8.3585 | 166.4848 | 7.8765 | 278.5676 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 391.0856 | 8.3585 | 284.1336 | 4.2765 | 249.809 | 11.8797 | 8.3585 | 4.2765 | 11.8797
|  | 500.6564 | 12.9311 | 204.3939 | 3.6098 | 143.9251 | 9.4954 | 12.9311 | 3.6098 | 9.4954
|  | 256.6124 | 9.6056 | 157.3343 | 10.8987 | 126.9313 | 3.7177 | 9.6056 | 10.8987 | 3.7177
|  | 342.9409 | 12.0166 | 225.3092 | 11.8797 | 117.7809 | 3.1843 | 12.0166 | 11.8797 | 3.1843
|  | 256.6124 | 9.6056 | 179.5569 | 11.8797 | 234.1225 | 6.7843 | 9.6056 | 11.8797 | 6.7843
|  | 362.8629 | 7.1877 | 133.8045 | 3.6098 | 194.9062 | 7.9843 | 7.1877 | 3.6098 | 7.9843
|  | 362.8629 | 7.1877 | 163.8704 | 1.8765 | 145.2323 | 3.1843 | 7.1877 | 1.8765 | 3.1843
|  | 371.1637 | 8.3585 | 166.4848 | 7.8765 | 194.9062 | 7.9843 | 8.3585 | 7.8765 | 7.9843
|  | 666.5945 | 8.3585 | 163.8704 | 1.8765 | 183.1413 | 8.9621 | 8.3585 | 1.8765 | 8.9621
|  | 500.6564 | 12.9311 | 179.5569 | 11.8797 | 117.7809 | 3.1843 | 12.9311 | 11.8797 | 3.1843
|  | 391.0856 | 8.3585 | 284.1336 | 4.2765 | 247.1946 | 3.9843 | 8.3585 | 4.2765 | 3.9843
|  | 391.0856 | 8.3585 | 180.8641 | 4.4543 | 145.2323 | 3.1843 | 8.3585 | 4.4543 | 3.1843
|  | 400 | 12 | 200 | 6 | 200 | 6 | 12 | 6 | 6

## Graph Data (hidden)
| Histogram Data |  |  | Cumulative Graph Data
| Bins | Frequency |  | Bins | Frequency | Cumulative Frequency | -600 | 0 | 0.004 | -130 | 0
407.0671 | [6 empty] | -580 | 0.004 | 0 | -130 | 0.266
105.3728 | -600 | 0.6% | 0.0006% | -600 | 0.004 | 0.004 | -560 | 0.004 | 0 | -600 | 0.266
-646.6608 | -500 | 1.9% | 0.0019% | -500 | 0.011 | 0.011 | -540 | 0.004 | 0.002
-541.288 | -400 | 5.4% | 0.0054% | -400 | 0.037 | 0.037 | -520 | 0.006 | 0.002
-435.9152 | -300 | 8.3% | 0.0083% | -300 | 0.094 | 0.094 | -500 | 0.008 | 0.003
-330.5425 | -200 | 11.5% | 0.0115% | -200 | 0.189 | 0.189 | -480 | 0.011 | 0.004
-225.1697 | -100 | 15.4% | 0.0154% | -100 | 0.305 | 0.305 | -460 | 0.015 | 0.004
-119.7969 | 0 | 17.6% | 0.0176% | 0 | 0.455 | 0.455 | -440 | 0.019 | 0.006
-14.4241 | 100 | 21.8% | 0.0218% | 100 | 0.619 | 0.619 | -420 | 0.025 | 0.004
90.9487 | 200 | 15% | 0.015% | 200 | 0.833 | 0.833 | -400 | 0.029 | 0.008
196.3215 | 300 | 2.5% | 0.0025% | 300 | 0.974 | 0.974 | -380 | 0.037 | 0.017
301.6943 | 400 |  |  | 400 | 0.998 | 0.998 | -360 | 0.054 | 0.006
[7 empty] | -340 | 0.06 | 0.013
0.006 | [6 empty] | -320 | 0.073 | 0.008
0.019 | [6 empty] | -300 | 0.081 | 0.013
0.054 | [6 empty] | -280 | 0.094 | 0.017
0.083 | [6 empty] | -260 | 0.111 | 0.018
0.115 | [6 empty] | -240 | 0.129 | 0.018
0.154 | [6 empty] | -220 | 0.147 | 0.019
0.176 | [6 empty] | -200 | 0.166 | 0.023
0.218 | [6 empty] | -180 | 0.189 | 0.016
0.15 | [6 empty] | -160 | 0.205 | 0.029
0.025 | [6 empty] | -140 | 0.234 | 0.018
[7 empty] | -120 | 0.252 | 0.025
0.006 | [6 empty] | -100 | 0.277 | 0.028
0.025 | [6 empty] | -80 | 0.305 | 0.029
0.079 | [6 empty] | -60 | 0.334 | 0.029
0.162 | [6 empty] | -40 | 0.363 | 0.025
0.277 | [6 empty] | -20 | 0.388 | 0.031
0.431 | [6 empty] | 0 | 0.419 | 0.036
0.607 | [6 empty] | 20 | 0.455 | 0.034
0.825 | [6 empty] | 40 | 0.489 | 0.024
0.975 | [6 empty] | 60 | 0.513 | 0.033
1 | [6 empty] | 80 | 0.546 | 0.036
[7 empty] | 100 | 0.582 | 0.037
[7 empty] | 120 | 0.619 | 0.039
[7 empty] | 140 | 0.658 | 0.05
[7 empty] | 160 | 0.708 | 0.035
[7 empty] | 180 | 0.743 | 0.05
[7 empty] | 200 | 0.793 | 0.04
[7 empty] | 220 | 0.833 | 0.036
[7 empty] | 240 | 0.869 | 0.037
[7 empty] | 260 | 0.906 | 0.034
[7 empty] | 280 | 0.94 | 0.011
[7 empty] | 300 | 0.951 | 0.023
[7 empty] | 320 | 0.974 | 0.013
[7 empty] | 340 | 0.987 | 0.003
[7 empty] | 360 | 0.99 | 0.006
[7 empty] | 380 | 0.996 | 0.002
[7 empty] | 400 | 0.998 | 0

## PMTable
1001 | Generated with the SIPmath™ Modeler Tools from ProbabilityManagement.org
| Index | Finish | Profit | Cost | Penalty
| Values | 18 | 100 | 800 | 0
| 1 | 31.9975 | 7.3737 | 472.7003 | 419.926
| 2 | 31.3121 | -383.1502 | 883.7861 | 399.3641
| 3 | 19.8931 | 2.9268 | 840.2817 | 56.7915
| 4 | 12.3428 | 149.1444 | 750.8556 | 0
| 5 | 20.2382 | -51.4031 | 884.2565 | 67.1466
| 6 | 16.235 | 95.235 | 804.765 | 0
| 7 | 17.3206 | 202.4262 | 697.5738 | 0
| 8 | 17.5899 | 130.3602 | 769.6398 | 0
| 9 | 28.3978 | -222.5149 | 810.5823 | 311.9325
| 10 | 13.3232 | 407.0671 | 492.9329 | 0
| 11 | 16.235 | 150.1378 | 749.8622 | 0
| 12 | 36.2642 | -266.9493 | 619.0233 | 547.926
| 13 | 10.372 | 175.7461 | 724.2539 | 0
| 14 | 19.0674 | -92.8811 | 960.8588 | 32.0223
| 15 | 40.2674 | -380.5096 | 612.4873 | 668.0223
| 16 | 15.6264 | 336.7623 | 563.2377 | 0
| 17 | 12.635 | 109.6143 | 790.3857 | 0
| 18 | 13.9899 | 246.7019 | 653.2981 | 0
| 19 | 19.0674 | 121.5013 | 746.4764 | 32.0223
| 20 | 15.172 | 238.4077 | 661.5923 | 0
| 21 | 16.5753 | 203.1975 | 696.8025 | 0
| 22 | 31.4642 | -18.3726 | 514.4466 | 403.926
| 23 | 40.2674 | -388.3528 | 620.3305 | 668.0223
| 24 | 21.4853 | 131.6858 | 663.7558 | 104.5584
| 25 | 32.2931 | -386.4356 | 857.6419 | 428.7937
| 26 | 24.8108 | -144.1479 | 839.8248 | 204.3231
| 27 | 16.3428 | -241.7128 | 1141.7128 | 0
| 28 | 12.635 | -86.1549 | 986.1549 | 0
| 29 | 36.2642 | -304.8584 | 656.9324 | 547.926
| 30 | 20.0009 | 62.4377 | 777.5357 | 60.0267
| 31 | 12.635 | 207.9688 | 692.0312 | 0
| 32 | 20.2382 | -285.3296 | 1118.183 | 67.1466
| 33 | 12.0762 | 177.5892 | 722.4108 | 0
| 34 | 28.3978 | -223.8221 | 811.8896 | 311.9325
| 35 | 18.9932 | 305.7967 | 564.4079 | 29.7954
| 36 | 40.2674 | -418.4186 | 650.3964 | 668.0223
| 37 | 17.2128 | 222.3481 | 677.6519 | 0
| 38 | 19.0674 | 65.2913 | 802.6864 | 32.0223
| 39 | 40.2674 | -396.1961 | 628.1738 | 668.0223
| 40 | 37.8831 | -288.0664 | 591.5719 | 596.4945
| 41 | 21.4853 | 139.5291 | 655.9125 | 104.5584
| 42 | 17.4821 | 357.8147 | 542.1853 | 0
| 43 | 12.8128 | 222.3481 | 677.6519 | 0
| 44 | 10.9054 | 308.6599 | 591.3401 | 0
| 45 | 37.8831 | -263.2294 | 566.7349 | 596.4945
| 46 | 16.3428 | 236.7274 | 663.2726 | 0
| 47 | 17.854 | 163.2099 | 736.7901 | 0
| 48 | 20.2382 | 100.2987 | 732.5547 | 67.1466
| 49 | 16.4708 | 249.2637 | 650.7363 | 0
| 50 | 24.8108 | -166.3705 | 862.0474 | 204.3231
| 51 | 24.0232 | -8.9255 | 728.2281 | 180.6974
| 52 | 20.2382 | 38.8598 | 793.9935 | 67.1466
| 53 | 28.3978 | -222.5149 | 810.5823 | 311.9325
| 54 | 21.4853 | 187.8958 | 607.5458 | 104.5584
| 55 | 20.0009 | -15.9949 | 855.9682 | 60.0267
| 56 | 20.2382 | -496.212 | 1329.0654 | 67.1466
| 57 | 16.3428 | 30.1883 | 869.8117 | 0
| 58 | 15.6264 | -13.9071 | 913.9071 | 0
| 59 | 22.3978 | 76.4412 | 691.6263 | 131.9325
| 60 | 16.4009 | 108.085 | 791.915 | 0
| 61 | 18.4598 | 162.3171 | 723.8874 | 13.7954
| 62 | 15.0931 | 285.8655 | 614.1345 | 0
| 63 | 17.7461 | 249.3124 | 650.6876 | 0
| 64 | 16.235 | 169.9943 | 730.0057 | 0
| 65 | 13.972 | 150.9091 | 749.0909 | 0
| 66 | 19.2572 | 194.775 | 667.508 | 37.717
| 67 | 36.2642 | -547.9994 | 900.0734 | 547.926
| 68 | 20.5043 | 236.9336 | 587.9376 | 75.1288
| 69 | 16.5787 | 257.1069 | 642.8931 | 0
| 70 | 37.3498 | -311.2827 | 630.7882 | 580.4945
| 71 | 16.4708 | 219.1979 | 680.8021 | 0
| 72 | 20.8076 | -74.1472 | 889.9204 | 84.2268
| 73 | 28.2899 | -410.1323 | 1001.4349 | 308.6974
| 74 | 12.0762 | 179.2102 | 720.7898 | 0
| 75 | 16.235 | -1.4985 | 901.4985 | 0
| 76 | 20.2382 | 136.5867 | 696.2666 | 67.1466
| 77 | 19.3651 | 186.6248 | 672.423 | 40.9521
| 78 | 31.42 | -387.6925 | 885.0933 | 402.5992
| 79 | 13.9428 | 184.1252 | 715.8748 | 0
| 80 | 21.7853 | -151.4257 | 937.8655 | 113.5602
| 81 | 20.2382 | 3.5652 | 829.2882 | 67.1466
| 82 | 17.854 | 160.5955 | 739.4045 | 0
| 83 | 20.2382 | -337.618 | 1170.4714 | 67.1466
| 84 | 16.235 | -277.0075 | 1177.0075 | 0
| 85 | 36.372 | -336.8521 | 685.691 | 551.1611
| 86 | 24.8108 | -340.2294 | 1035.9063 | 204.3231
| 87 | 24.0232 | 49.8144 | 669.4882 | 180.6974
| 88 | 12.9206 | 196.1385 | 703.8615 | 0
| 89 | 12.8128 | 205.2889 | 694.7111 | 0
| 90 | 17.3206 | 159.2882 | 740.7118 | 0
| 91 | 16.5787 | 279.245 | 620.755 | 0
| 92 | 13.835 | -193.346 | 1093.346 | 0
| 93 | 15.035 | -205.1109 | 1105.1109 | 0
| 94 | 16.235 | 164.7654 | 735.2346 | 0
| 95 | 10.6831 | -52.13 | 952.13 | 0
| 96 | 10.372 | 213.6552 | 686.3448 | 0
| 97 | 16.4009 | 78.0192 | 821.9808 | 0
| 98 | 11.642 | -80.8886 | 980.8886 | 0
| 99 | 12.8128 | -109.1113 | 1009.1113 | 0
| 100 | 36.372 | -202.2096 | 551.0484 | 551.1611
| 101 | 28.2899 | -299.0195 | 890.3221 | 308.6974
| 102 | 20.2382 | 32.3238 | 800.5296 | 67.1466
| 103 | 20.2382 | -185.9817 | 1018.8351 | 67.1466
| 104 | 17.854 | 218.4265 | 681.5735 | 0
| 105 | 40.2674 | -380.5096 | 612.4873 | 668.0223
| 106 | 20.2382 | -293.1729 | 1126.0263 | 67.1466
| 107 | 11.172 | 85.5487 | 814.4513 | 0
| 108 | 12.635 | -113.6063 | 1013.6063 | 0
| 109 | 16.3428 | -73.1467 | 973.1467 | 0
| 110 | 28.3978 | -414.6747 | 1002.7422 | 311.9325
| 111 | 12.0762 | -67.9384 | 967.9384 | 0
| 112 | 20.2382 | 102.5993 | 730.2541 | 67.1466
| 113 | 20.0009 | -255.2142 | 1095.1876 | 60.0267
| 114 | 28.3978 | -273.4961 | 861.5635 | 311.9325
| 115 | 23.8963 | -33.5081 | 756.6203 | 176.8878
| 116 | 15.4042 | 3.4238 | 896.5762 | 0
| 117 | 24.9755 | -134.2275 | 824.9616 | 209.2659
| 118 | 20.2382 | 140.7567 | 692.0967 | 67.1466
| 119 | 16.2931 | 147.3013 | 752.6987 | 0
| 120 | 36.2642 | -440.8082 | 792.8822 | 547.926
| 121 | 19.2572 | 154.2515 | 708.0315 | 37.717
| 122 | 15.172 | 175.7461 | 724.2539 | 0
| 123 | 16.3428 | 174.9748 | 725.0252 | 0
| 124 | 19.7154 | -170.3745 | 1018.9125 | 51.4619
| 125 | 16.6487 | 77.1689 | 822.8311 | 0
| 126 | 19.3651 | 71.5249 | 787.523 | 40.9521
| 127 | 19.0674 | 2.5452 | 865.4325 | 32.0223
| 128 | 24.8108 | -206.894 | 902.5709 | 204.3231
| 129 | 20.9154 | 6.7007 | 805.8374 | 87.4619
| 130 | 11.0642 | 166.5957 | 733.4043 | 0
| 131 | 20.2382 | 136.9006 | 695.9528 | 67.1466
| 132 | 12.235 | -146.2865 | 1046.2865 | 0
| 133 | 20.2382 | -90.5539 | 923.4073 | 67.1466
| 134 | 15.0931 | 285.8655 | 614.1345 | 0
| 135 | 17.3154 | -82.3107 | 982.3107 | 0
| 136 | 17.5899 | 144.7395 | 755.2605 | 0
| 137 | 13.835 | 47.1166 | 852.8834 | 0
| 138 | 15.8931 | 105.4706 | 794.5294 | 0
| 139 | 22.4265 | -131.4445 | 898.6493 | 132.7953
| 140 | 20.2382 | 109.4491 | 723.4042 | 67.1466
| 141 | 19.3651 | -146.7151 | 1005.763 | 40.9521
| 142 | 36.372 | -257.1124 | 605.9512 | 551.1611
| 143 | 16.3428 | 133.1441 | 766.8559 | 0
| 144 | 15.6264 | -13.9071 | 913.9071 | 0
| 145 | 15.1428 | 160.9093 | 739.0907 | 0
| 146 | 11.435 | 227.2631 | 672.7369 | 0
| 147 | 15.6264 | 207.433 | 692.567 | 0
| 148 | 21.7853 | -212.8646 | 999.3044 | 113.5602
| 149 | 16.3428 | -3.7991 | 903.7991 | 0
| 150 | 16.3428 | -104.7681 | 1004.7681 | 0
| 151 | 16.1154 | 121.614 | 778.386 | 0
| 152 | 16.3428 | 41.6394 | 858.3606 | 0
| 153 | 16.235 | 220.9754 | 679.0246 | 0
| 154 | 19.8931 | -156.5528 | 999.7613 | 56.7915
| 155 | 32.1054 | -57.2158 | 534.0547 | 423.1611
| 156 | 10.7239 | -15.5655 | 915.5655 | 0
| 157 | 23.8963 | -77.9532 | 801.0654 | 176.8878
| 158 | 14.0598 | 358.7003 | 541.2997 | 0
| 159 | 23.5978 | -39.2986 | 771.3661 | 167.9325
| 160 | 16.3428 | 169.7459 | 730.2541 | 0
| 161 | 16.4265 | -189.9235 | 1089.9235 | 0
| 162 | 20.2382 | 12.4018 | 820.4515 | 67.1466
| 163 | 36.2642 | -363.6828 | 715.7568 | 547.926
| 164 | 18.1943 | 257.5014 | 636.6708 | 5.8278
| 165 | 24.8108 | -338.9222 | 1034.5991 | 204.3231
| 166 | 16.3428 | -104.7681 | 1004.7681 | 0
| 167 | 13.8642 | 150.9091 | 749.0909 | 0
| 168 | 20.2382 | -200.7811 | 1033.6345 | 67.1466
| 169 | 16.3428 | 147.5234 | 752.4766 | 0
| 170 | 16.3428 | -48.3097 | 948.3097 | 0
| 171 | 12.7428 | 49.7965 | 850.2035 | 0
| 172 | 11.7498 | 259.3231 | 640.6769 | 0
| 173 | 28.3978 | -474.8063 | 1062.8738 | 311.9325
| 174 | 15.1428 | -133.2144 | 1033.2144 | 0
| 175 | 20.5043 | 251.3129 | 573.5583 | 75.1288
| 176 | 22.9153 | 5.072 | 747.4698 | 147.4582
| 177 | 29.9089 | -240.3968 | 783.1309 | 357.2659
| 178 | 20.9154 | -131.8635 | 944.4016 | 87.4619
| 179 | 11.9683 | -16.8727 | 916.8727 | 0
| 180 | 27.1978 | -191.7437 | 815.8112 | 275.9325
| 181 | 20.9154 | -167.1582 | 979.6963 | 87.4619
| 182 | 12.9206 | -102.2381 | 1002.2381 | 0
| 183 | 23.8963 | 5.7082 | 717.404 | 176.8878
| 184 | 12.3428 | 104.6338 | 795.3662 | 0
| 185 | 21.7853 | -31.1624 | 817.6023 | 113.5602
| 186 | 12.0762 | 207.5705 | 692.4295 | 0
| 187 | 18.5677 | 63.6557 | 819.3137 | 17.0306
| 188 | 20.9154 | -14.2147 | 826.7527 | 87.4619
| 189 | 20.9154 | -307.1141 | 1119.6521 | 87.4619
| 190 | 16.3899 | 168.2693 | 731.7307 | 0
| 191 | 19.0674 | 50.912 | 817.0658 | 32.0223
| 192 | 18.8009 | 14.7763 | 861.1971 | 24.0267
| 193 | 17.4821 | 208.7928 | 691.2072 | 0
| 194 | 12.3428 | 156.9876 | 743.0124 | 0
| 195 | 20.2382 | 135.2795 | 697.5738 | 67.1466
| 196 | 21.4853 | 153.9084 | 641.5332 | 104.5584
| 197 | 11.9683 | -307.5793 | 1207.5793 | 0
| 198 | 21.4853 | 115.9993 | 679.4423 | 104.5584
| 199 | 10.9054 | -97.5451 | 997.5451 | 0
| 200 | 20.2382 | 95.0044 | 737.849 | 67.1466
| 201 | 20.2382 | 62.3241 | 770.5292 | 67.1466
| 202 | 37.7753 | -284.8313 | 591.5719 | 593.2593
| 203 | 11.971 | 353.8931 | 546.1069 | 0
| 204 | 15.7342 | 248.8421 | 651.1579 | 0
| 205 | 22.3187 | 1.2043 | 769.2355 | 129.5602
| 206 | 22.7788 | 58.4736 | 698.1623 | 143.3641
| 207 | 20.8076 | -127.3212 | 943.0944 | 84.2268
| 208 | 19.2572 | 55.2174 | 807.0656 | 37.717
| 209 | 15.172 | 243.721 | 656.279 | 0
| 210 | 15.0642 | 251.5643 | 648.4357 | 0
| 211 | 28.2899 | -280.7186 | 872.0212 | 308.6974
| 212 | 32.2931 | -450.4888 | 921.6952 | 428.7937
| 213 | 11.9683 | 197.5111 | 702.4889 | 0
| 214 | 19.2572 | 74.76 | 787.523 | 37.717
| 215 | 29.801 | -157.8435 | 703.8128 | 354.0307
| 216 | 19.101 | 264.6525 | 602.3169 | 33.0306
| 217 | 16.3428 | 154.3732 | 745.6268 | 0
| 218 | 24.8108 | -248.7247 | 944.4016 | 204.3231
| 219 | 22.7788 | 58.4736 | 698.1623 | 143.3641
| 220 | 20.2382 | 118.5996 | 714.2538 | 67.1466
| 221 | 12.0762 | 272.9077 | 627.0923 | 0
| 222 | 20.9154 | -63.8886 | 876.4267 | 87.4619
| 223 | 19.0674 | 151.5671 | 716.4106 | 32.0223
| 224 | 17.5899 | 199.6423 | 700.3577 | 0
| 225 | 20.2382 | 118.5996 | 714.2538 | 67.1466
| 226 | 16.6487 | 138.6077 | 761.3923 | 0
| 227 | 24.2899 | -189.4772 | 900.7798 | 188.6974
| 228 | 15.035 | -444.7519 | 1344.7519 | 0
| 229 | 24.8108 | -179.4426 | 875.1195 | 204.3231
| 230 | 27.1978 | -191.7437 | 815.8112 | 275.9325
| 231 | 20.0009 | 211.3751 | 628.5982 | 60.0267
| 232 | 17.4821 | 39.7412 | 860.2588 | 0
| 233 | 36.2642 | -183.7095 | 535.7835 | 547.926
| 234 | 15.1428 | 162.2165 | 737.7835 | 0
| 235 | 19.101 | 180.9911 | 685.9783 | 33.0306
| 236 | 27.0899 | -236.8753 | 864.1779 | 272.6974
| 237 | 17.5899 | 357.7303 | 542.2697 | 0
| 238 | 19.0674 | 74.4417 | 793.536 | 32.0223
| 239 | 17.5899 | 89.8367 | 810.1633 | 0
| 240 | 12.0762 | 126.9218 | 773.0782 | 0
| 241 | 16.3428 | -90.1404 | 990.1404 | 0
| 242 | 12.7428 | -2.4919 | 902.4919 | 0
| 243 | 24.0232 | -61.2139 | 780.5165 | 180.6974
| 244 | 12.772 | 260.6303 | 639.3697 | 0
| 245 | 24.8108 | -256.568 | 952.2449 | 204.3231
| 246 | 12.635 | 100.7122 | 799.2878 | 0
| 247 | 17.6009 | 251.8781 | 648.1219 | 0
| 248 | 32.2931 | -317.1535 | 788.3598 | 428.7937
| 249 | 19.6076 | -62.5626 | 914.3358 | 48.2268
| 250 | 20.0009 | 138.2558 | 701.7175 | 60.0267
| 251 | 17.854 | -74.39 | 974.39 | 0
| 252 | 19.8931 | 42.143 | 801.0654 | 56.7915
| 253 | 32.2931 | -429.5735 | 900.7798 | 428.7937
| 254 | 20.9154 | -118.7914 | 931.3295 | 87.4619
| 255 | 20.2382 | 17.9445 | 814.9089 | 67.1466
| 256 | 40.2674 | -515.1522 | 747.1299 | 668.0223
| 257 | 17.3206 | 40.3322 | 859.6678 | 0
| 258 | 19.2572 | -134.3295 | 996.6125 | 37.717
| 259 | 12.235 | 52.3454 | 847.6546 | 0
| 260 | 31.3121 | -383.1502 | 883.7861 | 399.3641
| 261 | 20.2382 | 62.3896 | 770.4638 | 67.1466
| 262 | 17.3206 | 196.1385 | 703.8615 | 0
| 263 | 13.972 | 62.0189 | 837.9811 | 0
| 264 | 16.235 | 183.0664 | 716.9336 | 0
| 265 | 18.4598 | 282.5804 | 603.6241 | 13.7954
| 266 | 19.8931 | 114.0396 | 729.1689 | 56.7915
| 267 | 20.2382 | -218.8104 | 1051.6637 | 67.1466
| 268 | 17.4821 | 257.1596 | 642.8404 | 0
| 269 | 19.0674 | 82.285 | 785.6927 | 32.0223
| 270 | 36.2642 | -277.407 | 629.481 | 547.926
| 271 | 15.172 | 92.0847 | 807.9153 | 0
| 272 | 39.2864 | -417.7476 | 679.155 | 638.5927
| 273 | 15.1428 | -167.3503 | 1067.3503 | 0
| 274 | 12.8128 | -194.6532 | 1094.6532 | 0
| 275 | 20.2382 | 116.9786 | 715.8748 | 67.1466
| 276 | 12.635 | -95.3053 | 995.3053 | 0
| 277 | 37.242 | -387.7873 | 710.528 | 577.2593
| 278 | 16.235 | 10.2664 | 889.7336 | 0
| 279 | 16.3428 | 194.8967 | 705.1033 | 0
| 280 | 24.8108 | -102.3172 | 797.9941 | 204.3231
| 281 | 20.2382 | -26.5006 | 859.354 | 67.1466
| 282 | 31.572 | -21.6077 | 514.4466 | 407.1611
| 283 | 11.854 | -31.6722 | 931.6722 | 0
| 284 | 20.2382 | 87.2266 | 745.6268 | 67.1466
| 285 | 20.2382 | -260.4927 | 1093.346 | 67.1466
| 286 | 14.0598 | 267.6172 | 632.3828 | 0
| 287 | 15.0642 | 213.6552 | 686.3448 | 0
| 288 | 20.8076 | -120.7852 | 936.5583 | 84.2268
| 289 | 16.042 | 152.2164 | 747.7836 | 0
| 290 | 11.642 | 79.0126 | 820.9874 | 0
| 291 | 16.3428 | 205.2045 | 694.7955 | 0
| 292 | 16.235 | -68.1662 | 968.1662 | 0
| 293 | 12.0762 | 207.9688 | 692.0312 | 0
| 294 | 15.7342 | 301.1304 | 598.8696 | 0
| 295 | 18.1943 | 179.0688 | 715.1034 | 5.8278
| 296 | 9.172 | 254.1787 | 645.8213 | 0
| 297 | 16.3428 | -243.3323 | 1143.3323 | 0
| 298 | 19.8931 | -24.5246 | 867.7331 | 56.7915
| 299 | 12.0762 | 252.9857 | 647.0143 | 0
| 300 | 19.0674 | -28.8278 | 896.8055 | 32.0223
| 301 | 15.1428 | -205.1109 | 1105.1109 | 0
| 302 | 20.8076 | -238.434 | 1054.2072 | 84.2268
| 303 | 16.1154 | -2.5709 | 902.5709 | 0
| 304 | 17.5899 | 257.1596 | 642.8404 | 0
| 305 | 16.235 | 215.4983 | 684.5017 | 0
| 306 | 14.1677 | 343.4354 | 556.5646 | 0
| 307 | 11.5428 | 142.5429 | 757.4571 | 0
| 308 | 10.7239 | 239.3418 | 660.6582 | 0
| 309 | 31.42 | -266.122 | 763.5228 | 402.5992
| 310 | 12.0762 | -168.5091 | 1068.5091 | 0
| 311 | 12.635 | 128.229 | 771.771 | 0
| 312 | 24.8108 | -293.1698 | 988.8467 | 204.3231
| 313 | 16.3428 | 225.9559 | 674.0441 | 0
| 314 | 32.2931 | -274.0156 | 745.2219 | 428.7937
| 315 | 31.9975 | -53.9807 | 534.0547 | 419.926
| 316 | 16.0076 | 128.1501 | 771.8499 | 0
| 317 | 20.2382 | -217.3548 | 1050.2081 | 67.1466
| 318 | 11.9683 | 11.8014 | 888.1986 | 0
| 319 | 20.2382 | 36.18 | 796.6734 | 67.1466
| 320 | 16.3428 | -154.1937 | 1054.1937 | 0
| 321 | 13.9899 | 296.3759 | 603.6241 | 0
| 322 | 17.3206 | -233.8695 | 1133.8695 | 0
| 323 | 20.9154 | -282.1926 | 1094.7307 | 87.4619
| 324 | 20.2382 | -217.3548 | 1050.2081 | 67.1466
| 325 | 20.2382 | 84.5467 | 748.3067 | 67.1466
| 326 | 16.3428 | 167.4453 | 732.5547 | 0
| 327 | 40.2674 | -385.7384 | 617.7161 | 668.0223
| 328 | 21.4853 | 241.4914 | 553.9502 | 104.5584
| 329 | 16.3428 | 18.4234 | 881.5766 | 0
| 330 | 20.8076 | -13.594 | 829.3672 | 84.2268
| 331 | 16.3428 | 205.3544 | 694.6456 | 0
| 332 | 24.8677 | -183.2808 | 877.25 | 206.0307
| 333 | 16.2821 | 285.9182 | 614.0818 | 0
| 334 | 24.0232 | -59.9067 | 779.2093 | 180.6974
| 335 | 24.8108 | -227.8093 | 923.4862 | 204.3231
| 336 | 19.3651 | 213.6779 | 645.3699 | 40.9521
| 337 | 31.572 | -28.1437 | 520.9826 | 407.1611
| 338 | 15.0642 | -16.4137 | 916.4137 | 0
| 339 | 32.2931 | -385.1284 | 856.3347 | 428.7937
| 340 | 40.2674 | -353.0582 | 585.0359 | 668.0223
| 341 | 20.0009 | -13.3805 | 853.3538 | 60.0267
| 342 | 11.4642 | 135.2226 | 764.7774 | 0
| 343 | 16.1498 | 38.4891 | 861.5109 | 0
| 344 | 36.2642 | -351.918 | 703.992 | 547.926
| 345 | 20.2382 | 7.4213 | 825.432 | 67.1466
| 346 | 12.6821 | 313.3696 | 586.6304 | 0
| 347 | 19.0674 | 152.8743 | 715.1034 | 32.0223
| 348 | 16.235 | 48.4892 | 851.5108 | 0
| 349 | 19.8931 | 185.9361 | 657.2724 | 56.7915
| 350 | 40.2674 | -381.8168 | 613.7945 | 668.0223
| 351 | 16.235 | -299.23 | 1199.23 | 0
| 352 | 20.2382 | 88.22 | 744.6334 | 67.1466
| 353 | 16.3428 | -512.3896 | 1412.3896 | 0
| 354 | 40.2674 | -545.218 | 777.1957 | 668.0223
| 355 | 20.2382 | 156.5087 | 676.3447 | 67.1466
| 356 | 36.372 | -646.6608 | 995.4997 | 551.1611
| 357 | 13.8821 | 244.0875 | 655.9125 | 0
| 358 | 40.2674 | -609.2712 | 841.249 | 668.0223
| 359 | 11.5428 | 199.8117 | 700.1883 | 0
| 360 | 18.1943 | 176.4544 | 717.7178 | 5.8278
| 361 | 15.2009 | 207.433 | 692.567 | 0
| 362 | 11.572 | 136.5298 | 763.4702 | 0
| 363 | 16.235 | -107.0702 | 1007.0702 | 0
| 364 | 23.8963 | 27.9307 | 695.1815 | 176.8878
| 365 | 20.2382 | 34.6244 | 798.229 | 67.1466
| 366 | 11.4642 | 190.1254 | 709.8746 | 0
| 367 | 15.0642 | 190.1254 | 709.8746 | 0
| 368 | 31.572 | -73.8961 | 566.7349 | 407.1611
| 369 | 40.2674 | -334.7572 | 566.7349 | 668.0223
| 370 | 23.8963 | -63.5739 | 786.6861 | 176.8878
| 371 | 20.8076 | -104.2131 | 919.9862 | 84.2268
| 372 | 11.5428 | -44.3241 | 944.3241 | 0
| 373 | 31.9975 | -94.5042 | 574.5782 | 419.926
| 374 | 16.3428 | 63.8619 | 836.1381 | 0
| 375 | 16.3428 | -246.9416 | 1146.9416 | 0
| 376 | 15.1428 | -164.5874 | 1064.5874 | 0
| 377 | 20.2382 | 67.3046 | 765.5487 | 67.1466
| 378 | 16.3428 | -299.23 | 1199.23 | 0
| 379 | 13.8642 | 178.3605 | 721.6395 | 0
| 380 | 32.2931 | -450.4888 | 921.6952 | 428.7937
| 381 | 16.235 | 12.8808 | 887.1192 | 0
| 382 | 17.3206 | 71.7052 | 828.2948 | 0
| 383 | 17.7461 | -114.9135 | 1014.9135 | 0
| 384 | 18.1943 | 230.05 | 664.1222 | 5.8278
| 385 | 37.7753 | -203.7843 | 510.5249 | 593.2593
| 386 | 32.2931 | -331.5328 | 802.7391 | 428.7937
| 387 | 16.3428 | 125.3008 | 774.6992 | 0
| 388 | 20.2382 | -178.1385 | 1010.9918 | 67.1466
| 389 | 20.6121 | 288.6013 | 533.0348 | 78.3639
| 390 | 13.8642 | 122.1505 | 777.8495 | 0
| 391 | 20.2382 | -1.9775 | 834.8308 | 67.1466
| 392 | 16.5753 | 229.3417 | 670.6583 | 0
| 393 | 15.172 | 209.7336 | 690.2664 | 0
| 394 | 18.5677 | 319.8688 | 563.1006 | 17.0306
| 395 | 40.2674 | -418.4186 | 650.3964 | 668.0223
| 396 | 16.235 | -97.0326 | 997.0326 | 0
| 397 | 32.772 | -167.4978 | 624.3366 | 443.1611
| 398 | 17.2128 | -74.39 | 974.39 | 0
| 399 | 13.9428 | -120.1423 | 1020.1423 | 0
| 400 | 16.235 | 244.5707 | 655.4293 | 0
| 401 | 20.2382 | -272.2576 | 1105.1109 | 67.1466
| 402 | 15.7342 | 234.8844 | 665.1156 | 0
| 403 | 10.7239 | 239.3418 | 660.6582 | 0
| 404 | 17.7461 | -33.8665 | 933.8665 | 0
| 405 | 12.7899 | 400.9526 | 499.0474 | 0
| 406 | 32.2931 | -607.354 | 1078.5603 | 428.7937
| 407 | 16.0076 | 117.6924 | 782.3076 | 0
| 408 | 21.4853 | 186.5886 | 608.853 | 104.5584
| 409 | 40.2674 | -307.3058 | 539.2835 | 668.0223
| 410 | 25.8899 | -162.9663 | 826.2689 | 236.6974
| 411 | 17.4931 | 100.2418 | 799.7582 | 0
| 412 | 20.2382 | 135.2795 | 697.5738 | 67.1466
| 413 | 16.3428 | 49.7965 | 850.2035 | 0
| 414 | 20.2382 | 138.1423 | 694.7111 | 67.1466
| 415 | 20.2382 | 110.7564 | 722.097 | 67.1466
| 416 | 11.7461 | -51.0086 | 951.0086 | 0
| 417 | 16.3428 | -70.5323 | 970.5323 | 0
| 418 | 24.8108 | -263.104 | 958.7809 | 204.3231
| 419 | 16.235 | 45.4532 | 854.5468 | 0
| 420 | 20.2382 | -90.5539 | 923.4073 | 67.1466
| 421 | 25.8899 | -162.9663 | 826.2689 | 236.6974
| 422 | 24.8108 | -434.3485 | 1130.0254 | 204.3231
| 423 | 11.0642 | -154.0923 | 1054.0923 | 0
| 424 | 16.3428 | 167.4453 | 732.5547 | 0
| 425 | 20.2382 | -242.1917 | 1075.0451 | 67.1466
| 426 | 19.2572 | 168.6308 | 693.6522 | 37.717
| 427 | 10.9054 | 284.2445 | 615.7555 | 0
| 428 | 17.5899 | 231.0154 | 668.9846 | 0
| 429 | 16.3428 | -23.4073 | 923.4073 | 0
| 430 | 37.7753 | -203.7843 | 510.5249 | 593.2593
| 431 | 12.0762 | 220.6193 | 679.3807 | 0
| 432 | 17.2076 | -10.4141 | 910.4141 | 0
| 433 | 19.0674 | 162.0248 | 705.9529 | 32.0223
| 434 | 32.2931 | -391.6644 | 862.8707 | 428.7937
| 435 | 17.2076 | -10.4141 | 910.4141 | 0
| 436 | 19.3651 | 53.2894 | 805.7584 | 40.9521
| 437 | 20.9154 | -171.0798 | 983.6179 | 87.4619
| 438 | 28.3978 | -154.54 | 742.6074 | 311.9325
| 439 | 13.9899 | 323.8273 | 576.1727 | 0
| 440 | 37.8831 | -369.1134 | 672.6189 | 596.4945
| 441 | 16.3428 | 201.119 | 698.881 | 0
| 442 | 17.7461 | 196.1385 | 703.8615 | 0
| 443 | 19.0674 | 130.6517 | 737.326 | 32.0223
| 444 | 23.9376 | -108.803 | 830.6744 | 178.1286
| 445 | 10.7239 | 277.2509 | 622.7491 | 0
| 446 | 23.5978 | -66.75 | 798.8175 | 167.9325
| 447 | 20.9787 | -152.6039 | 963.2439 | 89.36
| 448 | 32.2642 | -462.4085 | 934.4825 | 427.926
| 449 | 24.8108 | -146.7623 | 842.4392 | 204.3231
| 450 | 23.8963 | -108.0191 | 831.1312 | 176.8878
| 451 | 16.3428 | -112.299 | 1012.299 | 0
| 452 | 21.7853 | -181.4915 | 967.9314 | 113.5602
| 453 | 17.4821 | 89.8367 | 810.1633 | 0
| 454 | 11.9683 | -32.0704 | 932.0704 | 0
| 455 | 23.8963 | -40.0442 | 763.1563 | 176.8878
| 456 | 13.9428 | 47.1166 | 852.8834 | 0
| 457 | 24.8108 | -234.3454 | 930.0223 | 204.3231
| 458 | 16.3428 | -482.3238 | 1382.3238 | 0
| 459 | 11.9683 | -26.0232 | 926.0232 | 0
| 460 | 16.3428 | 31.4955 | 868.5045 | 0
| 461 | 20.2382 | 28.0883 | 804.765 | 67.1466
| 462 | 40.2674 | -380.5096 | 612.4873 | 668.0223
| 463 | 29.801 | -331.2808 | 877.25 | 354.0307
| 464 | 17.854 | 234.113 | 665.887 | 0
| 465 | 19.0674 | 199.9339 | 668.0439 | 32.0223
| 466 | 23.8963 | 4.401 | 718.7112 | 176.8878
| 467 | 13.9428 | 211.5766 | 688.4234 | 0
| 468 | 16.3428 | -277.0075 | 1177.0075 | 0
| 469 | 31.42 | -304.0311 | 801.4319 | 402.5992
| 470 | 32.772 | -317.7424 | 774.5813 | 443.1611
| 471 | 17.7461 | 105.941 | 794.059 | 0
| 472 | 18.0864 | 195.376 | 702.0313 | 2.5927
| 473 | 13.972 | 199.1914 | 700.8086 | 0
| 474 | 23.0231 | 14.9089 | 734.3977 | 150.6933
| 475 | 36.372 | -193.1435 | 541.9824 | 551.1611
| 476 | 32.2931 | -394.2788 | 865.4851 | 428.7937
| 477 | 31.7753 | -350.6711 | 837.4118 | 413.2593
| 478 | 16.3428 | 215.4983 | 684.5017 | 0
| 479 | 21.4042 | 122.3018 | 675.5733 | 102.1249
| 480 | 21.512 | 126.91 | 667.73 | 105.36
| 481 | 12.7428 | -84.8476 | 984.8476 | 0
| 482 | 15.035 | -174.2235 | 1074.2235 | 0
| 483 | 40.2674 | -409.2682 | 641.2459 | 668.0223
| 484 | 11.854 | -328.4102 | 1228.4102 | 0
| 485 | 20.2382 | 39.8532 | 793.0001 | 67.1466
| 486 | 15.172 | 175.7461 | 724.2539 | 0
| 487 | 16.235 | 198.3313 | 701.6687 | 0
| 488 | 16.3428 | 3.7303 | 896.2697 | 0
| 489 | 16.3428 | -360.6689 | 1260.6689 | 0
| 490 | 13.3232 | 364.3508 | 535.6492 | 0
| 491 | 17.5899 | 80.6863 | 819.3137 | 0
| 492 | 24.8108 | -187.2858 | 882.9627 | 204.3231
| 493 | 21.4853 | 140.8363 | 654.6053 | 104.5584
| 494 | 17.6009 | 232.27 | 667.73 | 0
| 495 | 22.9153 | 57.3604 | 695.1815 | 147.4582
| 496 | 19.3651 | 113.1073 | 745.9406 | 40.9521
| 497 | 24.1311 | 37.0917 | 678.9758 | 183.9325
| 498 | 24.1311 | -135.0384 | 851.1058 | 183.9325
| 499 | 23.8963 | 7.0154 | 716.0968 | 176.8878
| 500 | 24.1311 | -34.4677 | 750.5352 | 183.9325
| 501 | 13.2154 | 72.4214 | 827.5786 | 0
| 502 | 24.6899 | -77.2923 | 776.5949 | 200.6974
| 503 | 20.8076 | -0.52187 | 816.2951 | 84.2268
| 504 | 11.172 | 156.138 | 743.862 | 0
| 505 | 12.3428 | 104.6338 | 795.3662 | 0
| 506 | 35.172 | -529.6983 | 914.5371 | 515.1611
| 507 | 28.2899 | -216.6653 | 807.9679 | 308.6974
| 508 | 15.172 | -2.0344 | 902.0344 | 0
| 509 | 16.235 | 71.9536 | 828.0464 | 0
| 510 | 13.835 | -107.8041 | 1007.8041 | 0
| 511 | 16.235 | -49.553 | 949.553 | 0
| 512 | 24.0232 | 48.5072 | 670.7954 | 180.6974
| 513 | 20.2382 | -6.958 | 839.8113 | 67.1466
| 514 | 16.235 | -33.865 | 933.865 | 0
| 515 | 20.2382 | 95.0044 | 737.849 | 67.1466
| 516 | 29.9089 | -291.378 | 834.1121 | 357.2659
| 517 | 15.6264 | 255.7153 | 644.2847 | 0
| 518 | 17.7461 | 193.524 | 706.476 | 0
| 519 | 13.972 | 139.1443 | 760.8557 | 0
| 520 | 18.0864 | -59.9515 | 957.3588 | 2.5927
| 521 | 18.5154 | 47.3276 | 837.2104 | 15.4619
| 522 | 19.7154 | -90.6347 | 939.1728 | 51.4619
| 523 | 24.8108 | -225.1949 | 920.8718 | 204.3231
| 524 | 15.035 | 40.646 | 859.354 | 0
| 525 | 24.7978 | -194.2547 | 890.3221 | 203.9325
| 526 | 10.235 | 286.4014 | 613.5986 | 0
| 527 | 20.2382 | 48.0103 | 784.8431 | 67.1466
| 528 | 30.372 | -35.2817 | 564.1205 | 371.1611
| 529 | 11.572 | 209.7336 | 690.2664 | 0
| 530 | 37.8831 | -235.778 | 539.2835 | 596.4945
| 531 | 18.6931 | 138.2747 | 740.9338 | 20.7915
| 532 | 20.2382 | -240.8845 | 1073.7379 | 67.1466
| 533 | 17.5899 | 281.9966 | 618.0034 | 0
| 534 | 19.6076 | -62.5626 | 914.3358 | 48.2268
| 535 | 28.2899 | -257.1888 | 848.4914 | 308.6974
| 536 | 16.3428 | 99.405 | 800.595 | 0
| 537 | 20.9154 | -265.1989 | 1077.737 | 87.4619
| 538 | 21.4853 | 163.0589 | 632.3828 | 104.5584
| 539 | 12.772 | 80.3198 | 819.6802 | 0
| 540 | 11.854 | -54.2085 | 954.2085 | 0
| 541 | 17.2128 | 141.3011 | 758.6989 | 0
| 542 | 15.172 | 79.0126 | 820.9874 | 0
| 543 | 16.9154 | 26.1877 | 873.8123 | 0
| 544 | 16.235 | 42.9466 | 857.0534 | 0
| 545 | 23.8963 | 3.0938 | 720.0184 | 176.8878
| 546 | 23.9376 | -33.0693 | 754.9407 | 178.1286
| 547 | 16.3428 | -73.0828 | 973.0828 | 0
| 548 | 16.3428 | 104.6338 | 795.3662 | 0
| 549 | 16.235 | 175.2231 | 724.7769 | 0
| 550 | 19.2572 | 161.1013 | 701.1817 | 37.717
| 551 | 10.7975 | 314.2259 | 585.7741 | 0
| 552 | 16.3187 | -154.2917 | 1054.2917 | 0
| 553 | 28.2899 | -610.557 | 1201.8596 | 308.6974
| 554 | 13.9428 | 77.1824 | 822.8176 | 0
| 555 | 25.9978 | -163.587 | 823.6544 | 239.9325
| 556 | 13.835 | 126.8564 | 773.1436 | 0
| 557 | 11.7498 | 199.2759 | 700.7241 | 0
| 558 | 10.7975 | 187.511 | 712.489 | 0
| 559 | 20.2382 | -15.0496 | 847.9029 | 67.1466
| 560 | 12.0762 | -74.8116 | 974.8116 | 0
| 561 | 19.2572 | -135.6368 | 997.9197 | 37.717
| 562 | 16.4009 | -157.363 | 1057.363 | 0
| 563 | 21.4853 | 84.6263 | 710.8153 | 104.5584
| 564 | 13.835 | 47.1166 | 852.8834 | 0
| 565 | 20.2382 | -128.5285 | 961.3818 | 67.1466
| 566 | 16.3428 | 23.6523 | 876.3477 | 0
| 567 | 20.2382 | 59.7752 | 773.0782 | 67.1466
| 568 | 16.2931 | -164.2362 | 1064.2362 | 0
| 569 | 15.035 | -174.2235 | 1074.2235 | 0
| 570 | 12.7428 | -27.3944 | 927.3944 | 0
| 571 | 16.3428 | -9.0934 | 909.0934 | 0
| 572 | 17.4821 | 194.4135 | 705.5865 | 0
| 573 | 17.2128 | 121.3792 | 778.6208 | 0
| 574 | 17.2128 | 121.3792 | 778.6208 | 0
| 575 | 28.2899 | -291.1763 | 882.4789 | 308.6974
| 576 | 11.9683 | -168.5091 | 1068.5091 | 0
| 577 | 12.0762 | 241.2208 | 658.7792 | 0
| 578 | 24.1311 | -367.8061 | 1083.8736 | 183.9325
| 579 | 16.235 | -53.7869 | 953.7869 | 0
| 580 | 36.372 | -413.9775 | 762.8164 | 551.1611
| 581 | 20.8076 | -84.1833 | 899.9565 | 84.2268
| 582 | 16.235 | 144.9089 | 755.0911 | 0
| 583 | 32.2931 | -355.0625 | 826.2689 | 428.7937
| 584 | 29.9089 | -240.3968 | 783.1309 | 357.2659
| 585 | 16.235 | -4.113 | 904.113 | 0
| 586 | 32.772 | -145.1907 | 602.0296 | 443.1611
| 587 | 15.172 | 174.4389 | 725.5611 | 0
| 588 | 20.2382 | -161.2087 | 994.0621 | 67.1466
| 589 | 15.1428 | 142.6083 | 757.3917 | 0
| 590 | 16.3428 | 166.1381 | 733.8619 | 0
| 591 | 16.3428 | -224.7191 | 1124.7191 | 0
| 592 | 24.8677 | -93.0833 | 787.0526 | 206.0307
| 593 | 20.2382 | 100.2987 | 732.5547 | 67.1466
| 594 | 15.1428 | 151.445 | 748.555 | 0
| 595 | 15.0642 | 218.884 | 681.116 | 0
| 596 | 16.235 | 170.0597 | 729.9403 | 0
| 597 | 17.2128 | -233.8695 | 1133.8695 | 0
| 598 | 13.972 | 169.2101 | 730.7899 | 0
| 599 | 21.4042 | 158.9037 | 638.9714 | 102.1249
| 600 | 20.2382 | 51.8665 | 780.9869 | 67.1466
| 601 | 20.2382 | -64.7235 | 897.5769 | 67.1466
| 602 | 20.2382 | -22.6445 | 855.4978 | 67.1466
| 603 | 36.2642 | -530.1201 | 882.1941 | 547.926
| 604 | 18.5154 | 86.5439 | 797.9941 | 15.4619
| 605 | 19.8931 | 99.6603 | 743.5482 | 56.7915
| 606 | 15.172 | 173.1317 | 726.8683 | 0
| 607 | 23.9376 | -170.2418 | 892.1132 | 178.1286
| 608 | 23.8963 | -108.0191 | 831.1312 | 176.8878
| 609 | 20.9154 | -237.7475 | 1050.2856 | 87.4619
| 610 | 20.2382 | 122.5212 | 710.3321 | 67.1466
| 611 | 19.6076 | -167.1394 | 1018.9125 | 48.2268
| 612 | 16.235 | 122.6864 | 777.3136 | 0
| 613 | 12.7428 | 97.8494 | 802.1506 | 0
| 614 | 12.635 | 59.9403 | 840.0597 | 0
| 615 | 21.4853 | 112.0777 | 683.3639 | 104.5584
| 616 | 28.2899 | -233.6591 | 824.9616 | 308.6974
| 617 | 20.9154 | -15.5219 | 828.0599 | 87.4619
| 618 | 22.9153 | 108.3415 | 644.2003 | 147.4582
| 619 | 20.2382 | 75.3962 | 757.4571 | 67.1466
| 620 | 20.8076 | -150.851 | 966.6242 | 84.2268
| 621 | 13.9899 | 164.3477 | 735.6523 | 0
| 622 | 16.235 | -316.2237 | 1216.2237 | 0
| 623 | 30.2642 | 8.477 | 523.597 | 367.926
| 624 | 35.172 | -272.0935 | 656.9324 | 515.1611
| 625 | 13.101 | 82.8791 | 817.1209 | 0
| 626 | 19.3651 | 137.9442 | 721.1036 | 40.9521
| 627 | 16.235 | -99.7125 | 999.7125 | 0
| 628 | 20.2382 | 105.2137 | 727.6397 | 67.1466
| 629 | 15.0642 | 102.5424 | 797.4576 | 0
| 630 | 12.6642 | 231.9561 | 668.0439 | 0
| 631 | 20.2382 | -260.4927 | 1093.346 | 67.1466
| 632 | 21.4853 | 161.7516 | 633.69 | 104.5584
| 633 | 16.4009 | 157.759 | 742.241 | 0
| 634 | 21.4042 | 131.4523 | 666.4228 | 102.1249
| 635 | 16.3428 | 225.9559 | 674.0441 | 0
| 636 | 12.0762 | 159.2882 | 740.7118 | 0
| 637 | 16.6487 | 68.0184 | 831.9816 | 0
| 638 | 19.3651 | 170.9383 | 688.1096 | 40.9521
| 639 | 18.5154 | 86.5439 | 797.9941 | 15.4619
| 640 | 28.2899 | -340.8502 | 932.1528 | 308.6974
| 641 | 16.3428 | -246.9416 | 1146.9416 | 0
| 642 | 28.2899 | -216.6653 | 807.9679 | 308.6974
| 643 | 18.4076 | 10.0393 | 877.7339 | 12.2268
| 644 | 15.1428 | 90.3199 | 809.6801 | 0
| 645 | 20.0009 | 133.027 | 706.9463 | 60.0267
| 646 | 19.0674 | -92.8811 | 960.8588 | 32.0223
| 647 | 10.3428 | 223.5899 | 676.4101 | 0
| 648 | 10.3428 | 228.5704 | 671.4296 | 0
| 649 | 20.2382 | 95.0044 | 737.849 | 67.1466
| 650 | 20.5043 | 251.3129 | 573.5583 | 75.1288
| 651 | 16.235 | 30.1883 | 869.8117 | 0
| 652 | 20.2382 | -21.3373 | 854.1906 | 67.1466
| 653 | 12.0762 | -307.5793 | 1207.5793 | 0
| 654 | 17.854 | 236.662 | 663.338 | 0
| 655 | 20.2382 | 36.18 | 796.6734 | 67.1466
| 656 | 11.572 | 133.9154 | 766.0846 | 0
| 657 | 18.5154 | 107.3748 | 777.1632 | 15.4619
| 658 | 16.3428 | -163.2802 | 1063.2802 | 0
| 659 | 17.3853 | 100.6987 | 799.3013 | 0
| 660 | 18.4598 | 294.3453 | 591.8593 | 13.7954
| 661 | 40.2674 | -499.4656 | 731.4434 | 668.0223
| 662 | 19.7154 | -50.1112 | 898.6493 | 51.4619
| 663 | 16.5409 | 120.3068 | 779.6932 | 0
| 664 | 40.2674 | -462.8638 | 694.8415 | 668.0223
| 665 | 17.5899 | -44.8058 | 944.8058 | 0
| 666 | 12.8128 | 222.3481 | 677.6519 | 0
| 667 | 11.642 | 229.3417 | 670.6583 | 0
| 668 | 24.7978 | -81.8346 | 777.9021 | 203.9325
| 669 | 18.8009 | 94.5161 | 781.4573 | 24.0267
| 670 | 28.2899 | -293.7907 | 885.0933 | 308.6974
| 671 | 16.235 | 134.4513 | 765.5487 | 0
| 672 | 12.635 | 183.0664 | 716.9336 | 0
| 673 | 16.2821 | 284.611 | 615.389 | 0
| 674 | 20.2382 | 85.9194 | 746.934 | 67.1466
| 675 | 20.2382 | -17.664 | 850.5174 | 67.1466
| 676 | 19.0674 | 130.6517 | 737.326 | 32.0223
| 677 | 20.9154 | -237.7475 | 1050.2856 | 87.4619
| 678 | 17.854 | 231.1848 | 668.8152 | 0
| 679 | 15.0821 | 306.8335 | 593.1665 | 0
| 680 | 20.8076 | -204.4466 | 1020.2198 | 84.2268
| 681 | 23.8963 | 7.0154 | 716.0968 | 176.8878
| 682 | 12.8128 | 125.5491 | 774.4509 | 0
| 683 | 12.0762 | -127.9856 | 1027.9856 | 0
| 684 | 23.8298 | -116.0255 | 841.132 | 174.8935
| 685 | 16.042 | 152.2164 | 747.7836 | 0
| 686 | 20.2382 | -51.4031 | 884.2565 | 67.1466
| 687 | 16.3428 | -23.4073 | 923.4073 | 0
| 688 | 16.3428 | 9.273 | 890.727 | 0
| 689 | 20.2382 | -26.5006 | 859.354 | 67.1466
| 690 | 12.8128 | 130.5296 | 769.4704 | 0
| 691 | 17.4821 | 281.9966 | 618.0034 | 0
| 692 | 40.2674 | -455.0205 | 686.9982 | 668.0223
| 693 | 23.8963 | -92.3325 | 815.4447 | 176.8878
| 694 | 16.1154 | 128.1501 | 771.8499 | 0
| 695 | 16.6487 | 139.915 | 760.085 | 0
| 696 | 28.2899 | -356.5368 | 947.8393 | 308.6974
| 697 | 16.235 | -135.0072 | 1035.0072 | 0
| 698 | 16.3428 | -186.8929 | 1086.8929 | 0
| 699 | 40.2674 | -308.613 | 540.5908 | 668.0223
| 700 | 18.4598 | 282.5804 | 603.6241 | 13.7954
| 701 | 15.0642 | 230.6489 | 669.3511 | 0
| 702 | 24.8108 | -243.4959 | 939.1728 | 204.3231
| 703 | 15.172 | 56.7901 | 843.2099 | 0
| 704 | 36.372 | -187.8303 | 536.6691 | 551.1611
| 705 | 15.035 | -111.4135 | 1011.4135 | 0
| 706 | 20.2382 | 79.0695 | 753.7839 | 67.1466
| 707 | 31.572 | -21.6077 | 514.4466 | 407.1611
| 708 | 36.372 | -212.6672 | 561.5061 | 551.1611
| 709 | 12.9206 | 231.1003 | 668.8997 | 0
| 710 | 12.0762 | 202.5901 | 697.4099 | 0
| 711 | 10.8317 | 270.7149 | 629.2851 | 0
| 712 | 24.7978 | -162.8816 | 858.9491 | 203.9325
| 713 | 21.7853 | -23.3192 | 809.759 | 113.5602
| 714 | 19.0674 | 181.6329 | 686.3448 | 32.0223
| 715 | 20.8076 | -46.2742 | 862.0474 | 84.2268
| 716 | 17.4821 | 329.0561 | 570.9439 | 0
| 717 | 29.801 | -211.0175 | 756.9867 | 354.0307
| 718 | 11.5899 | 360.4291 | 539.5709 | 0
| 719 | 17.5899 | 194.4135 | 705.5865 | 0
| 720 | 28.3978 | -260.424 | 848.4914 | 311.9325
| 721 | 32.1054 | -116.0403 | 592.8791 | 423.1611
| 722 | 20.2382 | -15.0496 | 847.9029 | 67.1466
| 723 | 21.4853 | 214.04 | 581.4016 | 104.5584
| 724 | 16.235 | -341.0607 | 1241.0607 | 0
| 725 | 13.9428 | 179.1447 | 720.8553 | 0
| 726 | 22.9153 | 107.0343 | 645.5075 | 147.4582
| 727 | 16.235 | 76.934 | 823.066 | 0
| 728 | 15.1428 | 168.7525 | 731.2475 | 0
| 729 | 19.8931 | -32.3679 | 875.5764 | 56.7915
| 730 | 12.0762 | -168.5091 | 1068.5091 | 0
| 731 | 15.6264 | 266.2574 | 633.7426 | 0
| 732 | 18.4076 | 89.7791 | 797.9941 | 12.2268
| 733 | 16.235 | 92.9344 | 807.0656 | 0
| 734 | 12.9932 | 89.7523 | 810.2477 | 0
| 735 | 21.4853 | 4.8865 | 790.5551 | 104.5584
| 736 | 16.3428 | -45.6298 | 945.6298 | 0
| 737 | 15.172 | 222.8057 | 677.1943 | 0
| 738 | 15.035 | 110.9215 | 789.0785 | 0
| 739 | 20.2382 | -30.7361 | 863.5895 | 67.1466
| 740 | 16.3428 | 210.5178 | 689.4822 | 0
| 741 | 11.435 | 231.1848 | 668.8152 | 0
| 742 | 12.7428 | 200.1256 | 699.8744 | 0
| 743 | 16.5409 | 169.8963 | 730.1037 | 0
| 744 | 19.0674 | 198.6266 | 669.3511 | 32.0223
| 745 | 16.3428 | 218.361 | 681.639 | 0
| 746 | 17.3154 | -3.8781 | 903.8781 | 0
| 747 | 16.3899 | 275.4605 | 624.5395 | 0
| 748 | 15.0642 | 133.9154 | 766.0846 | 0
| 749 | 12.235 | 117.7713 | 782.2287 | 0
| 750 | 37.8831 | -263.2294 | 566.7349 | 596.4945
| 751 | 23.8298 | -49.3578 | 774.4643 | 174.8935
| 752 | 19.8931 | 80.9377 | 762.2708 | 56.7915
| 753 | 20.8076 | -127.3212 | 943.0944 | 84.2268
| 754 | 37.8831 | -235.778 | 539.2835 | 596.4945
| 755 | 20.5043 | 236.9336 | 587.9376 | 75.1288
| 756 | 23.0231 | 14.9089 | 734.3977 | 150.6933
| 757 | 20.2382 | -196.4394 | 1029.2928 | 67.1466
| 758 | 19.8931 | 216.0019 | 627.2066 | 56.7915
| 759 | 15.172 | 60.6272 | 839.3728 | 0
| 760 | 18.9932 | 25.6322 | 844.5723 | 29.7954
| 761 | 20.2382 | -46.4226 | 879.276 | 67.1466
| 762 | 20.8076 | -43.6598 | 859.433 | 84.2268
| 763 | 16.3428 | 164.8309 | 735.1691 | 0
| 764 | 20.8076 | -0.52187 | 816.2951 | 84.2268
| 765 | 23.8963 | -71.4172 | 794.5294 | 176.8878
| 766 | 11.9683 | -42.1298 | 942.1298 | 0
| 767 | 29.801 | -211.0175 | 756.9867 | 354.0307
| 768 | 21.7853 | -31.1624 | 817.6023 | 113.5602
| 769 | 19.8931 | 12.0772 | 831.1312 | 56.7915
| 770 | 17.4821 | 241.4731 | 658.5269 | 0
| 771 | 11.5428 | -9.0295 | 909.0295 | 0
| 772 | 32.6642 | -102.7393 | 562.8133 | 439.926
| 773 | 13.9899 | 296.3759 | 603.6241 | 0
| 774 | 24.8108 | -340.2294 | 1035.9063 | 204.3231
| 775 | 27.0899 | -260.4051 | 887.7077 | 272.6974
| 776 | 15.172 | 133.9154 | 766.0846 | 0
| 777 | 20.9154 | -344.9387 | 1157.4768 | 87.4619
| 778 | 13.9899 | 314.6768 | 585.3232 | 0
| 779 | 17.854 | 226.2043 | 673.7957 | 0
| 780 | 13.9428 | 210.2694 | 689.7306 | 0
| 781 | 20.0009 | -97.0419 | 937.0152 | 60.0267
| 782 | 17.3154 | -79.6963 | 979.6963 | 0
| 783 | 12.635 | -135.0072 | 1035.0072 | 0
| 784 | 19.3651 | 178.7161 | 680.3318 | 40.9521
| 785 | 16.235 | 117.7713 | 782.2287 | 0
| 786 | 17.7461 | 258.95 | 641.05 | 0
| 787 | 19.2572 | -103.3766 | 965.6596 | 37.717
| 788 | 20.2382 | -16.3568 | 849.2102 | 67.1466
| 789 | 28.2899 | -390.5242 | 981.8268 | 308.6974
| 790 | 20.2382 | -321.9315 | 1154.7849 | 67.1466
| 791 | 16.5753 | 152.2164 | 747.7836 | 0
| 792 | 23.9376 | -131.0255 | 852.8969 | 178.1286
| 793 | 11.9683 | 288.6175 | 611.3825 | 0
| 794 | 21.4042 | 56.9414 | 740.9338 | 102.1249
| 795 | 16.3428 | 61.4959 | 838.5041 | 0
| 796 | 15.172 | 175.7461 | 724.2539 | 0
| 797 | 17.3206 | 71.7052 | 828.2948 | 0
| 798 | 28.3978 | -371.5368 | 959.6042 | 311.9325
| 799 | 17.7461 | -164.5874 | 1064.5874 | 0
| 800 | 23.0231 | 92.0343 | 657.2724 | 150.6933
| 801 | 10.8317 | 270.7149 | 629.2851 | 0
| 802 | 28.2899 | -178.7563 | 770.0588 | 308.6974
| 803 | 10.2642 | 175.7461 | 724.2539 | 0
| 804 | 19.0674 | 207.7771 | 660.2006 | 32.0223
| 805 | 31.572 | -111.8052 | 604.644 | 407.1611
| 806 | 16.6487 | -141.6412 | 1041.6412 | 0
| 807 | 16.235 | -130.6 | 1030.6 | 0
| 808 | 12.9206 | 173.9814 | 726.0186 | 0
| 809 | 15.0642 | 173.1317 | 726.8683 | 0
| 810 | 32.772 | -133.4258 | 590.2647 | 443.1611
| 811 | 17.5899 | 296.3759 | 603.6241 | 0
| 812 | 31.572 | -0.69234 | 493.5312 | 407.1611
| 813 | 36.372 | -369.5324 | 718.3713 | 551.1611
| 814 | 16.5753 | -50.8228 | 950.8228 | 0
| 815 | 12.0762 | -87.4621 | 987.4621 | 0
| 816 | 20.0009 | -80.0482 | 920.0215 | 60.0267
| 817 | 19.2572 | 189.8599 | 672.423 | 37.717
| 818 | 20.8076 | -126.014 | 941.7872 | 84.2268
| 819 | 19.0674 | 74.4417 | 793.536 | 32.0223
| 820 | 13.9428 | -65.2395 | 965.2395 | 0
| 821 | 24.6899 | -78.5995 | 777.9021 | 200.6974
| 822 | 20.2382 | 23.1079 | 809.7455 | 67.1466
| 823 | 12.3428 | -137.136 | 1037.136 | 0
| 824 | 20.2382 | 164.352 | 668.5014 | 67.1466
| 825 | 11.9683 | -96.6125 | 996.6125 | 0
| 826 | 21.4853 | 82.0119 | 713.4297 | 104.5584
| 827 | 16.3428 | 189.6679 | 710.3321 | 0
| 828 | 17.5899 | 242.7803 | 657.2197 | 0
| 829 | 32.2931 | -481.8619 | 953.0682 | 428.7937
| 830 | 11.5428 | 180.4519 | 719.5481 | 0
| 831 | 20.9154 | -99.1833 | 911.7214 | 87.4619
| 832 | 17.4931 | 220.5051 | 679.4949 | 0
| 833 | 16.2931 | 127.6932 | 772.3068 | 0
| 834 | 13.4821 | 285.4966 | 614.5034 | 0
| 835 | 16.235 | -9.0934 | 909.0934 | 0
| 836 | 16.235 | 60.1887 | 839.8113 | 0
| 837 | 18.0864 | 258.1221 | 639.2852 | 2.5927
| 838 | 13.8642 | 179.6678 | 720.3322 | 0
| 839 | 11.572 | 140.4515 | 759.5485 | 0
| 840 | 23.8963 | 55.3821 | 667.73 | 176.8878
| 841 | 19.3651 | 166.7029 | 692.345 | 40.9521
| 842 | 20.6121 | 288.6013 | 533.0348 | 78.3639
| 843 | 17.4821 | 315.984 | 584.016 | 0
| 844 | 16.6831 | 289.3889 | 610.6111 | 0
| 845 | 17.854 | -347.6812 | 1247.6812 | 0
| 846 | 10.9054 | 258.1003 | 641.8997 | 0
| 847 | 23.8298 | -116.0255 | 841.132 | 174.8935
| 848 | 20.2382 | 64.6902 | 768.1632 | 67.1466
| 849 | 24.8677 | -133.6068 | 827.5761 | 206.0307
| 850 | 11.5428 | 257.6428 | 642.3572 | 0
| 851 | 13.9428 | 52.0971 | 847.9029 | 0
| 852 | 13.835 | 102.0848 | 797.9152 | 0
| 853 | 16.3428 | 106.0065 | 793.9935 | 0
| 854 | 16.235 | 190.6613 | 709.3387 | 0
| 855 | 15.172 | -208.6579 | 1108.6579 | 0
| 856 | 16.3428 | -210.3398 | 1110.3398 | 0
| 857 | 16.3428 | -113.6063 | 1013.6063 | 0
| 858 | 23.8963 | -26.9721 | 750.0843 | 176.8878
| 859 | 16.4009 | 78.0192 | 821.9808 | 0
| 860 | 20.0009 | 61.1305 | 778.8429 | 60.0267
| 861 | 19.2572 | 189.7945 | 672.4885 | 37.717
| 862 | 39.2864 | -284.4123 | 545.8196 | 638.5927
| 863 | 15.172 | 203.1975 | 696.8025 | 0
| 864 | 20.2382 | -247.4206 | 1080.2739 | 67.1466
| 865 | 16.3428 | 96.4577 | 803.5423 | 0
| 866 | 16.235 | 5.2859 | 894.7141 | 0
| 867 | 19.0674 | -60.2009 | 928.1786 | 32.0223
| 868 | 20.8708 | 3.6592 | 810.2159 | 86.1249
| 869 | 20.2382 | 100.2987 | 732.5547 | 67.1466
| 870 | 36.372 | -253.1907 | 602.0296 | 551.1611
| 871 | 12.9932 | 80.6018 | 819.3982 | 0
| 872 | 17.5899 | 295.0686 | 604.9314 | 0
| 873 | 13.835 | -120.1423 | 1020.1423 | 0
| 874 | 20.2382 | -178.1385 | 1010.9918 | 67.1466
| 875 | 12.0762 | 248.0052 | 651.9948 | 0
| 876 | 20.2382 | -200.7811 | 1033.6345 | 67.1466
| 877 | 16.235 | 89.5845 | 810.4155 | 0
| 878 | 20.0009 | -15.9949 | 855.9682 | 60.0267
| 879 | 24.8108 | -157.22 | 852.8969 | 204.3231
| 880 | 36.2642 | -218.5826 | 570.6566 | 547.926
| 881 | 17.3206 | 155.6804 | 744.3196 | 0
| 882 | 28.3978 | -435.59 | 1023.6575 | 311.9325
| 883 | 17.854 | 232.492 | 667.508 | 0
| 884 | 11.572 | 55.4828 | 844.5172 | 0
| 885 | 18.4598 | 312.6462 | 573.5583 | 13.7954
| 886 | 20.0009 | 156.5568 | 683.4166 | 60.0267
| 887 | 15.512 | -317.2641 | 1217.2641 | 0
| 888 | 16.235 | -163.2802 | 1063.2802 | 0
| 889 | 16.235 | 153.066 | 746.934 | 0
| 890 | 23.5978 | -14.4616 | 746.5291 | 167.9325
| 891 | 32.2931 | -511.9277 | 983.134 | 428.7937
| 892 | 24.7978 | -100.1356 | 796.203 | 203.9325
| 893 | 35.0642 | -343.3694 | 731.4434 | 511.926
| 894 | 24.9755 | -113.3122 | 804.0463 | 209.2659
| 895 | 20.0009 | -80.0482 | 920.0215 | 60.0267
| 896 | 37.242 | -308.0475 | 630.7882 | 577.2593
| 897 | 20.9154 | -52.1238 | 864.6618 | 87.4619
| 898 | 20.0009 | 181.3938 | 658.5796 | 60.0267
| 899 | 16.235 | 163.2099 | 736.7901 | 0
| 900 | 17.2128 | 156.9222 | 743.0778 | 0
| 901 | 21.4853 | 79.3974 | 716.0442 | 104.5584
| 902 | 32.2931 | -400.8149 | 872.0212 | 428.7937
| 903 | 20.2382 | 43.7749 | 789.0785 | 67.1466
| 904 | 17.5899 | 319.9056 | 580.0944 | 0
| 905 | 11.5428 | 106.9999 | 793.0001 | 0
| 906 | 37.8831 | -234.4708 | 537.9763 | 596.4945
| 907 | 16.3428 | 65.1692 | 834.8308 | 0
| 908 | 18.1943 | 228.7428 | 665.4294 | 5.8278
| 909 | 21.4853 | 115.9993 | 679.4423 | 104.5584
| 910 | 24.8108 | -141.5335 | 837.2104 | 204.3231
| 911 | 20.2382 | -235.6557 | 1068.5091 | 67.1466
| 912 | 21.4853 | 240.1842 | 555.2574 | 104.5584
| 913 | 23.0231 | -59.602 | 808.9087 | 150.6933
| 914 | 18.5154 | 87.8511 | 796.6869 | 15.4619
| 915 | 24.8108 | -280.0977 | 975.7746 | 204.3231
| 916 | 12.0762 | 248.1785 | 651.8215 | 0
| 917 | 37.242 | -283.2106 | 605.9512 | 577.2593
| 918 | 20.2382 | 131.6063 | 701.2471 | 67.1466
| 919 | 21.4853 | 4.8865 | 790.5551 | 104.5584
| 920 | 20.2382 | -176.8313 | 1009.6846 | 67.1466
| 921 | 21.4042 | -68.5508 | 866.4259 | 102.1249
| 922 | 17.4821 | 164.3477 | 735.6523 | 0
| 923 | 16.3428 | -454.788 | 1354.788 | 0
| 924 | 16.3428 | 180.5174 | 719.4826 | 0
| 925 | 19.0674 | 129.3445 | 738.6332 | 32.0223
| 926 | 11.7461 | -85.2444 | 985.2444 | 0
| 927 | 9.5531 | 285.5517 | 614.4483 | 0
| 928 | 12.9206 | -66.5467 | 966.5467 | 0
| 929 | 12.0762 | 180.4519 | 719.5481 | 0
| 930 | 32.2931 | -385.1284 | 856.3347 | 428.7937
| 931 | 12.8128 | 75.8752 | 824.1248 | 0
| 932 | 20.2382 | 29.6439 | 803.2095 | 67.1466
| 933 | 9.6609 | 279.0157 | 620.9843 | 0
| 934 | 24.6899 | -77.2923 | 776.5949 | 200.6974
| 935 | 15.1899 | 289.8398 | 610.1602 | 0
| 936 | 22.3187 | -253.7015 | 1024.1414 | 129.5602
| 937 | 12.8128 | 202.4262 | 697.5738 | 0
| 938 | 20.9154 | -280.8854 | 1093.4235 | 87.4619
| 939 | 15.6264 | 306.7809 | 593.2191 | 0
| 940 | 28.2899 | -420.59 | 1011.8926 | 308.6974
| 941 | 20.9154 | -35.13 | 847.6681 | 87.4619
| 942 | 12.0762 | 126.9218 | 773.0782 | 0
| 943 | 11.9683 | -67.9384 | 967.9384 | 0
| 944 | 15.1428 | 117.7059 | 782.2941 | 0
| 945 | 37.8831 | -216.1699 | 519.6754 | 596.4945
| 946 | 15.172 | 30.6459 | 869.3541 | 0
| 947 | 27.0899 | -260.4051 | 887.7077 | 272.6974
| 948 | 15.8931 | 105.4706 | 794.5294 | 0
| 949 | 23.8963 | 55.3821 | 667.73 | 176.8878
| 950 | 16.3428 | 184.3736 | 715.6264 | 0
| 951 | 16.0076 | 90.241 | 809.759 | 0
| 952 | 23.8963 | 27.9307 | 695.1815 | 176.8878
| 953 | 37.3498 | -347.8845 | 667.3901 | 580.4945
| 954 | 20.2382 | 85.9194 | 746.934 | 67.1466
| 955 | 15.0642 | 103.8496 | 796.1504 | 0
| 956 | 17.5899 | 231.0154 | 668.9846 | 0
| 957 | 20.2382 | -128.5285 | 961.3818 | 67.1466
| 958 | 17.2128 | -233.8695 | 1133.8695 | 0
| 959 | 20.9154 | -101.7977 | 914.3358 | 87.4619
| 960 | 15.0931 | 247.9565 | 652.0435 | 0
| 961 | 23.9376 | -86.5804 | 808.4518 | 178.1286
| 962 | 16.235 | -127.9856 | 1027.9856 | 0
| 963 | 17.2128 | 30.1883 | 869.8117 | 0
| 964 | 15.172 | 136.5298 | 763.4702 | 0
| 965 | 11.971 | 353.8931 | 546.1069 | 0
| 966 | 20.8076 | -128.6284 | 944.4016 | 84.2268
| 967 | 16.3428 | 7.9003 | 892.0997 | 0
| 968 | 37.242 | -255.7592 | 578.4998 | 577.2593
| 969 | 20.2382 | -176.8313 | 1009.6846 | 67.1466
| 970 | 17.5899 | 302.9119 | 597.0881 | 0
| 971 | 10.372 | 255.4859 | 644.5141 | 0
| 972 | 23.4899 | -75.2797 | 810.5823 | 164.6974
| 973 | 17.7461 | 160.5955 | 739.4045 | 0
| 974 | 13.9899 | 233.6298 | 666.3702 | 0
| 975 | 17.3853 | 61.4824 | 838.5176 | 0
| 976 | 16.3428 | -30.0293 | 930.0293 | 0
| 977 | 20.2382 | 85.8539 | 746.9995 | 67.1466
| 978 | 40.2674 | -462.8638 | 694.8415 | 668.0223
| 979 | 21.4853 | 242.7986 | 552.643 | 104.5584
| 980 | 16.9154 | -11.7214 | 911.7214 | 0
| 981 | 11.435 | 185.4324 | 714.5676 | 0
| 982 | 17.3853 | 20.9589 | 879.0411 | 0
| 983 | 12.635 | 150.1378 | 749.8622 | 0
| 984 | 16.2821 | 125.1314 | 774.8686 | 0
| 985 | 13.9899 | 214.0217 | 685.9783 | 0
| 986 | 17.7461 | 252.4139 | 647.5861 | 0
| 987 | 17.2076 | 0.04353 | 899.9565 | 0
| 988 | 16.3428 | -211.647 | 1111.647 | 0
| 989 | 20.2382 | -92.1749 | 925.0283 | 67.1466
| 990 | 22.4265 | -81.7706 | 848.9753 | 132.7953
| 991 | 20.5043 | 283.9931 | 540.8781 | 75.1288
| 992 | 23.8963 | 37.0812 | 686.031 | 176.8878
| 993 | 21.4853 | 125.1498 | 670.2918 | 104.5584
| 994 | 15.172 | 208.4264 | 691.5736 | 0
| 995 | 10.372 | 228.0345 | 671.9655 | 0
| 996 | 16.3428 | 167.4453 | 732.5547 | 0
| 997 | 17.3206 | -113.6063 | 1013.6063 | 0
| 998 | 24.8108 | -102.3172 | 797.9941 | 204.3231
| 999 | 12.635 | -22.4139 | 922.4139 | 0
| 1000 | 12.8128 | 182.818 | 717.182 | 0