## Introduction
© Copyright 2012, Probability Management Inc., all rights reserved.
www.probabilitymanagement.org/
Why so many things are behind schedule
Sam L. Savage
If you've ever tried to load your family into the station wagon for a weekend trip, you know what I'm talking about. You never get away on time.
Lets not put the blame on anyone in particular, but assume that each person in a family of four is on time on average, with say a 50/50 chance of being early or late. Then getting all four people in the car at the appointed time is as likely as flipping four heads in a row on a coin, or one chance in 16, a classic case of the Flaw of Averages.
The following tabs demonstrate how Distribution Processing with SIPmath provides insight into such problems.

## Idealized Project
|  |  |  | Calculations based on | Averages
A Simple Project with Parallel Tasks
Tasks
Description | Duration
Task 1 | 6 |  |  | 0 | 6 | 0
Task 2 | 6 |  |  | 0 | 0
Task 3 | 6 |  |  | 6 | 0 | 0
Task 4 | 6 |  |  | 6 | 0 | 0
Task 5 | 6 |  |  | 6 | 0 | 0
Task 6 | 6 |  |  | 6 | 0 | 0
Task 7 | 6 |  |  | 6 | 0 | 0
Task 8 | 6 |  |  | 6 | 0 | 0
Task 9 | 6 |  |  | 6 | 0 | 0
Task 10 | 6 |  |  | 6 | 0 | 0
|  |  |  | 6 | 0 | 0
Complete | 6 |  |  | 6 | 0 | 0
© Copyright 2012, Probability Management Inc., all rights reserved.
www.probabilitymanagement.org/
Consider an idealized project with ten parallel tasks, each of which is to be performed by an independent team. Although the duration of each task is uncertain, past history indicates that on average, each one should take six months1.
It is common to assume in such situations that the average completion time for the project is six months. But this is analogous to getting a family of ten somewhere on time, and is like flipping ten heads in a row. The chance is less than one in 1,000.
This may be grasped by simulating different durations for each task. Click the spin button control above the graph to see some typical outcomes. For a real project the uncertain durations would ideally be based on historical data2.
Click on the next tab to see how Distribution Processing can further illuminate this issue.
1 Example based on The Flaw of Averages: Why we Underestimate Risk in the Face of Uncertainty, Sam L. Savage, John Wiley 2009, 2012, p. 14
2 The Flaw of Averages in Project Management, Philip Fahringer, John Hinton, Marc Thibault, and Sam Savage, Project Management Institute, 2011
http://www.probabilitymanagement.org/Press.htm
6.0
Completion in Months

## Experiment
[8 empty] | Calculations based on | Averages
A Simple Project with Parallel Tasks
Tasks
|  |  |  | Description | Duration
|  |  |  | Task 1 | 6 |  |  | 0 | 6 | 0
|  |  |  | Task 2 | 6 |  |  | 0 | 0 |  | 0 | 10001
Avg. Completion | 7.8571 | Chance of <=6 mos | 0.1% | Task 3 | 6 |  |  | 6 | 0 | 0
|  |  |  | Task 4 | 6 |  |  | 6 | 0 | 0
|  |  |  | Task 5 | 6 |  |  | 6 | 0 | 0
Degree of Task Uncertainty |  | Number of Tasks |  | Task 6 | 6 |  |  | 6 | 0 | 0
± | 3 |  | 10 | Task 7 | 6 |  |  | 6 | 0 | 0
|  |  |  | Task 8 | 6 |  |  | 6 | 0 | 0
|  |  |  | Task 9 | 6 |  |  | 6 | 0 | 0
|  |  |  | Task 10 | 6 |  |  | 6 | 0 | 0
[8 empty] | 6 | 0 | 0
|  |  |  | Complete | 6 |  |  | 6 | 0 | 0
© Copyright 2012, Probability Management Inc.
www.probabilitymanagement.org/
Experimenting with Distribution Processing
With Distribution Processing you don't ask what the number is, you ask what the chance of making your number is. This is done by running thousands of potential values of uncertain inputs through your model.
This example uses 10,000 values for each of the 10 task durations. Below you will see the resulting average completion time in months, which clearly demonstrates the Flaw of Averages. Also displayed is the chance of finishing within 6 months.
6.0
Completion in Months
You may also experiment with the degree of uncertainty of the task durations, as well as the number of tasks by using the controls below. Remember, that every time you click a control, 10,000 sets of numbers are run through the model.
For any setting of the controls above, the distribution of the 10,000 resulting completion times is shown below.

## Model (hidden)
| Selected number of tasks |  |  |  | Mean | Uncertainty
| 10 |  |  |  | 6 | 3
Model data for one trial
| Task Duration |  | Task Data from library | Task Duration | Task Number
Task 1 | 6 | Triang_01 | 0 | 6 | 1 |  | E5:E
Task 2 | 6 | Triang_02 | 0 | 6 | 2 |  | 14
Task 3 | 6 | Triang_03 | 0 | 6 | 3 |  | E5:E14
Task 4 | 6 | Triang_04 | 0 | 6 | 4
Task 5 | 6 | Triang_05 | 0 | 6 | 5 |  | Completion
Task 6 | 6 | Triang_06 | 0 | 6 | 6 |  | 6 | Maximum of the active task durations
Task 7 | 6 | Triang_07 | 0 | 6 | 7 |  | 7.8571 | Average of the 10,000 trial maximums
Task 8 | 6 | Triang_08 | 0 | 6 | 8
Task 9 | 6 | Triang_09 | 0 | 6 | 9 |  | 3 | 0 | Data for the uncertainty graph
Task 10 | 6 | Triang_10 | 0 | 6 | 10 |  | 6 | 1
[7 empty] | 9 | 0
Work out the range of the active tasks in the model data

## Library (hidden)
10000 | Number of trials
[5 empty] | Sample distributions for each task shape | [6 empty] | Table position of Average | 10001
|  | Triang_01 | Triang_02 | Triang_03 | Triang_04 | Triang_05 | Triang_06 | Triang_07 | Triang_08 | Triang_09 | Triang_10
| 1 | 0.10317 | 0.62946 | -0.045065 | -0.57964 | 0.024962 | -0.19981 | 0.43281 | -0.72197 | 0.49177 | 0.0010506
| 2 | -0.10664 | -0.30986 | 0.26454 | 0.19782 | -0.49433 | -0.11135 | -0.44134 | -0.37879 | -0.067316 | -0.09088
| 3 | 0.010404 | 0.023322 | -0.26631 | 0.35696 | -0.015876 | -0.33209 | -0.70555 | 0.68298 | 0.52157 | 0.67243
| 4 | 0.64886 | -0.023629 | 0.075284 | 0.36905 | -0.29311 | -0.23469 | -0.32732 | -0.45091 | 0.33977 | 0.56331
| 5 | 0.15035 | 0.057609 | -0.31436 | -0.11892 | -0.47189 | -0.12874 | -0.30293 | 0.089231 | -0.12461 | -0.21165
| 6 | -0.41034 | -0.43281 | -0.25804 | -0.32658 | -0.27854 | -0.32613 | -0.12267 | -0.50594 | 0.30552 | -0.44964
| 7 | -0.017503 | 0.3248 | 0.39792 | -0.70555 | 0.15247 | -0.48824 | 0.6077 | -0.24601 | -0.057291 | -0.010101
| 8 | 0.44529 | 0.38315 | 0.17677 | -0.09198 | 0.12017 | 0.38364 | -0.47379 | 0.25576 | 0.34862 | 0.061331
| 9 | -0.024141 | 0.75772 | 0.31189 | 0.27261 | -0.0079819 | -0.85752 | 0.67427 | -0.12439 | -0.093413 | -0.23143
| 10 | 0.5866 | -0.41802 | -0.038907 | 0.44188 | -0.20069 | -0.0078811 | 0.050421 | 0.49177 | -0.35727 | 0.47665
| 11 | -0.12667 | -0.089561 | 0.37606 | 0.11022 | -0.0016514 | -0.18753 | 0.96683 | 0.67643 | 0.019235 | 0.23809
| 12 | 0.18299 | -0.0091922 | -0.12165 | -0.2571 | 0.40561 | -0.23182 | -0.12816 | -0.15318 | 0.1513 | -0.063144
| 13 | -0.9089 | 0.31787 | -0.16244 | -0.23665 | -0.50513 | -0.11824 | 0.14425 | -0.46549 | -0.02097 | -0.010707
| 14 | 0.62543 | -0.42807 | -0.51 | -0.22109 | 0.36368 | 0.14006 | 0.68647 | -0.29014 | 0.60923 | -0.68936
| 15 | -0.69065 | 0.0041586 | 0.40578 | 0.43795 | 0.0866 | -0.17677 | 0.83721 | -0.094406 | 0.17133 | 0.5143
| 16 | 0.28705 | -0.24561 | 0.18067 | -0.15851 | 0.39958 | -0.4307 | -0.32435 | -0.1292 | 0.73149 | -0.11101
| 17 | 0.043287 | 0.18951 | 0.089012 | 0.12131 | -0.066351 | -0.22611 | 0.082449 | 0.42493 | -0.0728 | 0.17072
| 18 | 0.27495 | 0.088902 | -0.52366 | 0.47417 | -0.34388 | -0.44674 | 0.12313 | 0.17945 | 0.70285 | 0.14777
| 19 | 0.35712 | 0.46793 | -0.40376 | 0.34923 | -0.38478 | -0.10418 | -0.2575 | 0.13716 | -0.2907 | -0.23482
| 20 | 0.041616 | 0.35852 | 0.64181 | 0.41716 | 0.068281 | -0.012022 | 0.22508 | -0.17957 | 0.53385 | -0.70352
| 21 | 0.40209 | 0.071722 | -0.1921 | -0.56907 | 0.73335 | -0.61987 | -0.72018 | -0.38592 | -0.1162 | -0.29099
| 22 | 0.86771 | 0.57093 | -0.22173 | -0.068388 | -0.17241 | 0.079077 | 0.19994 | 0.38121 | -0.67427 | 0.14087
| 23 | 0.73981 | 0.75979 | 0.57186 | 0.37 | -0.12484 | -0.53794 | -0.69718 | 0.26836 | -0.52031 | 0.41836
| 24 | -0.31831 | -0.06197 | 0.39164 | 0.00065021 | -0.59343 | 0.10106 | 0.91456 | -0.0069743 | -0.27041 | 0.3306
| 25 | 0.24244 | 0.58976 | 0.72089 | 0.11417 | 0.086381 | -0.077341 | -0.65201 | 0.40932 | 0.69751 | -0.42947
| 26 | 0.42493 | 0.13265 | -0.90356 | 0.5143 | 0.52745 | 0.34008 | 0.32762 | -0.31802 | -0.18508 | 0.0026535
| 27 | 0.97 | 0.3882 | -0.43105 | 0.28901 | 0.14554 | -0.40595 | -0.14578 | 0.59368 | -0.75648 | 0.33419
| 28 | 0.25133 | -0.39643 | 0.20056 | 0.58563 | 0.36227 | -0.33269 | -0.46643 | 0.34357 | 0.31831 | 0.40075
| 29 | 0.3851 | 0.17933 | -0.16711 | -0.092972 | -0.049158 | 0.43053 | -0.43973 | 0.054643 | -0.53643 | 0.23169
| 30 | 0.24814 | 0.020357 | -0.56491 | -0.56148 | 0.12484 | -0.18827 | 0.0039578 | 0.82708 | 0.083103 | -0.025167
| 31 | 0.82422 | 0.75201 | 0.09209 | -0.37032 | -0.78952 | 0.28341 | -0.53902 | -0.32955 | -0.48241 | -0.33509
| 32 | 0.082013 | -0.27357 | 0.27605 | 0.2256 | 0.1308 | -0.14906 | -0.37462 | -0.552 | 0.11315 | 0.35743
| 33 | -0.4134 | 0.49572 | 0.023117 | 0.29282 | 0.094075 | 0.18385 | -0.095511 | -0.68425 | 0.3651 | -0.2625
| 34 | -0.55067 | 0.4717 | 0.21802 | -0.035583 | -0.41699 | 0.41871 | -0.6249 | 0.14285 | 0.31218 | -0.85613
| 35 | 0.71452 | 0.22199 | -0.16161 | -0.062183 | 0.21482 | 0.007478 | 0.035168 | 0.047162 | -0.81642 | 0.70453
| 36 | 0.36117 | -0.46121 | -0.38934 | 0.0022525 | -0.079185 | -0.11711 | 0.092641 | 0.28174 | -0.044647 | -0.0065716
| 37 | 0.49433 | 0.030825 | -0.47455 | 0.050105 | -0.1729 | -0.28425 | 0.12587 | 0.089341 | 0.77841 | 0.066351
| 38 | 0.019541 | 0.13127 | 0.3242 | -0.041616 | 0.35805 | -0.12006 | 0.15106 | -0.44565 | -0.16627 | 0.35665
| 39 | -0.26781 | -0.071184 | -0.1323 | 0.11858 | 0.099833 | -0.77528 | 0.049369 | 0.74096 | -0.57798 | -0.34785
| 40 | -0.13878 | -0.072908 | 0.44945 | -0.21355 | 0.5721 | -0.25107 | 0.53578 | -0.060266 | 0.088134 | -0.81159
| 41 | 0.25307 | 0.019439 | 0.16555 | -0.43334 | -0.020766 | -0.11394 | -0.7687 | -0.034961 | 0.38413 | 0.098723
| 42 | 0.3618 | -0.89753 | 0.4857 | 0.31758 | -0.25535 | 0.29665 | -0.59417 | -0.33359 | 0.15638 | -0.48726
| 43 | 0.014556 | -0.40915 | -0.74485 | -0.031651 | 0.17811 | -0.48922 | -0.27385 | -0.25281 | 0.50513 | -0.19235
| 44 | -0.064639 | -0.066994 | -0.77306 | 0.013542 | -0.012731 | 0.22186 | -0.25147 | -0.5347 | 0.65114 | 0.25388
| 45 | -0.82593 | -0.61231 | 0.17945 | 0.20634 | 0.6634 | 0.04517 | -0.29466 | -0.089121 | 0.5201 | -0.046847
| 46 | 0.52177 | -0.67396 | 0.20659 | -0.010606 | -0.93597 | 0.31203 | 0.72559 | -0.43529 | -0.14788 | -0.50837
| 47 | 0.41785 | 0.10028 | 0.34693 | 0.0040582 | 0.83118 | 0.46587 | -0.40175 | 0.022094 | 0.29367 | -0.080163
| 48 | -0.31261 | 0.25953 | -0.62039 | -0.22006 | 0.45622 | -0.41102 | 0.098612 | -0.3297 | -0.3366 | 0.75607
| 49 | -0.011213 | -0.82196 | 0.65576 | 0.01842 | -0.046533 | -0.20219 | -0.52073 | -0.44403 | -0.066887 | -0.16844
| 50 | 0.16006 | -0.59343 | -0.4991 | -0.078968 | 0.30437 | 0.41272 | 0.096396 | -0.11428 | 0.17471 | -0.37863
| 51 | -0.059202 | -0.78251 | 0.20458 | 0.092862 | -0.19744 | -0.051897 | 0.069248 | 0.40025 | -0.2674 | 0.58563
| 52 | -0.40359 | 0.4117 | -0.21866 | 0.33917 | -0.59738 | -0.5245 | 0.48454 | -0.13449 | -0.15863 | 0.011617
| 53 | 0.14636 | -0.2524 | 0.31655 | -0.070753 | -0.43246 | 0.069892 | 0.22728 | -0.52513 | 0.025885 | 0.56722
| 54 | -0.27633 | 0.31232 | 0.085506 | 0.64153 | -0.31787 | -0.21304 | 0.08234 | -0.015368 | -0.6044 | -0.52894
| 55 | 0.50351 | 0.061118 | 0.36526 | -0.47379 | -0.3306 | -0.26822 | 0.0040582 | -0.14988 | -0.28845 | -0.86108
| 56 | -0.09055 | 0.56354 | 0.4194 | -0.37095 | 0.27481 | 0.12851 | -0.3025 | -0.72889 | -0.64886 | 0.28972
| 57 | -0.76655 | 0.12017 | -0.036102 | -0.40915 | 0.43884 | 0.048738 | -0.020459 | 0.61856 | 0.10072 | 0.35262
| 58 | -0.22961 | 0.51906 | -0.7492 | 0.42372 | 0.49771 | -0.13426 | 0.19757 | 0.29028 | -0.50898 | 0.47379
| 59 | 0.76188 | -0.9089 | 0.53213 | 0.14847 | -0.27192 | 0.17423 | -0.76957 | -0.21355 | 0.89091 | 0.30667
| 60 | -0.71277 | 0.73186 | -0.41017 | 0.61542 | -0.32096 | 0.42825 | 0.17157 | -0.024141 | 0.49691 | 0.12336
| 61 | -0.23888 | -0.51205 | 0.099167 | -0.30667 | 0.55514 | 0.27069 | 0.1578 | -0.42912 | -0.53989 | -0.39066
| 62 | 0.012832 | 0.54492 | 0.24508 | -0.7496 | -0.60138 | -0.65143 | 0.081686 | -0.06603 | -0.010404 | 0.060798
| 63 | -0.12874 | -0.0728 | -0.55044 | -0.16125 | -0.016384 | -0.31831 | -0.21955 | 0.55 | -0.015876 | -0.7492
| 64 | 0.75731 | 0.49493 | 0.74485 | 0.11011 | 0.35961 | -0.4553 | 0.060798 | 0.54426 | -0.45751 | 0.14824
| 65 | -0.33329 | 0.22495 | -0.47398 | 0.21203 | -0.089451 | 0.77887 | 0.64574 | 0.35618 | 0.076582 | 0.93917
| 66 | -0.096507 | 0.46962 | -0.051369 | -0.6755 | -0.33796 | -0.24694 | 0.009798 | 0.11338 | -0.42164 | -0.3651
| 67 | -0.63572 | 0.0728 | -0.13646 | 0.47837 | 0.43476 | -0.046428 | -0.56445 | -0.62357 | 0.50533 | 0.69194
| 68 | 0.051686 | -0.67335 | -0.34494 | 0.46718 | 0.58976 | -0.464 | 0.49711 | 0.2484 | -0.03465 | -0.56814
| 69 | 0.25872 | -0.13115 | -0.5283 | -0.87311 | 0.21038 | 0.76399 | -0.60163 | -0.13507 | 0.45972 | -0.52303
| 70 | -0.48376 | -0.067637 | -0.36921 | -0.020561 | 0.68903 | 0.20697 | -0.46344 | -0.48435 | 0.59073 | -0.75444
| 71 | -0.23547 | -0.81 | 0.00055015 | -0.50311 | -0.17884 | 0.10328 | -0.17048 | 0.078317 | 0.46418 | 0.41854
| 72 | 0.86472 | -0.61335 | -0.8454 | -0.39263 | 0.95877 | -0.061331 | -0.75607 | 0.0013509 | -0.27055 | -0.72414
| 73 | 0.67829 | 0.8821 | -0.87077 | -0.70386 | -0.1338 | 0.25067 | 0.08485 | -0.066673 | -0.40831 | 0.18569
| 74 | 0.26061 | -0.18471 | -0.42164 | 0.3454 | 0.26332 | -0.41085 | 0.87233 | 0.057079 | 0.46437 | -0.51143
| 75 | -0.055913 | 0.89276 | -0.24429 | -0.48551 | 0.05984 | 0.48824 | 0.2052 | -0.21648 | -0.09187 | -0.36937
| 76 | 0.11926 | -0.26822 | 0.20106 | -0.62437 | -0.19894 | 0.21 | 0.32702 | 0.46793 | 0.25522 | -0.73037
| 77 | -0.44493 | 0.0026535 | 0.53363 | -0.82252 | 0.33179 | -0.1118 | 0.031135 | 0.093413 | -0.05984 | 0.077341
| 78 | 0.14006 | 0.48067 | -0.78716 | -0.66281 | -0.47019 | 0.12347 | -0.31029 | -0.28593 | -0.3303 | 0.08343
| 79 | -0.10418 | 0.09077 | 0.76021 | -0.45255 | 0.1109 | -0.11124 | -0.30754 | 0.50634 | -0.76827 | -0.32776
| 80 | 0.16197 | -0.24721 | -0.17012 | 0.67766 | -0.53578 | 0.51948 | -0.76612 | -0.0911 | -0.1546 | 0.43511
| 81 | 0.093523 | -0.020153 | 0.1153 | 0.26849 | -0.79384 | 0.41 | 0.1852 | -0.28817 | 0.45806 | -0.22573
| 82 | -0.11541 | 0.67091 | -0.35077 | -0.18446 | -0.37302 | 0.29936 | 0.31816 | -0.12541 | -0.79678 | 0.13438
| 83 | 0.23783 | 0.8755 | 0.19346 | -0.098612 | 0.46158 | 0.32911 | 0.22019 | -0.1221 | -0.51678 | 0.4755
| 84 | 0.18348 | 0.66489 | -0.43246 | -0.32554 | 0.20332 | 0.73866 | -0.29779 | 0.010808 | -0.20106 | -0.18214
| 85 | 0.24231 | 0.28021 | -0.22974 | 0.3297 | -0.52031 | 0.50553 | 0.087805 | -0.41204 | 0.63135 | 0.058565
| 86 | 0.2133 | -0.12496 | 0.61777 | -0.26849 | -0.89091 | 0.26156 | -0.1425 | -0.46121 | 0.74603 | 0.53578
| 87 | 0.089341 | 0.49295 | -0.28747 | -0.064639 | 0.065816 | -0.093082 | -0.43018 | 0.62171 | -0.55447 | 0.83477
| 88 | 0.59343 | -0.28873 | -0.045694 | -0.62251 | 0.12142 | -0.050737 | 0.28021 | -0.16952 | 0.3751 | -0.59689
| 89 | -0.28243 | 0.026604 | -0.18852 | 0.536 | 0.0995 | 0.2256 | 0.47626 | 0.61464 | -0.28495 | -0.17169
| 90 | 0.88295 | 0.25133 | -0.30725 | 0.3038 | -0.095401 | 0.59343 | 0.39676 | -0.056125 | -0.48106 | -0.37799
| 91 | -0.21508 | -0.30107 | 0.41408 | 0.021072 | -0.33781 | -0.0173 | -0.13519 | -0.86621 | 0.14145 | 0.15697
| 92 | 0.72889 | 0.63326 | -0.66789 | -0.64293 | -0.36652 | -0.051686 | 0.29197 | 0.028249 | -0.27688 | -0.20432
| 93 | 0.044019 | -0.27896 | -0.50351 | 0.82365 | 0.3851 | 0.075933 | -0.042242 | 0.80125 | -0.16868 | -0.45714
| 94 | -0.58251 | 0.17483 | -0.4426 | -0.36794 | 0.030928 | -0.066244 | -0.23691 | -0.37127 | 0.12017 | -0.27688
| 95 | -0.019235 | 0.44692 | -0.043496 | -0.048107 | -0.81642 | 0.20106 | -0.36023 | 0.43476 | -0.24072 | 0.22032
| 96 | -0.40561 | -0.12359 | -0.0065716 | 0.12347 | -0.1852 | 0.58951 | -0.36463 | 0.18557 | -0.23013 | 0.50654
| 97 | -0.082776 | 0.25508 | 0.0078811 | -0.73037 | 0.16807 | -0.20571 | 0.10061 | 0.73904 | -0.26658 | 0.47265
| 98 | -0.052108 | 0.47818 | 0.044542 | -0.035894 | 0.072369 | 0.89656 | 0.48183 | -0.2504 | -0.09022 | -0.59171
| 99 | -0.052002 | 0.1439 | 0.14285 | 0.40159 | -0.094296 | -0.27481 | 0.68078 | -0.018929 | -0.14742 | -0.16819
| 100 | -0.27481 | -0.16988 | -0.23574 | 0.038803 | -0.11394 | 0.64659 | -0.054326 | -0.44818 | -0.57093 | 0.36968
| 101 | 0.092751 | -0.019949 | -0.31875 | -0.4826 | 0.77483 | 0.014962 | -0.33886 | 0.15531 | 0.052213 | 0.28035
| 102 | -0.19223 | 0.021685 | -0.09706 | -0.049474 | 0.21738 | -0.21292 | 0.22006 | 0.70352 | -0.0053644 | -0.27965
| 103 | -0.076691 | 0.2287 | -0.16519 | 0.13369 | 0.44493 | -0.36573 | -0.22289 | -0.61542 | 0.47322 | -0.51886
| 104 | 0.34647 | 0.25307 | -0.90253 | 0.80226 | -0.29466 | -0.39395 | -0.44349 | 0.16042 | 0.19595 | -0.017605
| 105 | 0.47474 | 0.65029 | -0.071184 | -0.18766 | 0.82883 | -0.57822 | -0.12874 | -0.63903 | -0.40058 | 0.34205
| 106 | -0.0010506 | 0.46925 | -0.57327 | -0.44277 | 0.13855 | -0.33555 | 0.5007 | 0.41991 | -0.13843 | 0.58155
| 107 | 0.1118 | -0.22741 | 0.62145 | 0.45603 | 0.14496 | 0.21419 | -0.85964 | -0.051897 | 0.15283 | 0.51246
| 108 | -0.79925 | -0.14169 | -0.031135 | -0.31145 | 0.86621 | 0.21725 | 0.78251 | 0.25027 | -0.64014 | -0.25334
| 109 | 0.33464 | 0.11756 | -0.40326 | -0.81 | 0.56838 | -0.7504 | -0.094738 | -0.03465 | 0.66489 | -0.32435
| 110 | -0.83 | 0.10496 | 0.45219 | -0.16603 | 0.27605 | -0.1136 | -0.35339 | 0.36557 | 0.44027 | 0.35572
| 111 | 0.17012 | 0.33826 | 0.436 | -0.73599 | -0.36589 | -0.0054649 | -0.56422 | 0.52576 | 0.22754 | 0.35945
| 112 | -0.26727 | -0.22521 | 0.20975 | 0.72018 | 0.18128 | -0.57633 | -0.093082 | -0.060479 | -0.61206 | -0.90461
| 113 | 0.058884 | 0.35339 | 0.054431 | -0.1466 | -0.32806 | -0.09198 | -0.18741 | -0.29452 | 0.16209 | -0.58757
| 114 | 0.24429 | -0.39726 | -0.12006 | 0.41034 | 0.17532 | -0.19757 | 0.30093 | -0.0755 | -0.18092 | 0.053269
| 115 | 0.62946 | 0.069785 | -0.336 | 0.28845 | -0.62251 | -0.079185 | 0.087695 | -0.5608 | 0.38673 | 0.31978
| 116 | -0.55335 | -0.61309 | -0.015165 | -0.43991 | 0.37815 | -0.66221 | 0.62437 | -0.023015 | -0.70966 | -0.81588
| 117 | -0.3309 | 0.23391 | 0.24151 | 0.46102 | -0.64886 | 0.26318 | -0.39576 | -0.15875 | -0.43866 | -0.35293
| 118 | 0.11056 | 0.065923 | 0.33766 | 0.3618 | -0.72197 | -0.28104 | -0.22611 | -0.42807 | -0.31641 | -0.36541
| 119 | 0.74368 | -0.47076 | -0.56676 | -0.50371 | -0.47417 | 0.35727 | -0.12142 | 0.016283 | -0.14929 | -0.69784
| 120 | -0.025269 | -0.5728 | -0.40898 | 0.088243 | 0.36211 | -0.1162 | 0.50311 | 0.17265 | -0.25522 | 0.64574
| 121 | 0.36305 | 0.5199 | 0.093965 | -0.78669 | -0.053797 | -0.11688 | 0.56583 | -0.13357 | 0.28944 | 0.1841
| 122 | -0.24747 | -0.67766 | -0.24575 | -0.42407 | 0.24376 | -0.80739 | 0.56861 | 0.34969 | 0.5735 | 0.21279
| 123 | 0.062823 | 0.66015 | -0.136 | 0.38592 | -0.024654 | -0.2784 | -0.31758 | -0.72926 | -0.2791 | -0.3796
| 124 | 0.026604 | -0.69259 | 0.25683 | -0.097836 | 0.018725 | -0.77572 | -0.16892 | 0.56884 | -0.27868 | 0.016384
| 125 | -0.13739 | -0.064639 | 0.30567 | 0.01415 | -0.28916 | 0.43617 | -0.02322 | -0.19906 | 0.40393 | 0.034029
| 126 | -0.20684 | -0.10933 | 0.61387 | -0.59491 | -0.15401 | -0.15059 | 0.18201 | 0.90356 | -0.076582 | 0.35479
| 127 | -0.045065 | -0.2995 | 0.45935 | -0.068496 | -0.83783 | -0.50857 | -0.1694 | -0.33404 | 0.5003 | -0.36447
| 128 | -0.022606 | -0.22122 | -0.50796 | 0.11034 | 0.12759 | -0.46102 | -0.060692 | -0.24297 | -0.020051 | 0.21482
| 129 | 0.027632 | -0.86252 | -0.11067 | -0.71452 | -0.89851 | -0.79191 | 0.23941 | 0.81642 | 0.35774 | -0.04099
| 130 | -0.20031 | 0.31553 | 0.08649 | 0.11101 | -0.46344 | 0.1382 | -0.8454 | -0.093965 | -0.26441 | 0.34008
| 131 | -0.54076 | -0.056443 | -0.87793 | -0.54624 | -0.10989 | -0.19037 | 0.33224 | 0.12989 | 0.44511 | 0.44295
| 132 | -0.15401 | -0.015165 | -0.55694 | 0.032581 | 0.12461 | 0.10239 | 0.3735 | 0.26427 | -0.26713 | 0.0089904
| 133 | 0.54712 | 0.68298 | 0.20798 | 0.16723 | -0.20962 | -0.43973 | -0.63627 | -0.23182 | -0.27261 | -0.11135
| 134 | -0.39329 | 0.87077 | 0.094406 | 0.56791 | -0.20194 | 0.52387 | -0.19322 | 0.55267 | 0.067959 | -0.49512
| 135 | -0.50817 | 0.27178 | -0.32391 | -0.3838 | 0.55966 | 0.28146 | -0.31145 | 0.43264 | 0.72742 | 0.19595
| 136 | -0.76442 | 0.097393 | -0.62973 | 0.35031 | 0.21419 | 0.99 | 0.37542 | 0.0995 | 0.12702 | -0.3132
| 137 | 0.28063 | -0.4801 | 0.036932 | -0.070538 | -0.58275 | -0.61412 | 0.86696 | 0.4471 | -0.39444 | 0.348
| 138 | -0.46512 | 0.1136 | -0.094517 | 0.016181 | -0.050632 | -0.0048618 | 0.31787 | -0.37734 | 0.45714 | 0.40292
| 139 | 0.30899 | -0.082885 | -0.44927 | 0.042138 | 0.68615 | 0.42285 | 0.0090913 | -0.28285 | 0.034133 | 0.17787
| 140 | 0.12359 | 0.19433 | 0.042242 | -0.17665 | -0.069248 | -0.5001 | 0.21165 | 0.14788 | -0.57774 | -0.19994
| 141 | -0.31247 | -0.548 | 0.13276 | 0.31232 | -0.23967 | -0.40713 | 0.59294 | -0.82824 | -0.13669 | 0.4078
| 142 | 0.20282 | -0.031444 | 0.39 | 0.51534 | -0.25953 | -0.041407 | -0.33075 | 0.40142 | -0.93144 | -0.40309
| 143 | 0.0012508 | -0.25872 | -0.4272 | 0.13692 | 0.39992 | 0.31978 | 0.71911 | 0.27578 | -0.72889 | 0.027426
| 144 | -0.48048 | -0.025269 | -0.80739 | -0.80226 | 0.23286 | -0.39428 | 0.14753 | -0.14636 | 0.47665 | -0.09165
| 145 | 0.017401 | -0.25267 | 0.087257 | 0.49078 | -0.70117 | -0.62277 | 0.45255 | -0.87712 | -0.61516 | 0.4286
| 146 | 0.48902 | -0.0013509 | 0.41085 | -0.3214 | -0.057291 | 0.34311 | 0.066351 | 0.097836 | -0.043601 | -0.27082
| 147 | -0.15733 | -0.2791 | -0.53277 | -0.18975 | -0.12564 | 0.16018 | 0.45824 | -0.038283 | 0.088353 | -0.33992
| 148 | 0.15816 | -0.028043 | -0.031238 | -0.047897 | -0.0055655 | -0.035687 | -0.57798 | 0.29085 | -0.35463 | 0.31349
| 149 | -0.070861 | 0.53213 | -0.34846 | -0.16424 | -0.57186 | 0.34571 | -0.70217 | 0.18581 | -0.053058 | 0.60516
| 150 | 0.20495 | -0.16113 | -0.061864 | 0.086928 | -0.46083 | 0.62919 | 0.65143 | 0.59863 | 0.47 | -0.74761
| 151 | 0.25455 | 0.060905 | -0.44277 | 0.57633 | 0.12427 | -0.12966 | -0.10206 | 0.38869 | 0.26672 | 0.1646
| 152 | -0.22676 | -0.22071 | -0.35247 | -0.54889 | -0.078751 | 0.59913 | -0.0911 | 0.48164 | -0.41017 | 0.61803
| 153 | 0.25764 | -0.77175 | -0.50553 | -0.01182 | -0.67643 | 0.30667 | -0.28859 | -0.48067 | 0.30064 | 0.31378
| 154 | 0.16328 | -0.082231 | -0.45972 | 0.014049 | 0.099167 | 0.039844 | -0.1432 | 0.23273 | 0.30164 | 0.50371
| 155 | 0.57869 | 0.38722 | -0.60289 | -0.44367 | -0.24442 | -0.53707 | 0.30179 | 0.021992 | -0.59098 | -0.75241
| 156 | -0.26795 | -0.015368 | 0.63054 | 0.3214 | 0.61882 | 0.12874 | -0.13346 | 0.32494 | 0.078642 | 0.27357
| 157 | -0.23587 | -0.14122 | 0.01486 | 0.69553 | -0.74722 | -0.45806 | 0.34296 | 0.3087 | -0.031754 | -0.85067
| 158 | -0.22573 | 0.24707 | 0.83721 | 0.8739 | 0.37175 | -0.014962 | 0.55604 | 0.10128 | -0.099833 | 0.53128
| 159 | -0.23338 | -0.85964 | 0.67335 | -0.14215 | 0.8366 | 0.29679 | 0.4736 | -0.051264 | -0.50452 | -0.17726
| 160 | 0.22792 | -0.48048 | -0.56354 | 0.014454 | -0.22728 | -0.043705 | -0.30942 | 0.72963 | 0.83237 | -0.15236
| 161 | 0.45972 | -0.23849 | 0.12633 | -0.42078 | 0.32391 | 0.043078 | -0.76442 | 0.046952 | 0.31772 | -0.13832
| 162 | 0.077341 | 0.30322 | 0.10776 | 0.19086 | -0.3294 | -0.37398 | 0.44982 | 0.45401 | -0.69917 | 0.092421
| 163 | 0.07 | 0.3015 | 0.89091 | -0.69259 | 0.5347 | 0.09066 | -0.4041 | 0.084304 | 0.42337 | 0.086271
| 164 | -0.65143 | -0.67304 | -0.09022 | -0.55044 | -0.72669 | -0.47436 | 0.6811 | -0.37446 | -0.71417 | -0.065602
| 165 | -0.74329 | -0.48357 | 0.073987 | 5.0001e-05 | 0.57444 | 0.2161 | 0.34954 | -0.88126 | 0.06325 | 0.13069
| 166 | -0.55739 | -0.020255 | -0.6811 | -0.48435 | 0.27993 | 0.74135 | 0.15389 | -0.059096 | -0.051475 | -0.60364
| 167 | 0.14192 | 0.37095 | 0.020561 | -0.39626 | -0.21127 | -0.31685 | 0.53299 | -0.43795 | -0.47227 | -0.35867
| 168 | 0.50594 | 0.28607 | 0.088134 | -0.59368 | 0.28845 | -0.31524 | -0.3804 | -0.26169 | 0.12943 | 0.85893
| 169 | 0.0080827 | 0.29936 | 0.27041 | -0.43493 | -0.13127 | -0.41477 | -0.01791 | -0.14087 | 0.2516 | -0.16436
| 170 | -0.43193 | 0.53967 | 0.53256 | -0.40276 | 0.39726 | -0.03714 | 0.5447 | -0.50878 | -0.00035006 | -0.39197
| 171 | 0.16066 | -0.23534 | 0.42912 | -0.32184 | 0.47971 | -0.54978 | 0.77617 | 0.0755 | -0.65431 | 0.53837
| 172 | 0.06293 | 0.67061 | -0.018114 | 0.1425 | -0.35479 | 0.029279 | -0.43229 | 0.49751 | -0.61309 | -0.28104
| 173 | 0.50898 | 0.55178 | -0.5017 | -0.038595 | -0.75485 | 0.66133 | -0.089121 | 0.068925 | 0.16113 | 0.58036
| 174 | 0.10217 | -0.43884 | 0.33705 | 0.093523 | -0.73223 | -0.13161 | -0.040156 | 0.56491 | 0.14355 | -0.79579
| 175 | 0.43688 | -0.24694 | 0.11903 | -0.42842 | 0.03579 | -0.49177 | -0.26509 | 0.50452 | -0.61283 | 0.13971
| 176 | -0.63682 | -0.1425 | -0.20019 | 0.65985 | -0.11056 | 0.45493 | 0.13426 | -0.38024 | 0.82308 | -0.62811
| 177 | 0.43938 | -0.0076795 | 0.085615 | 0.19881 | -0.26495 | 0.86036 | -0.061757 | -0.12131 | -0.003155 | 0.073663
| 178 | 0.20596 | 0.66549 | -0.55469 | 0.51451 | -0.54956 | 0.088353 | 0.448 | 0.73223 | -0.32598 | -0.21674
| 179 | -0.10139 | 0.24628 | 0.035376 | 0.017401 | -0.55067 | -0.43211 | 0.0064709 | 0.62731 | 0.53235 | -0.57186
| 180 | 0.59838 | -0.90461 | -0.037244 | -0.71698 | 0.41528 | -0.32687 | -0.0077803 | -0.35789 | -0.17714 | 0.53299
| 181 | 0.71769 | -0.060053 | -0.094959 | -0.17909 | -0.78716 | -0.5143 | 0.51246 | -0.31963 | 0.0092932 | 0.62892
| 182 | -0.1758 | 0.1735 | -0.30581 | 0.5608 | -0.06325 | -0.31305 | -0.33209 | 0.02097 | -0.55067 | -0.27014
| 183 | -0.33194 | -0.018216 | -0.024449 | -0.82824 | -0.38853 | -0.45127 | -0.40292 | -0.13322 | 0.044019 | -0.51348
| 184 | -0.024654 | -0.06165 | 0.3116 | -0.25388 | 0.6118 | -0.26115 | -0.15271 | -0.62892 | 0.71208 | 0.7492
| 185 | -0.17605 | 0.20219 | -0.72926 | -0.2755 | 0.011314 | 0.22225 | 0.21432 | -0.21127 | 0.58155 | 0.11405
| 186 | -0.24389 | 0.0078811 | -0.5001 | -0.013744 | -0.31203 | -0.089012 | -0.028146 | -0.26918 | 0.33886 | 0.10306
| 187 | -0.53729 | -0.035065 | -0.73149 | 0.52282 | -0.35961 | -0.27702 | -0.3005 | 0.73789 | 0.12496 | 0.6952
| 188 | 0.12644 | -0.11169 | -0.7569 | 0.31831 | 0.39016 | 0.31116 | -0.6407 | -0.54956 | -0.0046609 | 0.23823
| 189 | -0.012427 | 0.36117 | -0.11915 | 0.10832 | 0.59738 | -0.25013 | 0.65927 | 0.66221 | -0.48707 | -0.077991
| 190 | -0.36683 | -0.20609 | -0.051475 | 0.13115 | 0.33314 | -0.28691 | 0.24376 | -0.56239 | -0.24323 | 0.76612
| 191 | 0.38984 | 0.56838 | -0.28369 | -0.23143 | -0.1758 | -0.24033 | 0.81807 | -0.34114 | 0.61206 | -0.35169
| 192 | 0.49592 | -0.62597 | 0.32465 | 0.74251 | 0.23026 | 0.452 | 0.57023 | 0.52661 | 0.09132 | -0.079185
| 193 | -0.81426 | 0.34617 | -0.37654 | 0.2508 | -0.54382 | 0.47703 | -0.22948 | -0.85543 | -0.24641 | -0.072476
| 194 | -0.21355 | 0.1729 | -0.40393 | 0.09209 | -0.29921 | -0.26278 | -0.22186 | -0.0018517 | 0.7839 | -0.039635
| 195 | 0.59863 | -0.079728 | 0.44837 | 0.0728 | 0.464 | -0.32155 | -0.088134 | 0.16976 | 0.21533 | -0.71382
| 196 | -0.32776 | -0.093965 | -0.77707 | -0.14847 | 0.48961 | 0.1803 | 0.0092932 | -0.37976 | -0.44837 | -0.4272
| 197 | 0.45091 | -0.87958 | -0.50291 | -0.31743 | 0.54646 | -0.23078 | -0.78905 | -0.38315 | -0.13023 | -0.076582
| 198 | 0.82196 | -0.58563 | -0.32509 | 0.49137 | -0.3882 | 0.08234 | 0.0027538 | -0.63027 | -0.6162 | 0.37847
| 199 | -0.54823 | -0.27137 | -0.25912 | 0.024756 | 0.51844 | -0.10139 | -0.28049 | -0.21508 | 0.051686 | -0.35448
| 200 | -0.17738 | 0.87958 | 0.0043595 | 0.31816 | 0.64914 | -0.69357 | 0.87311 | -0.34586 | 0.047897 | 0.1628
| 201 | -0.21635 | -0.024346 | -0.023424 | 0.81318 | 0.2689 | -0.37751 | 0.60188 | 0.54536 | -0.071722 | -0.51369
| 202 | 0.27757 | -0.3048 | 0.16149 | 0.38218 | -0.9245 | -0.41323 | -0.6833 | -0.82593 | -0.88295 | 0.21674
| 203 | -0.74212 | -0.63572 | -0.039531 | -0.36415 | -0.19099 | 0.38494 | 0.28481 | 0.10529 | -0.77175 | 0.42947
| 204 | -0.4736 | 0.003155 | -0.10899 | 0.27633 | 0.043287 | 0.37863 | -0.44206 | 0.54823 | -0.11972 | 0.4985
| 205 | 0.43281 | 0.14519 | 0.17823 | 0.10563 | -0.12165 | 0.37127 | 0.39643 | 0.37095 | 0.27882 | 0.14379
| 206 | -0.23117 | -0.32658 | -0.79678 | -0.14683 | -0.21 | 0.30725 | -0.049895 | -0.70589 | 0.29028 | 0.76484
| 207 | -0.37032 | 0.54163 | -0.068174 | -0.4041 | 0.080598 | 0.57751 | 0.053903 | -0.25804 | -0.18165 | -0.22831
| 208 | 0.086928 | 0.9245 | -0.85337 | -0.48318 | 0.50472 | 0.039427 | -0.66519 | -0.61961 | 0.040573 | 0.20044
| 209 | -0.06753 | 0.62892 | -0.24867 | -0.57751 | 0.033408 | 0.48067 | -0.13 | -0.1091 | -0.18803 | 0.33902
| 210 | -0.89 | -0.22135 | 0.13207 | 0.057928 | 0.071614 | 0.25508 | 0.39726 | 0.29381 | 0.42528 | 0.59863
| 211 | -0.27882 | 0.15047 | -0.29893 | 0.11767 | -0.41922 | -0.032581 | -0.19446 | 0.030722 | 0.16173 | 0.13646
| 212 | 0.70521 | 0.45018 | 0.46158 | 0.14192 | 0.13948 | -0.18544 | 0.20735 | -0.054537 | 0.06603 | 0.43105
| 213 | 0.348 | 0.96127 | 0.22469 | -0.54273 | -0.011112 | -0.037867 | 0.31993 | 0.10473 | 0.088024 | 0.22922
| 214 | -0.23875 | -0.23065 | 0.52703 | -0.33645 | 0.69652 | -0.076907 | 0.39742 | -0.40343 | 0.40527 | 0.40025
| 215 | 0.88909 | 0.39543 | 0.34433 | 0.10989 | -0.15839 | 0.27951 | 0.1439 | -0.69455 | 0.0019519 | 0.079077
| 216 | 0.40729 | 0.1841 | 0.81106 | 0.55762 | 0.63244 | 0.30466 | 0.025167 | 0.35262 | 0.71557 | -0.30682
| 217 | 0.26101 | 0.22598 | 0.8882 | -0.14988 | -0.18373 | -0.34235 | 0.13971 | -0.50695 | 0.1597 | -0.21317
| 218 | -0.49196 | -0.53277 | -0.0073772 | 0.49771 | -0.26932 | 0.85067 | 0.73981 | 0.25818 | -0.20169 | 0.49413
| 219 | -0.75979 | 0.12782 | 0.44403 | 0.44242 | 0.44547 | 0.19669 | 0.63627 | -0.13553 | 0.40814 | 0.45164
| 220 | 0.80843 | -0.092862 | -0.29979 | -0.32806 | 0.14461 | 0.66549 | -0.03714 | -0.21228 | -0.18766 | -0.44421
| 221 | 0.014657 | 0.0088895 | 0.77395 | -0.25643 | -0.13426 | 0.24323 | 0.2674 | -0.93597 | 0.1752 | 0.82422
| 222 | 0.02794 | -0.1628 | -0.18704 | 0.5019 | 0.66879 | -0.049579 | 0.64829 | -0.85752 | 0.19446 | 0.17702
| 223 | -0.029485 | 0.12496 | -0.18864 | -0.71382 | 0.6786 | 0.35634 | 0.53256 | 0.55582 | 0.36196 | -0.062077
| 224 | -0.84736 | 0.076474 | -0.20874 | 0.25227 | 0.47779 | -0.61829 | 0.47474 | 0.22302 | 0.74329 | 0.49612
| 225 | -0.29622 | -0.065709 | -0.046218 | -0.017096 | 0.3751 | 0.054326 | 0.75 | -0.031651 | 0.42615 | -0.6697
| 226 | -0.30265 | 0.41289 | -0.1136 | 0.40142 | -0.79875 | -0.70828 | 0.033098 | -0.52219 | 0.36211 | -0.22353
| 227 | 0.35618 | 0.3312 | -0.47379 | 0.12782 | 0.49532 | 0.16137 | -0.46493 | -0.31073 | 0.15578 | -0.35216
| 228 | 0.16161 | -0.031341 | 0.16018 | 0.014556 | -0.6265 | -0.0057666 | 0.22831 | 0.39362 | 0.10273 | 0.39875
| 229 | 0.64125 | -0.012326 | -0.60213 | -0.41068 | 0.29254 | -0.041303 | 0.25053 | -0.10306 | 0.42112 | -0.10083
| 230 | 0.4344 | -0.40848 | -0.57233 | -0.55604 | -0.2427 | -0.47684 | 0.55785 | 0.20144 | 0.50857 | 0.248
| 231 | 0.34342 | -0.39131 | 0.4989 | -0.89 | -0.12461 | 0.01415 | -0.12862 | -0.71769 | 0.24548 | 0.43546
| 232 | 0.48048 | 0.044123 | 0.68204 | -0.01486 | -0.065495 | 0.18975 | -0.76104 | 0.0042591 | 0.069677 | -0.12313
| 233 | -0.8747 | -0.063891 | 0.26237 | -0.18778 | -0.44529 | -0.2809 | 0.41699 | -0.39975 | 0.43476 | -0.033512
| 234 | 0.57163 | -0.15994 | 0.27398 | 0.45732 | -0.1315 | -0.49631 | 0.18018 | -0.0056661 | 0.28313 | -0.51123
| 235 | 0.8995 | 0.92584 | 0.20609 | -0.58805 | -0.51082 | -0.19247 | -0.7569 | 0.38755 | 0.48241 | -0.59024
| 236 | 0.48765 | -0.44457 | 0.16771 | -0.35899 | 0.060692 | 0.53751 | -0.63435 | 0.14309 | -0.10228 | 0.90253
| 237 | -0.2052 | -0.14274 | 0.38413 | 0.24112 | -0.51554 | 0.029382 | 0.70251 | 0.12028 | 0.078859 | 0.10351
| 238 | 0.72632 | 0.47626 | 0.36463 | 0.53881 | -0.61646 | 0.17653 | 0.26781 | -0.18238 | 0.48804 | 0.68711
| 239 | 0.43458 | -0.43991 | 0.22392 | -0.030412 | -0.12747 | -0.10106 | -0.027529 | -0.42407 | -0.4826 | -0.20357
| 240 | 0.51246 | -0.36636 | -0.33796 | 0.32539 | -0.4046 | 0.33284 | 0.27771 | -0.69 | -0.00015001 | 0.079185
| 241 | -0.17435 | -0.28663 | 0.2995 | 0.32702 | 0.5458 | -0.060905 | 0.14812 | -0.59073 | 0.84736 | 0.69553
| 242 | -0.38885 | -0.081251 | -0.032788 | -0.37783 | -0.85134 | 0.026707 | -0.19086 | -0.14006 | 0.34403 | 0.14788
| 243 | 0.73 | -0.12564 | 0.38543 | 0.064746 | 0.0075787 | -0.24178 | 0.57585 | 0.23521 | -0.2484 | -0.062183
| 244 | 0.031548 | -0.11892 | -0.17 | -0.12427 | -0.52282 | 0.52429 | -0.37992 | -0.014049 | 0.082776 | -0.49671
| 245 | -0.65086 | 0.68267 | -0.8937 | -0.14542 | -0.77175 | 0.24707 | -0.043496 | 0.71946 | -0.79776 | -0.25683
| 246 | 0.048317 | -0.66162 | -0.35618 | -0.043078 | -0.47474 | -0.36636 | -0.031031 | 0.065602 | 0.25939 | 0.55178
| 247 | 0.36841 | -0.91574 | -0.13276 | -0.15212 | -0.26291 | -0.42982 | 0.44457 | -0.4163 | -0.25455 | -0.41374
| 248 | -0.20823 | -0.51906 | -0.69685 | 0.012731 | -0.65201 | -0.20533 | 0.46549 | 0.20899 | 0.34357 | 0.57
| 249 | -0.36905 | -0.22289 | -0.36023 | -0.11022 | 0.17048 | -0.53235 | 0.16615 | 0.53235 | -0.27661 | 0.29807
| 250 | 0.13623 | -0.032477 | 0.46344 | 0.46306 | 0.19669 | 0.47 | -0.07 | -0.45787 | -0.054431 | 0.33615
| 251 | -0.0065716 | -0.39461 | 0.31029 | 0.4046 | 0.71104 | 0.13646 | 0.062077 | 0.48765 | -0.055066 | 0.57327
| 252 | -0.83297 | 0.18667 | -0.039948 | -0.69065 | -0.56884 | -0.080816 | -0.82365 | -0.12736 | 0.8956 | 0.76188
| 253 | -0.65809 | 0.53643 | 0.26345 | 0.10966 | -0.54011 | 0.2484 | 0.59196 | 0.39792 | -0.27522 | -0.14871
| 254 | 0.27192 | 0.09154 | 0.16844 | -0.088463 | -0.14017 | 0.095732 | 0.25885 | 0.52324 | 0.27096 | 0.051475
| 255 | 0.087476 | -0.017605 | -0.19881 | 0.69227 | 0.44206 | 0.1118 | 0.42703 | -0.27082 | 0.11473 | -0.061118
| 256 | 0.50878 | 0.54778 | -0.53342 | -0.046638 | 0.79531 | 0.37992 | 0.52073 | -0.30538 | -0.68047 | 0.42285
| 257 | 0.16723 | -0.0072765 | 0.14788 | 0.10776 | -0.69685 | -0.089451 | -0.18988 | -0.23508 | 0.35015 | -0.055595
| 258 | 0.062077 | 0.71242 | 0.55514 | 0.30957 | 0.27868 | -0.26386 | -0.31787 | -0.11259 | -0.50553 | 0.44529
| 259 | -0.39131 | -0.039219 | 0.96683 | 0.71104 | 0.22109 | 0.41545 | -0.69324 | 0.37606 | 0.31993 | -0.8995
| 260 | 0.39859 | -0.33781 | -0.23639 | 0.39197 | -0.14706 | -0.56285 | -0.31218 | 0.32317 | -0.69194 | -0.73411
| 261 | 0.0052639 | -0.0089904 | 0.17726 | -0.51041 | -0.32821 | 0.36368 | 0.71522 | 0.18446 | -0.63958 | -0.26278
| 262 | 0.35308 | -0.0021523 | 0.81053 | -0.12006 | -0.083976 | 0.18495 | 0.14871 | 0.087476 | 0.3038 | 0.12347
| 263 | 0.060905 | -0.60821 | -0.69718 | -0.38706 | -0.54889 | 0.028558 | 0.75241 | 0.60617 | 0.15306 | 0.44656
| 264 | -0.24323 | -0.014353 | 0.24442 | 0.5583 | -0.8882 | 0.47493 | 0.37751 | -0.26128 | -0.11281 | 0.70117
| 265 | 0.088024 | 0.36164 | -0.40192 | -0.033408 | -0.80226 | -0.76188 | -0.0093941 | -0.33705 | 0.58854 | 0.15567
| 266 | 0.033615 | -0.063037 | -0.41102 | -0.34617 | -0.44152 | -0.46121 | 0.56954 | -0.32081 | 0.24429 | 0.095954
| 267 | -0.9078 | 0.088463 | 0.051053 | 0.69817 | -0.2625 | 0.2924 | 0.28649 | 0.63545 | -0.9078 | 0.24893
| 268 | 0.71277 | -0.59689 | -0.6319 | -0.38624 | 0.019949 | -0.69162 | 0.024859 | 0.55357 | 0.50776 | -0.012022
| 269 | -0.032994 | 0.13207 | -0.31758 | 0.82651 | 0.28285 | 0.32273 | -0.67581 | -0.82308 | 0.72889 | 0.12633
| 270 | 0.78622 | -0.35 | 0.086819 | -0.039427 | 0.3651 | 0.3607 | 0.24814 | -0.68361 | 0.40662 | 0.46643
| 271 | 0.15614 | 0.31831 | -0.089012 | 0.028558 | -0.63545 | 0.5469 | 0.066994 | -0.29311 | -0.69129 | 0.47398
| 272 | 0.042451 | -0.52597 | 0.093303 | 0.27233 | -0.68361 | 0.45219 | -0.68298 | -0.083321 | 0.23091 | 0.436
| 273 | -0.25013 | -0.68267 | 0.09077 | -0.040886 | -0.6371 | 0.22392 | -0.49394 | 0.19148 | -0.59763 | 0.60617
| 274 | 0.027837 | -0.336 | -0.022606 | 0.25791 | 0.20169 | -0.56102 | 0.20344 | 0.20975 | 0.57703 | 0.29921
| 275 | -0.070645 | 0.14507 | -0.17714 | 0.40075 | 0.40797 | 0.34525 | -0.055278 | 0.23247 | -0.27206 | -0.23247
| 276 | -0.14988 | -0.029176 | -0.21789 | -0.74446 | 0.69884 | -0.5011 | 0.4999 | -0.15283 | 0.18043 | -0.38624
| 277 | 0.40797 | -0.19235 | 0.054008 | -0.18643 | 0.49572 | -0.025577 | -0.25926 | 0.4898 | -0.19408 | -0.4736
| 278 | -0.54033 | 0.352 | -0.44188 | -0.42355 | -0.35216 | 0.48164 | -0.71911 | 0.11609 | 0.63765 | -0.58708
| 279 | 0.40326 | 0.43671 | 0.87311 | 0.075392 | 0.30021 | -0.39842 | -0.023015 | 0.051475 | 0.040156 | 0.0069743
| 280 | 0.60744 | -0.02568 | -0.33449 | 0.57941 | -0.042451 | 0.53107 | 0.22534 | -0.45182 | -0.10832 | -0.31743
| 281 | 0.14215 | 0.71592 | 0.45787 | -0.17278 | -0.11236 | -0.14636 | 0.20081 | 0.085178 | 0.23678 | -0.38869
| 282 | 0.41836 | -0.18544 | -0.24112 | 0.5866 | -0.34816 | 0.352 | -0.36102 | 0.0018517 | 0.10652 | 0.23521
| 283 | -0.54956 | 0.3297 | -0.086053 | 0.39875 | 0.7496 | -0.042869 | -0.6852 | 0.30021 | 0.10989 | 0.041616
| 284 | 0.44511 | -0.10072 | -0.37207 | 0.33329 | -0.062183 | 0.0085869 | -0.084194 | 0.22482 | -0.45732 | 0.020868
| 285 | -0.061864 | -0.27233 | 0.68141 | -0.34816 | 0.11451 | -0.33329 | 0.47019 | -0.050632 | 0.072584 | 0.28271
| 286 | -0.44692 | -0.13196 | 0.40092 | -0.35169 | 0.51886 | -0.2975 | 0.62973 | -0.66162 | -0.34754 | -0.20056
| 287 | 0.032064 | 0.60541 | -0.75896 | -0.41017 | -0.025782 | 0.13692 | -0.40865 | -0.04172 | 0.96683 | -0.23391
| 288 | 0.4041 | -0.60238 | -0.3681 | -0.39925 | -0.5954 | 0.61412 | 0.32509 | -0.34281 | -0.21279 | -0.16316
| 289 | 0.33 | 0.6833 | 0.3477 | -0.22508 | -0.23404 | -0.26877 | -0.30351 | 0.23065 | -0.24165 | 0.032271
| 290 | -0.012832 | 0.031135 | 0.10351 | 0.40966 | 0.5954 | -0.7816 | 0.49295 | -0.097503 | -0.38624 | -0.35556
| 291 | 0.11586 | 0.23967 | 0.082013 | -0.45055 | -0.18495 | -0.85474 | 0.21891 | -0.020766 | -0.14215 | -0.42598
| 292 | -0.3422 | 0.77662 | 0.051475 | 0.15911 | 0.15059 | -0.016893 | 0.31174 | 0.63654 | -0.75938 | 0.57163
| 293 | -0.48241 | 0.67612 | 0.067852 | -0.2076 | 0.070215 | 0.041512 | 0.092751 | -0.080924 | 0.13357 | -0.41119
| 294 | 0.058565 | 0.36589 | -0.23091 | -0.087586 | 0.45127 | 0.88731 | -0.20722 | -0.10865 | -0.23547 | -0.088682
| 295 | 0.56583 | 0.04517 | -0.68839 | 0.24561 | -0.08234 | -0.11699 | 0.21904 | 0.36683 | 0.033201 | 0.025064
| 296 | 0.49473 | 0.12874 | 0.28383 | 0.75201 | -0.15 | 0.96683 | 0.14824 | -0.72815 | -0.73448 | -0.55312
| 297 | 0.028352 | -0.26169 | 0.18116 | 0.11824 | 0.093744 | -0.19384 | 0.58275 | 0.018522 | 0.68839 | 0.082776
| 298 | 0.47189 | -0.65634 | -0.15165 | 0.073231 | -0.1136 | 0.76063 | -0.018216 | -0.27757 | -0.62437 | -0.39033
| 299 | -0.05549 | 0.50675 | 0.33886 | 0.19458 | 0.14636 | -0.68583 | 0.10955 | -0.17205 | -0.33329 | 0.18914
| 300 | -0.38592 | -0.39742 | 0.20672 | 0.66578 | -0.31831 | -0.24231 | -0.22058 | 0.21776 | -0.40292 | -0.52282
| 301 | 0.46381 | 0.28901 | 0.42807 | -0.28341 | 0.11484 | -0.55694 | -0.060585 | 0.023322 | 0.4337 | 0.3751
| 302 | -0.28972 | 0.27371 | -0.44565 | 0.56308 | -0.23652 | -0.12336 | -0.3074 | 0.20031 | 0.22482 | 0.0078811
| 303 | 0.38836 | -0.72269 | -0.30754 | 0.070108 | -0.36731 | -0.76698 | -0.037659 | -0.35417 | 0.32717 | 0.35556
| 304 | 0.22547 | 0.19981 | 0.82766 | -0.095843 | -0.51492 | 0.15958 | 0.18889 | -0.1466 | 0.78576 | 0.18226
| 305 | 0.25347 | 0.25804 | 0.046323 | -0.95417 | 0.23234 | -0.1015 | 0.046008 | -0.042347 | 0.16639 | 0.48512
| 306 | -0.62092 | -0.74019 | -0.43511 | -0.4417 | 0.42009 | 0.34617 | 0.38121 | -0.51205 | -0.66519 | 0.60263
| 307 | -0.50959 | 0.49 | -0.84094 | -0.40983 | -0.46699 | -0.0017515 | -0.09165 | -0.17495 | 0.65057 | 0.36243
| 308 | 0.58443 | 0.14087 | -0.82941 | -0.0019519 | 0.70828 | 0.59763 | 0.25254 | 0.10217 | 0.37382 | 0.36604
| 309 | -0.11665 | -0.29779 | 0.38984 | -0.63299 | -0.033925 | 0.25953 | 0.93755 | 0.14554 | 0.55717 | 0.4392
| 310 | -0.87712 | 0.09022 | -0.73981 | -0.88467 | -0.034443 | -0.093303 | 0.0755 | 0.35401 | -0.41596 | 0.64631
| 311 | 0.53085 | -0.31553 | -0.20169 | 0.69884 | 0.65751 | 0.3568 | 0.26427 | 0.51802 | -0.089451 | -0.023424
| 312 | 0.0055655 | -0.21266 | 0.29665 | -0.44583 | 0.50331 | -0.40578 | 0.51678 | -0.73411 | 0.015063 | -0.12154
| 313 | 0.20407 | 0.40696 | -0.91112 | -0.30711 | 0.12063 | 0.73335 | 0.33075 | -0.3727 | 0.32007 | 0.11338
| 314 | 0.11518 | 0.44295 | -0.47665 | -0.011617 | 0.068496 | -0.93597 | 0.07183 | 0.076474 | -0.37382 | -0.12188
| 315 | 0.15543 | 0.49473 | 0.58563 | -0.060798 | 0.77707 | 0.24297 | -0.40008 | -0.58733 | 0.13623 | -0.32598
| 316 | 0.69162 | -0.7512 | 0.52471 | -0.56216 | -0.041929 | -0.33344 | -0.87876 | -0.25549 | 0.68488 | -0.04517
| 317 | 0.31919 | 0.38251 | 0.72779 | 0.071291 | -0.47284 | 0.13855 | 0.023629 | 0.15271 | 0.60038 | -0.08485
| 318 | 0.019337 | -0.1269 | -0.34724 | -0.69652 | 0.19632 | -0.50675 | 0.24495 | 0.45567 | 0.40561 | -0.27578
| 319 | 0.45255 | -0.15602 | -0.73186 | -0.16507 | -0.12943 | 0.55853 | 0.4258 | 0.85613 | 0.45585 | 0.60389
| 320 | -0.27 | -0.76569 | 0.32037 | 0.51637 | 0.0018517 | -0.35216 | 0.19794 | -0.68936 | 0.50553 | -0.82084
| 321 | -0.34985 | 0.059309 | -0.41136 | 0.68647 | 0.12279 | -0.30179 | -0.37159 | -0.40578 | 0.77617 | 0.86847
| 322 | 0.12222 | -0.39033 | -0.17253 | -0.046847 | -0.13878 | 0.57703 | -0.041407 | 0.59294 | 0.11405 | -0.07043
| 323 | 0.70555 | 0.43688 | -0.7623 | -0.39362 | 0.69718 | -0.52619 | 0.76442 | -0.4981 | -0.88467 | -0.098834
| 324 | 0.66519 | -0.73904 | -0.31831 | -0.040365 | 0.50231 | -0.075284 | 0.25441 | -0.16292 | 0.30365 | -0.50392
| 325 | 0.53772 | -0.16316 | 0.047897 | 0.61154 | 0.14367 | -0.1926 | -0.27799 | -0.16054 | 0.30279 | -0.67612
| 326 | -0.05422 | 0.53816 | 0.15602 | 0.53686 | -0.66728 | 0.15259 | -0.26863 | -0.2508 | 0.22173 | 0.36715
| 327 | -0.28523 | -0.60923 | 0.17 | -0.37079 | 0.41751 | -0.26577 | -0.015978 | -0.30122 | -0.5447 | -0.039219
| 328 | 0.14367 | 0.27385 | 0.014759 | -0.059947 | -0.032788 | -0.12759 | -0.1628 | 0.33615 | 0.81212 | -0.6162
| 329 | -0.3607 | -0.62677 | -0.35649 | 0.60744 | -0.40259 | 0.79776 | 0.11677 | -0.26183 | 0.41442 | 0.063891
| 330 | -0.40125 | 0.1382 | 0.14414 | 0.21699 | 0.92319 | -0.59913 | 0.26945 | -0.046847 | 0.95641 | -0.37191
| 331 | 0.59441 | -0.45073 | 0.18717 | -0.61128 | -0.74485 | 0.049369 | 0.12507 | 0.16149 | -0.39378 | -0.031341
| 332 | -0.34724 | -0.22805 | -0.43317 | 0.4542 | 0.47076 | 0.52073 | 0.55762 | 0.017809 | 0.20445 | -0.48648
| 333 | 0.35185 | 0.012225 | -0.91938 | -0.64715 | -0.59763 | -0.036309 | -0.09839 | 0.85201 | 0.054749 | -0.51389
| 334 | 0.62119 | -0.06016 | 0.536 | 0.33826 | -0.4799 | -0.46362 | 0.58371 | -0.56977 | -0.041407 | -0.16579
| 335 | -0.080163 | -0.36008 | -0.82084 | 0.15744 | -0.017503 | 0.54668 | 0.71208 | -0.58107 | 0.4163 | 0.12176
| 336 | 0.3038 | -0.002453 | -0.60898 | 0.4134 | -0.28565 | -0.11 | -0.036309 | -0.18104 | 0.32806 | 0.37783
| 337 | 0.33509 | 0.02097 | -0.4736 | 0.63931 | 0.26577 | 0.026501 | 0.66789 | -0.66074 | -0.21968 | -0.085068
| 338 | -0.65693 | -0.093854 | -0.17787 | -0.95641 | 0.33539 | 0.2326 | -0.058246 | 0.092641 | -0.34008 | -0.23613
| 339 | 0.29765 | -0.53686 | -0.39543 | -0.15177 | 0.17133 | 0.49512 | 0.54316 | 0.071399 | 0.25818 | 0.23613
| 340 | -0.35231 | 0.4293 | -0.39825 | -0.81534 | -0.55514 | 0.019643 | -0.21203 | 0.11079 | 0.31597 | 0.34433
| 341 | -0.31422 | -0.34174 | -0.70285 | 0.76569 | 0.084194 | -0.28285 | -0.13936 | 0.048317 | 0.59417 | -0.56377
| 342 | 0.079728 | -0.3419 | 0.9005 | -0.34023 | 0.15 | -0.10798 | -0.35556 | 0.30394 | 0.093082 | 0.1688
| 343 | -0.25872 | -0.25697 | -0.044019 | 0.16256 | -0.42772 | 0.086271 | 0.8956 | 0.38478 | -0.96127 | 0.31422
| 344 | -0.71069 | -0.55604 | 0.0026535 | -0.20987 | 0.32866 | 0.66608 | -0.055066 | 0.10989 | 0.86472 | 0.33149
| 345 | -0.12439 | 0.025782 | 0.31218 | -0.71277 | -0.3593 | 0.28118 | 0.11372 | -0.049053 | -0.26128 | 0.21942
| 346 | 0.24455 | -0.74212 | 0.10261 | 0.55785 | 0.58371 | 0.42043 | -0.13866 | -0.19235 | 0.10541 | 0.015673
| 347 | 0.0043595 | -0.39494 | 0.25428 | 0.20987 | -0.15578 | -0.26713 | -0.71382 | 0.10184 | 0.023732 | -0.18729
| 348 | 0.12805 | 0.7816 | -0.029588 | 0.94804 | 0.073987 | 0.20546 | 0.54033 | -0.68204 | 0.56653 | 0.70589
| 349 | 0.034236 | 0.37992 | 0.076691 | 0.43053 | -0.079402 | 0.34693 | -0.1005 | 0.29722 | -0.57822 | -0.49118
| 350 | 0.0922 | 0.2313 | 0.38105 | -0.096617 | 0.0004501 | 0.20899 | 0.056973 | -0.068174 | -0.58491 | -0.098058
| 351 | 0.28579 | -0.38186 | -0.65431 | -0.14274 | 0.27288 | 0.39676 | 0.35015 | -0.016079 | 0.093854 | 0.38105
| 352 | 0.72233 | 0.93755 | 0.15212 | -0.3369 | -0.3005 | -0.0092932 | -0.55537 | 0.59664 | 0.076907 | 0.72889
| 353 | 0.08649 | 0.31189 | -0.45273 | -0.021787 | -0.21114 | -0.13127 | -0.20911 | 0.15401 | 0.058777 | 0.70318
| 354 | 0.34846 | -0.62731 | -0.30509 | 0.17508 | 0.48357 | 0.098834 | 0.44421 | -0.67488 | -0.38315 | 0.29551
| 355 | 0.6118 | -0.55694 | 0.4588 | -0.46325 | 0.22702 | 0.17495 | 0.19198 | -0.30179 | 0.1375 | 0.41255
| 356 | -0.79579 | -0.17253 | 0.1425 | -0.027015 | -0.40309 | 0.097282 | -0.13542 | -0.7512 | 0.00085036 | -0.2791
| 357 | 0.5728 | 0.077449 | 0.37318 | -0.15436 | 0.26495 | 0.29226 | -0.075068 | 0.57397 | 0.33239 | -0.15958
| 358 | 0.38967 | 0.0051633 | 0.78206 | -0.29736 | -0.68936 | 0.17278 | -0.064853 | 0.25939 | -0.37702 | 0.38299
| 359 | 0.27688 | 0.19025 | -0.45182 | 0.4801 | 0.47952 | 0.014759 | -0.43582 | -0.81212 | -0.6241 | -0.2907
| 360 | 0.19185 | -0.24376 | 0.27896 | 0.10172 | 0.042347 | 0.6634 | -0.13727 | -0.083976 | -0.6755 | 0.036828
| 361 | -0.30971 | 0.22045 | -0.30495 | 0.094959 | 0.085615 | 0.57846 | -0.24231 | -0.70966 | -0.16328 | -0.017401
| 362 | 0.77751 | -0.92063 | 0.2711 | -0.58903 | 0.5005 | -0.11903 | 0.15271 | 0.057928 | 0.41306 | -0.5009
| 363 | 0.052213 | 0.19173 | -0.79191 | -0.15035 | 0.24231 | -0.27398 | 0.21508 | 0.4991 | -0.56377 | -0.38429
| 364 | -0.28887 | 0.063571 | -0.35123 | 0.86923 | 0.48415 | -0.3607 | 0.85752 | -0.10485 | -0.76188 | -0.30552
| 365 | -0.41425 | -0.38089 | 0.34908 | 0.30624 | 0.31743 | 0.066351 | 0.52094 | -0.16555 | -0.37127 | -0.1603
| 366 | -0.026809 | -0.009798 | 0.40175 | 0.18655 | 0.38429 | -0.01344 | -0.38592 | -0.022708 | -0.16352 | 0.33329
| 367 | -0.37494 | 0.21521 | -0.55357 | -0.11733 | 0.81318 | -0.058034 | -0.46288 | -0.12245 | 0.60719 | -0.59318
| 368 | 0.048107 | -0.5412 | 0.75813 | 0.24787 | -0.21546 | -0.23312 | 0.47914 | -0.44891 | 0.10351 | 0.12793
| 369 | -0.033925 | 0.3629 | -0.34464 | -0.45383 | 0.44242 | -0.58179 | 0.067423 | 0.65839 | -0.27385 | -0.19062
| 370 | 0.28369 | 0.068388 | 0.3817 | -0.70184 | 0.2175 | 0.017096 | 0.15472 | -0.032374 | 0.11417 | -0.039948
| 371 | -0.80176 | 0.5959 | -0.4417 | -0.24614 | 0.41272 | 0.30884 | -0.02189 | 0.22199 | 0.47151 | 0.053586
| 372 | 0.34494 | -0.12393 | 0.59689 | -0.2784 | -0.29566 | -0.22831 | 0.041094 | 0.80532 | 0.34144 | 0.08474
| 373 | -0.63299 | 0.5954 | 0.39213 | -0.050105 | 0.74446 | 0.29495 | -0.56216 | 0.24667 | -0.040156 | -0.12427
| 374 | -0.14239 | 0.41511 | 0.40225 | -0.69917 | 0.26223 | -0.19297 | -0.6044 | -0.09143 | -0.026398 | -0.14718
| 375 | -0.51328 | 0.36353 | -0.24455 | 0.63903 | 0.41034 | 0.049263 | -0.6265 | 0.062503 | 0.44529 | -0.13739
| 376 | -0.19384 | 0.23901 | -0.63271 | 0.22741 | 0.050211 | -0.60063 | 0.036413 | -0.59392 | 0.47818 | 0.41494
| 377 | 0.1015 | -0.10552 | -0.33539 | 0.16567 | 0.61803 | 0.45567 | 0.2225 | 0.029176 | -0.50331 | 0.48551
| 378 | -0.29679 | -0.39428 | -0.10228 | -0.43035 | 0.87311 | -0.53989 | 0.083539 | 0.36652 | -0.011415 | 0.18951
| 379 | -0.59417 | -0.068174 | 0.049579 | 0.5735 | -0.74407 | 0.36102 | 0.40578 | 0.25107 | 0.14519 | 0.72779
| 380 | 0.4668 | -0.40865 | 0.25656 | 0.27536 | -0.73827 | 0.53621 | -0.072153 | -0.025064 | -0.36478 | 0.4258
| 381 | -0.029588 | 0.094185 | -0.32955 | 0.57327 | -0.14052 | -0.18312 | -0.64687 | -0.20697 | 0.15141 | -0.71242
| 382 | 0.11779 | 0.46083 | 0.22521 | 0.074743 | 0.30136 | 0.11236 | 0.071614 | -0.52619 | -0.32806 | -0.14425
| 383 | 0.78251 | 0.7496 | -0.14204 | -0.47952 | -0.15887 | 0.13057 | -0.33 | 0.3242 | -0.19782 | 0.18422
| 384 | -0.66459 | -0.37175 | 0.45255 | 0.21304 | -0.081033 | 0.038803 | -0.021072 | -0.3759 | -0.16675 | 0.089012
| 385 | -0.31597 | 0.13797 | -0.10328 | -0.0059678 | 0.30639 | 0.033305 | -0.33826 | -0.36794 | 0.41085 | -0.35649
| 386 | -0.40343 | 0.057928 | -0.57585 | -0.67091 | -0.9134 | -0.013744 | -0.22405 | -0.08649 | 0.6578 | 0.7005
| 387 | -0.33555 | -0.00015001 | -0.12393 | 0.23078 | 0.11631 | -0.039844 | 0.21368 | -0.030722 | 0.57491 | -0.62039
| 388 | 0.15828 | -0.5005 | 0.36415 | -0.13449 | -0.049789 | 0.27123 | -0.27564 | -0.53535 | -0.1694 | 0.075176
| 389 | 0.13023 | -0.74761 | 0.13011 | -0.11259 | -0.14204 | 0.12324 | -0.25053 | -0.50715 | 0.45861 | -0.23705
| 390 | 0.094075 | 0.2689 | -0.48435 | -0.54734 | 0.30667 | -0.87958 | -0.18889 | 0.33314 | -0.71035 | 0.6697
| 391 | -0.42685 | -0.12805 | 0.14589 | 0.24482 | -0.3751 | 0.62277 | 0.36243 | -0.41819 | -0.3372 | 0.17241
| 392 | -0.093965 | 0.43018 | 0.43688 | -0.19557 | -0.080381 | 0.80379 | 0.025988 | 0.17072 | 0.0016514 | 0.61361
| 393 | -0.037347 | 0.6149 | -0.56331 | 0.79678 | 0.36384 | -0.1735 | 0.53213 | 0.2907 | -0.34038 | 0.11202
| 394 | 0.75979 | 0.095511 | 0.47741 | -0.2147 | 0.12188 | -0.11225 | -0.00065021 | -0.36008 | -0.79048 | -0.17121
| 395 | 0.28021 | -0.29155 | -0.69259 | -0.014353 | -0.29864 | -0.11518 | -0.24495 | 0.20445 | 0.58781 | -0.12667
| 396 | -0.29551 | 0.47 | 0.2377 | 0.098945 | 0.37718 | -0.28747 | -0.72197 | 0.10518 | -0.36353 | 0.96683
| 397 | 0.2313 | 0.12862 | -0.28944 | -0.4859 | -0.42546 | -0.17909 | -0.11983 | 0.10206 | 0.086162 | -0.18938
| 398 | -0.44656 | -0.012934 | -0.16916 | -0.083539 | -0.10485 | -0.64687 | 0.26836 | 0.54316 | 0.38885 | -0.52073
| 399 | 0.23941 | -0.10608 | -0.17084 | 0.24297 | -0.87311 | -0.69422 | 0.82766 | 0.25643 | -0.45347 | -0.52115
| 400 | 0.1375 | -0.29381 | 0.073879 | -0.34708 | 0.19595 | -0.22225 | -0.38902 | -0.10955 | 0.0922 | -0.11699
| 401 | 0.65258 | 0.10373 | 0.23325 | 0.19396 | 0.39378 | -0.037763 | -0.15071 | -0.2958 | -0.44493 | 0.40696
| 402 | 0.46605 | 0.40713 | 0.77887 | 0.070323 | -0.54756 | -0.21904 | 0.34555 | 0.75363 | 0.14496 | -0.012528
| 403 | -0.35 | 0.1245 | -0.11135 | 0.50776 | 0.23587 | 0.14029 | -0.31102 | -0.50412 | -0.6382 | -0.26822
| 404 | -0.067101 | -0.2234 | -0.77572 | 0.352 | 0.17 | 0.49374 | 0.62758 | 0.3015 | 0.37254 | -0.91693
| 405 | -0.12199 | -0.60339 | -0.27385 | 0.15484 | 0.05 | 0.26061 | -0.16388 | 0.38137 | 0.20785 | -0.12302
| 406 | 0.14122 | 0.27123 | 0.14227 | -0.35216 | 0.34846 | 0.38771 | -0.42078 | 0.11462 | -0.25267 | -0.52492
| 407 | 0.39792 | 0.42563 | -0.34159 | 0.45511 | 0.45991 | 0.49413 | -0.73261 | 0.38234 | 0.26631 | 0.7488
| 408 | -0.57023 | 0.34816 | 0.91574 | 0.3186 | -0.20244 | 0.12051 | 0.49157 | 0.57703 | -0.30538 | -0.086709
| 409 | 0.75855 | -0.063144 | -0.0049623 | -0.16077 | 0.51948 | -0.68615 | -0.13762 | 0.19384 | -0.35062 | -0.22045
| 410 | -0.3297 | -0.14777 | -0.41905 | 0.42251 | 0.32762 | -0.63517 | -0.52198 | 0.57585 | 0.17945 | -0.34908
| 411 | 0.59565 | -0.65518 | 0.076366 | 0.32406 | -0.33479 | -0.056761 | 0.0026535 | 0.252 | 0.064105 | -0.37654
| 412 | -0.53192 | -0.022708 | -0.11949 | 0.031754 | -0.34908 | -0.53107 | -0.0041586 | -0.45073 | -0.30007 | 0.29014
| 413 | 0.49315 | -0.39213 | -0.22663 | -0.098279 | 0.5883 | -0.44891 | 0.54911 | 0.10094 | 0.30682 | 0.42772
| 414 | -0.094517 | 0.1473 | -0.0079819 | 0.095511 | -0.14871 | -0.072476 | 0.34372 | 0.12245 | -0.20495 | -0.0995
| 415 | -0.36086 | 0.63654 | 0.22767 | -0.36039 | -0.45769 | -0.023629 | 0.13704 | 0.37191 | 0.86847 | 0.28132
| 416 | 0.17811 | -0.13219 | -0.13832 | -0.25831 | 0.1868 | -0.078425 | -0.094296 | -0.17217 | 0.57774 | 0.28705
| 417 | -0.76827 | 0.13623 | 0.32613 | -0.46512 | -0.27882 | 0.068174 | -0.09209 | 0.32985 | -0.025064 | 0.59888
| 418 | 0.015978 | -0.59098 | 0.037763 | -0.025372 | -0.038803 | -0.2948 | 0.74135 | -0.085287 | 0.82766 | 0.33209
| 419 | -0.30928 | 0.027015 | -0.22019 | -0.54823 | 0.21292 | 0.20798 | 0.1338 | 0.36086 | -0.23026 | 0.10195
| 420 | 0.43246 | -0.16256 | 0.38121 | -0.18483 | -0.15555 | 0.17775 | -0.071291 | 0.22096 | -0.28049 | 0.0079819
| 421 | 0.003155 | 0.63545 | 0.34846 | -0.0023528 | -0.30595 | -0.020868 | -0.29028 | 0.65809 | 0.029485 | -0.5447
| 422 | 0.24402 | 0.39033 | -0.15059 | 0.64014 | -0.0018517 | -0.5332 | -0.18361 | -0.098723 | -0.33194 | 0.016791
| 423 | 0.10061 | -0.21725 | -0.033201 | -0.016384 | -0.73335 | 0.51061 | 0.32896 | -0.56861 | -0.29936 | 0.17738
| 424 | 0.43158 | 0.10161 | -0.42389 | -0.4279 | 0.036828 | -0.7735 | 0.47952 | 0.31802 | 0.8422 | -0.51678
| 425 | 0.25912 | -0.065174 | -0.07043 | 0.12382 | -0.64293 | 0.077341 | 0.10284 | -0.1546 | -0.021072 | 0.077774
| 426 | -0.27398 | 0.17253 | -0.55424 | -0.22263 | 0.16892 | 0.34448 | 0.4392 | -0.09839 | 0.081469 | 0.52031
| 427 | -0.29395 | 0.27799 | 0.2512 | 0.31904 | -0.39659 | 0.38478 | 0.024244 | -0.54978 | 0.63435 | 0.40092
| 428 | 0.53213 | 0.71035 | 0.22071 | 0.24442 | -0.66939 | -0.46587 | 0.13346 | 0.0091922 | 0.06957 | 0.36841
| 429 | -0.3148 | -0.31772 | 0.13069 | 0.60567 | 0.21165 | -0.2571 | 0.17556 | -0.28439 | 0.19334 | 0.9219
| 430 | -0.41459 | 0.5656 | 0.53643 | -0.0064709 | -0.055807 | 0.097836 | 0.43564 | 0.18532 | -0.5768 | -0.59788
| 431 | 0.40881 | -0.56125 | 0.2133 | -0.18201 | -0.26631 | 0.83059 | -0.0023528 | 0.44152 | 0.16819 | 0.11
| 432 | -0.32955 | -0.074095 | -0.10217 | -0.29907 | 0.11903 | 0.42615 | 0.63545 | 0.49236 | -0.0781 | -0.064639
| 433 | 0.43529 | 0.46643 | -0.068281 | -0.27605 | -0.023322 | -0.17253 | 0.1646 | -0.33841 | -0.4857 | -0.23862
| 434 | 0.09529 | -0.31949 | 0.22418 | -0.20131 | 0.067101 | 0.80532 | 0.52724 | 0.22689 | -0.12747 | -0.57468
| 435 | 0.27343 | 0.25589 | -0.035894 | 0.57186 | -0.60491 | -0.14076 | -0.040886 | -0.22767 | -0.2985 | 0.12063
| 436 | -0.36589 | -0.50959 | -0.048107 | 0.46812 | 0.45055 | 0.10017 | -0.11394 | 0.37254 | -0.20382 | 0.21891
| 437 | -0.25187 | -0.69685 | 0.26332 | 0.31802 | 0.68393 | 0.82593 | 0.18495 | 0.10933 | 0.6637 | -0.33015
| 438 | 0.51225 | -0.21994 | 0.076149 | -0.27924 | -0.71347 | -0.18373 | -0.76357 | 0.48668 | 0.39378 | -0.42285
| 439 | 0.10574 | 0.0023528 | -0.89 | -0.38218 | -0.34448 | 0.54558 | -0.022196 | -0.18729 | -0.43724 | -0.56308
| 440 | -0.63765 | -0.056019 | -0.27 | 0.70794 | -0.012832 | -0.10608 | 0.094517 | 0.56745 | 0.074743 | 0.24522
| 441 | 0.033512 | 0.1418 | 0.11405 | 0.36984 | -0.88642 | 0.36117 | -0.4993 | -0.70487 | 0.008486 | 0.056443
| 442 | -0.82028 | 0.052635 | -0.61594 | -0.60795 | 0.30207 | 0.024039 | 0.40008 | -0.10395 | -0.2571 | 0.18324
| 443 | 0.41613 | -0.30179 | -0.35015 | -0.11631 | -0.024962 | -0.20596 | 0.2621 | -0.3796 | 0.70352 | 0.64321
| 444 | -0.76315 | -0.49532 | 0.45091 | -0.41034 | 0.0032553 | -0.18226 | 0.59318 | 0.69455 | 0.62946 | -0.065067
| 445 | 0.5021 | 0.35494 | -0.1797 | -0.34831 | -0.22818 | -0.028867 | -0.088682 | -0.31436 | 0.030309 | -0.26509
| 446 | -0.72889 | 0.16197 | -0.19148 | -0.34985 | -0.36086 | 0.085943 | -0.64293 | 0.47665 | 0.30136 | 0.26386
| 447 | 0.57798 | -0.09176 | 0.13994 | 0.36211 | -0.082122 | 0.18704 | 0.27757 | 0.18704 | -0.0042591 | -0.44764
| 448 | 0.10006 | 0.67519 | 0.037867 | -0.49157 | -0.64943 | 0.36149 | 0.081033 | 0.62597 | -0.1153 | 0.20094
| 449 | 0.36857 | 0.13311 | -0.02097 | -0.074959 | 0.64349 | -0.40915 | 0.18766 | 0.15923 | -0.39992 | 0.73186
| 450 | -0.74682 | -0.60013 | -0.21228 | -0.54382 | 0.013339 | 0.41034 | -0.4117 | 0.082231 | -0.0021523 | -0.073555
| 451 | -0.1323 | -0.46868 | 0.09044 | 0.068067 | 0.24482 | -0.72341 | 0.10206 | -0.51492 | -0.11699 | -0.22186
| 452 | -0.044961 | -0.82139 | -0.39875 | 0.18532 | 0.24442 | 0.029691 | 0.03974 | 0.010404 | -0.020766 | -0.093634
| 453 | -0.1688 | 0.88042 | 0.7839 | 0.12908 | -0.83417 | 0.017503 | 0.15816 | 0.25414 | 0.0018517 | -0.025885
| 454 | -0.09011 | 0.028352 | 0.19148 | 0.62224 | 0.37223 | -0.30913 | -0.10139 | -0.46812 | -0.45511 | -0.4163
| 455 | -0.26441 | -0.13948 | 0.59466 | -0.6546 | 0.13473 | -0.028455 | 0.32037 | -0.41408 | 0.44224 | 0.041825
| 456 | 0.26617 | -0.1952 | 0.076474 | 0.14589 | -0.24349 | -0.23338 | -0.35914 | -0.49651 | -0.87876 | -0.41802
| 457 | 0.3838 | -0.40949 | -0.25562 | -0.020459 | 0.37286 | -0.24151 | 0.029073 | -0.26142 | 0.46046 | 0.21114
| 458 | -0.35867 | 0.3796 | -0.38771 | -0.54426 | -0.89753 | 0.5728 | -0.62758 | 0.14496 | 0.19894 | 0.09077
| 459 | -0.29339 | -0.31305 | -0.3767 | 0.52052 | -0.20823 | 0.042869 | -0.41579 | 0.47856 | -0.080054 | 0.52345
| 460 | -0.10865 | -0.56791 | -0.31904 | -0.71208 | 0.1565 | 0.13542 | -0.06914 | -0.47417 | -0.016588 | -0.45456
| 461 | 0.31904 | 0.024346 | 0.46643 | 0.0043595 | 0.75241 | -0.23417 | -0.19235 | 0.60138 | -0.60491 | -0.54273
| 462 | 0.30279 | 0.22186 | -0.82422 | -0.35743 | -0.26509 | -0.66459 | -0.19284 | -0.32791 | -0.03714 | 0.46139
| 463 | 0.066887 | 0.83 | 0.023527 | 0.42026 | 0.3551 | 0.54207 | 0.26223 | 0.19458 | 0.27014 | -0.49216
| 464 | 0.15733 | -0.16066 | -0.0030547 | 0.85201 | -0.074203 | 0.46418 | 0.31509 | -0.50311 | 0.83177 | -0.15792
| 465 | -0.13866 | 0.043496 | -0.67984 | -0.21559 | -0.4989 | -0.17084 | -0.37254 | -0.91693 | 0.23547 | 0.11654
| 466 | 0.14052 | 0.46549 | -0.41802 | -0.089121 | 0.89753 | 0.48551 | 0.14906 | -0.53107 | 0.23338 | 0.10888
| 467 | -0.050105 | 0.24482 | -0.033408 | 0.57988 | 0.44475 | 0.29014 | -0.32465 | 0.35696 | -0.13855 | -0.2147
| 468 | 0.69194 | -0.4859 | -0.44728 | -0.31509 | 0.16376 | -0.86325 | 0.031961 | 0.35139 | 0.236 | -0.39942
| 469 | -0.30957 | 0.8366 | 0.26672 | 0.18471 | -0.39098 | -0.28495 | 0.28076 | 0.19719 | 0.74212 | 0.36762
| 470 | -0.18055 | 0.23026 | 0.75322 | -0.054114 | 0.0015512 | 0.092751 | -0.087257 | 0.31 | -0.32081 | -0.6149
| 471 | 0.0041586 | 0.030206 | -0.50939 | 0.52324 | -0.30812 | 0.76569 | -0.65868 | -0.15721 | -0.10966 | 0.40276
| 472 | -0.27938 | -0.0052639 | -0.27123 | -0.79776 | 0.2722 | -0.54911 | 0.7735 | -0.8618 | 0.77395 | 0.34678
| 473 | -0.20044 | -0.43795 | 0.65172 | -0.45567 | -0.27619 | 0.60138 | -0.22071 | -0.3629 | -0.43777 | 0.0080827
| 474 | 0.76399 | -0.19322 | 0.60213 | 0.38121 | 0.24933 | 0.075176 | 0.6637 | 0.40848 | -0.34785 | -0.041199
| 475 | -0.23718 | 0.62811 | 0.71982 | -0.40359 | -0.12393 | 0.06914 | -0.28202 | 0.33539 | 0.040469 | 0.018623
| 476 | 0.6833 | -0.86472 | -0.4258 | -0.48087 | 0.15638 | -0.54207 | 0.38722 | -0.26808 | -0.49433 | 0.11711
| 477 | 0.64943 | 0.23417 | -0.0755 | 0.21051 | 0.34785 | 0.81752 | -0.41682 | -0.47722 | 0.088902 | -0.39643
| 478 | 0.32524 | 0.029897 | 0.019337 | -0.28383 | -0.063677 | 0.020153 | 0.34785 | -0.43493 | 0.22922 | 0.29566
| 479 | -0.73411 | -0.37767 | -0.43211 | 0.65431 | -0.046638 | 0.21139 | 0.66849 | 0.19694 | 0.37478 | 0.12119
| 480 | -0.40628 | -0.35417 | -0.27137 | 0.39659 | -0.44511 | 0.30552 | -0.26386 | 0.093854 | 0.44638 | 0.29169
| 481 | -0.20344 | 0.19806 | 0.33105 | -0.10978 | 0.10664 | -0.41545 | 0.18914 | -0.060372 | -0.017096 | 0.29509
| 482 | 0.1868 | 0.49177 | 0.21304 | -0.024654 | 0.71911 | -0.69553 | -0.16663 | -0.021072 | -0.21994 | 0.83907
| 483 | -0.16042 | -0.085068 | 0.48183 | 0.048738 | -0.64377 | -0.40527 | 0.6697 | -0.22353 | -0.05899 | -0.9245
| 484 | 0.81106 | 0.1204 | 0.51246 | -0.0011507 | 0.061011 | 0.21343 | 0.45127 | -0.5332 | 0.19919 | 0.18348
| 485 | 0.22431 | -0.71104 | -0.3357 | -0.86696 | 0.18006 | 0.094406 | -0.20987 | -0.58878 | -0.11349 | -0.36415
| 486 | 0.26604 | -0.83297 | -0.37382 | 0.18495 | 0.077232 | -0.49572 | -0.22715 | -0.05814 | 0.9219 | -0.62597
| 487 | 0.34816 | 0.77131 | 0.10708 | 0.044123 | -0.55424 | -0.05158 | -0.2133 | -0.084413 | 0.10697 | 0.3735
| 488 | -0.47076 | -0.36857 | 0.77977 | -0.37414 | 0.038283 | 0.015165 | -0.72559 | -0.37831 | 0.3838 | 0.15224
| 489 | 0.045065 | 0.18128 | -0.20735 | 0.14157 | -0.11496 | -0.33524 | -0.018012 | -0.057503 | 0.58684 | -0.76612
| 490 | -0.3454 | 0.015774 | 0.49433 | -0.52873 | 0.35139 | -0.3005 | 0.68936 | 0.74722 | -0.94615 | 0.20495
| 491 | 0.21546 | -0.236 | 0.50959 | 0.5332 | -0.41716 | 0.15436 | -0.093303 | 0.3363 | -0.54207 | -0.54712
| 492 | -0.10652 | -0.5143 | 0.038179 | -0.34038 | 0.62039 | 0.61128 | 0.22495 | -0.15697 | 0.61646 | 0.0063703
| 493 | -0.18165 | -0.049474 | -0.0781 | 0.25441 | 0.43299 | 0.19994 | -0.12404 | 0.013846 | 0.085506 | -0.35945
| 494 | -0.83237 | -0.4542 | 0.68078 | -0.24814 | -0.17084 | -0.20257 | -0.05158 | 0.19806 | -0.10787 | -0.6634
| 495 | -0.074419 | -0.24086 | 0.2625 | 0.20495 | 0.19235 | 0.47856 | 0.29665 | 0.2689 | -0.40142 | -0.052213
| 496 | -0.65489 | 0.5174 | 0.29452 | -0.94255 | 0.8995 | 0.10865 | 0.020663 | 0.38332 | -0.2326 | -0.1308
| 497 | 0.016181 | 0.51266 | 0.35432 | 0.18177 | 0.055807 | 0.080054 | 0.44009 | -0.51595 | 0.18729 | -0.30222
| 498 | -0.49 | 0.47474 | -0.37558 | -0.13104 | -0.17592 | 0.33075 | 0.26183 | 0.72197 | -0.77707 | -0.54492
| 499 | -0.22444 | -0.74525 | -0.63572 | -0.40611 | 0.31363 | -0.59863 | 0.25939 | -0.087695 | -0.51865 | -0.65985
| 500 | -0.45769 | 0.39975 | -0.28216 | 0.3804 | 0.68235 | -0.33826 | 0.21584 | 0.24086 | 0.27495 | -0.030103
| 501 | 0.8739 | -0.19919 | -0.22071 | -0.20886 | 0.26359 | 0.57585 | 0.32081 | 0.65897 | 0.14472 | 0.056125
| 502 | -0.016689 | -0.24416 | 0.35883 | 0.54076 | 0.6755 | 0.12461 | -0.68839 | 0.14507 | 0.17362 | 0.068496
| 503 | 0.30064 | -0.14648 | -0.28789 | 0.27716 | 0.64237 | 0.49691 | 0.62145 | 0.29254 | 0.22109 | -0.79727
| 504 | 0.2484 | 0.09011 | 0.024551 | -0.19669 | -0.10473 | -0.76315 | -0.76527 | 0.01 | -0.041512 | -0.18889
| 505 | -0.075284 | 0.23718 | 0.45861 | 0.45824 | 0.4392 | 0.055807 | 0.32376 | 0.53021 | -0.25535 | -0.19371
| 506 | 0.56884 | -0.037659 | -0.52492 | -0.29694 | -0.1786 | 0.8043 | -0.12587 | -0.68078 | -0.22676 | 0.28313
| 507 | -0.5663 | 0.33871 | 0.65402 | -0.068067 | 0.58467 | 0.11869 | -0.016283 | 0.37927 | 0.14507 | 0.05549
| 508 | -0.27247 | -0.0755 | 0.2484 | 0.58371 | 0.78952 | 0.15851 | -0.73637 | 0.10888 | -0.28118 | 0.31131
| 509 | 0.80532 | 0.58539 | 0.078968 | 0.21776 | -0.37976 | -0.38575 | 0.50614 | 0.60238 | -0.45493 | 0.26959
| 510 | -0.017605 | -0.14871 | 0.14169 | 0.42112 | 0.057716 | -0.18581 | 0.26699 | 0.1752 | 0.14227 | -0.95204
| 511 | -0.27564 | 0.48376 | -0.036828 | 0.2924 | 0.2711 | 0.77439 | -0.038595 | -0.18877 | 0.54756 | 0.42615
| 512 | -0.0056661 | -0.37095 | -0.54778 | 0.37718 | 0.3132 | -0.3838 | -0.68583 | -0.93443 | -0.76698 | 0.10273
| 513 | 0.55357 | 0.41085 | 0.76784 | 0.44009 | -0.52703 | 0.59788 | -0.34662 | 0.14192 | 0.26115 | -0.29452
| 514 | 0.056443 | -0.27591 | -0.08136 | -0.92584 | -0.65809 | -0.17994 | -0.029794 | -0.16543 | 0.16844 | -0.2816
| 515 | -0.030619 | 0.73037 | 0.35169 | -0.41545 | 0.21304 | 0.17957 | -0.40713 | 0.00075028 | 0.028043 | -0.043914
| 516 | -0.66849 | 0.10451 | -0.31465 | 0.055595 | 0.26986 | 0.22276 | 0.35743 | -0.0032553 | -0.29893 | -0.67922
| 517 | 0.48493 | 0.34555 | 0.49532 | -0.19707 | -0.36196 | 0.43884 | -0.48629 | 0.85134 | 0.2326 | 0.87311
| 518 | -0.39444 | 0.51041 | -0.17544 | -0.6249 | -0.022606 | 0.35092 | 0.15792 | 0.42877 | -0.3817 | 0.023424
| 519 | -0.089231 | -0.077666 | 0.38967 | -0.024449 | 0.64687 | 0.045275 | -0.64857 | 0.35899 | -0.74019 | -0.41682
| 520 | 0.15059 | -0.0071757 | 0.46306 | 0.047267 | 0.21114 | 0.28986 | 0.22844 | -0.21457 | 0.16831 | 0.40578
| 521 | 0.4194 | -0.33766 | 0.1841 | 0.50271 | 0.0088895 | -0.39676 | -0.38186 | 0.066994 | 0.3743 | 0.4653
| 522 | -0.037763 | 0.40309 | 0.14192 | 0.010707 | 0.16472 | 0.5447 | -0.51 | -0.022299 | 0.64801 | -0.22122
| 523 | 0.23351 | 0.41425 | -0.88909 | -0.35139 | -0.26386 | -0.43582 | -0.45972 | 0.16173 | -0.47341 | -0.39411
| 524 | 0.72669 | 0.10787 | 0.11157 | -0.49453 | 0.48241 | 0.063571 | 0.05348 | 0.54207 | -0.1261 | 0.083212
| 525 | 0.56977 | 0.3743 | -0.72414 | -0.91693 | 0.68456 | -0.39115 | -0.31728 | 0.074095 | -0.1597 | 0.52661
| 526 | -0.24721 | 0.020153 | 0.65201 | -0.11665 | -0.5005 | 0.0911 | 0.22767 | 0.12828 | -0.024962 | -0.63027
| 527 | 0.10161 | -0.83969 | -0.14052 | 0.80328 | -0.092862 | 0.72963 | -0.0065716 | 0.44891 | -0.14718 | -0.39626
| 528 | -0.014252 | 0.046218 | -0.47894 | -0.40494 | -0.28901 | -0.42251 | 0.55022 | -0.0093941 | -0.79482 | 0.28285
| 529 | 0.56606 | -0.6703 | -0.10306 | 0.027426 | -0.19012 | 0.73149 | 0.9005 | -0.23731 | 0.28146 | -0.20672
| 530 | 0.41136 | -0.42164 | 0.65897 | -0.098058 | 0.22987 | 0.2147 | -0.51616 | -0.16591 | -0.56057 | 0.27123
| 531 | -0.67984 | -0.09154 | -0.14029 | -0.44313 | -0.21038 | -0.30682 | 0.10039 | 0.41408 | -0.5005 | 0.24694
| 532 | 0.038699 | -0.50756 | -0.071291 | 0.0077803 | -0.27896 | 0.3743 | -0.013947 | 0.4542 | -0.2948 | 0.011112
| 533 | -0.17278 | -0.42459 | 0.2975 | 0.48609 | -0.029073 | -0.45073 | -0.24007 | 0.61829 | 0.41682 | 0.24455
| 534 | -0.49473 | -0.0068736 | -0.043391 | 0.32985 | -0.25027 | 0.23574 | 0.28397 | -0.54163 | 0.43617 | 0.0065716
| 535 | 0.63 | -0.60138 | 0.35123 | -0.21776 | 0.54054 | -0.47265 | 0.4553 | 0.58805 | -0.51307 | 0.31495
| 536 | 0.066565 | 0.42877 | 0.5883 | -0.32081 | -0.13253 | -0.4991 | -0.49691 | -0.021685 | 0.94255 | -0.42668
| 537 | -0.37654 | -0.35945 | 0.40797 | -0.19819 | 0.36747 | -0.45438 | 0.22857 | -0.066244 | -0.31058 | -0.21955
| 538 | -0.2722 | 0.22909 | -0.74682 | -0.09154 | -0.21738 | 0.23351 | 0.33932 | 0.06603 | -0.72963 | -0.19769
| 539 | -0.49691 | 0.55649 | -0.80895 | -0.16519 | -0.046742 | 0.16952 | 0.24138 | 0.14402 | 0.14437 | -0.54734
| 540 | 0.31524 | 0.37111 | -0.29381 | -0.23104 | 0.53556 | 0.32465 | 0.13681 | 0.15555 | 0.043496 | 0.72742
| 541 | 0.39115 | 0.24086 | -0.41991 | -0.24694 | 0.55156 | 0.43546 | 0.60592 | -0.55943 | -0.69884 | -0.0058672
| 542 | 0.045799 | 0.53342 | 0.19894 | 0.39444 | 0.16066 | 0.45 | 0.31102 | -0.67735 | -0.43193 | 0.81972
| 543 | -0.1308 | 0.17532 | -0.68267 | -0.1841 | -0.26318 | -0.34954 | -0.22922 | 0.65143 | 0.61961 | -0.019031
| 544 | -0.75282 | -0.25214 | -0.19533 | -0.14777 | 0.89183 | 0.6233 | 0.77218 | -0.2941 | -0.039219 | 0.32435
| 545 | 0.13138 | 0.025269 | -0.21955 | -0.1962 | -0.073231 | 0.61646 | 0.39925 | -0.024962 | -0.18385 | -0.025064
| 546 | 0.70931 | 0.078534 | 0.43866 | 0.085834 | 0.093965 | -0.62357 | 0.11451 | -0.78529 | -0.13623 | -0.30783
| 547 | 0.034547 | 0.39859 | 0.1005 | 0.55 | -0.64321 | 0.61568 | -0.31116 | -0.19359 | -0.22818 | 0.32214
| 548 | 0.056337 | -0.11146 | 0.4717 | -0.043601 | 0.14006 | -0.016689 | -0.24046 | -0.0080827 | 0.33224 | -0.068711
| 549 | 0.31261 | -0.23247 | 0.13959 | 0.61387 | -0.35774 | -0.38673 | -0.58903 | -0.012427 | 0.32096 | 0.18864
| 550 | 0.36984 | -0.27288 | 0.9078 | -0.44764 | -0.69259 | 0.39494 | 0.10888 | -0.80125 | 0.11869 | -0.14695
| 551 | 0.7005 | 0.21063 | -0.69065 | 0.79143 | 0.69292 | -0.18434 | 0.092421 | 0.11972 | 0.13104 | 0.088353
| 552 | 0.16615 | 0.27868 | 0.34311 | -0.50351 | -0.43529 | 0.33314 | 0.43158 | 0.48843 | -0.44692 | -0.30293
| 553 | -0.035272 | -0.11079 | -0.16988 | 0.14965 | 0.62731 | -0.22045 | -0.21025 | 0.34647 | -0.50432 | -0.13542
| 554 | 0.69817 | 0.28719 | 0.59963 | -0.23744 | -0.070753 | 0.46288 | -0.16579 | -0.33329 | 0.44188 | 0.085178
| 555 | -0.01182 | -0.028661 | 0.14636 | -0.2427 | -0.28383 | 0.22006 | 0.21776 | 0.67829 | 0.15247 | 0.32925
| 556 | 0.36604 | 0.44027 | 0.36905 | -0.33509 | 0.48512 | 0.88381 | 0.085396 | 0.51637 | 0.20646 | 0.064105
| 557 | 0.62919 | 0.049158 | 0.68615 | -0.22573 | -0.23587 | -0.24933 | -0.28481 | -0.19831 | 0.67243 | 0.21406
| 558 | 0.34678 | 0.40259 | 0.11824 | 0.60465 | 0.10028 | -0.4163 | 0.20709 | -0.36196 | 0.55402 | -0.53256
| 559 | -0.013339 | 0.3025 | -0.61856 | -0.60289 | 0.59049 | 0.0089904 | 0.62624 | 0.038283 | -0.31451 | 0.1015
| 560 | -0.52957 | 0.42216 | 0.55604 | 0.31641 | 0.38008 | 0.017809 | 0.85 | 0.12519 | 0.071399 | -0.27412
| 561 | 0.37079 | -0.02897 | -0.5224 | -0.38951 | 0.013947 | 0.089231 | -0.1338 | -0.14859 | -0.052952 | -0.066994
| 562 | -0.2733 | -0.081904 | -0.023834 | -0.47132 | 0.0036567 | -0.27578 | -0.030103 | -0.2161 | 0.20219 | 0.29282
| 563 | 0.89656 | 0.20886 | -0.46587 | -0.78858 | 0.1921 | -0.023936 | 0.30308 | 0.28887 | 0.8995 | -0.27041
| 564 | 0.23169 | -0.073555 | 0.45751 | 0.20081 | -0.52979 | -0.89 | 0.5412 | -0.69784 | 0.14204 | 0.26699
| 565 | -0.12302 | -0.51823 | -0.23534 | 0.36589 | -0.63353 | -0.44277 | 0.78114 | 0.82084 | -0.14542 | 0.36573
| 566 | -0.39263 | 0.16807 | 0.29311 | -0.84736 | 0.21968 | 0.22045 | 0.42407 | -0.58275 | -0.023732 | 0.034858
| 567 | 0.20533 | -0.40292 | -0.61154 | 0.22006 | -0.57562 | 0.32836 | 0.61309 | -0.026604 | 0.5141 | 0.020766
| 568 | 0.019949 | -0.0039578 | 0.54668 | 0.089451 | 0.42389 | -0.2234 | -0.018522 | 0.037347 | 0.45401 | 0.45898
| 569 | 0.78905 | -0.64042 | 0.49413 | -0.22019 | -0.43158 | 0.32037 | 0.37863 | -0.06016 | -0.17629 | -0.31131
| 570 | -0.18079 | 0.62013 | 0.28021 | -0.55089 | -0.17896 | -0.26536 | 0.59913 | 0.12839 | 0.092311 | -0.62543
| 571 | 0.76272 | -0.0049623 | 0.097282 | 0.3923 | -0.26945 | -0.062077 | -0.53 | -0.20508 | 0.35123 | 0.44134
| 572 | -0.22096 | 0.46232 | 0.10094 | -0.45954 | -0.29736 | -0.37863 | -0.045694 | -0.071614 | 0.20269 | 0.12587
| 573 | 0.40075 | -0.61077 | 0.14507 | 0.011719 | 0.548 | -0.054114 | -0.52957 | -0.40881 | 0.083867 | -0.65489
| 574 | -0.043914 | 0.0060684 | -0.41051 | 0.061757 | 0.71663 | -0.5102 | -0.18594 | 0.28705 | 0.44837 | 0.77707
| 575 | -0.59196 | 0.56102 | -0.18067 | -0.007478 | 0.29979 | -0.71911 | -0.22637 | -0.22392 | -0.36023 | -0.44475
| 576 | 0.14753 | -0.35324 | 0.36731 | -0.37191 | 0.57656 | 0.47952 | -0.20332 | 0.75566 | -0.063571 | -0.52576
| 577 | 0.65634 | 0.16711 | -0.54098 | -0.62092 | 0.93443 | -0.65956 | 0.15177 | 0.94615 | -0.096839 | -0.17508
| 578 | 0.43724 | 0.70725 | -0.0021523 | 0.42772 | -0.62066 | -0.08978 | -0.096396 | -0.32672 | 0.070323 | -0.092641
| 579 | 0.054855 | 0.1546 | 0.21406 | -0.31451 | -0.31145 | -0.070108 | -0.35324 | -0.92859 | 0.32955 | -0.51102
| 580 | 0.52809 | 0.48164 | -0.0042591 | -0.30783 | -0.1735 | -0.23809 | -0.41922 | -0.89464 | 0.18165 | 0.067852
| 581 | -0.64971 | 0.67366 | -0.15271 | 0.39958 | 0.14695 | 0.72852 | 0.11949 | 0.10978 | -0.092531 | -0.31787
| 582 | 0.78297 | 0.61257 | -0.079728 | -0.056125 | -0.64349 | 0.43866 | -0.4194 | -0.56194 | -0.84348 | 0.79579
| 583 | -0.13299 | -0.27316 | 0.50412 | -0.2995 | 0.04517 | -0.76569 | -0.17605 | -0.40427 | 0.40058 | 0.17763
| 584 | 0.45347 | 0.06293 | -0.24522 | 0.24907 | 0.82308 | 0.29367 | -0.047477 | -0.12017 | 0.15413 | 0.22418
| 585 | -0.22637 | -0.076258 | 0.52724 | -0.41136 | -0.30193 | -0.24323 | -0.066458 | -0.32214 | -0.24734 | 0.11722
| 586 | 0.15626 | 0.92859 | -0.056231 | 0.38559 | 0.41682 | 0.75566 | 0.37191 | -0.20495 | 0.21482 | 0.1432
| 587 | 0.53385 | -0.41596 | -0.63435 | -0.76399 | 0.36541 | -0.33781 | 0.49216 | 0.39742 | -0.46512 | -0.42685
| 588 | 0.52979 | 0.32184 | -0.11034 | 0.47703 | 0.66549 | 0.33871 | 0.5201 | 0.20458 | -0.41374 | -0.65143
| 589 | 0.57303 | -0.40611 | 0.56194 | 0.34403 | -0.28271 | -0.06229 | -0.25953 | -0.35914 | -0.1884 | -0.16077
| 590 | 0.35961 | -0.044019 | 0.079728 | 0.1082 | -0.28509 | 0.44063 | -0.52177 | 0.26781 | -0.32214 | -0.53
| 591 | -0.62838 | 0.36086 | -0.21432 | 0.093744 | -0.65897 | 0.22366 | 0.37207 | 0.5001 | -0.27938 | -0.7623
| 592 | 0.85752 | -0.25347 | 0.70725 | -0.13785 | -0.36794 | 0.71592 | -0.22935 | 0.059096 | -0.019745 | 0.6985
| 593 | 0.018522 | -0.13658 | -0.47341 | -0.36573 | 0.43635 | -0.26563 | 0.38592 | -0.36636 | 0.37976 | 0.56102
| 594 | -0.46981 | 0.18938 | -0.046008 | 0.17763 | 0.24787 | -0.24402 | 0.60263 | 0.30036 | 0.41665 | -0.67953
| 595 | -0.55627 | 0.058246 | -0.047897 | -0.55898 | 0.58491 | 0.47398 | -0.39726 | 0.19645 | 0.0077803 | -0.059521
| 596 | -0.53085 | -0.25939 | -0.00085036 | -0.11801 | 0.90253 | 0.014049 | -0.75201 | -0.29296 | -0.39 | -0.20269
| 597 | -0.26305 | -0.36023 | -0.10787 | 0.95417 | 0.36841 | -0.15389 | 0.47741 | -0.19694 | -0.36889 | -0.19707
| 598 | 0.36826 | 0.048843 | 0.02609 | -0.29042 | -0.32037 | -0.1559 | 0.84801 | -0.39131 | -0.46925 | -0.39279
| 599 | -0.9245 | 0.36699 | -0.10675 | -0.29085 | 0.26237 | -0.2674 | 0.65431 | -0.67335 | -0.61438 | 0.034547
| 600 | 0.23039 | -0.046952 | 0.16472 | 0.42511 | -0.076258 | -0.078317 | 0.27014 | -0.55134 | -0.85613 | 0.092641
| 601 | -0.0035563 | 0.12142 | 0.83297 | -0.36541 | 0.31875 | -0.29921 | 0.63163 | -0.010707 | -0.45146 | 0.25508
| 602 | -0.20156 | 0.18815 | 0.5347 | -0.65663 | -0.63682 | -0.42372 | -0.010404 | 0.15935 | -0.019031 | -0.53385
| 603 | 0.63108 | -0.31568 | 0.21114 | 0.026501 | -0.55469 | 0.63517 | 0.32258 | 0.059415 | 0.73037 | -0.15768
| 604 | -0.34448 | 0.097614 | 0.63986 | -0.44909 | -0.71522 | 0.0073772 | -0.21343 | -0.65287 | 0.67984 | -0.36952
| 605 | 0.34372 | -0.20294 | 0.030516 | -0.36258 | 0.148 | -0.28202 | -0.079728 | -0.33239 | 0.055807 | 0.62463
| 606 | 0.41699 | 0.32081 | -0.76021 | 0.36668 | -0.10776 | -0.58275 | 0.62704 | -0.13808 | -0.10708 | -0.20019
| 607 | -0.24694 | -0.1015 | 0.2488 | -0.09011 | 0.65956 | 0.13565 | -0.4653 | -0.49631 | -0.14484 | -0.0082843
| 608 | -0.51844 | -0.022196 | -0.30899 | -0.25535 | 0.50756 | -0.67213 | 0.073231 | 0.13623 | 0.17605 | -0.57751
| 609 | -0.52703 | 0.34053 | 0.016181 | -0.16591 | 0.057185 | 0.68615 | 0.17 | 0.57917 | 0.25227 | 0.73037
| 610 | 0.45585 | 0.4471 | -0.049579 | 0.27509 | -0.43281 | 0.56377 | 0.66074 | 0.15744 | 0.22392 | -0.18263
| 611 | -0.82708 | -0.064746 | -0.13542 | 0.050632 | -0.46456 | 0.20937 | -0.2784 | -0.45751 | -0.54492 | -0.54207
| 612 | 0.71173 | -0.32125 | 0.12427 | -0.68425 | -0.071614 | 0.71875 | -0.19757 | -0.74135 | -0.095732 | -0.36715
| 613 | -0.34129 | 0.2161 | -0.013643 | 0.026193 | -0.4857 | -0.68968 | -0.28579 | -0.26577 | 0.25777 | 0.2985
| 614 | -0.47933 | -0.39115 | -0.57515 | -0.0048618 | -0.65634 | 0.019031 | -0.088902 | 0.062183 | 0.1775 | -0.46121
| 615 | -0.054326 | -0.38348 | 0.14988 | 0.3116 | 0.32258 | 0.27744 | 0.52555 | -0.074527 | -0.13553 | -0.2161
| 616 | 0.39312 | 0.41785 | -0.17205 | 0.38283 | -0.68078 | -0.083539 | 0.83783 | -0.21738 | -0.079837 | 0.21139
| 617 | 0.88126 | -0.10652 | 0.81972 | 0.35821 | -0.098169 | 0.10518 | -0.16436 | -0.016994 | -0.40511 | -0.56722
| 618 | -0.28327 | 0.56907 | 0.49275 | 0.1353 | 0.25361 | -0.20634 | -0.60846 | -0.39164 | -0.35603 | 0.33917
| 619 | -0.58854 | -0.35992 | -0.68361 | 0.012528 | -0.52661 | -0.93443 | 0.37302 | -0.37767 | -0.4588 | 0.53751
| 620 | -0.17714 | -0.52809 | -0.15756 | 0.036413 | 0.37767 | -0.65576 | 0.64237 | 0.66728 | -0.23823 | -0.6249
| 621 | 0.09055 | 0.063144 | -0.60617 | 0.78716 | 0.40746 | -0.046533 | -0.0075787 | -0.59813 | -0.33434 | -0.86621
| 622 | 0.057609 | -0.16531 | -0.45935 | 0.33645 | -0.02189 | -0.30064 | -0.35108 | 0.24987 | 0.77439 | 0.60465
| 623 | -0.15389 | -0.30451 | 0.53043 | 0.32465 | -0.12587 | -0.27082 | 0.42895 | 0.79384 | 0.18532 | 0.05158
| 624 | -0.044123 | -0.83118 | 0.01415 | 0.049789 | 0.44457 | 0.062077 | -0.36715 | -0.15496 | -0.14064 | -0.58012
| 625 | -0.66103 | -0.11938 | 0.27799 | -0.065495 | -0.066994 | -0.17459 | -0.20583 | 0.78114 | -0.43617 | -0.43617
| 626 | -0.49552 | -0.65316 | 0.31363 | -0.32007 | -0.45365 | 0.60821 | 0.14706 | 0.11654 | 0.28495 | -0.48183
| 627 | 0.4272 | -0.19508 | 0.15614 | 0.84476 | 0.72926 | -0.16161 | -0.40898 | -0.28299 | 0.39859 | 0.4981
| 628 | 0.12233 | 0.2773 | 0.098723 | 0.28677 | -0.30639 | -0.83297 | -0.81534 | 0.19657 | -0.69983 | -0.36778
| 629 | -0.32376 | 0.0039578 | -0.20583 | 0.3312 | 0.41221 | 0.57 | -0.0046609 | -0.070968 | 0.17169 | -0.2893
| 630 | 0.16376 | 0.044228 | 0.049474 | -0.49671 | 0.10117 | -0.074311 | -0.13196 | -0.35169 | -0.10462 | -0.51699
| 631 | 0.25899 | -0.71208 | 0.13971 | -0.43423 | -0.70657 | 0.14204 | 0.30136 | -0.29141 | 0.50675 | 0.17459
| 632 | -0.20458 | 0.26699 | -0.39016 | -0.70931 | -0.15982 | 0.28313 | -0.077341 | 0.34418 | -0.053374 | 0.51307
| 633 | -0.2907 | 0.3419 | 0.24376 | -0.34099 | 0.13322 | -0.5866 | 0.34357 | -0.43053 | 0.53171 | 0.76527
| 634 | 0.80791 | -0.25966 | 0.062717 | 0.42216 | 0.21241 | 0.047162 | 0.15744 | -0.5412 | -0.44045 | 0.14578
| 635 | 0.14111 | 0.38526 | -0.12074 | -0.72559 | 0.69097 | -0.075068 | 0.6257 | -0.24774 | -0.43018 | 0.4826
| 636 | -0.24787 | 0.10944 | 0.41682 | -0.08474 | -0.45658 | -0.60038 | 0.15496 | 0.1533 | 0.82708 | 0.32169
| 637 | -0.058777 | -0.3129 | -0.32747 | -0.19545 | 0.45843 | -0.29169 | -0.11022 | -0.3618 | 0.60592 | 0.47856
| 638 | -0.20672 | 0.90356 | 0.48087 | -0.83907 | 0.60744 | 0.37286 | -0.15982 | -0.24522 | 0.0048618 | -0.18581
| 639 | -0.64042 | 0.11112 | 0.31232 | -0.0047613 | -0.29085 | 0.012731 | -0.31422 | -0.044228 | -0.16687 | -0.47132
| 640 | 0.02322 | -0.095732 | -0.64042 | 0.82593 | 0.04381 | -0.83907 | 0.2733 | -0.24614 | 0.043914 | 0.01486
| 641 | -0.23731 | 0.16244 | 0.53342 | -0.38853 | -0.26822 | -0.79678 | -0.16807 | -0.45954 | 0.65956 | 0.45769
| 642 | 0.29907 | 0.034236 | 0.027015 | 0.58323 | 0.061437 | 0.63408 | -0.069355 | -0.1015 | -0.72161 | 0.047372
| 643 | -0.63326 | -0.18226 | 0.06197 | -0.035065 | 0.072153 | 0.26291 | -0.11915 | 0.04517 | 0.38787 | 0.18729
| 644 | 0.3116 | 0.25818 | 0.05984 | -0.74722 | -0.56653 | 0.094738 | -0.033822 | -0.26318 | 0.09198 | -0.36573
| 645 | -0.14192 | -0.22792 | 0.022196 | 0.29268 | 0.31699 | 0.78529 | 0.47265 | -0.037659 | -0.058671 | 0.49671
| 646 | -0.75444 | 0.93292 | 0.34008 | -0.23639 | -0.035998 | 0.47684 | 0.23 | -0.024244 | 0.33871 | -0.040469
| 647 | 0.35139 | 0.40108 | 0.0037571 | -0.82139 | 0.089451 | -0.26645 | 0.1706 | 0.068281 | 0.65985 | -0.35401
| 648 | -0.18815 | 0.16328 | -0.015673 | -0.23404 | 0.58155 | 0.43211 | -0.74368 | 0.14519 | -0.19906 | 0.6257
| 649 | -0.35154 | 0.12644 | -0.12507 | 0.73411 | -0.20031 | 0.28216 | 0.16844 | -0.04026 | 0.31087 | 0.29793
| 650 | 0.37686 | -0.53043 | -0.47227 | 0.43493 | -0.60516 | 0.11383 | -0.53043 | -0.69422 | 0.5529 | 0.074419
| 651 | 0.21013 | 0.2504 | -0.09088 | -0.36337 | -0.58563 | 0.37064 | 0.035376 | 0.17763 | -0.36463 | 0.0071757
| 652 | -0.092751 | -0.16615 | -0.11564 | 0.39692 | 0.48087 | -0.28537 | -0.18043 | -0.7504 | -0.63682 | 0.50594
| 653 | 0.33419 | -0.89183 | -0.20207 | -0.14589 | 0.37542 | 0.24455 | 0.36604 | -0.14824 | 0.5469 | -0.44045
| 654 | 0.18055 | -0.53064 | -0.42511 | -0.51205 | -0.0922 | -0.020663 | 0.47227 | 0.11847 | -0.77483 | -0.045065
| 655 | -0.94084 | -0.62811 | 0.41238 | 0.47151 | 0.50675 | 0.29212 | 0.14918 | 0.037867 | -0.61051 | 0.051897
| 656 | 0.14706 | -0.12793 | 0.77306 | -0.44547 | -0.23221 | -0.48299 | 0.28341 | 0.093744 | -0.77306 | -0.11383
| 657 | 0.55111 | -0.65172 | 0.70691 | -0.18422 | -0.38121 | -0.48961 | 0.23875 | 0.012225 | -0.43688 | -0.10876
| 658 | 0.66578 | -0.364 | -0.22135 | -0.23967 | 0.050842 | 0.15236 | 0.54889 | 0.26686 | -0.10083 | -0.34129
| 659 | -0.15472 | -0.5224 | -0.096728 | 0.79384 | 0.62624 | 0.18201 | 0.068388 | 0.20257 | 0.050737 | 0.092862
| 660 | -0.60013 | -0.071399 | -0.70352 | 0.10418 | 0.05158 | 0.16711 | -0.14894 | -0.71875 | -0.2431 | -0.73524
| 661 | -0.10083 | 0.49118 | -0.36699 | 0.72559 | -0.50735 | 0.013238 | 0.40881 | 0.051686 | 0.37 | -0.14041
| 662 | 0.136 | -0.81697 | 0.058353 | 0.17884 | -0.23534 | -0.27993 | 0.14344 | 0.83721 | 0.76569 | 0.47741
| 663 | -0.44152 | -0.70623 | 0.18864 | 0.39859 | -0.12267 | 0.074635 | 0.47933 | -0.10518 | 0.88467 | -0.37992
| 664 | -0.79191 | -0.41153 | 0.47914 | -0.079185 | 0.8747 | -0.19371 | -0.45036 | 0.46512 | 0.61464 | -0.10496
| 665 | 0.21559 | 0.027735 | -0.22611 | 0.043496 | -0.12199 | 0.17157 | 0.56148 | 0.41136 | 0.046742 | 0.27965
| 666 | 0.20899 | 0.21241 | -0.49532 | 0.083539 | 0.44855 | 0.012225 | -0.35821 | -0.058671 | -0.30855 | 0.17012
| 667 | 0.16567 | 0.19508 | 0.33917 | 0.43123 | -0.35821 | 0.18153 | -0.052319 | -0.18055 | -0.068818 | 0.8821
| 668 | -0.27951 | 0.76484 | 0.11835 | 0.58878 | 0.35293 | 0.26196 | -0.033201 | -0.16747 | 0.43902 | 0.15923
| 669 | 0.61 | 0.1091 | 0.26727 | 0.30451 | 0.29765 | 0.9078 | 0.29722 | 0.40326 | 0.35324 | 0.0066723
| 670 | -0.19981 | 0.40092 | -0.11394 | 0.57893 | -0.56699 | 0.3048 | -0.3568 | 0.44945 | -0.72596 | 0.081686
| 671 | 0.81 | -0.21917 | -0.43688 | -0.0078811 | 0.057822 | -0.31714 | -0.30337 | -0.007478 | -0.015267 | 0.73223
| 672 | -0.4117 | -0.17641 | -0.20094 | 0.35077 | -0.010303 | 0.23052 | -0.18275 | -0.67704 | -0.44421 | -0.35092
| 673 | -0.076474 | 0.76146 | -0.63462 | 0.39016 | -0.29907 | -0.60415 | 0.59024 | 0.29551 | -0.26481 | -0.33209
| 674 | 0.062503 | 0.28132 | -0.31145 | 0.081686 | 0.58012 | 0.10675 | -0.54911 | 0.4989 | -0.21763 | -0.9272
| 675 | -0.20962 | 0.24947 | -0.348 | 0.55807 | 0.38364 | 0.0017515 | 0.049895 | 0.045904 | 0.0094951 | -0.73486
| 676 | 0.26481 | 0.27771 | -0.40561 | 0.62731 | 0.20987 | 0.20269 | -0.45861 | 0.72233 | 0.61542 | -0.067208
| 677 | -0.35015 | 0.21559 | -0.29325 | -0.38722 | 0.38153 | 0.24867 | -0.5412 | -0.13727 | -0.31728 | -0.12393
| 678 | -0.24349 | -0.48902 | 0.054749 | -0.1389 | 0.079837 | -0.16783 | 0.92063 | 0.59888 | -0.99 | -0.019643
| 679 | 0.30164 | 0.63765 | -0.42615 | 0.46699 | 0.35355 | -0.63108 | -0.39992 | -0.5019 | -0.0057666 | 0.20899
| 680 | -0.10228 | 0.13519 | -0.26849 | 0.21013 | 0.051369 | -0.43352 | 0.21152 | 0.057822 | 0.11124 | -0.54033
| 681 | -0.13403 | 0.59689 | 0.19595 | -0.10809 | -0.57468 | -0.38624 | 0.21457 | 0.50878 | 0.35836 | -0.39312
| 682 | 0.31568 | 0.23521 | 0.3681 | 0.0065716 | 0.075825 | -0.1729 | -0.28118 | -0.037451 | -0.098834 | 0.33675
| 683 | 0.3309 | -0.23495 | 0.28313 | 0.72305 | -0.39809 | -0.0032553 | -0.031444 | 0.46121 | 0.2037 | 0.2488
| 684 | 0.32037 | 0.37175 | 0.73448 | 0.067852 | 0.36636 | 0.033615 | 0.47684 | -0.89656 | 0.75 | -0.12862
| 685 | 0.6371 | -0.52576 | 0.67243 | 0.71557 | -0.2216 | -0.024244 | 0.25777 | 0.41733 | -0.21623 | -0.20911
| 686 | 0.29395 | 0.072153 | -0.54514 | 0.87958 | -0.29495 | -0.19446 | 0.94084 | -0.48532 | -0.25214 | 0.28887
| 687 | -0.10921 | 0.31699 | -0.56377 | -0.58781 | -0.10172 | -0.51927 | -0.035894 | -0.087914 | 0.45146 | 0.079511
| 688 | 0.11157 | -0.44529 | 0.48435 | -0.1375 | -0.83177 | -0.32658 | -0.34494 | -0.58443 | -0.14006 | -0.16976
| 689 | -0.20772 | 0.15059 | -0.12793 | 0.036828 | -0.23247 | 0.31934 | -0.31392 | 0.24482 | 0.21432 | -0.15413
| 690 | 0.2431 | -0.31787 | -0.37542 | -0.6833 | 0.10809 | -0.45401 | -0.017096 | 0.12805 | -0.29495 | -0.72161
| 691 | -0.057928 | 0.10317 | 0.31787 | -0.52345 | -0.26986 | -0.83 | 0.51969 | 0.085724 | -0.060905 | -0.10384
| 692 | 0.24297 | 0.51616 | 0.066887 | 0.062397 | -0.15531 | 0.11699 | -0.6118 | -0.070753 | 0.14425 | -0.60163
| 693 | -0.38445 | -0.45055 | 0.63353 | -0.016588 | -0.041303 | -0.17653 | 0.33344 | 0.17253 | 0.20583 | 0.19545
| 694 | -0.038803 | -0.017096 | -0.82479 | 0.44027 | 0.23547 | 0.66489 | 0.01 | 0.017605 | 0.45438 | -0.11949
| 695 | 0.41102 | 0.36463 | 0.68172 | 0.20382 | 0.32155 | -0.24681 | -0.13553 | 0.21076 | 0.43866 | -0.60923
| 696 | -0.2985 | 0.083758 | 0.52682 | 0.79482 | -0.29452 | -0.19408 | -0.82422 | 0.18348 | 0.47875 | 0.10708
| 697 | -0.26918 | 0.13716 | 0.29779 | 0.14052 | 0.42546 | -0.81534 | 0.18963 | 0.028455 | 0.092862 | -0.38234
| 698 | 0.67304 | -0.2076 | -0.096285 | 0.044228 | -0.12119 | 0.73037 | 0.27343 | 0.10574 | 0.47684 | 0.51492
| 699 | -0.148 | 0.11214 | 0.037659 | 0.55223 | 0.041929 | 0.5264 | -0.54778 | 0.55223 | -0.11011 | 0.34372
| 700 | 0.098834 | -0.3357 | 0.65605 | -0.34571 | 0.83477 | -0.55022 | -0.65029 | -0.62704 | -0.17921 | -0.16161
| 701 | -0.43476 | -0.16018 | 0.74174 | -0.37767 | 0.34053 | -0.43902 | -0.62704 | -0.10239 | 0.068818 | 0.11169
| 702 | -0.50533 | 0.42825 | -0.248 | 0.28481 | 0.16197 | 0.11349 | -0.56194 | 0.62384 | -0.67061 | 0.30725
| 703 | -0.061118 | -0.95204 | 0.28243 | 0.042764 | 0.55943 | -0.33977 | -0.16197 | 0.008486 | 0.29183 | -0.69
| 704 | 0.080272 | 0.78436 | 0.088902 | -0.070861 | -0.16988 | 0.36039 | 0.56057 | -0.079077 | -0.39576 | 0.62865
| 705 | 0.54316 | -0.80277 | -0.84284 | 0.37751 | -0.78858 | -0.10006 | -0.44818 | -0.41 | -0.066565 | -0.77887
| 706 | 0.25845 | -0.23731 | -0.38413 | -0.44206 | -0.014049 | 0.29964 | 0.28775 | 0.4683 | 0.58371 | 0.16042
| 707 | -0.40848 | -0.20975 | 0.12302 | 0.16113 | 0.28021 | 0.11767 | -0.84157 | -0.83907 | -0.49453 | 0.15863
| 708 | -0.085943 | 0.43035 | 0.25912 | -0.38918 | -0.2047 | 0.90151 | -0.13288 | -0.75241 | -0.028352 | -0.62704
| 709 | 0.1597 | -0.14484 | 0.41785 | -0.10451 | -0.3245 | 0.75161 | 0.3651 | 0.33254 | 0.8454 | -0.86325
| 710 | -0.67061 | -0.58684 | -0.81588 | -0.75855 | -0.14449 | 0.080598 | 0.36905 | 0.050105 | -0.80379 | -0.16723
| 711 | 0.40561 | -0.29551 | -0.55604 | -0.17823 | 0.27453 | -0.23796 | 0.67488 | 0.3419 | -0.0049623 | -0.76188
| 712 | 0.33992 | 0.26509 | -0.14542 | 0.062183 | -0.14695 | 0.032477 | -0.22418 | -0.13971 | -0.23052 | 0.2161
| 713 | -0.56125 | 0.15496 | -0.62171 | 0.17205 | -0.3618 | 0.40025 | 0.22715 | 0.070108 | 0.48164 | 0.52703
| 714 | -0.4408 | 0.73448 | 0.39477 | -0.33 | 0.036517 | 0.47436 | 0.55807 | 0.34739 | 0.53021 | 0.22974
| 715 | -0.20646 | 0.0093941 | 0.027632 | -0.25 | -0.67674 | 0.54011 | 0.012832 | -0.5007 | -0.67581 | 0.59664
| 716 | -0.70251 | -0.27014 | 0.21725 | -0.34068 | -0.26549 | 0.56422 | 0.5264 | -0.34954 | -0.16137 | -0.19757
| 717 | 0.1962 | 0.20332 | 0.22818 | -0.018216 | -0.47894 | -0.36478 | 0.15035 | 0.7042 | -0.25845 | -0.40983
| 718 | -0.11079 | 0.53751 | 0.32435 | 0.45991 | -0.2488 | -0.16472 | 0.69917 | 0.10039 | -0.059309 | 0.36008
| 719 | 0.13797 | -0.17532 | -0.39692 | -0.010808 | 0.14988 | 0.87155 | -0.26672 | 0.54011 | 0.13369 | 0.050316
| 720 | 0.077124 | 0.7488 | 0.081904 | 0.28118 | 0.038491 | 0.7015 | -0.46624 | -0.47322 | 0.51 | -0.6371
| 721 | -0.040573 | 0.66429 | 0.80277 | -0.20044 | -0.51782 | 0.64631 | 0.28313 | 0.013339 | -0.34068 | 0.15024
| 722 | 0.64405 | -0.13983 | -0.80532 | -0.61594 | 0.0062697 | 0.20672 | -0.51246 | 0.1425 | 0.4653 | 0.33932
| 723 | 0.12404 | 0.85823 | 0.38853 | -0.51307 | -0.13924 | -0.14262 | 0.0025533 | -0.34159 | 0.39576 | -0.19136
| 724 | -0.2621 | 0.1253 | -0.032891 | 0.1277 | 0.16448 | 0.054114 | 0.70897 | -0.48648 | 0.09022 | 0.85752
| 725 | -0.076149 | 0.74407 | -0.34525 | -0.19732 | 0.027323 | -0.17714 | 0.80277 | -0.56491 | 0.66698 | -0.39213
| 726 | -0.48629 | -0.055066 | 0.54294 | 0.72341 | -0.1118 | -0.56308 | 0.35077 | -0.76021 | -0.48609 | 0.73599
| 727 | -0.09088 | -0.32613 | -0.46028 | 0.20106 | 0.19198 | 0.2343 | 0.43706 | -0.10406 | 0.002453 | 0.13658
| 728 | 0.49413 | 0.27151 | 0.67891 | 0.64181 | 0.55469 | 0.69227 | 0.10295 | -0.36826 | -0.30754 | 0.82139
| 729 | 0.28958 | 0.56954 | -0.34601 | 0.51886 | -0.31116 | 0.35914 | -0.28104 | 0.072908 | 0.63654 | -0.75607
| 730 | 0.26115 | -0.49413 | 0.72269 | 0.12336 | 0.17714 | -0.35401 | 0.15425 | -0.71382 | -0.17848 | -0.70017
| 731 | 0.25939 | 0.30754 | -0.22083 | 0.011112 | -0.1797 | -0.82084 | 0.15958 | -0.2625 | 0.76527 | 0.10664
| 732 | 0.0047613 | 0.32643 | -0.15685 | 0.34862 | 0.38186 | -0.21025 | -0.85823 | 0.71417 | -0.22392 | 0.30093
| 733 | 0.5174 | -0.6631 | 0.18397 | -0.69227 | 0.39263 | 0.33932 | 0.0054649 | 0.10228 | -0.68871 | -0.58419
| 734 | -0.80843 | -0.020868 | 0.70931 | -0.35432 | 0.042555 | 0.19074 | 0.050842 | -0.12702 | -0.27302 | 0.32658
| 735 | -0.55807 | 0.11405 | 0.13983 | -0.0026535 | -0.54185 | 0.35432 | 0.3419 | -0.40192 | -0.21674 | -0.68361
| 736 | -0.19557 | 0.71277 | 0.032271 | -0.15059 | 0.65029 | -0.23941 | -0.17109 | -0.7881 | -0.45055 | 0.16185
| 737 | -0.56216 | -0.37127 | 0.18483 | 0.34785 | -0.64914 | -0.36055 | -0.078751 | 0.32732 | -0.46195 | -0.007478
| 738 | -0.45991 | 0.098612 | 0.019133 | -0.86325 | 0.070753 | 0.022708 | -0.54098 | -0.51616 | 0.7245 | -0.34144
| 739 | -0.72852 | -0.32273 | -0.2265 | -0.086271 | 0.033098 | -0.7005 | 0.57869 | -0.11507 | -0.20987 | 0.25562
| 740 | 0.61257 | -0.13716 | 0.0091922 | -0.20621 | 0.10473 | 0.35758 | 0.032684 | -0.60088 | 0.13092 | -0.46624
| 741 | 0.65489 | -0.32465 | 0.4736 | -0.19645 | 0.39312 | -0.1418 | -0.32051 | 0.87233 | -0.54448 | 0.14227
| 742 | 0.28817 | 0.46121 | -0.075392 | -0.79095 | -0.14145 | -0.4717 | -0.19969 | 0.4995 | 0.49196 | -0.32273
| 743 | -0.82883 | 0.4279 | 0.53535 | 0.26986 | 0.28831 | -0.50654 | -0.6578 | -0.37191 | 0.15555 | -0.18483
| 744 | 0.11248 | 0.075825 | 0.57822 | 0.30079 | 0.21572 | 0.61387 | 0.15911 | 0.34892 | 0.17872 | -0.051369
| 745 | 0.042347 | 0.8454 | -0.22392 | 0.39742 | -0.22844 | 0.15047 | 0.19819 | 0.81807 | -0.35108 | -0.12874
| 746 | 0.21279 | 0.29282 | 0.3454 | 0.49059 | -0.42112 | -0.27771 | -0.55582 | 0.28202 | -0.066351 | -0.23928
| 747 | -0.097503 | 0.33524 | -0.047372 | -0.056231 | -0.0044599 | 0.30797 | -0.27233 | -0.082449 | 0.082449 | -0.60719
| 748 | -0.036309 | -0.12725 | 0.17641 | 0.38624 | -0.49078 | -0.13866 | 0.025577 | 0.88295 | 0.32287 | -0.51844
| 749 | 0.91815 | -0.27619 | -0.46981 | 0.070861 | -0.46102 | -0.44331 | 0.43088 | -0.60289 | -0.096728 | 0.43158
| 750 | -0.40595 | 0.44242 | 0.3759 | -0.4258 | -0.21994 | 0.41442 | -0.048002 | -0.33856 | -0.84157 | -0.58927
| 751 | 0.13242 | -0.4828 | 0.02897 | 0.34372 | -0.060692 | -0.18655 | -0.11733 | 0.0033556 | -0.070538 | 0.0041586
| 752 | -0.20019 | -0.12439 | 0.43334 | -0.37718 | -0.41085 | -0.28146 | -0.71347 | -0.20194 | 0.42982 | -0.46962
| 753 | -0.39908 | -0.048002 | 0.45843 | 0.37239 | -0.54734 | -0.25535 | -0.68016 | -0.26454 | 0.2958 | -0.24336
| 754 | 0.3294 | -0.018114 | -0.14461 | 0.64405 | 0.55067 | -0.03974 | 0.48164 | 0.34708 | -0.36305 | -0.3817
| 755 | 0.0094951 | -0.13426 | 0.10117 | 0.53772 | -0.56954 | -0.18618 | -0.11462 | 0.62704 | -0.21917 | 0.21063
| 756 | -0.00075028 | -0.13774 | -0.81862 | -0.27591 | 0.44927 | -0.16519 | 0.12667 | -0.5102 | 0.081033 | 0.025577
| 757 | -0.059628 | -0.53492 | -0.28132 | -0.0781 | -0.39775 | 0.37526 | 0.5707 | -0.53837 | -0.66698 | -0.086819
| 758 | 0.43884 | 0.81159 | -0.1179 | 0.24244 | 0.15863 | 0.059521 | -0.42043 | -0.43706 | 0.32732 | -0.015978
| 759 | 0.2711 | -0.3422 | -0.47741 | -0.15887 | 0.041512 | -0.39892 | -0.19421 | -0.06678 | 0.074419 | 0.25374
| 760 | 0.22199 | -0.46643 | -0.46868 | 0.058565 | 0.40494 | -0.35525 | 0.14507 | -0.71173 | -0.075284 | -0.036102
| 761 | -0.1221 | 0.3618 | -0.36227 | -0.44152 | 0.26932 | -0.29438 | 0.1136 | 0.020561 | 0.87793 | -0.60038
| 762 | 0.022912 | 0.060266 | -0.22263 | -0.40326 | -0.030825 | -0.45567 | -0.4265 | 0.16077 | -0.57585 | -0.54889
| 763 | 0.75 | -0.18006 | -0.29155 | -0.50695 | 0.046323 | -0.0087886 | -0.57374 | -0.11779 | 0.17653 | -0.076258
| 764 | 0.035168 | -0.067316 | 0.0038574 | 0.052424 | 0.25027 | -0.16066 | -0.11507 | 0.036932 | -0.96683 | 0.12302
| 765 | 0.73335 | 0.050421 | 0.28257 | -0.18067 | -0.42216 | -0.15188 | -0.052002 | 0.45475 | 0.59515 | -0.17896
| 766 | 0.66909 | -0.12006 | 0.24654 | 0.25737 | -0.16185 | 0.021276 | -0.31699 | -0.43653 | 0.5245 | -0.63682
| 767 | -0.021072 | -0.12188 | 0.09187 | -0.13265 | -0.29622 | 0.097614 | -0.56791 | 0.19111 | 0.046638 | -0.55559
| 768 | -0.64377 | -0.20596 | -0.031341 | -0.77796 | -0.30279 | -0.15436 | -0.17945 | -0.052108 | 0.34816 | 0.28579
| 769 | -0.23836 | -0.60643 | -0.10094 | -0.27288 | -0.15923 | 0.22805 | 0.91938 | -0.05422 | 0.16615 | -0.12222
| 770 | -0.63353 | 0.42615 | -0.18055 | 0.34754 | -0.15106 | 0.15709 | -0.05899 | -0.82028 | 0.036932 | -0.56034
| 771 | -0.082667 | 0.50492 | 0.37638 | 0.48318 | -0.18348 | -0.017198 | 0.3116 | 0.50756 | -0.17072 | 0.69032
| 772 | -0.1513 | 0.43405 | 0.14882 | 0.54756 | 0.73599 | -0.01415 | 0.12063 | 0.01182 | 0.39992 | 0.042555
| 773 | 0.016893 | -0.38024 | 0.75526 | 0.58539 | -0.37606 | 0.43938 | -0.12416 | -0.5693 | -0.64209 | -0.15543
| 774 | -0.30079 | -0.03 | -0.79288 | 0.73713 | -0.63627 | -0.58012 | -0.08967 | 0.48707 | 0.41425 | 0.10039
| 775 | 0.055913 | 0.084304 | 0.11858 | 0.34954 | -0.52177 | 0.16173 | -0.62066 | -0.21089 | -0.68172 | -0.47094
| 776 | -0.11067 | -0.55134 | 0.12006 | 0.7005 | -0.2733 | 0.92859 | -0.052741 | 0.12679 | 0.56722 | 0.23508
| 777 | -0.2524 | 0.0018517 | 0.36668 | -0.45273 | -0.29651 | -0.1025 | -0.19198 | 0.48106 | -0.087805 | -0.64801
| 778 | 0.4307 | 0.22366 | 0.26795 | -0.1863 | 0.014657 | 0.86621 | 0.5011 | -0.62624 | -0.082885 | 0.25629
| 779 | -0.43088 | -0.18569 | -0.082013 | -0.85134 | 0.19794 | 0.16639 | 0.023732 | 0.27233 | 0.50756 | -0.17836
| 780 | -0.23508 | -0.23338 | 0.11949 | 0.37815 | 0.26549 | 0.56011 | -0.60213 | 0.03434 | 0.27261 | 0.0866
| 781 | 0.38934 | 0.2081 | -0.39958 | -0.023936 | -0.38689 | -0.12564 | -0.42703 | -0.034133 | -0.052741 | -0.28831
| 782 | -0.14718 | -0.52745 | 0.39859 | 0.4279 | -0.27398 | 0.23744 | 0.0004501 | 0.33269 | 0.31846 | -0.23993
| 783 | -0.077558 | -0.49711 | 0.38624 | 0.3651 | -0.13219 | 0.52767 | 0.88467 | -0.19433 | -0.27924 | 0.33781
| 784 | 0.40746 | -0.73037 | -0.4279 | -0.38121 | 0.17568 | 0.6697 | -0.052952 | 0.41477 | 0.22715 | -0.26932
| 785 | -0.36778 | 0.40898 | 0.65258 | -0.22289 | -0.15448 | 0.25576 | 0.31465 | 0.016079 | 0.010707 | -0.6811
| 786 | 0.5656 | -0.44493 | -0.60339 | 0.12679 | -0.21304 | 0.15744 | -0.19732 | -0.76104 | 0.40276 | 0.62304
| 787 | 0.016791 | -0.35494 | -0.66879 | -0.23691 | 0.11135 | 0.23626 | -0.37143 | -0.12063 | -0.060053 | 0.44818
| 788 | 0.11451 | 0.26836 | -0.42947 | -0.2313 | -0.76655 | 0.41682 | -0.29155 | -0.16663 | -0.24469 | 0.77841
| 789 | 0.1803 | -0.3804 | -0.66819 | 0.0023528 | 0.11564 | 0.2995 | -0.097503 | 0.65956 | -0.55717 | -0.16952
| 790 | -0.10261 | -0.26305 | -0.21051 | -0.15425 | 0.49512 | -0.11892 | 0.23993 | 0.023936 | 0.41974 | 0.019439
| 791 | 0.21802 | -0.28859 | 0.21139 | -0.040469 | 0.38105 | -0.16077 | -0.30122 | -0.24588 | -0.095069 | 0.17326
| 792 | 0.13219 | -0.51969 | 0.54646 | 0.13011 | 0.35308 | 0.25885 | -0.40645 | -0.086928 | -0.26549 | -0.007075
| 793 | -0.27165 | -0.18361 | 0.24007 | -0.24059 | -0.60592 | 0.2893 | -0.11801 | 0.22818 | -0.02897 | 0.32125
| 794 | -0.41682 | -0.16507 | -0.37079 | 0.061118 | -0.072045 | -0.12085 | -0.81807 | -0.17241 | -0.15673 | -0.3369
| 795 | -0.080272 | -0.66909 | -0.15828 | 0.19694 | 0.62463 | -0.34174 | 0.23796 | -0.12108 | -0.17896 | -0.2575
| 796 | 0.3129 | 0.38056 | 0.55672 | -0.4653 | 0.13553 | -0.49552 | -0.23143 | -0.47019 | 0.32332 | -0.12828
| 797 | -0.11011 | -0.7623 | 0.23613 | -0.39792 | -0.010505 | -0.49394 | -0.76655 | -0.39444 | 0.17957 | 0.2076
| 798 | 0.18459 | -0.3951 | 0.027426 | -0.47474 | 0.32081 | -0.46139 | 0.058565 | -0.16042 | 0.50492 | 0.12885
| 799 | 0.74135 | -0.11654 | -0.077341 | -0.78529 | 0.42407 | 0.47303 | -0.36494 | -0.0173 | 0.014657 | -0.31831
| 800 | -0.47569 | 0.61751 | -0.30595 | -0.036932 | -0.11405 | -0.81 | -0.074419 | 0.2052 | 0.53967 | 0.44152
| 801 | 0.014252 | -0.082558 | 0.094517 | -0.75201 | -0.7496 | -0.2995 | 0.3454 | -0.64349 | -0.14111 | 0.28467
| 802 | -0.27027 | -0.63 | 0.009899 | 0.18643 | 0.64377 | -0.19198 | -0.042347 | -0.71312 | 0.12564 | -0.71557
| 803 | -0.63081 | 0.76357 | -0.32881 | -0.43777 | -0.23691 | 0.28481 | -0.23469 | 0.28944 | 0.35634 | -0.56537
| 804 | 0.2674 | 0.4902 | 0.021174 | 0.47645 | 0.84801 | -0.0069743 | -0.30624 | 0.43158 | 0.64042 | -0.43884
| 805 | -0.25508 | -0.22896 | 0.09143 | 0.073016 | 0.53621 | -0.0029544 | 0.25401 | 0.68968 | -0.39148 | 0.85
| 806 | 0.31102 | -0.059734 | -0.54602 | -0.76784 | 0.0014511 | 0.15106 | -0.63326 | -0.41068 | -0.59988 | 0.4293
| 807 | -0.77131 | -0.52429 | 0.084194 | -0.10217 | -0.10418 | 0.019745 | 0.27785 | -0.022196 | 0.34632 | 0.63737
| 808 | 0.087038 | 0.24933 | 0.09055 | 0.44964 | 0.84605 | 0.45091 | -0.062077 | 0.30899 | -0.066244 | 0.27027
| 809 | -0.33826 | -0.16555 | 0.23809 | -0.18287 | 0.59147 | -0.09077 | 0.31728 | 0.38885 | 0.13184 | -0.37542
| 810 | 0.54911 | -0.60314 | -0.52157 | -0.40561 | 0.12667 | -0.23508 | -0.0062697 | 0.018318 | -0.60949 | 0.63627
| 811 | -0.51906 | -0.11405 | -0.33902 | -0.13069 | 0.53989 | 0.047267 | 0.22148 | -0.49572 | -0.21457 | -0.0071757
| 812 | -0.06325 | 0.32658 | 0.070968 | 0.24363 | 0.45603 | 0.78251 | -0.14379 | 0.68936 | 0.3864 | 0.06165
| 813 | -0.10072 | 0.15236 | 0.45991 | 0.38722 | -0.53021 | 0.3369 | -0.55717 | 0.13948 | 0.78068 | -0.66281
| 814 | -0.14017 | 0.065602 | -0.70521 | 0.28593 | -0.21763 | -0.56422 | 0.3607 | 0.44403 | -0.17253 | -0.18092
| 815 | 0.55694 | 0.12336 | -0.43706 | -0.29722 | 0.052952 | 0.36762 | 0.19645 | 0.068067 | -0.73111 | -0.3245
| 816 | 0.3061 | 0.52177 | 0.2234 | 0.020663 | -0.45751 | -0.36447 | -0.30021 | 0.41085 | 0.10284 | -0.63163
| 817 | -0.18803 | 0.09165 | 0.44873 | 0.12416 | 0.26305 | 0.064425 | -0.71982 | -0.3838 | 0.348 | 0.099944
| 818 | -0.59343 | 0.15024 | -0.02568 | -0.61542 | -0.1229 | -0.28916 | -0.11575 | -0.080707 | -0.27744 | -0.77175
| 819 | -0.24244 | 0.70794 | -0.13959 | -0.34296 | -0.31247 | 0.41768 | 0.024551 | -0.17012 | 0.12541 | 0.072908
| 820 | 0.10955 | -0.45861 | -0.25723 | -0.58347 | -0.070108 | 0.53128 | -0.4799 | -0.052635 | -0.084304 | -0.70487
| 821 | -0.51369 | 0.16137 | -0.049158 | 0.3422 | -0.056973 | 0.87 | 0.4272 | 0.80947 | -0.51782 | 0.45954
| 822 | -0.44206 | 0.052952 | -0.011213 | -0.71138 | 0.80739 | -0.27247 | -0.1439 | 0.90151 | -0.36699 | -0.35992
| 823 | -0.25764 | 0.099833 | -0.73599 | -0.48804 | -0.45456 | 0.2948 | -0.50939 | -0.25053 | -0.20886 | -0.41768
| 824 | 0.30826 | -0.15259 | -0.93144 | -0.53967 | -0.10195 | 0.52282 | -0.20747 | 0.14613 | -0.34739 | -0.58371
| 825 | -0.35432 | -0.47569 | -0.48648 | 0.16412 | -0.49354 | -0.27055 | -0.04266 | -0.061118 | -0.15047 | -0.41408
| 826 | -0.38348 | 0.40527 | 0.5959 | 0.18067 | 0.078208 | -0.20031 | 0.15165 | -0.14169 | 0.10317 | -0.17072
| 827 | -0.53837 | 0.94255 | -0.6265 | 0.37016 | -0.69065 | -0.10507 | -0.24774 | -0.037347 | 0.063998 | 0.16687
| 828 | -0.50492 | -0.36604 | 0.1179 | -0.1473 | 0.68775 | -0.80791 | -0.21994 | -0.050211 | -0.19732 | -0.65172
| 829 | -0.31174 | -0.38673 | 0.10552 | 0.60238 | 0.15946 | 0.16328 | 0.16388 | 0.8747 | 0.14542 | 0.11598
| 830 | -0.41017 | 0.59098 | -0.051791 | -0.30394 | 0.3369 | -0.62784 | -0.46232 | -0.5728 | 0.28327 | -0.41751
| 831 | -0.39975 | 0.78622 | -0.43973 | -0.31247 | -0.022503 | 0.40696 | -0.51927 | -0.19471 | 0.38951 | -0.17605
| 832 | -0.12324 | -0.14929 | 0.05158 | -0.38234 | -0.31436 | 0.41836 | -0.44224 | -0.55559 | -0.24257 | -0.009899
| 833 | -0.39362 | 0.59147 | 0.06496 | 0.09518 | -0.78023 | -0.39494 | -0.10675 | -0.28887 | 0.052002 | -0.18717
| 834 | -0.073447 | -0.52534 | -0.00015001 | 0.061864 | 0.12267 | -0.36274 | 0.18348 | 0.58563 | 0.17763 | 0.28007
| 835 | -0.63108 | 0.11124 | -0.23796 | 0.048002 | 0.41494 | 0.17896 | -0.15024 | -0.41751 | -0.46437 | -0.18926
| 836 | -0.20508 | 0.31626 | -0.084413 | 0.73298 | -0.18459 | -0.26863 | -0.61751 | 0.26454 | 0.081904 | 0.38494
| 837 | 0.33194 | 0.071291 | 0.44152 | -0.28523 | 0.76784 | 0.85543 | 0.4801 | 0.55156 | 0.14941 | 0.41648
| 838 | -0.47894 | 0.42251 | 0.17605 | -0.35339 | 0.12404 | 0.04266 | -0.27785 | 0.76612 | 0.27605 | -0.26604
| 839 | -0.018827 | -0.07 | -0.6697 | -0.15259 | 0.5017 | 0.0086877 | -0.57917 | -0.82651 | -0.38984 | 0.41888
| 840 | -0.4553 | -0.17508 | -0.33781 | 0.19359 | -0.17447 | -0.14496 | -0.11417 | 0.37478 | -0.18018 | 0.22987
| 841 | 0.066458 | -0.20747 | -0.44764 | -0.49394 | -0.78622 | 0.18618 | -0.20924 | 0.23156 | 0.40511 | 0.35
| 842 | 0.053797 | -0.11315 | 0.47971 | 0.39709 | 0.12897 | 0.11191 | 0.17495 | -0.33886 | 0.082122 | -0.14965
| 843 | -0.60795 | -0.3189 | 0.28621 | -0.27495 | -0.57751 | 0.09176 | 0.44746 | -0.32258 | 0.37048 | -0.24588
| 844 | 0.19657 | -0.57917 | -0.01486 | -0.39296 | 0.52767 | 0.74251 | -0.1245 | 0.3005 | -0.28733 | 0.34938
| 845 | 0.045275 | -0.61777 | -0.41511 | -0.68488 | 0.39925 | -0.70555 | -0.081033 | 0.19062 | -0.26495 | 0.24165
| 846 | -0.099611 | 0.057503 | 0.2398 | 0.24007 | 0.52724 | -0.86472 | -0.36873 | -0.16376 | -0.45255 | 0.0055655
| 847 | -0.1559 | 0.10731 | 0.27771 | -0.32583 | -0.29822 | 0.59049 | -0.37783 | 0.11915 | 0.00015001 | -0.39378
| 848 | -0.053374 | 0.30884 | 0.0047613 | 0.044647 | -0.067745 | -0.26373 | 0.52767 | 0.27522 | 0.62092 | 0.4668
| 849 | -0.73149 | 0.1814 | 0.34327 | -0.60719 | -0.15994 | -0.53837 | -0.030825 | -0.74096 | 0.15224 | -0.025782
| 850 | -0.012123 | 0.22302 | -0.046533 | 0.364 | -0.081142 | -0.26699 | -0.44728 | -0.026912 | 0.13565 | 0.021685
| 851 | 0.040365 | -0.18287 | 0.60744 | 0.069892 | 0.064105 | -0.22534 | 0.28958 | 0.31087 | 0.029176 | 0.72089
| 852 | -0.79095 | 0.44134 | -0.09518 | -0.65489 | 0.37334 | -0.015063 | -0.3454 | -0.13276 | 0.48222 | -0.10217
| 853 | -0.4542 | -0.074635 | 0.28607 | 0.24947 | 0.83059 | -0.4041 | 0.095732 | -0.3422 | 0.64857 | -0.17994
| 854 | 0.22805 | -0.15709 | 0.19557 | -0.90151 | -0.64237 | -0.18778 | 0.13623 | -0.046428 | 0.25643 | 0.47722
| 855 | 0.11349 | -0.70487 | 0.42493 | -0.76146 | -0.062077 | 0.037763 | -0.30986 | 0.2356 | -0.2496 | 0.044961
| 856 | -0.32554 | 0.86036 | -0.30093 | -0.017809 | 0.09088 | 0.06197 | -0.19856 | 0.46028 | -0.013947 | -0.063784
| 857 | -0.5245 | -0.58903 | -0.065174 | 0.095732 | 0.67891 | -0.92859 | -0.21241 | 0.36937 | 0.82139 | -0.1694
| 858 | -0.77841 | 0.25522 | -0.073663 | -0.1315 | -0.027529 | 0.032684 | 0.075608 | 0.63931 | -0.71 | -0.44728
| 859 | -0.60063 | 0.40427 | 0.32066 | -0.018318 | 0.56676 | 0.69357 | -0.49612 | 0.50939 | 0.27716 | 0.62758
| 860 | -0.54978 | 0.44601 | 0.59049 | 0.12553 | -0.4717 | -0.34525 | -0.71733 | -0.4653 | -0.070968 | -0.062503
| 861 | 0.25777 | 0.15118 | -0.3309 | -0.65086 | 0.29594 | 0.19346 | 0.60289 | 0.19037 | -0.67519 | 0.73751
| 862 | 0.40628 | 0.058671 | 0.2816 | 0.5001 | 0.33299 | 0.20219 | -0.14169 | 0.31407 | -0.64042 | -0.64181
| 863 | -0.45585 | 0.068174 | -0.14367 | -0.19284 | -0.17169 | 0.52136 | 0.87958 | -0.10373 | -0.59171 | 0.064639
| 864 | 0.020255 | 0.61361 | 0.055172 | -0.55966 | -0.49157 | 0.10742 | -0.13115 | 0.3767 | 0.10731 | -0.035583
| 865 | 0.3248 | -0.19049 | -0.54911 | 0.40175 | 0.18275 | 0.060479 | -0.038907 | -0.63054 | 0.28188 | -0.27192
| 866 | -0.26142 | 0.93917 | -0.77977 | 0.26115 | -0.65345 | -0.53021 | -0.041825 | -0.16699 | 0.72378 | 0.54273
| 867 | 0.38461 | -0.088682 | 0.23195 | 0.23705 | -0.22366 | 0.010505 | -0.48396 | -0.25187 | 0.35758 | 0.073987
| 868 | 0.8422 | -0.26196 | -0.1559 | 0.65751 | 0.56653 | 0.29836 | -0.1565 | 0.61051 | -0.11779 | 0.031857
| 869 | -0.24416 | 0.56676 | 0.0011507 | -0.45935 | -0.71452 | -0.0035563 | 0.015165 | 0.59788 | -0.21533 | 0.14484
| 870 | -0.35774 | 0.34708 | 0.1082 | 0.42947 | -0.09706 | 0.54978 | 0.19297 | -0.53967 | 0.34174 | -0.46943
| 871 | -0.32465 | -0.046428 | -0.11428 | -0.36921 | 0.052213 | -0.12931 | 0.47798 | -0.36699 | 0.85752 | 0.17775
| 872 | -0.16244 | 0.58107 | 0.11972 | 0.24072 | 0.26034 | 0.26183 | 0.3214 | -0.055384 | -0.052846 | -0.83237
| 873 | 0.18397 | 0.61387 | -0.37302 | -0.22122 | -0.3132 | 0.041825 | -0.0063703 | -0.12587 | 0.58903 | 0.37318
| 874 | 0.059521 | -0.14157 | -0.011314 | -0.59689 | 0.31787 | 0.31014 | -0.16173 | 0.080381 | 0.74096 | -0.83059
| 875 | 0.069677 | -0.34464 | 0.050421 | 0.76021 | 0.20937 | -0.3186 | -0.006169 | 0.043601 | -0.76612 | 0.59988
| 876 | 0.48202 | -0.37318 | -0.024039 | -0.21942 | 0.33075 | 0.39033 | 0.030928 | -0.45806 | -0.0089904 | 0.42164
| 877 | 0.72559 | -0.86696 | -0.11733 | 0.25804 | 0.49751 | 0.16928 | -0.52682 | -0.0060684 | -0.55178 | -0.30725
| 878 | -0.018522 | 0.32214 | 0.13878 | 0.64687 | 0.67427 | 0.33841 | -0.59441 | 0.72889 | -0.86621 | -0.26945
| 879 | 0.19111 | -0.82479 | 0.14753 | -0.0755 | 0.015165 | -0.04266 | -0.4987 | -0.55717 | -0.039115 | 0.10295
| 880 | 0.018623 | 0.22741 | -0.22379 | -0.65258 | 0.15425 | -0.25468 | 0.26645 | 0.23954 | 0.46962 | 0.16579
| 881 | 0.26413 | 0.35046 | -0.053903 | 0.0011507 | -0.6546 | -0.27302 | -0.19844 | -0.1868 | -0.012731 | 0.37334
| 882 | -0.10966 | -0.022094 | 0.063464 | -0.30351 | 0.5656 | -0.7429 | 0.18951 | -0.28509 | -0.41255 | 0.037036
| 883 | 0.024551 | -0.18704 | -0.26918 | -0.83059 | -0.34923 | -0.058777 | -0.39444 | 0.19247 | -0.29197 | -0.15982
| 884 | 0.80947 | -0.041825 | -0.63217 | 0.30394 | 0.38984 | 0.41785 | 0.79048 | -0.020357 | 0.73373 | 0.080707
| 885 | 0.0067729 | 0.29921 | 0.27137 | 0.39033 | -0.40292 | 0.26169 | 0.12702 | -0.42285 | -0.48454 | -0.0060684
| 886 | -0.47227 | 0.1072 | -0.23273 | 0.032477 | -0.1025 | -0.46906 | -0.54251 | 0.31189 | 0.17084 | 0.10261
| 887 | 0.58757 | -0.51699 | 0.39842 | -0.072692 | 0.1082 | 0.075284 | 0.67891 | -0.044961 | 0.34205 | 0.22405
| 888 | 0.30581 | -0.016486 | -0.34327 | -0.90673 | 0.35031 | -0.046113 | -0.24072 | 0.11281 | -0.15024 | -0.28299
| 889 | -0.050316 | -0.15283 | 0.067637 | 0.18483 | 0.24734 | -0.28369 | -0.41391 | 0.049684 | 0.62758 | 0.28719
| 890 | -0.89183 | 0.21076 | -0.17411 | -0.035479 | 0.1769 | 0.83 | 0.47665 | -0.35541 | 0.67121 | 0.20194
| 891 | -0.030516 | -0.48473 | 0.352 | -0.041303 | 0.31174 | -0.068603 | 0.35216 | -0.29722 | 0.64943 | -0.2492
| 892 | -0.32821 | 0.40814 | 0.01091 | 0.29807 | 0.36023 | -0.32376 | 0.31685 | 0.17217 | -0.041303 | -0.072692
| 893 | 0.39395 | -0.35031 | 0.0055655 | 0.20949 | -0.37863 | -0.39859 | 0.1752 | 0.84348 | -0.15389 | 0.032374
| 894 | 0.35852 | 0.45917 | 0.12404 | 0.020459 | 0.74368 | 0.19844 | 0.15118 | 0.25535 | 0.30107 | -0.21853
| 895 | 0.41665 | -0.30797 | 0.10563 | -0.38673 | 0.020663 | 0.42982 | -0.11711 | -0.17483 | -0.37654 | 0.52157
| 896 | -0.022503 | 0.49433 | -0.39378 | 0.050842 | 0.19919 | 0.6162 | -0.078642 | -0.2313 | 0.91574 | 0.20785
| 897 | -0.50776 | 0.50878 | 0.14871 | 0.11949 | -0.039635 | -0.28831 | 0.37334 | -0.1269 | 0.079946 | 0.19471
| 898 | -0.083103 | -0.023936 | 0.32985 | -0.26061 | 0.88381 | 0.36415 | 0.47246 | 0.46065 | -0.12713 | 0.64349
| 899 | 0.1136 | 0.21444 | 0.093413 | 0.18729 | -0.055066 | 0.5458 | 0.33509 | -0.38918 | 0.27591 | 0.4828
| 900 | -0.34785 | -0.2431 | -0.82536 | 0.62066 | -0.32539 | -0.061544 | -0.24151 | 0.095511 | -0.50351 | -0.11405
| 901 | -0.60138 | 0.67182 | -0.4553 | 0.03434 | -0.43991 | 0.5412 | 0.64014 | -0.082776 | -0.12347 | -0.017503
| 902 | -0.042869 | -0.12633 | -0.50918 | 0.42199 | -0.011516 | 0.082122 | 0.45091 | -0.19894 | 0.14309 | 0.8755
| 903 | -0.11507 | -0.10395 | 0.6407 | 0.56331 | 0.10373 | 0.81642 | -0.39958 | -0.038803 | 0.35852 | -0.095511
| 904 | -0.31816 | -0.54098 | 0.73223 | 0.78669 | -0.34083 | -0.56262 | 0.30696 | 0.32199 | 0.21343 | -0.8821
| 905 | -0.48746 | 0.18557 | 0.52936 | -0.095069 | -0.025167 | 0.086162 | 0.026501 | -0.43813 | -0.12302 | -0.24561
| 906 | -0.44295 | -0.19272 | -0.20031 | 0.25643 | -0.09022 | -0.13392 | 0.10328 | 0.34923 | 0.055595 | 0.079728
| 907 | -0.72054 | 0.3951 | 0.0060684 | 0.57917 | 0.044437 | 0.40259 | 0.27896 | -0.43582 | 0.50939 | 0.44692
| 908 | 0.71733 | -0.47741 | -0.09695 | 0.54338 | -0.18704 | -0.15578 | 0.36447 | 0.12142 | 0.1382 | -0.034029
| 909 | 0.062397 | -0.074311 | 0.23208 | -0.5583 | -0.12427 | -0.53686 | 0.26359 | 0.063784 | -0.059947 | 0.74722
| 910 | -0.19607 | -0.72705 | 0.83477 | -0.35945 | 0.22469 | -0.44855 | -0.18717 | 0.20357 | 0.5656 | -0.18067
| 911 | -0.17205 | 0.46718 | -0.11248 | -0.29212 | -0.39925 | 0.57233 | -0.33524 | -0.078317 | -0.97354 | -0.15923
| 912 | -0.55921 | -0.49651 | 0.63462 | -0.64377 | 0.17884 | -0.10809 | 0.54734 | 0.40713 | -0.8956 | -0.75485
| 913 | -0.51616 | -0.49256 | 0.10641 | -0.21994 | 0.37686 | -0.57538 | -0.56814 | 0.51164 | 0.70897 | 0.65809
| 914 | 0.19309 | 0.086381 | 0.0014511 | -0.063037 | 0.60188 | -0.12954 | -0.48922 | 0.038595 | -0.47837 | -0.40443
| 915 | -0.68775 | 0.5283 | -0.38234 | -0.35587 | 0.58539 | -0.42441 | -0.62973 | 0.088024 | -0.15496 | 0.53816
| 916 | -0.58131 | -0.34311 | -0.78669 | -0.52303 | 0.082231 | 0.009596 | 0.42043 | 0.63737 | 0.28439 | -0.34464
| 917 | 0.028146 | 0.35278 | 0.2907 | 0.18226 | -0.348 | 0.51225 | -0.38559 | 0.040365 | -0.39082 | 0.45255
| 918 | 0.24667 | 0.11372 | 0.64772 | 0.33344 | -0.56377 | -0.0090913 | -0.17763 | -0.33449 | 0.24204 | 0.80532
| 919 | -0.58227 | -0.072476 | 0.018012 | 0.42285 | -0.43334 | -0.38592 | -0.057928 | -0.02097 | -0.30265 | -0.012427
| 920 | 0.64602 | -0.40025 | -0.49751 | 0.51906 | 0.58805 | -0.84933 | -0.55943 | 0.19906 | 0.13057 | -0.099056
| 921 | 0.2052 | 0.85134 | 0.58467 | 0.64461 | 0.063037 | -0.552 | 0.18988 | 0.24721 | 0.94432 | 0.048212
| 922 | -0.56468 | -0.40108 | 0.46868 | -0.11496 | 0.088682 | -0.28761 | -0.164 | 0.3132 | -0.24217 | 0.20395
| 923 | -0.15306 | -0.18594 | -0.12587 | -0.40645 | 0.83599 | 0.65057 | 0.44439 | -0.22922 | 0.19856 | -0.32539
| 924 | -0.073987 | -0.041199 | -0.35836 | -0.14076 | 0.6995 | -0.84867 | -0.32613 | -0.38804 | -0.28789 | -0.59368
| 925 | -0.10395 | -0.34954 | -0.18177 | 0.00025003 | -0.29679 | 0.18459 | 0.28831 | 0.62039 | 0.53621 | -0.063998
| 926 | -0.1952 | 0.27827 | 0.30136 | 0.076691 | -0.35945 | -0.26169 | 0.20069 | -0.21623 | 0.2256 | 0.51637
| 927 | -0.44116 | -0.061544 | -0.46643 | -0.10195 | -0.096839 | -0.3129 | 0.40645 | -0.64153 | 0.18312 | -0.20861
| 928 | 0.25966 | -0.09529 | 0.15804 | 0.039635 | 0.037659 | -0.33284 | -0.44855 | -0.34571 | 0.044856 | 0.14613
| 929 | 0.44818 | 0.38234 | -0.39975 | -0.26156 | -0.5728 | -0.2042 | 0.18852 | 0.35448 | -0.52661 | 0.42511
| 930 | 0.13 | 0.78068 | 0.32199 | 0.31261 | 0.49612 | 0.41528 | -0.53513 | 0.49691 | 0.85 | 0.65868
| 931 | -0.86546 | -0.057503 | 0.059947 | -0.15389 | -0.24721 | -0.27165 | -0.078859 | -0.52682 | 0.71875 | -0.37223
| 932 | 0.70285 | -0.017503 | -0.076041 | 0.66133 | 0.050948 | 0.19906 | -0.74564 | 0.57656 | 0.53149 | 0.41119
| 933 | 0.23443 | 0.29353 | 0.89851 | -0.67922 | -0.47722 | -0.59147 | -0.15828 | 0.39395 | 0.55559 | -0.47303
| 934 | -0.19334 | -0.21789 | -0.34114 | 0.46046 | 0.61568 | 0.42407 | -0.73074 | 0.30581 | -0.74564 | -0.097947
| 935 | -0.36794 | -0.012427 | 0.09706 | 0.43688 | 0.14894 | 0.26959 | -0.32081 | 0.049579 | 0.68679 | 0.42825
| 936 | -0.37191 | -0.26074 | -0.21776 | -0.60617 | 0.33 | -0.30265 | 0.52136 | 0.43458 | 0.6382 | 0.23967
| 937 | 0.24694 | -0.28355 | 0.1735 | 0.45328 | 0.30725 | -0.20684 | -0.40192 | -0.28411 | -0.45954 | -0.79826
| 938 | -0.17884 | -0.29226 | 0.71312 | -0.53171 | -0.32258 | -0.28803 | 0.3961 | 0.070323 | -0.25629 | -0.14777
| 939 | 0.09839 | -0.16831 | -0.64237 | -0.11575 | -0.49315 | 0.64518 | -0.064425 | 0.5347 | 0.12793 | -0.25428
| 940 | -0.5332 | 0.83417 | 0.51328 | -0.095954 | -0.29438 | -0.27785 | -0.20344 | -0.23443 | -0.90461 | 0.72161
| 941 | 0.61751 | 0.20823 | -0.48183 | -0.084631 | -0.01 | 0.28747 | -0.60668 | -0.015774 | -0.44511 | 0.13611
| 942 | 0.15047 | 0.35247 | -0.066673 | -0.10518 | 0.28607 | -0.023732 | -0.46512 | -0.69718 | -0.60038 | 0.26986
| 943 | -0.079511 | 0.82824 | 0.016283 | -0.16699 | -0.10764 | 0.68647 | 0.41204 | -0.087586 | 0.12051 | -0.12656
| 944 | 0.45146 | 0.077558 | -0.29509 | -0.1034 | -0.29099 | 0.72378 | -0.43176 | 0.1926 | -0.60923 | 0.11518
| 945 | -0.21381 | 0.5245 | -0.12679 | 0.51761 | -0.62838 | -0.24283 | 0.51595 | -0.83297 | 0.39329 | -0.13496
| 946 | -0.73298 | 0.11938 | -0.13369 | -0.41699 | -0.094848 | -0.20987 | 0.21076 | 0.085615 | 0.19136 | -0.29197
| 947 | 0.09 | 0.71875 | -0.010606 | 0.30222 | -0.80481 | -0.82252 | -0.11552 | 0.058246 | 0.41836 | 0.067316
| 948 | -0.24007 | 0.91938 | 0.066458 | -0.34846 | 0.032788 | 0.28677 | -0.23247 | 0.53924 | 0.60898 | -0.68235
| 949 | 0.18753 | 0.41528 | -0.021174 | 0.44403 | 0.81053 | -0.18238 | 0.05984 | 0.40611 | 0.0021523 | 0.68425
| 950 | 0.51205 | -0.73524 | -0.073447 | -0.059628 | -0.072261 | -0.25953 | 0.14134 | 0.75938 | -0.52724 | 0.026193
| 951 | -0.01415 | -0.19359 | 0.20119 | 0.54163 | 0.27055 | -0.65547 | -0.22741 | 0.80025 | -0.0020521 | 0.38673
| 952 | 0.48746 | 0.5017 | 0.66698 | -0.3309 | 0.60163 | -0.044437 | -0.58251 | 0.3796 | 0.26373 | -0.17848
| 953 | 0.89851 | 0.10865 | 0.35046 | -0.075933 | -0.0062697 | -0.034754 | -0.28873 | 0.12725 | -0.21393 | 0.071184
| 954 | 0.4859 | -0.78622 | 0.58951 | 0.9089 | 0.12977 | -0.029073 | -0.336 | 0.38429 | -0.17 | -0.09044
| 955 | 0.79336 | 0.26563 | -0.1578 | -0.25764 | 0.56354 | -0.46009 | 0.66015 | -0.010808 | -0.39527 | -0.28327
| 956 | 0.5529 | -0.6852 | 0.17921 | -0.26836 | 0.48648 | -0.19694 | 0.021787 | -0.51513 | -0.12587 | -0.6118
| 957 | -0.42355 | 0.52094 | 0.43742 | -0.5959 | -0.352 | 0.2823 | 0.094627 | -0.52408 | 0.39809 | 0.39692
| 958 | 0.17617 | 0.016689 | 0.86923 | -0.46213 | 0.14134 | -0.061757 | 0.07 | -0.05496 | -0.33766 | -0.33194
| 959 | -0.36368 | 0.099167 | -0.17957 | 0.50614 | -0.4902 | 0.077016 | -0.94615 | -0.069677 | -0.45036 | -0.43706
| 960 | 0.19819 | 0.29014 | -0.16304 | -0.051369 | -0.64715 | -0.046323 | -0.82651 | -0.21279 | -0.13936 | -0.79531
| 961 | -0.248 | 0.48029 | 0.23312 | 0.32125 | 0.067852 | 0.71417 | 0.032271 | -0.40108 | 0.32494 | -0.071291
| 962 | -0.25643 | 0.71982 | 0.32821 | -0.035687 | 0.46568 | 0.36636 | 0.11293 | -0.11034 | -0.63108 | -0.30451
| 963 | -0.15259 | -0.070861 | -0.41699 | 0.16831 | -0.16244 | -0.82422 | 0.15247 | -0.8739 | -0.14706 | 0.88126
| 964 | -0.4979 | -0.05422 | 0.4553 | 0.39131 | 0.23391 | -0.19894 | 0.60389 | -0.23221 | -0.87 | 0.39958
| 965 | 0.012022 | 0.4046 | 0.53816 | -0.2659 | -0.88295 | -0.25027 | -0.46661 | 0.53707 | -0.36937 | 0.18963
| 966 | 0.069785 | -0.53342 | -0.10072 | -0.53924 | 0.5714 | -0.40746 | 0.033512 | -0.44982 | 0.11779 | -0.40494
| 967 | -0.054855 | 0.030928 | 0.030206 | 0.35262 | 0.4989 | 0.25899 | 0.59343 | -0.025269 | 0.35727 | 0.07043
| 968 | -0.2674 | -0.49374 | 0.11643 | -0.099167 | -0.27522 | -0.27096 | 0.62304 | 0.48415 | 0.2755 | 0.49354
| 969 | -0.18852 | -0.13519 | 0.35758 | 0.2042 | 0.28691 | 0.53406 | 0.95641 | -0.42355 | -0.66489 | -0.7512
| 970 | -0.70352 | -0.66758 | -0.080489 | -0.036828 | -0.43795 | -0.42842 | 0.20282 | -0.28271 | 0.03434 | -0.20257
| 971 | -0.016588 | 0.90253 | -0.27055 | -0.71522 | -0.55672 | -0.12245 | -0.15863 | -0.26945 | -0.21203 | -0.044542
| 972 | 0.31831 | 0.2265 | -0.28007 | 0.1926 | 0.61103 | 0.09055 | -0.067316 | -0.79925 | 0.72018 | -0.036932
| 973 | -0.31276 | -0.29964 | 0.25 | -0.18963 | -0.11281 | -0.47569 | -0.58179 | -0.31772 | 0.1153 | 0.21051
| 974 | 0.054431 | 0.12028 | -0.28761 | 0.66015 | -0.51389 | 0.056443 | -0.89656 | -0.16018 | -0.15118 | -0.21814
| 975 | 0.36415 | -0.38885 | 0.85 | -0.55312 | -0.77483 | 0.23273 | 0.8995 | 0.26822 | 0.79191 | -0.63627
| 976 | 0.075392 | -0.45255 | -0.36149 | 0.12461 | 0.64744 | -0.14006 | 0.47208 | -0.38429 | -0.23338 | 0.2958
| 977 | -0.25361 | 0.12702 | 0.61257 | -0.7015 | 0.60238 | 0.19582 | 0.55537 | -0.29197 | -0.1775 | 0.15507
| 978 | 0.25414 | 0.64687 | -0.37992 | -0.5003 | -0.2924 | 0.54911 | -0.12966 | -0.34862 | 0.39775 | -0.63599
| 979 | -0.18238 | 0.30466 | 0.23534 | -0.097947 | 0.70117 | -0.27813 | 0.43493 | 0.058777 | 0.18079 | -0.30093
| 980 | 0.2216 | 0.053691 | -0.18951 | 0.29197 | -0.11938 | -0.65 | 0.59417 | 0.5199 | -0.79826 | -0.39164
| 981 | -0.17048 | -0.14239 | 0.10128 | -0.0027538 | 0.89 | -0.63027 | 0.66909 | 0.47626 | 0.25174 | 0.1513
| 982 | 0.5143 | 0.077991 | 0.21076 | 0.45273 | -0.56422 | 0.25737 | -0.21419 | 0.54845 | -0.89753 | -0.2722
| 983 | -0.14437 | -0.1082 | 0.54624 | 0.46661 | 0.20747 | -0.25777 | -0.011617 | -0.88642 | 0.13762 | 0.17314
| 984 | -0.19769 | -0.55424 | -0.3366 | 0.0013509 | 0.17544 | 0.18914 | 0.58227 | -0.25374 | 0.36447 | 0.1863
| 985 | -0.13461 | -0.2133 | -0.15768 | -0.56262 | -0.50675 | -0.057609 | -0.13901 | -0.29254 | -0.59963 | -0.032788
| 986 | 0.07962 | 0.20747 | 0.24601 | -0.17483 | -0.15507 | -0.13173 | 0.12908 | 0.11496 | -0.29722 | -0.23039
| 987 | 0.336 | 0.16699 | 0.7735 | 0.52809 | 0.50291 | -0.79095 | 0.85543 | 0.46493 | 0.026809 | 0.094406
| 988 | -0.1136 | 0.14683 | -0.29566 | -0.0050628 | 0.29495 | 0.51246 | -0.2508 | -0.45273 | 0.49 | 0.10529
| 989 | 0.27633 | 0.30538 | 0.079511 | 0.62357 | 0.56034 | 0.24007 | -0.020663 | 0.15448 | -0.22315 | 0.67152
| 990 | -0.27716 | 0.36337 | 0.30913 | -0.048738 | -0.61803 | -0.09044 | -0.23456 | -0.12085 | 0.16376 | 0.16376
| 991 | -0.51534 | 0.54624 | -0.16018 | 0.047687 | 0.39676 | 0.26101 | 0.32435 | -0.68141 | -0.063998 | 0.39181
| 992 | 0.52094 | -0.5283 | -0.50271 | 0.57303 | 0.62811 | -0.41221 | 0.89753 | -0.3607 | 0.80025 | -0.52219
| 993 | -0.14064 | -0.0057666 | -0.35448 | -0.0080827 | 0.57186 | 0.06678 | 0.14976 | -0.81642 | -0.20634 | 0.13299
| 994 | -0.57116 | 0.17945 | 0.44583 | -0.029485 | -0.66103 | 0.20772 | 0.29523 | -0.352 | -0.7735 | -0.53427
| 995 | 0.53902 | -0.41991 | -0.010303 | -0.32881 | -0.14601 | -0.17945 | -0.29296 | -0.48125 | 0.57609 | -0.58612
| 996 | -0.45603 | 0.24535 | 0.43546 | 0.27 | 0.10384 | 0.80481 | 0.51143 | 0.76569 | 0.39 | 0.059309
| 997 | 0.72926 | 0.61309 | 0.37064 | 0.7492 | -0.25576 | 0.31714 | 0.031031 | 0.32184 | 0.16507 | -0.23378
| 998 | -0.40511 | 0.21827 | -0.20232 | -0.18092 | 0.080816 | 0.87793 | 0.42563 | 0.024141 | 0.25495 | -0.66251
| 999 | 0.79628 | 0.39809 | 0.76442 | 0.17714 | -0.36699 | -0.67735 | 0.36731 | -0.41699 | -0.013035 | 0.52979
| 1000 | -0.72926 | 0.083103 | 0.55267 | -0.8618 | -0.17556 | 0.52661 | 0.55921 | 0.28216 | 0.14788 | -0.02189
| 1001 | -0.23104 | -0.57093 | 0.54492 | 0.31993 | 0.26795 | 0.027735 | 0.12267 | 0.074527 | 0.16567 | 0.070861
| 1002 | -0.28076 | 0.066244 | -0.5102 | 0.55582 | 0.58323 | -0.53085 | -0.09529 | -0.26007 | -0.58203 | 0.016283
| 1003 | 0.32911 | 0.16916 | 0.15496 | 0.54823 | 0.09022 | 0.4279 | 0.13658 | 0.21981 | -0.17278 | 0.060372
| 1004 | -0.45036 | 0.14204 | -0.10619 | -0.536 | 0.26849 | 0.09033 | 0.5954 | 0.57468 | -0.029588 | -0.45127
| 1005 | 0.015063 | -0.46139 | -0.24588 | -0.58757 | 0.009798 | 0.47588 | 0.043705 | 0.19844 | 0.039219 | 0.40831
| 1006 | 0.13762 | -0.11428 | -0.96683 | 0.44152 | 0.080489 | 0.53902 | 0.30021 | 0.61777 | 0.089121 | -0.21648
| 1007 | 0.2193 | 0.043078 | -0.38089 | -0.73637 | 0.064318 | 0.90253 | 0.024346 | 0.51102 | 0.015571 | 0.27757
| 1008 | -0.30509 | -0.41682 | 0.24072 | 0.23364 | 0.53859 | -0.016384 | 0.30667 | -0.30365 | -0.87631 | 0.28369
| 1009 | -0.52303 | 0.62066 | -0.35789 | -0.31276 | -0.13727 | 0.38429 | -0.29 | 0.33464 | -0.49354 | -0.64433
| 1010 | -0.0051633 | -0.030103 | -0.25549 | 0.071938 | -0.66819 | 0.66162 | 0.059521 | 0.10955 | 0.14029 | 0.48376
| 1011 | 0.099944 | 0.53513 | -0.86847 | -0.75444 | -0.32881 | 0.21457 | 0.033408 | 0.27288 | 0.1921 | -0.48922
| 1012 | 0.34662 | -0.027837 | -0.78529 | -0.086381 | -0.27357 | 0.46065 | -0.20156 | 0.34144 | 0.51534 | -0.060692
| 1013 | 0.1292 | 0.48609 | 0.43848 | 0.71452 | -0.61438 | -0.66074 | 0.51328 | -0.43141 | -0.096175 | 0.30754
| 1014 | -0.53363 | -0.40729 | -0.86621 | 0.36652 | 0.18348 | 0.50371 | 0.61283 | 0.59763 | -0.72926 | 0.023527
| 1015 | 0.3751 | 0.25281 | -0.0041586 | 0.55649 | 0.33269 | -0.69685 | 0.13242 | -0.61103 | 0.41459 | 0.33509
| 1016 | 0.39543 | -0.77087 | -0.72305 | -0.37863 | 0.50553 | -0.72161 | -0.37032 | 0.29452 | -0.45456 | 0.77977
| 1017 | -0.45109 | -0.64237 | 0.068388 | 0.69357 | 0.024141 | -0.31846 | 0.047057 | -0.047897 | -0.54251 | -0.69129
| 1018 | 0.45383 | -0.68936 | 0.86325 | -0.031238 | -0.51844 | 0.44403 | 0.34159 | -0.59614 | -0.18263 | 0.44728
| 1019 | 0.80687 | 0.38673 | 0.014252 | 0.68393 | -0.18914 | -0.63875 | 0.84284 | 0.15875 | 0.09143 | 0.53621
| 1020 | -0.23639 | 0.35324 | -0.061118 | 0.27799 | -0.089012 | 0.80176 | 0.28565 | 0.17411 | -0.41733 | 0.10731
| 1021 | -0.47284 | 0.12063 | 0.11881 | -0.25926 | 0.29197 | 0.39742 | 0.54251 | -0.39958 | -0.9005 | 0.43564
| 1022 | 0.62277 | 0.21623 | -0.39329 | -0.63 | -0.51348 | 0.82365 | -0.10529 | 0.17677 | -0.42285 | 0.027837
| 1023 | -0.26495 | -0.052319 | -0.63848 | -0.44403 | -0.11835 | -0.17629 | 0.10854 | 0.336 | -0.44206 | -0.21343
| 1024 | -0.020255 | -0.11756 | -0.31685 | 0.47038 | 0.50594 | -0.011314 | -0.53751 | 0.34525 | 0.33374 | 0.71452
| 1025 | 0.06197 | 0.26727 | 0.073555 | -0.44873 | 0.30107 | -0.0088895 | 0.53946 | 0.5866 | 0.032064 | -0.40797
| 1026 | -0.21661 | 0.58371 | -0.65114 | -0.32762 | -5.0001e-05 | -0.17399 | -0.32866 | 0.14671 | -0.14122 | -0.0088895
| 1027 | 0.21381 | 0.2659 | -0.80481 | -0.39527 | 0.33015 | -0.062503 | -0.10006 | 0.20006 | -0.39692 | -0.22896
| 1028 | -0.22767 | -0.50251 | 0.63435 | -0.35727 | 0.65402 | 0.067316 | -0.14671 | -0.39362 | 0.97 | -0.4653
| 1029 | -0.43813 | -0.39792 | 0.28803 | 0.21878 | -0.11202 | 0.034858 | -0.65287 | -0.070645 | -0.71487 | -0.39925
| 1030 | -0.15804 | -0.15365 | 0.50311 | 0.24138 | 0.57116 | 0.60694 | 0.16507 | 0.57421 | 0.23364 | 0.20861
| 1031 | 0.93755 | 0.46306 | 0.59171 | 0.36731 | 0.57023 | -0.54273 | 0.52345 | -0.84867 | -0.10373 | 0.0067729
| 1032 | -0.75526 | 0.44063 | -0.35278 | 0.052319 | 0.80843 | 0.30595 | 0.40042 | -0.093082 | -0.21572 | -0.61257
| 1033 | -0.032891 | 0.29637 | -0.73713 | 0.32376 | -0.69162 | 0.49651 | -0.41425 | -0.12119 | 0.21827 | 0.16892
| 1034 | 0.67735 | 0.22006 | -0.22702 | 0.54185 | 0.31758 | -0.13 | -0.77439 | -0.12839 | 0.5707 | -0.32583
| 1035 | -0.0094951 | -0.39676 | 0.35525 | -0.29381 | 0.4272 | -0.44909 | -0.67152 | 0.014252 | 0.34327 | -0.10184
| 1036 | -0.034236 | 0.40848 | -0.6631 | -0.00095045 | 0.0049623 | 0.11824 | -0.2571 | 0.026707 | 0.52366 | -0.21687
| 1037 | 0.24548 | -0.19607 | 0.26101 | -0.17145 | -0.0086877 | -0.068925 | -0.23052 | 0.17787 | -0.53235 | 0.2621
| 1038 | -0.24575 | -0.74603 | -0.062823 | -0.42598 | 0.97354 | 0.0030547 | -0.024551 | 0.38918 | 0.041094 | -0.48609
| 1039 | -0.32228 | -0.15946 | 0.43511 | 0.33509 | 0.2995 | -0.36984 | 0.11745 | -0.1578 | 0.77932 | -0.20458
| 1040 | 0.40865 | 0.58227 | -0.021072 | 0.53535 | 0.1179 | -0.31816 | -0.47189 | 0.5332 | -0.018929 | 0.68298
| 1041 | 0.44331 | 0.55022 | -0.18275 | 0.25953 | -0.70487 | -0.37783 | 0.38559 | -0.011314 | 0.12736 | -0.40376
| 1042 | -0.31714 | -0.066673 | 0.56377 | -0.13739 | -0.21776 | -0.34129 | 0.38902 | 0.00085036 | -0.15578 | 0.42441
| 1043 | 0.37558 | 0.60389 | 0.3375 | -0.17435 | 0.86472 | -0.43 | 0.31131 | -0.27426 | -0.60289 | 0.11124
| 1044 | -0.20924 | -0.36305 | 0.23639 | 0.25267 | 0.034754 | 0.44964 | -0.09143 | -0.21712 | -0.70828 | -0.1353
| 1045 | 0.060798 | 0.018522 | 0.086053 | -0.4307 | -0.43476 | 0.56491 | 0.33645 | -0.05 | -0.45972 | 0.55492
| 1046 | -0.21559 | 0.31 | -0.74058 | -0.4046 | 0.0017515 | -0.29056 | -0.39131 | 0.23 | -0.10061 | -0.34159
| 1047 | 0.17884 | 0.88295 | -0.66015 | 0.22173 | 0.63299 | 0.14671 | -0.067637 | -0.00025003 | -0.073231 | -0.63654
| 1048 | -0.16113 | 0.71452 | 0.35961 | 0.48048 | -0.46288 | -0.18348 | 0.60213 | -0.58612 | 0.60389 | -0.07183
| 1049 | -0.24987 | -0.4668 | -0.59073 | 0.35108 | 0.7076 | -0.044856 | -0.23325 | -0.47818 | 0.021276 | 0.24667
| 1050 | -0.86472 | -0.66789 | 0.058884 | -0.63135 | -0.095069 | -0.032788 | 0.54602 | -0.14976 | 0.047792 | -0.80176
| 1051 | 0.14953 | -0.45292 | -0.92584 | 0.20874 | -0.01791 | 0.13797 | 0.046952 | -0.28104 | 0.28803 | -0.20836
| 1052 | 0.62145 | 0.10395 | 0.81917 | 0.28369 | 0.95204 | 0.29793 | -0.33977 | 0.48144 | 0.12725 | 0.12553
| 1053 | 0.10496 | -0.42528 | 0.53902 | -0.34862 | -0.23026 | -0.29537 | -0.79191 | 0.72269 | 0.36857 | 0.00075028
| 1054 | -0.24667 | -0.047582 | -0.037659 | -0.55943 | -0.77932 | -0.5003 | -0.14601 | -0.049684 | 0.31043 | -0.336
| 1055 | 0.72161 | 0.69751 | 0.016384 | -0.57444 | -0.037867 | -0.098501 | 0.31641 | -0.6786 | -0.081469 | 0.3651
| 1056 | -0.43176 | 0.6338 | -0.16675 | 0.012427 | -0.37159 | -0.55853 | 0.22263 | -0.4857 | -0.09529 | 0.1879
| 1057 | -0.20169 | -0.73186 | -0.06197 | 0.67091 | -0.6382 | -0.036932 | -0.1162 | -0.3662 | -0.085506 | 0.45511
| 1058 | -0.33359 | 0.34418 | 0.41153 | -0.38283 | 0.14847 | 0.21789 | 0.073663 | -0.4258 | 0.41034 | 0.19309
| 1059 | 0.080381 | -0.15354 | 0.26115 | -0.47856 | 0.38267 | 0.48609 | -0.18214 | -0.44475 | -0.071291 | -0.016181
| 1060 | 0.37143 | 0.93 | 0.0083852 | 0.12931 | -0.39066 | -0.05814 | -0.25174 | 0.097947 | -0.59122 | 0.30279
| 1061 | 0.1323 | 0.5728 | -0.36968 | -0.21891 | 0.78716 | 0.078317 | 0.064105 | -0.43476 | 0.015978 | 0.5003
| 1062 | 0.20332 | 0.42912 | 0.16615 | 0.58757 | 0.27938 | 0.41819 | 0.09033 | 0.44188 | 0.11564 | -0.33585
| 1063 | -0.2893 | 0.64377 | 0.36227 | -0.12051 | -0.10619 | -0.35077 | -0.39395 | 0.66549 | 0.073555 | -0.21406
| 1064 | -0.47875 | 0.10876 | -0.44493 | 0.47569 | 0.046847 | 0.062823 | -0.39527 | 0.33224 | 0.68968 | -0.72523
| 1065 | -0.59913 | 0.84094 | 0.12954 | -0.083103 | -0.28007 | 0.015063 | -0.536 | -0.1432 | -0.27398 | 0.58083
| 1066 | -0.2037 | -0.85405 | 0.72378 | 0.055172 | -0.041616 | 0.14099 | -0.63462 | 0.2278 | -0.50776 | -0.13334
| 1067 | -0.043287 | 0.016079 | -0.2674 | -0.21381 | -0.60415 | -0.25522 | -0.58107 | 0.24907 | 0.25535 | 0.6637
| 1068 | 0.23691 | 0.65229 | -0.23809 | -0.45036 | 0.35587 | 0.85893 | -0.011213 | 0.61725 | -0.019133 | 0.27316
| 1069 | -0.027735 | 0.06678 | -0.30653 | -0.24628 | -0.56148 | 0.38689 | 0.27605 | -0.1646 | -0.33675 | 0.37079
| 1070 | 0.028249 | -0.16137 | -0.10462 | 0.46065 | -0.56262 | 0.77841 | -0.82084 | 0.50675 | -0.22922 | 0.35587
| 1071 | 0.19 | 0.17121 | -0.26318 | 0.073555 | 0.40259 | 0.073771 | -0.26169 | 0.58395 | -0.31714 | -0.29169
| 1072 | -0.1926 | 0.36494 | 0.13484 | 0.26169 | 0.22792 | -0.56768 | 0.16904 | -0.81265 | -0.25468 | -0.13438
| 1073 | -0.055701 | -0.54011 | -0.12816 | 0.4258 | -0.33194 | 0.79678 | 0.026193 | 0.0026535 | -0.72269 | -0.38902
| 1074 | 0.464 | -0.3537 | 0.13057 | 0.94084 | 0.6952 | 0.52957 | -0.24535 | 0.24099 | -0.14414 | -0.25133
| 1075 | -0.30064 | 0.50271 | -0.19931 | -0.14624 | -0.21432 | 0.21508 | -0.096175 | 0.19421 | 0.09154 | -0.65029
| 1076 | 0.3242 | 0.60846 | -0.24721 | 0.2674 | -0.96127 | 0.40108 | 0.69817 | 0.10697 | 0.0011507 | -0.34083
| 1077 | 0.70657 | 0.54933 | 0.14111 | -0.16952 | -0.23508 | 0.21368 | -0.23312 | 0.67458 | -0.056761 | -0.42303
| 1078 | 0.29793 | -0.23234 | 0.54933 | 0.91693 | 0.13034 | 0.21559 | 0.050632 | 0.95 | 0.042555 | -0.55424
| 1079 | -0.52157 | -0.21597 | 0.5015 | -0.26196 | -0.064746 | -0.4799 | -0.22689 | -0.11281 | 0.39742 | -0.28663
| 1080 | -0.17836 | 0.0067729 | -0.72269 | -0.51616 | 0.18043 | 0.37911 | -0.14367 | -0.06753 | -0.32169 | 0.028043
| 1081 | 0.28397 | 0.17544 | 0.099278 | 0.42078 | -0.39692 | -0.34938 | 0.66103 | -0.067745 | 0.0072765 | -0.28146
| 1082 | 0.12097 | -0.19247 | 0.24112 | 0.69751 | 0.37606 | -0.53064 | 0.16976 | 0.13046 | 0.50796 | -0.74603
| 1083 | -0.16328 | -0.63408 | 0.082231 | -0.24721 | 0.94084 | -0.01 | -0.44565 | -0.072153 | -0.64181 | 0.18434
| 1084 | 0.73186 | 0.19483 | 0.010808 | -0.066137 | 0.32776 | 0.063784 | -0.003456 | -0.12097 | -0.59565 | 0.36889
| 1085 | -0.24086 | -0.10328 | -0.012731 | 0.33615 | 0.13623 | 0.13161 | -0.54558 | 0.77483 | -0.64687 | -0.18434
| 1086 | -0.52345 | -0.32317 | 0.0057666 | -0.80584 | 0.04099 | -0.20044 | -0.52979 | 0.72815 | 0.56583 | 0.31509
| 1087 | -0.098945 | -0.59565 | 0.049369 | 0.34266 | -0.77977 | 0.64829 | -0.30696 | 0.1072 | -0.2524 | 0.042033
| 1088 | -0.78344 | 0.37847 | 0.61335 | -0.39726 | 0.58419 | 0.22844 | 0.49453 | -0.040677 | 0.078425 | 0.33374
| 1089 | -0.4776 | -0.35139 | -0.6546 | -0.52136 | 0.94432 | -0.25885 | 0.56606 | 0.14367 | -0.18324 | 0.017503
| 1090 | 0.045694 | -0.27799 | -0.41768 | -0.11112 | 0.55762 | 0.51205 | -0.74841 | -0.63599 | -0.57703 | -0.67427
| 1091 | -0.7623 | 0.95 | -0.21444 | -0.37143 | -0.23039 | -0.33179 | -0.10094 | 0.53449 | -0.052319 | 0.50857
| 1092 | -0.015063 | 0.61516 | -0.15106 | 0.35945 | 0.23351 | 0.012123 | -0.0051633 | 0.098834 | -0.60314 | -0.60465
| 1093 | 0.73261 | -0.34617 | -0.12085 | -0.44475 | 0.4995 | 0.43973 | 0.66281 | 0.25522 | -0.49572 | -0.29339
| 1094 | 0.54076 | 0.087586 | -0.10006 | 0.26237 | -0.61257 | -0.34923 | -0.53772 | -0.30653 | 0.080816 | 0.78206
| 1095 | 0.18067 | 0.41665 | -0.044647 | -0.55559 | 0.17629 | 0.17617 | 0.022503 | 0.49295 | -0.77977 | -0.1196
| 1096 | -0.093303 | -0.67152 | 0.036102 | -0.018114 | -0.93144 | -0.13739 | 0.27137 | 0.073339 | -0.68425 | 0.8422
| 1097 | 0.46981 | -0.21139 | -0.34174 | -0.25294 | 0.30509 | 0.5098 | -0.48144 | 0.41871 | 0.38429 | 0.2343
| 1098 | -0.045904 | 0.1797 | -0.81642 | 0.3148 | 0.67121 | 0.47208 | -0.23404 | -0.018216 | -0.84736 | 0.34388
| 1099 | 0.35836 | 0.3116 | -0.20508 | 0.50857 | -0.23954 | 0.3375 | -0.12782 | -0.1179 | 0.27661 | -0.5583
| 1100 | -0.092862 | -0.81212 | 0.88295 | -0.41768 | -0.20407 | 0.33555 | 0.14017 | 0.25845 | -0.016893 | -0.25482
| 1101 | -0.12587 | -0.10362 | 0.020766 | 0.11552 | 0.42668 | -0.17556 | 0.33781 | -0.33314 | -0.050632 | 0.26156
| 1102 | -0.0075787 | 0.6319 | -0.31538 | -0.15283 | -0.31582 | 0.10473 | -0.94432 | -0.3214 | -0.18397 | 0.011516
| 1103 | -0.42112 | 0.10641 | 0.11112 | 0.20722 | 0.3864 | -0.06016 | 0.69065 | -0.11541 | 0.033098 | 0.11903
| 1104 | 0.50837 | 0.20861 | 0.09121 | -0.51969 | -0.21406 | 0.39411 | 0.27288 | -0.13392 | 0.035065 | 0.79531
| 1105 | 0.26849 | 0.32672 | -0.49493 | 0.45255 | 0.074419 | -0.39312 | 0.57917 | 0.41204 | -0.021787 | 0.54054
| 1106 | 0.09121 | 0.022401 | 0.13034 | -0.11011 | 0.77439 | 0.6637 | 0.77306 | -0.40966 | -0.068925 | -0.40042
| 1107 | 0.25885 | 0.053903 | 0.044019 | -0.10172 | -0.2893 | -0.6755 | -0.38478 | -0.44009 | -0.42965 | -0.77395
| 1108 | -0.43458 | -0.47151 | 0.88381 | 0.56377 | -0.52851 | 0.45658 | -0.10429 | -0.16077 | 0.74058 | 0.6703
| 1109 | 0.53881 | -0.19458 | 0.1634 | 0.77483 | 0.60643 | 0.43018 | 0.8618 | -0.49157 | 0.062183 | 0.17157
| 1110 | -0.60238 | 0.26781 | -0.61829 | -0.099944 | -0.52115 | -0.031341 | -0.027837 | -0.58299 | -0.39593 | -0.11926
| 1111 | -0.53149 | 0.4553 | -0.29793 | -0.87793 | -0.51041 | -0.030928 | 0.82365 | -0.37911 | 0.081251 | 0.36211
| 1112 | 0.52894 | -0.82651 | -0.20949 | 0.79925 | 0.26142 | 0.5013 | -0.10753 | -0.11439 | 0.0056661 | -0.29622
| 1113 | 0.77439 | 0.35463 | -0.48687 | -0.37127 | -0.59565 | -0.38461 | -0.38445 | -0.27123 | 0.24641 | -0.094075
| 1114 | 0.5707 | 0.34357 | -0.18116 | -0.26918 | -0.31043 | 0.10933 | 0.031857 | -0.73866 | -0.023527 | 0.26332
| 1115 | -0.78297 | -0.44313 | -0.59689 | 0.10518 | 0.28916 | 0.39975 | 0.20911 | -0.24033 | -0.16507 | -0.27674
| 1116 | 0.046218 | -0.068711 | -0.18508 | -0.6786 | 0.48863 | 0.035376 | 0.33179 | -0.10742 | 0.1473 | 0.59938
| 1117 | 0.46793 | 0.05422 | -0.27233 | 0.63875 | -0.30079 | -0.10989 | 0.36258 | 0.4993 | -0.3838 | 0.30193
| 1118 | -0.34159 | -0.0012508 | -0.18717 | -0.3015 | 0.49334 | 0.86252 | -0.077232 | 0.46232 | 0.0076795 | -0.35961
| 1119 | 0.20886 | 0.28146 | -0.065923 | 0.57798 | 0.60013 | -0.33045 | -0.27674 | 0.28369 | 0.3048 | 0.95417
| 1120 | -0.038075 | -0.30653 | 0.048212 | 0.025372 | 0.62224 | 0.48902 | -0.22547 | 0.5608 | 0.46906 | -0.43582
| 1121 | 0.70623 | 0.22754 | -0.23013 | 0.30509 | -0.096507 | 0.59639 | -0.044437 | -0.064425 | 0.59988 | -0.14379
| 1122 | -0.44277 | 0.3375 | -0.099611 | 0.34708 | 0.71242 | 0.42528 | 0.11869 | 0.039427 | -0.548 | 0.13634
| 1123 | -0.15709 | -0.5141 | -0.21802 | 0.15236 | -0.20772 | -0.079402 | 0.41733 | 0.40865 | -0.069463 | -0.0039578
| 1124 | -0.11135 | 0.24867 | -0.59813 | -0.69488 | -0.13115 | 0.31846 | -0.62119 | 0.46962 | 0.1884 | 0.89091
| 1125 | 0.64377 | -0.097503 | -0.43635 | -0.053269 | -0.76913 | 0.089341 | 0.019337 | -0.83538 | -0.39742 | 0.0027538
| 1126 | -0.020561 | -0.46943 | -0.85474 | -0.3759 | 0.29622 | 0.32081 | 0.68204 | 0.5959 | -0.18348 | -0.16268
| 1127 | 0.63135 | -0.29722 | -0.17532 | -0.56102 | -0.52576 | -0.58684 | -0.52157 | -0.19981 | -0.51205 | -0.152
| 1128 | -0.08989 | 0.25912 | 0.62838 | 0.1432 | -0.48241 | -0.42511 | 0.10083 | -0.095511 | -0.061757 | -0.036828
| 1129 | -0.14847 | -0.11 | 0.88554 | -0.33134 | -0.40225 | -0.10083 | -0.39775 | -0.0015512 | 0.43264 | 0.21355
| 1130 | 0.68425 | 0.36604 | -0.35899 | -0.46774 | 0.16232 | 0.002453 | 0.38413 | -0.76272 | -0.28916 | 0.13948
| 1131 | -0.65029 | 0.01547 | 0.32836 | -0.12176 | -0.4993 | 0.40427 | 0.12564 | -0.79239 | 0.5458 | -0.09176
| 1132 | -0.53299 | 0.27165 | 0.43582 | -0.27619 | 0.38804 | 0.10899 | 0.65663 | 0.20558 | 0.034754 | -0.1841
| 1133 | 0.25858 | -0.84412 | 0.4859 | 0.68235 | 0.21076 | -0.67766 | 0.40477 | -0.0062697 | -0.042869 | -0.65402
| 1134 | -0.55447 | 0.37654 | -0.11496 | 0.051686 | -0.47645 | 0.30451 | -0.0866 | -0.13426 | -0.55469 | 0.18055
| 1135 | 0.56676 | -0.17084 | 0.27619 | 0.072369 | -0.024244 | 0.27426 | -0.58443 | -0.67922 | 0.43742 | 0.077449
| 1136 | 0.34008 | -0.29056 | 0.30855 | 0.40713 | 0.20609 | 0.038699 | 0.72926 | 0.3366 | -0.6319 | -0.53816
| 1137 | 0.54956 | -0.13496 | 0.7429 | -0.016181 | 0.4471 | -0.90673 | -0.30007 | 0.32302 | 0.3087 | 0.010303
| 1138 | -0.28845 | -0.33464 | -0.72197 | 0.50939 | 0.18557 | 0.55514 | -0.31743 | 0.43938 | -0.54668 | -0.013846
| 1139 | 0.78576 | 0.88642 | -0.13426 | -0.2278 | -0.22676 | 0.81265 | -0.43105 | 0.37767 | -0.15804 | 0.0050628
| 1140 | -0.28705 | -0.27785 | 0.81642 | -0.31334 | -0.62973 | -0.028043 | -0.63217 | -0.79143 | 0.016283 | -0.14578
| 1141 | -0.062183 | -0.15578 | -0.69652 | -0.27357 | 0.14589 | -0.58227 | 0.81534 | 0.10899 | 0.66819 | 0.25953
| 1142 | -0.074311 | -0.1196 | -0.01344 | 0.53837 | 0.41068 | 0.2784 | -0.012934 | 0.25872 | 0.17036 | 0.17532
| 1143 | 0.011112 | -0.56354 | -0.087147 | 0.61412 | -0.94615 | -0.13496 | -0.13299 | 0.027118 | -0.60694 | -0.88042
| 1144 | -0.71769 | -0.12063 | -0.2081 | -0.2512 | 0.044751 | -0.045799 | 0.22418 | 0.11983 | 0.0059678 | 0.24244
| 1145 | -0.42078 | -0.25629 | -0.16868 | -0.17605 | -0.4117 | 0.55379 | -0.85752 | 0.4999 | -0.051159 | 0.073771
| 1146 | -0.013846 | 0.3537 | 0.51205 | 0.85682 | 0.77751 | 0.57186 | 0.081795 | -0.40611 | -0.29921 | -0.62145
| 1147 | -0.41579 | -0.51 | 0.54251 | -0.27412 | 0.31087 | -0.085287 | -0.60541 | 0.74368 | -0.080381 | -0.050211
| 1148 | 0.24654 | -0.19471 | -0.52915 | 0.26808 | -0.38836 | -0.28677 | -0.61257 | 0.064853 | 0.18975 | -0.80584
| 1149 | 0.27467 | -0.67953 | 0.15899 | 0.76484 | -0.13971 | -0.64518 | 0.23757 | -0.47094 | 0.7735 | 0.3005
| 1150 | -0.0071757 | 0.97 | -0.29921 | -0.57774 | 0.39775 | -0.40309 | -0.57633 | -0.40025 | 0.31758 | 0.5007
| 1151 | 0.43088 | 0.20031 | -0.25589 | 0.28146 | 0.047267 | 0.031548 | -0.25027 | -0.39659 | 0.58733 | -0.37638
| 1152 | -0.13023 | 0.34327 | -0.7512 | -0.22315 | 0.17823 | 0.098279 | 0.13519 | 0.91 | 0.032477 | -0.033718
| 1153 | -0.43653 | 0.21393 | 0.57941 | -0.86252 | -0.17386 | -0.36243 | -0.071722 | 0.69685 | 0.72305 | -0.17253
| 1154 | -0.46587 | 0.66192 | -0.010707 | 0.79826 | 0.28355 | 0.75938 | -0.23993 | 0.085834 | 0.61 | 0.12439
| 1155 | 0.30179 | 0.13924 | -0.028661 | -0.58371 | 0.77572 | 0.31102 | -0.51328 | 0.47607 | -0.21597 | 0.30639
| 1156 | 0.17933 | -0.90673 | -0.66162 | 0.67704 | 0.35123 | 0.015876 | -0.67091 | 0.21038 | 0.47113 | 0.73373
| 1157 | 0.037971 | 0.18018 | -0.042555 | -0.45456 | -0.64042 | 0.29779 | -0.17677 | -0.45127 | -0.41785 | 0.052319
| 1158 | -0.48648 | 0.39792 | 0.11259 | -0.66728 | -0.10028 | -0.46868 | 0.47113 | 0.43546 | -0.019439 | 0.14859
| 1159 | -0.19582 | 0.44945 | -0.83783 | 0.063998 | 0.3767 | -0.75444 | -0.10284 | -0.30265 | 0.3132 | -0.11326
| 1160 | -0.67766 | 0.64943 | -0.2567 | -0.013238 | -0.43653 | 0.17048 | -0.017605 | -0.088792 | 0.33539 | 0.25147
| 1161 | 0.58587 | -0.22909 | -0.38836 | -0.012022 | -0.22238 | -0.50291 | -0.42459 | -0.61231 | 0.019745 | 0.23783
| 1162 | -0.18569 | 0.064532 | -0.41442 | 0.30021 | 0.42337 | 0.11983 | -0.12313 | 0.009697 | -0.22624 | 0.066673
| 1163 | -0.21177 | -0.10574 | 0.08234 | 0.013846 | -0.152 | -0.60263 | 0.27827 | -0.10944 | 0.071938 | -0.35139
| 1164 | 0.23652 | 0.034443 | -0.55807 | 0.62892 | 0.27261 | 0.19557 | 0.45073 | -0.53449 | -0.51 | 0.39842
| 1165 | -0.38738 | 0.10384 | -0.024654 | 0.077666 | -0.21712 | -0.76913 | 0.046742 | 0.45677 | -0.15697 | 0.1127
| 1166 | 0.3189 | -0.037451 | -0.27302 | -0.12461 | 0.076366 | 0.19297 | -0.51554 | 0.33826 | -0.15365 | -0.3425
| 1167 | -0.13948 | 0.062823 | -0.3242 | 0.74525 | 0.94255 | 0.36952 | -0.32524 | -0.26413 | 0.5102 | -0.081033
| 1168 | -0.26169 | 0.2941 | 0.35618 | -0.41562 | 0.59318 | 0.71242 | -0.42528 | -0.081033 | 0.36683 | 0.46624
| 1169 | 0.0085869 | 0.58083 | 0.33615 | 0.36794 | -0.50492 | 0.56768 | -0.081251 | 0.48087 | 0.55245 | 0.031961
| 1170 | -0.098723 | -0.65057 | 0.93292 | 0.084085 | -0.25966 | 0.46474 | 0.3186 | 0.4392 | -0.079511 | 0.13983
| 1171 | -0.82139 | 0.32539 | -0.10106 | -0.28565 | 0.0071757 | -0.073987 | -0.20533 | -0.53729 | 0.14484 | -0.04172
| 1172 | -0.35992 | -0.081033 | -0.14344 | 0.53924 | -0.23195 | -0.011617 | -0.77751 | 0.031341 | -0.61803 | 0.04538
| 1173 | 0.73223 | -0.28831 | 0.40881 | -0.69032 | 0.67152 | 0.3956 | -0.40075 | -0.47875 | 0.038491 | -0.21521
| 1174 | -0.55312 | -0.19757 | 0.85964 | -0.37111 | -0.46774 | -0.0013509 | -0.84801 | 0.38089 | 0.13634 | 0.051264
| 1175 | -0.042451 | -0.4531 | 0.011112 | 0.12074 | -0.08978 | -0.025988 | 0.48922 | -0.85893 | 0.73 | 0.28621
| 1176 | 0.61672 | 0.51699 | -0.30394 | 0.40326 | 0.58927 | -0.63572 | 0.57327 | 0.16066 | -0.16844 | 0.38951
| 1177 | -0.47398 | 0.43158 | 0.10966 | 0.84412 | -0.25522 | -0.83357 | -0.32096 | 0.73751 | 0.093965 | 0.089341
| 1178 | 0.32391 | 0.37976 | 0.046847 | -0.22071 | -0.40008 | 0.2941 | 0.77483 | -0.66133 | -0.15507 | -0.25
| 1179 | -0.47856 | 0.011516 | 0.60339 | 0.40578 | -0.027323 | -0.40763 | -0.36055 | -0.7005 | -0.13971 | 0.40966
| 1180 | -0.15614 | 0.80125 | -0.64489 | 0.38348 | 0.6546 | 0.29921 | -0.12977 | -0.81807 | 0.28621 | -0.30179
| 1181 | -0.2161 | -0.72305 | -0.58733 | 0.30769 | 0.45787 | 0.4668 | 0.43813 | -0.27481 | -0.030516 | -0.57869
| 1182 | -0.49751 | -0.57397 | -0.66519 | 0.039948 | 0.45456 | 0.43653 | 0.17109 | 0.32955 | -0.32287 | -0.056655
| 1183 | -0.34647 | -0.10184 | 0.34785 | 0.22495 | -0.30523 | 0.035583 | 0.20546 | 0.12897 | 0.31349 | 0.23954
| 1184 | -0.56791 | 0.002453 | -0.84031 | -0.152 | -0.19919 | -0.26973 | -0.28327 | 0.28481 | -0.44674 | -0.17775
| 1185 | 0.79433 | -0.37879 | 0.19981 | -0.16101 | -0.18877 | 0.42737 | -0.10664 | -0.77218 | -0.31816 | 0.24987
| 1186 | -0.13334 | -0.80075 | -0.089451 | -0.32406 | -0.41957 | -0.031548 | 0.29381 | 0.2427 | 0.81534 | -0.23678
| 1187 | -0.63435 | 0.74801 | 0.69784 | -0.095732 | 0.31728 | 0.26658 | -0.050105 | -0.6118 | 0.3961 | -0.24667
| 1188 | -0.43387 | 0.58854 | -0.026193 | -0.10284 | 0.3061 | -0.16448 | 0.22456 | 0.30769 | -0.41974 | 0.10451
| 1189 | -0.69751 | -0.85474 | 0.5332 | 0.2995 | 0.54845 | -0.8467 | 0.70453 | 0.31611 | 0.28579 | 0.50614
| 1190 | 0.22573 | 0.37783 | -0.83118 | -0.28035 | -0.068925 | -0.31131 | -0.030206 | 0.27385 | -0.09198 | -0.85752
| 1191 | 0.50291 | -0.22019 | 0.02281 | 0.047582 | 0.11045 | -0.54338 | -0.47607 | 0.59318 | -0.16304 | -0.56653
| 1192 | 0.13901 | 0.25831 | -0.094406 | -0.22663 | -0.11699 | 0.4307 | 0.48648 | 0.30509 | 0.021685 | 0.11915
| 1193 | 0.77395 | 0.10072 | 0.76569 | -0.26973 | -0.48222 | 0.69 | 0.040782 | 0.82651 | -0.11824 | 0.48804
| 1194 | -0.23665 | -0.68775 | 0.81212 | 0.65839 | 0.20019 | -0.25643 | 0.17411 | -0.32881 | 0.28035 | 0.34632
| 1195 | -0.53686 | -0.55649 | 0.30624 | 0.55898 | 0.05549 | -0.85134 | -0.19185 | 0.12176 | 0.38755 | 0.21955
| 1196 | 0.15507 | 0.43653 | -0.44475 | 0.56011 | -0.65229 | 0.80226 | -0.1926 | -0.40276 | -0.55943 | 0.55537
| 1197 | -0.015978 | 0.089561 | -0.81426 | -0.21266 | -0.14929 | -0.38413 | 0.3048 | 0.33645 | 0.0004501 | -0.31
| 1198 | 0.013542 | 0.056867 | -0.22741 | -0.097282 | 0.71592 | -0.014353 | 0.30451 | 0.19732 | -0.464 | 0.25885
| 1199 | -0.52177 | 0.017809 | 0.43229 | 0.51041 | -0.20747 | -0.55875 | -0.39329 | -0.033098 | -0.034754 | -0.29936
| 1200 | -0.99 | 0.20269 | 0.39066 | -0.27979 | -0.28635 | -0.34433 | 0.40159 | -0.40175 | 0.56194 | 0.37254
| 1201 | -0.17994 | 0.27674 | -0.24244 | 0.2398 | 0.18495 | 0.13138 | -0.17423 | 0.11722 | -0.23156 | 0.28565
| 1202 | 0.35386 | -0.029691 | -0.21917 | -0.039323 | -0.30093 | 0.07183 | -0.65663 | -0.21152 | 0.15377 | -0.15306
| 1203 | 0.14788 | -0.53751 | 0.075716 | -0.28761 | -0.54712 | -0.47151 | 0.60138 | 0.069677 | 0.22663 | -0.17157
| 1204 | 0.037867 | 0.67704 | 0.49157 | -0.068281 | -0.15059 | -0.39775 | -0.66044 | -0.17994 | -0.81053 | 0.50513
| 1205 | 0.092311 | 0.81265 | -0.29466 | -0.6637 | 0.062183 | -0.12017 | -0.81917 | 0.11473 | -0.15236 | -0.048317
| 1206 | 0.51678 | 0.18226 | 0.61412 | 0.3607 | -0.07962 | 0.052846 | -0.67488 | 0.037451 | 0.43281 | -0.083212
| 1207 | -0.59098 | -0.4258 | -0.11146 | 0.52619 | 0.42947 | -0.012528 | 0.18753 | 0.55875 | -0.26849 | -0.55044
| 1208 | -0.62973 | 0.30855 | -0.40746 | -0.25589 | -0.50472 | 0.19508 | 0.54382 | 0.54624 | 0.34708 | 0.44855
| 1209 | 0.028661 | 0.22987 | 0.69685 | 0.1803 | -0.43299 | 0.52177 | 0.49315 | 0.37831 | 0.14414 | -0.011921
| 1210 | -0.013643 | 0.073231 | 0.1825 | -0.31655 | 0.077883 | -0.13403 | 0.098834 | 0.22405 | 0.068711 | -0.08967
| 1211 | 0.097282 | -0.68141 | -0.62946 | 0.71208 | 0.22353 | -0.21597 | 0.21878 | -0.76827 | 0.16663 | 0.30437
| 1212 | -0.36873 | -0.12656 | -0.54382 | -0.022094 | -0.99 | 0.14695 | 0.85269 | -0.35945 | 0.09529 | 0.18092
| 1213 | -0.43246 | -0.079185 | -0.067852 | 0.24217 | 0.26863 | 0.054537 | -0.44493 | -0.51823 | 0.11135 | 0.35836
| 1214 | -0.057397 | 0.14402 | 0.27854 | 0.15141 | 0.013643 | 0.72305 | -0.14099 | -0.32806 | 0.44583 | -0.41854
| 1215 | -0.06914 | -0.30437 | -0.15602 | -0.21127 | -0.44439 | 0.11281 | 0.16627 | 0.49612 | -0.11801 | -0.42546
| 1216 | -0.51927 | -0.65201 | 0.37783 | -0.01344 | -0.60063 | 0.57798 | 0.55156 | 0.068174 | -0.47607 | 0.037971
| 1217 | -0.38234 | 0.15744 | -0.5458 | -0.28243 | -0.70251 | 0.44656 | 0.29637 | -0.90356 | 0.70657 | 0.49295
| 1218 | 0.64209 | 0.46139 | -0.21572 | 0.0092932 | 0.29325 | 0.70966 | -0.86771 | -0.042242 | 0.09044 | -0.38478
| 1219 | -0.028455 | 0.32762 | 0.52957 | 0.68583 | -0.56861 | 0.57303 | -0.3306 | -0.19582 | -0.017707 | 0.58903
| 1220 | 0.24007 | 0.47588 | 0.63572 | -0.51123 | -0.24257 | 0.36321 | -0.86108 | -0.51389 | -0.062397 | 0.27509
| 1221 | -0.44818 | -0.12816 | 0.63875 | -0.79531 | 0.39033 | 0.23456 | 0.55966 | 0.11236 | 0.52894 | -0.37526
| 1222 | 0.42199 | -0.62171 | -0.009596 | 0.048317 | -0.38951 | -0.081904 | -0.19557 | 0.45935 | 0.37095 | 0.64209
| 1223 | -0.11236 | -0.033512 | -0.8956 | 0.36415 | 0.1752 | -0.032064 | -0.42772 | -0.68807 | 0.80739 | -0.12074
| 1224 | -0.13785 | 0.11575 | -0.76784 | 0.47798 | -0.16328 | -0.2402 | -0.60013 | -0.15543 | -0.21891 | -0.53946
| 1225 | -0.092641 | -0.74368 | -0.04099 | -0.11214 | 0.36164 | -0.15768 | -0.039011 | 0.61026 | -0.1841 | 0.63875
| 1226 | -0.47417 | 0.13727 | 0.31102 | 0.96127 | -0.20207 | -0.42772 | -0.18397 | -0.37622 | 0.16472 | -0.19844
| 1227 | -0.12393 | 0.65 | -0.079185 | -0.6044 | 0.32911 | 0.037971 | -0.20319 | -0.39312 | 0.37606 | -0.26156
| 1228 | -0.12622 | -0.28383 | 0.011415 | 0.28579 | 0.062717 | -0.21994 | -0.14554 | -0.71138 | 0.4078 | -0.17592
| 1229 | 0.058353 | -0.86923 | -0.18153 | -0.75896 | -0.6349 | 0.21355 | 0.46213 | 0.14344 | 0.54712 | -0.022912
| 1230 | -0.36431 | 0.20257 | -0.41836 | -0.15318 | 0.29722 | 0.64433 | 0.10317 | 0.024859 | 0.20081 | -0.22857
| 1231 | -0.34908 | -0.76698 | -0.20344 | 0.084631 | 0.19111 | 0.46718 | 0.56977 | -0.44782 | -0.22122 | -0.39246
| 1232 | -0.11699 | 0.64265 | 0.59294 | 0.87077 | 0.66519 | 0.7735 | -0.12279 | 0.15071 | -0.036724 | 0.28635
| 1233 | 0.8821 | -0.78858 | -0.44116 | -0.46139 | -0.063998 | -0.51143 | -0.48454 | -0.57116 | -0.38445 | 0.16244
| 1234 | 0.64546 | -0.29 | -0.31816 | -0.41613 | -0.4995 | -0.043078 | -0.42511 | -0.36023 | 0.34038 | 0.41153
| 1235 | -0.33796 | -0.24522 | -0.037867 | 0.16018 | 0.10978 | 0.14624 | 0.48493 | 0.34617 | -0.44349 | 0.79239
| 1236 | 0.33045 | 0.33645 | -0.59491 | 0.24059 | -0.51246 | 0.24774 | -0.33539 | 0.093965 | -0.37767 | -0.57941
| 1237 | 0.24165 | 0.52915 | 0.22715 | 0.564 | -0.023834 | -0.063891 | -0.80025 | 0.025269 | -0.25899 | 0.58443
| 1238 | -0.24933 | 0.66728 | -0.49771 | 0.0067729 | -0.12439 | -0.056231 | 0.65114 | 0.39958 | 0.72779 | 0.55853
| 1239 | -0.093192 | 0.50695 | -0.2313 | -0.070108 | 0.32007 | -0.0728 | -0.40561 | 0.24033 | 0.55649 | -0.11372
| 1240 | -0.11801 | 0.18975 | 0.93597 | -0.98268 | 0.46605 | -0.6703 | 0.10608 | -0.39809 | -0.18704 | 0.14052
| 1241 | -0.4983 | 0.24349 | -0.61257 | 0.25683 | -0.41442 | -0.092311 | -0.62304 | 0.60113 | 0.49612 | 0.15875
| 1242 | 0.27924 | -0.015267 | 0.057822 | 0.15507 | -0.18569 | 0.36243 | -0.035687 | -0.93144 | -0.018522 | 0.09011
| 1243 | 0.20232 | -0.26713 | 0.22444 | -0.40125 | 0.025269 | -0.75896 | 0.09044 | 0.59049 | -0.0019519 | -0.11338
| 1244 | -0.32125 | -0.33524 | -0.49315 | -0.39197 | 0.38967 | -0.071184 | -0.5224 | 0.14145 | 0.74841 | -0.26918
| 1245 | -0.76188 | -0.14425 | -0.3804 | -0.24508 | -0.55739 | -0.18177 | -0.45328 | 0.81697 | -0.17872 | 0.09529
| 1246 | -0.14087 | -0.36039 | 0.013136 | -0.4293 | -0.3074 | 0.3189 | 0.19956 | -0.74329 | -0.73149 | 0.014962
| 1247 | -0.015673 | 0.33902 | 0.040469 | -0.55335 | 0.74564 | 0.78297 | -0.20244 | 0.31568 | 0.57116 | 0.053797
| 1248 | 0.88381 | -0.4117 | 0.06753 | -0.16868 | 0.16101 | -0.51123 | 0.0781 | 0.49631 | 0.51266 | -0.56354
| 1249 | 0.25831 | -0.1245 | 0.58878 | -0.86771 | 0.93917 | -0.62865 | -0.17617 | -0.73942 | -0.82139 | -0.061437
| 1250 | 0.31087 | -0.41785 | -0.152 | 0.76399 | -0.48125 | 0.12943 | -0.64461 | -0.009798 | -0.28859 | -0.71417
| 1251 | -0.06261 | 0.17872 | -0.2042 | 0.52979 | 0.85 | -0.45732 | 0.73 | 0.0072765 | 0.16077 | 0.17568
| 1252 | -0.22392 | 0.26332 | -0.21597 | 0.00085036 | -0.18606 | 0.24721 | -0.35494 | -0.38967 | 0.18889 | 0.49236
| 1253 | -0.16651 | -0.42181 | -0.75485 | 0.40797 | 0.080707 | 0.1825 | -0.50251 | 0.34129 | 0.53 | 0.070538
| 1254 | -0.42895 | -0.46699 | -0.51246 | -0.13634 | -0.082013 | 0.28271 | -0.027118 | -0.25616 | 0.39181 | 0.030412
| 1255 | -0.64943 | 0.17568 | 0.19483 | 0.72779 | -0.44927 | 0.29113 | 0.49473 | 0.18963 | 0.57798 | -0.067316
| 1256 | 0.0025533 | -0.26658 | -0.93917 | 0.35092 | 0.11586 | -0.43706 | -0.13496 | -0.32985 | -0.81106 | -0.3593
| 1257 | 0.19831 | -0.018623 | -0.4041 | -0.74368 | -0.14169 | 0.16579 | 0.87077 | 0.011314 | -0.050316 | 0.46028
| 1258 | 0.14029 | -0.23809 | 0.10306 | -0.39312 | 0.010101 | -0.30971 | -0.50634 | -0.14835 | 0.056867 | -0.42407
| 1259 | -0.45347 | -0.32007 | 0.16639 | 0.29367 | -0.44565 | 0.72089 | 0.11824 | -0.26373 | 0.98268 | 0.54602
| 1260 | 0.14613 | -0.045065 | -0.61646 | -0.23065 | -0.51061 | 0.37016 | 0.023015 | 0.52198 | -0.59614 | 0.17945
| 1261 | -0.71875 | 0.65956 | -0.028764 | 0.058353 | -0.12324 | 0.072153 | 0.46868 | 0.13403 | -0.32435 | -0.41494
| 1262 | -0.3727 | -0.36243 | -0.26373 | 0.29325 | -0.46418 | -0.44439 | -0.1729 | -0.1769 | 0.075933 | 0.1559
| 1263 | -0.12484 | 0.55989 | -0.064425 | -0.88295 | 0.092531 | -0.12576 | -0.39148 | -0.78023 | -0.043391 | 0.070108
| 1264 | -0.19894 | 0.039219 | -0.093965 | -0.0072765 | -0.045904 | 0.025064 | 0.55469 | -0.068925 | -0.073987 | 0.44674
| 1265 | 0.011314 | 0.52597 | 0.18988 | 0.45292 | -0.047477 | -0.2216 | -0.055701 | -0.16615 | 0.76484 | -0.33494
| 1266 | -0.072369 | 0.39066 | 0.76146 | 0.33871 | 0.25522 | -0.88909 | 0.50472 | -0.22883 | 0.42895 | -0.3662
| 1267 | -0.37366 | -0.25912 | 0.32125 | 0.65258 | -0.60339 | -0.44927 | -0.26973 | -0.22366 | 0.29893 | -0.1253
| 1268 | 0.098945 | -0.73942 | 0.62119 | 0.21559 | -0.19124 | 0.15071 | -0.40511 | 0.18397 | 0.63326 | -0.62384
| 1269 | -0.065923 | 0.27027 | 0.51307 | 0.26904 | -0.04266 | 0.19894 | 0.40746 | -0.50939 | -0.055278 | -0.070323
| 1270 | 0.35216 | -0.34571 | 0.35154 | -0.020255 | -0.36227 | 0.030103 | 0.54978 | -0.030309 | 0.75855 | 0.82651
| 1271 | -0.029794 | -0.11609 | -0.5141 | -0.62357 | 0.10128 | -0.081142 | 0.50735 | 0.72089 | -0.039011 | -0.2225
| 1272 | -0.26047 | -0.53192 | 0.30451 | 0.08485 | -0.26101 | -0.22058 | -0.15118 | 0.46605 | -0.54734 | -0.33615
| 1273 | -0.12382 | 0.88467 | -0.66429 | -0.37574 | -0.26699 | -0.42895 | -0.37048 | -0.56011 | -0.11428 | -0.012934
| 1274 | 0.15851 | -0.54054 | -0.17435 | -0.042138 | -0.15721 | -0.6241 | -0.048107 | -0.74019 | 0.2816 | -0.4991
| 1275 | -0.12736 | 0.45861 | -0.5922 | 0.55156 | 0.536 | 0.27137 | 0.65634 | -0.24112 | 0.55469 | -0.059734
| 1276 | 0.4134 | -0.49059 | -0.33284 | 0.27014 | -0.041825 | 0.43405 | 0.66638 | 0.019949 | 0.032994 | -0.073447
| 1277 | -0.65576 | -0.61568 | -0.34785 | 0.20583 | -0.1466 | 0.18877 | 0.49413 | -0.25013 | 0.096175 | -0.03974
| 1278 | -0.20874 | 0.1957 | -0.01182 | 0.22974 | 0.1628 | 0.564 | -0.31875 | -0.14847 | -0.28369 | 0.064853
| 1279 | 0.51616 | 0.20445 | -0.038179 | 0.4898 | -0.058671 | -0.45383 | 0.74058 | -0.58708 | -0.071399 | 0.061011
| 1280 | 0.48396 | 0.75938 | -0.39444 | 0.10854 | 0.2985 | 0.33539 | -0.19894 | 0.64801 | -0.01091 | 0.92859
| 1281 | 0.32273 | -0.63737 | -0.71208 | -0.45898 | -0.43759 | -0.34448 | 0.25576 | 0.15733 | 0.33509 | 0.048317
| 1282 | -0.22974 | 0.28118 | 0.32258 | -0.32022 | 0.24297 | -0.25147 | -0.056973 | -0.017096 | 0.79727 | 0.27426
| 1283 | 0.56861 | 0.051369 | -0.11293 | 0.046008 | 0.09187 | 0.096839 | 0.80739 | -0.46755 | 0.036205 | 0.69685
| 1284 | 0.50371 | -0.10451 | -0.63135 | -0.28104 | 0.041303 | 0.08343 | -0.35665 | 0.24827 | 0.148 | 0.22818
| 1285 | -0.044437 | 0.10619 | 0.77439 | -0.10933 | 0.067316 | -0.58733 | -0.85474 | 0.72018 | 0.48785 | -0.2265
| 1286 | 0.38089 | -0.14087 | 0.13115 | -0.62704 | -0.61594 | -0.58419 | -0.57964 | -0.49098 | 0.034858 | -0.17982
| 1287 | -0.48415 | -0.51164 | -0.17217 | 0.0089904 | -0.084413 | -0.43742 | -0.78297 | -0.17314 | -0.047582 | 0.064318
| 1288 | 0.86252 | 0.01091 | 0.037451 | 0.34601 | -0.26904 | -0.11575 | 0.30036 | -0.22961 | -0.73904 | -0.14542
| 1289 | 0.66074 | 0.27096 | 0.19744 | -0.85201 | 0.0173 | -0.022912 | -0.11124 | 0.69292 | 0.48396 | -0.19173
| 1290 | 0.11496 | 0.0046609 | -0.012832 | -0.49196 | 0.55178 | -0.5005 | -0.25616 | -0.17896 | 0.059415 | 0.48357
| 1291 | 0.099389 | -0.64405 | 0.3864 | 0.61725 | 0.46195 | 0.0027538 | -0.25107 | 0.25281 | 0.20609 | 0.39775
| 1292 | 0.94084 | 0.23351 | -0.063357 | -0.12736 | -0.80176 | 0.31029 | 0.34129 | -0.264 | -0.47741 | 0.30107
| 1293 | -0.51699 | 0.72125 | -0.11507 | 0.95204 | -0.0047613 | -0.06678 | 0.12805 | -0.45475 | 0.073447 | -0.48435
| 1294 | 0.046323 | -0.41716 | 0.031651 | 0.25174 | -0.41819 | -0.049684 | -0.10473 | -0.37927 | -0.15141 | 0.38706
| 1295 | -0.57491 | -0.83417 | 0.42459 | -0.031857 | 0.45475 | 0.45237 | 0.53881 | -0.077774 | 0.10888 | 0.23456
| 1296 | 0.53816 | 0.59714 | -0.10764 | 0.78436 | -0.017707 | -0.35914 | -0.1758 | 0.06016 | 0.38918 | -0.1229
| 1297 | -0.068711 | 0.034547 | 0.47341 | -0.36008 | 0.068925 | -0.20709 | 0.064532 | 0.52157 | 0.010202 | 0.020153
| 1298 | 0.019133 | 0.27785 | 0.01344 | 0.081904 | 0.35743 | 0.10854 | 0.23495 | 0.41442 | -0.18373 | 0.28188
| 1299 | 0.1091 | -0.19744 | -0.35463 | 0.19111 | 0.62597 | -0.38559 | -0.46046 | -0.18901 | 0.083758 | -0.44818
| 1300 | -0.20307 | 0.47684 | -0.13357 | 0.087038 | -0.020153 | -0.10742 | 0.05899 | -0.074095 | 0.31714 | -0.49394
| 1301 | 0.49039 | 0.20634 | -0.067637 | 0.24522 | -0.69032 | -0.70521 | 0.02097 | 0.62865 | 0.66578 | 0.57515
| 1302 | 0.32228 | -0.29936 | -0.16292 | 0.041825 | -0.0019519 | 0.49059 | 0.60643 | -0.016283 | 0.039948 | -0.031754
| 1303 | -0.80687 | -0.033925 | 0.13913 | 0.73335 | 0.11473 | -0.72926 | -0.065709 | -0.013136 | -0.93292 | -0.30079
| 1304 | 0.3363 | 0.18446 | -0.31334 | -0.1338 | -0.37127 | 0.52682 | 0.16543 | -0.19012 | 0.16256 | -0.68775
| 1305 | -0.10373 | 0.085724 | 0.1204 | 0.031238 | -0.40713 | -0.7496 | -0.25414 | 0.40746 | -0.52682 | 0.22534
| 1306 | 0.074851 | 0.152 | -0.34433 | -0.78344 | -0.18055 | -0.3303 | -0.029176 | -0.50675 | 0.092751 | -0.11631
| 1307 | 0.00025003 | 0.45658 | -0.61103 | -0.37702 | 0.09695 | -0.17568 | 0.080272 | 0.79579 | -0.066458 | -0.23364
| 1308 | -0.10195 | -0.054431 | 0.61361 | 0.20332 | -0.37207 | -0.78669 | 0.4293 | 0.12713 | 0.32583 | 0.1245
| 1309 | 0.22456 | -0.19632 | -0.24204 | 0.23757 | -0.20319 | 0.39842 | 0.13913 | 0.51927 | -0.27247 | 0.83721
| 1310 | -0.046218 | 0.022708 | -0.58251 | 0.030103 | -0.50311 | 0.59863 | -0.35541 | -0.38445 | -0.13438 | -0.15047
| 1311 | -0.51451 | -0.1308 | 0.29822 | 0.08649 | -0.03714 | -0.20975 | -0.36589 | 0.42181 | 0.3245 | 0.02609
| 1312 | 0.068067 | 0.67488 | 0.42268 | 0.64659 | 0.12416 | 0.14076 | 0.24482 | -0.15047 | -0.065602 | -0.33796
| 1313 | -0.016791 | -0.28257 | -0.14484 | -0.15828 | 0.40814 | 0.72054 | 0.10966 | 0.42511 | 0.61387 | 0.75896
| 1314 | -0.18741 | 0.066565 | 0.20395 | -0.40192 | 0.28076 | -0.14554 | 0.4989 | -0.055807 | 0.0079819 | -0.31029
| 1315 | 0.63163 | 0.08989 | 0.27412 | -0.41922 | 0.12874 | -0.21076 | 0.3038 | -0.53492 | 0.41854 | -0.074527
| 1316 | -0.50756 | 0.55537 | -0.58323 | 0.11892 | 0.42895 | -0.066458 | -0.39296 | 0.21866 | -0.26986 | 0.021481
| 1317 | 0.40949 | 0.53556 | 0.47665 | 0.43973 | -0.40343 | -0.43938 | -0.54845 | -0.47971 | 0.51969 | 0.5866
| 1318 | 0.0088895 | 0.029588 | 0.065923 | 0.072584 | -0.23169 | -0.59294 | -0.64153 | -0.39908 | 0.065602 | 0.65431
| 1319 | -0.17169 | -0.58083 | -0.05 | 0.021787 | 0.10563 | 0.032167 | -0.11451 | -0.67061 | 0.7508 | 0.60592
| 1320 | 0.28775 | -0.0004501 | -0.40713 | 0.4564 | 0.57562 | 0.56745 | -0.41255 | 0.14624 | -0.11293 | 0.32376
| 1321 | -0.53235 | 0.24112 | 0.17386 | -0.61934 | 0.17702 | 0.11801 | -0.33015 | 0.40192 | 0.1533 | -0.88126
| 1322 | -0.39527 | -0.33314 | 0.25697 | -0.23626 | -0.38315 | -0.61464 | -0.072584 | -0.41391 | -0.2744 | -0.18667
| 1323 | -0.19682 | -0.10742 | 0.17556 | -0.7245 | -0.3804 | -0.39246 | -0.25858 | -0.43617 | -0.082994 | 0.051791
| 1324 | -0.34083 | -0.8467 | -0.079402 | 0.37302 | 0.11146 | 0.78905 | -0.34418 | 0.080272 | -0.49216 | -0.45787
| 1325 | -0.19495 | -0.20672 | -0.15531 | -0.39428 | -0.025577 | -0.38137 | 0.58854 | 0.29212 | 0.43423 | 0.37799
| 1326 | -0.48357 | 0.11643 | 0.68936 | -0.38478 | 0.01791 | -0.25737 | 0.25629 | 0.05984 | -0.002453 | 0.82766
| 1327 | -0.83477 | -0.39049 | 0.4999 | 0.55424 | -0.13346 | -0.060372 | -0.057503 | 0.14239 | 0.39659 | -0.65345
| 1328 | -0.36321 | -0.71242 | 0.11034 | -0.1269 | -0.21866 | 0.072584 | 0.32925 | 0.20874 | -0.28313 | 0.22857
| 1329 | -0.67121 | 0.20899 | -0.71592 | 0.45972 | -0.44206 | -0.44385 | 0.32732 | -0.23104 | -0.16066 | 0.75322
| 1330 | -0.46269 | -0.078425 | -0.14134 | -0.63435 | 0.87793 | 0.51513 | 0.26822 | -0.29339 | -0.15744 | 0.43955
| 1331 | -0.65985 | 0.33509 | -0.3369 | 0.37831 | -0.040782 | -0.09066 | -0.54448 | 0.26481 | 0.37847 | -0.36826
| 1332 | 0.11079 | -0.12176 | -0.81752 | 0.56285 | -0.29836 | -0.46925 | -0.48299 | -0.29651 | -0.025474 | 0.37366
| 1333 | 0.82028 | 0.85752 | -0.09154 | -0.74251 | -0.7245 | -0.56861 | -0.54033 | 0.10507 | -0.21521 | 0.22019
| 1334 | -0.14636 | 0.09 | 0.019235 | -0.26563 | -0.37622 | 0.63931 | 0.28789 | 0.036102 | 0.3306 | 0.3961
| 1335 | -0.0088895 | 0.029485 | 0.39659 | -0.11326 | -0.5003 | 0.10966 | 0.32554 | -0.86472 | 0.0093941 | -0.87958
| 1336 | 0.5458 | 0.264 | -0.70453 | 0.059628 | 0.047057 | -0.25067 | 0.31626 | 0.32273 | -0.47703 | -0.41306
| 1337 | -0.47303 | 0.069463 | 0.39709 | 0.29169 | -0.5013 | -0.012225 | -0.38024 | -0.5806 | -0.34114 | -0.76272
| 1338 | 0.048843 | 0.48532 | -0.030206 | 0.8937 | 0.35945 | -0.43105 | 0.41408 | -0.050842 | -0.28035 | -0.21904
| 1339 | 0.35062 | -0.7735 | 0.42303 | -0.18741 | 0.73637 | 0.51184 | 0.1308 | -0.6755 | 0.24469 | 0.50351
| 1340 | 0.34296 | 0.17896 | -0.19074 | -0.24323 | 0.71417 | -0.41768 | -0.86546 | -0.67121 | -0.59441 | -0.55223
| 1341 | 0.80635 | -0.35603 | 0.10888 | 0.71312 | -0.14064 | 0.30021 | 0.016588 | -0.21051 | 0.67152 | -0.59343
| 1342 | -0.26986 | 0.4979 | 0.26549 | -0.098169 | -0.54624 | -0.073231 | 0.14929 | 0.050948 | 0.4801 | 0.45146
| 1343 | -0.0048618 | -0.87631 | 0.52366 | -0.36353 | 0.070538 | -0.33645 | -0.13808 | 0.30841 | -0.30495 | 0.61542
| 1344 | -0.069248 | -0.32896 | 0.040365 | -0.49059 | 0.73827 | -0.55469 | -0.1466 | 0.21215 | -0.21292 | -0.071938
| 1345 | 0.34479 | 0.061224 | -0.069355 | 0.21279 | -0.56057 | -0.068067 | 0.36683 | 0.67304 | 0.12989 | -0.027015
| 1346 | 0.40008 | 0.27965 | -0.47914 | 0.73942 | -0.51595 | -0.09187 | 0.021992 | -0.33735 | 0.048212 | -0.4683
| 1347 | -0.14344 | 0.16221 | 0.25347 | 0.067101 | -0.25818 | -0.28188 | -0.5098 | -0.009899 | -0.096507 | 0.54911
| 1348 | 0.21292 | -0.65373 | -0.069785 | 0.39 | -0.62198 | -0.29424 | 0.38984 | 0.97764 | -0.10798 | 0.23901
| 1349 | 0.21738 | -0.029382 | -0.14239 | -0.75241 | -0.46176 | 0.088682 | -0.47113 | -0.19458 | -0.078751 | 0.09176
| 1350 | 0.5201 | 0.22624 | -0.35262 | 0.14706 | 0.12747 | 0.39395 | -0.53729 | 0.46456 | -0.12131 | -0.21432
| 1351 | -0.87631 | 0.62119 | 0.21776 | 0.31 | 0.62066 | -0.0094951 | 0.032788 | -0.70828 | 0.23469 | -0.19495
| 1352 | -0.0054649 | 0.012934 | -0.32273 | -0.67674 | 0.040782 | -0.25912 | -0.22199 | 0.27165 | 0.57656 | 0.22909
| 1353 | 0.13299 | -0.52157 | -0.0092932 | 0.13936 | 0.40713 | -0.074959 | -0.46812 | -0.21177 | 0.11067 | -0.095732
| 1354 | -0.10933 | 0.4286 | -0.31714 | 0.88042 | -0.61154 | -0.20495 | -0.013339 | -0.27041 | -0.75282 | 0.33269
| 1355 | -0.39477 | 0.17217 | 0.33299 | -0.43088 | 0.34479 | -0.15224 | 0.15024 | 0.71347 | 0.33494 | -0.06678
| 1356 | -0.47779 | 0.57303 | 0.5007 | -0.76957 | -0.13681 | 0.055384 | -0.34831 | -0.0044599 | -0.75731 | 0.62919
| 1357 | 0.34831 | -0.45806 | 0.39263 | 0.21572 | -0.02322 | -0.136 | -0.71 | 0.17241 | 0.14111 | 0.72486
| 1358 | 0.16232 | -0.17193 | -0.050105 | -0.20609 | 0.17121 | 0.69652 | 0.37494 | 0.15804 | -0.34388 | -0.1082
| 1359 | 0.51061 | -0.29523 | 0.41648 | 0.11722 | -0.81318 | -0.11349 | -0.32687 | 0.32658 | 0.88731 | -0.83845
| 1360 | -0.74722 | -0.8821 | -0.13023 | 0.19136 | 0.50654 | -0.28579 | -0.35355 | -0.12816 | -0.022606 | -0.31538
| 1361 | 0.42615 | -0.76612 | 0.6852 | -0.20106 | -0.40797 | 0.011314 | -0.52894 | -0.25294 | -0.077774 | -0.19595
| 1362 | 0.1814 | 0.86399 | 0.0922 | -0.61309 | 0.42459 | 0.11372 | -0.23495 | -0.1153 | -0.1005 | -0.31919
| 1363 | 0.26577 | 0.62517 | -0.79776 | 0.10373 | -0.23104 | -0.058246 | -0.29665 | 0.29836 | 0.29608 | -0.026193
| 1364 | -0.099278 | 0.47436 | 0.011314 | -0.34159 | 0.2516 | -0.21279 | 0.19694 | 0.26509 | 0.29523 | -0.44782
| 1365 | -0.09022 | 0.03 | 0.052213 | -0.06261 | -0.28049 | 0.23065 | -0.026296 | -0.23521 | -0.52324 | 0.10239
| 1366 | -0.46121 | 0.49039 | 0.04517 | -0.4426 | 0.20445 | 0.071291 | -0.025885 | -0.19111 | 0.77707 | 0.15994
| 1367 | 0.18778 | 0.31597 | 0.15555 | -0.78622 | 0.15911 | -0.5959 | -0.24297 | 0.48435 | -0.36778 | -0.13161
| 1368 | -0.0058672 | 0.046742 | 0.27426 | 0.51513 | 0.75855 | 0.62171 | -0.22482 | 0.2744 | 0.37318 | -0.26468
| 1369 | 0.75444 | -0.10876 | 0.30509 | -0.50654 | 0.070323 | 0.15024 | -0.67829 | -0.52136 | 0.60113 | 0.054643
| 1370 | 0.52767 | 0.13449 | 0.81752 | -0.10039 | -0.36008 | -0.0075787 | -0.32391 | 0.4408 | 0.21814 | 0.5768
| 1371 | -0.036724 | -0.22948 | -0.64125 | 0.087147 | -0.72705 | 0.31728 | 0.25899 | 0.04381 | 0.060798 | 0.26795
| 1372 | -0.44728 | -0.6319 | 0.55022 | 0.014252 | 0.52682 | -0.019541 | 0.16952 | 0.39842 | -0.23104 | -0.65927
| 1373 | 0.22469 | 0.43123 | 0.37718 | 0.37895 | -0.39461 | 0.21917 | 0.28579 | 0.36589 | 0.66281 | -0.37767
| 1374 | -0.43777 | -0.31422 | -0.74329 | -0.47265 | 0.3743 | -0.035479 | -0.26264 | 0.54054 | -0.45 | -0.056125
| 1375 | -0.21139 | -0.30079 | -0.16388 | -0.15721 | 0.72341 | -0.054537 | 0.50959 | -0.31189 | 0.61438 | 0.019133
| 1376 | 0.49493 | 0.65518 | 0.26074 | 0.23143 | 0.44638 | -0.059521 | -0.048948 | 0.48125 | -0.25912 | 0.69652
| 1377 | 0.026809 | -0.24204 | -0.28537 | 0.6703 | -0.29708 | -0.21317 | 0.32155 | -0.33075 | 0.4408 | 0.42737
| 1378 | 0.46139 | 0.18741 | -0.097614 | -0.028249 | -0.50939 | -0.0064709 | 0.42216 | -0.1237 | -0.058459 | -0.26658
| 1379 | -0.21343 | 0.3306 | 0.30538 | -0.55469 | 0.31232 | -0.10955 | 0.17933 | 0.35216 | 0.11654 | 0.021992
| 1380 | -0.5735 | -0.58491 | 0.0088895 | -0.20874 | 0.53513 | -0.86621 | 0.054431 | 0.31203 | 0.27 | -0.66103
| 1381 | -0.39 | 0.034858 | -0.50959 | -0.15638 | 0.028146 | -0.55 | -0.74682 | 0.0052639 | -0.46306 | 0.47094
| 1382 | 0.46774 | 0.73904 | -0.17036 | 0.34205 | 0.48318 | -0.52073 | 0.37895 | -0.4989 | -0.19881 | -0.62198
| 1383 | 0.4426 | -0.68204 | -0.73448 | -0.097393 | 0.12943 | 0.30841 | -0.0067729 | 0.16185 | 0.19384 | 0.26713
| 1384 | -0.25912 | -0.32361 | 0.21661 | 0.22728 | -0.49532 | 0.043287 | 0.6995 | -0.51307 | -0.93443 | -0.89
| 1385 | -0.26932 | -0.18815 | -0.032271 | 0.049684 | -0.096617 | 0.15389 | 0.57047 | -0.098945 | 0.66162 | -0.3551
| 1386 | 0.072153 | -0.64801 | 0.18153 | 0.59664 | -0.82365 | -0.048633 | 0.65693 | 0.76399 | -0.64518 | -0.11733
| 1387 | 0.12347 | -0.23901 | 0.1597 | 0.41785 | -0.40527 | -0.51865 | -0.10306 | -0.4776 | -0.20697 | -0.33811
| 1388 | 0.38624 | 0.52957 | 0.044961 | 0.32037 | -0.055595 | 0.53924 | 0.25697 | -0.43123 | 0.054537 | -0.26973
| 1389 | 0.41716 | -0.18741 | -0.23691 | 0.0017515 | -0.73149 | 0.36841 | 0.30942 | 0.22456 | -0.12954 | -0.070215
| 1390 | 0.31218 | -0.12028 | -0.48493 | -0.51886 | -0.36023 | -0.40611 | 0.35665 | -0.10161 | -0.23534 | -0.15828
| 1391 | 0.11711 | -0.30222 | -0.21025 | -0.26264 | -0.70897 | -0.28481 | 0.53235 | 0.0021523 | -0.47779 | 0.1308
| 1392 | -0.64125 | 0.64097 | 0.16795 | 0.41255 | -0.47322 | 0.031444 | 0.15875 | -0.23954 | -0.2313 | -0.46981
| 1393 | -0.04026 | 0.39213 | -0.0076795 | 0.26509 | 0.47265 | -0.40645 | -0.089451 | 0.30093 | 0.21139 | -0.58878
| 1394 | 0.61961 | -0.77395 | -0.071076 | -0.11564 | -0.05549 | 0.022196 | 0.21393 | 0.49137 | 0.7816 | -0.11496
| 1395 | 0.23299 | -0.16795 | 0.0063703 | -0.67213 | -0.89 | -0.59171 | 0.018012 | 0.16615 | -0.13369 | -0.68647
| 1396 | -0.32361 | 0.082231 | 0.14367 | 0.68871 | 0.30308 | 0.63903 | -0.41051 | -0.51927 | -0.11881 | -0.13727
| 1397 | 0.27357 | -0.058353 | 0.71277 | 0.31334 | -0.38673 | -0.16197 | -0.23915 | -0.45109 | 0.17483 | -0.10362
| 1398 | -0.066994 | 0.11881 | -0.16137 | 0.33314 | -0.20044 | 0.14355 | 0.44385 | 0.035168 | 0.56239 | -0.67274
| 1399 | 0.12541 | 0.23404 | -0.025782 | 0.94255 | 0.81426 | -0.36826 | 0.42633 | -0.010303 | -0.20924 | -0.035687
| 1400 | 0.41289 | -0.15816 | 0.37 | 0.048422 | -0.077883 | 0.038595 | -0.49532 | 0.50392 | -0.8937 | -0.11665
| 1401 | 0.094848 | 0.048527 | 0.52492 | -0.71982 | -0.38348 | 0.0063703 | 0.69455 | 0.048527 | 0.18226 | 0.56216
| 1402 | 0.11665 | 0.21165 | -0.59738 | 0.3727 | 0.46009 | -0.048738 | -0.29226 | -0.1389 | -0.44728 | 0.31261
| 1403 | -0.5011 | -0.33494 | -0.018012 | -0.59938 | 0.047897 | 0.14041 | -0.54142 | 0.76063 | -0.78905 | -0.30884
| 1404 | -0.60744 | -0.40662 | -0.10496 | 0.36133 | 0.25602 | -0.10832 | 0.27151 | -0.18581 | -0.39345 | 0.08136
| 1405 | -0.53449 | 0.34433 | 0.79776 | 0.13577 | -0.42095 | -0.39809 | -0.38315 | -0.17568 | 0.2492 | 0.084959
| 1406 | -0.15271 | 0.03579 | 0.50796 | 0.29679 | -0.35031 | 0.042033 | -0.53128 | 0.30942 | 0.32037 | 0.39494
| 1407 | 0.28341 | -0.51369 | 0.41596 | 0.33992 | 0.27564 | 0.083867 | -0.24336 | 0.36384 | 0.18214 | 0.42043
| 1408 | 0.06325 | -0.30581 | -0.28118 | 0.48629 | -0.32051 | -0.40561 | 0.046847 | 0.62677 | -0.58515 | -0.7735
| 1409 | -0.081142 | 0.066351 | -0.26481 | -0.34464 | 0.76104 | -0.046847 | -0.035272 | 0.25428 | -0.0040582 | -0.096728
| 1410 | -0.54756 | 0.40142 | 0.40292 | -0.96683 | 0.047477 | 0.33359 | -0.20006 | -0.2476 | -0.39875 | 0.3422
| 1411 | -0.58539 | 0.067316 | -0.34877 | 0.3245 | -0.18544 | 0.13983 | 0.62092 | 0.47493 | 0.09518 | -0.83118
| 1412 | -0.98268 | 0.31363 | 0.69065 | 0.23652 | -0.10574 | 0.50412 | -0.12519 | -0.16006 | -0.23299 | -0.14192
| 1413 | -0.052952 | -0.044856 | -0.24033 | -0.80843 | 0.26686 | 0.64715 | -0.040677 | 0.33811 | 0.048002 | -0.12051
| 1414 | -0.13716 | 0.50351 | 0.38234 | 0.29523 | -0.40192 | 0.26536 | 0.042764 | 0.28859 | 0.010303 | 0.84605
| 1415 | -0.11462 | -0.52282 | 0.77707 | -0.075284 | -0.3116 | -0.32287 | 0.26373 | 0.9089 | -0.075392 | -0.02609
| 1416 | 0.34754 | 0.38024 | -0.73261 | -0.71663 | -0.014759 | -0.66429 | -0.84736 | -0.54404 | 5.0001e-05 | -0.18177
| 1417 | -0.33179 | -0.19025 | -0.21101 | 0.063144 | -0.79776 | 0.4717 | 0.66221 | -0.21878 | 0.09839 | -0.15697
| 1418 | -0.58179 | -0.32494 | -0.26617 | -0.82651 | 0.071291 | -0.46643 | -0.21738 | -0.01182 | 0.26332 | -0.048738
| 1419 | 0.53107 | -0.12828 | 0.18569 | 0.39461 | -0.66519 | -0.68204 | 0.055595 | 0.22598 | 0.1957 | -0.078317
| 1420 | -0.15 | -0.013238 | -0.85752 | 0.13878 | 0.56194 | 0.10406 | 0.18214 | 0.28257 | 0.38624 | 0.5469
| 1421 | -0.17362 | -0.34403 | 0.1797 | 0.75403 | -0.38267 | 0.48843 | 0.17241 | 0.81053 | -0.047372 | 0.31904
| 1422 | 0.20798 | -0.10899 | 0.36557 | -0.49295 | -0.048527 | 0.41238 | 0.10017 | 0.22225 | 0.16496 | 0.51348
| 1423 | 0.18214 | -0.061118 | -0.024551 | -0.34114 | -0.24601 | 0.58395 | -0.4258 | -0.5143 | 0.14402 | 0.18988
| 1424 | 0.16292 | 0.21584 | 0.77572 | 0.41991 | 0.47588 | 0.11202 | 0.53751 | -0.53043 | 0.48029 | -0.2193
| 1425 | -0.88042 | -0.30495 | 0.8467 | 0.71035 | -0.53772 | -0.25321 | 0.62171 | -0.53299 | 0.29141 | 0.55694
| 1426 | -0.0728 | 0.24297 | 0.018114 | 0.2659 | -0.62224 | 0.38056 | -0.34342 | -0.17447 | 0.16388 | -0.10574
| 1427 | -0.043078 | -0.10955 | -0.79239 | -0.78905 | -0.18778 | -0.0781 | -0.72815 | 0.13658 | 0.42493 | 0.32051
| 1428 | 0.22818 | -0.055595 | -0.59122 | 0.68807 | 0.22456 | -0.79433 | -0.16531 | 0.51554 | -0.010303 | 0.32465
| 1429 | -0.46774 | -0.10809 | 0.33269 | -0.30509 | 0.42424 | -0.092421 | 0.43848 | 0.80328 | 0.93755 | 0.21827
| 1430 | -0.48029 | 0.87793 | -0.13924 | -0.17775 | 0.019847 | 0.073987 | 0.7015 | -0.59888 | 0.50695 | -0.7488
| 1431 | -0.32199 | 0.72197 | -0.2234 | 0.063784 | -0.29 | -0.50898 | -0.65576 | 0.3357 | -0.024551 | 0.28411
| 1432 | -0.52936 | -0.28299 | -0.43546 | -0.80635 | 0.53192 | 0.62251 | 0.6407 | 0.85 | 0.36762 | 0.73448
| 1433 | 0.27481 | -0.34555 | -0.3956 | 0.90253 | 0.11801 | -0.48357 | 0.29085 | 0.18055 | 0.47512 | -0.18104
| 1434 | -0.031341 | -0.53427 | -0.30351 | 0.35603 | 0.011213 | 0.65114 | 0.081577 | -0.17508 | 0.19495 | 0.72669
| 1435 | -0.044647 | -0.099389 | 0.66221 | 0.19025 | 0.33494 | -0.23783 | -0.69917 | 0.31378 | 0.24535 | -0.45677
| 1436 | 0.044228 | -0.1533 | -0.36636 | -0.076041 | 0.019031 | -0.50594 | -0.50776 | -0.42268 | -0.3629 | -0.50878
| 1437 | 0.13681 | -0.11518 | -0.1825 | -0.17423 | 0.10787 | 0.23652 | -0.073987 | -0.075608 | -0.19099 | -0.087147
| 1438 | 0.24363 | -0.1091 | -0.41854 | 0.30337 | -0.63244 | 0.055172 | 0.13936 | -0.50898 | -0.58443 | 0.41323
| 1439 | 0.21891 | 0.55492 | -0.13634 | 0.059202 | 0.3366 | -0.65029 | 0.81697 | -0.4542 | 0.6995 | 0.27938
| 1440 | -0.11045 | -0.073339 | -0.08967 | 0.83297 | -0.80379 | 0.15685 | 0.67643 | -0.24853 | -0.41802 | -0.35278
| 1441 | 0.03434 | -0.1338 | 0.18226 | 0.28327 | -0.064532 | 0.44692 | 0.69652 | 0.1825 | 0.096285 | -0.18361
| 1442 | -0.52198 | 0.65663 | -0.56308 | -0.12656 | 0.63599 | -0.11643 | 0.35992 | -0.22896 | -0.4828 | 0.44945
| 1443 | -0.1921 | 0.14134 | 0.54076 | -0.66608 | 0.29936 | -0.045065 | -0.50796 | 0.44855 | 0.079077 | -0.28972
| 1444 | 0.32007 | -0.025988 | 0.053797 | -0.36478 | 0.25254 | 0.13288 | 0.53427 | 0.41289 | 0.28551 | -0.16244
| 1445 | -0.58805 | -0.59664 | 0.13843 | -0.65057 | 0.79239 | -0.26808 | -0.30928 | 0.22019 | 0.00035006 | 0.31568
| 1446 | 0.5447 | 0.38787 | -0.13843 | 0.58419 | -0.30552 | -0.1603 | 0.10899 | 0.18361 | -0.0050628 | 0.35977
| 1447 | 0.47588 | 0.38657 | -0.20106 | 0.54229 | -0.76272 | -0.27509 | -0.72414 | -0.27896 | -0.39428 | -0.91225
| 1448 | 0.78858 | -0.5693 | 0.38657 | -0.81972 | -0.1533 | 0.25683 | 0.5728 | 0.36023 | -0.67182 | 0.69488
| 1449 | -0.14695 | -0.21317 | -0.52387 | -0.49078 | 0.087805 | -0.38251 | 0.68807 | 0.30567 | 0.65345 | 0.48863
| 1450 | -0.18153 | -0.37414 | -0.34571 | -0.4736 | 0.52809 | -0.49157 | 0.54098 | -0.39494 | 0.5866 | -0.71769
| 1451 | 0.6319 | 0.30986 | -0.5656 | 0.0044599 | 0.44421 | -0.15982 | -0.055595 | -0.28901 | 0.76399 | 0.51225
| 1452 | 0.083321 | -0.56377 | -0.34372 | -0.11304 | -0.14554 | -0.04381 | -0.364 | -0.38186 | 0.55379 | -0.80791
| 1453 | 0.31378 | -0.020766 | 0.43724 | -0.7816 | 0.50939 | 0.2496 | -0.41905 | 0.58951 | 0.2234 | -0.87
| 1454 | -0.63408 | 0.036413 | 0.16161 | -0.75282 | -0.65839 | -0.0012508 | -0.093744 | 0.16651 | -0.45935 | 0.0022525
| 1455 | 0.38722 | -0.32643 | -0.041199 | -0.073879 | 0.65927 | -0.046638 | 0.030309 | -0.28635 | 0.36589 | -0.1803
| 1456 | 0.20874 | 0.55111 | -0.22676 | 0.025167 | -0.12256 | 0.22431 | 0.62784 | -0.16759 | 0.73866 | 0.0015512
| 1457 | 0.27123 | -0.64631 | -0.56171 | 0.10541 | -0.58395 | 0.27453 | 0.36747 | 0.0047613 | 0.24402 | -0.43405
| 1458 | 0.29085 | 0.41596 | -0.0075787 | 0.028146 | 0.35541 | 0.68711 | -0.022299 | -0.75648 | 0.30495 | 0.31787
| 1459 | 0.28944 | 0.46887 | 0.26061 | 0.046638 | 0.25845 | -0.88042 | 0.15012 | -0.48454 | 0.57633 | 0.70623
| 1460 | -0.080816 | -0.17121 | -0.1375 | 0.79 | -0.46737 | 0.13023 | 0.085615 | -0.41785 | 0.012427 | -0.25361
| 1461 | -0.13658 | -0.054114 | -0.38804 | 0.19582 | -0.32658 | -0.46512 | -0.41494 | 0.1127 | 0.16304 | 0.26658
| 1462 | 0.30466 | -0.47094 | -0.20069 | -0.32851 | -0.10328 | 0.70725 | -0.47132 | 0.47417 | 0.13173 | -0.47607
| 1463 | -0.15851 | -0.76827 | 0.47722 | -0.22987 | -0.31087 | -0.6257 | 0.7492 | -0.18006 | 0.55223 | -0.44331
| 1464 | 0.70453 | -0.23508 | -0.19062 | 0.56583 | 0.41153 | 0.13866 | -0.66668 | 0.25187 | 0.79239 | 0.39082
| 1465 | 0.057928 | 0.17677 | 0.10317 | -0.10832 | 0.78251 | 0.44385 | -0.17836 | -0.44728 | -0.14918 | 0.20294
| 1466 | -0.30322 | -0.017809 | 0.3294 | -0.8995 | 0.12085 | 0.35572 | -0.5656 | -0.44439 | -0.46065 | 0.10184
| 1467 | -0.23195 | -0.010303 | -0.71698 | 0.54867 | 0.024039 | -0.63435 | 0.059202 | -0.12793 | 0.19831 | 0.19235
| 1468 | -0.35821 | 0.040156 | 0.048738 | -0.1245 | 0.076799 | -0.152 | -0.17665 | -0.1752 | 0.48512 | 0.35758
| 1469 | 0.34053 | 0.27591 | 0.3015 | 0.16448 | 0.57941 | -0.20836 | 0.39477 | 0.36541 | -0.43884 | 0.63517
| 1470 | 0.54054 | 0.12347 | -0.1439 | -0.14859 | -0.37191 | -0.30122 | 0.0081835 | -0.018827 | 0.12587 | -0.73223
| 1471 | 0.052846 | -0.49612 | 0.20962 | -0.069785 | -0.038387 | 0.16699 | 0.64518 | -0.41051 | 0.074203 | 0.27771
| 1472 | 0.19161 | -0.16496 | 0.65 | 0.10094 | -0.49098 | -0.087038 | 0.37286 | -0.55649 | 0.93 | -0.64209
| 1473 | 0.15 | -0.27647 | 0.41888 | -0.60567 | 0.33585 | 0.9219 | -0.4859 | 0.15425 | 0.69227 | -0.23665
| 1474 | -0.14871 | 0.2488 | 0.76399 | 0.33299 | 0.5001 | 0.42268 | 0.51637 | -0.46381 | 0.10362 | -0.28733
| 1475 | -0.16173 | 0.31714 | 0.22702 | -0.45787 | 0.64971 | -0.1769 | -0.85201 | 0.2995 | 0.7042 | 0.099389
| 1476 | -0.3363 | 0.20194 | 0.21381 | -0.44295 | -0.48941 | -0.58587 | -0.24059 | -0.002453 | -0.074095 | 0.61257
| 1477 | 0.58903 | 0.01182 | -0.54978 | -0.72089 | -0.022708 | -0.28593 | -0.52303 | -0.27647 | -0.0088895 | 0.16519
| 1478 | -0.13484 | 0.41888 | -0.099944 | -0.56676 | -0.010404 | -0.14847 | -0.042973 | 0.9245 | -0.3759 | -0.61412
| 1479 | -0.3074 | 0.27924 | -0.3727 | -0.17884 | -0.057079 | -0.065281 | -0.048527 | -0.26904 | 0.37207 | -0.49236
| 1480 | -0.22006 | -0.77932 | -0.049369 | -0.012832 | 0.10039 | 0.4041 | -0.21699 | 0.09198 | 0.73789 | 0.56884
| 1481 | -0.55492 | 0.12725 | -0.4987 | 0.20432 | -0.0071757 | 0.55223 | 0.023527 | -0.0025533 | -0.11372 | 0.67091
| 1482 | -0.45917 | 0.16555 | -0.51492 | 0.27868 | 0.30595 | 0.12816 | 0.20962 | -0.24455 | 0.11598 | 0.68204
| 1483 | -0.11034 | 0.0004501 | 0.098834 | -0.09077 | 0.59689 | 0.45917 | -0.24283 | 0.27674 | -0.35992 | -0.60491
| 1484 | 0.22328 | 0.11564 | 0.19408 | -0.3425 | -0.32125 | -0.29028 | 0.39213 | 0.63435 | -0.77439 | -0.025372
| 1485 | 0.37254 | 0.86325 | 0.96127 | -0.28369 | -0.45585 | 0.29993 | -0.66074 | -0.21317 | -0.36683 | 0.0911
| 1486 | -0.45843 | 0.097171 | -0.07183 | -0.066458 | 0.71698 | 0.45751 | -0.29765 | -0.079294 | 0.28509 | -0.027323
| 1487 | 0.77306 | -0.34144 | -0.32494 | 0.060053 | 0.88554 | 0.36968 | -0.31597 | -0.18569 | 0.4826 | 0.058671
| 1488 | 0.013846 | -0.79 | -0.20596 | 0.64886 | -0.031548 | 0.08136 | -0.57538 | -0.33645 | -0.34464 | -0.60795
| 1489 | -0.075392 | -0.35247 | 0.21559 | 0.45769 | 0.77 | 0.046008 | -0.44891 | 0.37398 | -0.11677 | -0.39842
| 1490 | 0.14554 | 0.23941 | -0.37 | 0.548 | -0.42842 | -0.46774 | 0.41613 | 0.37414 | 0.24138 | -0.15212
| 1491 | 0.061864 | -0.4999 | -0.53299 | 0.19533 | -0.051686 | 0.080272 | 0.27522 | 0.49572 | 0.54514 | 0.76399
| 1492 | 0.009798 | -0.59988 | 0.2496 | -0.029897 | 0.67798 | 0.3759 | -0.16161 | -0.22469 | 0.035687 | 0.0059678
| 1493 | 0.42043 | -0.20357 | 0.9272 | -0.22238 | 0.012022 | 0.19719 | 0.5806 | -0.18153 | 0.70017 | 0.22263
| 1494 | 0.28901 | -0.19284 | -0.070323 | 0.15071 | 0.11034 | 0.42337 | 0.025372 | -0.49118 | -0.86325 | 0.15012
| 1495 | 0.10921 | 0.66519 | 0.35293 | -0.13832 | 0.264 | 0.79 | 0.11236 | -0.14472 | -0.065495 | -0.37446
| 1496 | -0.24641 | 0.42199 | 0.7569 | 0.37702 | -0.24151 | 0.089121 | 0.39411 | 0.79531 | 0.0040582 | -0.48067
| 1497 | -0.10518 | -0.5264 | -0.11 | 0.069677 | 0.72815 | -0.55898 | 0.12347 | 0.4046 | 0.18471 | 0.54845
| 1498 | -0.20445 | -0.68743 | 0.093523 | 0.17133 | -0.16819 | 0.087147 | 0.2484 | -0.30136 | 0.36102 | -0.19346
| 1499 | -0.2427 | -0.48299 | -0.62013 | 0.31787 | 0.089561 | -0.0011507 | 0.24086 | -0.26658 | -0.19124 | 0.79628
| 1500 | -0.11 | 0.12599 | 0.13265 | -0.41528 | 0.39908 | -0.46288 | -0.13426 | -0.10731 | -0.264 | -0.49078
| 1501 | 0.47856 | 0.37751 | -0.072692 | 0.44782 | -0.38234 | -0.015673 | -0.73335 | -0.16352 | 0.046428 | 0.16639
| 1502 | 0.32955 | 0.21495 | -0.012326 | -0.71487 | -0.52619 | -0.24747 | 0.057609 | 0.35649 | -0.048633 | 0.05253
| 1503 | -0.1127 | -0.016283 | 0.18852 | -0.32672 | 0.11541 | 0.26645 | -0.28313 | -0.16125 | 0.55312 | 0.052002
| 1504 | 0.27247 | 0.46568 | 0.27467 | 0.050948 | 0.07043 | -0.20558 | 0.2958 | 0.73298 | -0.22521 | 0.11892
| 1505 | 0.47875 | -0.44855 | -0.22353 | -0.63737 | 0.27412 | 0.78669 | 0.23915 | -0.1694 | 0.061331 | 0.62946
| 1506 | -0.61026 | -0.079837 | -0.77439 | 0.22302 | 0.014759 | 0.044123 | 0.27688 | -0.29807 | -0.19284 | 0.16868
| 1507 | -0.31407 | -0.22006 | -0.12885 | -0.13843 | 0.56722 | -0.38283 | -0.91938 | 0.13901 | 0.22534 | 0.19919
| 1508 | -0.32896 | 0.013947 | 0.031341 | -0.63654 | 0.98268 | -0.1044 | -0.19994 | 0.26658 | 0.1694 | -0.061331
| 1509 | 0.27827 | 0.37622 | -0.36164 | 0.20684 | 0.26386 | -0.041094 | 0.37911 | 0.45347 | 0.53881 | 0.25027
| 1510 | -0.15024 | 0.078859 | -0.21482 | -0.43955 | -0.35432 | -0.62758 | 0.41374 | 0.13069 | 0.1634 | -0.67766
| 1511 | -0.014454 | -0.36589 | 0.27385 | 0.25522 | -0.24482 | 0.017605 | -0.60516 | -0.12667 | -0.35386 | -0.62624
| 1512 | -0.22405 | -0.10978 | -0.16424 | -0.010404 | -0.27661 | 0.20232 | 0.9219 | -0.61283 | 0.048107 | -0.18951
| 1513 | -0.011112 | -0.039531 | 0.82593 | 0.033615 | 0.21546 | 0.69553 | -0.77528 | -0.15804 | 0.094738 | 0.27688
| 1514 | -0.046952 | -0.60113 | 0.015978 | 0.24601 | -0.12131 | -0.39792 | -0.16868 | -0.035998 | -0.045799 | -0.33419
| 1515 | -0.74096 | -0.68903 | 0.065174 | -0.50513 | 0.82422 | -0.27744 | 0.056231 | 0.27453 | -0.10429 | 0.22289
| 1516 | 0.043601 | 0.11281 | -0.57633 | -0.83357 | -0.09 | 0.45328 | -0.041199 | 0.019847 | -0.68647 | 0.08967
| 1517 | 0.45843 | -0.47038 | -0.10384 | 0.7512 | 0.82941 | -0.07183 | -0.18495 | -0.48106 | -0.3551 | 0.26034
| 1518 | -0.25133 | 0.035894 | -0.34144 | -0.65693 | 0.43671 | -0.31787 | -0.24469 | -0.45219 | 0.88554 | -0.43018
| 1519 | 0.19421 | 0.3048 | 0.47284 | -0.081795 | -0.096285 | 0.60795 | -0.23587 | -0.23338 | 0.34159 | 0.070753
| 1520 | -0.30164 | -0.49671 | 0.10854 | 0.6407 | 0.27813 | -0.75855 | 0.039531 | -0.074635 | 0.39875 | 0.12622
| 1521 | -0.73037 | 0.83357 | -0.017503 | 0.77175 | 0.05899 | 0.25187 | -0.21089 | -0.11824 | 0.3951 | 0.20344
| 1522 | -0.21063 | -0.081686 | -0.22689 | 0.59788 | -0.050526 | 0.51616 | -0.55156 | 0.50371 | 0.22844 | -0.019439
| 1523 | -0.43582 | -0.026912 | 0.3303 | 0.56422 | -0.027015 | 0.72269 | 0.90253 | 0.053163 | -0.12989 | -0.24165
| 1524 | -0.064746 | -0.21101 | -0.06229 | 0.68839 | 0.51969 | 0.0755 | 0.55492 | -0.26088 | 0.73942 | 0.58684
| 1525 | -0.14029 | 0.97354 | 0.34068 | 0.13392 | 0.28118 | 0.17921 | -0.14812 | -0.50918 | 0.56861 | 0.29268
| 1526 | 0.30222 | 0.22883 | -0.14859 | -0.20257 | 0.30653 | 0.028249 | 0.14484 | 0.36243 | -0.042973 | -0.20131
| 1527 | 0.07043 | 0.40797 | 0.4983 | 0.44764 | 0.46325 | -5.0001e-05 | 0.0035563 | -0.47779 | 0.28565 | -0.55537
| 1528 | -0.47208 | -0.13797 | -0.35805 | 0.80176 | 0.058459 | 0.95204 | 0.082013 | 0.11248 | -0.18483 | -0.5013
| 1529 | 0.25737 | 0.15354 | -0.31363 | 0.11983 | 0.2193 | 0.4987 | 0.69422 | 0.45732 | 0.4041 | -0.12108
| 1530 | -0.15578 | -0.14613 | -0.021787 | 0.91112 | -0.27716 | -0.084631 | 0.056761 | -0.13774 | -0.55649 | 0.73
| 1531 | -0.13507 | -0.77887 | 0.26413 | -0.44009 | -0.29551 | 0.047687 | 0.35108 | -0.57023 | -0.25576 | 0.25428
| 1532 | -0.49098 | -0.45677 | -0.28383 | -0.17459 | 0.27674 | 0.72414 | -0.33705 | -0.076258 | 0.29395 | -0.13716
| 1533 | 0.23849 | -0.12851 | -0.41 | -0.66489 | -0.25 | 0.045904 | -0.086162 | -0.063571 | 0.15828 | -0.28789
| 1534 | -0.039844 | -0.21559 | 0.4991 | -0.44493 | 0.51082 | -0.29622 | -0.24099 | -0.76063 | -0.41716 | 0.40611
| 1535 | -0.59788 | 0.42355 | -0.26156 | 0.4041 | -0.68775 | -0.18988 | -0.63903 | 0.019439 | -0.23849 | 0.71173
| 1536 | 0.38494 | 0.043705 | 0.19856 | -0.67953 | 0.5693 | 0.21254 | -0.60974 | 0.24654 | -0.2809 | 0.057503
| 1537 | 0.17957 | 0.44638 | 0.50878 | 0.26577 | 0.16868 | 0.010404 | -0.88467 | -0.35867 | -0.034547 | 0.26686
| 1538 | -0.036205 | 0.27633 | 0.33781 | -0.6811 | 0.26441 | -0.10317 | -0.1546 | 0.43053 | 0.53492 | 0.17386
| 1539 | 0.53235 | -0.29042 | -0.48551 | -0.21304 | -0.55134 | -0.62973 | 0.030619 | -0.44188 | 0.44134 | -0.011011
| 1540 | 0.14589 | -0.24138 | 0.48125 | 0.43211 | -0.13774 | 0.1513 | 0.31568 | -0.39395 | 0.048633 | 0.09099
| 1541 | 0.42233 | -0.57988 | -0.11541 | -0.14239 | -0.20546 | 0.035687 | -0.48746 | -0.57093 | -0.13716 | -0.04026
| 1542 | -0.36447 | 0.4542 | -0.46925 | -0.56377 | 0.050632 | 0.38951 | -0.47722 | -0.23639 | -0.75241 | 0.16615
| 1543 | 0.33284 | 0.025372 | 0.099833 | 0.19161 | 0.28467 | 0.16603 | -0.52492 | 0.15153 | -0.41905 | 0.30136
| 1544 | 0.14344 | -0.49394 | 0.11564 | 0.69 | 0.00015001 | -0.47474 | -0.24508 | -0.63271 | -0.69488 | -0.57327
| 1545 | 0.58878 | -0.0083852 | -0.33524 | -0.248 | -0.29523 | -0.86923 | 0.2076 | 0.55537 | -0.11462 | 0.21013
| 1546 | 0.1127 | 0.013035 | 0.09695 | -0.050737 | 0.020153 | 0.16436 | 0.046218 | -0.40042 | 0.65172 | -0.26699
| 1547 | 0.23312 | 0.015368 | -0.18975 | 0.077991 | 0.30783 | 0.18324 | 0.46849 | -0.73448 | 0.0081835 | 0.40242
| 1548 | 0.0038574 | 0.30797 | -0.67922 | 0.077774 | -0.029382 | 0.061011 | 0.33675 | -0.51699 | 0.57751 | -0.11767
| 1549 | 0.56308 | 0.95204 | -0.37239 | -0.043182 | -0.21635 | 0.74485 | 0.44619 | -0.056337 | -0.36055 | 0.063571
| 1550 | -0.89753 | -0.59738 | 0.89753 | -0.0037571 | -0.31073 | 0.0064709 | -0.0066723 | 0.18778 | 0.29708 | -0.37286
| 1551 | -0.51143 | -0.3132 | -0.50533 | -0.17921 | -0.85 | 0.12359 | -0.007478 | -0.061011 | 0.51123 | 0.71592
| 1552 | 0.45328 | -0.58251 | -0.65547 | -0.43938 | 0.11994 | 0.61725 | -0.47531 | 0.69129 | -0.28775 | 0.90356
| 1553 | 0.21215 | -0.59515 | 0.094185 | -0.24204 | -0.42947 | -0.084085 | 0.61412 | 0.71698 | -0.30797 | 0.09044
| 1554 | 0.20772 | -0.25549 | -0.83721 | -0.011516 | -0.073555 | -0.034236 | -0.18006 | -0.42181 | 0.62892 | -0.56422
| 1555 | 0.31073 | -0.5608 | 0.34342 | 0.32228 | -0.39825 | 0.34266 | 0.060585 | 0.37944 | -0.55022 | 0.9078
| 1556 | 0.16795 | -0.93443 | 0.5199 | -0.2256 | -0.72523 | 0.4999 | 0.30293 | 0.25858 | 0.63627 | -0.76146
| 1557 | -0.36008 | 0.26345 | -0.077124 | 0.2052 | -0.069892 | 0.58275 | -0.038179 | -0.18864 | 0.28523 | -0.14344
| 1558 | -0.070753 | -0.030309 | 0.32687 | -0.86108 | 0.33871 | -0.22573 | 0.06753 | 0.040052 | 0.34525 | 0.64377
| 1559 | 0.18128 | 0.38186 | 0.3312 | 0.31378 | -0.13104 | 0.52534 | 0.25522 | 0.4653 | -0.25334 | -0.36857
| 1560 | -0.29466 | 0.28327 | 0.16101 | 0.33479 | 0.43617 | 0.16771 | -0.20836 | 0.81917 | -0.017401 | 0.18557
| 1561 | 0.12862 | -0.61829 | 0.32007 | -0.045484 | -0.28691 | -0.017605 | -0.0026535 | -0.31714 | -0.53535 | -0.34892
| 1562 | -0.11281 | 0.042033 | -0.28901 | 0.41545 | 0.19694 | -0.38934 | 0.10273 | -0.24099 | 0.21457 | 0.34403
| 1563 | -0.87077 | 0.79975 | 0.236 | -0.12154 | -0.65868 | 0.3015 | 0.06603 | 0.23091 | 0.25428 | -0.37175
| 1564 | -0.16675 | 0.11349 | 0.21687 | 0.15342 | 0.53643 | 0.24734 | -0.23039 | 0.055807 | -0.25027 | -0.47113
| 1565 | -0.73 | -0.42546 | 0.77087 | 0.92859 | 0.53213 | 0.40192 | 0.25321 | 0.046533 | 0.045275 | -0.20798
| 1566 | 0.56445 | 0.41682 | 0.55898 | 0.55921 | -0.13808 | 0.062503 | 0.23182 | -0.87631 | -0.15 | -0.15177
| 1567 | -0.73561 | -0.67366 | 0.336 | 0.50251 | 0.1292 | -0.41 | 0.52387 | 0.76698 | -0.55604 | -0.1775
| 1568 | -0.35494 | 0.43529 | 0.24667 | 0.32007 | -0.37414 | 0.19869 | 0.64153 | 0.063464 | 0.016384 | 0.26863
| 1569 | -0.10017 | -0.087257 | 0.077774 | 0.080054 | -0.70386 | 0.26373 | -0.76569 | -0.12633 | 0.052635 | 0.49532
| 1570 | -0.088463 | 0.032788 | -0.65 | 0.27924 | 0.11779 | -0.74722 | 0.452 | 0.3551 | -0.036413 | 0.83118
| 1571 | 0.11293 | -0.28986 | 0.11146 | 0.26945 | -0.82422 | 0.36196 | -0.93292 | 0.24588 | 0.53556 | -0.10652
| 1572 | 0.26034 | -0.63299 | 0.077124 | -0.21533 | -0.45732 | -0.2504 | 0.094075 | 0.1852 | -0.6077 | 0.11801
| 1573 | -0.34296 | 0.18299 | -0.35 | 0.53363 | 0.02322 | -0.78763 | 0.71804 | -0.1375 | -0.24814 | 0.57023
| 1574 | 0.64971 | 0.44045 | -0.62811 | 0.18618 | -0.27274 | 0.7839 | 0.67674 | 0.93443 | -0.40628 | 0.44782
| 1575 | -0.074743 | -0.15756 | -0.26169 | -0.15982 | -0.40949 | 0.71769 | 0.23691 | 0.043496 | -0.00055015 | -0.16591
| 1576 | 0.038283 | -0.21687 | -0.31087 | 0.9272 | 0.34892 | -0.082885 | -0.5922 | -0.14777 | 0.077666 | -0.84284
| 1577 | 0.46925 | -0.20244 | -0.022196 | 0.24694 | -0.46887 | 0.082449 | 0.10541 | 0.31392 | -0.85474 | 0.18067
| 1578 | 0.0045604 | -0.013947 | 0.22238 | -0.12747 | -0.076149 | 0.53277 | -0.77662 | 0.22805 | 0.037036 | 0.15377
| 1579 | 0.14087 | -0.57751 | 0.12667 | -0.2621 | -0.85269 | 0.49078 | -0.37734 | -0.73524 | -0.053269 | -0.34342
| 1580 | 0.5436 | -0.57893 | -0.029485 | -0.79239 | 0.20094 | -0.8821 | 0.29183 | -0.14882 | -0.32184 | -0.13369
| 1581 | 0.12553 | 0.11926 | -0.081904 | 0.10128 | -0.020357 | -0.3061 | 0.49118 | -0.69983 | 0.48299 | -0.051897
| 1582 | -0.18557 | 0.65839 | -0.15507 | -0.072908 | 0.1034 | 0.070538 | 0.14683 | -0.51969 | -0.13057 | 0.24814
| 1583 | 0.022708 | 0.80025 | -0.5199 | 0.032167 | 0.20244 | -0.66939 | 0.39494 | 0.053691 | 0.29268 | -0.11575
| 1584 | 0.72523 | -0.76188 | -0.08649 | -0.32376 | -0.40025 | -0.40662 | 0.11462 | -0.098834 | 0.80843 | 0.26918
| 1585 | -0.58395 | 0.055066 | -0.69292 | -0.51164 | 0.24138 | 0.032891 | 0.70285 | 0.17982 | -0.4979 | -0.54978
| 1586 | 0.27069 | -0.034443 | 0.45347 | -0.23574 | -0.27495 | -0.60516 | -0.074851 | 0.29608 | -0.27813 | 0.37863
| 1587 | -0.56745 | 0.2076 | -0.60643 | -0.055913 | 0.40343 | -0.30222 | 0.36937 | -0.13461 | -0.057609 | -0.3005
| 1588 | -0.17544 | -0.72486 | 0.80739 | -0.22173 | -0.46981 | 0.47246 | 0.17653 | 0.14941 | -0.37686 | 0.90673
| 1589 | 0.67152 | 0.27854 | -0.35216 | 0.58927 | -0.48902 | -0.088353 | -0.89183 | -0.17133 | -0.36274 | -0.24402
| 1590 | 0.61206 | -0.27938 | -0.084959 | -0.34586 | 0.44565 | -0.16567 | -0.17592 | 0.14777 | -0.036932 | -0.6852
| 1591 | 0.31276 | 0.9078 | 0.42825 | -0.80791 | 0.4991 | -0.22392 | 0.69553 | -0.4041 | -0.034961 | 0.15496
| 1592 | 0.66789 | -0.27398 | 0.2047 | -0.066887 | -0.30107 | -0.072045 | 0.63875 | -0.6265 | -0.25414 | -0.075068
| 1593 | -0.65431 | -0.034236 | -0.011112 | 0.24508 | -0.33045 | 0.51844 | -0.90356 | 0.13276 | -0.75772 | 0.042869
| 1594 | -0.26074 | -0.2602 | 0.24787 | 0.16783 | 0.016079 | -0.14859 | 0.52851 | -0.24721 | -0.54382 | 0.54978
| 1595 | 0.10697 | 0.20106 | 0.76655 | 0.91815 | -0.28873 | -0.43831 | -0.34068 | 0.85964 | -0.028558 | 0.12382
| 1596 | -0.081686 | -0.57941 | -0.77044 | 0.28383 | 0.3245 | -0.4078 | 0.336 | 0.15318 | 0.77218 | 0.23156
| 1597 | 0.66819 | -0.28049 | -0.54536 | -0.58976 | -0.35139 | -0.54668 | -0.40326 | -0.4979 | -0.16209 | -0.55898
| 1598 | -0.66698 | -0.80635 | 0.51102 | 0.49295 | -0.0020521 | -0.23495 | -0.070753 | 0.10384 | 0.36243 | 0.095622
| 1599 | -0.035065 | 0.11915 | -0.47703 | -0.25414 | -0.079728 | -0.16591 | -0.0044599 | -0.66103 | -0.5001 | 0.25899
| 1600 | -0.38608 | 0.083539 | 0.35031 | -0.16161 | -0.093854 | -0.13948 | 0.018725 | -0.73486 | -0.21699 | -0.18803
| 1601 | -0.12656 | -0.016588 | 0.31305 | -0.51761 | 0.33374 | -0.32539 | 0.59738 | -0.5447 | 0.5447 | 0.21076
| 1602 | -0.36636 | 0.3681 | -0.91574 | -0.33962 | -0.14262 | 0.33224 | -0.029897 | -0.006169 | -0.033408 | 0.19645
| 1603 | -0.050211 | -0.014962 | -0.38186 | -0.17314 | 0.43546 | -0.10117 | -0.52915 | 0.64602 | 0.15507 | 0.13553
| 1604 | 0.42912 | 0.20962 | -0.24694 | 0.36747 | -0.19969 | 0.48648 | -0.35789 | -0.68647 | 0.25441 | -0.66638
| 1605 | -0.41699 | 0.69817 | -0.39792 | 0.095843 | -0.30667 | -0.63054 | 0.52745 | 0.87077 | 0.11045 | 0.29438
| 1606 | 0.69652 | -0.48941 | -0.26959 | -0.51 | 0.5245 | -0.38787 | 0.0088895 | -0.66399 | -0.48532 | -0.29495
| 1607 | -0.60923 | 0.27274 | 0.039115 | -0.45 | 0.40679 | -0.5721 | -0.40628 | -0.34068 | -0.5283 | -0.24535
| 1608 | 0.0004501 | 0.30509 | -0.031031 | 0.88126 | -0.17629 | -0.90461 | -0.46306 | -0.27192 | 0.39098 | 0.37414
| 1609 | 0.54668 | -0.0092932 | -0.42026 | 0.17775 | 0.57846 | 0.21891 | 0.086381 | -0.13046 | -0.013136 | 0.074743
| 1610 | -0.12359 | 0.024449 | 0.24575 | -0.62384 | 0.4408 | 0.17338 | -0.39 | -0.56308 | -0.14461 | 0.061224
| 1611 | -0.47057 | 0.14239 | -0.4293 | 0.17 | -0.21521 | 0.75403 | -0.21165 | -0.44927 | -0.64097 | -0.38348
| 1612 | -0.36826 | 0.041407 | 0.017605 | -0.6149 | 0.38234 | 0.40175 | 0.0012508 | -0.11994 | -0.16639 | 0.093744
| 1613 | -0.35727 | -0.059202 | 0.43053 | -0.46437 | -0.88554 | 0.75363 | 0.15899 | 0.43529 | 0.0911 | -0.33359
| 1614 | -0.33045 | -0.62277 | 0.52851 | -0.22586 | 0.42965 | -0.55089 | -0.78483 | 0.37526 | -0.099722 | -0.70862
| 1615 | -0.25307 | -0.76913 | 0.08136 | 0.40494 | -0.24561 | -0.016181 | 0.60617 | -0.48551 | 0.52619 | 0.89183
| 1616 | -0.14976 | 0.0911 | -0.55267 | -0.01 | -0.44493 | 0.41665 | 0.070968 | 0.39033 | -0.33871 | -0.33464
| 1617 | -0.57869 | -0.29537 | -0.070215 | -0.88554 | -0.6319 | 0.086928 | -0.018114 | -0.095843 | 0.057291 | -0.30007
| 1618 | 0.024756 | -0.39378 | -0.53686 | -0.48532 | 0.12028 | 0.60263 | 0.096175 | -0.097614 | -0.13265 | 0.23208
| 1619 | -0.049158 | -0.2398 | 0.072369 | -0.13577 | -0.16149 | 0.18655 | -0.19099 | -0.042973 | 0.53578 | -0.097393
| 1620 | 0.099167 | -0.13901 | -0.47818 | 0.64321 | -0.51513 | 0.053797 | 0.5608 | 0.4564 | 0.053903 | 0.34954
| 1621 | -0.48551 | 0.24575 | -0.23 | 0.24046 | 0.48183 | 0.32066 | -0.025167 | -0.050316 | -0.050105 | 0.39992
| 1622 | 0.32214 | 0.57 | -0.50251 | -0.48843 | 0.025577 | 0.37606 | -0.066673 | -0.14624 | 0.30351 | -0.2755
| 1623 | -0.067208 | -0.54207 | 0.59098 | 0.62463 | 0.43018 | 0.28607 | 0.57656 | 0.4286 | -0.4683 | 0.24046
| 1624 | 0.43955 | 0.18214 | 0.30495 | 0.70897 | 0.054008 | 0.036932 | 0.0995 | -0.06261 | 0.51699 | -0.74485
| 1625 | 0.1277 | -0.39312 | 0.30466 | 0.38902 | 0.33962 | -0.32509 | -0.64886 | -0.46981 | 0.51082 | 0.20069
| 1626 | -0.55469 | 0.36873 | 0.46624 | -0.064105 | -0.264 | -0.84157 | -0.28986 | 0.49731 | -0.24191 | 0.10753
| 1627 | -0.87155 | -0.15982 | -0.18766 | -0.031548 | -0.72926 | -0.38218 | 0.21687 | 0.55853 | -0.054855 | -0.47894
| 1628 | -0.30279 | -0.59639 | -0.84412 | -0.28425 | 0.30337 | 0.40292 | -0.089012 | -0.57656 | 0.44152 | 0.51699
| 1629 | 0.48299 | 0.15602 | -0.35603 | -0.22831 | -0.46793 | 0.33615 | -0.035583 | -0.69259 | -0.020357 | -0.070753
| 1630 | -0.63875 | -0.32881 | 0.066244 | 0.64943 | 0.4981 | -0.18324 | -0.20056 | -0.70657 | -0.34831 | 0.54448
| 1631 | 0.82308 | 0.10295 | 0.2948 | 0.5447 | 0.10261 | -0.48435 | 0.58323 | -0.30841 | -0.452 | 0.60038
| 1632 | -0.019541 | -0.11869 | -0.26727 | 0.030722 | 0.095732 | -0.8755 | 0.45109 | -0.32361 | 0.3593 | -0.80125
| 1633 | -0.75772 | 0.76698 | 0.021276 | -0.34754 | -0.35247 | 0.4078 | 0.30107 | -0.57257 | 0.36086 | -0.74251
| 1634 | 0.11972 | -0.008486 | 0.22754 | -0.60821 | 0.36117 | 0.30236 | 0.08649 | -0.12782 | -0.7496 | -0.11609
| 1635 | 0.010707 | -0.90151 | -0.34479 | 0.049579 | 0.54712 | 0.50796 | 0.35556 | 0.13507 | -0.74682 | 0.63
| 1636 | -0.4471 | -0.32583 | 0.63848 | 0.6637 | -0.88731 | -0.01263 | -0.66849 | 0.81 | -0.048212 | 0.45677
| 1637 | -0.15413 | -0.72632 | -0.40578 | 0.58781 | 0.35712 | 0.009899 | 0.50695 | -0.42546 | -0.3607 | 0.11304
| 1638 | 0.23234 | 0.15 | -0.42303 | -0.87876 | 0.17775 | -0.017503 | -0.12541 | -0.564 | 0.64602 | -0.37847
| 1639 | -0.35339 | 0.90673 | 0.68298 | -0.33045 | -0.01344 | 0.6149 | -0.076149 | 0.97354 | -0.46943 | 0.63903
| 1640 | -0.044751 | 0.33254 | -0.081795 | 0.36337 | 0.49671 | 0.16054 | 0.012326 | -0.43334 | 0.067316 | -0.20219
| 1641 | -0.046742 | -0.34632 | -0.79143 | 0.40309 | 0.065709 | 0.24165 | -0.34448 | -0.048843 | -0.65518 | 0.37831
| 1642 | -0.05984 | 0.047582 | -0.30222 | 0.14239 | -0.13138 | -0.030722 | -0.73713 | -0.0021523 | 0.40544 | -0.25307
| 1643 | -0.82536 | -0.56102 | -0.27716 | 0.12154 | 0.14859 | -0.51 | -0.058565 | 0.65927 | 0.099167 | 0.014556
| 1644 | -0.21495 | -0.026296 | -0.3851 | 0.25147 | -0.49334 | -0.14788 | 0.027837 | -0.35758 | -0.40494 | -0.13242
| 1645 | -0.038491 | 0.65431 | 0.40966 | -0.29155 | 0.016588 | 0.49493 | 0.14449 | 0.20672 | -0.54426 | -0.58227
| 1646 | 0.010303 | -0.30971 | 0.248 | -0.23286 | 0.13311 | -0.87876 | -0.49256 | -0.66251 | 0.3796 | 0.2256
| 1647 | -0.065709 | -0.47837 | 0.14402 | -0.23182 | 0.13565 | -0.018522 | 0.2948 | 0.35758 | 0.020766 | -0.43831
| 1648 | 0.34739 | -0.3309 | -0.68968 | -0.25858 | -0.65518 | 0.22857 | -0.67519 | -0.089012 | 0.51143 | 0.35123
| 1649 | 0.18692 | 0.35525 | -0.38984 | 0.044437 | 0.097393 | -0.10195 | 0.80843 | 0.49413 | -0.007478 | 0.069355
| 1650 | -0.47645 | 0.35541 | -0.030516 | -0.013542 | 0.30711 | 0.17096 | -0.028455 | 0.18373 | 0.20546 | -0.67152
| 1651 | -0.57233 | -0.052108 | -0.015267 | 0.63792 | 0.12908 | -0.27426 | 0.14542 | 0.082667 | 0.17193 | 0.40746
| 1652 | 0.072261 | -0.28761 | 0.34388 | 0.0085869 | -0.49493 | -0.58781 | 0.074527 | 0.4417 | 0.48087 | -0.45603
| 1653 | -0.075825 | 0.50817 | 0.29936 | 0.148 | 0.48785 | -0.069248 | -0.37638 | 0.29127 | -0.62066 | -0.017707
| 1654 | -0.64153 | -0.60744 | 0.27288 | 0.12017 | -0.087366 | 0.34418 | 0.16125 | 0.059947 | -0.63081 | -0.93
| 1655 | -0.14812 | -0.10094 | 0.064318 | -0.41854 | -0.035687 | -0.54602 | -0.3629 | -0.52115 | -0.35883 | 0.58107
| 1656 | -0.96394 | 0.84476 | 0.25147 | 0.11745 | 0.21152 | -0.69259 | -0.0033556 | 0.30523 | -0.4163 | -0.4857
| 1657 | 0.34908 | -0.37048 | 0.075608 | 0.83907 | 0.15744 | 0.045065 | -0.17921 | 0.35914 | 0.21559 | -0.39148
| 1658 | -0.01547 | -0.78068 | 0.89 | 0.36952 | 0.13369 | -0.074203 | 0.25723 | 0.16711 | -0.40075 | 0.6833
| 1659 | 0.068603 | 0.44493 | 0.42441 | -0.59738 | 0.09055 | 0.95641 | -0.10697 | -0.019337 | 0.43813 | 0.041094
| 1660 | -0.30899 | 0.75403 | 0.098279 | 0.25254 | 0.34114 | -0.1466 | -0.66429 | 0.12256 | 0.080489 | 0.28063
| 1661 | -0.21712 | -0.22238 | 0.3306 | -0.18864 | -0.18189 | 0.10206 | 0.066458 | -0.098501 | -0.1204 | -0.75979
| 1662 | 0.88731 | -0.8755 | -0.67612 | -0.5954 | -0.28467 | 0.75322 | 0.19421 | 0.19495 | 0.037971 | -0.065388
| 1663 | -0.83357 | 0.3422 | 0.074527 | 0.15768 | 0.15804 | -0.79288 | 0.4041 | 0.53881 | -0.20257 | -0.0755
| 1664 | 0.67581 | -0.15165 | -0.06603 | 0.30884 | 0.37446 | 0.40477 | -0.60744 | 0.039948 | -0.25147 | 0.30928
| 1665 | 0.12943 | -0.087695 | 0.15935 | -0.43688 | 0.4999 | 0.093192 | 0.29765 | -0.75322 | 0.61335 | -0.13357
| 1666 | 0.25294 | -0.38332 | -0.49631 | 0.09839 | 0.19719 | -0.97764 | -0.25723 | -0.34831 | 0.10933 | -0.64659
| 1667 | 0.039219 | -0.17629 | -0.42703 | -0.21853 | -0.24814 | -0.1852 | -0.057397 | 0.53256 | 0.18914 | 0.050105
| 1668 | 0.3568 | 0.038075 | 0.1546 | -0.051791 | 0.21994 | -0.36715 | 0.20307 | -0.48183 | 0.060372 | 0.052424
| 1669 | -0.28411 | 0.63572 | 0.096285 | 0.014759 | -0.19508 | -0.055701 | 0.073987 | 0.65518 | 0.025577 | -0.91938
| 1670 | -0.28397 | 0.68204 | 0.6952 | -0.7429 | 0.56537 | 0.236 | -0.39197 | 0.57751 | 0.30509 | 0.62198
| 1671 | -0.15863 | -0.81318 | 0.23364 | 0.030928 | -0.0728 | 0.16819 | -0.0094951 | 0.68903 | 0.85893 | -0.05348
| 1672 | -0.45383 | 0.52198 | 0.53277 | -0.74525 | -0.71173 | 0.34862 | -0.46269 | 0.75403 | 0.29282 | 0.019541
| 1673 | -0.052213 | -0.35262 | 0.55335 | -0.2037 | -0.65316 | 0.5021 | -0.15425 | -0.38121 | 0.26169 | -0.40427
| 1674 | -0.73981 | 0.78763 | -0.69422 | -0.076799 | 0.25013 | 0.26672 | 0.13253 | -0.65956 | -0.09033 | -0.40713
| 1675 | 0.094738 | 0.39049 | 0.021787 | -0.086819 | -0.19906 | -0.26849 | -0.18815 | -0.003155 | 0.21228 | -0.64265
| 1676 | 0.15519 | 0.72963 | 0.29424 | 0.64293 | -0.45255 | 0.27854 | 0.086928 | -0.77483 | 0.64181 | -0.80481
| 1677 | 0.37064 | 0.22689 | -0.37944 | -0.89656 | 0.14882 | -0.56537 | -0.23234 | -0.060053 | 0.17423 | -0.16376
| 1678 | -0.4279 | -0.43493 | -0.63054 | 0.093303 | -0.67366 | -0.12702 | -0.4417 | 0.21292 | 0.12885 | 0.10206
| 1679 | -0.29353 | 0.088243 | 0.72889 | 0.4995 | -0.22754 | -0.59318 | 0.27951 | -0.45972 | 0.26142 | -0.65287
| 1680 | 0.17592 | -0.021992 | -0.18189 | 0.85 | -0.68903 | -0.37032 | 0.4564 | -0.27069 | -0.42877 | -0.29296
| 1681 | -0.76104 | -0.44349 | -0.041825 | 0.77 | -0.4417 | -0.28719 | -0.26781 | 0.67366 | 0.2119 | -0.1852
| 1682 | 0.078534 | -0.0054649 | 0.64914 | -0.44638 | -0.2711 | 0.31993 | -0.57327 | -0.13438 | 0.32836 | 0.054749
| 1683 | -0.35463 | 0.16723 | -0.75526 | 0.66281 | -0.33766 | 0.11405 | -0.32985 | 0.049474 | -0.63875 | -0.028455
| 1684 | -0.29509 | 0.24721 | 0.25401 | 0.13426 | 0.86847 | -0.7488 | -0.20357 | -0.48357 | 0.014353 | -0.080816
| 1685 | 0.55089 | 0.11767 | 0.18803 | 0.84284 | -0.0866 | -0.033615 | 0.6349 | -0.23495 | -0.63986 | 0.65956
| 1686 | -0.48493 | -0.6755 | -0.06496 | -0.017707 | 0.33781 | -0.052002 | 0.097836 | 0.66668 | -0.059521 | 0.55762
| 1687 | -0.58708 | -0.0042591 | -0.6257 | 0.078317 | -0.35556 | 0.65345 | -0.51225 | 0.2476 | -0.252 | -0.68807
| 1688 | -0.25281 | 0.030309 | -0.034443 | -0.29028 | 0.9245 | -0.53664 | -0.42825 | 0.71173 | 0.16328 | -0.42528
| 1689 | -0.0092932 | -0.11722 | -0.13913 | 0.36117 | 0.30394 | -0.087586 | -0.41716 | 0.17048 | -0.2504 | 0.18116
| 1690 | 0.50756 | -0.14953 | 0.66133 | 0.044751 | 0.30222 | -0.19334 | 0.87631 | -0.71627 | 0.0057666 | 0.095843
| 1691 | -0.94615 | -0.4736 | 0.15035 | 0.037867 | -0.055913 | -0.0026535 | -0.25885 | 0.57163 | 0.06914 | 0.89276
| 1692 | 0.052635 | 0.43742 | -0.25576 | 0.11813 | -0.40814 | 0.24402 | -0.46568 | -0.38364 | -0.1688 | 0.73789
| 1693 | 0.39709 | 0.48804 | -0.48941 | 0.0030547 | 0.26481 | 0.14379 | 0.30624 | -0.58976 | -0.38673 | 0.27398
| 1694 | -0.11225 | 0.11428 | 0.22741 | -0.77662 | -0.09839 | 0.13519 | -0.69983 | 0.29637 | 0.84476 | 0.23639
| 1695 | -0.59318 | -0.047162 | -0.15543 | 0.67243 | 0.1758 | -0.56216 | 0.14589 | 0.436 | 0.69884 | -0.50654
| 1696 | -0.12759 | 0.56194 | 0.20495 | -0.15578 | 0.35727 | -0.096396 | 0.036932 | 0.50715 | -0.16819 | 0.81372
| 1697 | 0.48241 | 0.23809 | 0.18361 | -0.22225 | -0.21891 | -0.68839 | -0.4991 | 0.067637 | -0.49671 | -0.031444
| 1698 | -0.25053 | 0.36055 | 0.81 | 0.45456 | -0.010606 | 0.18815 | 0.24947 | 0.052002 | -0.46213 | 0.3618
| 1699 | 0.049895 | -0.17362 | -0.14929 | -0.52157 | -0.94255 | 0.71698 | 0.48902 | 0.13913 | 0.37944 | 0.7076
| 1700 | 0.87958 | -0.74174 | 0.14484 | -0.4987 | -0.2508 | -0.55178 | 0.60821 | 0.072584 | -0.30193 | -0.55694
| 1701 | -0.18938 | 0.27979 | 0.10184 | 0.82479 | 0.10854 | -0.2287 | 0.3366 | -0.21955 | 0.06197 | 0.048422
| 1702 | -0.37638 | 0.38299 | 0.38559 | -0.68903 | 0.10585 | 0.35 | 0.15047 | -0.41102 | -0.80791 | -0.25966
| 1703 | 0.38121 | 0.79048 | 0.34038 | 0.02097 | -0.63572 | 0.15401 | 0.25468 | 0.092972 | -0.018623 | -0.066351
| 1704 | 0.18667 | -0.54933 | -0.003155 | -0.41272 | -0.23312 | -0.37799 | -0.26305 | -0.20244 | 0.21712 | 0.087476
| 1705 | -0.14006 | 0.68903 | 0.3607 | 0.36636 | 0.13832 | -0.94804 | -0.69553 | 0.0071757 | 0.06261 | -0.20483
| 1706 | 0.20194 | 0.011415 | -0.56125 | 0.17447 | -0.49295 | 0.035168 | 0.13438 | -0.14519 | 0.17568 | -0.20697
| 1707 | 0.035894 | -0.10641 | 0.37127 | 0.16507 | -0.59863 | -0.59888 | 0.41991 | 0.0037571 | 0.41819 | 0.030103
| 1708 | -0.14554 | -0.019031 | -0.19483 | 0.77262 | -0.5583 | 0.36384 | 0.36889 | 0.039844 | -0.20659 | -0.38951
| 1709 | -0.36463 | 0.552 | 0.12862 | 0.164 | 0.40848 | 0.14239 | 0.28621 | 0.29964 | -0.68361 | 0.12828
| 1710 | 0.11643 | -0.91112 | -0.17982 | -0.76612 | 0.52936 | -0.67488 | 0.49275 | 0.38283 | 0.25187 | -0.41477
| 1711 | 0.84476 | -0.098612 | -0.43777 | -0.046952 | -0.26345 | 0.40125 | -0.51389 | -0.22135 | 0.013339 | 0.29879
| 1712 | 0.20975 | -0.0056661 | 0.53064 | -0.3681 | 0.22948 | -0.072261 | 0.045589 | 0.14414 | 0.24086 | -0.081795
| 1713 | 0.18618 | -0.011921 | -0.448 | 0.31538 | -0.54602 | 0.16496 | 0.14941 | -0.23534 | -0.53277 | -0.17617
| 1714 | 0.071291 | -0.094075 | -0.10406 | -0.47798 | 0.72559 | 0.035272 | 0.25093 | -0.58467 | -0.068281 | -0.33374
| 1715 | 0.63217 | 0.44855 | -0.13658 | 0.27316 | 0.17229 | 0.68393 | -0.19869 | -0.26074 | 0.47038 | -0.033615
| 1716 | -0.06603 | -0.40628 | 0.031031 | -0.17811 | 0.60113 | 0.080816 | -0.73751 | -0.19719 | 0.1261 | 0.097614
| 1717 | -0.5201 | -0.12085 | 0.25133 | 0.05984 | -0.22495 | -0.54382 | 0.094848 | 0.28188 | -0.038699 | 0.52597
| 1718 | 0.10541 | 0.074203 | -0.23875 | 0.88381 | 0.46774 | 0.077883 | 0.013542 | -0.07962 | 0.096507 | -0.15911
| 1719 | 0.58467 | 0.17302 | 0.10284 | 0.66459 | 0.0087886 | 0.28873 | 0.61361 | 0.96127 | 0.092972 | -0.21789
| 1720 | 0.25027 | 0.8422 | -0.56814 | -0.58733 | 0.11813 | -0.31349 | -0.61283 | -0.16161 | -0.71347 | 0.5806
| 1721 | 0.20044 | 0.19956 | 0.080381 | 0.29708 | -0.82824 | -0.024859 | -0.49137 | -0.33947 | -0.49512 | -0.084413
| 1722 | -0.23182 | -0.30957 | 0.43884 | 0.58012 | 0.51699 | 0.464 | 0.086271 | -0.28495 | 0.11101 | -0.49177
| 1723 | -0.33389 | -0.22315 | -0.063677 | -0.26699 | -0.12908 | 0.30279 | 0.19111 | 0.39809 | 0.26074 | 0.12142
| 1724 | 0.37366 | -0.53729 | -0.54756 | 0.14941 | 0.63217 | -0.60592 | 0.071507 | -0.72125 | -0.069892 | 0.47684
| 1725 | 0.31699 | -0.84933 | -0.25067 | 0.35355 | 0.19744 | -0.35247 | 0.31058 | 0.33449 | 0.65518 | -0.1957
| 1726 | 0.2256 | -0.47665 | -0.3551 | -0.044751 | -0.56491 | -0.18852 | 0.73827 | 0.42563 | -0.65172 | 0.34662
| 1727 | 0.56768 | 0.21457 | -0.012934 | -0.43653 | 0.34754 | 0.09154 | -0.50291 | -0.47265 | 0.075392 | 0.81588
| 1728 | 0.32583 | 0.37048 | -0.05549 | -0.036205 | 0.24588 | 0.37734 | 0.00085036 | 0.40595 | 0.2047 | -0.53021
| 1729 | 0.13785 | -0.099833 | -0.17048 | -0.68936 | -0.6233 | 0.00015001 | 0.10675 | 0.56216 | -0.41357 | -0.64237
| 1730 | 0.71946 | 0.25147 | -0.34281 | -0.08649 | 0.20344 | -0.30826 | -0.69652 | 0.0085869 | -0.037867 | 0.6382
| 1731 | -0.033512 | 0.22586 | 0.27661 | 0.13161 | 0.4344 | -0.28257 | -0.33871 | 0.60719 | -0.78114 | -0.26495
| 1732 | 0.038179 | -0.087914 | -0.017401 | -0.099833 | -0.20232 | -0.51061 | -0.17459 | -0.28243 | 0.22637 | 0.37734
| 1733 | -0.12404 | -0.39925 | 0.06165 | -0.18397 | -0.18153 | -0.32243 | -0.67243 | -0.15626 | -0.14624 | 0.83538
| 1734 | 0.56125 | 0.44331 | 0.16448 | 0.26918 | 0.056443 | 0.18741 | 0.14496 | -0.060585 | -0.50392 | 0.30783
| 1735 | 0.20684 | -0.70555 | 0.39494 | 0.42737 | 0.46755 | 0.12885 | -0.14145 | -0.44873 | -0.27426 | 0.18165
| 1736 | 0.21687 | -0.16675 | -0.054537 | 0.36368 | -0.52873 | 0.46661 | -0.086709 | -0.91456 | 0.79826 | -0.25872
| 1737 | 0.03714 | -0.0067729 | 0.18043 | -0.27938 | -0.09695 | -0.12839 | 0.16244 | -0.23967 | -0.37159 | -0.019337
| 1738 | 0.68141 | 0.19384 | 0.95877 | 0.075068 | 0.34831 | 0.59813 | -0.28845 | 0.7816 | -0.43529 | 0.48687
| 1739 | -0.0059678 | 0.76442 | 0.41528 | 0.044961 | 0.48687 | -0.45055 | -0.60364 | -0.64631 | -0.28355 | 0.10989
| 1740 | -0.56699 | -0.06293 | -0.026707 | -0.50331 | -0.47856 | -0.17738 | 0.13057 | -0.1628 | -0.41272 | -0.35821
| 1741 | 0.29381 | 0.1044 | -0.0032553 | 0.92063 | -0.7735 | 0.040886 | -0.43 | -0.073555 | 0.46288 | 0.71
| 1742 | 0.070108 | 0.18594 | -0.40159 | 0.052213 | -0.14425 | 0.53686 | 0.94804 | 0.51123 | -0.063144 | -0.51225
| 1743 | -0.26359 | 0.14835 | 0.20697 | -0.20533 | 0.33434 | -0.66103 | -0.58587 | 0.1292 | -0.24707 | 0.61026
| 1744 | 0.78483 | 0.43211 | 0.015063 | -0.03974 | 0.65605 | 0.76104 | -0.40159 | -0.093634 | -0.52303 | -0.12977
| 1745 | 0.43742 | 0.2975 | -0.81917 | -0.38934 | 0.40309 | -0.38299 | -0.068174 | -0.59245 | -0.6371 | -0.29779
| 1746 | -0.71487 | 0.65057 | 0.072908 | -0.10384 | 0.36337 | 0.093413 | -0.16844 | -0.48376 | -0.26904 | 0.54668
| 1747 | 0.10899 | 0.024141 | 0.18667 | -0.06016 | -0.16161 | -0.053903 | 0.17278 | 0.064105 | -0.15899 | 0.26549
| 1748 | -0.66879 | 0.14636 | 0.13334 | -0.18606 | 0.84348 | 0.37927 | -0.08989 | 0.75979 | 0.91 | -0.098723
| 1749 | 0.072476 | -0.13369 | -0.55943 | -0.93292 | 0.29113 | -0.25926 | -0.79776 | 0.3864 | 0.27137 | 0.29226
| 1750 | -0.32302 | 0.06753 | 0.15923 | 0.59963 | 0.12862 | -0.5954 | -0.65839 | 0.097503 | -0.20508 | 0.038283
| 1751 | -0.17399 | -0.5003 | -0.21076 | 0.50654 | -0.83118 | -0.24297 | -0.23508 | -0.52282 | -0.15082 | 0.23182
| 1752 | -0.02794 | -0.075825 | 0.21508 | 0.43848 | 0.04172 | -0.071722 | -0.44529 | 0.42112 | -0.89851 | 0.06678
| 1753 | 0.47914 | 0.35216 | 0.3248 | -0.061331 | -0.14671 | 0.15484 | -0.12302 | -0.58854 | -0.84412 | -0.1245
| 1754 | 0.17072 | 0.68679 | -0.60821 | -0.8956 | 0.67274 | -0.21241 | -0.50432 | 0.20911 | 0.76784 | 0.44331
| 1755 | -0.43211 | -0.20382 | -0.086709 | -0.77131 | 0.51369 | 0.66251 | 0.66608 | -0.045065 | 0.13727 | 0.06496
| 1756 | 0.1466 | -0.2081 | 0.23796 | -0.30971 | -0.77751 | 0.47818 | 0.67091 | 0.43902 | 0.55898 | -0.061757
| 1757 | -0.05899 | -0.056337 | 0.37446 | -0.37064 | -0.11722 | 0.0081835 | 0.40696 | -0.71208 | 0.46512 | 0.053163
| 1758 | 0.66879 | 0.17811 | 0.30265 | -0.15484 | 0.2356 | 0.097947 | -0.11191 | 0.40696 | 0.27799 | -0.33479
| 1759 | 0.062183 | 0.042242 | -0.75363 | 0.51205 | 0.83907 | -0.31495 | -0.38202 | 0.096507 | 0.46643 | -0.52387
| 1760 | 0.16388 | -0.55245 | -0.11439 | 0.16472 | -0.76784 | 0.22122 | -0.56491 | 0.27509 | 0.25872 | 0.40814
| 1761 | -0.38543 | 0.27192 | 0.48144 | 0.13461 | -0.10843 | 0.39726 | -0.53643 | 0.71277 | -0.2975 | 0.37574
| 1762 | 0.45917 | 0.12759 | -0.18238 | 0.8747 | -0.28803 | -0.56468 | 0.49532 | 0.3451 | -0.1797 | -0.009798
| 1763 | 0.2427 | -0.02794 | -0.27813 | 0.35665 | 0.23783 | 0.44331 | 0.1565 | 0.74058 | -0.40865 | -0.087695
| 1764 | 0.87 | 0.12256 | -0.078534 | -0.079837 | 0.32302 | 0.020357 | -0.29622 | -0.67 | -0.38121 | 0.72054
| 1765 | -0.3214 | 0.73298 | 0.12564 | -0.59417 | -0.38902 | -0.34831 | 0.40359 | -0.10284 | -0.24588 | 0.32702
| 1766 | 0.78716 | -0.37191 | -0.035998 | -0.24734 | -0.32717 | 0.074527 | -0.43671 | 0.6697 | 0.87876 | 0.22135
| 1767 | -0.38008 | 0.8747 | -0.43176 | -0.065923 | 0.28719 | 0.092862 | 0.35805 | 0.019031 | 0.63682 | -0.2689
| 1768 | 0.17605 | -0.43387 | -0.46344 | 0.13473 | -0.15828 | -0.33675 | -0.089341 | 0.34693 | 0.0035563 | -0.51595
| 1769 | 0.20672 | -0.27426 | 0.31465 | -0.54098 | 0.0922 | 0.94615 | -0.43813 | 0.25374 | 0.66251 | -0.17556
| 1770 | -0.15531 | 0.38283 | -0.28733 | 0.34448 | -0.20131 | -0.6634 | -0.42842 | 0.21266 | -0.22276 | 0.029588
| 1771 | 0.23078 | -0.43529 | 0.25899 | 0.45787 | -0.028558 | 0.17241 | -0.27247 | 0.14215 | 0.33269 | -0.79678
| 1772 | -0.61361 | 0.78669 | -0.76569 | -0.30769 | 0.12713 | -0.021276 | 0.27647 | -0.32406 | 0.82941 | 0.11938
| 1773 | -0.2175 | 0.10139 | 0.11507 | 0.34144 | -0.23065 | -0.034961 | -0.36274 | -0.16795 | 0.1628 | -0.037244
| 1774 | -0.011314 | -0.53363 | -0.32583 | -0.61257 | -0.16352 | 0.41374 | 0.4995 | -0.099944 | -0.34327 | 0.27096
| 1775 | 0.2625 | 0.14006 | -0.16747 | 0.65172 | -0.30207 | 0.26223 | -0.3419 | 0.083976 | 0.58083 | 0.54933
| 1776 | 0.092531 | -0.31276 | -0.2722 | 0.46474 | 0.4668 | 0.19284 | 0.19931 | 0.076907 | -0.30337 | -0.1559
| 1777 | 0.61231 | 0.20244 | 0.43035 | 0.028455 | 0.16496 | 0.5332 | -0.21495 | -0.1841 | 0.27951 | 0.14099
| 1778 | -0.36337 | -0.35216 | 0.15401 | 0.22611 | -0.18079 | -0.12188 | -0.52788 | -0.13369 | -0.0028541 | -0.014454
| 1779 | 0.11417 | 0.46812 | 0.41922 | 0.010303 | 0.62277 | 0.04172 | -0.085068 | 0.14029 | -0.5583 | -0.23312
| 1780 | 0.55627 | 0.11598 | -0.14965 | 0.95877 | 0.81534 | -0.59368 | 0.68679 | 0.10139 | 0.23796 | 0.15946
| 1781 | 0.68807 | -0.50614 | -0.3025 | -0.5608 | 0.088573 | 0.20949 | -0.91815 | 0.85893 | 0.7881 | -0.14169
| 1782 | -0.069892 | -0.051475 | -0.35139 | -0.76569 | -0.11315 | -0.011415 | 0.16892 | 0.057185 | 0.038283 | 0.22896
| 1783 | -0.64265 | -0.16089 | 0.20911 | -0.11507 | -0.09198 | 0.48029 | 0.38396 | -0.51451 | 0.43299 | 0.55921
| 1784 | 0.14671 | 0.5447 | -0.23993 | 0.87793 | -0.83477 | -0.17726 | -0.29085 | 0.5447 | -0.19794 | -0.086381
| 1785 | -0.48824 | -0.43564 | -0.39246 | 0.73675 | 0.1204 | -0.76827 | 0.36968 | -0.27951 | 0.30696 | 0.53535
| 1786 | -0.16988 | 0.35262 | 0.4898 | 0.51287 | -0.31597 | -0.71173 | -0.064746 | -0.21827 | 0.43 | -0.078968
| 1787 | 0.37847 | 0.1292 | -0.21304 | 0.72233 | -0.17787 | -0.1578 | 0.19744 | 0.58467 | 0.42563 | 0.22148
| 1788 | -0.71452 | 0.29113 | -0.61051 | 0.37976 | 0.20975 | 0.068067 | 0.18043 | -0.33962 | -0.48961 | -0.047897
| 1789 | -0.3882 | 0.36636 | -0.2476 | -0.31189 | -0.22805 | -0.60694 | -0.12793 | -0.2216 | 0.53192 | -0.0066723
| 1790 | -0.83538 | -0.16424 | -0.24734 | 0.099611 | -0.40393 | -0.46028 | -0.67213 | 0.052319 | 0.68298 | 0.035894
| 1791 | -0.43423 | 0.2809 | 0.48029 | -0.055066 | 0.53946 | 0.22547 | -0.52534 | 0.21597 | 0.64829 | -0.18446
| 1792 | -0.027837 | 0.3956 | 0.86771 | -0.47933 | 0.34281 | -0.9078 | 0.80075 | -0.30222 | -0.38706 | -0.32613
| 1793 | 0.014353 | 0.031651 | -0.26427 | -0.15413 | 0.70931 | -0.3651 | -0.054855 | 0.52387 | 0.71946 | 0.63682
| 1794 | 0.36243 | -0.94084 | 0.25629 | 0.43938 | 0.66578 | -0.33149 | 0.93292 | -0.15354 | -0.41888 | 0.22328
| 1795 | 0.077558 | -0.47474 | 0.0017515 | 0.82084 | -0.31102 | -0.51451 | 0.39576 | -0.32022 | 0.69324 | -0.14906
| 1796 | -0.019643 | -0.45585 | -0.2791 | -0.23456 | 0.034961 | 0.094848 | 0.082231 | 0.2625 | 0.22019 | -0.032684
| 1797 | -0.18778 | 0.13334 | 0.47626 | -0.2625 | 0.63054 | -0.086928 | -0.11835 | 0.18544 | 0.75241 | -0.3743
| 1798 | -0.076799 | -0.77977 | -0.46849 | 0.13046 | -0.61777 | 0.10228 | 0.14742 | -0.60113 | -0.047057 | -0.093965
| 1799 | 0.012123 | 0.12154 | 0.64687 | -0.25361 | -0.54978 | -0.85067 | -0.45511 | -0.052741 | -0.1769 | -0.90356
| 1800 | 0.52115 | 0.13426 | -0.33269 | 0.80635 | 0.7881 | -0.057291 | -0.60138 | 0.49275 | -0.14029 | -0.59392
| 1801 | 0.5469 | -0.62357 | 0.53621 | -0.19806 | 0.26563 | 0.066887 | -0.76698 | 0.23182 | 0.12324 | -0.33314
| 1802 | -0.13692 | 0.42528 | 0.69718 | -0.42268 | -0.85682 | -0.19944 | -5.0001e-05 | -0.22857 | 0.18778 | -0.38967
| 1803 | -0.43938 | 0.21981 | -0.47684 | -0.16137 | -0.19831 | -0.15365 | -0.66133 | -0.065923 | -0.42755 | -0.12839
| 1804 | -0.21994 | 0.4859 | 0.73599 | -0.10061 | 0.16352 | -0.10217 | 0.006169 | -0.50553 | 0.7504 | 0.065281
| 1805 | -0.27412 | -0.464 | -0.12347 | -0.46362 | 0.12439 | 0.11745 | -0.11473 | 0.28537 | -0.022401 | -0.44063
| 1806 | -0.0073772 | 0.0069743 | 0.19 | 0.072045 | -0.44224 | -0.070968 | 0.40309 | 0.46549 | -0.36668 | 0.37976
| 1807 | -0.15816 | -0.12989 | -0.50573 | 0.020561 | 0.30754 | 0.35805 | 0.10384 | 0.046742 | 0.32346 | -0.16687
| 1808 | -0.18275 | 0.18495 | -0.12897 | -0.11994 | -0.91225 | 0.57727 | -0.50614 | -0.11338 | 0.46195 | -0.20006
| 1809 | 0.049474 | -0.11665 | -0.36133 | -0.017605 | -0.034236 | 0.55492 | -0.27261 | 0.18067 | -0.013846 | -0.352
| 1810 | 0.39444 | -0.29466 | 0.10485 | -0.085506 | 0.67704 | 0.47875 | 0.43458 | -0.46176 | 0.26549 | -0.33932
| 1811 | -0.72963 | 0.1646 | 0.14437 | 0.55672 | -0.17909 | -0.96394 | 0.3451 | -0.24535 | 0.93443 | -0.53235
| 1812 | -0.096728 | -0.62517 | 0.18092 | -0.08989 | -0.059628 | 0.35525 | 0.02794 | 0.31934 | -0.14953 | -0.23026
| 1813 | -0.40713 | -0.23862 | -0.48629 | 0.035376 | 0.62758 | 0.30408 | -0.48106 | -0.84284 | -0.36731 | 0.20169
| 1814 | 0.36008 | -0.26373 | 0.80687 | 0.61882 | 0.38413 | -0.021685 | -0.1841 | 0.31963 | 0.4981 | -0.59938
| 1815 | -0.51389 | -0.21051 | -0.52597 | -0.48941 | 0.0026535 | -0.58878 | -0.29438 | 0.39543 | -0.19856 | -0.018522
| 1816 | -0.36305 | -0.16268 | 0.096728 | 0.18753 | 0.20962 | -0.63353 | 0.34632 | 0.53621 | 0.40915 | -0.031238
| 1817 | 0.12828 | -0.85543 | 0.4826 | 0.37048 | -0.21495 | -0.63599 | 0.12119 | -0.42598 | -0.044961 | -0.093192
| 1818 | -0.70691 | -0.21241 | 0.40142 | 0.32096 | 0.53967 | -0.94255 | 0.38885 | 0.023527 | 0.34846 | 0.52387
| 1819 | 0.51948 | 0.77483 | -0.2256 | 0.28972 | 0.22482 | -0.50634 | 0.63 | -0.24257 | 0.023527 | 0.51534
| 1820 | -0.24231 | -0.71487 | -0.05158 | -0.42965 | 0.15024 | 0.43423 | 0.42337 | 0.5707 | 0.11304 | -0.030619
| 1821 | -0.82196 | 0.046008 | 0.055701 | -0.026296 | -0.50432 | 0.10485 | -0.11112 | -0.042138 | -0.54033 | -0.38918
| 1822 | -0.32687 | 0.14449 | 0.21215 | -0.16113 | -0.19396 | 0.27014 | -0.52052 | 0.075284 | 0.17726 | -0.23065
| 1823 | -0.3211 | 0.74174 | -0.54668 | 0.040156 | 0.1315 | -0.85543 | -0.1868 | 0.61882 | -0.56977 | 0.95
| 1824 | -0.31568 | 0.0091922 | -0.41034 | 0.41153 | -0.52745 | 0.1841 | 0.093854 | -0.1308 | -0.54558 | -0.33179
| 1825 | 0.51865 | 0.34632 | -0.05253 | 0.11428 | 0.29085 | -0.70318 | 0.352 | -0.28621 | -0.36133 | 0.077558
| 1826 | -0.15744 | 0.81426 | 0.44964 | -0.52682 | -0.011011 | 0.16352 | 0.54558 | -0.20257 | 0.29964 | -0.09518
| 1827 | -0.80532 | -0.33179 | 0.21368 | -0.0067729 | -0.64829 | 0.68839 | 0.53643 | 0.34008 | -0.20319 | 0.28049
| 1828 | -0.14929 | 0.32732 | -0.45861 | -0.37831 | 0.097614 | 0.19099 | -0.1253 | 0.49433 | -0.86399 | 0.038907
| 1829 | -0.36747 | -0.42095 | -0.3306 | -0.0041586 | 0.29226 | 0.52324 | -0.36258 | -0.23757 | -0.14601 | 0.1425
| 1830 | 0.3048 | -0.27069 | 0.53171 | 0.59441 | -0.4987 | -0.27495 | -0.51575 | -0.65518 | -0.81426 | -0.49157
| 1831 | 0.45954 | 0.28035 | 0.74058 | 0.34357 | -0.013643 | -0.2119 | 0.57846 | 0.20019 | 0.88042 | -0.52177
| 1832 | -0.22586 | -0.95877 | -0.42216 | -0.00025003 | -0.35463 | 0.14215 | 0.77395 | 0.2948 | -0.10764 | 0.61882
| 1833 | -0.54602 | 0.48087 | -0.36683 | -0.16988 | -0.87712 | -0.4471 | 0.81642 | -0.16651 | -0.48765 | 0.15
| 1834 | 0.36039 | -0.26007 | -0.54734 | -0.013846 | 0.036413 | -0.011516 | -0.45603 | -0.8956 | -0.1863 | 0.21292
| 1835 | 0.54624 | 0.22071 | -0.47417 | 0.11146 | 0.13658 | 0.38869 | -0.29197 | -0.12324 | -0.18975 | 0.37
| 1836 | 0.14461 | -0.064532 | 0.48164 | 0.49572 | 0.54536 | 0.085834 | -0.15519 | -0.51184 | 0.097614 | 0.35324
| 1837 | 0.13704 | -0.13855 | -0.5721 | -0.57585 | -0.048843 | -0.14531 | 0.1072 | 0.16699 | 0.014759 | 0.025167
| 1838 | -0.22922 | -0.41119 | 0.78114 | 0.011415 | -0.83907 | 0.69129 | -0.25281 | 0.36494 | 0.53085 | -0.42615
| 1839 | -0.22818 | 0.15365 | 0.4258 | 0.70931 | -0.46943 | -0.29339 | 0.18557 | -0.0048618 | 0.39197 | -0.33524
| 1840 | 0.78763 | -0.15035 | 0.46418 | 0.2119 | 0.10462 | 0.39049 | -0.13369 | 0.022196 | 0.59147 | 0.0051633
| 1841 | 0.36937 | 0.68936 | 0.00085036 | -0.32896 | -0.31993 | -0.73675 | 0.16376 | -0.59664 | 0.33555 | -0.064105
| 1842 | -0.093744 | 0.23652 | 0.25737 | 0.083212 | -0.69357 | 0.10708 | -0.34892 | 0.58612 | 0.28747 | 0.33299
| 1843 | -0.52619 | 0.0033556 | -0.4979 | -0.53513 | 0.3419 | -0.32406 | 0.47057 | -0.56537 | 0.73981 | -0.060479
| 1844 | 0.52492 | 0.31611 | 0.37254 | -0.10184 | 0.09154 | 0.36937 | 0.72889 | 0.15259 | 0.37542 | 0.25818
| 1845 | -0.37286 | 0.031857 | -0.11349 | -0.34969 | -0.51287 | 0.52555 | -0.094185 | 0.098058 | -0.4531 | 0.2733
| 1846 | 0.23678 | 0.23705 | 0.033098 | -0.20798 | 0.57257 | 0.41459 | 0.39992 | -0.27882 | -0.14017 | -0.30523
| 1847 | -0.22148 | 0.88126 | 0.32332 | -0.25067 | 0.20131 | 0.20558 | 0.68456 | 0.10596 | -0.11722 | 0.13507
| 1848 | 0.90566 | 0.25939 | -0.54251 | 0.69718 | -0.66133 | -0.15733 | -0.33902 | -0.37048 | 0.067423 | 0.28523
| 1849 | -0.69685 | -0.23104 | -0.4995 | 0.23456 | -0.24893 | -0.24654 | -0.23941 | 0.50331 | -0.40393 | -0.053163
| 1850 | -0.3767 | -0.80226 | 0.29296 | -0.38332 | 0.1245 | -0.069355 | -0.30523 | 0.37175 | -0.34129 | 0.16567
| 1851 | -0.75566 | -0.22405 | 0.7687 | 0.60898 | -0.74058 | 0.55469 | 0.038075 | -0.40763 | 0.76655 | 0.15436
| 1852 | -0.40108 | -0.070538 | -0.58587 | -0.27041 | -0.17 | 0.31831 | 0.59565 | -0.53235 | -0.29993 | -0.33781
| 1853 | -0.73486 | 0.72089 | 0.6995 | -0.4117 | 0.7015 | -0.0020521 | 0.76357 | 0.011112 | 0.74682 | 0.47894
| 1854 | -0.19595 | 0.36102 | 0.11926 | 0.18348 | -0.12279 | 0.59888 | 0.44656 | 0.049895 | -0.74096 | 0.049789
| 1855 | 0.20006 | -0.2567 | -0.40142 | 0.35417 | -0.15863 | -0.44349 | 0.80532 | 0.69194 | -0.40276 | -0.10094
| 1856 | -0.68488 | 0.45091 | -0.094075 | -0.069033 | -0.024449 | 0.51761 | -0.23888 | -0.13034 | -0.21406 | -0.14988
| 1857 | -0.15177 | -0.32155 | 0.17241 | -0.13357 | 0.5707 | 0.18803 | 0.23391 | 0.62066 | -0.087586 | -0.5019
| 1858 | 0.3759 | 0.34281 | -0.42372 | 0.62919 | -0.3363 | -0.011719 | -0.63545 | -0.38738 | 0.2598 | 0.4993
| 1859 | 0.26509 | 0.35992 | 0.13173 | 0.51865 | 0.080924 | -0.19099 | -0.29452 | 0.0090913 | -0.092641 | 0.43317
| 1860 | 0.88467 | 0.44439 | -0.15555 | -0.50959 | -0.40544 | -0.76527 | 0.080163 | -0.436 | -0.08234 | 0.1752
| 1861 | -0.55853 | 0.86923 | 0.17411 | -0.39659 | -0.27481 | 0.82651 | 0.070323 | 0.22379 | 0.49039 | -0.43795
| 1862 | -0.82252 | -0.51554 | -0.20798 | 0.80277 | 0.59122 | -0.066351 | -0.40881 | 0.013744 | 0.22006 | -0.069463
| 1863 | -0.17799 | 0.038283 | 0.37334 | 0.060585 | -0.028455 | 0.79095 | -0.45164 | -0.21789 | -0.19981 | -0.012123
| 1864 | 0.11338 | 0.26468 | -0.19869 | -0.51906 | 0.075176 | 0.82028 | -0.19371 | -0.1634 | 0.45548 | 0.16328
| 1865 | -0.10295 | 0.41136 | 0.77617 | -0.1005 | 0.42912 | 0.23718 | 0.40797 | -0.18717 | -0.28677 | 0.87077
| 1866 | 0.21127 | -0.48668 | -0.58036 | 0.007075 | 0.023834 | 0.62758 | -0.099278 | -0.0922 | -0.51844 | 0.080816
| 1867 | -0.28803 | -0.60846 | 0.33015 | 0.86108 | 0.30884 | 0.26237 | 0.48941 | 0.6631 | -0.26617 | 0.11926
| 1868 | 0.029794 | 0.13138 | -0.89183 | 0.14871 | 0.15354 | 0.087586 | 0.15685 | -0.016893 | 0.23993 | -0.028764
| 1869 | -0.60339 | 0.0055655 | -0.25845 | -0.24973 | 0.66103 | 0.15295 | 0.071184 | -0.56838 | -0.98268 | -0.46755
| 1870 | -0.41511 | 0.22405 | 0.10083 | 0.57964 | 0.10006 | -0.11983 | -0.29907 | -0.41425 | 0.11711 | -0.10039
| 1871 | 0.10843 | -0.04026 | 0.28355 | -0.073016 | 0.33615 | -0.60113 | 0.34053 | 0.39494 | -0.15839 | 0.18532
| 1872 | -0.77977 | -0.21177 | -0.32613 | -0.13023 | -0.047372 | 0.34235 | -0.42251 | -0.36731 | -0.50271 | -0.081904
| 1873 | -0.10596 | 0.24973 | 0.47265 | -0.058777 | -0.14344 | -0.42424 | -0.076582 | 0.093303 | -0.051264 | -0.095069
| 1874 | -0.26959 | -0.4776 | 0.33856 | -0.65547 | -0.59269 | -0.50756 | -0.44331 | 0.093082 | -0.39543 | 0.43334
| 1875 | 0.12496 | -0.28747 | -0.31611 | -0.88731 | 0.044228 | -0.078751 | -0.18483 | 0.31102 | 0.13739 | 0.74446
| 1876 | 0.38105 | -0.63163 | 0.55424 | 0.15709 | 0.43405 | -0.10854 | -0.23862 | 0.15306 | 0.36431 | 0.42337
| 1877 | -0.52387 | 0.5469 | 0.13808 | 0.19919 | -0.37992 | -0.21508 | 0.028764 | -0.24469 | 0.51761 | 0.79433
| 1878 | -0.16699 | 0.19844 | -0.26332 | -0.2524 | 0.11281 | -0.48048 | 0.094296 | -0.41153 | 0.45732 | 0.079946
| 1879 | 0.42441 | 0.046533 | -0.73827 | -0.57186 | 0.69455 | -0.38853 | 0.36857 | 0.16675 | 0.24575 | -0.10172
| 1880 | -0.14227 | -0.60263 | 0.20445 | -0.078425 | 0.16747 | -0.25482 | -0.62624 | -0.23312 | -0.14554 | -0.76442
| 1881 | 0.63931 | 0.30107 | 0.092751 | -0.44439 | 0.38575 | -0.26836 | 0.05 | -0.55312 | -0.029691 | -0.25737
| 1882 | -0.063464 | -0.42772 | 0.10944 | 0.57538 | -0.71242 | 0.54142 | 0.048107 | 0.42043 | -0.73713 | 0.39809
| 1883 | 0.59269 | -0.36873 | 0.12074 | 0.45182 | -0.33284 | 0.19682 | -0.12599 | 0.20119 | 0.11281 | -0.40343
| 1884 | -0.056655 | -0.69751 | -0.14425 | 0.65201 | 0.32955 | 0.20382 | 0.31919 | -0.093413 | -0.044019 | 0.5245
| 1885 | -0.031754 | 0.24191 | 0.29254 | -0.29964 | -0.44421 | 0.35386 | -0.3148 | 0.7569 | -0.11079 | 0.62677
| 1886 | -0.062503 | -0.12667 | 0.60138 | 0.35154 | -0.1825 | -0.84412 | -0.076799 | -0.36447 | 0.30451 | -0.44403
| 1887 | 0.1261 | -0.34877 | -0.22405 | 0.3751 | -0.17994 | -0.35339 | -0.51886 | 0.13219 | 0.85405 | -0.0047613
| 1888 | -0.51061 | -0.01263 | 0.13577 | -0.13611 | 0.56491 | 0.24535 | 0.14064 | 0.77262 | 0.79975 | 0.79191
| 1889 | -0.3817 | 0.22263 | -0.055278 | 0.12943 | -0.22418 | 0.27924 | -0.012528 | 0.13565 | 0.59913 | -0.70589
| 1890 | 0.3425 | 0.3568 | -0.021276 | -0.85067 | -0.45292 | 0.23443 | 0.30812 | 0.33179 | -0.37847 | -0.40595
| 1891 | -0.63 | 0.13646 | -0.14507 | -0.61361 | 0.28859 | 0.19012 | 0.28243 | -0.10451 | 0.5015 | -0.248
| 1892 | 0.072369 | -0.34938 | 0.20207 | 0.71417 | -0.66849 | 5.0001e-05 | 0.27178 | 0.25093 | 0.73713 | -0.54933
| 1893 | 0.054008 | 0.60795 | -0.096617 | -0.048633 | -0.019949 | 0.4232 | -0.19719 | 0.08967 | -0.054643 | 0.26169
| 1894 | -0.026707 | 0.59838 | -0.4993 | 0.41836 | -0.018012 | 0.099056 | -0.07043 | 0.67735 | -0.28635 | 0.29523
| 1895 | 0.55267 | -0.16077 | -0.34342 | -0.2504 | -0.1439 | 0.065281 | -0.59318 | 0.0094951 | 0.13496 | 0.44547
| 1896 | 0.22857 | -0.29694 | 0.85893 | 0.14683 | 0.10106 | -0.51969 | -0.45935 | 0.078968 | -0.10295 | -0.39395
| 1897 | -0.14788 | -0.13762 | 0.38526 | 0.076582 | 0.48164 | -0.22212 | 0.75526 | 0.5143 | 0.58587 | 0.65345
| 1898 | -0.8821 | -0.1769 | 0.46362 | 0.67182 | 0.70862 | -0.41289 | 0.27247 | 0.29169 | 0.46213 | 0.1578
| 1899 | 0.11146 | 0.43053 | 0.53794 | -0.028146 | -0.83 | 0.34068 | -0.37414 | 0.4531 | -0.43476 | 0.12245
| 1900 | -0.32287 | -0.26509 | 0.52555 | -0.8467 | 0.043391 | 0.034547 | -0.74801 | 0.34433 | 0.51906 | 0.069463
| 1901 | -0.22379 | 0.14542 | -0.019949 | -0.096728 | 0.41408 | 0.81697 | 0.40092 | -0.38543 | -0.62013 | -0.24641
| 1902 | 0.31685 | 0.44116 | 0.44421 | 0.23915 | -0.15165 | 0.20848 | 0.46065 | 0.24522 | 0.26278 | 0.076582
| 1903 | -0.16209 | -0.27605 | 0.79579 | -0.81752 | -0.33105 | 0.38608 | 0.8454 | 0.6349 | -0.024141 | -0.31014
| 1904 | 0.56699 | -0.16952 | -0.34205 | 0.26536 | 0.13392 | 0.16232 | 0.24402 | 0.95877 | -0.27578 | -0.36968
| 1905 | -0.18226 | -0.19831 | -0.33705 | 0.17532 | 0.046638 | -0.18606 | -0.28803 | -0.21368 | -0.64744 | -0.050421
| 1906 | 0.30107 | 0.59196 | -0.64574 | -0.41991 | -0.10117 | -0.28299 | 0.20747 | -0.44295 | -0.77932 | 0.23247
| 1907 | 0.6257 | -0.55447 | 0.5143 | -0.01791 | -0.60923 | 0.29056 | -0.3551 | 0.24933 | 0.026707 | -0.0069743
| 1908 | -0.095622 | 0.39825 | 0.57444 | -0.74329 | 0.72197 | -0.0059678 | -0.63 | 0.19012 | -0.1706 | 0.59073
| 1909 | -0.72125 | -0.13623 | -0.15792 | -0.24827 | 0.13704 | -0.56377 | 0.23286 | 0.5283 | 0.2773 | 0.021379
| 1910 | -0.68936 | 0.041094 | -0.0047613 | 0.087914 | -0.11462 | -0.11881 | 0.62066 | -0.056443 | -0.3375 | 0.57609
| 1911 | 0.21266 | -0.12507 | 0.61438 | 0.10161 | 0.030722 | 0.1034 | -0.024346 | -0.1323 | -0.79531 | 0.45182
| 1912 | 0.51184 | -0.19994 | -0.17024 | 0.18422 | 0.56514 | -0.10518 | -0.050316 | -0.96683 | 0.38153 | 0.35805
| 1913 | -0.14542 | 0.14718 | 0.34159 | -0.31816 | 0.01842 | -0.39527 | -0.21572 | -0.85613 | 0.70217 | 0.022708
| 1914 | 0.20207 | 0.053374 | 0.10106 | -0.6118 | 0.57633 | -0.21495 | -0.80843 | 0.094075 | -0.093965 | -0.27979
| 1915 | -0.54448 | 0.45055 | -0.015774 | 0.25858 | -0.93 | 0.56606 | 0.24747 | 0.027426 | 0.58203 | 0.21089
| 1916 | -0.35603 | 0.18827 | 0.46195 | -0.73074 | -0.065174 | 0.22302 | -0.19769 | 0.036205 | 0.36826 | 0.97764
| 1917 | 0.096617 | -0.36227 | -0.33871 | -0.10596 | 0.59466 | 0.46943 | 0.27661 | 0.73448 | 0.20747 | -0.28369
| 1918 | 0.40159 | -0.48241 | -0.71663 | 0.022196 | 0.16268 | 0.011921 | 0.016181 | -0.77887 | 0.62013 | 0.22831
| 1919 | 0.063357 | -0.17411 | -0.32037 | 0.1136 | -0.85823 | 0.26781 | -0.30567 | -0.5866 | -0.2621 | 0.38722
| 1920 | 0.22096 | -0.45091 | -0.37462 | -0.86621 | -0.64631 | -0.42181 | 0.017401 | 0.15342 | -0.11847 | -0.087476
| 1921 | -0.46887 | -0.0016514 | -0.71982 | 0.71875 | -0.030722 | -0.078968 | -0.18827 | -0.040469 | 0.51844 | 0.64687
| 1922 | 0.32465 | 0.15436 | 0.29141 | 0.040573 | -0.56814 | 0.24217 | 0.49612 | 0.23783 | -0.86923 | 0.78068
| 1923 | 0.21878 | -0.26577 | 0.76741 | -0.19161 | -0.53729 | -0.19869 | -0.82941 | 0.564 | 0.51554 | -0.31058
| 1924 | 0.44009 | 0.35015 | 0.21827 | 0.031135 | -0.57397 | -0.068711 | -0.9245 | 0.1269 | 0.40645 | -0.53578
| 1925 | 0.12782 | -0.30136 | 0.21878 | -0.0049623 | -0.45824 | -0.63 | -0.67061 | 0.20495 | -0.35308 | 0.030722
| 1926 | 0.34129 | 0.21814 | 0.15839 | 0.42598 | -0.31305 | -0.41051 | 0.098945 | -0.48726 | -0.0014511 | 0.81426
| 1927 | -0.21853 | 0.65114 | -0.49473 | -0.27 | -0.27027 | 0.58131 | -0.23783 | 0.066458 | -0.5412 | 0.2184
| 1928 | -0.34662 | -0.0077803 | -0.22302 | -0.33464 | 0.2508 | -0.65663 | -0.057079 | -0.22948 | -0.11214 | -0.44116
| 1929 | 0.095843 | 0.048317 | -0.44367 | -0.27536 | 0.55379 | -0.58107 | -0.74446 | -0.33045 | -0.048002 | 0.42703
| 1930 | -0.42407 | -0.18827 | -0.4564 | -0.25347 | -0.24508 | -0.52157 | -0.13983 | 0.3375 | 0.53859 | 0.67953
| 1931 | 0.054114 | 0.44206 | -0.47588 | 0.60516 | -0.0088895 | -0.22328 | -0.055384 | 0.61103 | 0.18153 | -0.0022525
| 1932 | 0.33856 | -0.32702 | -0.16579 | -0.31641 | -0.84348 | -0.082449 | 0.61051 | -0.51164 | -0.09066 | 0.54956
| 1933 | -0.23286 | 0.72669 | 0.12233 | 0.57257 | -0.028249 | 0.66074 | 0.15946 | 0.33164 | 0.18299 | 0.16928
| 1934 | -0.24827 | 0.20583 | 0.60872 | 0.25697 | -0.055701 | 0.0083852 | 0.17775 | 0.20848 | -0.2256 | -0.056973
| 1935 | 0.092972 | -0.087476 | 0.3956 | -0.3245 | 0.34099 | -0.26727 | 0.63931 | -0.41477 | 0.024551 | -0.34632
| 1936 | 0.31582 | -0.29907 | -0.19694 | -0.41238 | -0.23639 | 0.040365 | -0.024654 | -0.14425 | 0.54426 | -0.52703
| 1937 | 0.12245 | -0.039844 | 0.60314 | -0.28775 | -0.46121 | -0.044019 | 0.44134 | -0.03434 | 0.20495 | 0.39759
| 1938 | 0.31597 | -0.65402 | 0.10462 | -0.6634 | 0.48338 | -0.16042 | -0.64801 | -0.47379 | -0.17217 | 0.4564
| 1939 | 0.33871 | 0.50472 | 0.13565 | 0.38885 | 0.32732 | 0.19371 | 0.063037 | -0.27137 | -0.58251 | 0.049474
| 1940 | 0.13288 | -0.67798 | 0.050737 | -0.4683 | -0.21013 | -0.21814 | 0.64321 | 0.50837 | 0.016689 | 0.164
| 1941 | -0.264 | 0.45475 | 0.011719 | 0.68552 | 0.056549 | -0.22883 | 0.13901 | 0.0012508 | 0.44601 | 0.029897
| 1942 | -0.024244 | -0.010202 | 0.051791 | -0.5721 | 0.097282 | -0.74801 | 0.33464 | 0.12085 | 0.79048 | -0.61699
| 1943 | -0.23823 | -0.20634 | -0.05814 | -0.082122 | -0.59491 | -0.4999 | 0.16567 | -0.12885 | -0.45769 | -0.38153
| 1944 | 0.15923 | -0.1735 | 0.66728 | 0.55335 | 0.16125 | 0.64237 | 0.15804 | 0.31334 | -0.57163 | -0.0014511
| 1945 | 0.30841 | 0.11722 | -0.59913 | -0.14531 | 0.0051633 | 0.1269 | 0.76146 | 0.59838 | 0.36353 | -0.50756
| 1946 | 0.025372 | 0.25388 | -0.42755 | -0.25629 | 0.19012 | -0.57491 | -0.073447 | 0.48473 | -0.28579 | -0.46605
| 1947 | 0.060053 | 0.51369 | 0.014049 | 0.02322 | -0.22586 | 0.071938 | -0.21827 | 0.39246 | 0.40092 | 0.41974
| 1948 | 0.067101 | 0.6349 | 0.46474 | -0.081033 | -0.29169 | 0.73 | 0.7245 | 0.19161 | -0.14765 | -0.47246
| 1949 | 0.18963 | -0.029794 | -0.14496 | -0.47569 | 0.015571 | -0.14918 | 0.00065021 | 0.09165 | -0.23247 | 0.27412
| 1950 | 0.13127 | -0.14965 | 0.5954 | 0.041199 | 0.48029 | 0.79727 | -0.74058 | 0.64886 | -0.19161 | -0.26034
| 1951 | -0.52788 | -0.41 | -0.67396 | -0.17362 | 0.12302 | -0.29282 | 0.40192 | 0.40427 | -0.78622 | 0.31116
| 1952 | 0.45787 | 0.043391 | -0.45255 | -0.62758 | -0.25214 | -0.1634 | -0.16484 | 0.6319 | -0.058353 | 0.22573
| 1953 | -0.37542 | 0.084194 | 0.26904 | -0.39213 | 0.28958 | -0.16856 | 0.19346 | 0.38348 | 0.0028541 | 0.23652
| 1954 | -0.5017 | -0.023322 | -0.038491 | -0.60974 | -0.12006 | 0.52619 | -0.5728 | 0.18214 | -0.12805 | 0.88381
| 1955 | 0.19124 | 0.16928 | 0.3074 | 0.58684 | 0.073879 | -0.40108 | -0.5264 | -0.23574 | -0.82308 | -0.13034
| 1956 | 0.42807 | 0.052846 | 0.53385 | -0.45219 | -0.0075787 | 0.065067 | -0.36826 | 0.22353 | 0.30812 | -0.27069
| 1957 | -0.37558 | -0.15177 | 0.082994 | -0.65956 | 0.20772 | 0.58781 | 0.26454 | -0.37638 | 0.41785 | 0.36905
| 1958 | -0.29141 | 0.33494 | -0.045589 | 0.060798 | -0.21228 | -0.17823 | 0.72742 | -0.54338 | 0.2081 | -0.23221
| 1959 | -0.62198 | -0.4337 | 0.3593 | -0.52031 | -0.067637 | 0.35603 | -0.5141 | -0.64546 | 0.089341 | -0.046323
| 1960 | 0.49078 | -0.050421 | 0.49473 | -0.33932 | 0.31641 | -0.3242 | 0.0063703 | 0.057716 | 0.0037571 | 0.23026
| 1961 | 0.93 | 0.30682 | 0.14519 | 0.18741 | 0.77977 | -0.48629 | -0.40058 | 0.25616 | 0.52936 | 0.18361
| 1962 | -0.4194 | 0.41306 | 0.54558 | -0.066351 | -0.53406 | -0.022094 | -0.31553 | 0.12977 | -0.26836 | 0.74368
| 1963 | -0.12644 | 0.68968 | 0.45972 | -0.55 | -0.6338 | 0.13034 | 0.20458 | 0.26877 | 0.35401 | -0.17036
| 1964 | -0.16531 | -0.083758 | 0.40662 | 0.4997 | -0.37815 | 0.76655 | -0.28355 | 0.64772 | -0.25495 | -0.71138
| 1965 | -0.22611 | 0.56331 | 0.046008 | -0.40544 | 0.3882 | 0.58443 | -0.16771 | -0.10978 | -0.069677 | -0.35883
| 1966 | 0.09099 | -0.096285 | 0.14052 | -0.81642 | 0.41017 | -0.26454 | -0.77707 | -0.31993 | 0.098169 | 0.53859
| 1967 | 0.33796 | -0.20432 | -0.11745 | -0.20445 | 0.20899 | -0.60188 | 0.35278 | -0.20069 | 0.48318 | 0.1418
| 1968 | 0.29822 | 0.062183 | 0.22109 | 0.57233 | -0.28146 | -0.34739 | -0.5011 | 0.083103 | 0.25549 | -0.080598
| 1969 | 0.66459 | 0.064212 | -0.72161 | -0.71069 | -0.061864 | -0.31087 | -0.32806 | -0.63765 | -0.025577 | 0.15082
| 1970 | -0.12427 | -0.56171 | -0.016384 | 0.033822 | -0.97354 | 0.057079 | -0.12427 | -0.16173 | 0.023322 | -0.64321
| 1971 | -0.16615 | -0.11236 | 0.12142 | -0.39098 | 0.061864 | -0.31189 | -0.4776 | -0.35977 | 0.42476 | 0.39395
| 1972 | -0.54558 | -0.55223 | -0.31772 | -0.45714 | 0.44909 | -0.29353 | -0.85067 | -0.023834 | 0.38315 | 0.84157
| 1973 | -0.14824 | 0.35821 | 0.1921 | -0.11756 | -0.27261 | 0.3211 | 0.24112 | 0.16988 | 0.62677 | 0.27069
| 1974 | -0.23796 | 0.061544 | -0.19198 | -0.6233 | -0.35324 | -0.15697 | -0.27069 | -0.32273 | 0.8755 | -0.27274
| 1975 | 0.38657 | 0.0020521 | 0.36636 | 0.62013 | 0.27385 | 0.42112 | -0.022912 | -0.0046609 | 0.54558 | 0.0036567
| 1976 | 0.32169 | 0.1775 | -0.24628 | -0.62865 | 0.19421 | 0.20646 | -0.54273 | 0.3681 | -0.17884 | -0.055701
| 1977 | -0.0029544 | -0.22974 | 0.93755 | 0.25388 | 0.19931 | -0.19235 | -0.080054 | -0.2193 | 0.39395 | -0.37895
| 1978 | 0.35603 | -0.47875 | -0.0018517 | -0.1253 | -0.27206 | -0.75241 | -0.15436 | 0.42703 | 0.49098 | -0.51451
| 1979 | -0.41768 | 0.25899 | -0.32287 | -0.40209 | 0.74485 | 0.17217 | 0.13034 | 0.35556 | -0.18717 | -0.68204
| 1980 | 0.26318 | 0.037555 | -0.31919 | 0.26822 | -0.70318 | 0.05348 | -0.076907 | -0.19049 | -0.024859 | -0.049895
| 1981 | 0.22263 | -0.32258 | 0.070538 | -0.12885 | 0.50634 | -0.58515 | -0.20219 | 0.045589 | -0.24907 | 0.30337
| 1982 | 0.013339 | 0.9272 | 0.21241 | 0.39213 | -0.14099 | -0.39148 | 0.11938 | -0.065174 | -0.1962 | 0.33449
| 1983 | -0.4799 | -0.24495 | 0.56262 | -0.27813 | -0.22058 | 0.14496 | 0.51886 | -0.69619 | 0.20987 | -0.19483
| 1984 | -0.042138 | -0.40561 | 0.21789 | -0.74682 | 0.087476 | 0.29127 | -0.3607 | -0.33479 | 0.19049 | 0.35899
| 1985 | 0.15118 | 0.033512 | 0.072153 | 0.79048 | -0.53535 | 0.27247 | -0.075933 | -0.63517 | 0.34388 | -0.60289
| 1986 | -0.33105 | -0.3294 | -0.66281 | -0.1559 | -0.21827 | -0.352 | -0.38673 | -0.53643 | -0.55335 | -0.47645
| 1987 | 0.027426 | 0.21228 | -0.44511 | 0.63 | 0.085287 | 0.097393 | -0.48687 | 0.24893 | -0.4265 | 0.036621
| 1988 | -0.0042591 | 0.019949 | -0.04538 | -0.40159 | 0.79975 | 0.27233 | 0.17677 | 0.73411 | 0.89183 | 0.57846
| 1989 | -0.047582 | -0.48222 | 0.11915 | -0.097171 | -0.42303 | -0.2431 | -0.077991 | -0.039844 | -0.76655 | 0.20886
| 1990 | 0.31641 | 0.010505 | -0.027323 | -0.8882 | 0.62357 | 0.45898 | 0.45954 | 0.3759 | 0.65547 | -0.34985
| 1991 | -0.18914 | -0.082667 | 0.039635 | 0.082885 | 0.13415 | -0.13253 | -0.43476 | 0.044123 | 0.44116 | 0.46325
| 1992 | 0.13727 | 0.77044 | -0.42737 | -0.77175 | -0.25401 | -0.35649 | 0.1952 | 0.55739 | 0.25147 | -0.85474
| 1993 | 0.17556 | 0.30639 | -0.17933 | 0.06229 | 0.43176 | -0.46962 | 0.039844 | -0.1382 | -0.22948 | -0.21891
| 1994 | -0.15224 | -0.025782 | -0.31524 | 0.38413 | -0.56331 | -0.44746 | 0.0079819 | 0.04538 | 0.54054 | -0.069033
| 1995 | -0.29665 | -0.11903 | 0.4117 | 0.35339 | -0.042869 | -0.32569 | 0.17957 | 0.47094 | 0.47856 | 0.64181
| 1996 | 0.29169 | 0.75322 | 0.0085869 | 0.030825 | 0.015774 | 0.37318 | -0.24178 | -0.39279 | 0.22263 | -0.072153
| 1997 | -0.17193 | -0.34038 | -0.41819 | -0.26549 | 0.098723 | 0.39875 | -0.4999 | -0.75526 | -0.88554 | -0.11994
| 1998 | 0.24099 | 0.78576 | -0.22637 | -0.59863 | -0.44242 | 0.1015 | 0.32287 | -0.76913 | -0.19682 | -0.047477
| 1999 | 0.69259 | -0.29353 | -0.41119 | 0.27027 | -0.01263 | -0.40192 | 0.65897 | 0.28916 | 0.66608 | 0.5224
| 2000 | 0.27647 | -0.57116 | 0.078425 | -0.95204 | 0.03465 | 0.76527 | 0.51082 | 0.42424 | 0.19669 | 0.32955
| 2001 | -0.47971 | 0.76612 | 0.16651 | 0.32598 | 0.39296 | 0.46437 | -0.36478 | -0.35852 | 0.60013 | 0.21584
| 2002 | -0.73261 | -0.63435 | -0.10865 | 0.54098 | -0.50837 | -0.40025 | 0.1082 | -0.59441 | 0.43564 | -0.35479
| 2003 | 0.81318 | 0.21266 | 0.022503 | -0.47076 | -0.8937 | -0.36164 | -0.29099 | -0.026809 | 0.65605 | 0.39345
| 2004 | 0.028455 | 0.35712 | -0.83538 | -0.45917 | -0.0060684 | -0.27757 | -0.079946 | 0.2504 | 0.32317 | -0.75201
| 2005 | 0.2488 | 0.2598 | 0.66549 | 0.04099 | -0.26918 | 0.14285 | -0.68615 | -0.38056 | -0.12404 | 0.056337
| 2006 | 0.40092 | 0.046428 | 0.028661 | -0.66192 | -0.40125 | -0.32955 | 0.14099 | -0.43884 | -0.56514 | 0.59515
| 2007 | -0.27137 | -0.52661 | 0.73675 | 0.45843 | 0.73186 | 0.58251 | 0.15851 | -0.3312 | 0.66429 | 0.13843
| 2008 | 0.42895 | -0.043496 | -0.24987 | -0.46755 | 0.50614 | -0.45714 | 0.76698 | -0.086381 | 0.62597 | 0.053374
| 2009 | 0.50251 | -0.34342 | 0.72341 | 0.31029 | 0.25133 | -0.71242 | -0.21038 | 0.2733 | -0.66162 | -0.9078
| 2010 | -0.42009 | -0.62892 | 0.074311 | -0.79482 | 0.01486 | -0.81053 | 0.26932 | -0.2175 | 0.65722 | 0.16472
| 2011 | -0.057185 | 0.15875 | -0.12805 | 0.32494 | 0.12622 | -0.0922 | 0.68267 | 0.083539 | -0.059628 | 0.25495
| 2012 | 0.45567 | -0.46418 | 0.55559 | 0.2516 | -0.21814 | 0.20294 | -0.72378 | 0.0038574 | 0.4902 | 0.01344
| 2013 | -0.35169 | -0.52073 | -0.36353 | 0.13866 | 0.36494 | 0.28901 | -0.23156 | -0.91225 | 0.62224 | -0.20382
| 2014 | 0.24389 | -0.23078 | 0.24138 | -0.18018 | 0.05496 | -0.91 | -0.68807 | 0.46269 | -0.4279 | -0.27453
| 2015 | -0.61777 | 0.2948 | -0.92319 | -0.064212 | -0.43105 | 0.34038 | -0.25441 | -0.07 | -0.52408 | 0.31993
| 2016 | -0.37334 | -0.39825 | 0.0911 | -0.13588 | -0.8618 | 0.096396 | -0.54011 | -0.31524 | -0.87155 | 0.21789
| 2017 | 0.35479 | -0.49177 | -0.89656 | 0.41357 | -0.54404 | 0.051897 | 0.47322 | -0.67304 | 0.76063 | -0.22676
| 2018 | 0.66429 | 0.26237 | -0.71277 | 0.71 | 0.14274 | -0.82824 | 0.080924 | -0.70285 | 0.11248 | 0.2791
| 2019 | 0.10094 | 0.41357 | -0.5143 | -0.57397 | 0.049474 | -0.18397 | 0.3087 | 0.33404 | -0.12279 | -0.19223
| 2020 | -0.27509 | 0.068711 | -0.066565 | 0.66489 | 0.82084 | 0.22987 | 0.50898 | -0.023732 | 0.1245 | -0.44152
| 2021 | -0.31802 | 0.0995 | -0.13855 | -0.13983 | 0.75322 | -0.75772 | -0.58299 | -0.25777 | -0.65663 | 0.13288
| 2022 | -0.45328 | 0.39925 | -0.86036 | 0.25307 | -0.0032553 | -0.40848 | 0.079185 | -0.02897 | 0.0075787 | 0.7881
| 2023 | -0.18951 | -0.75526 | -0.065816 | 0.020153 | 0.69357 | 0.25643 | 0.43352 | -0.20672 | 0.070645 | 0.080163
| 2024 | -0.95204 | -0.12427 | -0.1044 | -0.60188 | 0.1425 | -0.13438 | 0.049579 | 0.94804 | 0.21917 | 0.17495
| 2025 | -0.23013 | -0.079511 | -0.1758 | -0.16964 | 0.69129 | 0.41802 | 0.43211 | -0.079511 | 0.17157 | 0.28118
| 2026 | 0.22418 | -0.15804 | 0.021072 | 0.063357 | -0.057822 | 0.42233 | -0.21891 | 0.14847 | -0.016384 | -0.058246
| 2027 | -0.19969 | -0.82941 | -0.46624 | -0.30322 | 0.79095 | 0.03 | 0.046638 | -0.7687 | 0.58976 | -0.15
| 2028 | 0.56148 | 0.18704 | -0.18753 | 0.1382 | -0.71911 | -0.67366 | 0.068711 | -0.59763 | 0.15887 | -0.15295
| 2029 | 0.073447 | -0.49731 | 0.31597 | 0.030206 | -0.33902 | 0.29042 | -0.46943 | 0.44547 | -0.1127 | -0.67396
| 2030 | -0.068067 | 0.095732 | -0.58636 | -0.16675 | 0.034133 | -0.66879 | -0.23705 | 0.63108 | 0.69129 | -0.78436
| 2031 | 0.25067 | 0.19111 | 0.31145 | -0.35077 | -0.25227 | -0.10731 | -0.026501 | -0.10989 | 0.13023 | 0.4542
| 2032 | 0.082667 | 0.62437 | -0.73486 | 0.35541 | -0.27055 | -0.27688 | 0.029382 | -0.53707 | -0.68679 | -0.06914
| 2033 | 0.11067 | 0.13299 | 0.47837 | 0.45127 | -0.012427 | 0.36731 | 0.084959 | 0.94084 | 0.36921 | 0.09033
| 2034 | 0.048527 | 0.022503 | -0.10507 | 0.88554 | 0.12473 | -0.2773 | -0.6637 | 0.22289 | 0.16149 | -0.25939
| 2035 | 0.13924 | -0.033305 | -0.026296 | 0.5714 | 0.16018 | -0.69817 | 0.34708 | -0.83783 | -0.09209 | -0.22987
| 2036 | -0.12154 | -0.12622 | 0.51906 | -0.019031 | -0.13276 | 0.16531 | 0.27261 | 0.010202 | -0.73074 | -0.028661
| 2037 | 0.19632 | -0.092311 | 0.78716 | 0.32243 | -0.30581 | 0.30913 | 0.53794 | -0.066565 | -0.22006 | 0.0092932
| 2038 | 0.29042 | -0.42407 | -0.37734 | -0.5005 | -0.36447 | 0.37079 | -0.99 | -0.4859 | 0.099611 | 0.081577
| 2039 | -0.20094 | -0.31699 | -0.7735 | 0.32554 | -0.24072 | -0.38738 | -0.057822 | -0.1315 | 0.52788 | -0.15935
| 2040 | -0.20975 | 0.72486 | 0.66909 | -0.43246 | 0.17641 | -0.5201 | 0.62463 | -0.57703 | 0.2567 | 0.06261
| 2041 | -0.072692 | -0.21521 | 0.12977 | -0.15472 | 0.69685 | -0.40142 | -0.10028 | -0.16892 | -0.32228 | -0.38494
| 2042 | -0.27896 | -0.056973 | 0.76698 | 0.15531 | 0.36984 | -0.34144 | -0.30136 | -0.66909 | 0.14847 | 0.15602
| 2043 | -0.29964 | 0.48551 | 0.24165 | 0.3087 | -0.15697 | 0.26441 | -0.084959 | -0.31058 | 0.21317 | -0.63931
| 2044 | 0.13634 | 0.21917 | 0.12279 | -0.61077 | 0.49691 | 0.34083 | 0.18275 | 0.17933 | -0.7184 | -0.25885
| 2045 | -0.047897 | 0.093744 | 0.45328 | 0.32866 | 0.1814 | 0.44009 | -0.57421 | -0.79336 | 0.12851 | -0.041407
| 2046 | -0.20382 | -0.13785 | -0.12943 | -0.20031 | 0.048107 | -0.003155 | 0.56331 | -0.70117 | 0.33479 | -0.22392
| 2047 | 0.95 | 0.64181 | -0.60389 | -0.54185 | -0.15519 | 0.57964 | -0.61803 | 0.37064 | 0.21215 | 0.047897
| 2048 | -0.1957 | -0.089121 | 0.74801 | 0.55245 | 0.4859 | -0.45109 | 0.054749 | 0.067959 | -0.4134 | 0.52303
| 2049 | 0.43352 | -0.17726 | -0.45292 | 0.39626 | 0.35062 | 0.77395 | 0.55649 | 0.040677 | -0.11631 | 0.16268
| 2050 | -0.41272 | 0.12199 | -0.67366 | -0.082667 | 0.30423 | -0.73261 | -0.081577 | -0.32583 | 0.6257 | -0.57374
| 2051 | -0.057822 | 0.096507 | -0.19322 | -0.59813 | 0.21013 | -0.19744 | -0.41871 | 0.085068 | 0.3477 | -0.70623
| 2052 | -0.61231 | -0.23013 | 0.39312 | 0.58107 | -0.18594 | 0.10753 | 0.37382 | 0.14742 | 0.20861 | -0.44529
| 2053 | 0.29779 | -0.34816 | 0.73486 | 0.82308 | -0.074095 | 0.54163 | -0.43423 | 0.6162 | 0.56814 | -0.16054
| 2054 | 0.27938 | 0.18877 | -0.13449 | 0.17326 | 0.87712 | 0.010707 | 0.54229 | 0.70623 | -0.4983 | -0.41017
| 2055 | -0.47703 | 0.11507 | -0.17326 | -0.51287 | -0.58612 | 0.10776 | 0.66251 | 0.51205 | 0.094406 | 0.54163
| 2056 | -0.7015 | -0.39892 | 0.58515 | 0.27412 | 0.023117 | -0.48164 | -0.37064 | 0.06261 | 0.23104 | -0.55966
| 2057 | 0.4417 | -0.72054 | -0.4985 | -0.11157 | 0.10217 | -0.57163 | -0.6382 | -0.1603 | -0.3309 | 0.28677
| 2058 | -0.14052 | 0.2516 | -0.27757 | 0.72669 | 0.22637 | -0.032994 | 0.15626 | -0.025988 | 0.46568 | 0.20332
| 2059 | -0.084085 | 0.12679 | 0.71946 | 0.24973 | -0.17411 | -0.14507 | 0.24987 | -0.42633 | 0.45273 | 0.039427
| 2060 | 0.36196 | 0.37127 | 0.23652 | 0.23169 | 0.15141 | -0.061224 | 0.22663 | -0.2755 | -0.13415 | 0.22444
| 2061 | 0.40898 | -0.1786 | -0.29779 | -0.34724 | 0.2598 | 0.3366 | -0.53021 | -0.036517 | 0.44782 | 0.085068
| 2062 | -0.041199 | 0.67304 | -0.16627 | -0.44837 | -0.30696 | 0.023732 | 0.25535 | -0.25885 | -0.15306 | -0.82824
| 2063 | -0.018216 | 0.29694 | -0.14309 | 0.62251 | 0.35525 | 0.1308 | -0.19881 | -0.20848 | 0.13196 | -0.068603
| 2064 | -0.20583 | 0.62171 | 0.18263 | -0.3796 | -0.70794 | -0.43813 | 0.62384 | 0.19433 | 0.39115 | 0.56171
| 2065 | -0.35448 | -0.21114 | 0.095401 | 0.3851 | -0.5098 | 0.4426 | -0.79384 | 0.58227 | 0.74135 | -0.018318
| 2066 | 0.13253 | -0.067208 | 0.03579 | -0.46943 | 0.026707 | -0.67396 | -0.37111 | 0.14824 | -0.69065 | 0.40949
| 2067 | 0.42528 | -0.27123 | -0.74212 | -0.29665 | -0.085396 | 0.0173 | 0.58107 | -0.74643 | -0.5347 | -0.45972
| 2068 | 0.44964 | -0.019847 | 0.015571 | 0.82196 | 0.91693 | -0.28705 | -0.36086 | 0.063357 | -0.7245 | -0.3294
| 2069 | -0.28789 | -0.028867 | -0.48668 | 0.016588 | 0.52177 | 0.34053 | -0.85613 | 0.25804 | -0.78483 | -0.37366
| 2070 | -0.088902 | 0.13542 | -0.60592 | -0.12347 | -0.035065 | -0.29367 | 0.41494 | 0.64321 | 0.62437 | -0.12931
| 2071 | -0.69784 | 0.46028 | -0.085506 | -0.17896 | -0.12085 | 0.06293 | 0.49354 | -0.57 | 0.56148 | -0.28063
| 2072 | 0.049158 | 0.10832 | 0.39593 | 0.36937 | 0.14145 | -0.19012 | 0.021072 | 0.79925 | 0.51823 | -0.19782
| 2073 | 0.44728 | -0.18055 | 0.07183 | -0.19744 | 0.035479 | 0.27647 | -0.62597 | 0.57798 | 0.552 | -0.10518
| 2074 | 0.7492 | -0.72779 | 0.078534 | -0.093523 | 0.78436 | 0.24814 | -0.25347 | -0.36415 | 0.19 | 0.19894
| 2075 | -0.05348 | 0.081469 | 0.63244 | -0.60063 | 0.31305 | -0.27605 | 0.41665 | 0.36747 | 0.52957 | 0.32081
| 2076 | 0.87631 | -0.27082 | 0.11067 | 0.2733 | 0.55223 | -0.58251 | 0.2278 | -0.87958 | -0.51492 | 0.59318
| 2077 | 0.083539 | 0.36526 | -0.40848 | 0.81862 | -0.51865 | 0.11552 | 0.35031 | -0.02281 | -0.83599 | -0.64097
| 2078 | 0.78436 | -0.35634 | -0.17314 | -0.35852 | -0.05984 | 0.72125 | 0.70117 | 0.13184 | 0.44045 | 0.18618
| 2079 | -0.032271 | 0.57468 | -0.77262 | -0.73942 | -0.5608 | 0.16424 | 0.71452 | 0.21533 | 0.19408 | 0.58515
| 2080 | -0.031961 | -0.18532 | 0.6637 | -0.20382 | -0.44583 | 0.81972 | -0.15555 | -0.25764 | -0.20131 | -0.37111
| 2081 | 0.36541 | 0.30899 | 0.13519 | 0.23613 | -0.24588 | 0.36478 | 0.19272 | -0.15035 | -0.56491 | -0.041094
| 2082 | 0.65839 | -0.14812 | 0.41716 | 0.99 | -0.088134 | -0.30164 | -0.39842 | 0.58587 | 0.6077 | 0.5013
| 2083 | -0.64886 | -0.028249 | -0.18692 | 0.17726 | -0.71946 | 0.22818 | -0.28007 | -0.18324 | 0.18459 | 0.17338
| 2084 | 0.41905 | -0.58515 | -0.37095 | 0.33015 | -0.4801 | -0.89276 | 0.037451 | -0.36921 | 0.15804 | 0.44909
| 2085 | -0.89091 | 0.41408 | -0.62758 | -0.10072 | 0.17241 | -0.56514 | -0.14859 | -0.20131 | 0.020051 | -0.24694
| 2086 | 0.09518 | -0.31451 | 0.16868 | 0.68936 | -0.21419 | 0.60113 | 0.20634 | -0.29381 | -0.3451 | -0.16543
| 2087 | -0.031135 | 0.25791 | 0.055913 | -0.58083 | 0.06229 | 0.23941 | 0.16988 | 0.63517 | 0.1952 | -0.24231
| 2088 | -0.57703 | 0.11972 | 0.79482 | -0.14484 | -0.79826 | 0.5019 | 0.31904 | -0.089231 | 0.68235 | -0.75772
| 2089 | -0.1315 | -0.35231 | 0.22315 | -0.4981 | -0.68807 | -0.0018517 | -0.44475 | -0.61699 | -0.5693 | -0.31875
| 2090 | 0.40831 | 0.25482 | -0.63408 | -0.77218 | 0.19185 | -0.31422 | -0.12154 | -0.05158 | -0.25643 | -0.14145
| 2091 | 0.031754 | 0.15626 | 0.29197 | 0.61803 | 0.41974 | 0.15875 | -0.025064 | 0.39461 | 0.54778 | 0.14076
| 2092 | -0.75813 | -0.48707 | 0.41204 | 0.19545 | -0.54229 | -0.21432 | 0.056125 | -0.58781 | 0.30957 | -0.0781
| 2093 | 0.45861 | -0.10273 | -0.15354 | 0.8148 | -0.28607 | -0.95417 | 0.28327 | 0.23417 | 0.45898 | 0.45091
| 2094 | 0.16603 | 0.72341 | -0.13011 | 0.15413 | 0.2625 | 0.40142 | 0.348 | 0.031031 | -0.078642 | 0.40225
| 2095 | -0.32806 | 0.10429 | 0.40949 | 0.08978 | -0.58036 | 0.68743 | 0.50857 | 0.25912 | 0.42703 | 0.23915
| 2096 | 0.1706 | -0.7015 | -0.1015 | -0.19682 | -0.55717 | -0.5728 | -0.35961 | 0.56768 | -0.86847 | -0.31685
| 2097 | -0.66015 | 0.21 | 0.58976 | 0.15887 | 0.26904 | 0.18569 | 0.23456 | -0.52555 | 0.29993 | 0.0038574
| 2098 | 0.09209 | -0.28845 | 0.7005 | -0.99 | -0.40865 | 0.096064 | 0.24614 | 0.34311 | -0.50715 | 0.21343
| 2099 | -0.38934 | -0.23417 | 0.80125 | 0.88467 | 0.68807 | 0.64014 | 0.081469 | 0.18717 | -0.448 | 0.53492
| 2100 | 0.46456 | 0.011213 | 0.45622 | 0.73186 | -0.1879 | 0.12736 | -0.61777 | 0.43813 | -0.70862 | 0.59122
| 2101 | -0.19099 | -0.30595 | 0.21203 | -0.56954 | -0.12496 | 0.81372 | 0.097503 | -0.12382 | 0.51369 | -0.27827
| 2102 | -0.66133 | -0.12541 | -0.093413 | 0.18299 | 0.049369 | 0.0048618 | -0.27495 | 0.097393 | 0.79678 | 0.040469
| 2103 | -0.12336 | -0.20081 | -0.74096 | 0.6697 | -0.57047 | -0.0066723 | 0.33374 | 0.15212 | -0.53902 | -0.42095
| 2104 | -0.20319 | -0.13057 | -0.53 | -0.15012 | 0.35992 | 0.23915 | 0.68047 | -0.38902 | 0.91815 | -0.82651
| 2105 | 0.1253 | 0.037659 | -0.14718 | -0.36384 | -0.37286 | 0.2398 | -0.32243 | -0.29864 | -0.10384 | 0.19495
| 2106 | -0.00055015 | -0.30711 | 0.73111 | 0.41187 | -0.16232 | -0.2602 | -0.10966 | -0.46793 | -0.40008 | -0.43193
| 2107 | 0.83417 | -0.095069 | -0.4983 | -0.1063 | -0.4307 | -0.38105 | -0.17133 | -0.18459 | -0.33164 | 0.91456
| 2108 | -0.8043 | -0.60491 | -0.34053 | -0.045904 | -0.47971 | -0.39197 | 0.42476 | 0.13322 | -0.56285 | 0.36526
| 2109 | 0.1769 | -0.078859 | -0.21215 | 0.46849 | -0.040677 | -0.007075 | -0.039427 | 0.28453 | -0.73373 | 0.39942
| 2110 | 0.41 | 0.37286 | 0.22831 | 0.24429 | 0.13173 | -0.029485 | 0.023322 | -0.15165 | 0.52745 | -0.32509
| 2111 | 0.33524 | 0.23757 | -0.16352 | 0.42615 | 0.048317 | 0.2773 | 0.1466 | -0.364 | 0.40763 | 0.27467
| 2112 | -0.2343 | 0.5001 | -0.36415 | 0.10675 | 0.16916 | 0.23469 | 0.060053 | -0.36683 | -0.33149 | 0.94615
| 2113 | -0.7184 | -0.73074 | 0.2161 | -0.6697 | -0.48824 | 0.68361 | -0.084304 | -0.13924 | 0.44277 | 0.4337
| 2114 | 0.080163 | -0.25926 | 0.059521 | -0.099389 | -0.099056 | 0.44837 | 0.34342 | -0.63792 | -0.37398 | -0.14953
| 2115 | -0.50472 | 0.75896 | -0.4117 | 0.3882 | -0.70285 | -0.27371 | -0.039635 | -0.64602 | -0.064639 | -0.66939
| 2116 | -0.35914 | 0.5866 | -0.0064709 | 0.83969 | -0.73981 | 0.50472 | 0.13496 | -0.018623 | -0.093082 | 0.38251
| 2117 | -0.11564 | 0.17229 | -0.9272 | -0.88381 | 0.092421 | -0.32066 | 0.8043 | 0.44511 | -0.26088 | 0.34464
| 2118 | 0.15899 | -0.052635 | 0.70828 | -0.19173 | -0.37895 | -0.36589 | -0.57047 | -0.43246 | -0.91693 | -0.57656
| 2119 | -0.19994 | -0.38543 | -0.72054 | -0.48629 | -0.16856 | -0.45237 | 0.46962 | 0.67213 | 0.045484 | -0.23849
| 2120 | -0.38299 | 0.83599 | 0.18975 | 0.089012 | 0.53492 | 0.1634 | 0.035479 | 0.39477 | 0.93144 | -0.23967
| 2121 | -0.40209 | 0.87233 | -0.55335 | 0.27453 | -0.1921 | -0.41836 | 0.22987 | -0.021481 | -0.24138 | -0.030516
| 2122 | -0.38984 | 0.27495 | 0.32851 | 0.35805 | -0.092311 | 0.56148 | -0.4426 | 0.59122 | -0.12085 | 0.78529
| 2123 | 0.26863 | 0.41442 | -0.53924 | -0.15071 | -0.32509 | 0.30581 | 0.1814 | -0.33509 | 0.14064 | 0.5663
| 2124 | -0.083976 | -0.28509 | 0.20886 | 0.43617 | 0.013846 | -0.87155 | 0.28285 | -0.13496 | 0.31743 | -0.59417
| 2125 | 0.05348 | 0.72269 | 0.57774 | -0.72197 | -0.15283 | 0.32569 | 0.28355 | 0.025885 | -0.027118 | 0.068818
| 2126 | -0.11056 | 0.25737 | 0.1389 | 0.046952 | -0.23378 | -0.57303 | -0.15709 | -0.064853 | -0.1952 | -0.45036
| 2127 | -0.013238 | 0.05814 | 0.094959 | -0.41494 | 0.25401 | -0.74564 | 0.71557 | 0.033512 | -0.70285 | 0.023629
| 2128 | -0.17459 | -0.49453 | -0.75282 | 0.09143 | 0.17653 | 0.2356 | -0.49236 | -0.16976 | 0.32066 | 0.051686
| 2129 | -0.31189 | 0.58563 | -0.32643 | 0.24614 | 0.19297 | -0.39576 | 0.19471 | -0.17677 | 0.42078 | -0.4041
| 2130 | 0.23378 | 0.46943 | -0.2975 | 0.23521 | -0.19956 | -0.64886 | 0.098058 | 0.20823 | -0.77841 | 0.88295
| 2131 | -0.4981 | -0.0027538 | 0.16185 | 0.11326 | 0.1775 | 0.54889 | 0.40561 | 0.30986 | -0.36415 | -0.69259
| 2132 | -0.057503 | -0.025372 | -0.20836 | -0.5224 | 0.47417 | -0.65258 | 0.2907 | 0.094627 | -0.1603 | 0.148
| 2133 | 0.30928 | -0.14041 | 0.28439 | 0.18116 | -0.020051 | -0.11835 | -0.09099 | -0.79531 | 0.43246 | -0.2571
| 2134 | 0.022094 | -0.83357 | -0.77932 | 0.27165 | 0.11575 | 0.35649 | 0.092531 | -0.35231 | 0.42164 | -0.81972
| 2135 | -0.11972 | -0.47455 | 0.52873 | 0.17811 | 0.31058 | -0.035998 | -0.71208 | -0.050737 | -0.15259 | 0.45548
| 2136 | -0.14953 | -0.26536 | -0.081251 | 0.29622 | -0.2722 | 0.24257 | 0.5019 | -0.029485 | -0.39098 | -0.11
| 2137 | 0.34954 | -0.77306 | 0.76272 | 0.17665 | 0.9078 | -0.10944 | 0.09839 | 0.0069743 | 0.011112 | 0.41716
| 2138 | -0.51164 | -0.085178 | 0.26427 | -0.05422 | -0.25455 | 0.23234 | -0.18877 | -0.82139 | 0.8739 | 0.4471
| 2139 | -0.72742 | -0.12051 | -0.25053 | -0.59392 | 0.089231 | -0.18263 | -0.15354 | 0.5005 | 0.19284 | -0.35836
| 2140 | 0.22482 | -0.10843 | 0.042973 | 0.45091 | -0.40142 | -0.73981 | 0.27938 | 0.16221 | 0.11293 | -0.20094
| 2141 | -0.00065021 | 0.38121 | -0.43902 | 0.79776 | 0.076041 | 0.4826 | -0.31043 | 0.01415 | 0.136 | -0.023527
| 2142 | -0.38186 | -0.56148 | 0.72963 | -0.33329 | 0.86399 | -0.66758 | -0.21177 | -0.21432 | 0.17641 | -0.5714
| 2143 | 0.64829 | -0.24402 | 0.45127 | 0.29765 | 0.70386 | -0.16496 | 0.46887 | -0.19198 | -0.4194 | 0.37992
| 2144 | -0.038907 | -0.058884 | 0.056655 | -0.4857 | 0.35836 | -0.17338 | -0.13161 | 0.48882 | -0.14309 | 0.10028
| 2145 | -0.71 | 0.2722 | 0.38348 | -0.7839 | 0.36826 | 0.016486 | 0.4668 | -0.10418 | -0.3061 | 0.27827
| 2146 | -0.55582 | -0.5583 | 0.081033 | 0.17229 | -0.10944 | 0.22058 | -0.84094 | 0.14437 | 0.33449 | 0.42493
| 2147 | 0.6995 | -0.15543 | -0.10596 | -0.34555 | -0.30957 | -0.32524 | -0.27702 | -0.48785 | 0.56606 | -0.14064
| 2148 | 0.42511 | 0.3211 | 0.62463 | 0.6995 | -0.14835 | 0.30509 | -0.33464 | 0.49394 | -0.17641 | -0.53859
| 2149 | 0.58036 | 0.71522 | 0.036309 | 0.42563 | 0.53427 | -0.31145 | 0.012731 | -0.8043 | -0.26863 | 0.37718
| 2150 | 0.078968 | 0.065174 | 0.96394 | -0.48746 | 0.27495 | 0.27467 | 0.37127 | 0.2755 | 0.061757 | -0.045799
| 2151 | 0.1694 | 0.44152 | 0.30942 | 0.86252 | -0.53946 | 0.79288 | 0.84348 | 0.13288 | -0.17145 | 0.24217
| 2152 | -0.24508 | 0.11496 | 0.13948 | -0.36857 | -0.26604 | -0.50796 | -0.12484 | -0.36652 | -0.16988 | 0.66638
| 2153 | 0.50939 | 0.48687 | -0.099056 | 0.10955 | -0.38202 | 0.50231 | -0.033718 | 0.016689 | 0.10161 | -0.36889
| 2154 | -0.39411 | 0.25067 | 0.15295 | -0.56468 | -0.71104 | -0.10184 | 0.11994 | -0.36573 | -0.7881 | -0.76913
| 2155 | 0.27096 | 0.00095045 | 0.87958 | 0.4531 | -0.80687 | -0.30021 | -0.62013 | -0.3537 | 0.66074 | -0.94804
| 2156 | 0.48376 | -0.51927 | -0.27069 | -0.033201 | -0.62013 | -0.038491 | 0.37783 | -0.63135 | 0.44674 | 0.24469
| 2157 | 0.4392 | -0.61961 | 0.031857 | 0.26522 | -0.0076795 | 0.54756 | 0.41579 | 0.10418 | -0.048107 | 0.24442
| 2158 | -0.033718 | -0.30122 | -0.016588 | 0.69652 | 0.079185 | 0.16988 | -0.8148 | -0.075176 | -0.48067 | 0.069677
| 2159 | 0.14777 | -0.3303 | -0.25656 | -0.09033 | -0.26156 | -0.55312 | 0.42842 | -0.17374 | 0.59466 | 0.64518
| 2160 | -0.44746 | -0.11881 | 0.85269 | 0.20735 | 0.40966 | -0.14087 | -0.23208 | 0.11801 | 0.25629 | -0.066458
| 2161 | 0.19944 | 0.32361 | 0.10753 | -0.39477 | -0.30036 | 0.53192 | 0.058671 | -0.029279 | 0.28733 | -0.79482
| 2162 | 0.28453 | 0.28425 | -0.048317 | -0.066244 | 0.31261 | -0.51266 | 0.097614 | 0.7492 | -0.018827 | 0.56814
| 2163 | -0.34969 | 0.016994 | 0.26713 | 0.69422 | -0.30826 | -0.31655 | -0.35308 | 0.25361 | 0.19732 | -0.033098
| 2164 | 0.046113 | -0.38836 | 0.38024 | -0.17012 | 0.63792 | -0.75813 | 0.16089 | -0.14052 | 0.77131 | -0.16807
| 2165 | 0.43902 | 0.70521 | -0.23443 | 0.33105 | 0.46906 | -0.041825 | 0.32361 | -0.42877 | -0.59639 | 0.67581
| 2166 | 0.35031 | -0.77617 | -0.054643 | -0.050316 | -0.12679 | -0.60795 | 0.24787 | -0.036309 | 0.78763 | 0.16603
| 2167 | -0.093082 | -0.25414 | 0.67922 | 0.34739 | 0.50573 | -0.30928 | 0.42009 | 0.13334 | -0.081795 | -0.032167
| 2168 | -0.32836 | 0.39016 | -0.45714 | -0.72742 | -0.46158 | 0.13011 | 0.010303 | 0.71982 | -0.34494 | 0.074635
| 2169 | -0.62384 | 0.23013 | 0.55044 | 0.63108 | -0.25107 | 0.4983 | 0.06229 | -0.031031 | 0.063677 | -0.095401
| 2170 | 0.7496 | 0.62145 | -0.41648 | 0.17896 | 0.26345 | 0.32376 | 0.29936 | 0.61961 | 0.26509 | 0.41289
| 2171 | 0.18988 | 0.039115 | 0.49512 | -0.16831 | 0.72125 | -0.24853 | -0.28649 | 0.1921 | 0.23286 | 0.14601
| 2172 | -0.44638 | 0.15295 | -0.17605 | 0.080707 | -0.087695 | -0.43653 | 0.42772 | -0.39543 | -0.22199 | -0.049474
| 2173 | -0.023732 | 0.38153 | -0.58757 | -0.43352 | -0.029279 | -0.42112 | 0.21572 | -0.69488 | 0.097393 | 0.74643
| 2174 | -0.0072765 | 0.01344 | -0.77218 | 0.52387 | -0.09088 | 0.67519 | -0.25374 | -0.52429 | 0.52513 | 0.34724
| 2175 | 0.37815 | 0.72054 | -0.17884 | -0.003155 | -0.17811 | 0.57116 | -0.083758 | -0.049789 | -0.34266 | 0.65229
| 2176 | -0.552 | 0.31772 | 0.030722 | -0.29509 | 0.086928 | -0.09165 | -0.85 | 0.25953 | -0.1389 | -0.27398
| 2177 | 0.82479 | 0.5693 | -0.018827 | 0.82708 | -0.39444 | 0.33886 | 0.58443 | -0.016486 | -0.15875 | -0.64687
| 2178 | 0.30769 | -0.46962 | -0.14812 | -0.56308 | 0.41187 | 0.12256 | -0.26101 | -0.29042 | -0.28691 | 0.13034
| 2179 | -0.38967 | -0.21228 | -0.74174 | 0.7687 | 0.27123 | -0.099167 | 0.82028 | 0.52052 | -0.35247 | -0.60263
| 2180 | 0.28859 | 0.67829 | -0.075176 | 0.23731 | 0.069355 | 0.64321 | -0.46083 | -0.034547 | -0.40645 | -0.05422
| 2181 | 0.3743 | 0.52261 | -0.50857 | 0.36353 | -0.37686 | -0.2941 | 0.27979 | 0.64377 | -0.41477 | 0.43813
| 2182 | -0.021276 | -0.10128 | 0.16364 | -0.084304 | -0.27453 | 0.025167 | 0.64886 | 0.64744 | -0.4408 | 0.80687
| 2183 | 0.38413 | 0.38951 | -0.57822 | -0.077449 | 0.58757 | -0.77262 | 0.050948 | -0.39892 | -0.37191 | -0.020459
| 2184 | 0.26563 | 0.63435 | 0.33045 | -0.34235 | 0.81106 | -0.0043595 | 0.45861 | 0.74682 | 0.10675 | -0.52979
| 2185 | 0.78952 | -0.098945 | 0.89656 | 0.4426 | 0.02281 | 0.59073 | 0.12427 | 0.33977 | -0.58083 | 0.00085036
| 2186 | 0.1109 | 0.21177 | 0.2773 | 0.43564 | -0.53363 | 0.25147 | -0.29893 | 0.24707 | -0.43546 | 0.43777
| 2187 | 0.40814 | -0.84094 | 0.19062 | 0.17459 | -0.025064 | 0.12977 | 0.011921 | -0.61908 | -0.13299 | 0.21725
| 2188 | -0.78529 | -0.0073772 | -0.1237 | -0.051159 | 0.15887 | -0.025372 | 0.1375 | 0.51886 | 0.43193 | 0.018522
| 2189 | 0.04381 | 0.077016 | 0.096175 | 0.28621 | 0.058884 | 0.0012508 | 0.44909 | 0.35494 | 0.76104 | 0.48183
| 2190 | 0.13161 | 0.75813 | 0.2516 | 0.31963 | -0.16531 | 0.009798 | 0.12154 | -0.022503 | -0.095954 | -0.24099
| 2191 | 0.1797 | 0.54338 | 0.22212 | -0.072369 | 0.5283 | -0.11101 | -0.095622 | 0.3923 | 0.72963 | -0.058565
| 2192 | -0.94804 | -0.067745 | -0.57116 | -0.29311 | -0.32199 | 0.046218 | 0.248 | 0.1758 | -0.3454 | 0.78858
| 2193 | -0.5347 | 0.048948 | -0.94804 | 0.48029 | -0.10239 | -0.19161 | -0.063891 | 0.21827 | 0.80584 | 0.80791
| 2194 | 0.14566 | -0.020663 | 0.040886 | -0.063998 | -0.60364 | 0.11045 | -0.62039 | -0.17411 | -0.0922 | 0.77617
| 2195 | -0.014353 | 0.37526 | -0.19794 | -0.34601 | 0.20735 | 0.35821 | -0.072908 | -0.012832 | -0.068711 | -0.65114
| 2196 | -0.73637 | -0.6241 | 0.57798 | 0.1245 | 0.30552 | 0.63848 | 0.33269 | -0.15247 | 0.38218 | 0.29651
| 2197 | 0.49612 | -0.3923 | 0.37654 | 0.46213 | 0.22071 | -0.15709 | 0.055807 | -0.11225 | -0.67366 | -0.31073
| 2198 | 0.0018517 | 0.20495 | -0.37815 | 0.024141 | 0.072584 | 0.018216 | 0.40729 | 0.83783 | 0.020663 | -0.24349
| 2199 | -0.084304 | -0.72889 | 0.60694 | 0.054008 | -0.14192 | 0.50271 | -0.55402 | -0.85 | 0.26318 | -0.088134
| 2200 | -0.85543 | -0.36747 | 0.37079 | -0.19657 | -0.26808 | 0.041303 | -0.45182 | -0.66549 | -0.1578 | 0.12656
| 2201 | -0.0032553 | -0.72523 | -0.26536 | 0.23574 | 0.3372 | -0.49 | -0.24973 | -0.1253 | -0.20709 | -0.048843
| 2202 | -0.77662 | 0.14274 | 0.26563 | 0.72414 | 0.35789 | -0.51595 | 0.09706 | 0.0055655 | 0.30007 | -0.072369
| 2203 | 0.030825 | -0.89276 | 0.64631 | 0.033201 | -0.30783 | -0.15828 | -0.88642 | -0.60872 | 0.10776 | 0.77439
| 2204 | -0.27965 | 0.91456 | -0.026398 | 0.47474 | 0.098501 | 0.23639 | 0.46083 | 0.11067 | 0.56354 | 0.20382
| 2205 | 0.55762 | -0.48512 | 0.17399 | -0.72963 | 0.79628 | -0.037971 | 0.51699 | -0.19545 | -0.057503 | -0.0041586
| 2206 | -0.086709 | 0.019847 | -0.35992 | -0.68871 | -0.55267 | 0.49711 | -0.3245 | -0.52324 | 0.47455 | 0.12188
| 2207 | 0.19371 | -0.3838 | 0.37223 | 0.4307 | -0.70725 | -0.087147 | -0.069785 | 0.31699 | 0.087695 | -0.15839
| 2208 | 0.29594 | 0.42737 | 0.27192 | 0.75979 | -0.46605 | -0.17302 | -0.8739 | -0.05984 | -0.26047 | -0.20785
| 2209 | -0.29212 | -0.14076 | 0.21648 | 0.45714 | 0.05253 | 0.0033556 | -0.32747 | 0.65114 | 0.17217 | -0.20407
| 2210 | -0.093413 | -0.36431 | -0.020561 | 0.2193 | -0.046008 | 0.53535 | -0.60923 | 0.087805 | -0.40359 | -0.82028
| 2211 | -0.38494 | -0.66399 | 0.09088 | 0.088682 | -0.18165 | 0.030619 | 0.53621 | 0.44331 | 0.14777 | 0.60898
| 2212 | 0.40763 | 0.031031 | 0.35541 | -0.038907 | -0.2784 | 0.014657 | 0.46774 | 0.09033 | -0.057928 | -0.26332
| 2213 | 0.26427 | -0.013035 | -0.06325 | -0.27137 | 0.057609 | 0.41699 | -0.78716 | -0.094185 | -0.052108 | -0.093744
| 2214 | -0.012225 | 0.64321 | 0.65722 | 0.61987 | 0.45383 | -0.31509 | 0.14777 | 0.061437 | -0.8043 | -0.14765
| 2215 | 0.18385 | -0.26754 | 0.43018 | -0.53213 | 0.152 | -0.35308 | 0.77977 | -0.53556 | 0.50735 | -0.12165
| 2216 | -0.24376 | 0.89 | 0.60465 | -0.12989 | 0.11022 | 0.046323 | 0.45018 | -0.49275 | -0.29183 | -0.67829
| 2217 | 0.56354 | 0.34023 | 0.79095 | 0.89091 | -0.16221 | 0.46362 | 0.54426 | -0.24867 | 0.33105 | -0.3242
| 2218 | 0.7623 | -0.031548 | -0.26305 | 0.78858 | -0.31014 | -0.17 | -0.4553 | 0.1841 | -0.11 | -0.17181
| 2219 | 0.20244 | 0.011011 | 0.72852 | -0.85964 | 0.42043 | -0.19322 | -0.16723 | -0.65431 | -0.19545 | -0.21763
| 2220 | -0.014759 | 0.052741 | 0.2052 | 0.29879 | 0.26169 | -0.17811 | 0.16651 | 0.023424 | 0.037244 | -0.06325
| 2221 | 0.58227 | -0.054643 | -0.33962 | 0.336 | 0.59269 | -0.26196 | -0.52219 | -0.29523 | 0.51637 | 0.62171
| 2222 | -0.52492 | -0.093192 | -0.51164 | -0.66939 | 0.31276 | 0.91456 | -0.52767 | 0.039323 | 0.044751 | 0.099833
| 2223 | 0.1786 | 0.58515 | 0.47227 | -0.03434 | -0.12017 | 0.01791 | 0.30855 | 0.70217 | -0.031548 | 0.53967
| 2224 | -0.45365 | 0.248 | 0.1162 | -0.70521 | 0.15958 | -0.1338 | 0.033305 | -0.41459 | -0.80947 | -0.2711
| 2225 | -0.3551 | -0.39263 | 0.58539 | -0.013035 | -0.16376 | -0.22405 | -0.67922 | 0.71733 | -0.15484 | -0.1153
| 2226 | -0.077016 | 0.47665 | 0.18104 | -0.73373 | 0.27965 | -0.30754 | 0.12006 | 0.09209 | -0.83907 | 0.39411
| 2227 | -0.33134 | -0.1439 | 0.23065 | -0.15047 | 0.4542 | -0.13357 | -0.076041 | 0.72378 | -0.62946 | -0.20106
| 2228 | 0.52136 | 0.31846 | 0.22122 | -0.2508 | 0.43123 | -0.60668 | -0.070323 | -0.13832 | -0.65316 | 0.4232
| 2229 | -0.28341 | -0.24787 | 0.1578 | 0.29353 | -0.34403 | -0.070323 | 0.041929 | 0.29622 | 0.14753 | -0.20987
| 2230 | 0.16759 | -0.29993 | -0.093634 | -0.059734 | -0.35712 | 0.11688 | 0.13288 | 0.55559 | 0.37079 | -0.22754
| 2231 | -0.36384 | -0.19346 | -0.41221 | 0.23391 | -0.78114 | 0.22896 | 0.13611 | -0.092641 | -0.66849 | 0.2037
| 2232 | 0.4995 | -0.10217 | -0.2755 | -0.5102 | 0.26973 | -0.15792 | -0.14052 | -0.41034 | 0.81106 | 0.044333
| 2233 | -0.27854 | -0.24707 | 0.64014 | 0.018522 | -0.19732 | 0.25455 | -0.42233 | 0.12154 | 0.40983 | 0.53794
| 2234 | -0.31641 | 0.11518 | 0.60038 | -0.58878 | -0.56011 | -0.32332 | -0.44964 | 0.5245 | 0.83118 | -0.10061
| 2235 | 0.34892 | -0.48435 | 0.070108 | -0.068818 | -0.15377 | -0.0911 | -0.78023 | -0.23547 | -0.48183 | -0.045904
| 2236 | 0.065923 | 0.067101 | -0.28873 | 0.71069 | -0.027837 | -0.34693 | -0.30308 | -0.25455 | 0.24774 | 0.25441
| 2237 | -0.09176 | 0.37223 | 0.51369 | 0.31465 | 0.12599 | 0.26088 | 0.15614 | 0.78023 | -0.31334 | -0.30265
| 2238 | 0.45055 | 0.34724 | 0.070753 | -0.56171 | 0.36526 | -0.49592 | -0.96127 | 0.086053 | 0.19173 | -0.60668
| 2239 | 0.21 | 0.56216 | -0.20747 | -0.1803 | 0.032167 | -0.0015512 | -0.2598 | -0.62758 | 0.21165 | 0.53342
| 2240 | 0.47952 | 0.14099 | -0.34708 | -0.32051 | -0.60163 | -0.76104 | 0.11383 | -0.037244 | 0.054008 | -0.32881
| 2241 | 0.032271 | 0.4206 | -0.5959 | 0.1466 | -0.31758 | 0.45255 | -0.70623 | 0.097171 | -0.19062 | -0.43317
| 2242 | -0.28649 | -0.39362 | -0.36321 | 0.073339 | 0.71875 | -0.73074 | -0.030722 | -0.35712 | -0.10697 | -0.1204
| 2243 | -0.65751 | -0.66489 | -0.25441 | -0.53621 | 0.067208 | -0.82651 | 0.81588 | -0.15177 | -0.51246 | -0.056443
| 2244 | 0.34281 | 0.33434 | 0.63081 | 0.70657 | -0.5009 | 0.16663 | 0.62865 | -0.17848 | 0.19099 | -0.52471
| 2245 | 0.23521 | 0.43546 | 0.57421 | -0.68393 | 0.85823 | 0.17799 | -0.2958 | -0.0049623 | 0.29466 | 0.40125
| 2246 | -0.2816 | -0.3864 | 0.035168 | 0.039427 | 0.043078 | -0.28174 | 0.61077 | 0.27302 | -0.72742 | -0.14204
| 2247 | -0.25522 | -0.47894 | -0.10664 | 0.071614 | -0.086162 | -0.48493 | 0.28803 | 0.35092 | 0.23626 | -0.62119
| 2248 | 0.61856 | -0.089341 | 0.071184 | -0.39033 | -0.22096 | -0.13207 | -0.31934 | 0.86546 | -0.15626 | 0.3593
| 2249 | 0.063037 | -0.6995 | -0.048843 | 0.032788 | 0.56445 | -0.0091922 | 0.054114 | -0.44511 | 0.32643 | 0.16651
| 2250 | -0.75607 | -0.47322 | 0.050316 | 0.51061 | -0.76104 | 0.14472 | -0.061864 | -0.019439 | -0.073771 | 0.37095
| 2251 | 0.19148 | -0.051159 | -0.34647 | -0.15082 | -0.11711 | 0.73942 | -0.58323 | -0.27343 | 0.25414 | -0.46718
| 2252 | 0.60872 | -0.08474 | -0.41085 | 0.45751 | 0.016283 | -0.065495 | -0.05549 | 0.7076 | -0.34969 | -0.044123
| 2253 | 0.32066 | 0.017401 | -0.2598 | -0.57257 | 0.042973 | -0.80379 | 0.097393 | 0.050842 | -0.073663 | -0.45018
| 2254 | 0.52366 | -0.63545 | -0.77662 | -0.48648 | -0.10429 | -0.33932 | -0.077124 | -0.092421 | 0.32554 | -0.016384
| 2255 | 0.083212 | -0.036205 | 0.095622 | -0.14461 | 0.26781 | -0.17592 | 0.61568 | -0.11349 | -0.69324 | -0.4999
| 2256 | 0.55044 | -0.095622 | 0.28663 | 0.30423 | -0.007075 | 0.6349 | 0.24721 | -0.83845 | -0.12496 | 0.53513
| 2257 | -0.33434 | 0.19819 | 0.40848 | -0.5735 | -0.15543 | 0.67798 | -0.74722 | 0.077124 | -0.26781 | -0.35247
| 2258 | -0.31538 | -0.59049 | -0.63682 | 0.79875 | -0.4997 | 0.31904 | -0.30639 | 0.051369 | 0.31436 | 0.364
| 2259 | -0.17133 | -0.38951 | -0.65086 | 0.22818 | -0.098945 | 0.17205 | 0.11801 | 0.18606 | -0.12245 | 0.76784
| 2260 | 0.04266 | 0.58419 | 0.24204 | -0.029073 | -0.73599 | 0.25401 | 0.13797 | 0.43299 | -0.27647 | -0.015267
| 2261 | -0.48318 | -0.41733 | -0.45127 | -0.47094 | -0.3372 | -0.18594 | -0.3015 | 0.21025 | -0.67735 | -0.76741
| 2262 | 0.38869 | 0.17823 | -0.14064 | -0.26278 | -0.55447 | 0.080489 | 0.19384 | 0.16496 | -0.25697 | 0.18815
| 2263 | -0.040677 | 0.049789 | 0.51699 | 0.53946 | -0.62145 | 0.099833 | -0.56308 | 0.45493 | -0.69357 | -0.39809
| 2264 | 0.27 | 0.13994 | 0.53492 | 0.42528 | 0.26454 | -0.13322 | 0.78297 | 0.056655 | 0.3629 | 0.36984
| 2265 | -0.11598 | 0.56884 | 0.57703 | -0.12131 | 0.044333 | 0.15661 | -0.45347 | -0.073771 | -0.22767 | 0.25589
| 2266 | -0.60567 | -0.32435 | -0.54185 | 0.47303 | -0.23665 | 0.31611 | 0.18153 | -0.60263 | 0.066565 | -0.58155
| 2267 | 0.18815 | -0.64744 | 0.31949 | 0.10206 | -0.24323 | 0.4408 | 0.4983 | 0.38364 | -0.0082843 | -0.051264
| 2268 | 0.58395 | -0.42842 | -0.42842 | -0.37334 | 0.32494 | 0.15306 | -0.0058672 | 0.50231 | -0.4542 | 0.44511
| 2269 | 0.37702 | -0.050948 | 0.53406 | -0.15626 | 0.24893 | -0.12154 | 0.19831 | 0.15177 | 0.63517 | -0.54668
| 2270 | -0.032064 | 0.43848 | -0.41613 | -0.06197 | 0.14624 | 0.58684 | -0.60389 | 0.45182 | 0.45347 | -0.023322
| 2271 | -0.57585 | 0.65316 | 0.01182 | 0.20194 | 0.68141 | -0.032684 | -0.71035 | 0.14531 | -0.12188 | 0.24641
| 2272 | -0.40578 | 0.25683 | -0.57303 | -0.27398 | -0.8956 | 0.55111 | 0.47645 | -0.074743 | 0.84867 | -0.02281
| 2273 | 0.58733 | 0.67953 | 0.63958 | 0.15295 | 0.012731 | -0.62198 | 0.15887 | 0.15365 | 0.35712 | -0.70691
| 2274 | 0.18581 | 0.0019519 | -0.22534 | -0.09706 | 0.21597 | -0.57327 | 0.46251 | 0.11417 | 0.48415 | 0.43211
| 2275 | -0.10039 | 0.054855 | 0.0027538 | 0.48902 | -0.58251 | -0.1261 | 0.20056 | -0.0019519 | -0.37048 | 0.052952
| 2276 | 0.66638 | -0.12713 | 0.45511 | -0.11915 | 0.32346 | -0.41119 | -0.0072765 | -0.67581 | -0.11643 | -0.036517
| 2277 | -0.22353 | 0.27522 | 0.47189 | -0.15247 | 0.51554 | 0.40679 | -0.41221 | -0.79191 | 0.65897 | 0.50533
| 2278 | -0.50513 | 0.33344 | 0.84867 | -0.34205 | 0.093634 | -0.050632 | -0.15851 | -0.43955 | 0.91456 | 0.030825
| 2279 | -0.034443 | 0.52282 | 0.035583 | 0.11654 | -0.35293 | 0.4258 | 0.67 | -0.013035 | 0.15733 | 0.19881
| 2280 | -0.53816 | -0.15318 | -0.30913 | -0.29296 | 0.65114 | -0.79048 | 0.15377 | -0.39527 | -0.17726 | 0.30322
| 2281 | 0.49354 | 0.037036 | -0.67829 | -0.35355 | -0.52724 | 0.53021 | -0.11767 | -0.38283 | -0.24774 | 0.51948
| 2282 | -0.83907 | -0.11586 | 0.20282 | -0.25683 | 0.2216 | -0.48746 | -0.058884 | -0.54207 | 0.67891 | -0.68839
| 2283 | -0.52809 | 0.19495 | -0.45787 | 0.50756 | 0.01263 | 0.030412 | -0.46102 | -0.37159 | -0.71592 | -0.0017515
| 2284 | 0.61077 | 0.071938 | 0.3651 | 0.4293 | -0.69652 | -0.81318 | -0.18446 | 0.2893 | 0.032891 | 0.23862
| 2285 | 0.45456 | 0.082449 | 0.083212 | 0.6241 | -0.16125 | 0.05496 | 0.032891 | -0.29779 | -0.20407 | 0.53
| 2286 | 0.26495 | 0.51472 | -0.54956 | -0.14087 | -0.34114 | 0.076149 | 0.37095 | -0.72596 | -0.54054 | -0.13634
| 2287 | 0.27041 | -0.38608 | -0.16507 | -0.30279 | 0.34555 | -0.49078 | 0.023834 | 0.75896 | 0.62624 | -0.11881
| 2288 | 0.37334 | 0.29042 | -0.53192 | -0.20646 | -0.21508 | -0.37048 | -0.3048 | -0.57893 | -0.58684 | -0.15377
| 2289 | -0.40915 | -0.40058 | 0.19359 | 0.047372 | 0.0020521 | -0.16113 | -0.080924 | -0.61051 | -0.059415 | -0.68078
| 2290 | 0.02189 | 0.31904 | 0.025577 | -0.28817 | 0.5021 | 0.60846 | 0.60163 | 0.57093 | -0.4736 | 0.38984
| 2291 | -0.41888 | 0.12473 | 0.65373 | -0.77617 | 0.0066723 | -0.28118 | 0.0728 | -0.19037 | 0.52324 | -0.023834
| 2292 | -0.096285 | 0.033822 | 0.080054 | 0.45954 | 0.38526 | 0.08989 | 0.60314 | -0.6995 | -0.26563 | 0.52745
| 2293 | -0.1775 | 0.29651 | -0.0036567 | -0.18043 | 0.29993 | 0.54448 | -0.87631 | 0.45843 | 0.060905 | 0.2496
| 2294 | -0.58903 | -0.10239 | -0.20962 | 0.06197 | -0.30769 | -0.36526 | 0.86252 | 0.48629 | -0.10206 | 0.50291
| 2295 | -0.14835 | -0.66221 | 0.5283 | -0.34281 | 0.0045604 | -0.13762 | 0.12336 | 0.31261 | 0.15012 | -0.15744
| 2296 | -0.16663 | 0.067208 | -0.33194 | 0.24535 | 0.44439 | 0.97354 | -0.57186 | 0.19223 | 0.38706 | -0.17884
| 2297 | -0.90253 | -0.32554 | 0.66608 | 0.38396 | 0.28049 | -0.11949 | 0.77662 | -0.0055655 | 0.60088 | 0.47208
| 2298 | 0.2575 | -0.044437 | -0.69129 | 0.054114 | -0.28243 | -0.0038574 | -0.050632 | -0.41905 | -0.26577 | 0.010606
| 2299 | -0.15792 | 0.49691 | 0.40611 | 0.061011 | -0.036724 | -0.51472 | 0.37239 | -0.50735 | -0.66044 | 0.25791
| 2300 | -0.37686 | -0.43423 | -0.64321 | -0.083321 | 0.17896 | -0.19458 | 0.28118 | 0.2343 | -0.31846 | -0.21076
| 2301 | -0.44421 | 0.86696 | 0.26169 | 0.53277 | -0.064105 | -0.55739 | -0.078208 | -0.057185 | 0.20382 | -0.52094
| 2302 | 0.078317 | 0.49552 | 0.18938 | -0.086928 | 0.0025533 | 0.14449 | 0.44098 | 0.021072 | -0.34586 | 0.020663
| 2303 | -0.085615 | -0.26441 | 0.13936 | 0.52031 | -0.76827 | 0.88126 | -0.21559 | -0.031961 | -0.009798 | -0.18508
| 2304 | -0.22315 | -0.37382 | 0.148 | 0.59024 | -0.040365 | -0.088902 | -0.63299 | 0.50573 | -0.16771 | -0.28621
| 2305 | -0.55604 | -0.50735 | 0.78622 | 0.074095 | 0.45365 | -0.11056 | -0.53064 | 0.40578 | -0.70794 | -0.16928
| 2306 | -0.24297 | -0.15188 | 0.080707 | -0.63792 | 0.43281 | -0.08989 | 0.24231 | -0.095622 | 0.32658 | -0.11858
| 2307 | 0.40292 | -0.26345 | 0.49 | -0.83721 | 0.21878 | -0.16149 | -0.7245 | 0.35308 | -0.43564 | 0.65518
| 2308 | 0.6786 | 0.90151 | 0.16916 | 0.72926 | 0.04026 | -0.38348 | 0.39115 | -0.3306 | 0.26604 | 0.12897
| 2309 | 0.51287 | 0.035998 | -0.43564 | -0.76272 | -0.43123 | 0.34114 | 0.48629 | 0.052846 | 0.85543 | 0.25067
| 2310 | 0.24138 | 0.50513 | 0.04026 | -0.95 | -0.19235 | -0.27178 | -0.23796 | 0.10295 | -0.70897 | -0.26536
| 2311 | -0.16472 | -0.12931 | -0.23678 | 0.22238 | -0.27 | -0.065816 | -0.18655 | 0.17157 | -0.39477 | -0.52555
| 2312 | -0.3294 | -0.14461 | 0.068818 | 0.0039578 | 0.0047613 | 0.69718 | -0.5458 | -0.24231 | 0.074527 | 0.028764
| 2313 | 0.079294 | 0.03465 | 0.4417 | -0.41733 | 0.14041 | 0.055066 | -0.24138 | 0.38251 | -0.40309 | -0.34418
| 2314 | 0.72742 | 0.045694 | -0.28803 | -0.2733 | 0.099722 | -0.35696 | 0.18177 | -0.48765 | 0.025167 | 0.10608
| 2315 | 0.22534 | 0.16006 | 0.12885 | -0.64265 | -0.22263 | -0.53406 | -0.83907 | -0.51678 | -0.012832 | 0.024449
| 2316 | 0.2147 | -0.071938 | -0.77796 | -0.28467 | 0.33224 | 0.05253 | -0.33947 | -0.085615 | 0.59343 | -0.27316
| 2317 | 0.60188 | 0.13913 | 0.45603 | -0.17848 | 0.36149 | -0.85 | 0.2081 | -0.067208 | -0.16364 | 0.72523
| 2318 | -0.019031 | -0.30423 | -0.11824 | 0.51802 | -0.72742 | -0.43991 | -0.060798 | 0.44837 | -0.35139 | -0.16185
| 2319 | -0.6118 | -0.052846 | 0.3451 | -0.19881 | 0.037347 | -0.057822 | 0.34662 | 0.18238 | -0.15519 | 0.63244
| 2320 | -0.54011 | 0.32406 | 0.3167 | 0.26088 | 0.63903 | 0.01344 | -0.050948 | -0.42441 | 0.55 | 0.16352
| 2321 | -0.050421 | -0.24455 | -0.25093 | -0.62543 | -0.31334 | -0.14519 | 0.67182 | 0.60289 | -0.16113 | -0.25414
| 2322 | 0.36889 | -0.46102 | -0.3425 | 0.025474 | -0.90151 | -0.065709 | 0.54076 | 0.064532 | -0.9134 | -0.45658
| 2323 | -0.13983 | -0.36494 | 0.66429 | 0.26713 | 0.75282 | -0.23888 | 0.39461 | 0.06325 | -0.14835 | 0.044542
| 2324 | 0.49059 | 0.64801 | -0.050842 | 0.02794 | -0.026809 | 0.7816 | -0.64237 | -0.12564 | 0.04381 | -0.15271
| 2325 | -0.23915 | 0.031341 | 0.69553 | 0.18594 | -0.7076 | -0.40696 | 0.079294 | 0.21725 | -0.64715 | -0.16795
| 2326 | 0.82365 | 0.37254 | -0.18729 | 0.053586 | 0.54338 | 0.57633 | -0.45 | -0.27233 | 0.78716 | 0.72341
| 2327 | 0.086053 | 0.45677 | -0.17775 | 0.096396 | -0.48707 | 0.086381 | -0.48338 | -0.19 | -0.54076 | -0.021379
| 2328 | -0.87 | 0.40192 | -0.09165 | -0.75731 | 0.43088 | -0.0065716 | 0.13924 | -0.37286 | -0.88042 | -0.0076795
| 2329 | -0.35308 | 0.22148 | -0.58012 | -0.32836 | 0.51906 | -0.078642 | 0.30437 | 0.042764 | -0.094738 | -0.32821
| 2330 | -0.031548 | 0.19334 | -0.11338 | -0.79727 | -0.12576 | 0.2042 | 0.045799 | -0.30754 | 0.36778 | -0.25093
| 2331 | 0.070968 | 0.085396 | -0.60923 | 0.93 | 0.34877 | -0.83538 | 0.57562 | -0.39049 | -0.048527 | 0.64602
| 2332 | 0.73599 | 0.31422 | 0.11056 | -0.12507 | 0.23078 | 0.41136 | 0.36149 | 0.464 | -0.10473 | 0.2524
| 2333 | -0.84348 | 0.074635 | -0.2985 | 0.88642 | -0.2234 | -0.74525 | -0.11654 | -0.3568 | 0.4542 | -0.28243
| 2334 | -0.44601 | -0.066887 | 0.31436 | 0.40611 | 0.017605 | 0.24469 | -0.57727 | -0.55604 | -0.73223 | -0.33856
| 2335 | 0.085834 | -0.037347 | -0.010505 | -0.71875 | 0.27661 | 0.0021523 | 0.30193 | -0.2398 | -0.10876 | -0.21266
| 2336 | 0.33389 | -0.77439 | 0.77175 | -0.089451 | -0.31261 | 0.48376 | -0.3363 | 0.37494 | 0.3419 | -0.80739
| 2337 | -0.30207 | -0.37734 | -0.28188 | 0.039844 | -0.29127 | -0.22186 | -0.19944 | 0.6265 | -0.7076 | -0.42112
| 2338 | 0.17241 | 0.19782 | -0.11045 | 0.15863 | -0.38218 | 0.4471 | 0.36573 | -0.0022525 | 0.3425 | -0.46232
| 2339 | -0.48125 | 0.30653 | -0.48048 | -0.096285 | -0.79482 | 0.36826 | -0.35432 | 0.72125 | 0.10686 | -0.75938
| 2340 | 0.67061 | 0.35587 | -0.36778 | -0.27716 | -0.18434 | 0.70555 | -0.47322 | -0.35618 | 0.12759 | -0.44367
| 2341 | 0.58781 | -0.032994 | -0.44964 | -0.48668 | 0.055595 | -0.45365 | 0.57374 | 0.30408 | 0.35 | 0.0781
| 2342 | -0.24628 | 0.032891 | 0.5806 | -0.73411 | 0.063784 | -0.00085036 | -0.048738 | 0.047582 | -0.27192 | 0.46793
| 2343 | 0.42947 | 0.13901 | -0.17459 | -0.3167 | -0.28831 | -0.26604 | 0.21827 | 0.43193 | -0.0022525 | 0.0025533
| 2344 | 0.10764 | -0.55898 | -0.436 | -0.32214 | 0.15792 | 0.62119 | 0.12576 | -0.14812 | -0.88909 | 0.042138
| 2345 | 0.40427 | -0.76442 | 0.49711 | 0.074419 | -0.59245 | -0.053586 | -0.33841 | -0.59565 | 0.030619 | -0.58347
| 2346 | -0.33374 | 0.7569 | -0.0078811 | -0.23678 | 0.11405 | -0.62066 | 0.52157 | -0.096507 | 0.82593 | -0.6703
| 2347 | -0.18508 | 0.68775 | -0.023629 | -0.90253 | 0.52073 | -0.34418 | -0.17471 | -0.3186 | -0.76527 | 0.56606
| 2348 | 0.02568 | 0.30725 | 0.58684 | -0.082994 | -0.10161 | 0.019337 | 0.072153 | 0.22935 | 0.47379 | -0.34724
| 2349 | 0.6952 | -0.46587 | -0.8467 | 0.22148 | -0.41888 | 0.41974 | 0.13994 | 0.12131 | 0.41562 | 0.35821
| 2350 | 0.076258 | 0.59788 | -0.24072 | 0.68298 | -0.08136 | 0.89183 | 0.50573 | 0.51061 | -0.55156 | 0.55989
| 2351 | -0.3864 | -0.43035 | -0.76698 | -0.24495 | -0.31392 | 0.35123 | -0.1775 | -0.044856 | 0.45787 | -0.64943
| 2352 | 0.55514 | -0.41306 | 0.73827 | -0.38299 | -0.20144 | -0.031135 | -0.55267 | 0.4279 | -0.20684 | 0.09055
| 2353 | -0.1546 | -0.67488 | 0.068496 | 0.16006 | 0.0058672 | 0.32583 | 0.84476 | 0.29907 | -0.2784 | -0.030206
| 2354 | 0.22702 | -0.15448 | 0.1034 | -0.021685 | 0.76188 | -0.68298 | 0.34754 | -0.75813 | 0.1196 | -0.47531
| 2355 | -0.30222 | -0.25441 | 0.23823 | -0.19607 | -0.00075028 | -0.018623 | 0.25013 | 0.42807 | 0.4755 | -0.10675
| 2356 | -0.55649 | -0.30523 | 0.45401 | -0.36636 | 0.062823 | -0.13704 | 0.019541 | -0.29113 | 0.36463 | 0.07183
| 2357 | -0.49631 | -0.10462 | -0.12599 | -0.06603 | 0.26088 | 0.15756 | -0.72161 | -0.57964 | 0.44063 | -0.13669
| 2358 | -0.32911 | -0.10776 | -0.16759 | -0.078534 | 0.43938 | -0.097503 | -0.5199 | -0.22586 | 0.56331 | -0.06293
| 2359 | -0.58491 | -0.11135 | -0.2602 | -0.68615 | 0.6233 | -0.41153 | -0.54602 | -0.4997 | -0.021583 | 0.10384
| 2360 | 0.59614 | 0.2476 | -0.25133 | -0.16364 | 0.11711 | -0.11654 | -0.010505 | -0.69065 | 0.68267 | -0.60339
| 2361 | -0.49216 | -0.08485 | -0.45036 | 0.1513 | -0.29964 | -0.36102 | 0.33134 | -0.048002 | 0.34053 | 0.31058
| 2362 | 0.53643 | 0.22637 | 0.078859 | 0.20357 | 0.14204 | -0.039948 | -0.045484 | -0.7429 | 0.85613 | -0.042869
| 2363 | -0.51575 | -0.071722 | -0.54712 | 0.065281 | -0.25347 | -0.46661 | 0.0069743 | 0.74329 | -0.33509 | 0.24707
| 2364 | 0.53256 | 0.36196 | 0.59888 | -0.0075787 | -0.7429 | 0.10128 | 0.44855 | -0.087147 | 0.30711 | -0.011112
| 2365 | -0.59 | -0.0043595 | 0.26495 | 0.27827 | 0.61412 | 0.45109 | 0.24072 | 0.048422 | -0.031031 | 0.43688
| 2366 | 0.26713 | -0.81917 | -0.65839 | 0.069248 | 0.48299 | -0.29736 | -0.35805 | 0.44457 | -0.16161 | 0.13913
| 2367 | 0.31626 | -0.70017 | -0.57774 | 0.50817 | 0.10742 | -0.70117 | 0.64377 | 0.352 | 0.033512 | -0.33871
| 2368 | 0.57941 | 0.10172 | -0.13716 | -0.047477 | 0.09066 | 0.28551 | 0.17193 | 0.34938 | -0.29679 | -0.063677
| 2369 | -0.15602 | 0.18336 | 0.49315 | 0.60339 | -0.032167 | 0.50251 | 0.20823 | -0.18287 | 0.019949 | -0.050737
| 2370 | -0.035687 | -0.57562 | 0.2037 | -0.82941 | -0.31174 | -0.52492 | -0.67396 | -0.48687 | -0.17109 | -0.65547
| 2371 | 0.15685 | 0.085615 | 0.10652 | 0.40561 | -0.1204 | 0.37879 | -0.56239 | -0.01415 | -0.32613 | 0.36337
| 2372 | -0.54911 | 0.027426 | 0.057397 | 0.26549 | -0.043182 | 0.36573 | -0.57023 | 0.067852 | -0.66789 | -0.3681
| 2373 | -0.46437 | -0.25053 | -0.21013 | 0.19944 | 0.39892 | -0.13774 | 0.17253 | 0.2225 | -0.20094 | -0.29964
| 2374 | -0.088573 | -0.39992 | -0.17836 | -0.026707 | 0.39759 | 0.41068 | 0.055913 | -0.14122 | 0.1136 | 0.074851
| 2375 | 0.22276 | -0.1634 | 0.31626 | 0.13184 | -0.047897 | -0.77218 | -0.27633 | -0.39148 | -0.17121 | 0.42303
| 2376 | 0.16579 | 0.52745 | 0.56722 | 0.041929 | -0.25441 | -0.15816 | -0.45787 | -0.32702 | 0.44818 | 0.74841
| 2377 | 0.28313 | 0.25656 | -0.27951 | 0.19769 | 0.47837 | -0.59664 | -0.034754 | -0.0064709 | -0.7508 | 0.58131
| 2378 | 0.60163 | -0.13739 | -0.050211 | 0.10462 | -0.36905 | -0.16639 | 0.21917 | 0.43317 | 0.098501 | -0.020255
| 2379 | 0.15236 | 0.068818 | 0.164 | 0.080924 | 0.20056 | 0.61077 | 0.54142 | -0.13936 | 0.42424 | 0.33826
| 2380 | 0.1646 | 0.14425 | 0.018318 | -0.30928 | 0.18299 | 0.80328 | -0.052108 | -0.61751 | -0.52619 | -0.15496
| 2381 | -0.36984 | 0.11451 | 0.16687 | -0.1109 | 0.50371 | -0.2256 | -0.5347 | -0.038595 | -0.45787 | -0.36305
| 2382 | 0.33179 | 0.079511 | 0.54448 | -0.70285 | 0.56884 | -0.045694 | 0.4828 | -0.56034 | -0.33962 | -0.082231
| 2383 | -0.57633 | -0.15638 | 0.44475 | 0.10061 | -0.20659 | 0.82139 | -0.095732 | -0.31641 | -0.53946 | 0.059415
| 2384 | -0.42372 | -0.24151 | 0.15012 | -0.55111 | -0.10306 | 0.31436 | -0.43053 | -0.22637 | -0.086162 | -0.042555
| 2385 | 0.75896 | 0.48785 | 0.33645 | -0.044333 | -0.48396 | -0.29127 | 0.078534 | -0.0068736 | 0.3015 | 0.17193
| 2386 | 0.077774 | 0.33766 | 0.61961 | -0.21648 | 0.18753 | -0.31728 | 0.094185 | -0.39066 | 0.28049 | -0.31509
| 2387 | 0.068925 | -0.19074 | 0.60289 | -0.30696 | -0.22534 | -0.19111 | 0.13219 | 0.1025 | -0.37334 | 0.43884
| 2388 | 0.11575 | 0.27536 | 0.35774 | -0.025269 | -0.24099 | -0.57917 | 0.83477 | 0.057291 | 0.37686 | 0.25294
| 2389 | -0.28537 | -0.044333 | 0.89183 | -0.47208 | -0.29254 | 0.067852 | 0.2161 | 0.59639 | 0.24191 | -0.16904
| 2390 | -0.19086 | -0.40242 | 0.23391 | -0.65634 | -0.11654 | 0.448 | -0.068496 | -0.8882 | -0.22456 | 0.043705
| 2391 | -0.4801 | -0.067101 | -0.33209 | -0.088243 | -0.10664 | 0.10217 | -0.073339 | -0.18434 | -0.82593 | 0.29353
| 2392 | 0.79 | -0.73298 | 0.18312 | -0.22456 | 0.06957 | 0.032271 | 0.47417 | -0.30783 | 0.6349 | -0.043078
| 2393 | 0.54933 | -0.69455 | -0.09044 | -0.078751 | -0.2278 | -0.61026 | 0.09518 | 0.37976 | 0.26034 | -0.60949
| 2394 | -0.041094 | 0.023015 | 0.060692 | -0.55694 | 0.1603 | -0.18361 | 0.65258 | 0.38396 | 0.11507 | -0.1868
| 2395 | -0.38315 | -0.2689 | -0.37622 | 0.023322 | 0.83969 | 0.4857 | -0.57491 | 0.074743 | -0.38008 | -0.24086
| 2396 | -0.061011 | 0.023629 | -0.2047 | 0.74058 | 0.19757 | -0.75607 | -0.082558 | -0.63572 | -0.94432 | 0.70794
| 2397 | -0.70487 | -0.17653 | -0.40797 | -0.34418 | -0.67984 | -0.041512 | -0.19582 | 0.29042 | 0.055066 | -0.53043
| 2398 | 0.23967 | -0.33977 | 0.44313 | 0.067316 | -0.14906 | -0.10373 | 0.52198 | -0.56171 | -0.81752 | 0.39246
| 2399 | -0.4307 | -0.48376 | 0.47208 | 0.71173 | 0.15697 | 0.45824 | -0.61987 | -0.52534 | 0.049895 | 0.3129
| 2400 | -0.050632 | 0.87 | 0.032788 | -0.29708 | 0.60923 | -0.43176 | -0.20621 | -0.28607 | -0.17169 | 0.19856
| 2401 | -0.24907 | -0.26767 | 0.68903 | 0.5663 | -0.33419 | 0.40595 | 0.46158 | 0.70691 | -0.27123 | 0.061864
| 2402 | 0.35046 | -0.5015 | -0.64801 | 0.12199 | -0.0025533 | 0.46699 | 0.41854 | 0.59491 | 0.20558 | -0.64715
| 2403 | -0.8618 | 0.20069 | -0.70897 | 0.31276 | 0.10753 | 0.72559 | -0.78436 | 0.18299 | -0.30207 | 0.22961
| 2404 | 0.052424 | -0.21343 | 0.44565 | 0.75241 | -0.55178 | -0.019031 | -0.13959 | -0.14041 | 0.48106 | -0.81106
| 2405 | 0.035479 | -0.05899 | -0.30193 | -0.050526 | 0.84736 | 0.36164 | 0.60923 | -0.55492 | 0.53989 | -0.24151
| 2406 | 0.057397 | -0.56514 | 0.2313 | -0.11101 | -0.79531 | 0.12245 | -0.6349 | 0.58443 | 0.68456 | -0.71522
| 2407 | 0.66192 | 0.11202 | -0.12302 | 0.0073772 | 0.73448 | 0.41306 | 0.20031 | -0.078425 | 0.62517 | 0.36937
| 2408 | 0.26973 | 0.38853 | -0.81 | 0.59368 | -0.38461 | -0.16018 | -0.072261 | 0.76784 | -0.40477 | 0.19433
| 2409 | 0.83297 | -0.28958 | -0.044123 | -0.27481 | -0.042033 | -0.4995 | -0.48668 | -0.23169 | -0.4272 | -0.22238
| 2410 | 0.37286 | -0.70589 | -0.017707 | -0.30408 | 0.065495 | 0.063998 | -0.11338 | 0.35961 | -0.32554 | 0.1382
| 2411 | 0.25576 | 0.19408 | 0.46139 | 0.070753 | -0.24178 | 0.15555 | -0.18901 | 0.14965 | -0.28481 | 0.79727
| 2412 | 0.18079 | 0.67152 | -0.0053644 | -0.57846 | -0.10518 | 0.55921 | -0.0081835 | 0.080489 | -0.29708 | 0.0018517
| 2413 | 0.92584 | -0.75772 | -0.33045 | -0.58275 | 0.8454 | 0.21521 | 0.57515 | 0.14683 | -0.23378 | -0.17278
| 2414 | -0.10061 | -0.84867 | 0.09529 | 0.41905 | -0.30538 | -0.3357 | -0.86472 | 0.039011 | -0.10552 | 0.47455
| 2415 | 0.54251 | -0.054326 | -0.4337 | 0.097171 | 0.37016 | 0.75444 | 0.01791 | 0.5015 | 0.30913 | 0.19198
| 2416 | 0.26223 | 0.45383 | 0.084631 | 0.10384 | -0.22186 | -0.33359 | -0.21139 | 0.38706 | 0.89464 | -0.26128
| 2417 | 0.25804 | 0.50898 | 0.19371 | -0.057503 | 0.057397 | -0.47 | 0.72305 | 0.11711 | -0.35821 | -0.58443
| 2418 | 0.11169 | -0.31919 | 0.50351 | 0.35216 | 0.34008 | 0.71557 | -0.05814 | 0.36478 | 0.29551 | 0.22754
| 2419 | -0.66939 | -0.22702 | 0.62357 | -0.088134 | -0.46624 | 0.72926 | 0.45567 | -0.6546 | 0.87631 | 0.088573
| 2420 | 0.29254 | -0.13403 | -0.17909 | 0.66162 | 0.23273 | 0.014252 | -0.0013509 | 0.8618 | 0.69718 | 0.55402
| 2421 | -0.16149 | -0.63517 | 0.51616 | 0.48376 | -0.14239 | -0.092751 | -0.18803 | 0.77841 | 0.55785 | -0.035479
| 2422 | 0.52576 | -0.48493 | -0.21687 | 0.15792 | 0.24508 | 0.21241 | 0.7623 | 0.22961 | -0.22109 | 0.074527
| 2423 | -0.70931 | 0.51082 | -0.28691 | 0.1533 | 0.052635 | 0.79875 | -0.1578 | -0.80379 | 0.4668 | 0.39726
| 2424 | 0.10429 | 0.21292 | -0.10429 | -0.31699 | -0.76146 | -0.51699 | -0.36431 | -0.10798 | 0.34586 | 0.80075
| 2425 | 0.18938 | 0.045065 | -0.1221 | -0.0922 | -0.016486 | 0.58323 | -0.037347 | -0.073987 | 0.16916 | 0.33886
| 2426 | 0.0022525 | 0.45438 | -0.8747 | 0.33494 | -0.11801 | 0.051264 | 0.67984 | -0.19396 | 0.34479 | 0.46755
| 2427 | 0.29736 | 0.11315 | 0.43317 | 0.42129 | 0.066244 | -0.54316 | -0.31919 | 0.23443 | 0.096617 | -0.21368
| 2428 | 0.13542 | -0.033718 | -0.34008 | 0.53235 | 0.74096 | -0.05899 | -0.7496 | -0.081577 | 0.062823 | -0.48396
| 2429 | 0.069355 | -0.78669 | -0.11056 | -0.27178 | -0.097393 | 0.24575 | 0.049053 | -0.22573 | 0.077449 | 0.37207
| 2430 | -0.30581 | -0.82422 | -0.46512 | 0.57822 | 0.47132 | 0.18926 | -0.62092 | -0.017503 | 0.042347 | 0.43635
| 2431 | -0.048633 | -0.19421 | 0.61672 | -0.84412 | 0.051475 | 0.54602 | -0.057291 | 0.50796 | -0.29212 | -0.30754
| 2432 | 0.069463 | -0.57303 | 0.51782 | 0.35743 | 0.23013 | -0.79925 | -0.21533 | -0.02322 | 0.17411 | -0.13646
| 2433 | -0.14122 | 0.70083 | 0.0048618 | 0.50492 | 0.8148 | 0.2184 | 0.60238 | 0.84736 | 0.50878 | -0.16232
| 2434 | -0.44547 | 0.32125 | -0.057928 | -0.51184 | -0.17495 | 0.84157 | -0.0781 | 0.28076 | -0.57491 | 0.067423
| 2435 | 0.3882 | 0.35696 | 0.33 | 0.41888 | -0.033305 | -0.098058 | 0.16256 | 0.44421 | 0.34954 | -0.14157
| 2436 | 0.37032 | -0.56011 | 0.18336 | 0.70184 | -0.6578 | 0.32881 | 0.82252 | -0.070215 | 0.18373 | -0.66221
| 2437 | -0.49354 | 0.38934 | -0.088353 | 0.11394 | 0.31043 | -0.37526 | -0.56171 | -0.61438 | 0.42511 | -0.88731
| 2438 | 0.26237 | 0.15768 | 0.32866 | 0.6338 | 0.68078 | -0.74446 | 0.17072 | 0.54273 | 0.92584 | 0.60213
| 2439 | -0.58036 | -0.36652 | -0.32022 | 0.28537 | -0.75403 | 0.40915 | -0.029588 | -0.56148 | -0.78952 | 0.8956
| 2440 | 0.38738 | -0.18938 | 0.62811 | 0.63054 | 0.52619 | 0.91574 | 0.25602 | 0.058671 | 0.72414 | 0.54404
| 2441 | -0.13276 | -0.64181 | 0.37462 | 0.074635 | -0.51184 | 0.69983 | -0.11045 | -0.22792 | 0.2659 | -0.33329
| 2442 | -0.069677 | -0.29495 | -0.29268 | -0.10854 | 0.15283 | -0.9089 | -0.56102 | 0.035894 | 0.13011 | -0.041303
| 2443 | 0.2512 | 0.26074 | -0.42493 | 0.025064 | 0.33766 | -0.2265 | -0.21482 | -0.36149 | -0.42615 | -0.30769
| 2444 | -0.39098 | -0.19185 | -0.14648 | 0.10652 | -0.26196 | 0.65985 | 0.23195 | -0.069892 | 0.0052639 | -0.31728
| 2445 | -0.36952 | 0.85964 | -0.13681 | -0.35696 | 0.2313 | -0.73411 | -0.54978 | -0.16268 | 0.6265 | 0.37446
| 2446 | 0.26549 | 0.36857 | -0.19309 | 0.56148 | -0.42737 | 0.31509 | 0.044961 | -0.71982 | -0.56102 | 0.082885
| 2447 | 0.23547 | 0.59938 | 0.4134 | -0.69 | 0.75772 | 0.067101 | -0.061331 | -0.40292 | -0.66459 | -0.25187
| 2448 | 0.77977 | 0.054008 | -0.77528 | 0.73261 | 0.30769 | 0.48493 | 0.27316 | 0.25831 | -0.19025 | 0.83059
| 2449 | 0.56491 | -0.21127 | -0.11756 | -0.079946 | 0.2343 | 0.55989 | 0.22199 | 0.65402 | -0.91815 | 0.36086
| 2450 | 0.33434 | -0.89464 | -0.48396 | -0.15661 | -0.42268 | 0.36526 | 0.088134 | 0.25267 | 0.39726 | -0.19894
| 2451 | -0.48863 | 0.1353 | -0.059521 | -0.10697 | 0.085724 | 0.051053 | -0.39411 | 0.22071 | 0.61699 | -0.26074
| 2452 | 0.01547 | 0.036205 | 0.45036 | -0.7687 | 0.024346 | 0.2602 | 0.3242 | -0.09011 | 0.57047 | 0.3245
| 2453 | 0.14531 | -0.5922 | 0.52661 | 0.1597 | -0.071507 | 0.051159 | -0.54382 | -0.43405 | -0.32955 | -0.62251
| 2454 | 0.33585 | -0.10619 | -0.63931 | -0.078317 | 0.40831 | -0.19582 | -0.28467 | -0.26986 | 0.3537 | 0.082122
| 2455 | -0.37718 | 0.050105 | -0.063464 | -0.12382 | -0.27069 | -0.53449 | 0.27882 | 0.18618 | 0.026501 | 0.015876
| 2456 | -0.6952 | 0.15756 | -0.49512 | 0.036621 | 0.18704 | 0.19359 | -0.014657 | -0.56331 | -0.39263 | 0.05984
| 2457 | 0.21827 | 0.10261 | 0.029794 | -0.3743 | 0.20634 | -0.1786 | -0.24349 | 0.2287 | 0.062397 | -0.63903
| 2458 | -0.21266 | -0.20232 | -0.75444 | 0.11112 | -0.31422 | -0.062717 | -0.1646 | 0.18594 | -0.064105 | -0.28481
| 2459 | -0.60872 | -0.62784 | 0.49493 | -0.25845 | -0.40108 | 0.28035 | -0.73373 | 0.13496 | 0.09055 | 0.4163
| 2460 | 0.22974 | 0.1694 | 0.46887 | -0.26318 | -0.35417 | -0.72197 | -0.14402 | 0.044856 | 0.32791 | 0.22547
| 2461 | 0.2823 | 0.35774 | -0.44403 | 0.080272 | -0.65029 | 0.43264 | -0.39626 | 0.1803 | -0.48824 | 0.43795
| 2462 | 0.46418 | 0.24601 | -0.018216 | 0.71733 | 0.93 | 0.15733 | -0.49374 | 0.25468 | 0.025064 | 0.40159
| 2463 | 0.52788 | 0.77707 | 0.46943 | -0.62171 | -0.58179 | -0.035376 | -0.029485 | 0.17957 | -0.022094 | 0.14355
| 2464 | -0.40797 | 0.62919 | -0.83477 | 0.20131 | 0.063144 | -0.83118 | -0.15082 | -0.56791 | -0.02609 | 0.71208
| 2465 | -0.66909 | -0.11688 | 0.55156 | -0.15756 | 0.49275 | 0.034443 | 0.56699 | 0.23325 | -0.17193 | -0.10921
| 2466 | 0.13392 | -0.032891 | 0.2343 | 0.13449 | -0.20106 | -0.13299 | -0.1769 | -0.17084 | -0.17302 | 0.20319
| 2467 | 0.12679 | 0.14706 | 0.087038 | 0.61026 | -0.47837 | 0.22741 | -0.42026 | 0.056443 | 0.056019 | -0.32806
| 2468 | -0.54185 | -0.81426 | 0.62517 | -0.22328 | -0.76698 | 0.1044 | -0.099833 | -0.018012 | 0.27467 | -0.22715
| 2469 | 0.1628 | 0.25187 | 0.51595 | -0.85 | 0.32702 | 0.27661 | 0.44891 | 0.076149 | 0.31816 | 0.54207
| 2470 | -0.17072 | -0.13692 | -0.086381 | 0.14064 | -0.5102 | 0.12006 | -0.22032 | 0.45585 | 0.40881 | 0.69751
| 2471 | 0.085615 | 0.26115 | 0.058671 | -0.18901 | -0.30725 | -0.20546 | -0.3294 | -0.23039 | -0.16615 | 0.36353
| 2472 | 0.76442 | -0.43264 | 0.39362 | -0.31846 | -0.69619 | 0.10641 | 0.68552 | 0.13034 | 0.21891 | 0.16735
| 2473 | -0.2225 | 0.24641 | 0.16484 | -0.081469 | -0.26074 | -0.34266 | 0.13069 | 0.006169 | 0.53427 | 0.14169
| 2474 | 0.43617 | -0.54646 | 0.20019 | 0.039115 | 0.22521 | 0.61464 | -0.20194 | -0.27744 | 0.47132 | -0.25993
| 2475 | -0.1229 | -0.92319 | 0.32569 | 0.77044 | 0.38543 | -0.066137 | -0.68267 | 0.15024 | -0.5019 | 0.54142
| 2476 | 0.28355 | -0.50837 | -0.60974 | -0.00015001 | -0.30711 | 0.24641 | 0.58131 | 0.38689 | 0.092641 | -0.3366
| 2477 | -0.38836 | -0.39908 | -0.44746 | 0.82941 | 0.66281 | -0.0073772 | -0.15165 | -0.23993 | 0.0073772 | 0.23993
| 2478 | -0.1694 | 0.29212 | 0.564 | -0.39992 | 0.3422 | 0.37159 | 0.48609 | -0.448 | 0.12633 | 0.18336
| 2479 | -0.15519 | 0.12484 | 0.10061 | -0.69751 | -0.47379 | 0.21814 | 0.25683 | -0.42895 | -0.23286 | -0.12759
| 2480 | -0.31787 | -0.19956 | -0.42129 | -0.3477 | 0.042451 | -0.52408 | 0.051791 | 0.08136 | -0.62198 | -0.21712
| 2481 | 0.031651 | 0.52788 | 0.23783 | 0.19994 | 0.46213 | 0.86546 | 0.099833 | 0.063891 | 0.17072 | 0.69259
| 2482 | 0.16543 | -0.11972 | 0.046218 | 0.49216 | -0.45954 | 0.83477 | 0.75566 | -0.69751 | -0.2081 | -0.062823
| 2483 | 0.61829 | -0.2823 | -0.27426 | -0.72305 | -0.21981 | 0.21025 | 0.044542 | 0.28132 | -0.19956 | 0.67674
| 2484 | 0.34327 | -0.20056 | 0.17836 | -0.076691 | 0.52894 | 0.37302 | -0.18287 | 0.47703 | -0.089012 | 0.01415
| 2485 | 0.17133 | -0.038803 | -0.19508 | -0.45493 | -0.094627 | -0.41017 | 0.13484 | 0.42147 | 0.23013 | 0.13785
| 2486 | 0.47 | 0.59466 | -0.10708 | 0.25616 | 0.15875 | 0.28916 | -0.34099 | -0.051475 | -0.20232 | 0.73111
| 2487 | 0.10552 | -0.13288 | 0.0082843 | -0.3087 | 0.13577 | 0.60974 | 0.50939 | -0.0039578 | -0.13346 | 0.061118
| 2488 | 0.09022 | 0.080924 | 0.50492 | 0.3369 | 0.13357 | -0.7569 | 0.096064 | 0.89183 | -0.59417 | -0.52429
| 2489 | 0.41733 | 0.64461 | 0.36023 | -0.64801 | 0.18165 | -0.032271 | -0.20709 | 0.61231 | 0.67798 | 0.73713
| 2490 | -0.019337 | 0.47531 | 0.67458 | 0.65809 | 0.23208 | 0.3186 | -0.58733 | 0.09 | 0.59763 | -0.27247
| 2491 | 0.23091 | -0.45146 | 0.27993 | 0.043287 | -0.62517 | 0.46812 | 0.4987 | -0.36133 | 0.33209 | 0.57633
| 2492 | -0.53859 | -0.50715 | -0.80226 | -0.75526 | 0.59664 | 0.49433 | 0.45843 | -0.52873 | -0.62304 | 0.33766
| 2493 | -0.68615 | 0.39726 | 0.15247 | -0.085396 | 0.33209 | -0.30279 | 0.28523 | -0.2784 | -0.37207 | -0.029588
| 2494 | -0.18753 | -0.02609 | 0.7042 | -0.24947 | 0.056761 | 0.93443 | -0.27165 | -0.22508 | 0.56468 | 0.60744
| 2495 | 0.33735 | -0.6162 | 0.041407 | 0.06496 | 0.10061 | 0.53837 | 0.084413 | -0.071938 | -0.32258 | -0.77483
| 2496 | 0.4989 | -0.14554 | 0.061224 | 0.15851 | -0.56468 | 0.11225 | -0.67182 | -0.30899 | 0.098058 | -0.25294
| 2497 | 0.010202 | -0.30308 | -0.55156 | 0.59343 | 0.37382 | 0.33992 | 0.17386 | -0.021583 | -0.021481 | 0.5728
| 2498 | 0.047582 | -0.047372 | 0.13634 | 0.10184 | -0.20609 | -0.24349 | 0.67396 | -0.1338 | -0.28607 | -0.34479
| 2499 | 0.32406 | -0.48746 | -0.28621 | 0.35293 | 0.38559 | 0.50452 | -0.073663 | 0.37048 | 0.087257 | -0.21127
| 2500 | 0.62224 | -0.23718 | -0.57846 | 0.23013 | 0.077124 | -0.22109 | -0.19831 | -0.38396 | -0.029897 | 0.30207
| 2501 | -0.60541 | 0.28579 | -0.252 | 0.64546 | -0.53621 | 0.084194 | -0.029691 | -0.25067 | 0.42441 | 0.046638
| 2502 | 0.4232 | 0.15012 | -0.55582 | 0.14402 | -0.84094 | 0.02722 | 0.51554 | 0.099833 | -0.31949 | 0.25643
| 2503 | -0.084194 | -0.74058 | 0.50715 | -0.093413 | 0.07 | 0.28705 | -0.03465 | -0.0010506 | 0.070753 | 0.31831
| 2504 | 0.77 | -0.71173 | -0.25374 | 0.016384 | 0.47227 | 0.0028541 | 0.48299 | -0.5714 | -0.22019 | 0.0045604
| 2505 | -0.79776 | -0.60617 | 0.40192 | -0.11972 | 0.32051 | 0.50594 | 0.71592 | 0.31816 | -0.012427 | 0.26047
| 2506 | -0.065067 | 0.31758 | 0.29551 | -0.21878 | -0.48785 | -0.27979 | 0.1292 | 0.45036 | -0.91456 | 0.63654
| 2507 | 0.10485 | 0.018216 | 0.42598 | 0.75485 | -0.32985 | 0.19881 | -0.25307 | -0.46887 | -0.76442 | -0.055066
| 2508 | 0.94804 | -0.016384 | 0.35324 | -0.36952 | 0.58878 | -0.09518 | 0.089341 | -0.48707 | 0.44242 | 0.0052639
| 2509 | 0.17629 | -0.55156 | -0.26563 | -0.11484 | 0.60516 | 0.079728 | -0.1015 | -0.38575 | 0.47265 | 0.42355
| 2510 | 0.38153 | 0.38984 | -0.42965 | -0.5529 | 0.050105 | 0.40645 | 0.29042 | 0.2571 | -0.087914 | 0.1565
| 2511 | 0.39659 | 0.072476 | -0.35977 | -0.15923 | 0.39148 | 0.27785 | 0.3148 | -0.41442 | -0.1814 | -0.094959
| 2512 | -0.56377 | 0.82252 | 0.35587 | -0.32925 | 0.12564 | 0.38299 | 0.70521 | 0.07 | 0.61128 | -0.13184
| 2513 | -0.18116 | -0.44927 | -0.69553 | 0.49256 | 0.93292 | -0.071614 | -0.53859 | 0.17532 | -0.47436 | -0.58515
| 2514 | 0.60516 | 0.25616 | -0.32465 | 0.27137 | -0.34494 | -0.40544 | 0.42095 | 0.06293 | -0.0010506 | -0.31261
| 2515 | -0.38413 | 0.5015 | -0.80687 | 0.0091922 | -0.38396 | 0.45714 | 0.11484 | 0.32509 | -0.019949 | -0.56285
| 2516 | -0.38218 | 0.54316 | 0.20031 | -0.69129 | 0.10284 | -0.27137 | -0.47094 | 0.36794 | 0.22521 | 0.13855
| 2517 | 0.13832 | 0.26767 | 0.02568 | 0.054326 | 0.59417 | 0.20307 | 0.66758 | 0.20772 | -0.57869 | -0.044333
| 2518 | -0.69227 | 0.31802 | 0.18692 | -0.36164 | 0.64153 | 0.40008 | -0.21521 | -0.27288 | 0.17532 | -0.13196
| 2519 | -0.348 | 0.067637 | 0.41511 | -0.1852 | 0.42129 | -0.64772 | -0.040469 | 0.22728 | -0.67891 | -0.85269
| 2520 | -0.097947 | -0.55739 | 0.34053 | -0.97764 | -0.21266 | -0.27882 | -0.27688 | -0.2722 | -0.088134 | 0.70285
| 2521 | -0.11202 | -0.29099 | 0.32732 | -0.61803 | -0.11949 | 0.18312 | -0.27178 | 0.49334 | -0.038283 | 0.18299
| 2522 | -0.61542 | 0.032477 | -0.17181 | -0.19869 | -0.15638 | 0.59318 | 0.08474 | -0.29566 | 0.27965 | -0.31993
| 2523 | 0.4902 | 0.32096 | -0.37064 | 0.058884 | 0.18938 | -0.093523 | 0.86546 | -0.048212 | -0.23508 | 0.21317
| 2524 | -0.2941 | -0.16054 | 0.22148 | 0.83845 | -0.0042591 | 0.20975 | -0.30957 | 0.25589 | 0.23234 | -0.074095
| 2525 | 0.40393 | -0.57233 | -0.11813 | -0.3025 | 0.20232 | 0.1786 | 0.32583 | 0.25388 | -0.164 | 0.49631
| 2526 | -0.65402 | 0.58951 | 0.012528 | -0.19931 | 0.43053 | 0.24853 | 0.31087 | 0.079077 | 0.59738 | 0.0087886
| 2527 | 0.8937 | -0.38902 | 0.19869 | -0.21254 | -0.073771 | 0.49334 | -0.66758 | 0.17 | -0.068067 | -0.20546
| 2528 | 0.75363 | 0.11135 | 0.086381 | -0.5201 | 0.012123 | -0.14355 | 0.030103 | -0.25254 | 0.15165 | -0.057079
| 2529 | -0.44674 | 0.43281 | 0.41391 | 0.11124 | -0.85893 | -0.11462 | 0.016994 | 0.025064 | 0.21866 | 0.050632
| 2530 | -0.86923 | -0.17423 | 0.38396 | -0.019235 | 0.5009 | 0.10072 | -0.34525 | 0.25 | 0.2265 | -0.49039
| 2531 | -0.39016 | -0.53816 | 0.41459 | -0.50837 | -0.034547 | 0.75282 | 0.60694 | 0.18079 | 0.29127 | -0.079402
| 2532 | 0.50553 | -0.42877 | 0.097836 | 0.17556 | -0.5458 | -0.24575 | -0.58757 | 0.40814 | 0.087038 | 0.040782
| 2533 | 0.54207 | 0.20319 | -0.26278 | 0.41733 | 0.44224 | -0.9219 | 0.16066 | -0.0023528 | -0.059734 | -0.013339
| 2534 | 0.28663 | 0.11869 | -0.071722 | 0.2958 | 0.24469 | -0.021992 | 0.21597 | -0.3961 | 0.1063 | 0.67922
| 2535 | 0.46288 | -0.40209 | 0.14894 | 0.85134 | -0.18988 | -0.097393 | -0.38234 | -0.34266 | 0.41255 | 0.1323
| 2536 | -0.093854 | -0.034547 | 0.11541 | -0.12245 | -0.098501 | 0.24907 | -0.19408 | -0.20094 | -0.5656 | 0.54229
| 2537 | -0.71035 | 0.10955 | -0.17617 | 0.64489 | -0.41974 | -0.82479 | -0.63931 | 0.63792 | 0.37799 | -0.049263
| 2538 | 0.59318 | 0.54536 | 0.4755 | 0.047792 | 0.44746 | 0.71173 | 0.54448 | 0.0027538 | -0.29879 | 0.69619
| 2539 | -0.79975 | -0.28635 | -0.19049 | 0.23482 | -0.15816 | -0.10596 | -0.47933 | -0.25027 | 0.17982 | -0.10708
| 2540 | -0.45237 | -0.22212 | -0.40662 | 0.41 | -0.25737 | -0.19545 | -0.14332 | 0.024039 | 0.077016 | -0.42493
| 2541 | -0.44331 | 0.084959 | 0.5003 | 0.61829 | -0.17205 | -0.65518 | -0.53171 | 0.069033 | 0.3294 | -0.46213
| 2542 | 0.40125 | 0.051791 | -0.21546 | 0.37944 | -0.27605 | -0.074527 | 0.29438 | 0.1769 | 0.20019 | 0.55717
| 2543 | 0.082231 | -0.38869 | -0.59888 | 0.092531 | 0.80125 | -0.0068736 | 0.47076 | -0.4293 | -0.24007 | 0.71312
| 2544 | 0.66399 | -0.041407 | -0.13739 | -0.37686 | 0.43991 | 0.93 | 0.31392 | 0.48804 | 0.84094 | 0.77932
| 2545 | -0.1179 | 0.070645 | 0.28007 | 0.46774 | 0.0030547 | 0.053163 | 0.077666 | -0.47493 | 0.25374 | -0.5436
| 2546 | 0.64744 | 0.071076 | -0.4653 | 0.74407 | 0.47189 | -0.20772 | 0.36039 | -0.17775 | -0.11733 | -0.55739
| 2547 | 0.43229 | 0.089341 | -0.40595 | 0.58443 | -0.95417 | 0.50573 | -0.1063 | 0.17374 | -0.5021 | -0.24257
| 2548 | -0.66668 | -0.15875 | 0.48473 | 0.49512 | -0.39428 | 0.28958 | -0.83417 | -0.54646 | -0.22508 | -0.79925
| 2549 | -0.071722 | 0.24336 | 0.32539 | 0.29381 | 0.82139 | -0.1375 | -0.46981 | -0.66728 | 0.63931 | 0.55739
| 2550 | 0.073339 | 0.20848 | -0.22767 | 0.58036 | -0.30265 | -0.55379 | 0.28188 | -0.36526 | -0.4307 | 0.52136
| 2551 | 0.032891 | -0.35448 | 0.13855 | 0.74368 | -0.12759 | 0.11972 | -0.013542 | 0.015673 | 0.18852 | 0.1237
| 2552 | -0.10563 | -0.57656 | 0.16496 | 0.037244 | -0.24641 | -0.20081 | -0.14695 | -0.068281 | -0.43706 | 0.60415
| 2553 | -0.094848 | 0.16173 | -0.025474 | 0.22456 | -0.2674 | 0.35278 | 0.10406 | -0.49671 | -0.11451 | -0.23954
| 2554 | 0.098058 | -0.66133 | 0.36984 | -0.47684 | -0.0089904 | 0.22238 | 0.08343 | 0.09839 | 0.43724 | 0.52915
| 2555 | -0.21968 | 0.51164 | 0.17109 | 0.71663 | 0.53 | 0.42095 | -0.42947 | -0.38348 | 0.21419 | -0.8366
| 2556 | -0.2571 | -0.066565 | -0.36589 | 0.026296 | 0.0077803 | 0.84412 | 0.020357 | -0.013238 | -0.36526 | -0.42703
| 2557 | 0.62384 | -0.59269 | 0.42772 | -0.34678 | 0.21457 | -0.51102 | -0.4471 | 0.42372 | 0.64772 | -0.18348
| 2558 | -0.13207 | -0.047792 | 0.33524 | 0.1921 | 0.82593 | 0.45603 | -0.2602 | 0.37783 | -0.19969 | -0.22328
| 2559 | -0.22186 | 0.80739 | 0.50654 | 0.28063 | -0.36604 | -0.035272 | 0.75201 | 0.024244 | -0.86472 | 0.29708
| 2560 | -0.025782 | 0.15507 | 0.20006 | -0.21521 | -0.7042 | -0.1382 | -0.55424 | 0.077341 | 0.26522 | 0.40797
| 2561 | 0.075176 | -0.85893 | 0.039531 | -0.12644 | 0.90566 | 0.26808 | 0.5721 | 0.40477 | -0.32022 | 0.65402
| 2562 | -0.29282 | 0.15958 | -0.94615 | -0.33917 | -0.67735 | 0.11665 | 0.33254 | -0.17738 | -0.031857 | -0.17641
| 2563 | -0.47151 | 0.49137 | 0.35945 | 0.59318 | 0.57727 | 0.23013 | 0.26061 | -0.83177 | -0.35293 | 0.22212
| 2564 | -0.58083 | -0.04266 | -0.49394 | 0.31043 | -0.40578 | 0.16101 | 0.30552 | -0.13634 | 0.49493 | 0.3851
| 2565 | -0.17411 | -0.18153 | -0.065602 | -0.72926 | -0.24853 | -0.37095 | -0.58036 | 0.80843 | 0.22045 | 0.063144
| 2566 | -0.054749 | -0.23039 | -0.7429 | -0.088792 | -0.15436 | 0.84348 | -0.13924 | -0.43938 | -0.4981 | 0.6162
| 2567 | -0.022299 | 0.01263 | -0.74446 | 0.15318 | -0.17459 | 0.040156 | -0.057716 | 0.30538 | 0.10039 | -0.56102
| 2568 | 0.47798 | -0.21968 | -0.042347 | -0.15839 | -0.20081 | 0.39197 | -0.047162 | -0.039011 | -0.8422 | -0.24721
| 2569 | -0.25428 | -0.69652 | -0.021481 | -0.36699 | 0.012225 | 0.61361 | -0.027015 | -0.41768 | 0.4307 | -0.64125
| 2570 | 0.2287 | -0.068925 | -0.26549 | -0.1879 | 0.67061 | -0.16699 | -0.086928 | -0.09121 | -0.007075 | 0.48067
| 2571 | 0.040052 | 0.20081 | -0.21533 | 0.36841 | 0.16723 | -0.31538 | -0.052635 | 0.3025 | -0.29056 | -0.49374
| 2572 | 0.0066723 | 0.10899 | -0.077016 | -0.18165 | 0.53578 | -0.13276 | -0.12943 | -0.5141 | -0.21254 | -0.29113
| 2573 | -0.85405 | 0.039531 | 0.45567 | -0.62463 | -0.1513 | 0.53946 | -0.031548 | -0.37494 | 0.40125 | -0.53064
| 2574 | -0.22521 | -0.047477 | 0.47569 | 0.017605 | -0.16209 | 0.65634 | 0.23928 | 0.042347 | -0.40578 | -0.19272
| 2575 | -0.26034 | -0.64265 | -0.072153 | -0.099722 | -0.58491 | -0.14099 | 0.082558 | 0.52261 | 0.33419 | -0.37976
| 2576 | 0.050948 | -0.43848 | -0.17386 | -0.65751 | 0.59788 | 0.50392 | 0.16232 | -0.64687 | 0.45055 | 0.16759
| 2577 | -0.052635 | 0.054431 | 0.37944 | 0.26034 | 0.79 | -0.20659 | -0.09088 | 0.10429 | 0.41596 | 0.34053
| 2578 | 0.0079819 | -0.057291 | 0.55357 | -0.47493 | 0.079946 | -0.50331 | -0.40142 | -0.39428 | -0.17508 | -0.89091
| 2579 | -0.10608 | -0.82824 | -0.17702 | -0.148 | 0.5436 | -0.085615 | -0.15816 | 0.40092 | -0.18275 | -0.33449
| 2580 | -0.41068 | 0.55853 | 0.055807 | 0.2893 | -0.34023 | -0.69884 | 0.11711 | 0.37446 | 0.51595 | 0.58275
| 2581 | 0.1034 | 0.17763 | -0.1884 | 0.59073 | 0.84094 | -0.3038 | 0.21802 | 0.16507 | 0.18557 | 0.41221
| 2582 | -0.3568 | 0.37239 | 0.065388 | -0.7512 | 0.23705 | 0.29807 | -0.0019519 | -0.059202 | 0.013035 | -0.14367
| 2583 | 0.63353 | -0.7488 | 0.21343 | 0.45548 | 0.3297 | -0.51616 | 0.020766 | -0.32747 | -0.034133 | -0.26577
| 2584 | 0.097836 | 0.16663 | 0.19831 | -0.00085036 | -0.11586 | 0.16197 | -0.45475 | 0.052952 | 0.56377 | -0.26563
| 2585 | 0.051475 | 0.52115 | -0.38722 | 0.8467 | 0.36039 | 0.23809 | -0.48164 | 0.2674 | 0.14332 | -0.11552
| 2586 | 0.16173 | -0.85823 | 0.28216 | 0.079185 | -0.27938 | -0.48029 | 0.069677 | 0.13843 | -0.12427 | 0.46251
| 2587 | -0.022196 | 0.094075 | 0.075392 | 0.31131 | 0.31524 | -0.43866 | -0.32494 | 0.16687 | -0.34892 | 0.22767
| 2588 | -0.02281 | 0.042347 | -0.31495 | -0.21699 | 0.003155 | -0.12633 | 0.061118 | 0.050737 | -0.22045 | -0.84348
| 2589 | -0.16077 | -0.097282 | -0.50756 | 0.19894 | -0.36526 | 0.76188 | -0.19906 | 0.17121 | 0.013136 | 0.21546
| 2590 | 0.26441 | 0.74096 | 0.3005 | 0.15982 | -0.38657 | 0.83538 | -0.032477 | 0.056867 | 0.54448 | 0.77
| 2591 | 0.77887 | -0.53837 | 0.4987 | 0.23052 | -0.54338 | -0.24734 | -0.41768 | -0.58491 | -0.16531 | -0.32169
| 2592 | -0.47493 | 0.060585 | 0.58371 | -0.078859 | -0.2995 | 0.27771 | -0.71138 | -0.010202 | 0.21725 | -0.8755
| 2593 | -0.047792 | -0.059096 | 0.43423 | -0.092641 | -0.25643 | -0.43759 | -0.70017 | 0.35541 | -0.21051 | 0.015978
| 2594 | -0.080598 | -0.63217 | -0.21254 | -0.022196 | 0.10507 | -0.34357 | 0.23744 | 0.022606 | -0.34053 | 0.18877
| 2595 | 0.15709 | -0.61882 | -0.40292 | 0.15106 | 0.34862 | 0.44583 | -0.028764 | -0.30639 | 0.84031 | -0.020561
| 2596 | 0.45714 | 0.12564 | -0.50432 | -0.57468 | -0.37879 | 0.70931 | 0.10776 | -0.26441 | 0.30193 | 0.9005
| 2597 | -0.35401 | -0.19719 | -0.15118 | 0.65316 | -0.72779 | 0.82883 | -0.39942 | -0.056867 | 0.41579 | 0.47952
| 2598 | -0.14367 | -0.32955 | -0.68172 | -0.020153 | -0.032581 | -0.31568 | 0.042138 | 0.0081835 | 0.1432 | 0.41357
| 2599 | 0.81588 | 0.056019 | 0.28775 | -0.099611 | 0.17738 | -0.8995 | -0.13658 | -0.2037 | 0.464 | 0.24535
| 2600 | -0.43281 | -0.038283 | -0.41785 | 0.41613 | -0.10006 | -0.35634 | 0.40932 | -0.031238 | 0.43123 | 0.3248
| 2601 | -0.42755 | 0.16567 | 0.6044 | -0.26767 | 0.06325 | -0.30595 | -0.88295 | 0.69488 | 0.0866 | 0.13057
| 2602 | 0.071722 | 0.037347 | 0.27744 | 0.87876 | -0.62892 | -0.45769 | 0.044647 | -0.58036 | -0.40159 | -0.7015
| 2603 | -0.54338 | -0.3454 | 0.093854 | 0.47132 | 0.13774 | -0.10161 | 0.38089 | 0.93597 | -0.055595 | 0.30769
| 2604 | -0.60821 | 0.76784 | 0.048002 | -0.45548 | -0.080598 | -0.053374 | 0.077991 | -0.051053 | 0.098723 | 0.68235
| 2605 | 0.31422 | 0.74722 | -0.41391 | 0.26413 | -0.49691 | 0.59196 | 0.026398 | 0.66459 | 0.42251 | 0.058246
| 2606 | -0.23705 | 0.51143 | 0.47875 | 0.18128 | -0.28986 | 0.16412 | -0.56262 | 0.39942 | -0.32702 | -0.2773
| 2607 | 0.38202 | -0.096175 | 0.2744 | -0.12667 | -0.41102 | 0.66789 | -0.43884 | -0.019541 | 0.58395 | 0.23234
| 2608 | 0.47569 | 0.36715 | -0.0090913 | 0.06914 | -0.078425 | -0.095069 | 0.51906 | -0.42303 | 0.74761 | -0.54911
| 2609 | 0.29807 | 0.49275 | -0.29495 | -0.16232 | -0.15768 | 0.44493 | 0.093303 | -0.25656 | -0.085068 | -0.33902
| 2610 | 0.64801 | -0.039011 | 0.21432 | -0.2287 | 0.064639 | 0.44188 | -0.89 | 0.20735 | 0.0045604 | 0.75731
| 2611 | -0.47038 | -0.44063 | -0.41974 | -0.13242 | -0.37254 | 0.35852 | 0.3951 | -0.39925 | -0.21814 | 0.0056661
| 2612 | 0.2995 | -0.89656 | 0.13299 | 0.15306 | 0.33329 | 0.014353 | -0.25939 | 0.55424 | -0.52219 | 0.42199
| 2613 | -0.22844 | 0.53107 | 0.096507 | -0.099278 | -0.76399 | 0.6118 | 0.41682 | -0.64886 | -0.39197 | -0.71312
| 2614 | -0.45 | 0.05496 | -0.0057666 | 0.46083 | 0.0016514 | 0.32643 | 0.24628 | -0.17909 | 0.14601 | -0.22199
| 2615 | 0.21776 | -0.24508 | -0.073339 | 0.11191 | 0.11892 | 0.39131 | 0.75855 | -0.4668 | 0.016893 | 0.60289
| 2616 | -0.15768 | -0.097393 | -0.0072765 | -0.092421 | -0.39362 | 0.39016 | 0.62039 | -0.11496 | -0.6338 | 0.63135
| 2617 | -0.15247 | 0.65086 | -0.11417 | 0.12393 | -0.11112 | 0.17036 | 0.30423 | 0.54163 | -0.39461 | 0.019235
| 2618 | -0.49374 | -0.53021 | -0.088463 | 0.18238 | -0.43777 | -0.84284 | 0.57538 | 0.65751 | -0.50918 | 0.46512
| 2619 | -0.20533 | 0.42493 | 0.54756 | -0.035376 | -0.14976 | -0.46232 | 0.47 | 0.18434 | 0.12359 | 0.66728
| 2620 | -0.3005 | 0.20558 | -0.79048 | -0.49512 | -0.37048 | -0.40058 | -0.69065 | 0.19881 | 0.31524 | -0.16663
| 2621 | -0.10172 | -0.23993 | -0.80379 | -0.36889 | -0.19074 | 0.4736 | 0.057503 | -0.5013 | 0.1269 | 0.74761
| 2622 | 0.52703 | -0.24007 | -0.49196 | 0.46418 | 0.043914 | 0.40042 | -0.49039 | 0.60541 | -0.063677 | 0.098612
| 2623 | -0.021379 | 0.70017 | -0.083321 | -0.91225 | 0.45861 | 0.32435 | 0.47151 | 0.28817 | 0.19956 | 0.13739
| 2624 | -0.032167 | -0.6371 | -0.10529 | -0.18508 | 0.34985 | 0.018725 | 0.094738 | -0.41255 | 0.11938 | -0.41836
| 2625 | -0.18692 | 0.21343 | 0.54911 | -0.14507 | -0.1752 | -0.1884 | 0.71769 | 0.94255 | -0.12324 | -0.4078
| 2626 | 0.45603 | 0.81917 | 0.14531 | -0.051053 | -0.42895 | -0.073016 | -0.79678 | 0.37863 | -0.59073 | -0.69586
| 2627 | 0.21152 | 0.26034 | 0.30394 | -0.59441 | -0.016791 | -0.39066 | 0.76063 | -0.18226 | -0.042347 | 0.22521
| 2628 | 0.081904 | -0.31043 | 0.23234 | 0.74682 | 0.65287 | -0.30236 | -0.080381 | -0.12267 | -0.56907 | 0.03434
| 2629 | -0.032788 | -0.013744 | 0.026912 | 0.067959 | 0.26115 | -0.77841 | 0.61594 | 0.35355 | -0.43035 | 0.37462
| 2630 | -0.21789 | 0.19881 | -0.51761 | -0.42615 | 0.56239 | 0.1323 | -0.70453 | 0.65693 | 0.4232 | 0.30855
| 2631 | 0.69718 | -0.30812 | 0.28537 | -0.37254 | -0.12051 | -0.16436 | 0.57093 | 0.20785 | -0.79143 | 0.57468
| 2632 | -0.19148 | -0.45917 | -0.008486 | 0.031651 | -0.14472 | 0.37032 | -0.11315 | 0.4041 | -0.73561 | -0.18385
| 2633 | 0.076041 | -0.49592 | -0.056019 | 0.84157 | -0.28747 | 0.69619 | -0.26332 | 0.84801 | 0.67182 | 0.28299
| 2634 | 0.1072 | -0.42337 | 0.5721 | -0.68647 | -0.22122 | 0.49157 | -0.032167 | 0.099389 | -0.068174 | -0.48902
| 2635 | 0.29268 | -0.43458 | -0.40443 | -0.38804 | 0.0029544 | 0.49671 | -0.22676 | -0.058565 | 0.66638 | 0.094296
| 2636 | -0.17933 | -0.24349 | -0.37494 | 0.45585 | 0.11949 | 0.39279 | 0.014353 | 0.20646 | 0.25 | -0.50918
| 2637 | -0.61051 | 0.23104 | 0.063571 | -0.00035006 | 0.069248 | 0.64042 | -0.080163 | 0.2313 | -0.32658 | 0.34266
| 2638 | -0.27674 | -0.7569 | 0.60821 | -0.47057 | -0.39942 | 0.009697 | -0.45991 | -0.91112 | 0.19769 | 0.24072
| 2639 | 0.95641 | 0.23587 | -0.83417 | -0.4531 | -0.3796 | 0.56861 | 0.13878 | 0.19346 | -0.015978 | 0.26767
| 2640 | -0.12633 | 0.91 | 0.0069743 | 0.3025 | -0.068603 | -0.4736 | 0.36086 | -0.5001 | 0.69162 | -0.75403
| 2641 | 0.63627 | 0.22096 | 0.3767 | 0.41974 | -0.21942 | -0.0028541 | -0.89851 | 0.18655 | -0.82422 | -0.77528
| 2642 | 0.45164 | -0.87 | 0.52219 | -0.66849 | -0.19582 | -0.29993 | -0.60314 | 0.39181 | 0.36841 | -0.26169
| 2643 | 0.40477 | 0.018012 | 0.49394 | -0.37398 | -0.43902 | 0.15377 | -0.23901 | -0.084959 | 0.25737 | -0.017809
| 2644 | -0.14777 | 0.60263 | -0.52957 | 0.62384 | 0.21955 | 0.5174 | 0.56216 | -0.48087 | -0.21648 | 0.68488
| 2645 | 0.41238 | -0.29822 | -0.7245 | 0.26658 | 0.27302 | -0.30437 | 0.57116 | 0.16376 | -0.46083 | 0.7512
| 2646 | 0.19794 | -0.029485 | -0.060372 | -0.22948 | -0.68425 | -0.43088 | 0.27123 | 0.4194 | 0.032374 | 0.050211
| 2647 | -0.78251 | 0.097725 | -0.71312 | -0.02794 | -0.017809 | 0.01091 | 0.52873 | 0.42842 | -0.21368 | 0.48824
| 2648 | 0.18043 | -0.21955 | -0.043078 | -0.006169 | 0.28439 | -0.089561 | -0.26318 | -0.65634 | 0.028764 | -0.23652
| 2649 | 0.053691 | -0.079946 | 0.23443 | -0.42303 | 0.054749 | -0.13484 | -0.59689 | -0.11881 | -0.19557 | 0.54646
| 2650 | 0.59294 | 0.1127 | -0.065495 | -0.41425 | 0.24548 | 0.075716 | 0.67612 | 0.33494 | -0.48376 | -0.079946
| 2651 | -0.21432 | -0.57774 | -0.058777 | -0.028764 | 0.49651 | -0.59738 | 0.17848 | -0.16916 | -0.66133 | -0.10787
| 2652 | -0.056549 | 0.67643 | -0.33841 | 0.14988 | -0.17872 | -0.20458 | 0.37526 | -0.84348 | -0.2508 | -0.55267
| 2653 | -0.57538 | 0.084631 | 0.58347 | 0.074203 | -0.4776 | -0.13011 | 0.48804 | 0.68871 | 0.18864 | 0.074311
| 2654 | 0.12006 | 0.094738 | -0.32361 | 0.060692 | 0.18116 | 0.80584 | 0.21304 | 0.64042 | -0.51886 | 0.41
| 2655 | 0.46251 | -0.77796 | 0.21051 | 0.098612 | 0.33284 | 0.17386 | 0.64125 | 0.28035 | -0.66728 | -0.076366
| 2656 | 0.060479 | 0.14742 | 0.65693 | -0.11146 | 0.42233 | -0.5007 | -0.36762 | 0.36984 | 0.16735 | 0.49256
| 2657 | -0.44964 | -0.12165 | -0.62092 | -0.3593 | -0.2492 | 0.85 | -0.039531 | -0.35 | -0.098945 | 0.41819
| 2658 | -0.028249 | 0.26441 | 0.68016 | -0.51844 | 0.74212 | 0.35308 | 0.034547 | 0.5264 | -0.050948 | -0.0059678
| 2659 | 0.14718 | -0.19533 | -0.24376 | -0.28257 | 0.53385 | 0.19421 | 0.60846 | -0.38413 | 0.26904 | 0.85067
| 2660 | -0.097836 | 0.61412 | 0.91112 | 0.02609 | 0.15035 | -0.70352 | 0.29836 | 0.084085 | -0.10006 | -0.32214
| 2661 | -0.83845 | 0.46158 | 0.56977 | -0.38105 | -0.18692 | 0.57988 | 0.52052 | 0.57562 | 0.54734 | 0.8366
| 2662 | -0.29381 | -0.88731 | 0.34479 | -0.092751 | 0.20382 | -0.22173 | -0.88909 | 0.033305 | 0.087147 | -0.19309
| 2663 | 0.1921 | 0.64914 | -0.66608 | 0.93917 | -0.13901 | -0.4134 | -0.023936 | -0.088024 | -0.71138 | 0.77175
| 2664 | -0.58733 | -0.26727 | 0.33434 | -0.076366 | -0.02794 | 0.51123 | -0.3796 | 0.39626 | -0.24827 | 0.35339
| 2665 | 0.26128 | 0.42424 | 0.032167 | 0.15578 | -0.31509 | 0.71138 | -0.56011 | 0.056231 | -0.0045604 | -0.49
| 2666 | 0.41187 | -0.26631 | -0.41459 | -0.048002 | 0.23718 | -0.079837 | -0.32762 | 0.62463 | 0.3767 | -0.34617
| 2667 | 0.046638 | -0.41136 | 0.0090913 | 0.71522 | 0.30265 | 0.38105 | 0.086819 | 0.35293 | -0.10239 | 0.2313
| 2668 | -0.1863 | -0.54294 | -0.56722 | 0.54142 | -0.59073 | -0.35618 | -0.22019 | 0.65868 | 0.012123 | 0.060905
| 2669 | -0.50898 | -0.40343 | 0.19309 | -0.21152 | -0.84867 | 0.65086 | -0.39477 | -0.56102 | 0.11903 | 0.31597
| 2670 | 0.20621 | -0.08234 | 0.75731 | -0.42112 | -0.4134 | -0.70285 | -0.25495 | -0.077124 | 0.28411 | 0.09706
| 2671 | -0.0085869 | 0.26754 | -0.096396 | 0.13843 | -0.093303 | -0.15118 | -0.31568 | 0.68204 | 0.51164 | -0.83599
| 2672 | -0.69718 | -0.40393 | 0.86696 | 0.042555 | -0.19471 | -0.030309 | -0.02281 | -0.19062 | 0.12656 | 0.37223
| 2673 | 0.24086 | -0.45935 | -0.17374 | -0.0090913 | -0.50898 | -0.6338 | -0.25508 | 0.11394 | -0.23652 | 0.43848
| 2674 | 0.58131 | -0.095511 | -0.19124 | -0.11135 | -0.27827 | -0.35556 | 0.12439 | -0.39759 | -0.47379 | 0.063998
| 2675 | -0.53967 | -0.1353 | 0.15863 | -0.14613 | -0.69324 | -0.056019 | -0.39792 | 0.33284 | 0.039011 | -0.26617
| 2676 | -0.14099 | -0.35092 | -0.60541 | -0.43724 | 0.0092932 | 0.31058 | -0.17714 | -0.087257 | 0.2823 | 0.2431
| 2677 | -0.1063 | -0.5098 | -0.56422 | -0.15685 | -0.051897 | 0.20131 | 0.05253 | 0.14111 | 0.11801 | 0.13565
| 2678 | 0.32732 | -0.29183 | -0.3419 | 0.1884 | -0.080054 | -0.16424 | 0.48338 | -0.075068 | 0.72596 | 0.09518
| 2679 | -0.6162 | 0.41 | -0.21152 | -0.15224 | 0.2524 | -0.40477 | 0.25737 | 0.2042 | -0.57633 | 0.7508
| 2680 | -0.071184 | -0.54076 | -0.22935 | 0.13057 | -0.55156 | 0.00035006 | -0.17145 | 0.12667 | 0.050316 | -0.552
| 2681 | 0.42303 | 0.092862 | 0.18324 | -0.74019 | 0.48222 | -0.2524 | -0.81426 | -0.1063 | 0.60465 | 0.011011
| 2682 | 0.29893 | 0.28733 | -0.17726 | 0.038179 | 0.31685 | -0.69619 | -0.15792 | -0.50291 | 0.09165 | 0.36683
| 2683 | 0.40108 | -0.098834 | 0.37702 | -0.0082843 | 0.0042591 | -0.87 | 0.37638 | 0.79048 | 0.084959 | -0.40814
| 2684 | 0.04026 | -0.18128 | 0.094848 | 0.18165 | -0.2402 | 0.30079 | 0.61803 | -0.81972 | -0.35278 | -0.33224
| 2685 | 0.29921 | -0.21776 | -0.46046 | -0.039115 | -0.17024 | -0.082231 | -0.27014 | 0.61361 | -0.5608 | -0.38836
| 2686 | 0.013035 | 0.42546 | 0.45055 | 0.53902 | -0.18557 | -0.19 | -0.016689 | 0.28439 | 0.32569 | 0.27647
| 2687 | 0.24178 | -0.24244 | -0.33359 | 0.77306 | 0.021276 | -0.15236 | -0.008486 | 0.66044 | -0.40797 | -0.011213
| 2688 | -0.61699 | -0.1473 | 0.72669 | 0.2234 | 0.074635 | 0.13322 | 0.10552 | -0.3593 | 0.017707 | 0.17411
| 2689 | -0.44457 | 0.7881 | 0.93144 | 0.31875 | -0.64574 | 0.53449 | -0.39759 | -0.88554 | -0.42355 | 0.56468
| 2690 | -0.19732 | 0.1863 | -0.20987 | -0.43742 | 0.035376 | 0.5007 | -0.20962 | 0.65431 | 0.21776 | -0.37751
| 2691 | -0.13069 | -0.3242 | 0.022094 | -0.38592 | -0.15295 | -0.12599 | 0.26169 | -0.086271 | -0.06229 | -0.12245
| 2692 | 0.78023 | -0.38008 | 0.24973 | 0.046428 | -0.48746 | -0.021379 | -0.28719 | -0.46195 | -0.74603 | -0.24125
| 2693 | -0.25777 | 0.20483 | 0.42982 | 0.018725 | -0.3425 | 0.58012 | -0.26877 | -0.011617 | -0.64293 | -0.87793
| 2694 | 0.90253 | -0.23888 | -0.077883 | 0.022299 | 0.096285 | -0.26128 | -0.16627 | 0.034443 | -0.1044 | 0.13994
| 2695 | 0.016079 | -0.19037 | -0.27247 | 0.075284 | -0.066137 | 0.23026 | -0.83599 | -0.093854 | 0.41699 | -0.55134
| 2696 | -0.12131 | -0.32539 | 0.14554 | -0.70794 | -0.17982 | 0.43158 | -0.068281 | -0.9134 | -0.023936 | -0.0072765
| 2697 | 0.0042591 | 0.12461 | 0.32317 | -0.52492 | -0.74096 | -0.059309 | 0.24694 | -0.35077 | -0.37751 | -0.0086877
| 2698 | -0.58951 | 0.0021523 | -0.55402 | -0.55785 | 0.02189 | -0.0049623 | 0.53989 | 0.59245 | 0.12931 | 0.024756
| 2699 | 0.58539 | -0.76272 | 0.5245 | 0.15673 | -0.37079 | -0.9272 | -0.056019 | -0.52094 | -0.43795 | 0.16964
| 2700 | -0.78905 | 0.81534 | -0.3817 | -0.010101 | 0.12097 | 0.20571 | 0.34388 | 0.67121 | 0.6786 | 0.8467
| 2701 | -0.2625 | 0.81212 | 0.60592 | -0.11236 | -0.11733 | 0.10944 | 0.67458 | -0.33164 | -0.8821 | 0.70083
| 2702 | -0.25347 | -0.1153 | 0.87631 | 0.23312 | 0.019745 | 0.15578 | -0.059202 | -0.43299 | 0.27069 | 0.58179
| 2703 | 0.15448 | 0.27716 | 0.69259 | 0.20937 | -0.19371 | 0.67735 | 0.45182 | -0.67458 | 0.36117 | 0.71911
| 2704 | -0.40276 | -0.12017 | 0.51225 | -0.20571 | 0.52534 | 0.364 | 0.19247 | 0.041512 | 0.05253 | 0.31203
| 2705 | -0.077774 | -0.36102 | -0.12496 | -0.3303 | 0.082558 | 0.13219 | 0.73261 | -0.40915 | 0.0036567 | 0.043078
| 2706 | -0.42511 | 0.77175 | -0.17133 | 0.30711 | -0.56445 | 0.54734 | 0.23626 | -0.20144 | 0.36889 | 0.003456
| 2707 | -0.60314 | -0.026193 | -0.22469 | -0.18557 | 0.79433 | 0.52261 | -0.32569 | -0.17617 | -0.0030547 | -0.022708
| 2708 | -0.13253 | 0.34586 | -0.063144 | -0.85543 | -0.16928 | 0.024346 | -0.10541 | 0.30639 | -0.25966 | 0.018929
| 2709 | -0.74058 | 0.046952 | -0.3454 | 0.35634 | 0.22857 | 0.35587 | -0.056761 | -0.20646 | 0.27536 | 0.52471
| 2710 | 0.4987 | 0.079946 | 0.019439 | 0.30653 | 0.10541 | 0.60389 | 0.72233 | 0.10017 | -0.38853 | -0.46493
| 2711 | -0.087366 | 0.10978 | 0.83783 | 0.58155 | 0.52661 | -0.46306 | 0.35308 | -0.63217 | 0.4286 | -0.12816
| 2712 | 0.59988 | -0.15071 | -0.2427 | -0.59171 | -0.3961 | -0.28551 | -0.22212 | -0.14507 | -0.18055 | -0.49433
| 2713 | 0.69685 | -0.97354 | -0.057079 | -0.14472 | -0.83059 | 0.058034 | 0.67152 | 0.49216 | 0.34494 | 0.59813
| 2714 | -0.15436 | -0.52177 | 0.63545 | 0.4653 | 0.33239 | -0.4194 | 0.06261 | 0.36305 | 0.13461 | 0.85613
| 2715 | 0.30437 | -0.58131 | -0.31934 | -0.14894 | -0.32866 | -0.35 | 0.59122 | 0.11304 | -0.31934 | -0.0085869
| 2716 | 0.5608 | 0.30265 | 0.52157 | -0.077124 | -0.042242 | -0.28411 | 0.44224 | -0.070108 | -0.42095 | 0.030309
| 2717 | -0.017809 | 0.60491 | -0.46158 | -0.22032 | -0.13716 | -0.060479 | 0.6833 | -0.56768 | 0.19994 | -0.0173
| 2718 | -0.18618 | -0.044647 | 0.024859 | -0.61751 | 0.18092 | -0.22521 | -0.76021 | -0.46288 | -0.18067 | -0.30437
| 2719 | 0.71104 | -0.077558 | 0.16268 | 0.076366 | 0.52136 | -0.38885 | 0.11496 | -0.18397 | 0.5019 | 0.49157
| 2720 | 0.15342 | 0.36541 | -0.0995 | 0.19346 | 0.0068736 | -0.81588 | 0.45972 | 0.41255 | -0.56171 | -0.006169
| 2721 | 0.4046 | 0.19346 | -0.47322 | 0.10843 | -0.27813 | -0.19272 | -0.085396 | -0.34601 | -0.46624 | 0.50735
| 2722 | 0.56216 | -0.58951 | 0.28202 | -0.42947 | 0.15271 | -0.24893 | -0.7042 | 0.13253 | 0.015368 | 0.078968
| 2723 | 0.39643 | 0.47493 | 0.10596 | 0.022401 | -0.12404 | -0.11372 | -0.017401 | 0.53107 | 0.23325 | -0.019949
| 2724 | -0.020868 | -0.64209 | 0.59938 | -0.68711 | -0.41238 | 0.16723 | 0.079402 | 0.1418 | -0.018012 | -0.29907
| 2725 | -0.21687 | -0.5447 | 0.23901 | -0.16579 | -0.22702 | -0.098612 | 0.8739 | 0.17036 | 0.10764 | 0.30164
| 2726 | 0.36557 | -0.30466 | -0.26413 | 0.58275 | -0.4859 | 0.63682 | 0.52429 | -0.0090913 | -0.21152 | 0.66251
| 2727 | 0.19235 | -0.45787 | 0.028764 | 0.19433 | -0.031961 | 0.22948 | 0.1735 | -0.078859 | -0.57917 | -0.049579
| 2728 | -0.030412 | -0.058565 | -0.27702 | 0.34433 | 0.40578 | 0.0781 | -0.46418 | -0.033822 | 0.12747 | -0.75363
| 2729 | 0.92859 | 0.19632 | 0.15567 | 0.13173 | 0.49098 | -0.26332 | -0.29836 | 0.2791 | 0.45843 | 0.15401
| 2730 | 0.30408 | 0.013744 | 0.50452 | 0.23534 | 0.37911 | 0.11733 | -0.30222 | 0.4265 | 0.20886 | -0.28887
| 2731 | -0.049684 | -0.1863 | 0.30595 | 0.045484 | 0.67829 | 0.22883 | 0.53707 | -0.34525 | -0.31261 | 0.030928
| 2732 | 0.14988 | -0.27467 | 0.16125 | 0.68903 | -0.39792 | -0.065174 | -0.10239 | 0.75648 | 0.42807 | 0.65839
| 2733 | -0.24402 | -0.1127 | -0.13971 | 0.22379 | -0.030206 | -0.16687 | 0.16759 | -0.67798 | -0.51761 | 0.04517
| 2734 | 0.046952 | -0.83907 | -0.35696 | 0.22598 | 0.30495 | 0.53816 | 0.0065716 | 0.79826 | 0.43831 | -0.36463
| 2735 | 0.080489 | -0.35977 | 0.043705 | 0.28733 | 0.049263 | 0.15247 | 0.40713 | 0.21051 | 0.66909 | 0.052846
| 2736 | 0.040886 | 0.17265 | 0.24099 | 0.14953 | 0.27522 | -0.44242 | -0.26183 | -0.4408 | 0.14929 | 0.38836
| 2737 | 0.2524 | -0.44224 | -0.59565 | -0.72341 | 0.23941 | 0.62304 | -0.26904 | -0.049895 | -0.033201 | 0.47875
| 2738 | -0.64574 | 0.047057 | -0.28775 | -0.57703 | -0.67488 | -0.33105 | 0.0016514 | 0.60491 | 0.44964 | 0.034961
| 2739 | -0.44855 | 0.38348 | -0.19657 | -0.010505 | -0.36778 | -0.34464 | 0.0077803 | -0.37574 | -0.049474 | -0.14824
| 2740 | -0.49078 | 0.040365 | 0.088792 | -0.24046 | -0.045484 | 0.56171 | 0.0023528 | 0.065281 | -0.51184 | -0.0051633
| 2741 | -0.18926 | -0.21942 | 0.66459 | -0.12017 | 0.85201 | -0.45991 | -0.42668 | -0.20119 | -0.39164 | -0.60063
| 2742 | 0.31728 | 0.49157 | -0.11892 | -0.37175 | -0.03579 | -0.39444 | 0.10139 | -0.19185 | -0.15792 | -0.18495
| 2743 | -0.096617 | 0.31993 | 0.20571 | 0.33209 | 0.11202 | 0.11586 | 0.18938 | -0.099056 | 0.76272 | 0.21559
| 2744 | -0.023117 | -0.7492 | -0.25187 | 0.43458 | -0.90673 | -0.81697 | 0.41051 | 0.21712 | 0.18655 | 0.30986
| 2745 | -0.48726 | 0.42026 | 0.38461 | -0.36117 | -0.53385 | -0.56745 | 0.6546 | 0.53385 | 0.35572 | -0.36589
| 2746 | 0.40225 | 0.092641 | 0.10978 | 0.36541 | -0.24933 | -0.78114 | -0.11236 | 0.43973 | -0.69455 | 0.36699
| 2747 | 0.026707 | -0.058034 | 0.10764 | 0.58179 | 0.1418 | -0.40075 | 0.46288 | -0.048527 | 0.21994 | 0.33479
| 2748 | 0.079511 | 0.34969 | -0.18827 | 0.26672 | 0.16771 | -0.21891 | -0.57656 | 0.45292 | -0.22444 | -0.20684
| 2749 | 0.083649 | 0.06261 | 0.017096 | -0.35278 | -0.15484 | -0.62384 | -0.32022 | 0.38771 | 0.36747 | -0.30193
| 2750 | 0.22961 | -0.11733 | -0.097503 | 0.39263 | -0.077558 | -0.064853 | -0.43902 | -0.10708 | -0.011213 | 0.12393
| 2751 | 0.048738 | 0.2571 | -0.020153 | 0.28523 | 0.37526 | 0.39925 | 0.16054 | 0.026912 | 0.083649 | -0.0077803
| 2752 | -0.21076 | -0.35789 | 0.13242 | -0.60263 | 0.55 | -0.35821 | 0.19632 | -0.25993 | 0.90356 | -0.28188
| 2753 | -0.020051 | 0.55357 | -0.35961 | 0.24349 | -0.83599 | 0.56194 | 0.12484 | -0.29964 | 0.29765 | 0.30509
| 2754 | -0.4755 | -0.87233 | 0.56102 | 0.13785 | -0.28817 | -0.29155 | 0.63135 | -0.73223 | 0.20106 | -0.39131
| 2755 | 0.57703 | 0.21114 | -0.39049 | 0.27178 | -0.61026 | -0.33224 | -0.29736 | 0.013035 | 0.059309 | 0.11056
| 2756 | 0.29637 | -0.34678 | -0.31655 | -0.029794 | 0.19894 | 0.33977 | -0.61908 | 0.4987 | 0.1315 | -0.16089
| 2757 | -0.1962 | 0.20508 | -0.075933 | -0.14332 | 0.075284 | 0.31276 | -0.074635 | -0.40662 | 0.48961 | -0.29466
| 2758 | -0.3366 | 0.28803 | -0.45677 | -0.56791 | 0.09209 | -0.57116 | 0.20621 | -0.069033 | 0.19645 | -0.17024
| 2759 | 0.33705 | 0.09518 | -0.37223 | -0.016791 | 0.81212 | 0.14566 | -0.28495 | 0.23039 | -0.02722 | -0.027837
| 2760 | -0.2516 | 0.61206 | 0.69652 | 0.53556 | 0.11722 | -0.067316 | -0.021583 | 0.0004501 | -0.11112 | -0.83357
| 2761 | -0.58515 | 0.48183 | -0.64014 | 0.37847 | -0.41802 | 0.68267 | 0.21089 | -0.34342 | -0.55379 | -0.28761
| 2762 | -0.055172 | -0.11462 | -0.053058 | -0.18263 | -0.86036 | 0.20156 | -0.43299 | 0.070645 | 0.51886 | -0.64518
| 2763 | 0.050526 | -0.85067 | 0.22598 | -0.33164 | -0.11 | 0.11124 | -0.54207 | -0.35556 | 0.68361 | 0.002453
| 2764 | 0.46849 | -0.21827 | -0.5347 | -0.0058672 | 0.087586 | 0.1884 | 0.3882 | -0.41289 | -0.083976 | 0.49039
| 2765 | -0.51595 | 0.80226 | 0.058777 | -0.27261 | 0.40628 | 0.32896 | -0.049053 | -0.65316 | -0.2234 | -0.23013
| 2766 | 0.21994 | 0.2484 | 0.13473 | -0.17157 | 0.35216 | -0.36889 | -0.62224 | 0.33434 | -0.61542 | 0.76021
| 2767 | -0.93917 | 0.47076 | 0.11439 | -0.76698 | -0.11598 | 0.29864 | -0.65927 | 0.010303 | 0.25388 | -0.28986
| 2768 | 0.14041 | -0.11496 | -0.48241 | -0.65897 | 0.0080827 | 0.12473 | -0.12736 | 0.30682 | 0.33359 | -0.37478
| 2769 | 0.48029 | 0.32228 | 0.081469 | 0.44909 | 0.43848 | 0.64125 | 0.77887 | -0.39792 | -0.45182 | 0.51513
| 2770 | -0.1634 | 0.077774 | -0.32007 | -0.82593 | 0.093192 | 0.31087 | -0.92319 | 0.28691 | -0.54404 | -0.30136
| 2771 | -0.30107 | 0.89183 | 0.4392 | -0.053691 | -0.47246 | 0.19198 | 0.4117 | -0.1884 | -0.61856 | -0.10608
| 2772 | -0.094406 | 0.8956 | 0.23156 | 0.26291 | -0.057716 | 0.67213 | -0.061011 | 0.29822 | 0.37446 | 0.11293
| 2773 | 0.080598 | -0.26101 | -0.27522 | 0.045275 | 0.15165 | -0.59491 | -0.82139 | 0.14134 | -0.60567 | 0.2225
| 2774 | -0.50594 | 0.18385 | 0.067423 | -0.40578 | -0.16615 | 0.28579 | 0.42441 | -0.13138 | 0.59024 | 0.13426
| 2775 | 0.22135 | -0.72669 | 0.24827 | 0.60491 | 0.24389 | 0.052213 | 0.37366 | -0.20924 | 0.05 | 0.55807
| 2776 | 0.025064 | 0.20232 | -0.1852 | -0.13173 | 0.28216 | 0.3537 | 0.44152 | -0.52936 | -0.036517 | 0.21101
| 2777 | 0.148 | -0.27302 | 0.13901 | 0.26101 | 0.17109 | -0.40729 | -0.5015 | -0.46232 | 0.33675 | 0.23665
| 2778 | 0.57421 | -0.087147 | -0.86546 | 0.14111 | -0.15389 | -0.46493 | 0.72852 | 0.51782 | -0.81318 | 0.093854
| 2779 | 0.24907 | 0.07183 | -0.26345 | -0.45182 | 0.1015 | -0.39992 | 0.53513 | -0.33389 | -0.63599 | 0.47626
| 2780 | 0.035376 | -0.09518 | -0.53794 | -0.49275 | 0.51637 | -0.4344 | -0.42546 | 0.42772 | -0.18459 | 0.33796
| 2781 | -0.026501 | -0.31495 | -0.65172 | -0.91456 | 0.86696 | 0.21444 | 0.65751 | -0.40746 | -0.24548 | 0.0053644
| 2782 | 0.44927 | -0.56745 | -0.29311 | -0.65809 | 0.043601 | 0.38853 | -0.2313 | 0.06957 | -0.10843 | -0.69324
| 2783 | -0.10552 | 0.14976 | -0.00055015 | 0.71242 | 0.66044 | -0.43123 | -0.55492 | 0.91112 | 0.75161 | -0.47474
| 2784 | 0.23508 | -0.43299 | 0.19198 | -0.27151 | -0.003155 | -0.25602 | 0.095069 | 0.08474 | -0.0004501 | -0.58395
| 2785 | 0.65956 | -0.0062697 | -0.11405 | 0.43866 | 0.79288 | 0.44421 | 0.60898 | 0.30725 | -0.22096 | 0.3167
| 2786 | 0.086709 | -0.37159 | -0.047792 | 0.36305 | 0.12496 | 0.087257 | 0.48726 | -0.14157 | -0.21089 | -0.46306
| 2787 | 0.13519 | -0.15851 | 0.31728 | 0.3132 | 0.060479 | 0.69884 | -0.21508 | -0.41306 | 0.67519 | 0.082667
| 2788 | -0.1072 | 0.56262 | 0.72233 | -0.80277 | 0.51782 | -0.34403 | -0.26278 | -0.18373 | -0.41153 | 0.15661
| 2789 | -0.081033 | 0.42129 | 0.18189 | 0.77796 | -0.89276 | 0.33254 | 0.19906 | 0.63958 | 0.026398 | 0.29085
| 2790 | -0.57751 | -0.26863 | 0.54185 | -0.42877 | -0.91938 | -0.42755 | -0.54185 | -0.25147 | -0.18043 | 0.15721
| 2791 | 0.27882 | -0.10206 | -0.27564 | 0.071399 | -0.10809 | 0.33705 | 0.25227 | -0.15602 | 0.57869 | -0.23195
| 2792 | -0.61438 | 0.33045 | -0.046847 | -0.61516 | 0.92859 | -0.25656 | 0.1533 | -0.76188 | 0.80226 | -0.13948
| 2793 | -0.66728 | -0.26481 | -0.7687 | 0.36431 | 0.49711 | 0.85474 | -0.8755 | -0.28174 | 0.5009 | 0.33045
| 2794 | -0.067637 | 0.87876 | -0.22186 | -0.065709 | 0.20458 | -0.22071 | -0.23652 | -0.49612 | -0.43742 | -0.8739
| 2795 | 0.1245 | 0.50533 | 0.41545 | 0.48843 | 0.57774 | 0.016079 | -0.0064709 | -0.56814 | -0.58539 | -0.28021
| 2796 | -0.26237 | 0.46774 | -0.43759 | 0.13623 | 0.12256 | 0.084631 | -0.018623 | 0.58927 | 0.043078 | -0.47019
| 2797 | -0.41477 | 0.53535 | 0.058459 | -0.85893 | -0.063144 | 0.079185 | 0.7569 | 0.71875 | -0.72054 | 0.42668
| 2798 | 0.22728 | -0.018827 | 0.36937 | -0.082449 | -0.20094 | -0.54448 | 0.58733 | -0.14134 | -0.31218 | -0.4588
| 2799 | -0.14753 | -0.22379 | 0.60188 | 0.29594 | -0.61206 | 0.75896 | 0.39066 | -0.54492 | -0.29141 | -0.094185
| 2800 | -0.24217 | -0.45018 | 0.42251 | 0.23039 | -0.048948 | 0.1565 | -0.043078 | 0.32391 | -0.63217 | -0.4826
| 2801 | -0.71173 | 0.19533 | 0.041929 | 0.050421 | -0.27041 | 0.083103 | -0.14519 | -0.24628 | 0.53924 | 0.73675
| 2802 | -0.62946 | 0.46906 | -0.007478 | 0.42043 | 0.62543 | 0.13507 | 0.57257 | 0.43724 | -0.41204 | -0.31145
| 2803 | 0.71138 | -0.0037571 | 0.038075 | 0.29311 | -0.4426 | -0.027632 | -0.69129 | -0.2484 | 0.63986 | -0.82308
| 2804 | 0.50492 | -0.62384 | -0.27799 | 0.12063 | -0.17799 | -0.536 | -0.35154 | -0.38657 | -0.10284 | 0.36117
| 2805 | -0.21 | 0.49394 | -0.8148 | 0.33164 | 0.15484 | -0.36023 | -0.25602 | 0.24747 | 0.50392 | -0.24297
| 2806 | 0.065067 | 0.056761 | 0.3132 | -0.13762 | 0.24112 | 0.15792 | 0.10876 | -0.44457 | -0.087038 | 0.62357
| 2807 | -0.3025 | -0.61464 | 0.39958 | -0.027735 | 0.69586 | 0.19981 | -0.21546 | 0.25602 | -0.30942 | 0.46568
| 2808 | 0.50231 | 0.53277 | -0.4668 | 0.049474 | -0.236 | 0.79975 | 0.04517 | -0.73 | 0.78344 | 0.26822
| 2809 | 0.2893 | -0.37032 | -0.3618 | -0.79 | 0.1466 | -0.11202 | -0.25522 | 0.19669 | 0.24907 | -0.16675
| 2810 | 0.19297 | -0.39148 | -0.12176 | 0.15496 | 0.15994 | 0.013846 | -0.13634 | -0.57751 | -0.38951 | -0.15531
| 2811 | 0.81265 | 0.016791 | -0.1196 | 0.67735 | 0.29608 | -0.040365 | -0.055807 | 0.76104 | 0.16976 | -0.083103
| 2812 | 0.020357 | -0.39 | 0.17848 | -0.024859 | -0.0056661 | -0.26672 | -0.36778 | 0.15709 | 0.52915 | 0.16771
| 2813 | -0.039531 | 0.42598 | -0.36841 | -0.53643 | 0.61961 | 0.06753 | 0.23325 | -0.26468 | -0.17665 | -0.1769
| 2814 | 0.2809 | 0.57163 | 0.18704 | 0.35525 | -0.1418 | -0.18532 | 0.44728 | -0.069355 | 0.050632 | 0.2575
| 2815 | -0.51287 | -0.22624 | 0.14965 | -0.0035563 | -0.47779 | -0.032167 | 0.70217 | -0.34816 | 0.36794 | 0.14554
| 2816 | -0.0046609 | -0.01344 | -0.09121 | -0.16844 | 0.041407 | -0.088243 | -0.56699 | -0.020153 | 0.45456 | 0.5011
| 2817 | -0.60898 | 0.26196 | 0.34525 | -0.27316 | 0.95 | 0.38137 | 0.12108 | -0.59491 | 0.15082 | -0.069785
| 2818 | -0.26183 | -0.36731 | 0.29212 | -0.29367 | -0.43848 | -0.26781 | -0.041303 | 0.78436 | 0.058565 | -0.60694
| 2819 | 0.44385 | 0.35092 | 0.020255 | 0.54933 | -0.61387 | 0.057185 | -0.1706 | -0.26781 | -0.31305 | -0.39296
| 2820 | -0.46812 | 0.045904 | -0.17921 | 0.6349 | 0.2161 | 0.34433 | 0.13646 | 0.03 | -0.15012 | -0.57023
| 2821 | 0.12051 | -0.73261 | 0.35494 | -0.36243 | 0.052424 | 0.42216 | 0.68903 | -0.075392 | -0.034029 | -0.19819
| 2822 | -0.077666 | -0.11451 | 0.69586 | 0.36557 | 0.002453 | 0.4755 | 0.14169 | 0.43759 | -0.552 | -0.30122
| 2823 | -0.47512 | -0.69586 | 0.21482 | 0.1229 | 0.41238 | 0.53664 | 0.66429 | -0.043078 | 0.74525 | 0.55604
| 2824 | 0.051159 | -0.15118 | 0.067208 | -0.24244 | -0.12063 | 0.70318 | 0.81212 | -0.52576 | -0.47246 | 0.018012
| 2825 | 0.16639 | -0.54338 | -0.9078 | 0.63462 | 0.36133 | -0.56125 | 0.29736 | -0.84736 | -0.65868 | 0.22302
| 2826 | -0.50939 | 0.23169 | -0.12017 | -0.081251 | -0.12188 | 0.72779 | 0.014962 | -0.11869 | 0.58227 | -0.54756
| 2827 | -0.31743 | 0.15697 | 0.13426 | 0.021992 | -0.041407 | 0.30265 | 0.047687 | 0.23026 | -0.6546 | 0.26781
| 2828 | -0.19881 | 0.25723 | -0.6349 | -0.82536 | -0.60541 | 0.29736 | 0.3369 | 0.25562 | -0.23169 | 0.62039
| 2829 | 0.49731 | -0.38283 | 0.41905 | -0.17957 | -0.36258 | -0.88381 | -0.69032 | 0.33992 | 0.11225 | -0.8747
| 2830 | -0.26427 | 0.22431 | -0.53643 | -0.9272 | -0.44547 | 0.0080827 | -0.30437 | 0.11767 | -0.01842 | 0.12747
| 2831 | 0.28621 | 0.088024 | -0.58805 | 0.47436 | 0.06261 | 0.72018 | -0.43334 | -0.66849 | -0.38787 | 0.24973
| 2832 | -0.51123 | 0.43759 | 0.20987 | 0.44349 | -0.22276 | 0.077558 | 0.021481 | -0.15839 | -0.051897 | 0.81159
| 2833 | -0.51823 | -0.46887 | -0.039635 | -0.20848 | 0.058246 | -0.55067 | -0.6149 | 0.5663 | 0.22276 | 0.32687
| 2834 | -0.060053 | 0.67458 | -0.59417 | 0.11473 | -0.29879 | 0.55089 | -0.071614 | -0.55694 | 0.012022 | 0.19782
| 2835 | -0.67427 | -0.31014 | 0.20294 | 0.23156 | -0.53192 | 0.30538 | -0.16567 | -0.11733 | 0.64659 | 0.20006
| 2836 | 0.2516 | 0.15555 | -0.43724 | -0.27302 | 0.66698 | -0.61908 | 0.45677 | -0.14285 | 0.69357 | 0.051053
| 2837 | 0.044751 | 0.20094 | -0.09839 | 0.70487 | 0.59392 | -0.69751 | -0.62543 | -0.28202 | -0.2924 | 0.1769
| 2838 | 0.47057 | 0.17145 | -0.70487 | 0.088024 | -0.67061 | -0.42233 | -0.17205 | -0.66578 | 0.095622 | -0.32911
| 2839 | 0.23117 | 0.40159 | 0.4307 | 0.099944 | 0.52408 | -0.079294 | -0.42268 | -0.086162 | 0.047477 | -0.013744
| 2840 | -0.17726 | -0.33886 | 0.18018 | -0.24033 | -0.17374 | 0.48087 | 0.11643 | 0.052108 | 0.27151 | 0.12461
| 2841 | -0.7508 | 0.41459 | -0.81212 | -0.20924 | 0.016486 | 0.70828 | 0.27206 | -0.092531 | -0.66103 | -0.047162
| 2842 | -0.23221 | -0.42268 | -0.53902 | 0.41391 | -0.78206 | -0.33539 | -0.75526 | 0.67335 | -0.17957 | 0.4801
| 2843 | 0.43635 | 0.46512 | 0.1375 | 0.0995 | 0.11112 | 0.010101 | -0.53427 | -0.56884 | -0.13658 | -0.76357
| 2844 | 0.67458 | 0.09706 | -0.55312 | -0.12851 | 0.048843 | -0.39726 | 0.19669 | 0.14017 | -0.14613 | 0.40376
| 2845 | 0.28104 | -0.11767 | 0.38918 | -0.36447 | -0.65057 | -0.13983 | -0.28188 | -0.5224 | -0.21038 | -0.37318
| 2846 | -0.5721 | 0.69784 | 0.4279 | -0.29793 | 0.58131 | -0.46737 | -0.26007 | 0.32169 | 0.05422 | -0.15448
| 2847 | -0.27619 | -0.70285 | 0.35108 | 0.25361 | -0.36984 | -0.64943 | -0.42407 | -0.40814 | 0.0068736 | 0.074095
| 2848 | 0.065281 | 0.28859 | 0.2504 | -0.4408 | 0.42685 | 0.14111 | 0.10395 | -0.43831 | -0.82708 | -0.13426
| 2849 | -0.19446 | 0.35355 | -0.7042 | -0.4272 | 0.22263 | 0.016893 | -0.31846 | -0.066994 | 0.071184 | -0.10888
| 2850 | 0.42476 | -0.12222 | 0.05496 | 0.57093 | 0.1118 | -0.49236 | 0.36415 | -0.080381 | -0.40696 | 0.3372
| 2851 | -0.12553 | -0.14683 | 0.22199 | 0.12165 | -0.32494 | -0.57444 | 0.074419 | 0.08649 | 0.049263 | -0.14671
| 2852 | -0.32346 | 0.3148 | -0.21827 | -0.0053644 | 0.74643 | 0.33947 | -0.14648 | -0.11722 | -0.05496 | 0.095511
| 2853 | 0.037763 | -0.38396 | -0.10273 | -0.071722 | 0.66668 | 0.65868 | 0.35386 | -0.0091922 | -0.12108 | -0.087914
| 2854 | 0.41922 | 0.70828 | -0.47 | -0.024551 | 0.32524 | 0.043601 | 0.93 | 0.63682 | 0.46102 | -0.027118
| 2855 | 0.46512 | -0.6952 | -0.09187 | -0.41682 | 0.61283 | 0.19919 | 0.24893 | -0.20899 | 0.22315 | 0.18643
| 2856 | -0.031651 | -0.44188 | -0.056973 | 0.6371 | -0.085615 | 0.57538 | 0.21955 | 0.56445 | 0.77044 | -0.61568
| 2857 | 0.33902 | -0.56308 | 0.03974 | 0.048948 | 0.3607 | -0.96127 | -0.3189 | 0.51906 | 0.70966 | -0.63737
| 2858 | -0.3419 | -0.20533 | 0.34601 | 0.19062 | 0.010505 | 0.19856 | -0.32287 | -0.047372 | -0.025885 | 0.17653
| 2859 | -0.1382 | -0.70453 | 0.11598 | 0.082558 | 0.10206 | -0.4983 | 0.5735 | 0.73037 | -0.79925 | -0.1432
| 2860 | -0.4995 | -0.79143 | -0.59788 | -0.056549 | -0.32243 | -0.64293 | 0.55514 | -0.45567 | 0.71769 | 0.42233
| 2861 | -0.68393 | -0.38234 | -0.71035 | -0.30595 | 0.15082 | 0.15141 | 0.20006 | -0.13762 | -0.11169 | 0.077124
| 2862 | 0.93917 | -0.10529 | -0.081033 | -0.0066723 | 0.66939 | 0.17726 | -0.37382 | -0.68679 | 0.18275 | -0.85964
| 2863 | -0.031031 | 0.092751 | 0.12725 | -0.32717 | 0.35883 | -0.21444 | 0.15756 | -0.18483 | -0.16006 | 0.3087
| 2864 | 0.3306 | -0.085834 | 0.046952 | 0.51492 | 0.68583 | -0.59938 | 0.1769 | -0.75403 | -0.56745 | -0.99
| 2865 | -0.16125 | -0.13046 | -0.45991 | 0.62039 | 0.59343 | -0.009596 | 0.33555 | 0.68807 | 0.21444 | 0.36463
| 2866 | -0.16137 | 0.66668 | 0.052108 | -0.074095 | -0.043496 | -0.10708 | 0.3662 | 0.46812 | 0.73074 | -0.22148
| 2867 | -0.52555 | 0.26945 | -0.79875 | -0.25053 | -0.60974 | -0.49771 | 0.24867 | -0.46306 | -0.20772 | -0.55672
| 2868 | -0.64518 | 0.044961 | 0.10675 | -0.46474 | -0.37239 | -0.2193 | 0.10697 | 0.20069 | 0.076474 | 0.3477
| 2869 | -0.016283 | -0.54404 | 0.4337 | -0.45109 | 0.79143 | 0.1196 | 0.49 | -0.39842 | 0.47703 | 0.47512
| 2870 | -0.62543 | -0.24297 | -0.32658 | -0.24257 | 0.59098 | -0.49532 | -0.22096 | 0.13173 | 0.42772 | -0.22083
| 2871 | -0.34846 | -0.23052 | -0.14578 | 0.45383 | -0.41596 | 0.13901 | 0.58155 | 0.40359 | -0.06261 | 0.30293
| 2872 | 0.75282 | 0.60314 | 0.49671 | -0.25549 | 0.74761 | 0.046847 | 0.17617 | 0.32376 | 0.72089 | -0.053058
| 2873 | -0.66221 | -0.78436 | -0.31787 | -0.64349 | -0.4588 | -0.025474 | -0.41272 | -0.62198 | -0.24787 | -0.43281
| 2874 | -0.0076795 | -0.1375 | 0.074095 | 0.0050628 | 0.77131 | -0.52979 | 0.37927 | -0.27495 | 0.71242 | 0.44583
| 2875 | -0.69488 | -0.3735 | 0.13046 | 0.15685 | 0.23652 | 0.47076 | -0.5172 | 0.11881 | -0.80481 | -0.4997
| 2876 | 0.23469 | -0.066458 | 0.46493 | 0.49236 | -0.14765 | -0.22366 | -0.26563 | 0.2924 | -0.029279 | 0.46774
| 2877 | 0.29722 | 0.11169 | -0.035687 | -0.3629 | 0.46306 | 0.053374 | -0.083867 | 0.72054 | -0.22547 | -0.20244
| 2878 | 0.41477 | -0.25013 | 0.06261 | -0.23378 | -0.84801 | -0.021787 | 0.60038 | 0.62517 | -0.22173 | 0.21457
| 2879 | -0.52873 | -0.040052 | 0.84605 | -0.34008 | 0.28944 | 0.43123 | -0.75322 | 0.042869 | 0.87 | -0.10955
| 2880 | 0.57917 | -0.37334 | -0.76741 | 0.08989 | 0.27827 | 0.22624 | -0.13913 | 0.61206 | 0.013846 | 0.043287
| 2881 | -0.43902 | -0.63792 | -0.55492 | 0.69129 | -0.044647 | -0.34068 | -0.60872 | -0.46493 | 0.12382 | 0.025988
| 2882 | 0.55989 | -0.50695 | 0.37494 | -0.04099 | -0.011314 | 0.38836 | 0.79875 | 0.42895 | -0.45861 | -0.464
| 2883 | -0.14765 | -0.035583 | -0.010808 | 0.20672 | -0.38089 | 0.0035563 | -0.27041 | -0.48222 | 0.51616 | -0.20031
| 2884 | -0.1803 | -0.86325 | -0.061011 | 0.013947 | -0.58927 | 0.11428 | 0.40966 | 0.66939 | -0.28944 | -0.28271
| 2885 | -0.80791 | -0.3369 | 0.74761 | 0.47933 | 0.043182 | -0.28887 | -0.17338 | -0.13611 | 0.21013 | -0.27854
| 2886 | -0.43795 | 0.39892 | -0.067316 | -0.91938 | -0.019847 | -0.12302 | 0.16735 | -0.27302 | -0.41991 | 0.043182
| 2887 | 0.077991 | 0.44909 | -0.33932 | 0.037036 | -0.89464 | 0.21648 | -0.12336 | 0.10552 | 0.51513 | -0.71035
| 2888 | 0.37494 | -0.33992 | 0.46028 | 0.19074 | 0.61516 | -0.08474 | 0.14111 | 0.29282 | -0.0065716 | 0.38934
| 2889 | -0.11881 | 0.23182 | -0.38673 | -0.63958 | 0.66638 | -0.10541 | -0.50472 | -0.66459 | -0.76741 | -0.26047
| 2890 | -0.12051 | -0.33404 | 0.6162 | 0.1034 | -0.13299 | -0.26345 | 0.28035 | 0.35774 | -0.31465 | 0.72125
| 2891 | -0.024449 | -0.48454 | 0.097393 | -0.044437 | 0.14648 | -0.34647 | -0.39925 | -0.65258 | 0.21089 | 0.34708
| 2892 | 0.085506 | 0.74368 | 0.68807 | 0.53449 | 0.58251 | -0.31451 | -0.27716 | 0.67488 | -0.34525 | -0.2278
| 2893 | -0.5954 | -0.27993 | -0.041303 | 0.4736 | 0.16244 | -0.32022 | 0.52219 | 0.060798 | -0.011719 | -0.81534
| 2894 | 0.22611 | -0.17568 | 0.018929 | 0.12564 | 0.037971 | -0.097282 | 0.14029 | -0.10966 | 0.74485 | -0.35572
| 2895 | -0.4041 | 0.59988 | 0.56171 | 0.14542 | -0.49374 | -0.21063 | 0.27924 | -0.28958 | -0.43759 | 0.11394
| 2896 | -0.23901 | 0.44277 | 0.40125 | 0.10933 | 0.086271 | -0.30308 | 0.043182 | -0.45 | -0.37976 | -0.42842
| 2897 | 0.6634 | -0.21279 | -0.16615 | 0.034547 | -0.040469 | -0.80584 | 0.045484 | 0.0053644 | 0.027632 | -0.50675
| 2898 | 0.6755 | -0.15436 | 0.41562 | 0.029382 | 0.77662 | 0.8618 | 0.49098 | 0.021276 | 0.58036 | -0.09187
| 2899 | 0.25227 | 0.36747 | 0.22058 | -0.40966 | 0.78858 | -0.44116 | 0.49334 | 0.40831 | -0.39709 | 0.15614
| 2900 | -0.42441 | -0.17072 | 0.056443 | 0.27055 | -0.65258 | -0.67922 | 0.60013 | -0.062503 | -0.51534 | -0.20307
| 2901 | -0.65927 | 0.033201 | -0.25643 | -0.60113 | 0.23404 | 0.081577 | 0.27578 | -0.15306 | 0.63217 | 0.24376
| 2902 | -0.009899 | 0.18067 | -0.73789 | -0.25321 | -0.39958 | 0.15816 | 0.64914 | 0.5019 | 0.14882 | -0.86399
| 2903 | -0.10832 | 0.30064 | 0.19769 | 0.068174 | 0.1261 | 0.23104 | 0.26413 | 0.448 | 0.86325 | 0.45824
| 2904 | -0.31685 | -0.09011 | -0.76104 | 0.59417 | 0.71557 | -0.080163 | 0.25764 | 0.52073 | 0.012731 | 0.48338
| 2905 | 0.089012 | 0.054537 | 0.23273 | -0.28076 | 0.70318 | -0.055595 | 0.059309 | 0.6995 | -0.248 | -0.061011
| 2906 | 0.0040582 | 0.13253 | 0.14204 | 0.10317 | 0.10652 | -0.14835 | -0.44764 | -0.20874 | -0.29381 | -0.14029
| 2907 | -0.72233 | -0.54558 | -0.21165 | 0.71804 | -0.15804 | 0.56057 | -0.44188 | 0.67396 | 0.02322 | 0.61751
| 2908 | 0.27302 | -0.18177 | 0.011011 | -0.17229 | -0.24654 | 0.14765 | 0.30783 | -0.27564 | -0.036828 | -0.18852
| 2909 | 0.029073 | -0.16663 | -0.53427 | 0.36447 | -0.32228 | 0.37638 | 0.28453 | -0.066458 | -0.5866 | -0.68456
| 2910 | -0.30351 | -0.40042 | 0.066351 | 0.52682 | -0.34266 | -0.49256 | 0.14274 | 0.39593 | -0.19508 | 0.2193
| 2911 | 0.43795 | -0.30193 | -0.27633 | -0.28397 | 0.40042 | -0.56194 | 0.16161 | 0.068818 | 0.4799 | 0.20672
| 2912 | 0.60795 | 0.55604 | 0.37414 | -0.14029 | 0.55559 | -0.35992 | 0.22032 | 0.50857 | -0.3211 | 0.01547
| 2913 | 0.063571 | 0.20836 | 0.27965 | 0.3451 | -0.070645 | 0.0043595 | 0.2492 | 0.56148 | 0.14835 | 0.61934
| 2914 | -0.31029 | 0.31261 | 0.15507 | -0.81697 | -0.28944 | -0.29979 | -0.24442 | 0.40225 | 0.031135 | -0.19086
| 2915 | -0.4417 | 0.7508 | 0.62251 | -0.16496 | 0.30797 | 0.13242 | 0.099278 | -0.0020521 | -0.066673 | 0.56907
| 2916 | 0.1338 | 0.67922 | 0.060798 | 0.033408 | -0.5172 | 0.36715 | -0.0028541 | -0.26264 | -0.25926 | -0.53707
| 2917 | -0.50857 | -0.31846 | -0.34038 | -0.12142 | -0.070538 | -0.24628 | -0.29169 | -0.30855 | -0.55966 | -0.42009
| 2918 | -0.13519 | 0.28257 | 0.20382 | -0.19458 | 0.024449 | 0.09706 | 0.38364 | -0.20031 | -0.037451 | -0.5721
| 2919 | 0.41871 | -0.18692 | -0.060266 | 0.45475 | 0.7569 | -0.23234 | -0.27896 | 0.031548 | -0.18226 | -0.03
| 2920 | 0.049263 | -0.67674 | 0.57047 | -0.037036 | -0.84476 | -0.76484 | 0.0075787 | 0.5098 | -0.0058672 | 0.65897
| 2921 | -0.21942 | 0.78905 | 0.21 | 0.60113 | -0.26332 | -0.83477 | -0.11756 | 0.73335 | -0.59318 | -0.88381
| 2922 | 0.37911 | -0.09165 | -0.23417 | -0.069248 | -0.13023 | 0.033098 | 0.0022525 | -0.35992 | 0.22702 | 0.52936
| 2923 | -0.06678 | 0.45073 | 0.3422 | 0.40125 | 0.18397 | -0.028146 | 0.37767 | 0.59343 | 0.57964 | -0.26645
| 2924 | 0.44764 | -0.68807 | -0.6149 | 0.34662 | 0.11699 | -0.047267 | 0.11552 | 0.0058672 | -0.56768 | 0.14965
| 2925 | 0.024244 | 0.042555 | -0.80947 | -0.069355 | -0.24575 | 0.41922 | 0.60541 | 0.28761 | -0.63408 | 0.32199
| 2926 | 0.18116 | -0.18324 | -0.0922 | 0.27674 | 0.078534 | 0.19062 | 0.1091 | -0.31261 | -0.20458 | -0.65693
| 2927 | -0.43617 | 0.52324 | 0.24244 | -0.53535 | 0.39362 | 0.75241 | 0.039011 | -0.73827 | -0.80584 | -0.13461
| 2928 | -0.32273 | 0.55245 | -0.30423 | 0.19297 | -0.59963 | 0.08649 | -0.039844 | -0.49059 | 0.62171 | 0.71627
| 2929 | -0.080489 | 0.31407 | -0.22547 | 0.45401 | 0.24072 | 0.22702 | -0.31524 | 0.50472 | -0.28901 | -0.081469
| 2930 | 0.40025 | -0.21215 | 0.2278 | -0.35247 | -0.1292 | -0.14753 | -0.40125 | 0.43671 | 0.75322 | -0.074743
| 2931 | -0.85964 | -0.047267 | 0.18606 | -0.011011 | 0.24244 | -0.61594 | -0.63599 | 0.58781 | -0.20156 | 0.32836
| 2932 | 0.16904 | 0.47057 | 0.32361 | -0.53729 | 0.4857 | 0.10552 | 0.28761 | 0.79288 | 0.58636 | -0.53085
| 2933 | 0.14425 | 0.12954 | -0.12473 | -0.19037 | -0.52219 | 0.62784 | 0.47569 | -0.30667 | -0.15472 | -0.84867
| 2934 | 0.16424 | -0.39975 | 0.29722 | 0.21038 | 0.2047 | 0.21827 | 0.4588 | -0.8422 | -0.083867 | -0.17096
| 2935 | -0.19235 | -0.0026535 | -0.18018 | -0.41459 | -0.077666 | 0.47933 | 0.13507 | -0.31349 | 0.27757 | -0.58636
| 2936 | 0.31816 | 0.19769 | 0.11045 | 0.62946 | -0.89183 | -0.48804 | 0.018318 | -0.95204 | 0.12393 | -0.72089
| 2937 | -0.73335 | 0.17653 | 0.42043 | -0.39958 | -0.73486 | 0.24561 | -0.51205 | 0.31993 | -0.09077 | -0.62066
| 2938 | 0.16687 | 0.054114 | 0.52073 | 0.15923 | -0.15153 | 0.70453 | 0.35899 | 0.27206 | -0.18153 | 0.20307
| 2939 | -0.80025 | -0.27757 | 0.56861 | 0.22715 | -0.41068 | 0.34908 | -0.38218 | 0.91693 | -0.70083 | 0.18471
| 2940 | 0.0030547 | -0.1921 | -0.57751 | 0.58083 | 0.45898 | 0.16856 | -0.10317 | -0.67182 | -0.35914 | 0.022299
| 2941 | -0.1338 | -0.6044 | 0.032684 | 0.038491 | 0.40898 | 0.8995 | 0.34281 | -0.69292 | -0.34311 | 0.15899
| 2942 | -0.0922 | 0.62039 | 0.69097 | 0.01547 | -0.81534 | -0.4564 | 0.62892 | -0.080816 | -0.017503 | 0.29042
| 2943 | -0.17109 | 0.5332 | -0.19806 | -0.22689 | -0.3312 | 0.23143 | -0.046113 | 0.19782 | 0.78114 | 0.21738
| 2944 | -0.36557 | 0.70318 | -0.020357 | -0.081686 | 0.24973 | 0.28397 | 0.00035006 | 0.0068736 | -0.09055 | 0.064425
| 2945 | -0.094075 | -0.19433 | 0.62198 | 0.15602 | 0.40949 | 0.62624 | 0.4531 | 0.020766 | 0.60516 | 0.09695
| 2946 | 0.34862 | -0.75813 | 0.014454 | 0.55134 | 0.11372 | 0.61542 | -0.065281 | -0.06229 | -0.33015 | 0.42877
| 2947 | -0.087586 | -0.49354 | 0.61283 | 0.49039 | 0.72669 | 0.020868 | -0.37767 | -0.54602 | -0.31378 | -0.083867
| 2948 | -0.18324 | 0.15271 | 0.20144 | -0.31875 | -0.70966 | -0.3375 | -0.72742 | 0.5806 | -0.58395 | 0.082994
| 2949 | -0.63986 | 0.023834 | 0.20709 | -0.49711 | 0.26822 | -0.0037571 | -0.047897 | 0.19297 | -0.82252 | 0.10641
| 2950 | 0.32985 | -0.027735 | 0.65927 | 0.20458 | -0.32155 | 0.33269 | 0.12782 | -0.37702 | -0.35046 | 0.31758
| 2951 | -0.095843 | 0.20056 | -0.037971 | 0.18803 | -0.23521 | 0.19408 | 0.53277 | 0.38413 | -0.28243 | -0.37334
| 2952 | 0.6233 | 0.5007 | 0.33675 | -0.47341 | 0.43706 | -0.45182 | 0.40058 | 0.081795 | 0.50594 | -0.015368
| 2953 | 0.59 | 0.089121 | -0.76146 | 0.51844 | -0.020459 | -0.11157 | -0.65605 | 0.35062 | 0.69917 | 0.72233
| 2954 | -0.057609 | 0.40881 | -0.83 | -0.40108 | 0.51061 | -0.20269 | 0.086053 | 0.059734 | -0.2516 | -0.56745
| 2955 | -0.0019519 | 0.035479 | -0.16376 | -0.5017 | 0.073124 | 0.65751 | 0.09209 | -0.073339 | 0.65927 | 0.093303
| 2956 | 0.19931 | 0.072045 | 0.26007 | 0.45677 | -0.41272 | 0.15 | 0.095954 | -0.47588 | -0.10094 | -0.72305
| 2957 | 0.32258 | 0.8148 | -0.5264 | 0.52597 | -0.23456 | 0.14753 | -0.20081 | 0.63462 | 0.55044 | 0.06753
| 2958 | 0.053586 | -0.6338 | 0.47933 | -0.23731 | -0.054643 | 0.45401 | 0.63682 | -0.0057666 | -0.11484 | -0.57515
| 2959 | 0.44242 | -0.48067 | -0.41545 | -0.12587 | -0.73186 | -0.56884 | 0.20533 | -0.26034 | -0.088463 | 0.17556
| 2960 | 0.20458 | -0.060479 | -0.23547 | 0.34555 | 0.094517 | 0.073124 | -0.092751 | 0.061224 | -0.017198 | 0.45456
| 2961 | -0.09 | 0.10596 | -0.23364 | -0.13727 | -0.29155 | 0.064746 | 0.4859 | 0.35077 | -0.62704 | -0.66549
| 2962 | 0.17848 | -0.54778 | 0.36494 | 0.33359 | 0.54251 | -0.74174 | -0.11688 | 0.44313 | 0.51948 | -0.23325
| 2963 | 0.32332 | 0.59343 | -0.06261 | 0.24814 | -0.33947 | -0.63244 | -0.24575 | 0.34266 | 0.1578 | -0.35355
| 2964 | 0.081142 | 0.26536 | 0.80025 | -0.63081 | -0.73411 | -0.05422 | 0.030412 | -0.49256 | 0.76957 | 0.15626
| 2965 | -0.22624 | 0.34174 | 0.55537 | 0.13092 | 0.34372 | 0.5959 | 0.82479 | -0.71557 | 0.67458 | 0.014657
| 2966 | -0.19694 | -0.25522 | -0.10574 | -0.35992 | 0.03714 | -0.17872 | 0.45237 | -0.066887 | -0.73335 | -0.40511
| 2967 | 0.039115 | -0.47493 | -0.76913 | -0.39775 | 0.16054 | 0.39626 | 0.28593 | -0.51143 | 0.23221 | -0.82196
| 2968 | 0.63517 | 0.22935 | -0.19645 | -0.39082 | -0.1109 | -0.16675 | 0.084631 | -0.4801 | -0.15283 | -0.60213
| 2969 | -0.27206 | 0.68141 | 0.41802 | -0.26754 | 0.65897 | 0.52219 | 0.21038 | 0.17617 | 0.20659 | -0.01344
| 2970 | 0.68583 | -0.34923 | -0.19185 | 0.16304 | 0.073339 | 0.040573 | 0.39444 | 0.78716 | 0.57468 | 0.38445
| 2971 | -0.24734 | -0.11813 | 0.40645 | 0.042451 | 0.18643 | 0.49394 | -0.26522 | 0.044647 | -0.12966 | 0.12989
| 2972 | -0.11722 | -0.30682 | 0.26183 | -0.52471 | 0.12989 | -0.16209 | -0.40092 | 0.64914 | 0.050948 | -0.20609
| 2973 | 0.0087886 | 0.74251 | -0.22754 | 0.28607 | -0.3607 | 0.43088 | -0.31247 | -0.28467 | 0.4194 | -0.30567
| 2974 | 0.10128 | 0.35758 | 0.27206 | 0.3838 | -0.071722 | -0.42459 | 0.099611 | -0.62171 | -0.47038 | -0.5001
| 2975 | -0.5098 | -0.93755 | 0.33254 | -0.16316 | 0.252 | -0.57964 | 0.43884 | 0.30293 | 0.30783 | 0.43018
| 2976 | 0.31787 | -0.086928 | 0.71138 | -0.31714 | 0.046428 | 0.082231 | -0.036517 | 0.39115 | 0.013947 | -0.038803
| 2977 | 0.35339 | -0.77131 | 0.16567 | 0.13948 | 0.47 | 0.75526 | -0.28383 | -0.28986 | -0.12336 | 0.15106
| 2978 | -0.087257 | 0.46456 | 0.16819 | -0.02568 | -0.06678 | 0.17848 | -0.13611 | -0.20044 | 0.45935 | 0.32007
| 2979 | 0.088573 | 0.18459 | -0.075716 | 0.21457 | -0.25791 | 0.57327 | -0.11631 | 0.018827 | -0.44982 | 0.16221
| 2980 | 0.25953 | -0.33841 | 0.22573 | -0.74058 | -0.34708 | 0.17145 | 0.23888 | -0.50472 | 0.38348 | 0.20081
| 2981 | -0.23273 | -0.47284 | 0.36117 | -0.31407 | 0.047162 | 0.23862 | -0.55111 | 0.073663 | 0.20307 | -0.86546
| 2982 | 0.2234 | 0.16675 | -0.088792 | 0.15271 | -0.57374 | 0.022503 | 0.41768 | 0.42546 | 0.39975 | 0.5264
| 2983 | -0.57515 | 0.0781 | 0.069248 | 0.28916 | -0.16101 | -0.54011 | -0.066137 | 0.17109 | 0.23757 | 0.55044
| 2984 | -0.25267 | -0.029588 | 0.4801 | 0.52366 | -0.46306 | 0.51906 | -0.083212 | -0.6338 | 0.96394 | 0.12966
| 2985 | 0.50513 | -0.25818 | -0.19969 | -0.40949 | -0.10731 | 0.68425 | 0.39958 | -0.53816 | -0.22974 | 0.78763
| 2986 | -0.46195 | -0.3087 | 0.59614 | 0.60364 | -0.057609 | -0.40427 | -0.2225 | -0.49413 | -0.24575 | 0.29127
| 2987 | 0.12633 | -0.17459 | 0.38056 | -0.050421 | -0.39709 | 0.052002 | 0.56768 | 0.33902 | -0.70589 | -0.51307
| 2988 | 0.025988 | 0.64829 | -0.28467 | 0.18975 | 0.33841 | -0.02281 | -0.046847 | -0.43635 | 0.24244 | 0.020255
| 2989 | -0.59763 | 0.74525 | 0.30826 | 0.29085 | 0.77306 | -0.52957 | -0.062717 | -0.63958 | -0.3422 | 0.052741
| 2990 | -0.72559 | -0.33917 | 0.5264 | -0.048843 | -0.29056 | 0.59024 | 0.35479 | -0.0066723 | -0.13924 | -0.46046
| 2991 | 0.58854 | -0.38787 | -0.029794 | -0.077232 | 0.22096 | -0.19919 | -0.25133 | -0.00065021 | -0.11157 | 0.2823
| 2992 | -0.18299 | 0.059521 | -0.48532 | -0.17532 | 0.1025 | -0.38073 | 0.71312 | -0.40898 | 0.55111 | 0.45365
| 2993 | -0.31728 | 0.33105 | -0.31189 | -0.29466 | -0.5447 | -0.18495 | 0.55245 | 0.23875 | -0.14192 | 0.68903
| 2994 | 0.01091 | 0.17109 | -0.52471 | 0.42233 | -0.05158 | -0.020051 | -0.3882 | -0.2995 | 0.18446 | -0.54602
| 2995 | -0.63848 | 0.34954 | 0.27757 | 0.61335 | -0.044228 | -0.096175 | -0.32911 | 0.17012 | 0.48687 | 0.23325
| 2996 | 0.14064 | -0.15626 | 0.08967 | 0.27564 | -0.4683 | 0.61231 | 0.038595 | 0.10328 | -0.71452 | -0.099389
| 2997 | -0.20747 | -0.25683 | -0.81318 | -0.40814 | -0.33615 | 0.076041 | -0.59343 | 0.70251 | 0.14531 | -0.11293
| 2998 | 0.40309 | -0.16161 | -0.75813 | -0.0071757 | -0.41187 | 0.0058672 | -0.31963 | -0.13948 | -0.78068 | -0.96394
| 2999 | -0.16868 | 0.047267 | 0.26034 | 0.20144 | 0.28299 | -0.56148 | 0.21495 | 0.10006 | -0.29254 | -0.56491
| 3000 | 0.11214 | -0.072153 | 0.28677 | 0.25508 | 0.72632 | 0.11677 | -0.84348 | -0.38234 | 0.12966 | -0.31116
| 3001 | -0.16579 | -0.16783 | -0.040782 | 0.081795 | 0.019541 | -0.70657 | 0.15484 | -0.11665 | -0.35805 | 0.29028
| 3002 | 0.10518 | 0.098169 | 0.12119 | 0.14765 | 0.27178 | -0.5347 | 0.56011 | 0.6952 | 0.29622 | 0.27993
| 3003 | 0.89091 | -0.23299 | 0.59318 | -0.028867 | 0.064746 | 0.41477 | 0.2402 | -0.60339 | 0.18544 | 0.40309
| 3004 | -0.1237 | 0.00025003 | 0.0013509 | 0.034961 | 0.032477 | 0.046952 | -0.076366 | 0.036309 | 0.3211 | -0.33269
| 3005 | -0.044228 | -0.29141 | -0.092641 | 0.80584 | -0.80277 | 0.65143 | -0.092641 | 0.23665 | 0.37654 | 0.46868
| 3006 | 0.58491 | 0.32776 | 0.20319 | 0.72054 | 0.053269 | -0.82708 | -0.72926 | -0.32569 | 0.038803 | 0.14753
| 3007 | 0.72378 | -0.24336 | 0.28397 | -0.73298 | -0.065388 | 0.16591 | 0.13138 | -0.11892 | -0.015673 | 0.34586
| 3008 | -0.41751 | 0.71069 | 0.33992 | -0.32955 | 0.11507 | 0.03465 | 0.74525 | 0.16555 | -0.10039 | -0.1221
| 3009 | -0.1196 | 0.018827 | -0.23182 | -0.3242 | 0.009697 | 0.21266 | -0.06496 | 0.37911 | 0.49671 | -0.003155
| 3010 | -0.15094 | -0.41613 | 0.092641 | -0.76913 | 0.12165 | -0.41733 | 0.89656 | 0.12347 | 0.9089 | -0.068388
| 3011 | 0.63081 | -0.43617 | 0.30365 | 0.19906 | 0.11926 | -0.54558 | 0.69194 | -0.51575 | -0.39246 | 0.33645
| 3012 | -0.09121 | 0.63875 | 0.27178 | 0.10708 | -0.046847 | 0.23875 | 0.061864 | 0.042242 | 0.59664 | -0.15733
| 3013 | -0.81053 | -0.12736 | 0.45824 | 0.24336 | -0.35836 | -0.29296 | 0.39246 | 0.22521 | 0.11372 | -0.10933
| 3014 | 0.13983 | 0.096175 | -0.23065 | -0.059521 | 0.29 | -0.86036 | -0.041094 | -0.009697 | -0.56676 | 0.68078
| 3015 | 0.29155 | -0.072261 | 0.14145 | 0.22573 | 0.9272 | -0.1962 | 0.027323 | -0.54867 | 0.49078 | 0.25602
| 3016 | -0.095069 | 0.14648 | -0.4989 | 0.83599 | 0.17921 | -0.010505 | -0.21661 | 0.33134 | 0.073339 | 0.30913
| 3017 | 0.2504 | -0.60415 | -0.46176 | 0.67213 | -0.085178 | 0.25468 | 0.11881 | 0.055066 | 0.18018 | -0.11236
| 3018 | 0.70217 | -0.13727 | -0.1841 | 0.071722 | -0.24827 | 0.60898 | 0.57774 | 0.15082 | -0.15153 | 0.1118
| 3019 | 0.42703 | 0.047477 | 0.04099 | -0.052213 | -0.37111 | 0.22495 | 0.61438 | 0.066351 | 0.40865 | -0.016994
| 3020 | -0.76146 | 0.72926 | -0.30769 | -0.22728 | 0.78576 | -0.15306 | 0.01182 | 0.36055 | -0.74643 | -0.52031
| 3021 | 0.27137 | 0.022912 | -0.14169 | -0.17253 | 0.25482 | 0.044751 | -0.52031 | 0.63765 | 0.08485 | 0.26088
| 3022 | -0.3425 | -0.32911 | 0.42563 | -0.023629 | 0.2567 | 0.44295 | 0.15401 | -0.2598 | 0.68871 | 0.020357
| 3023 | -0.068496 | -0.86621 | 0.50918 | 0.65 | 0.67213 | -0.27564 | 0.26727 | -0.16221 | 0.063891 | -0.14683
| 3024 | 0.24072 | 0.5721 | 0.0071757 | 0.42441 | -0.70931 | -0.28649 | 0.067852 | 0.20294 | -0.51969 | -0.41051
| 3025 | 0.6249 | 0.30581 | 0.19421 | -0.57023 | -0.85405 | 0.32554 | -0.44421 | 0.23143 | 0.0067729 | 0.52073
| 3026 | -0.5608 | -0.040677 | 0.52198 | -0.44782 | 0.89464 | 0.068925 | 0.2755 | 0.065388 | -0.23941 | -0.35031
| 3027 | 0.038595 | 0.12245 | 0.25495 | 0.1221 | 0.27716 | 0.31 | 0.65201 | -0.27151 | 0.23143 | 0.74682
| 3028 | -0.49394 | 0.22534 | 0.32228 | -0.69324 | -0.036102 | -0.09176 | 0.085943 | 0.84094 | 0.28118 | -0.26808
| 3029 | -0.12233 | 0.21089 | -0.52282 | -0.027426 | -0.68488 | 0.71733 | -0.61412 | -0.9005 | 0.36164 | -0.41716
| 3030 | -0.41323 | 0.22353 | -0.60872 | 0.023629 | 0.6631 | -0.40881 | -0.13484 | 0.24231 | -0.030206 | -0.27178
| 3031 | 0.89464 | 0.20533 | -0.20924 | 0.33464 | -0.52471 | 0.23665 | 0.042869 | -0.14461 | 0.72815 | 0.052213
| 3032 | -0.47588 | 0.26877 | 0.044228 | -0.023732 | 0.69 | 0.10261 | -0.33045 | 0.76188 | 0.34662 | -0.37079
| 3033 | 0.28481 | 0.40393 | 0.4799 | -0.42441 | -0.28118 | -0.35324 | 0.020868 | 0.54933 | -0.29466 | -0.25013
| 3034 | 0.13936 | -0.1688 | -0.19981 | -0.73981 | 0.34938 | 0.18177 | 0.44873 | 0.018012 | -0.33179 | -0.12541
| 3035 | 0.29127 | 0.03974 | -0.10753 | 0.36762 | -0.026501 | 0.0078811 | -0.64744 | 0.452 | -0.42147 | -0.20395
| 3036 | 0.011011 | 0.21038 | -0.2175 | 0.22961 | 0.083649 | 0.25482 | -0.53213 | 0.10675 | 0.76357 | -0.70184
| 3037 | 0.40343 | -0.47019 | 0.19645 | -0.085834 | 0.10865 | 0.10652 | -0.20823 | -0.60744 | -0.44891 | -0.34877
| 3038 | -0.24774 | -0.83177 | 0.029176 | 0.3167 | 0.097947 | 0.29282 | -0.49334 | -0.31363 | 0.16424 | -0.26088
| 3039 | 0.056973 | -0.13265 | -0.11609 | 0.43299 | -0.17921 | 0.35618 | 0.06325 | -0.7488 | -0.46643 | 0.22792
| 3040 | -0.00095045 | 0.60694 | -0.17278 | 0.6382 | -0.67121 | 0.21623 | 0.36984 | 0.11428 | 0.25013 | -0.11711
| 3041 | 0.39411 | -0.10541 | 0.13184 | 0.16244 | -0.35308 | 0.2225 | -0.58563 | 0.8882 | 0.019439 | 0.32896
| 3042 | -0.095401 | -0.64321 | 0.39279 | -0.5714 | 0.13104 | 0.60364 | -0.40477 | -0.29936 | -0.24455 | 0.18189
| 3043 | -0.49334 | 0.22225 | -0.17302 | -0.40797 | -0.044123 | 0.68679 | 0.011213 | -0.22444 | -0.09706 | -0.21063
| 3044 | 0.13449 | -0.36149 | -0.16904 | -0.29566 | -0.2496 | 0.34647 | 0.11349 | -0.043496 | -0.25053 | -0.064853
| 3045 | -0.94255 | 0.26495 | 0.13496 | -0.41836 | 0.026604 | 0.25966 | -0.17435 | 0.51678 | 0.064532 | 0.55559
| 3046 | -0.32435 | -0.16149 | -0.13104 | 0.19669 | -0.56583 | 0.31261 | 0.36478 | 0.12336 | 0.17994 | 0.19371
| 3047 | 0.71698 | 0.64489 | 0.86621 | -0.037659 | 0.0093941 | 0.23757 | 0.098169 | -0.0088895 | 0.077774 | 0.23678
| 3048 | 0.070861 | 0.02897 | -0.29254 | -0.28986 | 0.67458 | 0.061544 | 0.23404 | 0.011011 | -0.11383 | 0.12782
| 3049 | 0.30986 | 0.19719 | 0.31919 | 0.85067 | 0.58395 | -0.68141 | -0.018929 | 0.028043 | -0.27591 | 0.41425
| 3050 | 0.23639 | 0.053586 | -0.31 | -0.20836 | 0.26767 | 0.30682 | -0.36415 | -0.66758 | 0.40898 | 0.16125
| 3051 | 0.50857 | 0.20144 | -0.28146 | -0.4194 | 0.16699 | 0.38073 | -0.31131 | -0.14064 | 0.32821 | 0.087695
| 3052 | 0.25401 | -0.37494 | -0.18643 | -0.60668 | 0.33705 | -0.76655 | 0.058459 | 0.036517 | 0.094296 | -0.23404
| 3053 | -0.30179 | -0.43405 | -0.51969 | 0.15661 | 0.18889 | 0.12484 | 0.42078 | 0.09121 | 0.18128 | 0.32554
| 3054 | -0.028558 | -0.26617 | -0.95 | 0.0069743 | -0.16137 | 0.12862 | -0.20294 | -0.024551 | -0.28202 | -0.29822
| 3055 | -0.28944 | -0.21981 | 0.29993 | -0.092862 | -0.053163 | -0.20382 | -0.21968 | -0.003456 | -0.024756 | 0.0047613
| 3056 | 0.57633 | -0.056867 | 0.5224 | -0.48067 | -0.059309 | -0.19359 | 0.76957 | 0.55469 | -0.29608 | -0.46325
| 3057 | -0.8422 | 0.010202 | 0.15141 | -0.26373 | -0.06293 | -0.19782 | 0.6149 | -0.5922 | -0.073879 | 0.51
| 3058 | -0.54624 | -0.2508 | 0.17629 | 0.39975 | -0.60694 | 0.078859 | 0.17096 | 0.13878 | 0.11813 | -0.4755
| 3059 | 0.46046 | -0.10563 | -0.37446 | 0.48222 | 0.76957 | 0.54823 | 0.35417 | 0.25777 | 0.20169 | 0.34479
| 3060 | 0.068281 | -0.15153 | 0.69455 | -0.51575 | 0.18667 | -0.17544 | 0.2037 | -0.63737 | -0.39958 | 0.48048
| 3061 | 0.1546 | -0.46176 | 0.36873 | 0.34327 | 0.21699 | -0.35479 | 0.36211 | 0.59392 | 0.16591 | -0.95877
| 3062 | -0.040886 | -0.23665 | 0.069355 | -0.03579 | -0.33962 | -0.67643 | -0.29879 | 0.89656 | -0.38073 | 0.39709
| 3063 | 0.4588 | 0.61672 | 0.19086 | 0.80379 | -0.18092 | -0.46213 | -0.69817 | 0.69817 | -0.63654 | 0.90566
| 3064 | 0.50695 | 0.77977 | 0.40393 | -0.47398 | 0.16555 | -0.12725 | 0.28719 | -0.048738 | 0.0728 | 0.22225
| 3065 | 0.36463 | 0.37478 | -0.56745 | 0.14437 | -0.28705 | 0.15177 | -0.073771 | 0.77796 | 0.67396 | -0.074635
| 3066 | 0.14285 | -0.2941 | -0.31058 | 0.29694 | -0.25629 | 0.027426 | -0.30466 | -0.41836 | -0.38608 | -0.68583
| 3067 | -0.56954 | 0.30624 | 0.68267 | 0.23823 | 0.047792 | -0.21968 | -0.26536 | -0.21635 | 0.2476 | 0.094848
| 3068 | 0.10017 | -0.036413 | 0.63027 | 0.13855 | 0.47455 | -0.57656 | -0.46737 | 0.28313 | 0.031548 | 0.41391
| 3069 | 0.52851 | 0.73751 | 0.35805 | -0.3312 | 0.045065 | -0.36937 | -0.15697 | 0.014759 | -0.041094 | -0.47
| 3070 | -0.51246 | 0.6162 | 0.32391 | 0.28495 | 0.25562 | 0.64461 | -0.17702 | 0.37334 | -0.1533 | 0.65114
| 3071 | -0.13704 | 0.026912 | 0.83907 | 0.00015001 | -0.22212 | 0.084413 | 0.16185 | -0.24007 | -0.13127 | 0.070215
| 3072 | 0.25522 | -0.50271 | -0.0066723 | 0.4985 | 0.010606 | 0.15923 | -0.016588 | -0.48746 | 0.1162 | -0.24601
| 3073 | 0.50959 | 0.27744 | -0.68235 | 0.30495 | -0.58323 | -0.30408 | -0.6233 | 0.21955 | 0.033925 | -0.06957
| 3074 | 0.75648 | 0.15685 | -0.64631 | 0.62119 | 0.31655 | -0.077232 | -0.17532 | -0.30451 | 0.5954 | 0.34448
| 3075 | -0.31 | 0.41733 | 0.28789 | -0.45328 | 0.27951 | 0.25629 | 0.4163 | 0.51451 | 0.13438 | 0.11507
| 3076 | -0.074851 | -0.26945 | 0.32081 | -0.52115 | 0.09706 | 0.064853 | -0.1962 | 0.27661 | -0.38526 | 0.5199
| 3077 | 0.85682 | -0.51595 | 0.82252 | 0.58951 | 0.086053 | 0.61882 | -0.16472 | -0.39345 | 0.098945 | -0.4279
| 3078 | 0.38429 | -0.053374 | -0.85134 | -0.35867 | 0.33524 | -0.41306 | -0.31407 | 0.51143 | -0.2037 | 0.48726
| 3079 | 0.10978 | -0.10787 | 0.55469 | -0.80075 | 0.52031 | 0.17702 | -0.41785 | -0.35634 | -0.49592 | -0.0062697
| 3080 | 0.85067 | -0.55943 | 0.3851 | 0.35247 | 0.29708 | -0.22508 | 0.26386 | 0.18189 | 0.19483 | 0.033925
| 3081 | -0.6382 | 0.28593 | -0.46661 | 0.62865 | -0.82593 | -0.66251 | 0.81372 | 0.29339 | -0.13115 | -0.68615
| 3082 | -0.27316 | -0.095401 | -0.29936 | -0.4993 | -0.042138 | -0.4898 | 0.043287 | -0.38559 | -0.1825 | -0.082994
| 3083 | -0.026296 | -0.63462 | -0.18557 | -0.4668 | 0.46793 | -0.14274 | -0.68679 | 0.22045 | -0.16424 | -0.76484
| 3084 | -0.68456 | -0.71804 | -0.04026 | 0.34816 | -0.020561 | 0.12576 | 0.54933 | 0.43246 | -0.64489 | 0.1091
| 3085 | -0.071614 | -0.030928 | -0.020051 | -0.83477 | -0.19037 | -0.18803 | 0.84412 | 0.54338 | -0.37911 | 0.44009
| 3086 | 0.436 | 0.20924 | -0.4801 | 0.0018517 | -0.083539 | -0.40092 | -0.16747 | -0.031135 | 0.23954 | 0.17726
| 3087 | 0.25281 | -0.89851 | -0.050316 | 0.020255 | -0.34892 | 0.059202 | 0.23221 | -0.10888 | 0.55089 | -0.46251
| 3088 | 0.11202 | 0.27316 | -0.51886 | -0.21814 | 0.073016 | 0.1688 | -0.5954 | 0.7508 | -0.20899 | 0.03974
| 3089 | 0.85543 | 0.031754 | -0.71875 | -0.88642 | -0.042973 | 0.62811 | -0.12439 | -0.28663 | -0.35154 | -0.78251
| 3090 | 0.24787 | -0.21089 | 0.53967 | 0.8956 | 0.42563 | -0.095843 | -0.19025 | -0.062077 | -0.19769 | 0.52619
| 3091 | 0.047057 | -0.030516 | 0.32762 | -0.016689 | 0.21776 | -0.4993 | 0.09187 | -0.18963 | -0.12599 | 0.3038
| 3092 | 0.57964 | -0.0069743 | 0.34708 | -0.25697 | -0.097171 | -0.57562 | -0.51143 | 0.47875 | -0.21482 | -0.15342
| 3093 | -0.097393 | 0.49216 | 0.26822 | 0.08967 | 0.14017 | 0.17326 | 0.31232 | 0.35821 | -0.085943 | 0.013136
| 3094 | -0.23954 | -0.33284 | 0.24336 | 0.60289 | 0.2496 | 0.19223 | 0.78952 | 0.16723 | -0.077124 | -0.030722
| 3095 | 0.43334 | 0.13855 | -0.5693 | -0.4983 | 0.079728 | -0.50837 | 0.077341 | -0.0085869 | 0.34342 | 0.55875
| 3096 | 0.35494 | 0.62092 | 0.55627 | 0.51927 | -0.11813 | -0.41034 | 0.19 | -0.41085 | 0.54404 | -0.72269
| 3097 | -0.050842 | 0.51948 | 0.092531 | -0.02189 | 0.44009 | 0.21955 | -0.52366 | -0.079728 | -0.79579 | -0.084304
| 3098 | 0.5264 | -0.11202 | -0.61751 | 0.33555 | 0.10989 | -0.54294 | 0.19223 | 0.036828 | 0.32925 | 0.18901
| 3099 | -0.22689 | 0.028455 | 0.14309 | 0.39992 | 0.69751 | 0.070968 | 0.57941 | -0.055701 | 0.23039 | 0.24151
| 3100 | -0.5883 | 0.32806 | -0.45548 | -0.25254 | -0.19981 | -0.73904 | -0.61672 | 0.27924 | 0.085068 | 0.68172
| 3101 | 0.9005 | -0.15295 | 0.34923 | -0.51678 | -0.069355 | 0.7687 | 0.59614 | 0.3248 | -0.044437 | 0.19582
| 3102 | 0.38315 | 0.43317 | -0.26836 | -0.61206 | -0.13658 | -0.22741 | 0.1269 | 0.15661 | 0.59614 | 0.26237
| 3103 | 0.77218 | 0.45292 | 0.26047 | 0.018929 | 0.20798 | 0.10462 | -0.12989 | 0.10843 | 0.59963 | -0.1063
| 3104 | -0.22857 | -0.67274 | -0.27412 | 0.42424 | -0.26563 | -0.45255 | -0.1879 | -0.089561 | -0.44277 | -0.43176
| 3105 | 0.15071 | -0.094738 | -0.42685 | 0.20659 | -0.13577 | -0.54536 | 0.37686 | -0.20583 | -0.50594 | -0.0056661
| 3106 | 0.60694 | -0.093744 | -0.67274 | -0.42511 | 0.68204 | 0.10731 | -0.042451 | -0.31407 | -0.78763 | 0.25093
| 3107 | -0.35852 | -0.69129 | 0.069033 | -0.1797 | 0.45146 | 0.30928 | -0.31831 | -0.16364 | 0.049158 | 0.28327
| 3108 | -0.68839 | 0.30236 | 0.81588 | -0.41221 | -0.74212 | 0.18446 | 0.17945 | 0.17714 | -0.074203 | -0.35185
| 3109 | 0.11824 | -0.10485 | -0.16006 | 0.72269 | 0.19384 | -0.18766 | 0.57609 | 0.2216 | 0.56791 | -0.30021
| 3110 | 0.55402 | 0.1015 | -0.25535 | 0.019133 | 0.61646 | 0.25027 | -0.26128 | -0.09132 | 0.78023 | -0.018114
| 3111 | -0.13265 | -0.087586 | 0.29099 | 0.77932 | -0.53064 | 0.074851 | 0.36952 | -0.2278 | 0.65431 | 0.62145
| 3112 | -0.25939 | 0.18729 | 0.31582 | 0.097725 | -0.23836 | 0.60038 | 0.017096 | -0.071291 | -0.57515 | 0.53686
| 3113 | -0.21891 | 0.40662 | -0.20244 | -0.12222 | 0.55447 | 0.48765 | 0.76399 | 0.3882 | 0.29793 | -0.26549
| 3114 | 0.34617 | 0.51637 | 0.017198 | -0.009899 | -0.35867 | -0.43264 | 0.25656 | 0.45769 | -0.26427 | 0.02189
| 3115 | -0.19136 | 0.80687 | -0.38657 | -0.10764 | 0.020459 | 0.48144 | -0.13403 | 0.5458 | 0.42825 | 0.67061
| 3116 | 0.12931 | -0.46344 | -0.27509 | -0.033305 | 0.06914 | -0.053269 | -0.012731 | 0.45091 | 0.51389 | 0.14006
| 3117 | 0.61882 | -0.021583 | 0.0065716 | 0.01263 | -0.48922 | -0.52851 | -0.077016 | -0.50351 | 0.29807 | -0.076907
| 3118 | 0.057716 | -0.45972 | 0.71733 | 0.66519 | 0.62704 | -0.23639 | -0.10161 | 0.44063 | 0.14718 | 0.074959
| 3119 | 0.00035006 | 0.45255 | 0.12679 | -0.75363 | -0.043914 | -0.59441 | 0.56514 | 0.51534 | 0.32896 | 0.63163
| 3120 | 0.18226 | -0.49295 | 0.2524 | 0.85269 | 0.027426 | 0.19322 | -0.082994 | -0.77707 | 0.057079 | 0.085615
| 3121 | -0.025988 | -0.32717 | -0.40225 | -0.21546 | 0.016181 | 0.43706 | -0.48882 | 0.83969 | 0.37992 | -0.60821
| 3122 | 0.047267 | 0.4265 | -0.42268 | -0.19981 | -0.063037 | 0.42459 | 0.21994 | 0.45328 | -0.060692 | -0.024859
| 3123 | -0.56102 | 0.13473 | -0.54558 | -0.12519 | -0.48202 | 0.74174 | -0.49118 | 0.094185 | -0.73037 | -0.057716
| 3124 | 0.17495 | -0.6634 | -0.83177 | -0.28803 | -0.34205 | 0.37944 | 0.21114 | -0.28146 | 0.54294 | 0.70657
| 3125 | -0.013035 | 0.85201 | 0.19582 | 0.56606 | -0.5529 | -0.40966 | -0.29367 | 0.0011507 | 0.26849 | -0.29836
| 3126 | -0.51865 | -0.83 | -0.19831 | 0.5199 | -0.072692 | 0.3618 | 0.52576 | -0.8148 | 0.15425 | -0.10128
| 3127 | 0.34099 | -0.38073 | -0.45219 | -0.50634 | 0.0083852 | -0.3294 | -0.24814 | 0.2076 | -0.18569 | -0.90673
| 3128 | 0.017809 | -0.18753 | 0.22896 | -0.099056 | 0.51451 | 0.70117 | 0.14076 | -0.2492 | 0.057822 | 0.86108
| 3129 | -0.48922 | -0.34068 | -0.15472 | 0.58491 | 0.36968 | -0.35789 | -0.19384 | 0.48202 | 0.52136 | 0.18741
| 3130 | -0.084413 | 0.73942 | 0.60923 | 0.28747 | -0.009899 | 0.21776 | 0.30769 | -0.4588 | 0.10006 | -0.65751
| 3131 | -0.059415 | -0.13866 | 0.44242 | -0.016486 | 0.58563 | 0.075825 | -0.24694 | 0.72559 | 0.45695 | -0.26754
| 3132 | 0.12519 | 0.0090913 | -0.02722 | 0.44855 | 0.49394 | 0.58515 | -0.22521 | 0.64574 | 0.70623 | 0.67366
| 3133 | -0.91 | 0.012528 | 0.20357 | 0.046847 | 0.12541 | -0.32125 | 0.012427 | -0.20546 | -0.12484 | 0.38689
| 3134 | -0.066351 | -0.069892 | -0.3189 | -0.34785 | 0.36102 | -0.014759 | 0.0094951 | 0.47971 | -0.85682 | -0.93597
| 3135 | -0.062823 | 0.76655 | -0.12908 | -0.27371 | -0.044856 | -0.22598 | 0.13276 | 0.043078 | 0.81265 | -0.099167
| 3136 | -0.081469 | -0.20987 | -0.57964 | -0.80328 | 0.29141 | 0.14414 | -0.19458 | 0.2784 | 0.16125 | 0.024962
| 3137 | -0.54098 | -0.57444 | -0.26386 | -0.30624 | -0.040886 | 0.082667 | 0.063784 | 0.54911 | 0.39477 | -0.12439
| 3138 | -0.34266 | 0.74682 | 0.81697 | 0.49552 | -0.20219 | -0.30783 | -0.0755 | -0.65839 | 0.30293 | 0.1926
| 3139 | -0.25737 | 0.3804 | -0.16699 | -0.29594 | -0.40058 | -0.2733 | 0.76272 | 0.60744 | -0.60415 | -0.093523
| 3140 | -0.45127 | -0.011011 | 0.18214 | 0.3366 | -0.071076 | 0.045694 | -0.092862 | -0.12404 | 0.049474 | 0.02794
| 3141 | 0.59963 | -0.57 | 0.0023528 | 0.70623 | -0.052213 | 0.48241 | -0.75896 | 0.44674 | 0.24059 | 0.73411
| 3142 | -0.70794 | -0.04381 | -0.47569 | 0.13219 | -0.42043 | -0.42546 | 0.19769 | -0.28523 | -0.23809 | 0.10395
| 3143 | 0.08136 | -0.2476 | 0.16232 | 0.17471 | -0.12347 | 0.10496 | 0.11304 | -0.44547 | 0.02189 | -0.43866
| 3144 | 0.009596 | -0.23836 | -0.87631 | 0.4989 | -0.28677 | 0.64943 | -0.4078 | 0.21355 | 0.047582 | 0.19334
| 3145 | 0.82708 | 0.48882 | 0.26359 | -0.66015 | -0.18532 | -0.088573 | 0.36353 | 0.56838 | -0.077558 | 0.15153
| 3146 | 0.54514 | 0.056231 | -0.40259 | -0.61464 | -0.45055 | -0.048422 | -0.53664 | 0.36431 | 0.38364 | 0.46925
| 3147 | 0.0071757 | 0.28537 | -0.03714 | 0.05253 | -0.18214 | -0.91815 | -0.020561 | -0.12954 | -0.61908 | 0.11745
| 3148 | -0.026193 | -0.25107 | -0.27261 | 0.19806 | -0.039323 | -0.73524 | 0.37734 | -0.62811 | 0.4985 | -0.34586
| 3149 | -0.53772 | -0.22883 | -0.36731 | -0.35836 | -0.0064709 | -0.18287 | 0.10989 | -0.17435 | -0.53751 | 0.42965
| 3150 | -0.053269 | 0.029279 | 0.18385 | 0.18397 | 0.074095 | -0.2313 | -0.1127 | -0.096285 | -0.065174 | 0.65634
| 3151 | -0.17423 | -0.20044 | -0.027118 | 0.4683 | 0.24641 | -0.23221 | 0.61725 | -0.41733 | 0.30624 | 0.66549
| 3152 | -0.52724 | 0.31131 | 0.11 | 0.01182 | -0.95877 | 0.5001 | -0.27619 | -0.34433 | 0.44385 | 0.29155
| 3153 | -0.37095 | 0.36258 | 0.59245 | 0.95 | 0.76741 | 0.84476 | -0.15614 | -0.60213 | -0.076691 | -0.74174
| 3154 | -0.076907 | -0.536 | 0.77044 | 0.45146 | -0.21343 | 0.80635 | -0.031238 | 0.085396 | -0.44188 | -0.65431
| 3155 | -0.86771 | -0.13588 | 0.17592 | 0.80687 | -0.81053 | -0.38315 | 0.22573 | -0.46868 | 0.43635 | 0.01182
| 3156 | 0.087805 | -0.1706 | 0.36699 | -0.19906 | -0.088573 | -0.65489 | -0.49711 | 0.25254 | -0.0066723 | 0.55627
| 3157 | 0.012427 | -0.81807 | -0.13196 | -0.05814 | -0.084194 | 0.37207 | -0.27288 | -0.082885 | 0.18177 | -0.15578
| 3158 | -0.13104 | 0.093192 | 0.09033 | -0.22598 | -0.65172 | -0.4206 | 0.69227 | -0.3363 | -0.38918 | 0.19931
| 3159 | 0.22624 | 0.40025 | -0.3005 | 0.48746 | -0.47341 | 0.1261 | 0.29566 | 0.23901 | -0.45109 | -0.13057
| 3160 | -0.62517 | 0.64659 | 0.26686 | 0.05496 | 0.039844 | 0.59466 | -0.0728 | -0.18275 | 0.73675 | 0.74407
| 3161 | 0.42026 | -0.29028 | 0.50573 | 0.27247 | 0.6811 | 0.2524 | 0.0922 | 0.80481 | -0.36636 | 0.68267
| 3162 | 0.11869 | -0.034961 | -0.40645 | 0.30036 | -0.59147 | -0.11994 | 0.27 | -0.063784 | -0.1063 | 0.058777
| 3163 | -0.41153 | -0.43123 | 0.34205 | -0.021992 | -0.092421 | 0.25428 | -0.35463 | -0.47645 | 0.23351 | 0.46474
| 3164 | -0.56171 | -0.75855 | -0.44891 | -0.10708 | -0.0057666 | -0.089341 | -0.0092932 | 0.59714 | 0.10843 | 0.0042591
| 3165 | -0.11101 | 0.049369 | -0.58467 | -0.43902 | -0.25858 | -0.10787 | -0.02097 | -0.060798 | -0.19371 | 0.72815
| 3166 | 0.95204 | 0.12805 | -0.68647 | -0.64971 | -0.24747 | 0.29155 | -0.51307 | 0.14461 | -0.20735 | 0.65086
| 3167 | -0.055278 | 0.039323 | -0.50634 | -0.18336 | -0.23482 | -0.21942 | 0.14519 | -0.5264 | 0.011617 | -0.047687
| 3168 | 0.56954 | 0.012832 | -0.14882 | 0.068603 | -0.5693 | 0.22289 | -0.75282 | 0.55785 | -0.49394 | 0.11779
| 3169 | -0.39992 | -0.080381 | 0.020663 | 0.51699 | -0.22148 | 0.3951 | -0.79095 | -0.65029 | 0.83721 | 0.67396
| 3170 | -0.76272 | -0.089231 | -0.364 | -0.5347 | -0.64209 | 0.11938 | -0.48376 | 0.32435 | -0.64574 | -0.2674
| 3171 | 0.60314 | -0.33826 | 0.78436 | -0.0016514 | 0.048002 | 0.17909 | 0.21381 | -0.67674 | 0.042242 | -0.59963
| 3172 | -0.4985 | 0.036517 | -0.086162 | -0.59664 | 0.027735 | 0.011516 | -0.93917 | 0.25482 | -0.11756 | -0.20583
| 3173 | -0.61516 | 0.25993 | -0.49592 | -0.038179 | 0.59441 | -0.21368 | 0.31875 | 0.50533 | -0.064425 | 0.32583
| 3174 | -0.27041 | 0.19906 | 0.5714 | -0.35525 | -0.62092 | -0.48318 | 0.037763 | 0.84476 | 0.21597 | -0.053586
| 3175 | 0.52534 | 0.20672 | 0.45954 | 0.32643 | 0.76655 | -0.25254 | 0.076907 | 0.083867 | -0.29282 | 0.12404
| 3176 | -0.6786 | 0.055172 | -0.09198 | 0.18373 | -0.43053 | 0.035894 | 0.061544 | 0.33239 | 0.40159 | -0.088243
| 3177 | -0.28049 | 0.098058 | -0.67 | 0.077449 | -0.45127 | -0.64433 | 0.06496 | 0.27082 | -0.60516 | -0.9134
| 3178 | 0.59171 | 0.014962 | 0.33134 | 0.67152 | -0.79433 | -0.35092 | -0.74525 | 0.28649 | 0.18815 | 0.063784
| 3179 | 0.23888 | 0.51886 | -0.67458 | -0.12679 | 0.13057 | 0.67 | -0.17483 | -0.12313 | -0.29367 | 0.38592
| 3180 | -0.017707 | -0.27924 | -0.45954 | -0.073987 | -0.54142 | 0.2504 | -0.16364 | -0.21917 | 0.058353 | -0.78114
| 3181 | -0.67396 | -0.88126 | -0.058353 | 0.53 | 0.24086 | 0.0092932 | 0.29311 | -0.033305 | -0.13611 | -0.19806
| 3182 | 0.74643 | 0.20949 | 0.67984 | -0.62731 | -0.19657 | -0.49315 | -0.067959 | 0.09187 | 0.10876 | -0.53449
| 3183 | -0.35092 | 0.65345 | -0.26822 | 0.43706 | -0.93443 | -0.62731 | 0.12713 | 0.66281 | 0.43387 | -0.054326
| 3184 | 0.18104 | -0.15012 | -0.13057 | -0.019949 | -0.14507 | 0.34205 | -0.18471 | -0.52851 | 0.086819 | -0.22741
| 3185 | 0.38689 | -0.87712 | -0.21139 | -0.72705 | -0.16472 | -0.064425 | 0.29509 | 0.10764 | 0.2711 | 0.56034
| 3186 | 0.094517 | -0.39098 | 0.79678 | 0.33796 | 0.38315 | -0.14064 | 0.00055015 | 0.46981 | -0.088573 | 0.43866
| 3187 | -0.11259 | -0.073447 | -0.01 | 0.44134 | 0.84284 | -0.33239 | 0.27096 | 0.61128 | -0.23678 | 0.41596
| 3188 | 0.048002 | -0.66251 | -0.37286 | 0.44927 | -0.06261 | 0.023117 | -0.13507 | -0.15792 | -0.0078811 | -0.13173
| 3189 | 0.26932 | -0.21699 | -0.18336 | 0.31116 | -0.63792 | -0.39742 | -0.084522 | -0.70352 | -0.1921 | 0.59049
| 3190 | 0.25482 | 0.28817 | 0.50371 | 0.25294 | 0.083867 | 0.29622 | 0.35727 | -0.15816 | -0.59788 | -0.85543
| 3191 | 0.10809 | 0.22392 | 0.28104 | 0.348 | 0.009899 | 0.18827 | -0.83969 | 0.77175 | 0.064746 | -0.55492
| 3192 | -0.24178 | 0.088353 | 0.78251 | -0.076149 | 0.15828 | -0.37767 | -0.59294 | -0.028661 | 0.08978 | -0.060266
| 3193 | 0.55178 | -0.51061 | -0.0077803 | 0.082231 | -0.61412 | -0.5264 | 0.28986 | 0.14484 | -0.68298 | 0.1546
| 3194 | -0.1261 | 0.82422 | 0.011921 | -0.13797 | 0.40142 | -0.0072765 | 0.026296 | -0.37143 | -0.24151 | 0.45109
| 3195 | -0.59863 | -0.40645 | -0.13334 | 0.65576 | 0.070968 | 0.043391 | -0.16328 | 0.077774 | 0.11236 | -0.077341
| 3196 | -0.72815 | -0.018929 | -0.014252 | -0.65143 | 0.064425 | -0.051159 | 0.19284 | -0.43688 | -0.2816 | -0.51041
| 3197 | 0.19806 | 0.48415 | -0.27495 | 0.33149 | 0.41051 | -0.32598 | -0.15804 | -0.22045 | 0.61672 | 0.77306
| 3198 | -0.36526 | 0.40443 | 0.082122 | 0.15082 | -0.06914 | -0.31641 | -0.015876 | 0.26318 | 0.16197 | -0.17326
| 3199 | 0.54845 | -0.17763 | 0.23691 | 0.11135 | -0.54054 | 0.31553 | 0.81159 | -0.28355 | 0.12028 | 0.086162
| 3200 | -0.011011 | -0.70897 | -0.17399 | 0.46624 | -0.36715 | 0.13948 | -0.27151 | -0.67766 | -0.22302 | 0.015571
| 3201 | -0.31305 | -0.38689 | 0.022299 | 0.13253 | 0.32672 | -0.25281 | -0.18189 | 0.57491 | 0.039844 | 0.30122
| 3202 | -0.42164 | 0.45585 | -0.12416 | -0.42233 | 0.39279 | -0.30079 | -0.464 | -0.3681 | -0.37095 | -0.70897
| 3203 | -0.044542 | -0.51328 | -0.1389 | -0.74407 | 0.46549 | -0.60138 | 0.086162 | -0.26291 | 0.19148 | 0.57093
| 3204 | -0.15354 | -0.6985 | -0.0016514 | -0.10406 | 0.35758 | 0.093744 | -0.012326 | 0.35324 | 0.011719 | 0.21241
| 3205 | 0.26672 | -0.038491 | 0.25993 | 0.81426 | -0.32569 | 0.041199 | 0.45585 | 0.16783 | -0.27014 | 0.66909
| 3206 | 0.3366 | -0.088792 | -0.33404 | 0.11248 | -0.57093 | -0.11146 | -0.57233 | -0.15851 | 0.1389 | 0.045589
| 3207 | -0.43831 | -0.26686 | -0.52745 | -0.1261 | -0.62277 | -0.08649 | 0.30351 | 0.87155 | 0.25791 | 0.51575
| 3208 | -0.45861 | -0.52788 | 0.19247 | 0.85474 | -0.68871 | -0.38267 | -0.46139 | 0.48338 | -0.27882 | -0.40008
| 3209 | -0.86108 | 0.17726 | 0.036828 | -0.044856 | 0.29893 | -0.61438 | -0.021379 | -0.69884 | 0.66728 | -0.24482
| 3210 | -0.30653 | 0.29226 | 0.093634 | 0.035894 | -0.71035 | 0.43813 | -0.26454 | 0.082776 | -0.0047613 | 0.53107
| 3211 | -0.53342 | -0.23221 | 0.064425 | -0.1153 | 0.32037 | 0.2431 | -0.012832 | -0.84605 | -0.74251 | 0.15792
| 3212 | -0.34114 | 0.37927 | -0.16735 | -0.018725 | 0.080054 | -0.4531 | 0.52661 | -0.43991 | -0.31247 | 0.62973
| 3213 | 0.66221 | 0.41836 | 0.0093941 | 0.54602 | 0.3025 | -0.23613 | 0.11847 | -0.79776 | 0.71347 | -0.09011
| 3214 | -0.5714 | 0.36557 | -0.036724 | 0.29099 | 0.1797 | 0.37622 | -0.15673 | -0.058034 | 0.03714 | 0.6077
| 3215 | -0.53043 | 0.6852 | -0.27647 | 0.48435 | -0.44188 | -0.64097 | -0.48726 | -0.81372 | 0.24442 | 0.21712
| 3216 | -0.6257 | 0.28063 | -0.34083 | -0.62919 | -0.76315 | -0.70623 | 0.53043 | 0.62013 | -0.31611 | -0.87631
| 3217 | 0.52052 | 0.67 | -0.32228 | 0.49612 | -0.37095 | 0.2037 | -0.22148 | -0.20432 | 0.28007 | 0.81697
| 3218 | -0.66192 | 0.52052 | 0.1603 | 0.51554 | 0.73904 | 0.13334 | 0.83 | 0.30552 | 0.24336 | -0.083649
| 3219 | 0.75322 | -0.29197 | 0.20722 | -0.4799 | -0.79925 | -0.55492 | -0.4588 | -0.20962 | -0.13519 | -0.53213
| 3220 | 0.013744 | -0.12759 | 0.12851 | 0.8882 | -0.59639 | -0.67274 | -0.264 | -0.37366 | 0.0010506 | 0.71277
| 3221 | 0.44638 | 0.51205 | 0.25455 | 0.29226 | -0.18238 | -0.12587 | 0.62224 | 0.01263 | -0.34023 | 0.3551
| 3222 | -0.59689 | 0.33735 | -0.17423 | 0.10273 | -0.11034 | -0.55717 | -0.38413 | 0.13127 | -0.43671 | 0.037347
| 3223 | 0.45292 | 0.27302 | -0.55762 | -0.54251 | 0.007478 | 0.069463 | 0.11699 | -0.45055 | 0.070861 | -0.0010506
| 3224 | -0.75896 | -0.79925 | -0.20006 | 0.34038 | 0.51575 | 0.68078 | 0.10686 | -0.0053644 | 0.96127 | -0.11428
| 3225 | -0.11688 | -0.17483 | -0.36039 | -0.38348 | 0.43653 | 0.069248 | -0.064639 | -0.18655 | 0.026193 | -0.01842
| 3226 | 0.38787 | -0.54889 | 0.51865 | 0.42389 | -0.030412 | -0.39543 | 0.17896 | 0.47019 | -0.055172 | -0.23823
| 3227 | 0.59938 | -0.28439 | 0.038699 | -0.29226 | 0.36573 | -0.22792 | -0.34403 | 0.33344 | -0.82824 | -0.14566
| 3228 | 0.14227 | 0.17096 | -0.236 | -0.41579 | 0.21635 | -0.10295 | 0.83538 | 0.19969 | 0.41272 | 0.10406
| 3229 | -0.15496 | 0.25174 | -0.37016 | 0.89656 | 0.024244 | -0.30986 | 0.16149 | -0.072261 | -0.60795 | 0.1786
| 3230 | -0.049789 | -0.93597 | -0.79 | -0.19919 | -0.58757 | 0.33735 | 0.39527 | -0.32125 | 0.10117 | -0.59294
| 3231 | -0.76357 | -0.68647 | -0.044228 | 0.64377 | 0.60668 | 0.10697 | 0.61128 | 0.14169 | 0.20194 | 0.076799
| 3232 | 0.4776 | -0.31582 | 0.048527 | -0.62838 | -0.39527 | -0.67674 | 0.055278 | -0.13519 | -0.30899 | -0.22212
| 3233 | 0.011213 | 0.006169 | -0.3375 | -0.44349 | -0.12233 | 0.81588 | 0.49078 | 0.020459 | 0.09706 | -0.70657
| 3234 | -0.26945 | -0.61699 | 0.21419 | -0.67735 | -0.16868 | -0.0022525 | -0.81642 | -0.33105 | -0.15721 | 0.20244
| 3235 | 0.44313 | -0.32776 | 0.070645 | 0.54294 | -0.037555 | -0.19969 | 0.06293 | 0.033718 | 0.35216 | -0.24429
| 3236 | 0.29325 | -0.67182 | 0.043601 | 0.35169 | 0.13762 | -0.44457 | 0.74446 | 0.65287 | 0.11451 | 0.57233
| 3237 | -0.65634 | 0.30711 | 0.49771 | -0.51266 | 0.85269 | 0.050632 | -0.089231 | 0.26047 | -0.054326 | -0.031651
| 3238 | 0.03465 | 0.43193 | -0.022708 | 0.57 | -0.013542 | 0.066244 | -0.15946 | 0.32406 | -0.37175 | 0.24508
| 3239 | -0.043496 | -0.23312 | 0.32494 | 0.1072 | -0.20357 | 0.05158 | -0.11034 | 0.34571 | -0.72197 | 0.44349
| 3240 | 0.0728 | -0.52724 | 0.90461 | -0.057928 | -0.41425 | -0.71592 | -0.13322 | 0.51969 | 0.65809 | -0.39444
| 3241 | 0.053903 | -0.56699 | -0.40511 | -0.40729 | 0.022708 | -0.094738 | -0.77087 | -0.5583 | -0.39131 | -0.10261
| 3242 | -0.22508 | 0.3309 | -0.66578 | -0.47894 | 0.10608 | 0.29452 | -0.019949 | -0.077883 | 0.264 | 0.53085
| 3243 | -0.70184 | 0.16304 | -0.25858 | -0.20294 | -0.0004501 | -0.22961 | -0.28761 | 0.26522 | -0.38869 | -0.25858
| 3244 | -0.10239 | 0.00055015 | 0.38364 | 0.59838 | -0.42407 | 0.61961 | 0.067637 | 0.64265 | -0.2278 | 0.27343
| 3245 | 0.52387 | -0.99 | 0.057185 | -0.59024 | -0.30122 | -0.084413 | 0.11903 | -0.21 | -0.089121 | -0.41136
| 3246 | 0.028867 | 0.65985 | -0.57023 | 0.63271 | -0.050948 | 0.27509 | 0.40225 | -0.065602 | 0.28887 | -0.40561
| 3247 | 0.83477 | -0.35821 | 0.35743 | 0.33781 | 0.43529 | 0.028661 | -0.046008 | 0.64461 | 0.23299 | -0.18914
| 3248 | -0.35108 | 0.4828 | -0.73111 | -0.49771 | 0.65258 | 0.056655 | -0.15212 | 0.14636 | -0.12313 | -0.23104
| 3249 | 0.24508 | -0.40477 | -0.30408 | 0.44511 | -0.62946 | -0.10529 | 0.64293 | 0.34985 | -0.021174 | -0.20332
| 3250 | 0.66939 | -0.94255 | 0.18495 | -0.0030547 | 0.43777 | -0.51657 | -0.44583 | 0.32911 | -0.071184 | -0.0081835
| 3251 | 0.41442 | 0.23613 | 0.46737 | 0.46737 | 0.63027 | -0.57751 | -0.40259 | -0.044123 | 0.073663 | -0.11972
| 3252 | 0.3422 | -0.21444 | 0.062503 | 0.45109 | 0.17459 | 0.34678 | 0.069785 | -0.30337 | -0.58131 | -0.057822
| 3253 | -0.13311 | 0.14332 | -0.7184 | -0.35479 | -0.092531 | -0.24072 | 0.074851 | 0.19471 | -0.062823 | -0.11202
| 3254 | 0.27014 | 0.063998 | 0.06016 | -0.57893 | 0.51348 | 0.35216 | -0.20382 | -0.43458 | 0.66849 | 0.4999
| 3255 | 0.023322 | -0.075068 | -0.087695 | 0.26563 | -0.30308 | 0.24681 | 0.065067 | 0.27813 | -0.086271 | 0.046533
| 3256 | -0.1025 | -0.04517 | 0.057928 | -0.5264 | 0.24575 | 0.064318 | -0.11972 | 0.38934 | -0.022299 | 0.62597
| 3257 | 0.68456 | 0.56814 | -0.10418 | 0.18988 | 0.50513 | -0.16328 | 0.73866 | 0.11745 | 0.17884 | 0.38234
| 3258 | -0.17181 | 0.1425 | -0.29028 | 0.69162 | 0.56699 | 0.11484 | -0.52745 | -0.27813 | 0.047162 | -0.61829
| 3259 | 0.34464 | 0.53492 | -0.062717 | -0.057822 | 0.5728 | 0.6257 | -0.33796 | -0.96394 | 0.56514 | -0.13299
| 3260 | 0.1425 | 0.11045 | -0.28174 | -0.23718 | -0.55943 | 0.036205 | -0.36008 | 0.23849 | -0.47971 | 0.61412
| 3261 | 0.041094 | 0.52555 | -0.050632 | -0.14906 | -0.35015 | 0.44873 | -0.015267 | 0.86847 | -0.30624 | 0.65057
| 3262 | 0.043496 | -0.10731 | 0.54142 | 0.16747 | -0.72341 | -0.25831 | -0.23547 | 0.073771 | 0.10128 | -0.1466
| 3263 | 0.14204 | 0.79826 | 0.22186 | -0.085068 | -0.26836 | -0.69194 | 0.55089 | 0.57846 | 0.62119 | -0.60188
| 3264 | 0.16054 | -0.48164 | 0.09839 | 0.20031 | -0.75938 | 0.029485 | 0.92584 | -0.061437 | -0.39066 | 0.38771
| 3265 | 0.028043 | -0.26877 | 0.4471 | -0.44224 | -0.12667 | -0.03465 | 0.90461 | 0.020153 | -0.91574 | -0.2175
| 3266 | 0.56422 | -0.55 | 0.50553 | 0.18055 | -0.34969 | -0.4683 | -0.25549 | 0.23941 | -0.14052 | 0.61387
| 3267 | 0.60213 | -0.044542 | 0.34678 | 0.031341 | 0.45438 | -0.23915 | -0.14777 | -0.36243 | 0.73751 | -0.59269
| 3268 | 0.86847 | -0.46437 | -0.10978 | -0.034133 | -0.083321 | 0.8882 | -0.01091 | 0.6755 | 0.088573 | 0.9089
| 3269 | -0.021992 | 0.12966 | -0.25027 | -0.78068 | 0.50817 | -0.026193 | -0.91574 | -0.28719 | 0.066458 | 0.057185
| 3270 | -0.78716 | -0.54229 | 0.40713 | 0.12736 | 0.053163 | -0.024039 | -0.57988 | 0.54734 | 0.71417 | -0.052108
| 3271 | 0.45401 | 0.063357 | 0.12359 | -0.29864 | -0.073987 | -0.32051 | 0.83845 | -0.055066 | -0.26918 | -0.75161
| 3272 | 0.093082 | -0.28775 | -0.021992 | 0.36258 | -0.24165 | -0.39692 | -0.7881 | 0.58323 | -0.032374 | 0.11462
| 3273 | -0.17702 | -0.016079 | 0.033822 | 0.028352 | -0.46195 | 0.23 | 0.080707 | -0.10652 | -0.54011 | 0.70862
| 3274 | -0.39197 | 0.54978 | -0.3923 | 0.13346 | 0.29028 | 0.27082 | 0.21482 | -0.31978 | -0.94804 | 0.37175
| 3275 | -0.16964 | 0.34785 | -0.21891 | -0.15697 | 0.53881 | -0.47246 | 0.77841 | -0.40949 | -0.14402 | 0.1221
| 3276 | -0.21114 | 0.78529 | -0.33675 | -0.41289 | 0.0755 | -0.56239 | -0.41802 | -0.8747 | -0.23234 | -0.44583
| 3277 | -0.64321 | 0.50371 | -0.2193 | 0.082994 | -0.55357 | 0.008486 | 0.52957 | 0.28243 | 0.15106 | 0.12702
| 3278 | -0.027015 | 0.018929 | -0.05496 | -0.68267 | 0.66399 | -0.26918 | 0.75938 | -0.22935 | -0.75161 | -0.11756
| 3279 | -0.46213 | 0.6811 | -0.25697 | -0.025064 | -0.024756 | 0.32791 | -0.40225 | 0.86696 | -0.61699 | -0.066887
| 3280 | -0.025577 | -0.55785 | -0.15247 | -0.33404 | 0.60949 | -0.37895 | 0.15567 | -0.43 | -0.12222 | 0.13369
| 3281 | 0.38445 | -0.18581 | 0.3357 | -0.24561 | 0.22418 | -0.074851 | -0.10362 | -0.58587 | -0.59294 | 0.21025
| 3282 | -0.59441 | 0.14309 | -0.66459 | 0.28341 | 0.83177 | -0.16388 | -0.16496 | 0.016588 | -0.49315 | -0.57822
| 3283 | -0.74485 | 0.30812 | -0.69032 | -0.25455 | 0.056231 | 0.35293 | 0.64097 | 0.81318 | 0.40611 | 0.25174
| 3284 | -0.046008 | -0.71452 | -0.91693 | 0.28803 | 0.39098 | 0.47113 | 0.12461 | 0.15165 | -0.21139 | 0.0081835
| 3285 | -0.41922 | -0.00095045 | 0.44782 | -0.5922 | 0.59838 | -0.64546 | -0.36699 | -0.4987 | -0.053586 | 0.33359
| 3286 | 0.63682 | -0.20823 | 0.65518 | 0.54448 | 0.064532 | -0.45456 | -0.23678 | -0.23286 | -0.10574 | -0.62731
| 3287 | 0.035998 | -0.26849 | -0.39809 | 0.27302 | -0.52157 | 0.32243 | 0.51225 | 0.55694 | 0.0014511 | -0.29566
| 3288 | -0.16304 | -0.4279 | -0.16113 | -0.10843 | 0.03 | 0.0019519 | -0.33269 | 0.46925 | 0.011011 | -0.067423
| 3289 | -0.75731 | -0.29282 | -0.59466 | 0.22831 | 0.26047 | 0.18766 | 0.20596 | 0.16567 | 0.13034 | -0.11813
| 3290 | 0.83059 | 0.71627 | -0.39213 | 0.14367 | -0.43 | -0.13219 | 0.53385 | 0.36258 | 0.44692 | -0.4983
| 3291 | 0.096396 | -0.79678 | 0.97 | -0.28593 | 0.15543 | -0.23364 | -0.065495 | -0.35185 | -0.32273 | 0.57703
| 3292 | -0.91112 | -0.40966 | 0.25966 | -0.31073 | 0.093413 | 0.20019 | 0.38283 | 0.35432 | 0.42233 | -0.3074
| 3293 | -0.66281 | -0.79875 | -0.0071757 | 0.0088895 | -0.081904 | 0.35077 | -0.71592 | 0.16904 | -0.42493 | 0.051369
| 3294 | 0.29113 | -0.48125 | 0.032064 | -0.060266 | 0.63271 | -0.32391 | -0.032788 | 0.30265 | -0.50857 | 0.019949
| 3295 | -0.67213 | 0.45806 | -0.67519 | 0.62677 | -0.32628 | -0.3882 | 0.42164 | 0.66429 | 0.19247 | 0.51328
| 3296 | 0.24893 | -0.075608 | 0.11101 | 0.18361 | -0.57421 | -0.058353 | 0.63737 | -0.50817 | 0.44493 | -0.37414
| 3297 | 0.2398 | 0.5021 | 0.47398 | 0.016283 | 0.61672 | 0.55067 | 0.021174 | -0.69032 | 0.026912 | 0.46009
| 3298 | 0.21853 | -0.14753 | 0.052319 | -0.81212 | -0.71069 | -0.063998 | 0.82196 | 0.070968 | 0.20344 | 0.27564
| 3299 | -0.29226 | 0.22238 | 0.20069 | 0.28873 | -0.50271 | -0.18153 | -0.57846 | -0.76957 | 0.44475 | 0.32851
| 3300 | 0.0062697 | -0.051264 | 0.020868 | -0.0045604 | -0.46925 | -0.30711 | 0.21 | -0.044647 | 0.4987 | 0.047477
| 3301 | 0.31451 | 0.42842 | 0.024141 | -0.46906 | -0.61283 | 0.57822 | 0.31963 | 0.57116 | -0.41068 | -0.45401
| 3302 | -0.88642 | 0.096617 | -0.82766 | 0.20319 | 0.5529 | -0.61646 | 0.23065 | -0.046323 | -0.10652 | 0.31611
| 3303 | -0.52261 | -0.39775 | 0.002453 | 0.048212 | -0.12989 | 0.97764 | 0.26142 | 0.24283 | -0.24363 | 0.10809
| 3304 | 0.61361 | 0.23547 | 0.67182 | -0.38526 | -0.10675 | -0.26549 | -0.081904 | 0.57727 | 0.12519 | -0.05549
| 3305 | 0.15094 | 0.10006 | -0.21 | 0.50959 | -0.21584 | -0.094959 | 0.13357 | 0.12006 | 0.21076 | 0.3116
| 3306 | 0.65663 | -0.015673 | 0.45493 | -0.17726 | 0.81697 | 0.63627 | 0.11428 | 0.8755 | -0.25508 | 0.17605
| 3307 | -0.47818 | -0.076691 | 0.70184 | 0.43884 | 0.16603 | -0.34601 | 0.096507 | -0.2512 | -0.24099 | -0.68871
| 3308 | -0.065174 | 0.39908 | 0.29979 | 0.67519 | 0.17909 | -0.52936 | -0.11496 | 0.46887 | -0.43123 | -0.24191
| 3309 | 0.35821 | -0.059521 | -0.21661 | 0.44421 | 0.11394 | -0.1952 | -0.20031 | -0.65809 | 0.31611 | -0.19969
| 3310 | 0.068818 | 0.19124 | -0.13288 | -0.41802 | 0.026296 | -0.32851 | -0.0057666 | -0.29594 | 0.027837 | -0.067101
| 3311 | 0.452 | -0.69032 | 0.75772 | -0.30899 | 0.26536 | -0.7512 | -0.8366 | -0.22728 | -0.25013 | -0.49612
| 3312 | -0.44619 | -0.14824 | 0.53946 | -0.098834 | 0.8821 | -0.29779 | 0.16268 | 0.12885 | -0.067959 | -0.55649
| 3313 | 0.87876 | 0.56537 | -0.4981 | 0.41768 | 0.061544 | 0.43848 | 0.48048 | -0.68615 | -0.32037 | -0.71698
| 3314 | 0.09044 | 0.68361 | 0.43123 | -0.52597 | 0.42303 | -0.01842 | 0.037036 | -0.41854 | -0.084085 | -0.034858
| 3315 | -0.45255 | -0.4981 | -0.2326 | -0.50291 | 0.67674 | -0.11631 | -0.59171 | 0.4857 | 0.30437 | -0.030309
| 3316 | -0.53794 | 0.18287 | 0.16304 | 0.63027 | -0.48804 | 0.042764 | 0.13785 | -0.0094951 | 0.9134 | -0.13092
| 3317 | -0.4286 | -0.19582 | 0.48609 | -0.40058 | 0.3454 | 0.23705 | -0.044228 | 0.3618 | -0.24522 | 0.23849
| 3318 | -0.044856 | -0.34785 | 0.62704 | 0.16232 | 0.61856 | -0.27 | -0.2076 | 0.50695 | 0.066244 | -0.22935
| 3319 | 0.75607 | -0.14029 | -0.55739 | 0.48668 | -0.47569 | 0.22096 | -0.32672 | 0.6546 | 0.54251 | 0.78436
| 3320 | -0.39809 | 0.39246 | -0.78114 | 0.62277 | -0.58467 | 0.90461 | 0.51041 | -0.11394 | 0.043287 | 0.45273
| 3321 | 0.55245 | 0.37382 | 0.023732 | 0.56057 | 0.72089 | 0.27702 | 0.13692 | 0.11372 | -0.36494 | -0.021787
| 3322 | -0.49711 | 0.18079 | -0.13473 | 0.27951 | 0.65576 | -0.12989 | -0.80125 | -0.65057 | -0.20269 | 0.64097
| 3323 | -0.2256 | 0.40359 | 0.73561 | 0.60949 | -0.046113 | 0.35463 | -0.21432 | -0.17787 | 0.036724 | -0.1136
| 3324 | 0.65547 | 0.063464 | 0.34647 | -0.28313 | 0.53342 | -0.18877 | -0.70691 | -0.30725 | 0.57822 | 0.33841
| 3325 | 0.4206 | 0.078968 | -0.85613 | 0.37143 | 0.082013 | -0.12119 | -0.00015001 | 0.60567 | 0.19557 | -0.36211
| 3326 | 0.73751 | 0.72233 | 0.11428 | 0.035272 | 0.16844 | 0.010202 | -0.80277 | -0.12553 | 0.21241 | 0.56422
| 3327 | -0.063144 | -0.02722 | -0.16472 | -0.5015 | 0.62437 | 0.1136 | -0.39279 | -0.2571 | 0.077124 | -0.15709
| 3328 | 0.17362 | -0.065281 | 0.66192 | -0.32125 | -0.6703 | -0.085178 | -0.4163 | 0.88381 | 0.80687 | 0.56699
| 3329 | -0.039115 | -0.020051 | 0.64829 | 0.24734 | 0.54911 | -0.43493 | -0.61699 | 0.61335 | -0.45018 | -0.48048
| 3330 | -0.078317 | -0.31714 | 0.26536 | -0.74841 | -0.1063 | -0.71 | 0.72963 | -0.47531 | 0.099833 | -0.4046
| 3331 | -0.1253 | -0.08989 | 0.075068 | -0.087147 | -0.14941 | -0.23443 | 0.017198 | 0.30279 | 0.72852 | 0.95877
| 3332 | 0.55492 | -0.18618 | -0.28299 | 0.47779 | -0.21101 | 0.21381 | 0.28132 | -0.73751 | 0.6407 | 0.65316
| 3333 | 0.3214 | -0.29836 | -0.25508 | 0.049263 | 0.41579 | 0.0082843 | 0.22212 | 0.3817 | 0.60872 | -0.54514
| 3334 | -0.29608 | 0.69685 | 0.067745 | -0.63848 | -0.26973 | -0.51886 | -0.60719 | -0.27522 | -0.12828 | 0.28663
| 3335 | 0.030928 | -0.39659 | -0.073555 | -0.1786 | -0.049053 | 0.17641 | -0.23195 | 0.080816 | -0.023834 | -0.26413
| 3336 | -0.22045 | -0.13127 | 0.49216 | -0.42895 | -0.4293 | 0.011617 | -0.76063 | 0.12759 | 0.10921 | 0.096285
| 3337 | -0.12347 | -0.46605 | -0.12279 | -0.37526 | -0.039844 | -0.025885 | -0.18951 | -0.029588 | 0.19371 | 0.64829
| 3338 | 0.93292 | -0.53107 | -0.31203 | -0.20395 | 0.90356 | -0.47493 | -0.40393 | -0.0047613 | 0.049053 | -0.22456
| 3339 | -0.40075 | -0.52052 | -0.27661 | -0.55514 | 0.3727 | -0.54492 | 0.10172 | -0.11451 | -0.15923 | -0.45843
| 3340 | -0.16747 | -0.65489 | 0.5656 | -0.085724 | -0.01091 | -0.20937 | -0.25267 | -0.96127 | -0.57047 | 0.054008
| 3341 | 0.4653 | -0.44583 | -0.86771 | 0.085178 | 0.71 | -0.019949 | -0.15887 | 0.43035 | -0.68204 | 0.26142
| 3342 | -0.89851 | -0.47952 | -0.72596 | -0.68456 | 0.1229 | 0.5806 | -0.93 | 0.60795 | -0.35401 | 0.61516
| 3343 | 0.54404 | 0.45972 | -0.17872 | -0.46028 | 0.02897 | 0.15413 | 0.15448 | -0.66221 | 0.70251 | 0.59963
| 3344 | 0.47113 | 0.060372 | 0.5693 | -0.50472 | 0.20672 | -0.096839 | 0.41459 | -0.030412 | -0.78436 | -0.43938
| 3345 | -0.089121 | 0.014759 | 0.48357 | 0.2602 | -0.059202 | 0.53342 | 0.20181 | 0.83 | -0.55492 | 0.90151
| 3346 | 0.23796 | -0.45732 | -0.61516 | 0.16209 | -0.36039 | 0.73561 | 0.041303 | -0.29127 | -0.44439 | -0.84933
| 3347 | 0.14824 | -0.448 | -0.51802 | 0.11699 | -0.57727 | 0.40209 | -0.31641 | 0.032374 | 0.64914 | 0.34754
| 3348 | 0.40645 | -0.16304 | 0.029588 | -0.76484 | 0.44045 | 0.1109 | 0.21635 | -0.46083 | -0.17012 | 0.035272
| 3349 | 0.11011 | -0.11022 | -0.17483 | 0.036309 | 0.073663 | 0.96394 | 0.56491 | 0.43582 | -0.8747 | 0.20609
| 3350 | -0.069463 | -0.47341 | -0.37638 | 0.052846 | -0.041094 | -0.5608 | -0.21 | 0.37558 | 0.037867 | -0.2504
| 3351 | 0.099611 | -0.08978 | 0.21444 | -0.49731 | -0.17641 | -0.45 | -0.61594 | 0.13161 | -0.51802 | 0.28202
| 3352 | -0.14496 | -0.48202 | 0.25804 | -0.29495 | -0.054431 | 0.61309 | -0.56676 | 0.046638 | -0.7569 | -0.2476
| 3353 | -0.27467 | -0.17314 | -0.6077 | -0.66909 | 0.096396 | 0.095511 | 0.4826 | 0.13553 | -0.40125 | -0.77796
| 3354 | 0.17374 | -0.41051 | -0.32598 | 0.16928 | 0.37 | 0.28565 | -0.026707 | 0.027735 | -0.29864 | 0.66608
| 3355 | 0.3005 | 0.087695 | -0.34068 | -0.11688 | 0.59024 | -0.5693 | 0.19396 | 0.7184 | 0.11022 | 0.17592
| 3356 | -0.70897 | -0.73411 | -0.21674 | -0.72378 | -0.72815 | 0.76957 | 0.75896 | 0.53085 | 0.0029544 | -0.13588
| 3357 | -0.50371 | 0.032167 | -0.10809 | 0.19645 | -0.50959 | -0.25187 | 0.8148 | 0.4859 | -0.70931 | 0.94255
| 3358 | -0.25899 | 0.28663 | -0.82252 | -0.1196 | -0.78763 | -0.37318 | -0.18729 | 0.24151 | 0.051791 | -0.017096
| 3359 | 0.10039 | 0.39428 | -0.48125 | -0.35231 | 0.28007 | -0.029279 | 0.42199 | -0.30986 | 0.65287 | -0.28118
| 3360 | 0.34174 | 0.22805 | 0.39975 | 0.2504 | -0.29183 | 0.072261 | -0.1852 | 0.54514 | -0.34479 | 0.043914
| 3361 | 0.53277 | 0.030412 | 0.8755 | 0.16197 | 0.71627 | 0.30624 | -0.8747 | -0.45018 | -0.19819 | 0.19111
| 3362 | 0.017198 | 0.22444 | 0.056549 | -0.52324 | 0.86546 | 0.39759 | 0.55379 | 0.33841 | -0.16149 | 0.77572
| 3363 | -0.4997 | -0.26223 | -0.34678 | 0.29907 | 0.28453 | -0.1921 | 0.1729 | 0.27151 | 0.15982 | 0.17423
| 3364 | -0.051159 | -0.050632 | -0.53664 | -0.18373 | 0.78669 | 0.078425 | -0.17508 | 0.30667 | 0.23849 | 0.013542
| 3365 | 0.39576 | 0.62973 | -0.6755 | 0.079511 | 0.47284 | -0.60821 | 0.064212 | -0.75772 | -0.012022 | 0.75
| 3366 | -0.31334 | -0.046847 | -0.043705 | -0.44927 | 0.12154 | -0.12347 | 0.9078 | -0.4426 | -0.60163 | 0.73486
| 3367 | 0.34357 | 0.26604 | 0.61051 | -0.18299 | 0.088353 | -0.66849 | -0.51948 | -0.60188 | 0.17775 | -0.12097
| 3368 | 0.066137 | -0.19769 | -0.3838 | -0.28649 | 0.087038 | 0.79826 | -0.43352 | 0.18803 | 0.0025533 | -0.44027
| 3369 | 0.18336 | 0.11903 | -0.0022525 | -0.15614 | -0.24681 | -0.1204 | 0.060692 | 0.07183 | -0.0995 | 0.46493
| 3370 | 0.71208 | -0.15768 | 0.39692 | 0.43176 | -0.10608 | -0.033512 | 0.6755 | -0.26536 | 0.13832 | 0.46232
| 3371 | -0.095732 | 0.4683 | -0.27481 | -0.11835 | 0.4717 | -0.57257 | -0.50392 | -0.83357 | 0.044123 | -0.1261
| 3372 | -0.22715 | 0.46418 | 0.16856 | -0.057079 | 0.4206 | -0.24389 | 0.39098 | 0.35743 | 0.33149 | -0.55807
| 3373 | 0.21457 | -0.2625 | 0.15071 | -0.65287 | -0.40359 | -0.45861 | 0.30265 | -0.5721 | 0.47474 | -0.83907
| 3374 | -0.352 | -0.012832 | -0.28397 | -0.10507 | -0.36494 | 0.54316 | -0.093413 | -0.59024 | 0.42268 | 0.068067
| 3375 | -0.10206 | -0.41665 | -0.37831 | 0.34494 | 0.17314 | 0.33149 | 0.50251 | 0.56606 | 0.38657 | -0.5172
| 3376 | 0.070215 | 0.17471 | -0.094738 | 0.68425 | 0.65489 | -0.51184 | -0.15106 | -0.28775 | 0.33434 | -0.046533
| 3377 | 0.37 | -0.49039 | -0.35945 | -0.075825 | -0.14894 | 0.80687 | -0.1091 | -0.49137 | -0.12142 | -0.031961
| 3378 | -0.49572 | 0.16232 | -0.40763 | -0.5143 | 0.50271 | 0.27605 | -0.31014 | -0.41119 | -0.13104 | 0.20848
| 3379 | -0.1565 | 0.10039 | -0.32302 | -0.92063 | -0.18397 | 0.099167 | 0.52115 | -0.19074 | 0.18938 | 0.13936
| 3380 | -0.7512 | -0.25993 | -0.68903 | -0.16723 | -0.45787 | -0.59614 | 0.24363 | 0.6077 | -0.27165 | -0.52345
| 3381 | -0.15828 | -0.2674 | -0.39925 | -0.3454 | 0.0010506 | 0.16388 | 0.29254 | -0.42112 | -0.36149 | 0.45751
| 3382 | -0.84094 | -0.84284 | -0.57468 | 0.44385 | 0.31349 | 0.13936 | -0.094406 | 0.30928 | -0.69032 | 0.3242
| 3383 | -0.068388 | -0.34969 | 0.40108 | 0.4117 | 0.79727 | 0.048843 | -0.58012 | -0.4736 | -0.50573 | 0.43529
| 3384 | -0.56262 | 0.49771 | -0.82824 | -0.64097 | 0.28411 | 0.35789 | -0.34144 | -0.32465 | -0.72523 | 0.93755
| 3385 | -0.67091 | 0.12324 | -0.32806 | 0.25347 | -0.23495 | -0.0083852 | 0.3751 | -0.59417 | -0.17532 | -0.017198
| 3386 | 0.073016 | -0.95641 | -0.73 | 0.23508 | -0.1952 | -0.43281 | 0.32273 | 0.11124 | -0.0041586 | 0.10061
| 3387 | 0.036828 | -0.048948 | 0.33374 | 0.60694 | -0.45328 | 0.010303 | -0.40763 | 0.24442 | 0.47019 | 0.1292
| 3388 | 0.15377 | -0.13299 | -0.27605 | 0.41494 | 0.60339 | -0.23404 | 0.28944 | -0.36747 | -0.15436 | 0.24112
| 3389 | -0.11643 | -0.61154 | -0.25495 | 0.81372 | 0.34923 | -0.36196 | -0.23273 | -0.77131 | 0.066673 | 0.27522
| 3390 | -0.57186 | -0.071507 | 0.43813 | 0.82824 | 0.22922 | 0.17024 | 0.29339 | 0.44909 | 0.51782 | 0.5017
| 3391 | -0.22083 | -0.32569 | -0.5735 | -0.028661 | 0.19371 | 0.55 | 0.78483 | 0.063037 | 0.84284 | -0.15118
| 3392 | -0.42842 | 0.075716 | -0.08343 | -0.13971 | -0.36337 | 0.019949 | -0.64349 | -0.01344 | -0.2941 | -0.38771
| 3393 | 0.20609 | -0.50918 | 0.29113 | 0.66638 | 0.87 | 0.23078 | -0.085943 | 0.16113 | 0.3214 | 0.60974
| 3394 | -0.74603 | 0.17048 | 0.32806 | -0.84031 | -0.21139 | 0.60668 | -0.048633 | -0.95417 | 0.29254 | 0.5721
| 3395 | -0.080924 | 0.29169 | -0.56057 | -0.20207 | -0.3454 | -0.020357 | 0.31378 | 0.74446 | -0.093854 | 0.14134
| 3396 | -0.33645 | 0.32851 | 0.52387 | 0.23378 | 0.049158 | 0.38445 | -0.62384 | 0.28972 | 0.21393 | 0.44385
| 3397 | -0.16221 | -0.094406 | 0.15816 | -0.10563 | 0.82196 | 0.74643 | -0.3129 | 0.82593 | -0.41408 | -0.24376
| 3398 | -0.43848 | 0.099056 | -0.28593 | 0.11586 | 0.33902 | -0.15259 | 0.15071 | 0.42685 | -0.24933 | 0.14064
| 3399 | -0.44313 | -0.58036 | 0.42372 | 0.63299 | 0.2278 | 0.55694 | -0.097171 | -0.29268 | 0.13138 | -0.73637
| 3400 | -0.40645 | -0.25307 | -0.12954 | 0.8821 | 0.061331 | -0.27827 | -0.01415 | 0.0025533 | 0.58179 | 0.029279
| 3401 | -0.43724 | -0.4408 | 0.1884 | -0.4588 | 0.22225 | -0.77439 | 0.32391 | -0.62066 | -0.35696 | 0.14425
| 3402 | 0.26699 | -0.40359 | 0.14718 | 0.27619 | -0.25174 | 0.77796 | 0.12633 | 0.098945 | -0.31875 | 0.40108
| 3403 | 0.76913 | 0.09695 | -0.24046 | -0.48048 | -0.22909 | 0.4979 | 0.69129 | 0.58347 | 0.15236 | -0.33075
| 3404 | -0.41991 | -0.13484 | -0.32125 | 0.27578 | 0.16675 | -0.86847 | -0.49157 | 0.019235 | -0.54098 | 0.66849
| 3405 | 0.055066 | -0.22173 | 0.052741 | -0.20962 | -0.0067729 | -0.26468 | 0.042451 | 0.35945 | 0.27868 | 0.49177
| 3406 | -0.46362 | -0.81862 | -0.015978 | 0.36857 | -0.24667 | -0.31043 | 0.35247 | 0.012123 | -0.13983 | 0.25187
| 3407 | 0.15768 | -0.5017 | -0.33239 | -0.29353 | -0.248 | 0.60289 | -0.46158 | -0.58951 | 0.8937 | 0.64433
| 3408 | 0.29 | -0.5721 | -0.41665 | -0.68552 | -0.081577 | 0.1253 | -0.60643 | 0.081469 | -0.83059 | 0.57656
| 3409 | -0.18594 | -0.52979 | 0.60668 | -0.17872 | -0.43229 | -0.57397 | 0.48125 | 0.22637 | -0.097282 | -0.4293
| 3410 | 0.065709 | 0.47856 | 0.51041 | 0.015267 | 0.73751 | 0.20094 | -0.044751 | -0.47132 | 0.33284 | -0.09839
| 3411 | 0.28076 | 0.38461 | -0.79482 | 0.14285 | 0.25 | -0.66668 | 0.63517 | -0.13184 | 0.010404 | -0.5469
| 3412 | 0.14472 | -0.15744 | 0.059734 | 0.16352 | -0.67704 | -0.29325 | -0.12931 | 0.66578 | -0.12553 | 0.47436
| 3413 | -0.1852 | 0.0048618 | 0.3245 | -0.66758 | -0.21292 | 0.25562 | -0.095954 | 0.12199 | 0.0055655 | 0.20621
| 3414 | 0.34068 | -0.073987 | 0.36478 | 0.17241 | 0.15578 | 0.30855 | -0.36652 | 0.46868 | 0.8882 | 0.58419
| 3415 | -0.23521 | 0.61464 | -0.63081 | -0.50817 | 0.072045 | 0.29141 | -0.77977 | 0.37032 | 0.037347 | -0.40966
| 3416 | -0.23967 | -0.6637 | 0.36589 | -0.13196 | 0.37207 | 0.068711 | 0.30509 | 0.045694 | 0.46549 | 0.31363
| 3417 | -0.10888 | 0.011112 | -0.093854 | 0.76957 | 0.00095045 | 0.6338 | -0.37127 | -0.47189 | -0.043287 | 0.21699
| 3418 | -0.93443 | 0.12279 | 0.032581 | 0.39049 | -0.36937 | 0.0041586 | -0.70828 | -0.21572 | -0.4717 | 0.21152
| 3419 | 0.58251 | 0.73827 | 0.050105 | -0.11202 | -0.093082 | -0.076366 | 0.52282 | 0.58203 | -0.20962 | -0.30595
| 3420 | 0.63271 | 0.40276 | 0.74603 | -0.74174 | 0.35899 | -0.63299 | 0.030722 | -0.27206 | -0.65809 | -0.01182
| 3421 | 0.31334 | 0.23091 | 0.032994 | -0.44982 | 0.056655 | -0.50472 | -0.16988 | -0.043182 | -0.22212 | -0.048527
| 3422 | 0.081686 | 0.70623 | 0.16892 | -0.7504 | -0.33675 | 0.10507 | 0.34862 | 0.12267 | 0.65868 | -0.0046609
| 3423 | -0.27123 | -0.069033 | -0.18397 | 0.09706 | 0.55537 | -0.2225 | -0.0055655 | -0.28944 | -0.092751 | 0.31816
| 3424 | 0.078859 | 0.252 | -0.46737 | -0.10395 | -0.11972 | 0.18165 | -0.19124 | -0.24389 | -0.21228 | -0.38853
| 3425 | 0.16507 | 0.72815 | 0.97354 | 0.066565 | -0.45273 | 0.095843 | 0.34739 | -0.0040582 | 0.45109 | -0.30107
| 3426 | -0.29936 | -0.34433 | 0.79925 | -0.27206 | 0.18483 | -0.21738 | -0.013035 | 0.36826 | 0.16651 | 0.41665
| 3427 | 0.55898 | 0.017605 | 0.44511 | -0.26454 | -0.14461 | -0.79143 | -0.031135 | -0.53 | 0.36149 | 0.24297
| 3428 | 0.46269 | -0.40443 | 0.077341 | 0.096064 | -0.21699 | 0.38283 | -0.12085 | -0.23378 | 0.62731 | -0.18988
| 3429 | -0.073016 | -0.6578 | -0.24469 | 0.49532 | 0.4979 | 0.09198 | -0.35231 | 0.20583 | 0.54229 | -0.19297
| 3430 | 0.19334 | 0.15661 | -0.74019 | -0.2496 | 0.10686 | 0.073339 | 0.10128 | 0.098612 | -0.50878 | 0.38478
| 3431 | 0.61464 | -0.34418 | 0.49059 | 0.37286 | 0.7245 | -0.64237 | 0.64461 | -0.15994 | -0.47208 | 0.67829
| 3432 | 0.2602 | 0.68647 | -0.22909 | 0.34678 | -0.50695 | 0.59491 | 0.16221 | -0.42668 | -0.50472 | -0.32747
| 3433 | -0.42199 | 0.3245 | -0.41957 | -0.50271 | -0.32598 | -0.039219 | 0.51823 | 0.56239 | 0.51328 | -0.024244
| 3434 | -0.44583 | 0.15094 | 0.39892 | -0.37016 | 0.25294 | 0.75772 | 0.17024 | 0.68583 | 0.027015 | 0.69
| 3435 | 0.57444 | 0.42441 | -0.57941 | 0.10139 | -0.063891 | 0.33645 | 0.51782 | 0.26237 | 0.28761 | 0.44242
| 3436 | -0.22366 | -0.10496 | 0.31904 | 0.12725 | -0.23364 | 0.78023 | -0.15756 | -0.3743 | 0.48357 | 0.0057666
| 3437 | -0.24204 | -0.53385 | 0.15887 | 0.44746 | 0.6833 | -0.3214 | -0.16113 | -0.22212 | 0.67581 | 0.55649
| 3438 | 0.26468 | 0.11146 | -0.0082843 | 0.21343 | 0.14437 | -0.34617 | 0.50817 | -0.24508 | -0.27343 | 0.1729
| 3439 | 0.67335 | 0.59888 | 0.61882 | 0.12541 | -0.28551 | -0.2488 | -0.48609 | 0.3214 | -0.25254 | 0.42685
| 3440 | -0.09143 | 0.44529 | 0.15697 | 0.012225 | 0.27702 | -0.24867 | 0.28663 | -0.82252 | -0.29169 | 0.13762
| 3441 | -0.2476 | 0.049684 | 0.14215 | 0.65956 | -0.71487 | -0.63408 | 0.59888 | 0.23299 | 0.094185 | 0.29594
| 3442 | -0.013947 | -0.28411 | 0.56606 | 0.71592 | -0.20874 | -0.41974 | -0.1688 | -0.12851 | 0.55739 | -0.19148
| 3443 | -0.0021523 | -0.33947 | -0.087914 | 0.089341 | 0.46028 | 0.19782 | 0.29452 | 0.0051633 | 0.078751 | 0.64265
| 3444 | -0.57327 | -0.19012 | -0.72018 | -0.21051 | 0.62919 | -0.044647 | -0.55898 | 0.84284 | 0.12977 | 0.552
| 3445 | 0.4985 | -0.1034 | -0.75201 | 0.37446 | -0.075176 | -0.20646 | -0.16376 | -0.1229 | -0.95641 | -0.020051
| 3446 | -0.20332 | -0.70931 | 0.15283 | 0.17157 | -0.59788 | 0.3309 | 0.8755 | -0.0075787 | -0.10217 | -0.23508
| 3447 | -0.34877 | 0.27481 | 0.46718 | 0.20975 | -0.2567 | 0.3735 | -0.063144 | -0.80328 | 0.68172 | 0.64886
| 3448 | 0.64659 | -0.34099 | 0.087695 | 0.52429 | -0.14648 | 0.49453 | 0.41888 | -0.2427 | 0.17253 | 0.61077
| 3449 | 0.68871 | -0.41528 | 0.37175 | -0.37239 | -0.35278 | -0.19173 | 0.049474 | 0.078642 | 0.11949 | 0.25737
| 3450 | 0.27965 | 0.057716 | -0.2907 | -0.23325 | 0.28495 | -0.23378 | 0.61516 | -0.033925 | 0.16066 | 0.053058
| 3451 | -0.077341 | 0.164 | -0.44439 | 0.30093 | -0.11609 | -0.15958 | -0.46009 | -0.68267 | -0.34342 | -0.89276
| 3452 | 0.066673 | 0.72596 | 0.16221 | -0.11938 | -0.072369 | -0.42216 | 0.075825 | 0.52471 | 0.15816 | 0.24336
| 3453 | -0.60088 | -0.042347 | -0.052635 | 0.050526 | -0.28341 | 0.70251 | -0.22006 | -0.34038 | 0.18092 | -0.87233
| 3454 | -0.023834 | 0.14145 | 0.2326 | -0.67704 | -0.28789 | 0.046113 | 0.16197 | -0.69194 | 0.26007 | -0.92063
| 3455 | 0.41272 | -0.0033556 | 0.31407 | 0.052741 | 0.34357 | -0.52745 | -0.36321 | -0.21942 | 0.08234 | 0.036205
| 3456 | -0.6811 | 0.81588 | -0.38105 | -0.13959 | -0.41991 | 0.60339 | 0.15863 | 0.079946 | -0.047267 | -0.1863
| 3457 | -0.40898 | -0.14566 | 0.84284 | -0.71347 | 0.16687 | 0.38738 | 0.78344 | 0.011719 | -0.67984 | 0.25723
| 3458 | -0.31919 | -0.44746 | 0.46962 | -0.46251 | -0.24947 | -0.056655 | 0.67798 | -0.46512 | -0.076907 | -0.45695
| 3459 | 0.30682 | 0.017503 | -0.79975 | -0.44098 | 0.10798 | -0.030206 | 0.39942 | 0.26904 | -0.6257 | 0.10507
| 3460 | 0.17084 | -0.077449 | 0.18348 | -0.037347 | -0.14624 | 0.058565 | 0.66698 | -0.42009 | -0.67612 | -0.83969
| 3461 | 0.34235 | -0.80895 | 0.13774 | -0.088024 | -0.69455 | -0.72233 | 0.84031 | 0.45 | 0.29381 | -0.42895
| 3462 | 0.043914 | -0.33015 | 0.55 | 0.13276 | 0.19471 | -0.50553 | -0.1044 | 0.33932 | -0.47493 | 0.1315
| 3463 | -0.37702 | -0.81159 | 0.049263 | 0.025988 | -0.062503 | -0.25899 | 0.25589 | -0.32155 | 0.38984 | -0.46587
| 3464 | 0.57609 | 0.2621 | -0.30365 | -0.38967 | -0.044437 | 0.12897 | -0.093523 | 0.14882 | 0.021379 | -0.26427
| 3465 | -0.85337 | 0.4991 | 0.39296 | 0.88295 | -0.42476 | 0.56884 | -0.21317 | 0.033201 | -0.56537 | -0.3048
| 3466 | 0.17909 | -0.01 | -0.12759 | -0.0017515 | -0.27509 | 0.5172 | -0.019337 | -0.67953 | 0.37815 | 0.44098
| 3467 | 0.37478 | -0.39329 | -0.29 | -0.26795 | -0.045275 | 0.24349 | -0.22083 | -0.2733 | 0.29169 | 0.41785
| 3468 | -0.43158 | -0.31174 | 0.096839 | -0.17 | -0.19297 | -0.033305 | -0.047792 | -0.58347 | -0.59466 | 0.29
| 3469 | -0.10686 | 0.78251 | 0.56583 | -0.61412 | 0.80025 | -0.056443 | -0.16904 | -0.23404 | 0.32391 | 0.17957
| 3470 | -0.11326 | 0.57538 | 0.68775 | 0.048107 | -0.28397 | 0.20169 | 0.1044 | -0.89276 | -0.64377 | 0.13832
| 3471 | 0.26169 | 0.51554 | -0.38853 | 0.82766 | -0.031754 | -0.32791 | -0.41648 | -0.10072 | -0.31349 | -0.084194
| 3472 | 0.031238 | 0.0013509 | 0.40729 | -0.12336 | 0.00035006 | -0.047792 | -0.68968 | 0.042451 | -0.098501 | -0.37016
| 3473 | 0.29551 | -0.35479 | 0.26836 | -0.020868 | 0.17556 | -0.63792 | 0.37111 | 0.40242 | -0.44331 | -0.70966
| 3474 | -0.087038 | 0.34159 | 0.51348 | 0.010101 | -0.3211 | -0.1221 | -0.44837 | -0.00095045 | -0.46139 | -0.11451
| 3475 | 0.32881 | 0.098834 | -0.048948 | -0.55582 | 0.29339 | 0.77306 | -0.57257 | 0.2809 | 0.26822 | 0.12051
| 3476 | 0.056761 | -0.30855 | 0.50614 | 0.088134 | -0.86696 | -0.1432 | 0.60719 | -0.57774 | -0.71104 | 0.098058
| 3477 | 0.10239 | 0.77395 | -0.73298 | 0.25093 | 0.15413 | -0.01547 | -0.019133 | 0.19944 | -0.19931 | 0.3882
| 3478 | 0.00015001 | -0.54756 | 0.14379 | -0.20144 | 0.034236 | 0.11926 | -0.41017 | 0.43742 | -0.39759 | 0.32273
| 3479 | -0.50695 | 0.34601 | -0.43193 | -0.38186 | -0.38008 | -0.080924 | 0.51534 | -0.032167 | -0.056549 | -0.77617
| 3480 | -0.058884 | -0.51865 | 0.19844 | 0.1292 | 0.23482 | -0.15484 | -0.29183 | -0.39643 | 0.35945 | -0.38251
| 3481 | -0.40494 | -0.1292 | 0.039011 | 0.3363 | -0.61961 | -0.45347 | 0.051264 | -0.011921 | 0.42668 | -0.37734
| 3482 | -0.097282 | 0.024962 | 0.15106 | 0.079946 | 0.28663 | -0.10473 | -0.43511 | 0.59988 | 0.1814 | -0.12576
| 3483 | -0.011415 | 0.24987 | 0.21597 | 0.22663 | -0.30682 | 0.15212 | 0.5436 | -0.36968 | -0.9219 | 0.80947
| 3484 | 0.013947 | 0.16771 | 0.52745 | -0.08343 | -0.20785 | -0.15721 | 0.32539 | 0.21802 | 0.24231 | -0.34266
| 3485 | -0.5959 | -0.15911 | 0.052424 | 0.82536 | -0.062397 | 0.034754 | -0.44098 | -0.67829 | -0.32125 | -0.35852
| 3486 | -0.36573 | -0.31934 | -0.14906 | -0.10485 | -0.49572 | 0.21572 | 0.15768 | 0.15 | 0.013744 | -0.7076
| 3487 | -0.15153 | -0.021481 | -0.25791 | 0.61361 | 0.64125 | -0.26945 | -0.42164 | -0.39726 | 0.48863 | -0.40881
| 3488 | 0.47722 | -0.27261 | 0.072692 | -0.20056 | -0.39049 | -0.23299 | 0.75772 | -0.86325 | 0.59441 | 0.54011
| 3489 | -0.50291 | 0.37334 | 0.51472 | -0.021379 | 0.030103 | 0.11507 | -0.0069743 | 0.47151 | 0.24734 | -0.067959
| 3490 | 0.69619 | 0.21317 | -0.2484 | -0.24575 | 0.15839 | 0.23521 | 0.16496 | -0.02189 | -0.40427 | 0.22948
| 3491 | 0.65518 | -0.39593 | -0.1646 | -0.30523 | -0.052635 | -0.38706 | -0.45237 | 0.26088 | -0.14239 | 0.15059
| 3492 | 0.087695 | -0.19148 | -0.45146 | 0.29339 | -0.095622 | 0.14122 | 0.050737 | -0.22148 | 0.42009 | 0.63299
| 3493 | 0.27412 | -0.084522 | -0.11983 | -0.060053 | 0.30942 | -0.47189 | 0.81426 | 0.42216 | -0.28174 | -0.28845
| 3494 | -0.2809 | -0.49216 | -0.080054 | 0.16424 | -0.094959 | -0.077449 | 0.42268 | -0.16089 | 0.64209 | 0.0032553
| 3495 | 0.085068 | -0.032064 | 0.72523 | 0.25133 | -0.69129 | -0.076258 | 0.2343 | -0.82365 | 0.46587 | -0.31934
| 3496 | -0.80895 | -0.12966 | -0.15082 | -0.38413 | -0.82479 | 0.26345 | -0.53578 | -0.14309 | -0.0025533 | -0.27771
| 3497 | -0.74525 | 0.2893 | 0.044333 | 0.23299 | -0.53643 | -0.4392 | 0.53107 | -0.81159 | -0.41854 | -0.74058
| 3498 | -0.20395 | -0.95417 | -0.54142 | -0.30164 | 0.5663 | -0.25939 | 0.38934 | 0.72742 | -0.49473 | -0.021072
| 3499 | 0.23482 | -0.61103 | 0.073339 | 0.70862 | 0.070645 | 0.066994 | 0.33585 | 0.55022 | -0.05422 | -0.7569
| 3500 | 0.0037571 | -0.4987 | 0.64125 | 0.19124 | -0.5019 | -0.37815 | -0.63163 | 0.33015 | -0.63517 | 0.13519
| 3501 | -0.59245 | 0.40125 | -0.41323 | 0.86696 | -0.40696 | 0.16292 | 0.03434 | 0.65985 | -0.089561 | -0.23534
| 3502 | 0.54602 | -0.31 | -0.21241 | -0.24336 | -0.009596 | 0.32199 | -0.54712 | -0.096064 | -0.37574 | 0.87712
| 3503 | 0.2265 | 0.13553 | -0.19719 | 0.041407 | -0.79095 | -0.52809 | 0.0089904 | 0.34954 | -0.21177 | -0.67735
| 3504 | -0.32317 | -0.21457 | 0.57562 | 0.53967 | 0.61051 | -0.3743 | 0.2924 | 0.31014 | -0.4997 | 0.14906
| 3505 | 0.12908 | -0.14367 | -0.58203 | 0.32747 | 0.10395 | -0.24774 | 0.84867 | 0.30495 | -0.055807 | -0.44457
| 3506 | 0.096507 | -0.53946 | -0.16185 | 0.013136 | 0.45935 | -0.12404 | -0.22135 | 0.48222 | 0.54646 | -0.37143
| 3507 | -0.2042 | 0.42147 | 0.2567 | -0.24086 | 0.51041 | -0.22547 | -0.13138 | -0.40477 | -0.17338 | -0.63353
| 3508 | 0.42129 | -0.44295 | -0.26237 | 0.027837 | 0.25508 | 0.37847 | 0.44349 | -0.73904 | 0.17836 | 0.54889
| 3509 | 0.33555 | -0.24059 | 0.030412 | -0.27522 | 0.050526 | 0.55178 | -0.77044 | -0.17096 | 0.12667 | 0.10776
| 3510 | 0.15177 | 0.42755 | -0.85067 | -0.19632 | 0.77175 | 0.27674 | -0.49651 | -0.35108 | 0.39148 | 0.27206
| 3511 | -0.29523 | -0.56285 | -0.52534 | -0.14566 | 0.57397 | -0.73 | 0.025269 | 0.85269 | -0.69553 | -0.13104
| 3512 | -0.29254 | -0.69553 | -0.50614 | -0.0086877 | 0.27357 | -0.15804 | -0.36039 | 0.61309 | -0.16101 | 0.19757
| 3513 | -0.1389 | -0.60795 | 0.1044 | 0.56125 | -0.24191 | -0.34708 | 0.40611 | 0.20924 | 0.28243 | 0.58976
| 3514 | 0.033925 | 0.77796 | -0.5013 | -0.35805 | 0.24033 | -0.038179 | 0.19124 | 0.13299 | 0.18067 | -0.44945
| 3515 | 0.68298 | -0.11259 | -0.4902 | -0.2567 | 0.74329 | -0.55604 | -0.28271 | -0.58251 | 0.60314 | 0.20407
| 3516 | -0.099944 | 0.28845 | -0.14765 | 0.85337 | 0.28565 | -0.35231 | 0.7881 | -0.38478 | 0.44746 | -0.094738
| 3517 | 0.073555 | -0.14788 | 0.45073 | 0.051159 | 0.22276 | -0.16916 | -0.022708 | -0.14566 | 0.46121 | -0.29085
| 3518 | -0.15035 | 0.069248 | -0.11643 | 0.10686 | 0.79191 | 0.70657 | 0.0173 | 0.43653 | -0.089231 | 0.024039
| 3519 | 0.77175 | 0.46605 | 0.024039 | -0.073231 | 0.23221 | -0.055066 | -0.095069 | 0.41102 | 0.057503 | 0.51678
| 3520 | 0.82824 | 0.69884 | 0.14953 | 0.21712 | -0.58587 | -0.051791 | -0.45585 | 0.73981 | 0.90673 | -0.38315
| 3521 | -0.46868 | 0.37895 | 0.4668 | 0.21482 | 0.26427 | -0.82883 | 0.33284 | 0.91574 | 0.20848 | 0.33464
| 3522 | -0.68361 | 0.17157 | -0.28551 | -0.73751 | 0.60138 | 0.73074 | -0.49592 | 0.32791 | 0.8148 | -0.20558
| 3523 | 0.039427 | -0.080598 | 0.2958 | 0.27495 | -0.19309 | -0.32228 | -0.05496 | 0.019541 | 0.084085 | 0.40343
| 3524 | -0.14309 | 0.17181 | -0.15047 | -0.40008 | 0.21853 | -0.6265 | -0.64265 | -0.61412 | -0.14227 | 0.23875
| 3525 | 0.11699 | -0.30021 | -0.40042 | -0.071076 | -0.11383 | 0.093082 | -0.067745 | 0.086162 | -0.45622 | 0.027632
| 3526 | 0.10832 | -0.40527 | -0.04381 | 0.80947 | -0.3422 | 0.056549 | 0.13265 | 0.074959 | -0.16651 | -0.35525
| 3527 | 0.11813 | 0.98268 | 0.12085 | -0.2484 | -0.64181 | 0.5583 | 0.10764 | 0.51246 | -0.12851 | 0.2784
| 3528 | 0.28049 | -0.46195 | -0.6703 | -0.20307 | -0.78068 | -0.59963 | -0.059415 | -0.26509 | -0.63271 | 0.4736
| 3529 | 0.021481 | -0.11225 | 0.15638 | -0.40142 | -0.23731 | 0.01 | -0.06753 | -0.57444 | 0.20823 | 0.43759
| 3530 | -0.48338 | 0.052213 | 0.48882 | -0.49374 | -0.7687 | -0.14239 | 0.77262 | 0.62277 | -0.25872 | 0.056867
| 3531 | 0.20357 | 0.68615 | 0.37239 | 0.98268 | -0.17617 | 0.49731 | -0.27192 | 0.32613 | -0.35169 | 0.43264
| 3532 | -0.4668 | 0.23325 | -0.29665 | -0.57869 | -0.087586 | 0.30107 | -0.65518 | -0.020663 | -0.35015 | 0.44045
| 3533 | 0.3796 | 0.54514 | -0.55717 | -0.52513 | -0.38722 | -0.42528 | -0.1634 | 0.084631 | 0.022503 | -0.38984
| 3534 | 0.36337 | 0.44367 | 0.48843 | -0.12108 | 0.75731 | -0.63848 | 0.29708 | 0.62758 | -0.24495 | -0.14894
| 3535 | -0.31203 | -0.13646 | 0.24641 | 0.17012 | 0.56468 | 0.11394 | 0.075284 | 0.09099 | -0.61128 | -0.57397
| 3536 | -0.25468 | -0.23482 | -0.52979 | -0.19719 | -0.10865 | -0.052952 | -0.02722 | -0.42842 | -0.14566 | 0.61568
| 3537 | 0.064532 | -0.25455 | 0.056867 | 0.4471 | -0.40932 | 0.047897 | -0.082776 | 0.087038 | -0.10933 | -0.71277
| 3538 | -0.47914 | 0.12908 | 0.22961 | -0.12063 | 0.50878 | -0.088792 | -0.098612 | 0.23757 | 0.071507 | 0.13669
| 3539 | 0.22741 | 0.30495 | 0.53686 | 0.19869 | 0.25912 | -0.22896 | 0.18299 | 0.38722 | -0.55921 | 0.059521
| 3540 | -0.48765 | -0.28677 | 0.12793 | 0.29042 | -0.18043 | 0.41905 | 0.58467 | -0.39676 | 0.50898 | 0.20911
| 3541 | -0.012326 | -0.66698 | 0.41957 | -0.51699 | 0.32214 | 0.043914 | -0.081469 | -0.29466 | -0.17544 | -0.3951
| 3542 | 0.35883 | 0.34908 | 0.3061 | -0.43635 | 0.57093 | 0.33209 | 0.081251 | 0.0093941 | -0.34662 | 0.18606
| 3543 | 0.49256 | -0.36715 | -0.19994 | 0.42825 | 0.29127 | 0.1926 | 0.29807 | 0.59171 | -0.62251 | 0.18594
| 3544 | -0.53707 | -0.80532 | -0.029382 | -0.19099 | -0.21457 | 0.13115 | 0.38787 | 0.26101 | 0.031341 | -0.7687
| 3545 | 0.72815 | -0.63599 | 0.10921 | -0.82883 | -0.17945 | 0.52492 | 0.057079 | 0.19794 | -0.29736 | -0.21292
| 3546 | -0.30423 | 0.17 | -0.38332 | 0.78068 | -0.18741 | 0.19173 | 0.79579 | -0.16735 | -0.16856 | 0.16484
| 3547 | -0.27343 | 0.32569 | 0.57116 | -0.14812 | 0.20407 | 0.12154 | -0.02897 | -0.40696 | 0.095843 | 0.56148
| 3548 | -0.83969 | -0.97764 | 0.56148 | 0.081577 | -0.080924 | -0.22199 | 0.095622 | -0.083649 | -0.19012 | -0.80532
| 3549 | -0.068818 | -0.3148 | 0.25468 | 0.41596 | -0.021174 | 0.81807 | -0.40595 | -0.14379 | -0.12564 | 0.37944
| 3550 | 0.48106 | -0.12302 | 0.31058 | -0.37223 | -0.45237 | 0.33404 | 0.15638 | -0.34008 | 0.040886 | 0.46083
| 3551 | 0.4293 | 0.12667 | 0.75201 | 0.093082 | -0.15354 | 0.64153 | 0.39875 | -0.37718 | 0.23823 | -0.41323
| 3552 | 0.35324 | 0.079837 | 0.66281 | 0.15389 | -0.14087 | -0.20407 | -0.61464 | -0.054643 | 0.10708 | -0.48106
| 3553 | 0.36274 | -0.50817 | -0.11835 | -0.11598 | -0.18667 | 0.23836 | 0.50452 | -0.39692 | 0.038595 | 0.15839
| 3554 | -0.24681 | 0.086162 | -0.21738 | 0.1439 | 0.68679 | 0.16364 | 0.44493 | 0.41238 | -0.05 | -0.088902
| 3555 | 0.014049 | 0.13832 | 0.078317 | 0.83 | -0.025372 | 0.30322 | 0.44583 | 0.13924 | 0.68807 | -0.15851
| 3556 | -0.46737 | 0.57585 | 0.70862 | -0.19994 | -0.38332 | 0.57893 | 0.58708 | 0.68552 | 0.1735 | 0.16316
| 3557 | 0.42685 | 0.25321 | 0.047687 | -0.23652 | 0.20785 | 0.51266 | -0.22767 | 0.20319 | 0.1353 | -0.84605
| 3558 | 0.26658 | 0.33977 | -0.093744 | 0.81053 | 0.14309 | 0.074959 | -0.68141 | 0.78622 | 0.080598 | 0.14332
| 3559 | 0.055384 | -0.29169 | -0.2287 | 0.15035 | 0.22173 | -0.87233 | -0.58083 | -0.015571 | -0.40763 | -0.16759
| 3560 | -0.089561 | -0.68679 | -0.72378 | 0.25885 | -0.39181 | 0.11779 | 0.083758 | -0.076474 | -0.29395 | -0.70251
| 3561 | 0.23901 | -0.29566 | 0.51657 | 0.4392 | 0.066994 | -0.049158 | 0.10664 | -0.1277 | -0.79628 | -0.30653
| 3562 | 0.10854 | 0.62758 | 0.15673 | -0.3735 | 0.058777 | 0.69422 | 0.68172 | 0.13426 | -0.33781 | -0.16472
| 3563 | -0.0093941 | 0.0073772 | -0.81534 | -0.93597 | -0.08989 | -0.20697 | 0.66133 | -0.51782 | -0.20294 | -0.17665
| 3564 | 0.44457 | 0.11304 | -0.24601 | 0.68743 | 0.66429 | 0.39345 | 0.078859 | -0.41187 | -0.06496 | -0.80328
| 3565 | -0.12966 | 0.055278 | -0.30538 | -0.14262 | -0.46213 | 0.31787 | 0.25174 | 0.2575 | 0.6118 | -0.24747
| 3566 | -0.016181 | 0.087147 | 0.12382 | -0.75938 | -0.0010506 | 0.17714 | 0.12966 | -0.069248 | -0.65693 | 0.21661
| 3567 | 0.14262 | -0.0029544 | 0.65287 | 0.21114 | -0.52788 | 0.76146 | -0.36794 | 0.85752 | 0.066994 | -0.035998
| 3568 | 0.040677 | 0.25872 | 0.67 | -0.20735 | 0.34068 | -0.13611 | 0.099056 | -0.2711 | -0.22135 | 0.36557
| 3569 | -0.063891 | 0.24125 | -0.2744 | -0.37815 | -0.41306 | -0.50371 | -0.3727 | -0.13658 | -0.51143 | -0.42511
| 3570 | 0.26522 | 0.31247 | 0.82422 | -0.77044 | 0.2184 | -0.010404 | 0.25818 | -0.24681 | -0.032477 | 0.01263
| 3571 | -0.15236 | -0.23744 | 0.024756 | -0.58179 | 0.19769 | 0.32022 | -0.067852 | -0.09033 | 0.83417 | 0.055701
| 3572 | 0.019031 | 0.014049 | 0.59813 | -0.060372 | 0.052319 | 0.54185 | -0.0050628 | -0.15519 | 0.2791 | 0.16663
| 3573 | -0.48707 | -0.81053 | 0.37815 | 0.24125 | 0.042869 | 0.65722 | -0.47798 | 0.73675 | 0.7488 | -0.6578
| 3574 | -0.5021 | -0.65143 | 0.13681 | -0.22392 | 0.18569 | 0.031651 | 0.067959 | -0.10753 | -0.85201 | 0.44982
| 3575 | 0.044123 | -0.6257 | 0.25067 | -0.12279 | 0.50412 | -0.54933 | -0.4736 | 0.13311 | 0.26237 | -0.27426
| 3576 | -0.36133 | 0.44385 | -0.67304 | -0.0088895 | 0.42112 | 0.73373 | 0.00095045 | 0.2193 | -0.28132 | -0.5224
| 3577 | -0.075068 | -0.041094 | -0.051264 | -0.10273 | 0.72414 | -0.21127 | 0.43 | -0.039531 | -0.35945 | 0.53556
| 3578 | 0.43317 | 0.015267 | -0.24933 | 0.13681 | 0.018623 | 0.0004501 | -0.35216 | 0.060692 | 0.024449 | 0.11281
| 3579 | 0.021379 | 0.19223 | 0.20785 | 0.22948 | 0.29665 | -0.3537 | 0.33615 | -0.12233 | 0.33299 | 0.078425
| 3580 | -0.074959 | 0.69652 | -0.21508 | 0.0048618 | 0.36415 | 0.27302 | -0.011314 | -0.042555 | -0.073124 | 0.025782
| 3581 | 0.12702 | -0.042973 | 0.28118 | -0.82365 | 0.011011 | -0.72089 | 0.28271 | -0.10083 | 0.10328 | -0.068067
| 3582 | 0.52915 | 0.087257 | -0.48765 | -0.38461 | 0.078642 | -0.27069 | 0.64857 | 0.093634 | 0.52094 | -0.37718
| 3583 | 0.21572 | 0.093303 | -0.11722 | 0.0035563 | -0.64772 | 0.16735 | 0.034029 | 0.66162 | -0.13196 | -0.14309
| 3584 | -0.18214 | -0.19595 | 0.81265 | -0.43476 | 0.56583 | 0.049579 | -0.20044 | -0.1162 | 0.34023 | 0.17994
| 3585 | -0.69422 | -0.13392 | 0.060266 | 0.027529 | -0.36478 | -0.0086877 | -0.60898 | -0.49691 | 0.0038574 | 0.19062
| 3586 | 0.19483 | 0.75566 | 0.64377 | 0.028764 | 0.3309 | -0.19794 | -0.13276 | 0.22754 | -0.29665 | -0.067745
| 3587 | 0.025167 | -0.66879 | 0.2598 | 0.040886 | -0.2773 | -0.30007 | 0.41751 | -0.65605 | -0.011314 | 0.096507
| 3588 | 0.1634 | 0.56445 | 0.48961 | 0.30682 | -0.11631 | -0.48785 | 0.27702 | 0.14355 | 0.39246 | 0.49275
| 3589 | -0.53064 | 0.86546 | -0.12051 | -0.13704 | -0.04099 | -0.45328 | -0.034236 | -0.31232 | -0.094185 | -0.48376
| 3590 | -0.03434 | 0.077883 | 0.83969 | -0.38885 | 0.27398 | 0.4898 | -0.43795 | -0.38722 | -0.64461 | -0.17532
| 3591 | 0.54823 | -0.21495 | 0.067316 | 0.10295 | 0.15685 | 0.13634 | -0.2567 | 0.67581 | -0.35665 | -0.58733
| 3592 | -0.20785 | -0.29127 | 0.55649 | 0.44674 | 0.58515 | -0.50392 | 0.10485 | 0.55178 | -0.28649 | -0.15661
| 3593 | 0.20987 | -0.013643 | -0.44313 | 0.43582 | -0.18177 | 0.23299 | -0.38918 | 0.066673 | -0.021379 | 0.67458
| 3594 | -0.59963 | 0.18312 | -0.30322 | 0.29736 | 0.20558 | 0.039323 | 0.15295 | 0.11056 | 0.1034 | -0.035168
| 3595 | -0.037036 | 0.73261 | 0.11552 | 0.30408 | 0.23809 | -0.034133 | -0.12359 | 0.19025 | -0.91225 | 0.05348
| 3596 | -0.3116 | -0.0075787 | 0.69 | -0.053797 | -0.35185 | -0.012123 | 0.73751 | -0.29028 | 0.26427 | 0.37016
| 3597 | -0.055066 | -0.29651 | -0.16149 | 0.1091 | 0.3568 | 0.21546 | -0.28733 | 0.063571 | -0.22405 | -0.25321
| 3598 | -0.41613 | -0.63027 | -0.13565 | -0.037763 | 0.24217 | -0.27633 | 0.2504 | -0.69324 | -0.41442 | -0.33947
| 3599 | -0.04517 | -0.19881 | 0.23757 | 0.38089 | -0.44331 | 0.10832 | 0.3132 | 0.95204 | 0.10574 | -0.38283
| 3600 | 0.13069 | 0.14262 | 0.37398 | 0.045799 | 0.23678 | -0.84736 | -0.34969 | 0.10753 | 0.23156 | -0.086271
| 3601 | 0.36747 | -0.82766 | -0.31276 | -0.13496 | 0.34266 | 0.71069 | -0.17787 | 0.53 | 0.78858 | 0.72963
| 3602 | -0.12097 | 0.14192 | -0.22032 | 0.39345 | 0.73486 | 0.84284 | 0.3838 | 0.12473 | -0.73827 | 0.29452
| 3603 | 0.43493 | 0.61908 | 0.59515 | 0.54273 | -0.19931 | -0.30725 | -0.1292 | 0.39692 | -0.36227 | -0.264
| 3604 | 0.42965 | 0.35867 | -0.20382 | 0.010606 | 0.0072765 | 0.11135 | -0.09187 | 0.51657 | -0.10362 | 0.1034
| 3605 | -0.16916 | -0.050842 | 0.23247 | -0.19856 | 0.73223 | 0.056019 | -0.06229 | 0.31758 | -0.48629 | 0.40192
| 3606 | 0.21482 | 0.86621 | 0.42737 | -0.48961 | 0.42147 | -0.11281 | -0.12828 | 0.13936 | -0.29566 | -0.24217
| 3607 | -0.30812 | 0.18201 | 0.10496 | 0.4717 | -0.2398 | 0.18753 | 0.74841 | 0.28063 | -0.2427 | 0.4979
| 3608 | 0.67366 | 0.12439 | 0.57585 | 0.30754 | -0.010707 | 0.076366 | 0.71069 | 0.73074 | -0.0051633 | 0.084522
| 3609 | 0.11631 | -0.64461 | -0.40679 | 0.057291 | 0.13403 | -0.017707 | -0.31993 | 0.10451 | -0.73675 | 0.006169
| 3610 | 0.71875 | -0.3618 | -0.081686 | -0.3956 | -0.089231 | 0.55762 | 0.33194 | -0.11847 | -0.26522 | -0.54426
| 3611 | -0.29183 | -0.2958 | 0.26808 | -0.59466 | 0.037555 | -0.73448 | -0.73904 | -0.24734 | 0.2809 | 0.083867
| 3612 | -0.0026535 | -0.17896 | 0.50291 | -0.87077 | 0.95417 | -0.2516 | -0.30408 | -0.025885 | 0.048843 | -0.4542
| 3613 | -0.082885 | 0.20282 | -0.032581 | -0.79875 | -0.061437 | -0.39925 | -0.42633 | -0.0038574 | 0.21114 | 0.32184
| 3614 | 0.7687 | -0.78114 | 0.26305 | 0.76741 | -0.039011 | 0.71104 | -0.10776 | -0.60567 | -0.34678 | 0.70931
| 3615 | -0.1769 | -0.47436 | 0.29183 | -0.067101 | 0.63 | -0.023424 | 0.047582 | -0.15236 | -0.01486 | -0.38722
| 3616 | -0.79048 | 0.27896 | -0.34403 | -0.28537 | -0.0054649 | 0.35015 | 0.071938 | -0.50513 | 0.28341 | 0.16507
| 3617 | 0.1603 | -0.50392 | -0.78206 | -0.2398 | 0.021072 | -0.11428 | -0.26088 | 0.02722 | -0.22715 | 0.13623
| 3618 | -0.5707 | 0.43387 | 0.69324 | -0.74564 | 0.041199 | -0.43476 | -0.022094 | 0.27137 | -0.47645 | 0.17265
| 3619 | 0.69586 | -0.034029 | 0.53449 | 0.40058 | -0.1425 | -0.26495 | -0.67735 | 0.35154 | 0.022094 | -0.24072
| 3620 | 0.37526 | -0.07962 | -0.054008 | 0.83417 | -0.36353 | 0.46793 | 0.15721 | -0.32539 | -0.03 | 0.76272
| 3621 | -0.12119 | 0.074419 | -0.4999 | -0.1926 | 0.29509 | -0.62039 | -0.64772 | 0.29993 | -0.39626 | 0.85964
| 3622 | -0.61829 | 0.34144 | -0.64687 | 0.51266 | 0.076582 | -0.8366 | 0.47341 | 0.1694 | -0.55537 | -0.31436
| 3623 | 0.082122 | -0.45991 | -0.42078 | 0.38056 | 0.06753 | 0.057291 | 0.13762 | 0.056337 | -0.070753 | -0.19
| 3624 | 0.20949 | -0.37366 | -0.020663 | 0.56445 | 0.16209 | -0.45036 | -0.52345 | -0.4717 | -0.11101 | -0.065281
| 3625 | 0.28007 | 0.44421 | 0.15153 | 0.1546 | 0.78297 | -0.4997 | -0.35634 | 0.25227 | -0.072476 | -0.27591
| 3626 | 0.23757 | -0.015876 | 0.036621 | -0.3568 | -0.50331 | -0.081251 | 0.1803 | 0.5721 | 0.51657 | -0.046952
| 3627 | 0.70487 | -0.8148 | 0.32051 | -0.7881 | 0.39942 | 0.29765 | 0.47703 | 0.33917 | -0.61231 | -0.26237
| 3628 | -0.73074 | -0.3743 | -0.46121 | -0.3366 | -0.042347 | 0.45365 | 0.91574 | 0.19819 | 0.2488 | -0.19198
| 3629 | 0.34144 | 0.016181 | 0.74643 | -0.64659 | 0.42095 | -0.19557 | 0.33735 | -0.35092 | -0.0069743 | -0.95417
| 3630 | -0.5436 | 0.29296 | -0.051686 | -0.62198 | 0.73149 | -0.56791 | 0.16006 | -0.16928 | 0.026296 | -0.27813
| 3631 | -0.17471 | 0.35805 | 0.79531 | -0.59147 | -0.095843 | -0.21355 | 0.58878 | 0.54448 | -0.060479 | 0.16904
| 3632 | -0.27799 | 0.37159 | -0.060692 | 0.61231 | 0.37558 | 0.62731 | 0.27564 | 0.45806 | 0.0026535 | 0.032994
| 3633 | -0.73942 | 0.15519 | 0.47455 | -0.21215 | 0.16819 | 0.35867 | -0.2659 | 0.1879 | -0.19944 | -0.050105
| 3634 | -0.27426 | -0.49433 | 0.11767 | -0.25804 | 0.11079 | -0.61803 | 0.010404 | 0.56861 | -0.19359 | 0.1775
| 3635 | 0.1229 | -0.7184 | -0.12154 | 0.48512 | 0.88126 | 0.52094 | -0.41545 | 0.073231 | -0.69292 | 0.25468
| 3636 | -0.61464 | 0.40983 | -0.095622 | -0.32273 | -0.24535 | -0.59098 | -0.25013 | 0.081033 | -0.14472 | -0.019745
| 3637 | -0.16627 | 0.20937 | 0.41306 | -0.13461 | -0.70352 | -0.26413 | -0.35139 | 0.1559 | -0.95204 | -0.5954
| 3638 | -0.20181 | 0.23378 | 0.23026 | -0.046218 | 0.60592 | -0.16006 | 0.10362 | 0.50553 | -0.47076 | -0.35743
| 3639 | 0.44098 | 0.536 | 0.58927 | 0.32258 | 0.38885 | -0.35123 | 0.17738 | 0.054537 | 0.016486 | -0.082449
| 3640 | 0.50776 | -0.60541 | -0.54033 | 0.15425 | -0.29212 | -0.009697 | -0.09695 | -0.58563 | -0.17495 | 0.068281
| 3641 | -0.011617 | 0.81807 | 0.11394 | 0.062503 | -0.4983 | 0.26359 | 0.18581 | -0.2689 | -0.039948 | 0.40259
| 3642 | 0.0049623 | 0.22469 | -0.39676 | 0.62092 | 0.094738 | -0.54054 | -0.21013 | 0.50654 | -0.22611 | 0.40662
| 3643 | -0.1091 | -0.2809 | -0.053586 | -0.33524 | -0.37366 | -0.56653 | 0.36196 | -0.19732 | -0.55044 | -0.54536
| 3644 | -0.036413 | -0.20181 | -0.21038 | -0.52387 | -0.58131 | -0.5768 | -0.16543 | -0.70453 | 0.20207 | 0.17048
| 3645 | 0.548 | 0.54889 | 0.38073 | -0.062077 | -0.45972 | -0.95641 | 0.1196 | -0.53171 | -0.47417 | -0.19931
| 3646 | -0.10876 | 0.53772 | -0.37783 | -0.11383 | -0.22508 | 0.29296 | 0.79482 | 0.74212 | 0.44891 | -0.062397
| 3647 | 0.32051 | -0.093413 | 0.76827 | -0.57116 | -0.14029 | 0.67366 | 0.44692 | -0.49771 | 0.63 | 0.29056
| 3648 | -0.18532 | -0.35355 | 0.096396 | -0.10731 | 0.039219 | -0.47038 | -0.2119 | 0.63408 | -0.01791 | -0.59466
| 3649 | -0.3306 | -0.78023 | 0.27453 | -0.3607 | 0.3618 | 0.09143 | -0.066244 | 0.3211 | 0.13473 | 0.087805
| 3650 | -0.070538 | 0.20785 | 0.16964 | 0.19794 | -0.42685 | 0.69784 | -0.2234 | -0.50331 | -0.96394 | 0.0028541
| 3651 | 0.85964 | -0.16928 | -0.23823 | 0.40008 | -0.448 | 0.16543 | -0.15958 | 0.47455 | 0.36952 | -0.21584
| 3652 | -0.21013 | 0.74564 | -0.33479 | 0.66789 | 0.72233 | 0.15425 | -0.89753 | 0.21904 | -0.0017515 | 0.080924
| 3653 | 0.55853 | -0.83237 | -0.17823 | 0.40225 | 0.30841 | -0.09 | 0.28146 | 0.36463 | 0.54338 | 0.36384
| 3654 | -0.69357 | -0.17048 | -0.2924 | 0.76146 | 0.18189 | -0.88295 | 0.19508 | 0.26386 | -0.39213 | -0.016791
| 3655 | 0.14157 | 0.53064 | -0.40108 | -0.48609 | -0.20294 | 0.012427 | -0.1153 | 0.40276 | -0.26264 | 0.055595
| 3656 | -0.078968 | -0.0028541 | -0.13207 | -0.01842 | 0.5143 | -0.13265 | -0.63792 | 0.12747 | 0.45991 | -0.010404
| 3657 | -0.3061 | 0.57609 | -0.046113 | 0.77572 | -0.24204 | 0.14052 | 0.66519 | -0.93755 | 0.28901 | 0.24947
| 3658 | 0.058246 | -0.048843 | -0.46962 | -0.46009 | 0.59714 | 0.44367 | -0.14227 | -0.085396 | 0.01091 | -0.55178
| 3659 | 0.3369 | 0.20709 | 0.24628 | 0.12747 | 0.29466 | 0.52915 | -0.085834 | 0.45365 | -0.42026 | -0.10295
| 3660 | 0.42389 | 0.34068 | 0.53556 | -0.80125 | -0.19881 | -0.4668 | 0.32465 | 0.46474 | 0.15602 | -0.67
| 3661 | 0.54756 | 0.76569 | 0.082776 | -0.60491 | -0.22353 | 0.25522 | 0.26672 | -0.18189 | -0.37366 | -0.19645
| 3662 | 0.01182 | 0.10933 | 0.6319 | 0.28021 | -0.047582 | -0.078534 | -0.30236 | 0.22366 | -0.49493 | -0.71875
| 3663 | -0.18704 | -0.080054 | 0.50594 | -0.033615 | -0.55604 | -0.10876 | 0.20232 | -0.46213 | 0.46251 | -0.43724
| 3664 | -0.75161 | -0.45383 | -0.31802 | 0.49374 | 0.52157 | -0.13553 | -0.56057 | -0.15024 | -0.2598 | 0.13104
| 3665 | 0.24588 | -0.58395 | -0.29551 | -0.10017 | -0.76484 | 0.056867 | -0.087147 | -0.024654 | -0.34632 | -0.055913
| 3666 | -0.35139 | 0.64293 | 0.62277 | -0.23052 | -0.48532 | 0.21763 | -0.86036 | 0.80895 | -0.79336 | 0.38396
| 3667 | -0.48222 | -0.088353 | 0.53085 | 0.12702 | -0.13994 | -0.71875 | -0.73524 | 0.12404 | -0.4668 | -0.36431
| 3668 | 0.055172 | 0.14029 | -0.28049 | 0.64631 | -0.059521 | 0.062397 | -0.47019 | 0.40797 | -0.29099 | 0.56445
| 3669 | -0.24495 | -0.049158 | 0.054855 | -0.23705 | 0.15733 | -0.35961 | 0.5693 | 0.56699 | -0.07183 | 0.038491
| 3670 | 0.54163 | 0.73411 | -0.72742 | 0.09529 | 0.62119 | -0.61 | -0.051791 | -0.73561 | 0.33992 | -0.29993
| 3671 | -0.27522 | 0.19831 | -0.95204 | -0.58419 | 0.053903 | 0.22083 | 0.64687 | -0.14765 | -0.11598 | 0.41272
| 3672 | 0.76698 | -0.3116 | 0.3189 | -0.73335 | 0.28481 | 0.33194 | -0.033305 | -0.33977 | 0.30725 | 0.53729
| 3673 | 0.28202 | 0.54823 | 0.17508 | 0.12759 | 0.43458 | -0.063677 | 0.071291 | 0.16006 | 0.71733 | -0.10641
| 3674 | 0.59466 | -0.21546 | 0.83177 | 0.086271 | -0.20169 | -0.41442 | 0.47398 | -0.019745 | 0.75363 | -0.023015
| 3675 | 0.61699 | -0.2256 | 0.39115 | 0.46269 | 0.24402 | 0.36337 | -0.1204 | -0.34479 | 0.087366 | -0.50351
| 3676 | 0.068496 | -0.011516 | 0.047267 | -0.38073 | 0.31131 | 0.06261 | -0.3248 | 0.45383 | -0.44224 | -0.21228
| 3677 | -0.55875 | -0.24575 | -0.16844 | 0.5224 | 0.43246 | 0.79143 | -0.4989 | -0.40645 | -0.13311 | -0.045694
| 3678 | 0.21051 | 0.05348 | -0.24947 | 0.59515 | -0.24455 | 0.63737 | -0.10418 | -0.29907 | 0.41922 | -0.53149
| 3679 | -0.47455 | 0.02322 | -0.75648 | -0.26128 | -0.18803 | 0.148 | -0.25334 | -0.39197 | -0.39362 | 0.079294
| 3680 | 0.23338 | 0.22276 | -0.019031 | 0.14449 | 0.027529 | -0.31626 | -0.58227 | -0.046742 | 0.045694 | 0.63326
| 3681 | 0.19074 | 0.18483 | -0.65345 | 0.48338 | 0.59938 | -0.14204 | -0.23091 | -0.81588 | 0.82479 | -0.094848
| 3682 | -0.19161 | 0.09066 | -0.39312 | -0.37159 | -0.32836 | -0.016588 | 0.25562 | 0.2508 | -0.13797 | 0.12977
| 3683 | -0.39626 | 0.34662 | -0.19769 | -0.29537 | 0.46381 | -0.04172 | 0.17763 | 0.28467 | 0.37286 | -0.37944
| 3684 | -0.15543 | 0.20395 | -0.093303 | 0.53816 | -0.23391 | 0.076474 | -0.025988 | -0.12496 | 0.48125 | -0.51082
| 3685 | -0.58371 | 0.14695 | 0.28901 | 0.018012 | 0.67304 | 0.28944 | -0.59763 | 0.16819 | 0.72486 | -0.46437
| 3686 | 0.3419 | 0.068281 | -0.18043 | -0.12908 | -0.37175 | -0.04026 | -0.21623 | -0.38689 | -0.37064 | -0.17193
| 3687 | -0.23809 | 0.58757 | -0.5583 | -0.021072 | -0.48144 | 0.13346 | 0.26047 | 0.19757 | 0.73411 | 0.16256
| 3688 | 0.072908 | 0.13069 | 0.32184 | 0.0082843 | 0.01182 | -0.34494 | -0.031341 | 0.38624 | -0.34099 | 0.47322
| 3689 | -0.40192 | -0.58757 | 0.13704 | 0.092751 | -0.54845 | -0.17896 | 0.58757 | 0.023629 | -0.050526 | 0.41306
| 3690 | -0.39115 | -0.5458 | 0.43299 | -0.82422 | -0.87 | -0.17036 | 0.81265 | -0.40983 | 0.046218 | 0.58805
| 3691 | 0.51082 | -0.46028 | -0.0093941 | 0.23495 | -0.033408 | 0.63163 | -0.046218 | -0.31043 | -0.26373 | 0.11315
| 3692 | 0.7735 | 0.24455 | -0.97354 | 0.63958 | -0.18483 | -0.46083 | -0.12702 | -0.62224 | -0.136 | 0.39825
| 3693 | -0.22805 | -0.11835 | 0.20924 | 0.028661 | 0.11304 | -0.12324 | 0.074959 | -0.48144 | -0.14965 | -0.061224
| 3694 | -0.42181 | -0.77218 | -0.72523 | -0.51637 | -0.82028 | -0.24217 | 0.24774 | -0.38526 | -0.59515 | 0.23482
| 3695 | -0.44927 | 0.57257 | 0.53707 | -0.3618 | 0.50776 | 0.46176 | 0.17121 | -0.27055 | 0.21623 | -0.38024
| 3696 | 0.48357 | -0.51287 | -0.5436 | 0.27467 | -0.26767 | 0.26822 | 0.85474 | -0.094517 | -0.17775 | 0.28775
| 3697 | -0.39842 | 0.54185 | -0.18104 | -0.32066 | 0.12222 | -0.08343 | 0.39775 | 0.093523 | -0.16904 | 0.11045
| 3698 | 0.4258 | 0.60949 | 0.095511 | -0.63108 | 0.14718 | 0.84605 | 0.70589 | -0.55044 | -0.1758 | -0.37095
| 3699 | 0.15012 | 0.3838 | -0.16066 | -0.36321 | -0.6637 | 0.56537 | -0.37606 | -0.41665 | -0.25347 | -0.76063
| 3700 | -0.085068 | -0.51513 | 0.35401 | 0.045904 | 0.45695 | -0.38008 | -0.51595 | -0.36952 | -0.15851 | -0.39576
| 3701 | -0.085834 | 0.095843 | 0.32955 | -0.15295 | 0.15224 | -0.62543 | -0.092311 | -0.45401 | -0.3048 | -0.024962
| 3702 | -0.49532 | -0.40763 | 0.82139 | 0.57846 | 0.19782 | 0.31378 | 0.036724 | 0.28901 | -0.72632 | 0.58854
| 3703 | 0.7881 | -0.03714 | -0.3422 | -0.29879 | -0.75813 | -0.30812 | 0.3743 | -0.092311 | -0.085178 | 0.0072765
| 3704 | 0.22521 | 0.2037 | 0.17169 | 0.40746 | 0.67243 | -0.18459 | -0.21597 | -0.85964 | -0.24046 | -0.02897
| 3705 | -0.48804 | -0.13023 | 0.1879 | -0.020051 | 0.17957 | -0.23547 | -0.61309 | -0.08978 | -0.38478 | 0.10128
| 3706 | 0.030206 | 0.0059678 | 0.10217 | 0.73637 | 0.73037 | -0.66728 | -0.28341 | 0.44638 | 0.023834 | 0.80226
| 3707 | -0.3804 | -0.57257 | -0.87311 | 0.83177 | 0.19994 | 0.55966 | -0.085615 | 0.032684 | -0.09695 | -0.41357
| 3708 | 0.19099 | 0.03714 | -0.20432 | 0.055913 | -0.1382 | 0.24588 | 0.32125 | 0.72414 | 0.055278 | -0.11869
| 3709 | -0.19533 | -0.75938 | 0.32598 | 0.64857 | -0.63958 | -0.28565 | -0.083539 | 0.19831 | -0.072584 | -0.16627
| 3710 | -0.27702 | 0.54734 | -0.06753 | -0.56977 | 0.78483 | -0.45751 | -0.29353 | 0.31875 | 0.11609 | -0.53171
| 3711 | 0.20646 | -0.18043 | 0.20747 | -0.19322 | 0.20621 | -0.16376 | -0.09 | 0.23705 | -0.27 | 0.20684
| 3712 | 0.44945 | 0.19458 | 0.086928 | -0.22353 | 0.69324 | 0.24283 | 0.46699 | -0.048948 | -0.46737 | 0.053691
| 3713 | 0.28986 | 0.61934 | 0.48785 | -0.094848 | 0.094406 | 0.2755 | -0.50351 | 0.41459 | 0.50251 | -0.24575
| 3714 | -0.42337 | -0.16101 | -0.27938 | -0.5283 | -0.63848 | -0.5174 | 0.066565 | -0.8995 | 0.14461 | 0.50939
| 3715 | -0.67798 | 0.06197 | 0.46568 | -0.51927 | 0.017809 | 0.25818 | 0.18312 | -0.20169 | -0.34403 | 0.86923
| 3716 | -0.039219 | -0.036309 | -0.53989 | 0.57609 | 0.27591 | -0.36149 | 0.19495 | 0.043287 | 0.70521 | 0.60013
| 3717 | -0.73524 | 0.78344 | -0.54229 | -0.64602 | -0.29197 | -0.21827 | -0.68552 | -0.11926 | -0.16831 | 0.18852
| 3718 | -0.30855 | -0.60038 | 0.46755 | 0.0093941 | -0.86325 | 0.016689 | -0.87712 | 0.68141 | 0.38445 | -0.05253
| 3719 | -0.37879 | -0.80791 | -0.21127 | 0.018114 | 0.1221 | -0.71452 | -0.041616 | 0.096396 | -0.021276 | 0.24416
| 3720 | -0.017401 | 0.20344 | -0.32214 | -0.034029 | -0.3061 | 0.12989 | -0.54823 | -0.37318 | 0.56125 | 0.26427
| 3721 | 0.21597 | 0.028249 | -0.41272 | 0.23587 | 0.46587 | -0.050526 | -0.47151 | 0.83118 | 0.65 | -0.88909
| 3722 | 0.36321 | -0.30164 | 0.67519 | 0.38478 | -0.52261 | -0.53556 | -0.51534 | -0.56285 | 0.57257 | 0.63435
| 3723 | -0.13553 | -0.098501 | -0.019745 | -0.34525 | -0.17738 | 0.71277 | -0.14239 | -0.64857 | -0.82365 | 0.22624
| 3724 | -0.47474 | -0.29085 | 0.59073 | -0.019337 | 0.48551 | 0.22792 | -0.54956 | -0.3294 | 0.31232 | -0.64829
| 3725 | -0.15982 | -0.1005 | -0.21419 | -0.067745 | 0.39709 | 0.032994 | -0.38689 | 0.29367 | 0.25334 | -0.099833
| 3726 | -0.095511 | -0.76957 | 0.069463 | -0.23928 | -0.0037571 | 0.39148 | 0.028249 | -0.28579 | -0.36604 | 0.37127
| 3727 | 0.10462 | 0.1162 | 0.08485 | 0.70691 | -0.43405 | -0.45843 | -0.039219 | 0.32598 | 0.072045 | -0.53277
| 3728 | 0.0086877 | 0.53299 | 0.034029 | 0.22431 | -0.85067 | -0.33947 | 0.12416 | 0.72926 | 0.27744 | -0.54867
| 3729 | -0.11417 | 0.48629 | -0.52767 | 0.10306 | 0.067959 | 0.12954 | 0.70083 | -0.85474 | -0.25791 | 0.19458
| 3730 | 0.27785 | 0.2744 | -0.69194 | 0.054643 | -0.63462 | 0.41888 | 0.15059 | 0.15578 | -0.53128 | 0.24827
| 3731 | 0.28593 | 0.49315 | 0.29367 | 0.036724 | -0.29637 | -0.33615 | 0.25414 | 0.024346 | -0.84094 | -0.20722
| 3732 | -0.16928 | 0.65751 | 0.49374 | -0.13322 | 0.4776 | 0.52471 | 0.4898 | -0.32524 | -0.42511 | -0.0027538
| 3733 | 0.59664 | -0.22715 | 0.24191 | 0.69065 | 0.34418 | -0.46046 | 0.37702 | -0.72341 | 0.0078811 | -0.3189
| 3734 | 0.9272 | 0.46325 | -0.14157 | -0.28453 | -0.35062 | 0.1425 | 0.56791 | -0.15567 | -0.51102 | -0.31451
| 3735 | -0.46962 | 0.43831 | 0.58636 | -0.17945 | -0.55898 | -0.70386 | 0.252 | -0.20621 | 0.77572 | -0.057928
| 3736 | -0.15756 | -0.11383 | -0.25013 | -0.83237 | 0.248 | -0.17145 | -0.051264 | 0.015774 | -0.083103 | 0.21495
| 3737 | -0.20848 | -0.20483 | -0.31131 | 0.0086877 | 0.16964 | 0.13299 | 0.29622 | 0.21891 | -0.043182 | -0.1005
| 3738 | -0.25401 | 0.14753 | -0.33434 | 0.012934 | 0.078968 | -0.23156 | 0.32776 | 0.6249 | -0.73866 | -0.058034
| 3739 | 0.20747 | -0.50291 | -0.30437 | 0.74643 | 0.48765 | -0.24046 | -0.062823 | 0.17302 | 0.89656 | 0.19185
| 3740 | -0.065816 | 0.0054649 | -0.88295 | -0.018623 | 0.40209 | 0.12667 | -0.021276 | -0.42476 | -0.5007 | 0.2689
| 3741 | 0.016486 | 0.16735 | -0.25939 | 0.39593 | -0.71733 | 0.16113 | 0.24191 | 0.63217 | 0.23508 | 0.21432
| 3742 | 0.11428 | -0.75 | -0.38153 | 0.16376 | -0.74761 | -0.13623 | -0.19782 | -0.29836 | -0.50513 | -0.39
| 3743 | 0.10083 | -0.35743 | 0.087805 | -0.46102 | 0.063357 | 0.044228 | -0.34601 | -0.5245 | 0.08989 | 0.19981
| 3744 | -0.27371 | 0.7504 | 0.64265 | 0.63599 | -0.46325 | 0.1868 | 0.21292 | 0.34601 | 0.56977 | -0.13565
| 3745 | -0.19111 | 0.54956 | -0.63903 | 0.60038 | -0.21789 | -0.12977 | -0.34785 | -0.0028541 | 0.68711 | 0.02281
| 3746 | -0.19794 | 0.0035563 | -0.088243 | -0.35649 | 0.32628 | 0.037451 | -0.096617 | 0.31597 | 0.094848 | -0.083539
| 3747 | -0.63737 | -0.79288 | 0.33509 | 0.083649 | -0.39082 | 0.50817 | 0.5015 | -0.24376 | -0.47952 | -0.22109
| 3748 | -0.10731 | 0.014556 | -0.57893 | 0.19446 | 0.02722 | -0.3372 | -0.22663 | -0.35525 | 0.40175 | 0.094075
| 3749 | -0.6546 | -0.56814 | -0.22109 | -0.39859 | -0.035894 | 0.073447 | -0.73223 | -0.40008 | -0.049895 | 0.10462
| 3750 | -0.55156 | -0.29793 | 0.28761 | 0.28944 | 0.3214 | 0.3297 | 0.045065 | -0.26877 | -0.13866 | 0.072584
| 3751 | 0.11304 | 0.21968 | 0.052635 | 0.0037571 | -0.55649 | 0.23613 | -0.68047 | 0.19533 | 0.18827 | -0.29254
| 3752 | -0.098612 | -0.80025 | -0.83237 | -0.39066 | -0.049579 | -0.86771 | 0.61829 | 0.39527 | -0.12816 | 0.14472
| 3753 | 0.45 | -0.093303 | -0.23338 | 0.12989 | 0.26291 | 0.22482 | 0.19309 | 0.55245 | 0.84605 | -0.034547
| 3754 | -0.32332 | -0.72125 | -0.089561 | 0.29537 | 0.050421 | 0.63299 | -0.14414 | -0.32821 | 0.93597 | -0.13265
| 3755 | 0.48415 | 0.33164 | 0.29028 | 0.28202 | -0.53107 | 0.15673 | -0.4307 | -0.20735 | -0.14988 | -0.4668
| 3756 | -0.12473 | 0.15106 | -0.63244 | -0.69619 | 0.21444 | 0.62198 | 0.46176 | -0.81426 | 0.50432 | 0.64943
| 3757 | 0.53729 | -0.14006 | 0.21355 | -0.2893 | 0.37831 | -0.57609 | 0.30222 | 0.58515 | -0.16042 | -0.70555
| 3758 | -0.29793 | 0.39378 | 0.00095045 | -0.45603 | -0.26237 | 0.15697 | -0.086381 | 0.32776 | 0.73599 | 0.4417
| 3759 | -0.30797 | -0.33134 | 0.47952 | 0.37111 | 0.088463 | 0.1628 | 0.24641 | 0.53664 | -0.23915 | -0.35123
| 3760 | -0.19831 | 0.052002 | 0.24522 | 0.12862 | 0.20697 | 0.86771 | -0.23665 | -0.15271 | -0.52936 | -0.33886
| 3761 | -0.058459 | -0.27564 | -0.6162 | -0.044542 | 0.40865 | 0.21635 | -0.2744 | -0.15094 | 0.078317 | 0.73298
| 3762 | -0.30783 | -0.20659 | -0.30855 | 0.31014 | -0.38299 | 0.031238 | -0.6241 | -0.12051 | -0.23639 | -0.40259
| 3763 | -0.18104 | 0.5714 | -0.73335 | 0.02897 | 0.071722 | -0.077124 | 0.011314 | -0.27619 | 0.37175 | 0.081033
| 3764 | -0.17532 | -0.35961 | -0.31102 | 0.37911 | -0.72559 | 0.28831 | -0.20131 | 0.9134 | 0.58563 | -0.23443
| 3765 | 0.018318 | 0.041616 | 0.038803 | 0.51082 | 0.16089 | -0.35386 | 0.025474 | 0.89753 | -0.19446 | -0.12063
| 3766 | -0.040469 | 0.64014 | 0.26781 | 0.38494 | -0.13392 | -0.007478 | 0.11259 | 0.69259 | -0.16448 | -0.10485
| 3767 | 0.22032 | 0.148 | -0.26781 | -0.057397 | 0.26468 | 0.2625 | 0.54338 | -0.027837 | 0.38396 | -0.49413
| 3768 | -0.47265 | -0.27027 | -0.4232 | 0.27661 | 0.16591 | 0.52157 | 0.54207 | 0.1261 | 0.25764 | 0.9134
| 3769 | 0.48512 | 0.23495 | 0.053374 | -0.056761 | -0.07043 | 0.43458 | -0.1921 | 0.34174 | 0.14578 | -0.43973
| 3770 | -0.88467 | 0.14554 | 0.27274 | 0.11677 | -0.12507 | -0.19148 | 0.38137 | -0.36211 | -0.039635 | -0.69685
| 3771 | -0.29014 | 0.71804 | -0.13299 | 0.2524 | -0.59049 | 0.72742 | -0.87793 | -0.43973 | 0.66015 | 0.19359
| 3772 | -0.45091 | -0.50939 | -0.35665 | -0.0028541 | -0.72089 | -0.44529 | 0.54273 | 0.35015 | 0.42095 | 0.0033556
| 3773 | -0.38624 | -0.09 | 0.18963 | 0.092421 | 0.37318 | -0.59466 | 0.4985 | 0.58371 | -0.37111 | -0.4553
| 3774 | 0.21241 | -0.43053 | -0.37799 | 0.61283 | 0.37574 | 0.47057 | -0.58805 | -0.49039 | -0.70251 | 0.1962
| 3775 | 0.64489 | -0.43742 | -0.10686 | -0.53427 | 0.5332 | 0.14648 | -0.25576 | 0.41699 | -0.2225 | 0.065602
| 3776 | -0.49493 | -0.20131 | 0.21101 | 0.34647 | 0.16006 | 0.071076 | -0.20772 | -0.25818 | 0.1204 | 0.70966
| 3777 | -0.61154 | -0.023834 | -0.06293 | -0.21279 | -0.65431 | -0.4279 | 0.35139 | 0.073016 | 0.10798 | 0.15389
| 3778 | 0.8148 | 0.096396 | -0.40494 | -0.26183 | -0.075284 | 0.10574 | -0.64489 | -0.088902 | -0.41034 | -0.61672
| 3779 | 0.71069 | 0.28453 | 0.48687 | 0.021379 | -0.44782 | -0.30653 | 0.55627 | 0.16928 | -0.73186 | 0.2512
| 3780 | 0.13739 | -0.20257 | 0.37831 | -0.1179 | 0.66819 | -0.16292 | -0.33992 | -0.5172 | 0.70725 | 0.24033
| 3781 | -0.24151 | -0.27965 | 0.21904 | 0.52219 | 0.61309 | 0.47569 | -0.31203 | -0.60138 | 0.3248 | 0.36102
| 3782 | -0.093523 | -0.46493 | -0.047687 | -0.7623 | -0.70083 | 0.29509 | -0.22302 | 0.36274 | -0.056231 | -0.043601
| 3783 | 0.96683 | -0.016893 | 0.12439 | -0.69817 | -0.27288 | 0.09839 | 0.074311 | 0.60314 | -0.27605 | -0.47398
| 3784 | 0.047687 | 0.0015512 | 0.16591 | 0.26156 | -0.19645 | 0.6995 | -0.25254 | 0.26713 | -0.22366 | -0.12176
| 3785 | 0.24495 | -0.48648 | 0.10418 | -0.35185 | 0.030516 | 0.69194 | -0.45018 | -0.072369 | -0.33585 | 0.43671
| 3786 | -0.72018 | 0.11699 | 0.60063 | 0.50311 | 0.32509 | -0.89183 | -0.10184 | 0.099722 | -0.36589 | -0.78716
| 3787 | 0.15756 | -0.46793 | -0.12553 | -0.55447 | -0.31451 | 0.28593 | 0.23665 | -0.17121 | -0.10776 | 0.36636
| 3788 | 0.36526 | 0.1063 | 0.51287 | 0.31363 | 0.19396 | 0.42424 | 0.11892 | 0.57964 | 0.44439 | -0.0021523
| 3789 | -0.46158 | -0.16472 | 0.45548 | 0.11372 | -0.10787 | 0.40544 | 0.095511 | -0.70318 | 0.081686 | -0.40915
| 3790 | 0.34114 | -0.20031 | -0.28076 | -0.5007 | -0.010202 | 0.75485 | -0.079294 | 0.56954 | 0.020153 | 0.11756
| 3791 | -0.24059 | -0.42703 | -0.12359 | -0.78952 | 0.19173 | -0.76063 | 0.77796 | 0.11541 | -0.24244 | -0.15721
| 3792 | 0.27055 | -0.025474 | -0.095401 | -0.49552 | -0.62919 | -0.049895 | -0.070108 | -0.22083 | 0.36573 | -0.47779
| 3793 | -0.088682 | -0.46362 | 0.39925 | -0.34388 | 0.67984 | -0.15899 | -0.13092 | -0.19446 | -0.30581 | 0.44116
| 3794 | 0.027118 | -0.37302 | -0.62066 | 0.33194 | 0.17495 | 0.01263 | 0.069355 | -0.31831 | 0.48746 | 0.82536
| 3795 | -0.050948 | 0.04026 | -0.060798 | -0.083867 | 0.049684 | -0.69227 | -0.64321 | -0.32762 | -0.49059 | -0.065709
| 3796 | 0.52219 | 0.19707 | -0.50371 | 0.31436 | 0.038075 | -0.45917 | 0.040573 | -0.21076 | 0.48902 | -0.14239
| 3797 | 0.33539 | 0.30667 | -0.56791 | -0.3129 | 0.063998 | 0.16089 | -0.0022525 | 0.16856 | 0.022708 | 0.56491
| 3798 | 0.2816 | -0.76484 | 0.32346 | -0.68172 | -0.13646 | 0.46381 | 0.073447 | 0.2816 | 0.016181 | 0.12199
| 3799 | -0.05253 | 0.076799 | -0.1597 | 0.19099 | -0.71982 | 0.11915 | 0.012022 | -0.53902 | -0.30322 | 0.35139
| 3800 | -0.16543 | 0.80277 | -0.3186 | 0.1375 | -0.34357 | 0.17556 | -0.22896 | -0.60516 | -0.5806 | 0.1044
| 3801 | -0.0066723 | -0.13924 | 0.04172 | 0.065388 | 0.081904 | 0.15507 | -0.15923 | 0.2184 | 0.35556 | -0.27495
| 3802 | -0.9219 | -0.4995 | 0.16988 | 0.11665 | -0.53043 | 0.26767 | -0.020255 | 0.61077 | -0.16916 | -0.039531
| 3803 | 0.28747 | 0.14765 | 0.78905 | -0.67581 | 0.90673 | 0.88642 | -0.40209 | -0.0011507 | -0.032684 | -0.1044
| 3804 | 0.18655 | -0.82252 | -0.11903 | 0.20546 | -0.018827 | 0.34144 | 0.27453 | -0.62919 | 0.39345 | -0.041825
| 3805 | 0.26631 | 0.22135 | -0.26495 | -0.12393 | 0.31334 | 0.081033 | 0.38804 | 0.17629 | 0.37302 | -0.05899
| 3806 | 0.053374 | 0.52513 | -0.052952 | 0.74212 | -0.26115 | 0.51823 | 0.64349 | -0.72378 | 0.53643 | -0.25549
| 3807 | -0.09209 | 0.12176 | 0.065602 | -0.56285 | 0.84933 | 0.024141 | -0.21152 | -0.022606 | 0.41733 | 0.2476
| 3808 | 0.015571 | -0.48087 | -0.22495 | 0.040677 | 0.20646 | -0.48125 | 0.74761 | 0.0036567 | 0.88909 | -0.59196
| 3809 | 0.21981 | 0.24217 | 0.9089 | -0.2744 | 0.11326 | 0.36133 | -0.43564 | -0.2907 | -0.028455 | 0.20207
| 3810 | 0.0173 | -0.29807 | 0.19694 | -0.59888 | -0.23469 | 0.49196 | -0.68235 | 0.20156 | 0.30394 | 0.17133
| 3811 | -0.038179 | 0.42078 | 0.064853 | 0.12793 | 0.27041 | -0.24641 | 0.73904 | 0.16412 | 0.22302 | 0.44313
| 3812 | -0.46925 | -0.164 | 0.41733 | 0.59714 | -0.18963 | 0.23325 | 0.29594 | 0.74251 | 0.56034 | 0.060479
| 3813 | 0.74801 | 0.18569 | 0.5583 | -0.43158 | -0.65956 | -0.78529 | -0.76827 | 0.6634 | -0.42441 | -0.1825
| 3814 | 0.5959 | 0.24416 | 0.68839 | 0.60088 | 0.46288 | 0.66044 | 0.24535 | 0.59813 | -0.27509 | -0.40192
| 3815 | 0.34403 | -0.77 | 0.22302 | -0.66251 | 0.65373 | -0.088463 | -0.59515 | 0.81752 | -0.095511 | 0.58467
| 3816 | 0.06753 | 0.68456 | 0.17048 | -0.48687 | 0.076907 | 0.4286 | 0.79826 | 0.54142 | 0.51061 | 0.32524
| 3817 | 0.3662 | -0.24191 | -0.14274 | 0.22482 | 0.046008 | -0.51761 | -0.27426 | -0.36274 | -0.36117 | 0.097282
| 3818 | -0.51554 | -0.30567 | 0.043182 | -0.076474 | -0.25147 | -0.39975 | -0.73448 | -0.034858 | -0.62171 | 0.27868
| 3819 | 0.32836 | 0.49374 | -0.25388 | -0.11609 | 0.76569 | 0.45677 | 0.16364 | 0.26945 | -0.13727 | 0.78023
| 3820 | -0.42476 | -0.3662 | 0.13785 | 0.34632 | 0.77887 | 0.015368 | 0.024962 | 0.57257 | 0.11428 | -0.046428
| 3821 | -0.37976 | -0.49137 | -0.10172 | -0.564 | 0.24059 | -0.028764 | 0.33045 | 0.56011 | 0.56422 | 0.35216
| 3822 | 0.47246 | 0.23836 | -0.54338 | 0.86546 | 0.2733 | -0.49453 | 0.13104 | -0.64433 | 0.12622 | 0.16364
| 3823 | -0.074095 | 0.58395 | 0.59763 | 0.12427 | 0.33947 | -0.20344 | 0.27165 | -0.043705 | 0.34555 | -0.63792
| 3824 | -0.15673 | 0.29099 | 0.55402 | 0.032271 | 0.38445 | -0.93144 | 0.28859 | 0.029279 | 0.096064 | -0.20735
| 3825 | -0.64857 | -0.035998 | -0.06016 | -0.072261 | 0.25885 | -0.056867 | 0.27993 | -0.012225 | -0.83721 | -0.22302
| 3826 | -0.20722 | 0.061757 | -0.30021 | 0.45365 | -0.39759 | -0.11045 | 0.10596 | 0.44927 | -0.01182 | 0.81
| 3827 | -0.57609 | 0.054643 | -0.19173 | 0.1578 | -0.41051 | -0.38722 | 0.17544 | 0.09055 | 0.66399 | -0.43742
| 3828 | 0.39626 | 0.42895 | -0.19272 | 0.19384 | -0.29367 | 0.069355 | 0.0078811 | -0.12427 | -0.014556 | 0.22096
| 3829 | -0.49039 | 0.23691 | -0.74761 | 0.36873 | 0.13011 | -0.070215 | -0.44945 | 0.011617 | -0.26169 | -0.23718
| 3830 | -0.42129 | 0.49059 | 0.78529 | -0.28132 | -0.28063 | -0.2893 | 0.11473 | -0.33015 | -0.44945 | -0.06165
| 3831 | 0.46868 | 0.15472 | 0.62784 | -0.16448 | 0.64772 | 0.4046 | 0.037971 | -0.28313 | 0.47569 | 0.55111
| 3832 | -0.29028 | -0.67581 | 0.07962 | -0.056443 | 0.5224 | -0.18864 | -0.049474 | -0.36384 | -0.10317 | -0.90151
| 3833 | -0.26577 | 0.23888 | -0.30207 | 0.65373 | 0.40696 | 0.23221 | 0.2216 | 0.15436 | 0.3681 | -0.12416
| 3834 | 0.44027 | -0.35805 | -0.21981 | 0.11259 | -0.5245 | 0.088134 | -0.59938 | -0.20634 | -0.07043 | -0.09695
| 3835 | -0.44873 | 0.47284 | 0.62066 | -0.55739 | 0.2674 | -0.18508 | -0.25562 | 0.58757 | -0.65751 | -0.38673
| 3836 | 0.050421 | 0.59024 | 0.10574 | 0.081469 | -0.47588 | -0.336 | -0.079511 | -0.089451 | -0.39279 | -0.74135
| 3837 | -0.67891 | 0.19161 | -0.48843 | -0.51451 | 0.71173 | 0.4799 | -0.010303 | -0.13983 | -0.25764 | 0.57988
| 3838 | 0.3025 | 0.44098 | -0.66103 | 0.25414 | -0.061544 | 0.060692 | -0.12063 | 0.69357 | 0.62463 | 0.14929
| 3839 | 0.056867 | 0.21648 | -0.33992 | -0.2216 | 0.43866 | -0.26427 | -0.38804 | -0.14145 | -0.36557 | -0.52661
| 3840 | 0.12017 | 0.85543 | -0.2948 | 0.91225 | 0.053691 | 0.017401 | -0.63682 | -0.15071 | -0.12233 | 0.19
| 3841 | -0.57846 | -0.62066 | -0.56537 | -0.82479 | -0.67953 | 0.18864 | -0.0049623 | 0.11665 | -0.18741 | -0.64349
| 3842 | 0.33254 | 0.57491 | 0.21089 | -0.38771 | -0.29141 | 0.83357 | 0.52031 | 0.67243 | 0.20798 | 0.34617
| 3843 | -0.60592 | -0.31131 | 0.6118 | 0.89851 | -0.73561 | 0.75648 | 0.53967 | -0.73186 | -0.22741 | 0.082558
| 3844 | -0.92319 | -0.252 | 0.3087 | 0.041303 | 0.015673 | -0.13092 | 0.43617 | -0.046952 | -0.43991 | 0.00015001
| 3845 | 0.049369 | 0.58012 | -0.26509 | -0.47455 | 0.060905 | 0.033201 | 0.83177 | 0.074851 | -0.022196 | -0.47436
| 3846 | 0.4337 | -0.47417 | -0.77395 | 0.28411 | 0.13496 | -0.49334 | -0.28831 | 0.56034 | 0.13299 | 0.22805
| 3847 | -0.0086877 | 0.48357 | -0.32985 | 0.11439 | -0.14589 | 0.30337 | 0.50715 | 0.21917 | -0.11124 | -0.34433
| 3848 | -0.51969 | 0.0062697 | -0.41596 | 0.47626 | 0.27799 | -0.12747 | 0.58203 | -0.060692 | 0.19272 | -0.14742
| 3849 | -0.18877 | -0.19969 | 0.23941 | 0.073663 | 0.03434 | -0.50513 | 0.0062697 | 0.1775 | 0.46868 | -0.5005
| 3850 | 0.14918 | -0.70828 | -0.26142 | 0.21687 | 0.38608 | 0.27979 | 0.35062 | -0.38706 | 0.0042591 | 0.19707
| 3851 | -0.81807 | -0.38967 | -0.27674 | 0.60314 | -0.013136 | -0.22935 | 0.44331 | -0.60314 | -0.33209 | 0.085724
| 3852 | 0.49771 | -0.2427 | 0.33871 | 0.77751 | 0.25616 | -0.70487 | 0.81917 | 0.45898 | 0.17823 | 0.086053
| 3853 | -0.48668 | -0.24987 | 0.087914 | -0.73866 | -0.3629 | -0.63627 | -0.85893 | -0.35355 | 0.24681 | -0.20596
| 3854 | -0.39676 | -0.15342 | 0.042764 | -0.16555 | 0.70017 | -0.34327 | 0.2133 | -0.75161 | -0.27316 | 0.022912
| 3855 | -0.15507 | -0.49236 | -0.38918 | 0.082776 | 0.85752 | 0.52873 | -0.12954 | 0.11191 | -0.42112 | 0.21597
| 3856 | -0.18483 | 0.33224 | -0.68583 | 0.0081835 | -0.59368 | 0.0049623 | -0.087914 | -0.23783 | -0.18214 | -0.28565
| 3857 | -0.47094 | 0.1261 | 0.17909 | -0.26959 | -0.61231 | -0.023527 | 0.6233 | -0.27702 | -0.15177 | -0.27302
| 3858 | 0.10888 | 0.448 | 0.52345 | -0.093634 | 0.70453 | -0.37446 | -0.075284 | 0.053374 | 0.42685 | 0.87876
| 3859 | -0.95641 | 0.23508 | 0.39825 | 0.06016 | 0.27854 | -0.35031 | -0.18238 | -0.031548 | 0.18508 | -0.80277
| 3860 | -0.40983 | 0.66162 | -0.42199 | 0.11 | 0.30293 | 0.10978 | 0.19894 | -0.17714 | -0.080924 | -0.20747
| 3861 | -0.15721 | 0.18766 | -0.15661 | -0.22482 | -0.23915 | 0.063357 | 0.19856 | -0.11949 | -0.0077803 | 0.7569
| 3862 | -0.25535 | 0.14227 | -0.37718 | -0.2575 | -0.15118 | 0.10608 | 0.50675 | 0.14835 | 0.35386 | 0.41017
| 3863 | 0.18189 | -0.28789 | 0.2508 | -0.26169 | -0.25361 | -0.68047 | -0.51287 | -0.12461 | -0.16892 | -0.14285
| 3864 | -0.5199 | 0.60238 | 0.012326 | 0.22122 | 0.066137 | 0.18889 | -0.29708 | -0.78576 | 0.88295 | 0.56954
| 3865 | 0.2941 | -0.61 | -0.13138 | 0.84867 | 0.71208 | 0.13913 | -0.51969 | -0.40443 | -0.38364 | -0.34388
| 3866 | 0.35727 | 0.18043 | -0.59938 | 0.65897 | 0.26645 | -0.31073 | 0.38918 | -0.21495 | -0.70453 | -0.27233
| 3867 | -0.71804 | -0.58733 | 0.18557 | 0.15543 | 0.42355 | -0.030516 | 0.53837 | 0.070753 | 0.33254 | 0.18483
| 3868 | -0.13855 | 0.12931 | 0.1269 | 0.30581 | 0.24455 | -0.24244 | 0.41272 | 0.21089 | -0.17933 | -0.40092
| 3869 | -0.26088 | -0.057609 | -0.8366 | 0.32687 | -0.37382 | -0.51389 | 0.052741 | -0.51844 | 0.098279 | 0.74135
| 3870 | 0.093744 | -0.61803 | 0.084522 | -0.12931 | 0.32687 | -0.34678 | -0.31465 | 0.1277 | -0.08343 | -0.15247
| 3871 | 0.10798 | 0.68711 | 0.016791 | 0.51164 | 0.55627 | 0.23247 | 0.14835 | 0.32524 | 0.35293 | 0.38657
| 3872 | -0.36715 | 0.31509 | 0.68583 | -0.8739 | 0.85682 | 0.09077 | 0.54404 | -0.86036 | -0.33841 | 0.57893
| 3873 | 0.7508 | -0.45511 | -0.04517 | 0.53256 | -0.13739 | 0.15519 | -0.58854 | -0.23208 | 0.45182 | -0.0087886
| 3874 | -0.48961 | 0.3851 | -0.83907 | -0.52788 | -0.099611 | 0.72233 | 0.20144 | -0.20823 | -0.67953 | -0.25267
| 3875 | 0.023936 | -0.65258 | 0.45456 | -0.30653 | -0.81917 | -0.087695 | 0.44295 | 0.02189 | 0.25616 | -0.34571
| 3876 | 0.21419 | -0.082013 | -0.30523 | -0.17568 | -0.62437 | 0.81106 | 0.53729 | -0.037971 | 0.77 | -0.26849
| 3877 | -0.78206 | 0.13565 | -0.32199 | 0.3309 | -0.30293 | -0.87077 | 0.93597 | -0.35696 | 0.054855 | -0.2431
| 3878 | 0.61335 | 0.11552 | -0.01415 | 0.024962 | 0.14262 | -0.49374 | 0.3568 | 0.76315 | -0.29779 | -0.4344
| 3879 | 0.88554 | 0.095069 | 0.11699 | -0.022503 | 0.34296 | -0.15994 | 0.092972 | 0.14099 | -0.22353 | -0.26904
| 3880 | 0.51328 | 0.70657 | -0.9134 | -0.5866 | -0.62624 | 0.32687 | 0.085834 | -0.24086 | 0.14122 | 0.11983
| 3881 | 0.12473 | -0.40881 | -0.38267 | 0.58251 | 0.30279 | 0.068496 | -0.082013 | -0.015673 | 0.10944 | -0.68679
| 3882 | 0.0083852 | -0.1179 | -0.73866 | 0.024039 | 0.22379 | -0.32096 | 0.70386 | 0.89091 | -0.4898 | 0.14988
| 3883 | 0.20861 | -0.34739 | -0.19099 | 0.3796 | -0.46028 | -0.57421 | 0.39329 | 0.31524 | 0.41051 | 0.10832
| 3884 | 0.4163 | -0.10596 | -0.69455 | 0.46437 | 0.32022 | -0.82139 | 0.56377 | 0.096617 | -0.2893 | -0.17314
| 3885 | -0.31949 | -0.63081 | 0.048948 | -0.21572 | 0.21648 | -0.66638 | 0.83969 | -0.5098 | -0.83783 | -0.72341
| 3886 | 0.0026535 | 0.021379 | 0.66015 | -0.065602 | -0.78251 | 0.58587 | -0.11892 | -0.55921 | 0.017198 | 0.26183
| 3887 | -0.45935 | -0.21738 | 0.17495 | 0.52724 | 0.60974 | 0.62437 | 0.61961 | 0.22534 | 0.54933 | 0.97354
| 3888 | 0.38559 | -0.040573 | 0.59664 | 0.37879 | -0.33344 | 0.083649 | 0.087257 | -0.25697 | 0.38738 | -0.34403
| 3889 | -0.31904 | -0.35154 | 0.27151 | 0.052002 | 0.017198 | 0.14262 | -0.087695 | 0.082013 | 0.35417 | 0.39263
| 3890 | 0.054643 | 0.11101 | 0.74329 | 0.2265 | 0.436 | 0.66103 | 0.072692 | 0.18336 | -0.067208 | 0.16173
| 3891 | 0.087366 | -0.09033 | -0.1072 | -0.07183 | -0.14636 | 0.49552 | 0.72414 | 0.22948 | 0.11349 | 0.2907
| 3892 | -0.86696 | 0.45567 | 0.20874 | 0.059947 | -0.52492 | 0.58878 | -0.26645 | 0.37079 | -0.40561 | -0.078859
| 3893 | 0.20169 | -0.84031 | -0.49374 | 0.3015 | -0.067959 | 0.50492 | 0.036517 | -0.22405 | 0.32465 | -0.61361
| 3894 | -0.028043 | 0.18116 | 0.75282 | 0.5015 | 0.096064 | -0.16651 | -0.012022 | -0.69817 | -0.68807 | 0.29395
| 3895 | 0.45677 | -0.44152 | -0.034236 | 0.50331 | 0.085834 | 0.21802 | 0.42389 | -0.028558 | 0.38722 | 0.62437
| 3896 | -0.40259 | -0.59318 | -0.13936 | -0.017503 | -0.17338 | 0.24046 | 0.22328 | 0.10776 | -0.051053 | -0.43105
| 3897 | -0.21827 | 0.25107 | 0.01 | 0.4668 | 0.13242 | -0.070645 | 0.1957 | -0.2042 | 0.028455 | -0.55
| 3898 | -0.21279 | -0.38153 | -0.78023 | -0.65839 | -0.1389 | 0.068603 | 0.064318 | 0.62092 | 0.23052 | 0.58491
| 3899 | -0.28916 | -0.081795 | 0.66638 | -0.30466 | -0.11451 | 0.24973 | -0.22315 | 0.038699 | -0.13276 | -0.44891
| 3900 | -0.012934 | -0.33344 | -0.52073 | 0.18153 | -0.35992 | 0.049474 | 0.21266 | 0.62973 | 0.045799 | -0.25107
| 3901 | -0.24257 | 0.075933 | -0.077558 | 0.64265 | 0.46046 | -0.51823 | -0.054749 | -0.32346 | -0.06325 | 0.23469
| 3902 | 0.38543 | 0.47322 | -0.1091 | -0.2816 | -0.24217 | -0.8937 | -0.1136 | -0.032271 | -0.09165 | 0.13461
| 3903 | 0.093413 | -0.28537 | -0.084085 | -0.11541 | -0.57703 | 0.46568 | 0.036205 | -0.40393 | -0.89464 | -0.1533
| 3904 | -0.23456 | 0.015876 | -0.20056 | 0.063571 | -0.81862 | -0.37366 | 0.17726 | 0.41665 | 0.6703 | 0.19769
| 3905 | 0.47019 | -0.35108 | 0.78763 | -0.46793 | 0.47512 | -0.10686 | 0.12954 | -0.5003 | 0.95417 | 0.17435
| 3906 | 0.58347 | -0.17544 | 0.034133 | -0.39809 | -0.56676 | 0.36699 | -0.66221 | 0.29679 | 0.59122 | -0.67519
| 3907 | 0.16711 | -0.060798 | -0.45511 | 0.094627 | 0.3923 | -0.016079 | -0.20445 | 0.64943 | 0.27509 | -0.24363
| 3908 | 0.6578 | -0.42965 | -0.36258 | -0.87712 | 0.10273 | -0.61934 | -0.037763 | 0.040782 | -0.32925 | -0.59147
| 3909 | -0.56653 | -0.25576 | 0.38429 | -0.28007 | 0.028661 | 0.29 | 0.92859 | -0.73298 | -0.86696 | -0.20044
| 3910 | -0.63027 | 0.19694 | 0.19185 | 0.24283 | 0.09176 | -0.019745 | -0.16101 | -0.12006 | -0.22289 | 0.19161
| 3911 | -0.33464 | -0.012528 | 0.063144 | 0.43546 | -0.43511 | -0.69488 | 0.024141 | 0.12222 | -0.40527 | -0.16711
| 3912 | 0.078642 | -0.18397 | -0.070861 | -0.056337 | 0.48435 | 0.37478 | -0.24522 | -0.51886 | -0.56583 | 0.04026
| 3913 | -0.13936 | -0.22728 | -0.20294 | 0.28691 | 0.27165 | -0.18692 | 0.40544 | 0.041303 | -0.035065 | 0.18803
| 3914 | 0.28118 | -0.064853 | -0.18877 | 0.15365 | -0.26047 | -0.22263 | -0.35867 | 0.22547 | 0.36274 | 0.136
| 3915 | -0.5768 | -0.4983 | -0.42982 | 0.40814 | -0.67581 | -0.54646 | -0.47588 | -0.57186 | 0.10619 | -0.40865
| 3916 | -0.1533 | -0.2356 | -0.40932 | -0.33479 | 0.47856 | 0.34296 | 0.043078 | 0.58299 | -0.37254 | 0.27274
| 3917 | -0.048843 | -0.76063 | -0.15212 | -0.23039 | -0.071938 | -0.44045 | 0.20684 | -0.16856 | -0.76784 | 0.039115
| 3918 | -0.33224 | -0.82883 | 0.41187 | -0.029382 | -0.16795 | -0.23117 | -0.011719 | 0.32821 | -0.37606 | -0.049158
| 3919 | -0.24973 | 0.68871 | 0.15519 | 0.30437 | -0.90253 | 0.53427 | 0.27965 | 0.092311 | -0.17423 | 0.3817
| 3920 | 0.6149 | -0.13542 | -0.29353 | -0.21968 | -0.25294 | -0.6149 | -0.18128 | -0.6319 | 0.055913 | -0.83538
| 3921 | 0.46737 | -0.60063 | -0.59392 | 0.28425 | 0.35046 | 0.7042 | -0.29212 | 0.45273 | -0.62092 | -0.43493
| 3922 | -0.48299 | 0.0071757 | 0.31611 | 0.2037 | 0.23469 | 0.56838 | -0.048422 | -0.75607 | -0.066994 | 0.41477
| 3923 | -0.06016 | -0.40511 | -0.24297 | 0.5174 | 0.21203 | 0.24389 | -0.15188 | -0.3369 | 0.46083 | -0.7816
| 3924 | -0.18544 | 0.056337 | -0.76484 | 0.018623 | -0.17933 | 0.17072 | -0.25361 | 0.3245 | -0.32628 | -0.2809
| 3925 | -0.26672 | -0.073771 | -0.054114 | 0.25831 | 0.19869 | 0.25 | -0.0047613 | 0.68016 | 0.02722 | 0.33856
| 3926 | -0.20709 | -0.36937 | 0.56216 | 0.09033 | -0.2313 | 0.55245 | -0.60949 | -0.25912 | -0.56216 | -0.48746
| 3927 | 0.65809 | -0.44547 | 0.067959 | -0.52052 | -0.28257 | 0.16651 | 0.0076795 | -0.53621 | 0.49315 | -0.5015
| 3928 | 0.57023 | 0.29339 | 0.087476 | -0.063891 | 0.42285 | -0.89091 | -0.00095045 | 0.77131 | -0.23613 | -0.17109
| 3929 | -0.15911 | -0.043078 | -0.28663 | -0.63986 | -0.08649 | 0.60088 | 0.14367 | 0.089121 | -0.24429 | -0.46661
| 3930 | 0.33404 | -0.22987 | -0.68552 | -0.43706 | 0.19247 | 0.066137 | -0.76188 | 0.54185 | 0.12245 | 0.4265
| 3931 | 0.5922 | 0.35914 | 0.18729 | 0.13507 | 0.96127 | 0.52052 | -0.77262 | 0.63986 | 0.57846 | 0.2625
| 3932 | 0.28174 | 0.8467 | -0.11654 | 0.54382 | -0.22392 | -0.58395 | 0.10507 | -0.16723 | 0.20697 | 0.15165
| 3933 | 0.37718 | -0.44782 | -0.44982 | 0.35046 | 0.37992 | 0.068388 | 0.017707 | 0.16603 | 0.12713 | 0.51886
| 3934 | -0.27178 | -0.37254 | 0.25374 | 0.72815 | -0.37064 | -0.63545 | 0.62013 | 0.47057 | 0.62838 | 0.452
| 3935 | -0.36243 | -0.18312 | 0.4776 | 0.088353 | 0.88467 | 0.19483 | -0.25764 | 0.14753 | -0.046952 | 0.20357
| 3936 | -0.051791 | 0.087476 | -0.43848 | -0.3372 | -0.007478 | 0.31131 | 0.22896 | -0.067637 | -0.31029 | -0.34969
| 3937 | 0.54098 | 0.54756 | -0.16831 | -0.61568 | 0.34693 | 0.44027 | 0.12725 | -0.3129 | -0.34555 | 0.062183
| 3938 | 0.21063 | 0.3214 | -0.70691 | -0.45732 | -0.36636 | -0.28775 | -0.24125 | 0.51948 | 0.028867 | -0.50594
| 3939 | 0.70083 | -0.38918 | -0.24681 | 0.66103 | -0.16424 | -0.0042591 | 0.35712 | -0.53385 | -0.3419 | 0.012934
| 3940 | -0.77483 | -0.46009 | -0.31116 | -0.13936 | 0.23443 | 0.66519 | -0.63875 | -0.95641 | -0.093523 | -0.29
| 3941 | 0.63903 | -0.95 | 0.011213 | -0.67061 | -0.3148 | -0.58443 | -0.12667 | -0.2823 | 0.76146 | -0.69422
| 3942 | -0.89276 | -0.30279 | -0.67735 | 0.10406 | 0.12074 | 0.10161 | 0.099389 | 0.26808 | -0.22573 | -0.43158
| 3943 | 0.16149 | 0.19446 | 0.82084 | 0.63627 | -0.24734 | -0.060053 | -0.65809 | -0.57397 | 0.040782 | -0.33766
| 3944 | -0.448 | 0.13403 | 0.09022 | -0.011112 | -0.10596 | 0.071184 | 0.033925 | 0.063677 | -0.057185 | -0.027735
| 3945 | -0.40881 | 0.081142 | -0.11518 | -0.14052 | 0.079402 | 0.19831 | -0.23 | 0.26156 | -0.09518 | -0.50695
| 3946 | -0.51225 | -0.3607 | 0.71522 | 0.17072 | -0.65143 | -0.71035 | 0.17641 | 0.41494 | -0.33977 | -0.58903
| 3947 | 0.29466 | -0.76655 | 0.6811 | 0.81265 | 0.39329 | 0.11949 | -0.034961 | 0.31116 | 0.054643 | 0.52576
| 3948 | 0.011617 | 0.27605 | -0.58155 | 0.021276 | -0.62758 | -0.03 | -0.072045 | -0.25334 | 0.70931 | 0.58878
| 3949 | -0.075933 | -0.21063 | -0.010101 | -0.60314 | 0.50837 | 0.22689 | -0.19247 | 0.012022 | 0.094075 | -0.10619
| 3950 | -0.28467 | -0.050737 | 0.34892 | -0.61051 | 0.17302 | -0.39593 | -0.30107 | 0.51348 | 0.29311 | 0.035479
| 3951 | 0.23182 | 0.28621 | -0.21853 | 0.51575 | 0.63353 | 0.54426 | -0.018318 | 0.045484 | 0.03 | 0.34342
| 3952 | -0.19025 | 0.088573 | 0.009798 | 0.43476 | -0.26142 | 0.11304 | 0.91693 | -0.0026535 | -0.046533 | -0.080272
| 3953 | -0.25697 | 0.73789 | 0.15024 | -0.14285 | 0.35463 | 0.43724 | -0.79482 | -0.36984 | 0.56057 | -0.09066
| 3954 | -0.84476 | -0.038387 | 0.40932 | 0.28789 | -0.015673 | 0.40797 | 0.90356 | 0.3369 | -0.22431 | -0.71946
| 3955 | 0.47607 | 0.011617 | 0.043078 | -0.087476 | -0.48338 | 0.51164 | 0.69619 | -0.42078 | 0.0088895 | 0.79975
| 3956 | -0.066458 | 0.09209 | -0.74564 | -0.26468 | 0.60364 | 0.33781 | 0.70931 | 0.21508 | 0.51184 | 0.21776
| 3957 | -0.0057666 | 0.46251 | -0.036413 | 0.13519 | 0.023322 | -0.22444 | -0.75648 | -0.15224 | -0.46344 | -0.77044
| 3958 | 0.74251 | 0.84348 | 0.12108 | -0.054643 | 0.48609 | -0.031754 | 0.13127 | 0.40949 | 0.075716 | 0.24614
| 3959 | 0.68204 | -0.33149 | 0.17362 | 0.84736 | -0.12713 | -0.71208 | -0.071938 | -0.12519 | 0.098612 | -0.28719
| 3960 | 0.092641 | 0.19682 | 0.70623 | 0.34342 | 0.080163 | 0.37542 | 0.15306 | -0.5959 | 0.74564 | -0.054537
| 3961 | -0.36921 | 0.13346 | 0.17471 | 0.39148 | -0.22974 | -0.6939 | -0.25831 | 0.22624 | -0.079946 | -0.74564
| 3962 | -0.5583 | -0.26237 | -0.50392 | 0.3074 | 0.54514 | 0.22199 | 0.089231 | -0.6637 | 0.65402 | 0.57538
| 3963 | 0.027015 | 0.16892 | -0.51184 | 0.18312 | 0.54756 | 0.31247 | -0.2402 | -0.36841 | 0.12165 | -0.0035563
| 3964 | 0.12393 | 0.5009 | -0.64433 | -0.58636 | -0.50533 | 0.087476 | 0.10832 | 0.54033 | 0.7623 | 0.45475
| 3965 | -0.44782 | 0.053797 | -0.073987 | 0.28049 | 0.044856 | 0.55739 | -0.45622 | -0.061331 | -0.54933 | 0.22598
| 3966 | -0.7076 | -0.038075 | -0.35308 | -0.26727 | 0.28509 | -0.28621 | -0.26345 | -0.25723 | -0.2265 | 0.28817
| 3967 | -0.56491 | 0.13173 | -0.042869 | -0.31043 | -0.23705 | -0.71698 | -0.86621 | 0.13855 | -0.14496 | -0.24389
| 3968 | 0.36368 | 0.41051 | -0.049474 | -0.16687 | -0.66549 | -0.51348 | -0.13034 | 0.074311 | -0.79191 | -0.72197
| 3969 | -0.40662 | -0.32672 | 0.010101 | 0.17399 | 0.19944 | -0.48222 | -0.84412 | -0.79288 | 0.61594 | -0.21942
| 3970 | -0.7245 | 0.19732 | 0.084959 | -0.24191 | 0.13023 | 0.89091 | 0.65722 | 0.13983 | 0.2744 | 0.66044
| 3971 | -0.092311 | -0.44242 | 0.67427 | -0.7492 | 0.85893 | -0.08136 | 0.64631 | 0.79482 | -0.12782 | -0.60113
| 3972 | -0.29765 | 0.25053 | 0.11281 | -0.40427 | -0.71382 | 0.8148 | 0.26345 | 0.44385 | 0.19819 | -0.5883
| 3973 | -0.002453 | 0.43582 | -0.85823 | -0.68968 | 0.81642 | 0.48863 | -0.23928 | -0.0043595 | -0.088792 | 0.11688
| 3974 | -0.38056 | 0.73599 | 0.23 | -0.35401 | -0.79628 | -0.41957 | -0.040052 | 0.77617 | -0.12839 | -0.27096
| 3975 | -0.82308 | 0.2216 | -0.072369 | 0.22676 | 0.16328 | -0.26142 | -0.2924 | 0.48785 | -0.37622 | -0.11722
| 3976 | -0.12599 | 0.37302 | 0.31392 | 0.72378 | -0.79191 | 0.71208 | -0.35758 | 0.26849 | -0.67304 | -0.21725
| 3977 | -0.01344 | -0.70966 | -0.76527 | -0.11858 | 0.13219 | 0.083539 | -0.25993 | 0.41562 | -0.33856 | 0.063357
| 3978 | 0.27951 | -0.46269 | 0.49039 | 0.013643 | -0.18852 | 0.42546 | 0.20395 | 0.09143 | -0.436 | -0.060905
| 3979 | -0.41494 | -0.48629 | -0.63986 | -0.23221 | -0.13692 | 0.030722 | -0.14076 | 0.20937 | 0.34571 | -0.20823
| 3980 | -0.43405 | 0.087805 | 0.44764 | -0.37382 | -0.57257 | 0.61699 | -0.33675 | -0.59196 | -0.30408 | 0.31524
| 3981 | 0.17302 | -0.4471 | -0.11972 | 0.15188 | 0.2948 | -0.25508 | 0.70657 | -0.75 | -0.19173 | 0.42026
| 3982 | 0.20219 | -0.43582 | 0.6939 | -0.009697 | -0.00055015 | 0.61206 | 0.74722 | 0.20056 | 0.023424 | -0.69718
| 3983 | 0.71982 | -0.010505 | -0.69 | -0.64209 | -0.5866 | 0.37783 | -0.21981 | -0.03 | 0.089451 | 0.038803
| 3984 | 0.47837 | 0.13739 | -0.3214 | -0.47531 | -0.60898 | -0.30394 | -0.52619 | -0.47284 | -0.10518 | 0.083539
| 3985 | 0.248 | -0.054537 | -0.60088 | 0.2496 | -0.10507 | -0.41802 | 0.11575 | 0.348 | -0.045904 | -0.19545
| 3986 | 0.79975 | -0.34205 | -0.55514 | 0.65057 | -0.93917 | -0.16747 | 0.47303 | -0.099278 | 0.28271 | 0.26318
| 3987 | 0.2476 | -0.42078 | -0.70657 | 0.31174 | -0.30855 | -0.44206 | 0.90151 | -0.36086 | -0.76569 | 0.16831
| 3988 | 0.044542 | 0.79531 | -0.32243 | -0.84094 | -0.31553 | -0.36541 | -0.80328 | -0.14076 | 0.099056 | 0.48785
| 3989 | -0.6939 | -0.61594 | -0.074527 | 0.12313 | 0.38755 | 0.27192 | -0.72705 | -0.68393 | -0.46474 | 0.28691
| 3990 | -0.036828 | -0.06753 | -0.76399 | -0.09121 | 0.17435 | -0.23143 | 0.067745 | -0.15614 | -0.3214 | -0.092862
| 3991 | -0.35262 | -0.4857 | 0.014556 | 0.48357 | -0.078859 | 0.30293 | -0.042555 | -0.65489 | 0.45036 | 0.10094
| 3992 | -0.58347 | 0.36731 | -0.10697 | 0.50695 | 0.0039578 | -0.14578 | 0.24681 | 0.24416 | -0.31495 | -0.23901
| 3993 | -0.08967 | -0.077991 | -0.59049 | 0.065816 | 0.031238 | -0.059628 | 0.23574 | 0.31495 | 0.32598 | 0.25804
| 3994 | -0.59073 | 0.24787 | -0.87876 | -0.28188 | -0.08967 | -0.81265 | -0.47208 | 0.42912 | 0.48668 | -0.034443
| 3995 | 0.12336 | 0.059734 | 0.34235 | -0.15994 | -0.77218 | -0.31904 | -0.65373 | -0.31305 | -0.42043 | 0.075392
| 3996 | 0.085396 | -0.55111 | 0.24734 | -0.24907 | 0.42615 | 0.038075 | 0.68141 | -0.23247 | 0.048527 | -0.34525
| 3997 | 0.16868 | 0.29879 | 0.05348 | 0.43777 | -0.23299 | -0.19471 | 0.065388 | -0.078751 | -0.63792 | -0.69227
| 3998 | 0.039948 | -0.12131 | -0.3363 | -0.41085 | 0.52555 | -0.14017 | -0.25643 | 0.28104 | -0.70521 | -0.50371
| 3999 | 0.52957 | 0.77617 | 0.80176 | -0.20937 | -0.5436 | -0.19124 | -0.17811 | 0.14064 | 0.5021 | 0.12097
| 4000 | -0.37734 | 0.092311 | -0.6241 | 0.79191 | 0.13808 | 0.38755 | 0.24244 | -0.55245 | -0.042764 | 0.56537
| 4001 | -0.13173 | -0.67829 | -0.30667 | -0.12313 | -0.14859 | -0.14215 | 0.48067 | -0.016689 | 0.25697 | 0.2941
| 4002 | -0.051053 | -0.13959 | -0.022912 | 0.89753 | -0.67829 | -0.09143 | 0.25926 | 0.33075 | 0.46176 | -0.40125
| 4003 | 0.075068 | 0.67274 | -0.28243 | -0.46232 | -0.065067 | 0.48435 | 0.27591 | 0.45714 | -0.35572 | -0.82536
| 4004 | -0.78669 | -0.73713 | -0.065388 | -0.076582 | -0.31846 | 0.85682 | -0.069463 | 0.31465 | 0.1603 | 0.35494
| 4005 | 0.24987 | -0.25764 | 0.20407 | 0.074959 | -0.2689 | -0.61128 | 0.26617 | 0.04172 | 0.32866 | 0.66819
| 4006 | 0.16675 | -0.88467 | 0.21942 | 0.26631 | -0.13403 | 0.026604 | -0.5436 | 0.60415 | 0.16603 | -0.47971
| 4007 | 0.037347 | -0.30236 | -0.62704 | 0.36008 | 0.33917 | 0.11756 | -0.074527 | 0.55067 | -0.40848 | 0.15188
| 4008 | -0.028867 | -0.66103 | -0.80075 | -0.54338 | 0.71733 | 0.7496 | 0.58515 | -0.30942 | 0.42199 | -0.28285
| 4009 | 0.17471 | 0.76188 | 0.46793 | 0.17386 | -0.57869 | -0.25294 | -0.81862 | 0.20596 | 0.6241 | 0.77131
| 4010 | 0.24947 | -0.7429 | -0.41477 | -0.37478 | -0.56745 | -0.8882 | -0.70794 | -0.50776 | 0.37879 | -0.30351
| 4011 | 0.24853 | -0.29594 | -0.15425 | 0.55022 | -0.019133 | 0.28719 | 0.18361 | 0.88126 | 0.48532 | -0.47322
| 4012 | -0.25107 | 0.13762 | 0.20156 | -0.22754 | -0.39742 | -0.44475 | -0.49552 | 0.68078 | -0.40679 | -0.49493
| 4013 | -0.12977 | 0.26481 | -0.24482 | -0.36526 | 0.34969 | 0.037036 | -0.5883 | -0.87793 | -0.071076 | -0.53989
| 4014 | -0.02322 | -0.19297 | -0.098834 | 0.46887 | 0.39395 | -0.18643 | -0.81106 | -0.3375 | 0.64631 | -0.65868
| 4015 | 0.17799 | -0.03579 | 0.045065 | -0.54756 | 0.4997 | -0.27206 | -0.08649 | 0.034961 | -0.24402 | 0.26007
| 4016 | 0.40042 | -0.56907 | 0.31451 | 0.32302 | -0.61309 | -0.64153 | -0.36164 | -0.08234 | -0.70691 | -0.17909
| 4017 | 0.23052 | -0.65431 | -0.1565 | 0.0866 | -0.34008 | 0.8755 | -0.099944 | -0.24694 | -0.081142 | -0.073016
| 4018 | -0.21419 | -0.84348 | 0.33449 | 0.19198 | 0.62013 | 0.6852 | -0.26932 | -0.12336 | 0.48765 | -0.6338
| 4019 | 0.058777 | -0.039115 | 0.68647 | 0.50918 | 0.18324 | 0.10061 | 0.68425 | 0.21661 | -0.46325 | -0.057185
| 4020 | -0.41 | 0.063891 | 0.13658 | 0.31699 | 0.79336 | -0.053163 | -0.078317 | 0.13692 | 0.37702 | -0.31407
| 4021 | 0.070753 | -0.6697 | -0.19446 | -0.15804 | -0.42129 | 0.66578 | -0.076691 | 0.066137 | 0.19161 | 0.28509
| 4022 | -0.23091 | 0.83059 | 0.03434 | 0.76104 | 0.23967 | -0.49118 | 0.043914 | 0.016893 | 0.40192 | -0.28383
| 4023 | 0.20962 | -0.61438 | -0.13092 | 0.1559 | 0.68711 | -0.13023 | -0.24376 | 0.70862 | -0.030103 | -0.2042
| 4024 | -0.12564 | 0.43141 | -0.66668 | 0.13542 | -0.076691 | 0.40092 | 0.075068 | 0.10809 | 0.18483 | -0.38137
| 4025 | -0.52979 | 0.041825 | -0.82651 | 0.18914 | -0.10496 | 0.71347 | -0.23286 | 0.26495 | 0.3422 | -0.52198
| 4026 | 0.35977 | 0.40209 | -0.52851 | -0.16042 | -0.31655 | 0.20924 | 0.02722 | 0.049263 | -0.19421 | 0.18766
| 4027 | -0.15047 | -0.011213 | -0.10966 | 0.31685 | 0.73942 | -0.25764 | 0.011617 | -0.06197 | 0.1044 | -0.32361
| 4028 | -0.38073 | 0.25227 | 0.0995 | 0.42164 | -0.11259 | 0.0055655 | 0.21942 | 0.035376 | -0.033305 | -0.0020521
| 4029 | -0.42807 | -0.42633 | -0.44619 | -0.43387 | -0.31641 | 0.54404 | -0.011011 | -0.14262 | -0.43831 | -0.18006
| 4030 | -0.7839 | 0.51246 | 0.2216 | -0.0081835 | 0.12885 | 0.26904 | -0.68936 | 0.37239 | 0.036309 | -0.75855
| 4031 | -0.16424 | -0.23757 | 0.20094 | -0.46568 | 0.26727 | -0.63135 | -0.31949 | 0.10072 | -0.23757 | 0.50432
| 4032 | 0.59368 | 0.58684 | 0.075933 | -0.12874 | 0.14812 | 0.26427 | 0.19944 | 0.32007 | 0.48144 | 0.38804
| 4033 | 0.21317 | -0.65663 | -0.45622 | -0.74212 | 0.044542 | -0.69032 | 0.9089 | -0.43317 | 0.31963 | -0.51637
| 4034 | 0.33329 | 0.31685 | -0.11112 | -0.72596 | -0.28845 | 0.73298 | 0.01344 | -0.023424 | -0.35867 | -0.53664
| 4035 | 0.33932 | -0.11541 | 0.11169 | 0.031444 | -0.099278 | -0.30624 | -0.24734 | -0.18092 | -0.43902 | -0.26061
| 4036 | 0.11034 | 0.31934 | 0.24297 | -0.30293 | -0.20307 | -0.10921 | -0.47057 | 0.087366 | -0.061011 | -0.45164
| 4037 | -0.2598 | 0.60138 | 0.29395 | 0.52345 | 0.29537 | -0.13507 | 0.10117 | -0.20911 | 0.25455 | -0.7042
| 4038 | -0.36668 | 0.29736 | -0.61128 | -0.19297 | -0.18226 | 0.76612 | -0.34083 | -0.47227 | 0.17181 | -0.67488
| 4039 | -0.18717 | 0.31728 | 0.1338 | 0.28035 | -0.19421 | -0.075825 | -0.30495 | 0.80739 | 0.12279 | 0.57047
| 4040 | -0.7816 | -0.15661 | 0.12816 | 0.14274 | -0.25508 | 0.071722 | -0.64209 | -0.19136 | -0.099056 | -0.10306
| 4041 | -0.51205 | -0.068603 | -0.22431 | -0.59614 | 0.11101 | -0.037244 | 0.063357 | -0.29694 | -0.083758 | -0.72054
| 4042 | -0.1432 | 0.10764 | -0.70083 | 0.79579 | 0.34403 | 0.92584 | 0.73037 | -0.61672 | 0.29509 | 0.25307
| 4043 | -0.39892 | -0.28188 | -0.082449 | 0.13762 | -0.30236 | -0.94432 | -0.14835 | 0.15685 | 0.28691 | -0.73074
| 4044 | 0.27027 | -0.17338 | 0.43564 | 0.25872 | -0.18263 | -0.32037 | 0.049684 | 0.82196 | 0.23901 | -0.042242
| 4045 | -0.1162 | -0.69065 | 0.14929 | -0.84476 | 0.27882 | 0.36683 | -0.38121 | -0.15982 | -0.026707 | 0.40058
| 4046 | -0.25441 | -0.35432 | 0.55245 | 0.47 | 0.21266 | 0.48941 | -0.15012 | 0.5201 | -0.11146 | 0.018318
| 4047 | 0.23208 | 0.12404 | -0.81697 | 0.023527 | -0.028352 | -0.073124 | 0.055384 | -0.40209 | -0.016486 | 0.34969
| 4048 | -0.72632 | -0.84476 | -0.53128 | 0.058671 | 0.035998 | 0.47607 | 0.73713 | -0.82883 | -0.47019 | -0.33434
| 4049 | -0.5013 | 0.91574 | 0.36368 | -0.51865 | -0.91815 | -0.40209 | 0.48882 | 0.68647 | 0.82365 | 0.13276
| 4050 | 0.059202 | 0.27647 | -0.30957 | -0.32866 | -0.10697 | -0.0023528 | 0.063571 | -0.57798 | -0.49236 | -0.72815
| 4051 | 0.65172 | 0.52936 | -0.25966 | -0.53837 | 0.093854 | 0.3817 | 0.31305 | -0.49532 | 0.32524 | -0.42755
| 4052 | 0.53578 | 0.028043 | 0.14029 | 0.136 | -0.23757 | 0.67427 | -0.11598 | 0.089451 | -0.18815 | -0.18753
| 4053 | 0.7839 | 0.20646 | -0.23351 | -0.75772 | -0.54426 | -0.10552 | 0.18104 | 0.76146 | -0.22598 | -0.16783
| 4054 | 0.01344 | -0.092421 | -0.62304 | -0.41408 | 0.38951 | 0.5015 | -0.016994 | 0.30711 | 0.19185 | -0.63572
| 4055 | 0.048422 | -0.32228 | 0.39444 | 0.38186 | -0.91456 | -0.11259 | -0.053374 | 0.73827 | -0.42233 | -0.77131
| 4056 | -0.011719 | 0.94615 | -0.58878 | -0.29325 | -0.15946 | 0.31495 | -0.38836 | -0.073879 | -0.044123 | 0.016588
| 4057 | -0.34892 | -0.013542 | 0.59269 | 0.0036567 | 0.36086 | -0.50351 | -0.25093 | -0.097393 | 0.42355 | -0.24204
| 4058 | 0.74446 | 0.46344 | 0.21457 | 0.044333 | 0.053797 | -0.55921 | -0.61438 | -0.2621 | 0.81807 | 0.38869
| 4059 | -0.25656 | 0.41068 | -0.073879 | -0.5469 | -0.076366 | 0.35494 | 0.58491 | 0.43105 | -0.26115 | -0.64602
| 4060 | -0.69259 | -0.5866 | 0.47379 | -0.037555 | -0.13507 | -0.39082 | 0.31978 | -0.19483 | -0.028249 | 0.066887
| 4061 | -0.5529 | -0.5199 | -0.2343 | 0.10899 | -0.55762 | 0.12507 | -0.64829 | -0.05549 | 0.14297 | -0.52136
| 4062 | -0.15082 | 0.33404 | -0.057185 | -0.66044 | -0.04381 | 0.027632 | -0.4898 | 0.10161 | -0.62277 | -0.2567
| 4063 | -0.34693 | 0.61283 | 0.43831 | -0.34266 | 0.1597 | -0.44583 | -0.043391 | -0.12576 | -0.59368 | 0.040052
| 4064 | -0.25455 | -0.77483 | -0.72559 | -0.20119 | -0.5735 | 0.28537 | -0.10552 | 0.63027 | -0.13739 | 0.39378
| 4065 | 0.74841 | -0.14017 | 0.079294 | -0.1418 | 0.83417 | 0.84867 | -0.48415 | 0.088792 | 0.56011 | -0.46568
| 4066 | 0.39213 | -0.061011 | -0.37863 | -0.18655 | -0.081686 | 0.20332 | 0.56308 | -0.09088 | 0.42947 | -0.19012
| 4067 | 0.10284 | 0.86771 | -0.6634 | 0.034029 | -0.2958 | -0.22922 | -0.030619 | 0.011921 | -0.12885 | -0.1091
| 4068 | 0.013136 | -0.53513 | 0.16256 | -0.42147 | 0.073555 | 0.12541 | -0.58708 | -0.79678 | -0.68267 | -0.0048618
| 4069 | -0.20106 | 0.60516 | 0.58708 | -0.025782 | 0.012427 | 0.36778 | 0.50492 | 0.40561 | -0.38348 | -0.050526
| 4070 | 0.11733 | 0.2674 | 0.56034 | -0.14953 | 0.057928 | 0.56468 | -0.38267 | 0.43777 | 0.39676 | 0.73981
| 4071 | -0.52682 | 0.94084 | 0.31685 | 0.23351 | -0.22896 | 0.44638 | 0.23039 | -0.32658 | -0.17605 | 0.28383
| 4072 | -0.11293 | 0.28551 | -0.34418 | 0.17933 | 0.31934 | 0.022401 | 0.072261 | -0.30079 | 0.63958 | 0.51369
| 4073 | 0.020459 | 0.3303 | 0.028043 | -0.7042 | -0.72269 | 0.24747 | 0.0085869 | 0.18569 | 0.21254 | 0.43176
| 4074 | 0.037244 | 0.47303 | 0.034547 | -0.54602 | 0.16388 | -0.52177 | -0.60694 | -0.11202 | 0.050842 | 0.22199
| 4075 | -0.14671 | 0.35665 | 0.43264 | 0.13104 | 0.019643 | -0.18729 | -0.43264 | -0.33149 | -0.73789 | 0.11699
| 4076 | -0.086053 | -0.10061 | 0.31846 | -0.077666 | -0.19223 | 0.37831 | 0.18667 | -0.36321 | 0.20899 | 0.09839
| 4077 | 0.16699 | -0.54712 | -0.0087886 | 0.0041586 | -0.6852 | 0.30365 | -0.48357 | -0.35821 | -0.47284 | 0.11631
| 4078 | -0.7569 | -0.69194 | 0.30423 | -0.15188 | 0.13669 | -0.64971 | -0.90566 | -0.11756 | 0.24376 | -0.75813
| 4079 | -0.68267 | -0.18729 | 0.037347 | 0.011921 | 0.041616 | 0.16675 | -0.02794 | -0.34174 | -0.8882 | 0.39643
| 4080 | 0.61908 | 0.34846 | -0.25764 | 0.14215 | 0.25899 | 0.27495 | 0.50634 | 0.61516 | 0.29736 | 0.22469
| 4081 | 0.31509 | -0.024654 | 0.068711 | -0.54978 | 0.26509 | -0.043601 | 0.15 | 0.35805 | 0.035376 | -0.27868
| 4082 | 0.55875 | -0.011617 | 0.55943 | -0.70217 | 0.48493 | -0.11858 | 0.26101 | 0.32702 | 0.72705 | -0.14589
| 4083 | 0.58805 | -0.2985 | 0.45695 | -0.13346 | -0.0022525 | 0.59122 | 0.27509 | -0.095732 | -0.35961 | -0.0033556
| 4084 | -0.053163 | 0.016384 | -0.12874 | 0.72705 | 0.32658 | 0.33239 | 0.26959 | 0.15236 | -0.23731 | 0.057609
| 4085 | 0.15484 | -0.1559 | 0.25643 | 0.21508 | 0.54933 | -0.5663 | -0.086271 | -0.24244 | -0.80739 | 0.27055
| 4086 | 0.023732 | -0.059309 | 0.55921 | -0.3817 | 0.35278 | 0.20044 | 0.029485 | -0.16496 | -0.72559 | 0.40359
| 4087 | -0.28174 | -0.17 | 0.17096 | -0.17084 | 0.29679 | 0.48357 | 0.37159 | 0.78206 | -0.25281 | -0.43123
| 4088 | 0.35665 | -0.41836 | 0.2809 | 0.21241 | 0.59294 | 0.79925 | -0.47436 | 0.17811 | -0.14812 | 0.45585
| 4089 | -0.21866 | -0.39279 | 0.19707 | 0.16807 | 0.53085 | -0.30899 | -0.43706 | 0.28677 | 0.24072 | -0.13207
| 4090 | -0.30567 | 0.10273 | -0.26904 | 0.17799 | 0.42633 | 0.044542 | -0.46755 | -0.079185 | 0.29836 | 0.068174
| 4091 | 0.86621 | -0.16185 | 0.38008 | -0.041825 | 0.13438 | -0.028661 | -0.11101 | 0.16771 | 0.085943 | 0.009596
| 4092 | 0.093303 | -0.19371 | -0.11699 | -0.20269 | 0.22741 | 0.19235 | -0.069248 | -0.71347 | -0.3297 | 0.39197
| 4093 | -0.059734 | -0.12461 | -0.070538 | 0.42337 | -0.0051633 | -0.12233 | -0.46887 | 0.49552 | 0.49731 | 0.39
| 4094 | -0.42303 | 0.27069 | 0.10843 | 0.072261 | -0.20836 | 0.30957 | 0.34601 | 0.38559 | 0.33045 | -0.043496
| 4095 | 0.13115 | 0.6703 | -0.26686 | -0.26074 | -0.39115 | 0.00095045 | 0.23247 | -0.010606 | 0.78206 | -0.016079
| 4096 | -0.75938 | 0.82479 | -0.08474 | -0.058459 | -0.016079 | 0.18422 | -0.3838 | -0.14742 | -0.26291 | 0.45328
| 4097 | -0.06293 | 0.41187 | 0.57538 | 0.59689 | -0.10039 | 0.20836 | -0.28901 | -0.10552 | -0.38299 | -0.57093
| 4098 | -0.63599 | -0.3015 | 0.64857 | 0.029794 | 0.2225 | -0.016486 | 0.33239 | -0.44116 | -0.36086 | -0.12496
| 4099 | 0.19346 | -0.3167 | -0.25737 | 0.36826 | 0.86771 | -0.32346 | 0.21215 | -0.33254 | -0.16018 | -0.23888
| 4100 | 0.036413 | 0.13774 | 0.69032 | 0.10978 | -0.75322 | 0.22508 | 0.53021 | -0.68016 | 0.05814 | -0.2133
| 4101 | -0.028661 | 0.4232 | -0.1926 | 0.093192 | 0.61438 | 0.36447 | -0.45292 | -0.22456 | 0.72341 | -0.21457
| 4102 | -0.21241 | -0.56491 | 0.50392 | -0.64687 | -0.47875 | -0.47722 | 0.40075 | 0.59073 | 0.10373 | -0.026604
| 4103 | 0.56034 | -0.060692 | -0.1803 | 0.70725 | -0.16268 | -0.17241 | -0.019541 | -0.2567 | -0.75485 | -0.91456
| 4104 | -0.59888 | 0.4987 | 0.4993 | -0.28887 | 0.29042 | -0.64659 | 0.83237 | 0.21114 | -0.34296 | -0.33134
| 4105 | -0.29438 | -0.26795 | -0.043601 | 0.16615 | 0.13484 | -0.78858 | 0.21203 | -0.34724 | -0.60974 | 0.46699
| 4106 | 0.7015 | 0.31029 | -0.016689 | -0.2161 | 0.24191 | -0.47284 | -0.092972 | -0.45935 | -0.1179 | 0.06197
| 4107 | 0.11135 | 0.022196 | 0.19433 | -0.06753 | 0.58854 | 0.069677 | 0.62838 | 0.66074 | -0.79727 | 0.59466
| 4108 | 0.448 | -0.12885 | 0.56422 | 0.14929 | 0.13901 | 0.57374 | 0.44116 | -0.16101 | -0.1221 | -0.31218
| 4109 | -0.058353 | -0.0051633 | 0.0064709 | 0.85823 | 0.37879 | -0.52031 | -0.28705 | -0.19495 | -0.15935 | -0.26373
| 4110 | -0.040156 | -0.1513 | 0.73411 | 0.061224 | -0.31714 | -0.76146 | 0.72018 | -0.42129 | 0.23941 | -0.48824
| 4111 | 0.010808 | 0.53235 | 0.16089 | -0.086053 | -0.32896 | 0.0037571 | -0.6995 | 0.5141 | -0.39942 | 0.089121
| 4112 | 0.39066 | -0.41204 | -0.44134 | -0.82084 | 0.096175 | 0.50735 | -0.20269 | -0.093744 | 0.21687 | -0.48357
| 4113 | 0.047792 | -0.2744 | 0.15236 | -0.021276 | 0.092862 | 0.31641 | -0.27827 | 0.39378 | -0.61335 | -0.71911
| 4114 | 0.19049 | 0.56011 | 0.12313 | 0.1015 | -0.63875 | -0.042138 | 0.28691 | -0.055172 | 0.20031 | -0.7496
| 4115 | -0.056973 | -0.31538 | -0.33314 | 0.51307 | 0.4426 | 0.50634 | 0.35 | -0.30021 | 0.025988 | 0.30957
| 4116 | -0.11338 | 0.064639 | -0.059415 | -0.67366 | -0.42633 | -0.19819 | -0.18422 | 0.1565 | 0.83969 | -0.40175
| 4117 | 0.51513 | -0.0063703 | 0.43795 | -0.30913 | 0.47722 | 0.43352 | 0.77751 | -0.1025 | 0.20432 | 0.087366
| 4118 | -0.33015 | -0.26645 | 0.79727 | -0.30567 | -0.36668 | 0.28761 | 0.072908 | -0.33796 | -0.2958 | 0.35185
| 4119 | 0.015165 | 0.31058 | -0.35154 | 0.25013 | 0.29964 | 0.11 | -0.55044 | -0.30236 | 0.28663 | 0.35634
| 4120 | -0.056231 | -0.049579 | -0.45456 | 0.35977 | -0.57491 | -0.085943 | 0.73373 | 0.79095 | -0.51948 | -0.027426
| 4121 | -0.35758 | 0.038387 | -0.67643 | 0.26427 | -0.1245 | -0.31 | 0.20886 | -0.083758 | 0.25993 | -0.18043
| 4122 | -0.51307 | -0.85682 | -0.27868 | 0.62145 | -0.44964 | -0.5412 | 0.10028 | 0.026296 | 0.13669 | -0.25777
| 4123 | -0.26264 | -0.0078811 | 0.57751 | -0.30122 | 0.46176 | -0.077991 | -0.0025533 | -0.12747 | 0.080707 | -0.68711
| 4124 | 0.22754 | 0.24204 | -0.29183 | -0.023424 | 0.45806 | 0.30093 | 0.11586 | 0.44277 | 0.10418 | 0.66074
| 4125 | -0.51082 | 0.15425 | -0.37478 | -0.47645 | -0.015571 | -0.4293 | -0.075392 | 0.15768 | -0.0023528 | 0.54778
| 4126 | -0.24429 | -0.44421 | -0.12142 | -0.18877 | 0.27771 | -0.097171 | 0.42285 | 0.29495 | 0.1797 | -0.21101
| 4127 | 0.2975 | 0.55717 | 0.20194 | 0.028249 | 0.62198 | -0.2985 | -0.25737 | 0.47798 | -0.34617 | 0.19819
| 4128 | 0.68361 | 0.71208 | 0.40343 | 0.7429 | -0.44855 | -0.236 | -0.17121 | -0.6162 | 0.084522 | -0.016283
| 4129 | -0.44063 | 0.099944 | -0.34388 | 0.49177 | 0.023936 | 0.089012 | 0.52915 | -0.35154 | 0.46456 | 0.5347
| 4130 | -0.55966 | 0.28495 | -0.36384 | -0.87155 | 0.30451 | 0.6382 | 0.096285 | 0.31846 | 0.5001 | 0.025269
| 4131 | 0.34693 | -0.20395 | -0.56907 | 0.11564 | -0.18471 | -0.3422 | -0.30797 | 0.019745 | 0.16232 | 0.43742
| 4132 | -0.74368 | 0.74485 | 0.012123 | -0.12862 | -0.51823 | -0.23104 | -0.8956 | -0.31174 | 0.028352 | -0.29042
| 4133 | -0.79678 | -0.18557 | -0.11484 | 0.41528 | 0.68425 | 0.18729 | 0.24151 | -0.23078 | 0.15958 | -0.80895
| 4134 | 0.69751 | 0.16603 | -0.20081 | -0.50857 | 0.20156 | -0.3751 | 0.31014 | 0.054749 | 0.55357 | -0.23456
| 4135 | 0.27578 | 0.018114 | -0.68711 | 0.77617 | 0.021685 | 0.31802 | -0.53686 | -0.2975 | 0.72632 | 0.083976
| 4136 | -0.10473 | 0.48144 | -0.11801 | -0.19844 | -0.2052 | -0.0085869 | -0.28035 | -0.012123 | 0.52282 | -0.51
| 4137 | -0.53902 | 0.78716 | 0.17374 | 0.5469 | -0.37799 | 0.078968 | -0.073231 | -0.74368 | -0.12874 | -0.053691
| 4138 | -0.76741 | -0.67735 | -0.094848 | 0.27041 | -0.32317 | -0.53256 | 0.19446 | 0.5583 | -0.52345 | -0.30899
| 4139 | -0.73186 | -0.040156 | 0.048317 | -0.45401 | 0.38121 | 0.021174 | 0.61206 | 0.52345 | -0.32317 | 0.1706
| 4140 | 0.49512 | -0.024756 | -0.32346 | -0.21661 | -0.25885 | 0.028455 | 0.38853 | -0.19322 | -0.16976 | 0.89464
| 4141 | -0.24283 | 0.076907 | -0.027632 | 0.39428 | 0.13913 | 0.17399 | -0.4232 | -0.62784 | -0.32747 | -0.22534
| 4142 | 0.16018 | -0.86399 | -0.39859 | -0.073447 | 0.76021 | -0.14402 | 0.5922 | -0.5663 | -0.364 | -0.096617
| 4143 | -0.51184 | 0.019133 | -0.34754 | 0.68361 | 0.61387 | 0.17532 | -0.3961 | 0.1221 | -0.35031 | 0.1884
| 4144 | -0.71911 | 0.79925 | 0.47246 | 0.13774 | -0.008486 | -0.12736 | -0.32125 | 0.19334 | 0.64349 | 0.83417
| 4145 | 0.36905 | 0.22122 | -0.25831 | -0.02722 | 0.016994 | 0.76698 | 0.39759 | 0.44565 | 0.88381 | 0.48454
| 4146 | 0.11045 | 0.50331 | -0.049053 | -0.21025 | 0.2377 | 0.1752 | -0.54404 | -0.34662 | 0.22676 | 0.078208
| 4147 | 0.38608 | 0.83177 | -0.45824 | -0.42251 | 0.096839 | -0.14624 | -0.35031 | -0.66429 | 0.00095045 | 0.18975
| 4148 | -0.087147 | 0.29495 | -0.13438 | 0.47741 | -0.024039 | -0.61077 | -0.01182 | -0.19994 | 0.074311 | -0.4995
| 4149 | -0.79239 | 0.66879 | -0.23901 | -0.50573 | -0.1926 | 0.18287 | -0.46121 | -0.27398 | -0.42982 | 0.76146
| 4150 | 0.31392 | 0.24827 | 0.64744 | -0.70017 | -0.067208 | -0.53946 | 0.10261 | 0.23888 | 0.060266 | -0.18238
| 4151 | -0.47741 | 0.43476 | 0.27302 | 0.0075787 | -0.20937 | -0.0077803 | 0.73149 | 0.35789 | -0.047687 | -0.45917
| 4152 | -0.49236 | -0.35665 | 0.13322 | 0.070968 | -0.049684 | 0.12759 | -0.043287 | 0.24535 | 0.38608 | 0.43053
| 4153 | 0.57397 | 0.15389 | 0.02794 | -0.06165 | -0.58539 | -0.15923 | 0.32406 | 0.026809 | 0.059521 | -0.10072
| 4154 | 0.16412 | 0.30021 | 0.11654 | -0.042451 | -0.079946 | -0.67243 | 0.63299 | -0.42095 | 0.32228 | -0.26318
| 4155 | -0.11586 | -0.74643 | -0.1025 | -0.21368 | 0.25147 | 0.33675 | 0.59963 | -0.28677 | -0.23836 | -0.19831
| 4156 | -0.12793 | -0.23783 | 0.50735 | -0.18914 | 0.17508 | -0.91112 | -0.34388 | -0.06293 | -0.39115 | -0.26264
| 4157 | 0.32509 | 0.86252 | 0.014657 | -0.56884 | -0.10206 | -0.21254 | 0.23482 | -0.48396 | -0.37734 | -0.23744
| 4158 | 0.56285 | -0.046638 | 0.50857 | -0.057185 | -0.81426 | 0.34479 | -0.70285 | -0.31597 | 0.37895 | 0.57374
| 4159 | -0.16006 | 0.54207 | 0.28705 | 0.1565 | -0.39908 | 0.1559 | 0.09011 | 0.1382 | 0.39825 | -0.98268
| 4160 | -0.55379 | -0.15094 | 0.5735 | -0.25307 | -0.39892 | 0.12279 | -0.41596 | -0.087805 | -0.64857 | 0.6118
| 4161 | 0.43018 | 0.23456 | -0.19433 | 0.52936 | -0.3309 | 0.15602 | -0.88381 | 0.80379 | -0.31963 | -0.65
| 4162 | 0.36133 | -0.44116 | 0.10876 | -0.84867 | -0.60314 | 0.011213 | 0.11518 | 0.6637 | 0.68016 | 0.29608
| 4163 | 0.81642 | 0.15733 | -0.039011 | -0.46269 | -0.60872 | 0.15448 | 0.27619 | -0.26672 | 0.14706 | 0.80481
| 4164 | -0.26007 | -0.36384 | 0.037555 | -0.32643 | 0.050737 | 0.28691 | -0.24947 | -0.21559 | -0.85269 | 0.86472
| 4165 | 0.6631 | -0.1646 | 0.11135 | -0.066565 | -0.27674 | -0.42337 | -0.038283 | 0.22186 | 0.13484 | 0.35154
| 4166 | 0.36683 | 0.0077803 | -0.080598 | 0.33419 | -0.50594 | -0.10675 | -0.026604 | 0.84157 | -0.43955 | -0.48164
| 4167 | -0.26973 | -0.25845 | -0.037555 | -0.20949 | 0.36604 | 0.06325 | -0.3303 | -0.080272 | -0.60617 | -0.011314
| 4168 | 0.35945 | -0.051369 | 0.28719 | 0.12473 | 0.31714 | -0.25374 | -0.58131 | 0.62784 | -0.56239 | -0.012326
| 4169 | -0.55044 | -0.80328 | -0.32539 | -0.66549 | 0.28733 | -0.74841 | -0.31685 | -0.40494 | -0.11575 | 0.83845
| 4170 | -0.39759 | -0.24601 | -0.44692 | 0.0015512 | -0.4553 | -0.252 | 0.53664 | -0.41716 | 0.016791 | 0.017605
| 4171 | 0.16856 | 0.43991 | -0.52177 | 0.12656 | 0.34678 | -0.84094 | -0.3923 | -0.42424 | 0.24654 | 0.60314
| 4172 | -0.13473 | -0.62758 | -0.65751 | 0.2076 | 0.61206 | 0.4272 | -0.90673 | -0.28188 | -0.074419 | 0.017096
| 4173 | 0.43831 | -0.46568 | 0.39197 | -0.25441 | 0.43105 | 0.44601 | -0.39066 | 0.62838 | 0.052952 | -0.48512
| 4174 | 0.5693 | -0.3767 | 0.60238 | 0.85964 | -0.26183 | -0.48376 | -0.20432 | 0.14859 | -0.56331 | -0.032581
| 4175 | 0.52936 | -0.063464 | -0.61438 | -0.15024 | -0.40898 | -0.77395 | 0.68871 | 0.09176 | -0.34448 | 0.42216
| 4176 | -0.28495 | -0.43229 | 0.24469 | 0.026604 | -0.23091 | -0.23626 | -0.44313 | 0.22676 | -0.13913 | 0.76442
| 4177 | 0.11259 | 0.053163 | 0.83237 | 0.48941 | -0.14531 | 0.21942 | 0.36337 | 0.1863 | -0.49731 | -0.31904
| 4178 | -0.52513 | -0.047897 | -0.082994 | 0.22225 | -0.39494 | -0.008486 | -0.72125 | -0.064532 | -0.12633 | 0.073447
| 4179 | -0.52366 | 0.10228 | -0.047267 | 0.019337 | -0.11473 | 0.08474 | 0.70318 | -0.10686 | 0.11496 | 0.31538
| 4180 | 0.62811 | 0.59863 | -0.78068 | -0.20785 | 0.087695 | -0.24508 | 0.42181 | 0.11214 | -0.66015 | 0.57941
| 4181 | -0.073663 | 0.033098 | -0.62463 | 0.062717 | -0.0781 | -0.14041 | -0.80379 | -0.10641 | 0.24987 | 0.23351
| 4182 | 0.28383 | 0.21139 | -0.34831 | -0.352 | -0.45493 | -0.81426 | -0.022503 | 0.19322 | -0.48318 | 0.3148
| 4183 | 0.1025 | -0.043287 | 0.00025003 | 0.010404 | 0.46624 | 0.084304 | 0.11022 | -0.21406 | 0.075176 | 0.44188
| 4184 | 0.54338 | 0.070753 | 0.14824 | 0.18446 | 0.033201 | 0.26617 | -0.54536 | -0.80025 | -0.029176 | 0.34846
| 4185 | 0.19744 | 0.098279 | -0.33374 | 0.17592 | -0.79239 | -0.37574 | 0.1237 | 0.65547 | -0.35587 | 0.62092
| 4186 | 0.55379 | -0.10017 | -0.14742 | -0.31685 | -0.86923 | 0.26795 | 0.36494 | -0.28341 | 0.67061 | -0.40276
| 4187 | 0.16089 | -0.09077 | 0.0030547 | 0.63572 | -0.16006 | -0.20181 | -0.1382 | -0.60846 | 0.22225 | 0.37143
| 4188 | -0.22263 | 0.364 | -0.066994 | 0.41068 | -0.11552 | -0.18741 | -0.37079 | 0.075825 | 0.34099 | -0.15519
| 4189 | 0.021174 | 0.47607 | -0.30696 | 0.23954 | -0.59122 | -0.01486 | -0.10809 | 0.21241 | -0.89183 | 0.25535
| 4190 | -0.36055 | -0.22573 | 0.19458 | -0.29056 | -0.11575 | 0.67121 | 0.1015 | -0.011112 | -0.28285 | -0.72926
| 4191 | 0.43 | 0.10061 | 0.31538 | 0.24086 | 0.57233 | 0.35046 | 0.088573 | -0.21814 | 0.37127 | 0.50675
| 4192 | 0.17386 | 0.007478 | 0.016079 | 0.32346 | 0.36243 | -0.42355 | -0.48961 | 0.85823 | -0.069033 | 0.29296
| 4193 | 0.51123 | 0.098723 | -0.038595 | 0.9078 | -0.41785 | 0.38804 | 0.22611 | 0.48824 | -0.043914 | 0.77887
| 4194 | -0.28831 | -0.036724 | 0.15531 | -0.34327 | -0.29268 | 0.25254 | 0.047162 | -0.45493 | 0.32081 | -0.23299
| 4195 | 0.086271 | -0.05814 | 0.77841 | 0.30365 | -0.62304 | 0.29822 | -0.020766 | -0.12908 | -0.080272 | -0.23169
| 4196 | 0.7076 | -0.1775 | -0.2402 | 0.16759 | 0.34038 | -0.16244 | -0.35247 | 0.27178 | 0.93292 | -0.028352
| 4197 | -0.060798 | -0.23325 | -0.53621 | 0.066994 | 0.70794 | 0.59 | -0.039948 | 0.019643 | -0.54624 | 0.45347
| 4198 | 0.042138 | -0.34647 | 0.34877 | -0.37976 | 0.13127 | -0.42598 | -0.19396 | 0.54889 | -0.29113 | 0.1603
| 4199 | -0.49592 | 0.011314 | -0.25 | -0.24376 | -0.5143 | -0.013947 | 0.36841 | 0.47779 | 0.47303 | 0.16412
| 4200 | 0.20546 | -0.50878 | -0.23587 | -0.16244 | 0.20044 | -0.54514 | 0.16916 | -0.452 | -0.019643 | 0.5735
| 4201 | -0.58203 | 0.17775 | -0.23613 | 0.28188 | -0.0050628 | -0.22006 | 0.022606 | 0.68267 | -0.31831 | 0.33194
| 4202 | -0.62811 | -0.31029 | 0.61206 | 0.013339 | 0.25576 | 0.2193 | -0.71875 | -0.063144 | -0.7623 | 0.028661
| 4203 | -0.46643 | 0.46362 | 0.89464 | 0.22444 | -0.064318 | -0.29822 | 0.62919 | -0.12393 | 0.27316 | -0.1634
| 4204 | 0.2047 | -0.40797 | -0.13994 | -0.14344 | -0.47113 | 0.0922 | 0.22624 | 0.85067 | 0.99 | 0.31174
| 4205 | 0.065816 | 0.9134 | -0.014962 | -0.78023 | 0.026501 | -0.36841 | 0.38056 | 0.69324 | 0.28425 | 0.075716
| 4206 | 0.50392 | 0.24522 | -0.63299 | -0.29438 | 0.29793 | -0.015774 | -0.69619 | -0.52724 | -0.74761 | 0.54033
| 4207 | -0.10529 | 0.43105 | 0.37382 | -0.066673 | -0.63408 | -0.047057 | -0.45898 | -0.047267 | 0.27288 | -0.14006
| 4208 | 0.44188 | -0.078968 | 0.040573 | -0.32911 | 0.0037571 | -0.92584 | 0.50351 | 0.51 | -0.48357 | -0.40292
| 4209 | -0.29594 | 0.023527 | 0.2265 | 0.7184 | 0.18827 | 0.21292 | 0.010202 | -0.4902 | -0.81534 | -0.9005
| 4210 | 0.22598 | -0.41922 | -0.53837 | -0.29339 | -0.53085 | 0.11881 | -0.41 | -0.47151 | -0.59738 | 0.46195
| 4211 | -0.30093 | -0.22754 | 0.43617 | -0.32569 | -0.15236 | 0.73981 | -0.38853 | -0.21266 | 0.15047 | -0.13
| 4212 | 0.22289 | -0.4653 | 0.21393 | -0.56537 | -0.021379 | 0.11146 | 0.00015001 | 0.16868 | 0.67274 | 0.34281
| 4213 | 0.48941 | 0.26713 | -0.48922 | -0.39461 | -0.031341 | -0.42078 | -0.5714 | 0.029485 | 0.11079 | -0.31597
| 4214 | 0.15188 | -0.70862 | -0.41562 | -0.34403 | -0.13519 | 0.71312 | -0.41034 | 0.4902 | 0.77751 | 0.57822
| 4215 | -0.12816 | -0.50452 | -0.02281 | -0.63903 | -0.17314 | -0.41991 | 0.69162 | -0.5283 | 0.32184 | 0.73827
| 4216 | 0.21648 | 0.36384 | -0.49671 | 0.059309 | -0.00085036 | 0.27096 | 0.42112 | -0.08474 | 0.16089 | 0.70017
| 4217 | 0.19173 | 0.24495 | -0.19012 | -0.10083 | 0.36463 | 0.28803 | 0.44547 | -0.38624 | -0.2175 | 0.31846
| 4218 | -0.32169 | -0.023732 | -0.17362 | -0.00075028 | 0.19148 | -0.0079819 | -0.36526 | 0.19198 | -0.34174 | 0.95641
| 4219 | 0.69324 | -0.64125 | -0.067959 | 0.20244 | -0.093413 | -0.39659 | 0.54756 | -0.0052639 | -0.10854 | -0.81642
| 4220 | 0.18238 | -0.37526 | -0.20546 | -0.22547 | 0.41255 | 0.23338 | -0.55966 | -0.059415 | 0.5224 | 0.64489
| 4221 | 0.072692 | 0.80791 | -0.14636 | -0.1868 | -0.45603 | 0.43035 | 0.61542 | -0.65201 | -0.67798 | -0.68393
| 4222 | 0.095732 | -0.19173 | -0.80843 | -0.5332 | -0.65605 | 0.80025 | -0.55022 | 0.0075787 | 0.73486 | 0.14683
| 4223 | 0.18092 | -0.25067 | 0.45677 | 0.44063 | 0.021481 | 0.43334 | -0.026193 | -0.21381 | -0.22032 | 0.18201
| 4224 | -0.28775 | -0.11214 | 0.28593 | 0.66698 | -0.09099 | 0.25013 | -0.39593 | -0.085506 | -0.67766 | 0.3629
| 4225 | -0.71417 | -0.32524 | -0.57397 | -0.57656 | -0.74564 | 0.5721 | -0.1261 | -0.082667 | 0.57444 | 0.47132
| 4226 | -0.023424 | 0.40544 | -0.2398 | -0.5707 | 0.47684 | -0.54033 | -0.32791 | -0.52957 | 0.43795 | -0.031857
| 4227 | -0.67152 | 0.22767 | -0.35169 | -0.0173 | 0.80328 | 0.44855 | -0.098834 | 0.41187 | -0.47265 | -0.79239
| 4228 | -0.71592 | -0.32985 | 0.60263 | 0.85543 | -0.47208 | -0.30351 | 0.32836 | -0.78858 | -0.44063 | 0.23221
| 4229 | 0.10619 | 0.36305 | -0.052846 | -0.13415 | -0.95 | 0.93292 | -0.51041 | 0.58708 | 0.40209 | -0.24814
| 4230 | 0.066994 | -0.60163 | -0.1868 | -0.086709 | 0.0012508 | -0.63462 | -0.36117 | 0.18287 | 0.028146 | 0.75772
| 4231 | 0.46344 | 0.39395 | -0.61 | -0.56745 | -0.066887 | 0.58491 | -0.52851 | 0.40763 | -0.5003 | 0.0922
| 4232 | -0.1204 | -0.64659 | 0.19956 | -0.44601 | -0.16507 | 0.28299 | -0.27938 | 0.34053 | -0.65229 | -0.58467
| 4233 | -0.33585 | 0.33705 | 0.5608 | 0.74603 | 0.039323 | -0.54185 | 0.026809 | -0.34632 | 0.05984 | -0.30466
| 4234 | 0.073124 | 0.79336 | -0.50735 | -0.29268 | -0.28174 | -0.69983 | 0.12851 | 0.552 | -0.15661 | -0.13484
| 4235 | -0.37992 | 0.13496 | -0.61387 | 0.51348 | 0.13924 | -0.21165 | -0.37847 | -0.23156 | -0.50231 | -0.70117
| 4236 | 0.18508 | 0.57869 | -0.41153 | 0.20798 | -0.47132 | 0.29551 | 0.070753 | 0.51287 | 0.56745 | -0.047582
| 4237 | -0.85201 | -0.076041 | 0.21266 | 0.094296 | 0.16988 | -0.26767 | 0.022401 | 0.09132 | -0.14332 | 0.034443
| 4238 | -0.38689 | -0.070323 | 0.72305 | -0.1634 | 0.053374 | 0.3681 | -0.43246 | 0.83237 | -0.2161 | 0.5436
| 4239 | 0.4265 | -0.27055 | 0.42842 | -0.53989 | 0.2504 | -0.2278 | -0.46587 | 0.15721 | -0.95417 | -0.45732
| 4240 | 0.00085036 | 0.50452 | 0.67152 | 0.017096 | -0.13832 | 0.26686 | 0.20924 | -0.079837 | -0.075068 | -0.41665
| 4241 | -0.46288 | -0.53578 | 0.33977 | 0.63163 | 0.41545 | 0.82708 | -0.042869 | -0.38771 | 0.60263 | 0.18079
| 4242 | 0.15106 | -0.07043 | 0.14683 | -0.0052639 | 0.42982 | 0.81212 | -0.13855 | -0.48941 | -0.27495 | -0.25027
| 4243 | 0.55156 | -0.14718 | -0.25227 | 0.052635 | 0.11972 | -0.80895 | 0.018929 | -0.15911 | -0.5707 | 0.26454
| 4244 | -0.60516 | -0.0035563 | 0.30783 | -0.067423 | 0.18594 | 0.19694 | -0.10507 | 0.98268 | 0.13948 | 0.8739
| 4245 | -0.88909 | 0.69455 | -0.036932 | 0.43511 | -0.0011507 | 0.24178 | 0.23208 | -0.011719 | 0.47398 | -0.62517
| 4246 | -0.12279 | 0.08967 | -0.092751 | -0.10955 | 0.35821 | 0.6407 | -0.76913 | 0.61672 | -0.19458 | 0.036309
| 4247 | -0.30236 | -0.88642 | -0.35867 | -0.13473 | -0.39676 | -0.055384 | 0.31 | 0.22148 | 0.7496 | -0.4134
| 4248 | 0.27896 | 0.13023 | 0.13866 | -0.045799 | -0.62119 | 0.035065 | 0.32747 | -0.4279 | 0.49552 | -0.032374
| 4249 | -0.3593 | 0.41255 | 0.12908 | -0.70725 | -0.10563 | -0.09132 | 0.05549 | -0.77751 | 0.18741 | -0.24548
| 4250 | 0.25818 | -0.057397 | 0.17036 | -0.24707 | -0.079077 | -0.20056 | 0.61154 | -0.59938 | 0.62357 | 0.13265
| 4251 | -0.21699 | -0.059628 | -0.41204 | -0.51472 | 0.073447 | -0.17957 | 0.76315 | -0.82941 | 0.072261 | -0.037659
| 4252 | 0.56722 | 0.2052 | 0.15744 | 0.44982 | 0.18201 | -0.14157 | 0.63271 | 0.0035563 | 0.54668 | 0.19173
| 4253 | 0.69455 | -0.7687 | -0.12119 | 0.20924 | -0.62811 | 0.83599 | -0.024756 | 0.10966 | -0.030928 | -0.45567
| 4254 | 0.077666 | 0.27041 | -0.41425 | 0.19148 | -0.3864 | 0.0018517 | -0.10832 | 0.029588 | -0.11315 | -0.52851
| 4255 | 0.14297 | -0.33735 | -0.37847 | -0.29523 | -0.69817 | -0.68078 | -0.88042 | -0.8467 | -0.0044599 | -0.31582
| 4256 | 0.25589 | -0.10028 | 0.088573 | -0.67121 | 0.27233 | -0.18569 | -0.1533 | -0.076366 | -0.16197 | -0.41204
| 4257 | -0.55089 | 0.2958 | 0.22379 | -0.19012 | 0.3186 | 0.94432 | -0.54646 | -0.023936 | -0.51637 | -0.56171
| 4258 | 0.30567 | 0.0755 | -0.18914 | 0.11293 | 0.10843 | -0.18079 | 0.1425 | 0.06914 | -0.26959 | -0.27757
| 4259 | 0.3375 | -0.43193 | -0.38885 | -0.22058 | 0.39643 | 0.087038 | 0.27633 | -0.18214 | -0.033718 | -0.071399
| 4260 | -0.059521 | -0.38771 | -0.10128 | 0.34525 | -0.1688 | -0.047372 | -0.20069 | -0.77796 | 0.13843 | -0.097282
| 4261 | 0.34877 | 0.33449 | -0.098945 | 0.46793 | -0.058246 | 0.25347 | -0.30711 | 0.53686 | 0.27357 | -0.63958
| 4262 | 0.16928 | 0.41119 | -0.16723 | 0.020357 | -0.12885 | -0.28523 | 0.012528 | -0.53772 | 0.21981 | -0.036413
| 4263 | -0.18643 | 0.05 | 0.48629 | -0.6349 | -0.12382 | -0.12667 | -0.67427 | -0.41221 | 0.10978 | -0.22315
| 4264 | -0.50553 | 0.24814 | -0.42563 | 0.69259 | 0.3662 | 0.13392 | -0.0060684 | 0.63572 | 0.22071 | -0.32628
| 4265 | -0.093634 | -0.49098 | 0.35417 | 0.46587 | -0.2907 | -0.44837 | -0.45493 | 0.077016 | 0.12142 | -0.17483
| 4266 | 0.50452 | -0.21406 | 0.10451 | -0.13034 | -0.053691 | -0.54778 | -0.14507 | -0.36589 | 0.52345 | -0.0028541
| 4267 | 0.37127 | 0.5013 | 0.51886 | 0.22987 | -0.6118 | -0.24138 | 0.40831 | 0.2492 | 0.21 | 0.77751
| 4268 | 0.53837 | -0.14134 | 0.25174 | 0.62811 | -0.23351 | 0.28132 | -0.39975 | -0.11643 | -0.71312 | -0.44098
| 4269 | 0.20937 | -0.35618 | -0.70555 | -0.039531 | -0.39842 | 0.18067 | -0.13623 | -0.057609 | 0.065495 | 0.58012
| 4270 | 0.015673 | 0.32376 | -0.13692 | -0.7184 | -0.22987 | -0.30423 | 0.040469 | 0.57303 | 0.31582 | 0.19682
| 4271 | -0.058034 | -0.21866 | -0.86108 | 0.21101 | -0.43617 | 0.15911 | 0.26631 | 0.30826 | 0.0069743 | 0.68871
| 4272 | 0.56537 | -0.35914 | 0.16783 | -0.14929 | 0.53772 | -0.35743 | 0.1962 | -0.015267 | 0.79384 | 0.044751
| 4273 | -0.36699 | 0.27014 | 0.20483 | -0.56699 | -0.28132 | 0.018623 | 0.59714 | 0.33374 | 0.022401 | -0.49552
| 4274 | 0.12427 | -0.71069 | -0.056761 | 0.56514 | -0.046952 | 0.78114 | -0.59122 | 0.5728 | -0.43653 | -0.20232
| 4275 | -0.045275 | -0.037971 | -0.17811 | 0.024654 | 0.19322 | 0.30639 | -0.027323 | -0.26305 | 0.72161 | 0.26359
| 4276 | 0.76784 | 0.61438 | 0.23169 | -0.057609 | 0.088792 | -0.67704 | 0.50776 | 0.79239 | 0.15863 | -0.042033
| 4277 | -0.68807 | 0.055384 | -0.22199 | -0.59913 | -0.42355 | 0.029588 | -0.13357 | 0.6703 | -0.13808 | 0.54185
| 4278 | 0.65086 | -0.55966 | 0.47684 | -0.013339 | 0.039427 | -0.21533 | -0.25777 | 0.5172 | 0.082013 | -0.45328
| 4279 | 0.52408 | 0.78858 | 0.39395 | 0.1646 | -0.22792 | 0.93755 | -0.47 | -0.09209 | 0.47779 | 0.14367
| 4280 | -0.31102 | 0.5735 | -0.02897 | 0.63326 | -0.46812 | -0.51492 | 0.10106 | -0.11699 | 0.10608 | -0.44313
| 4281 | 0.57774 | -0.40679 | -0.68871 | -0.48241 | 0.081686 | -0.47626 | -0.35046 | 0.55672 | 0.1439 | 0.097947
| 4282 | -0.39378 | -0.39543 | 0.1473 | -0.23234 | 0.71382 | 0.58419 | -0.84031 | -0.87311 | -0.4232 | 0.25401
| 4283 | 0.25468 | 0.72161 | 0.36762 | 0.61594 | -0.65373 | -0.7839 | -0.38885 | -0.28551 | 0.9005 | 0.16448
| 4284 | 0.18263 | 0.35572 | 0.16173 | -0.16352 | 0.025474 | -0.46381 | -0.066565 | 0.30136 | -0.23273 | 0.046218
| 4285 | -0.88381 | -0.27771 | -0.0048618 | 0.045589 | -0.13565 | 0.016283 | -0.21406 | 0.49196 | -0.26536 | 0.18508
| 4286 | 0.47665 | 0.00065021 | 0.80843 | -0.075392 | -0.55312 | -0.65431 | 0.11326 | 0.8995 | -0.26468 | -0.28132
| 4287 | 0.026296 | -0.87311 | -0.31029 | 0.66909 | 0.17036 | -0.77887 | -0.37976 | 0.51389 | -0.3132 | 0.011213
| 4288 | -0.64433 | -0.34083 | 0.060479 | -0.3186 | -0.19869 | -0.39643 | -0.29608 | -0.12931 | 0.045065 | 0.53021
| 4289 | 0.40058 | 0.36794 | 0.039323 | 0.37366 | 0.045694 | -0.6786 | -0.42181 | -0.25508 | -0.61257 | -0.023117
| 4290 | -0.81212 | 0.72632 | -0.24125 | -0.19359 | 0.34954 | 0.41562 | -0.72596 | 0.29155 | -0.055701 | 0.06957
| 4291 | -0.2492 | 0.062397 | 0.62171 | 0.14122 | 0.4258 | -0.075933 | -0.0042591 | -0.63299 | -0.44764 | 0.11564
| 4292 | 0.36447 | 0.79727 | -0.39992 | -0.64829 | -0.22767 | 0.027837 | 0.076149 | -0.084194 | -0.59147 | -0.40108
| 4293 | -0.76957 | 0.38755 | 0.5174 | -0.27661 | 0.47151 | -0.64489 | -0.81318 | 0.10406 | -0.43973 | -0.14519
| 4294 | -0.64237 | -0.30913 | -0.50715 | 0.0072765 | 0.072908 | 0.22212 | 0.18864 | -0.024449 | 0.80947 | -0.20169
| 4295 | 0.04172 | -0.13092 | 0.34083 | -0.53277 | -0.17193 | 0.028867 | 0.09143 | -0.66698 | -0.5017 | -0.36683
| 4296 | 0.36478 | -0.58107 | -0.29722 | 0.67427 | -0.60668 | -0.48902 | 0.4194 | -0.18361 | -0.63163 | -0.23521
| 4297 | 0.080707 | 0.39131 | 0.23469 | 0.2975 | 0.34311 | -0.62119 | -0.1179 | -0.60643 | 0.14683 | -0.39181
| 4298 | -0.37382 | -0.088463 | -0.37686 | -0.45677 | -0.64014 | 0.81917 | 0.3167 | 0.17181 | -0.16388 | 0.032684
| 4299 | -0.3048 | -0.80739 | 0.051897 | -0.34357 | 0.039115 | 0.44982 | -0.50573 | 0.088353 | 0.2524 | 0.34892
| 4300 | -0.10161 | -0.69292 | 0.39775 | -0.28495 | 0.52366 | 0.26631 | -0.28076 | -0.59515 | 0.55335 | 0.44601
| 4301 | -0.14111 | 0.39676 | 0.87155 | -0.80532 | -0.60744 | 0.35992 | -0.12245 | 0.022299 | 0.29424 | 0.69718
| 4302 | -0.1425 | -0.094627 | -0.36305 | -0.21419 | -0.61361 | -0.058459 | -0.23117 | -0.57609 | 0.57538 | -0.10273
| 4303 | -0.28007 | 0.42337 | -0.88554 | -0.31087 | 0.91112 | -0.41699 | -0.6077 | 0.044228 | -0.65373 | -0.26345
| 4304 | 0.010606 | -0.72089 | 0.20044 | -0.10228 | -0.69884 | 0.18018 | -0.27868 | 0.10921 | 0.06678 | 0.10496
| 4305 | 0.25267 | 0.48106 | -0.74368 | 0.34129 | 0.49631 | -0.1389 | -0.05 | 0.19707 | -0.053691 | -0.03434
| 4306 | 0.49374 | 0.38494 | -0.033925 | 0.2326 | 0.59963 | -0.53192 | -0.67304 | 0.23286 | 0.11394 | -0.75566
| 4307 | 0.65316 | -0.032581 | 0.04381 | 0.19 | -0.0046609 | -0.60898 | -0.34846 | 0.25885 | 0.28104 | -0.040677
| 4308 | -0.5007 | -0.074743 | 0.27827 | 0.34099 | -0.26522 | 0.68016 | -0.15839 | -0.11473 | 0.78436 | -0.16856
| 4309 | -0.3245 | 0.055913 | -0.57917 | 0.05549 | 0.3048 | -0.24614 | 0.34586 | 0.086709 | -0.1868 | 0.0035563
| 4310 | -0.063784 | -0.14894 | 0.47038 | -0.85823 | -0.85752 | -0.050105 | -0.65057 | 0.51513 | 0.46812 | 0.22715
| 4311 | 0.11609 | -0.71557 | 0.2076 | -0.094517 | 0.32836 | 0.18594 | 0.4134 | -0.86546 | 0.26836 | 0.20874
| 4312 | 0.4979 | 0.49334 | -0.23286 | 0.20709 | 0.26278 | 0.33134 | 0.33977 | -0.3303 | 0.16723 | -0.70521
| 4313 | 0.29212 | -0.63108 | 0.33404 | -0.052002 | 0.74135 | 0.16759 | -0.1786 | -0.059734 | -0.26142 | -0.39329
| 4314 | 0.26986 | 0.67674 | 0.53128 | -0.022708 | -0.31685 | -0.096285 | -0.93597 | 0.56514 | 0.38089 | -0.71104
| 4315 | 0.17738 | 0.071399 | -0.39461 | 0.59888 | -0.36889 | -0.13588 | 0.20659 | -0.28007 | -0.26318 | -0.032271
| 4316 | 0.020153 | 0.70966 | 0.0781 | 0.53385 | -0.32554 | 0.21853 | 0.88126 | -0.10228 | 0.67 | 0.36274
| 4317 | -0.40763 | -0.084194 | 0.21584 | 0.68047 | -0.13 | -0.58155 | -0.030412 | 0.61803 | 0.4999 | -0.10776
| 4318 | -0.1292 | 0.023424 | 0.44063 | -0.57327 | 0.83845 | 0.73111 | 0.018216 | 0.15602 | 0.25294 | -0.63135
| 4319 | 0.65751 | 0.58179 | -0.48299 | -0.34938 | -0.14285 | 0.23928 | 0.41136 | -0.64744 | -0.1432 | 0.071507
| 4320 | 0.76315 | 0.051475 | 0.8148 | 0.31772 | 0.42026 | 0.49612 | 0.33329 | -0.42164 | 0.84933 | 0.028867
| 4321 | 0.1758 | 0.079077 | 0.53427 | 0.03579 | -0.4344 | -0.11169 | 0.16042 | 0.38218 | 0.40696 | -0.17823
| 4322 | -0.57727 | -0.5436 | -0.041094 | -0.25334 | 0.5015 | 0.90356 | 0.58805 | -0.27771 | -0.24601 | 0.52809
| 4323 | -0.42026 | 0.25361 | 0.23182 | -0.54011 | 0.036932 | 0.43635 | -0.11157 | 0.33419 | -0.40611 | -0.56468
| 4324 | 0.14414 | -0.018012 | 0.1136 | 0.064532 | -0.19458 | 0.17836 | 0.46718 | 0.52136 | -0.63135 | -0.32732
| 4325 | -0.40008 | -0.31363 | -0.26604 | 0.2689 | -0.59664 | -0.13311 | -0.28593 | 0.45018 | -0.83538 | 0.64659
| 4326 | 0.29141 | -0.037867 | 0.10664 | -0.20659 | 0.36715 | -0.23731 | 0.2313 | 0.11011 | -0.20056 | -0.22767
| 4327 | -0.23691 | -0.22109 | -0.080816 | 0.078968 | 0.42251 | 0.099611 | -0.54316 | -0.32628 | 0.49532 | 0.30222
| 4328 | 0.58299 | -0.19794 | 0.59838 | -0.057291 | 0.031341 | 0.42009 | -0.54756 | 0.64209 | -0.17265 | -0.54054
| 4329 | 0.22173 | -0.80584 | -0.34816 | -0.045589 | 0.6697 | -0.21878 | -0.23065 | 0.83477 | 0.20395 | 0.82479
| 4330 | 0.36055 | 0.49236 | -0.1109 | 0.049158 | 0.19062 | 0.70184 | 0.051369 | 0.56653 | -0.30365 | 0.021276
| 4331 | 0.24217 | -0.52324 | -0.12564 | -0.1118 | 0.27426 | -0.47057 | -0.27965 | -0.19099 | 0.58107 | 0.080381
| 4332 | -0.44565 | 0.024756 | -0.29367 | 0.30279 | -0.4828 | 0.16807 | -0.31276 | -0.15744 | 0.26645 | -0.63081
| 4333 | 0.09088 | -0.25 | -0.60846 | -0.1136 | 0.06293 | -0.30538 | 0.2119 | -0.53513 | 0.33962 | -0.48493
| 4334 | 0.6407 | -0.2265 | 0.099056 | 0.13658 | 0.20596 | 0.0050628 | -0.18975 | 0.39098 | 0.11767 | 0.50331
| 4335 | 0.38885 | 0.13983 | 0.31014 | -0.33254 | -0.51886 | -0.23849 | -0.86325 | 0.73261 | -0.23901 | -0.69817
| 4336 | 0.043078 | 0.8739 | 0.32911 | -0.37366 | -0.54668 | 0.50715 | 0.67581 | 0.15792 | 0.028661 | 0.56514
| 4337 | -0.44909 | -0.27481 | 0.11496 | -0.67519 | 0.3961 | 0.0015512 | 0.79239 | 0.12622 | 0.54956 | -0.75
| 4338 | 0.35293 | -0.06496 | 0.1221 | -0.46195 | 0.0076795 | 0.12427 | -0.17884 | 0.15224 | 0.52261 | -0.61309
| 4339 | 0.20056 | -0.72742 | -0.91815 | -0.40042 | -0.48299 | 0.50614 | -0.21904 | -0.22754 | 0.32851 | 0.46121
| 4340 | -0.40025 | 0.43706 | 0.19657 | -0.53299 | -0.6407 | 0.43564 | -0.0040582 | -0.54624 | -0.67152 | 0.28341
| 4341 | -0.049895 | 0.16639 | 0.070323 | 0.057079 | -0.51616 | 0.31963 | 0.5469 | -0.36541 | -0.20646 | 0.4997
| 4342 | 0.15259 | 0.32332 | 0.92319 | -0.47626 | -0.55335 | -0.67519 | -0.23104 | 0.25764 | 0.34938 | -0.60643
| 4343 | -0.41442 | 0.2524 | -0.018725 | -0.23091 | -0.48629 | -0.16964 | 0.46755 | 0.3189 | -0.39643 | 0.060692
| 4344 | -0.55134 | -0.36211 | -0.83297 | -0.24667 | 0.40477 | -0.64829 | -0.079077 | -0.68711 | -0.28188 | -0.34831
| 4345 | 0.0051633 | 0.28873 | 0.066673 | 0.67581 | -0.35883 | 0.63958 | -0.58612 | 0.28593 | 0.18951 | -0.10429
| 4346 | 0.55604 | -0.012123 | 0.35789 | 0.054537 | -0.065281 | -0.010202 | 0.070861 | -0.16066 | -0.026501 | 0.23587
| 4347 | 0.40192 | 0.17072 | 0.53235 | 0.2377 | -0.084304 | -0.40125 | -0.15401 | 0.28146 | -0.55223 | -0.10899
| 4348 | -0.052741 | 0.11994 | 0.79826 | 0.14859 | -0.72018 | -0.23678 | -0.68078 | -0.13023 | -0.64971 | -0.44349
| 4349 | -0.029897 | 0.16856 | -0.077774 | -0.69194 | 0.80687 | -0.044751 | 0.054008 | 0.21279 | 0.20911 | -0.41991
| 4350 | -0.67643 | 0.21661 | -0.53385 | -0.056867 | 0.77932 | -0.33075 | 0.19582 | -0.22844 | -0.63765 | 0.015063
| 4351 | 0.28565 | 0.24376 | 0.10373 | -0.0012508 | 0.36683 | 0.32214 | -0.10328 | 0.26577 | 0.3882 | -0.49137
| 4352 | 0.4117 | -0.76784 | -0.039844 | -0.43281 | -0.27233 | 0.50513 | 0.22482 | -0.019847 | -0.59196 | -0.2958
| 4353 | 0.031031 | -0.39444 | 0.32717 | -0.28733 | -0.072476 | -0.39378 | -0.1109 | -0.34739 | -0.056867 | 0.58539
| 4354 | 0.008486 | -0.68456 | 0.57303 | -0.22715 | 0.45401 | 0.32391 | 0.055066 | -0.45585 | 0.57186 | 0.21878
| 4355 | 0.01842 | 0.45511 | 0.32554 | -0.19235 | 0.57964 | 0.40326 | -0.17823 | 0.12484 | 0.033718 | 0.50251
| 4356 | -0.29993 | -0.1962 | -0.072045 | 0.14414 | -0.044333 | 0.55717 | -0.16916 | 0.54076 | -0.2689 | -0.71208
| 4357 | -0.11711 | -0.33299 | 0.46232 | -0.18348 | 0.35618 | -0.11112 | -0.70318 | -0.020051 | -0.37638 | -0.3186
| 4358 | -0.11847 | 0.19869 | 0.62973 | -0.31029 | 0.15094 | 0.55604 | 0.22392 | 0.39312 | 0.31451 | -0.54338
| 4359 | -0.4828 | -0.55582 | 0.0075787 | -0.4902 | 0.35417 | -0.54142 | 0.37799 | -0.76484 | -0.53707 | -0.25764
| 4360 | -0.34586 | 0.029691 | 0.18201 | 0.39115 | 0.036205 | 0.71982 | -0.33105 | -0.27924 | -0.19632 | -0.052741
| 4361 | -0.34954 | -0.47779 | -0.35712 | 0.11688 | -0.27702 | 0.3422 | 0.16484 | 0.01091 | 0.044228 | 0.21904
| 4362 | -0.24947 | 0.016283 | 0.51061 | 0.42459 | -0.0090913 | 0.085615 | -0.42355 | -0.20886 | -0.45898 | 0.47
| 4363 | 0.53021 | 0.83721 | 0.39643 | -0.54514 | 0.0079819 | -0.55762 | -0.070645 | 0.40042 | 0.60163 | -0.20924
| 4364 | 0.09132 | 0.33284 | -0.56977 | 0.30942 | -0.28958 | 0.38315 | 0.48106 | -0.11405 | 0.009798 | 0.78114
| 4365 | -0.74251 | -0.28021 | 0.80226 | 0.16964 | -0.39875 | -0.79531 | 0.80379 | -0.37944 | 0.62251 | -0.54316
| 4366 | -0.16904 | 0.009899 | 0.58491 | -0.41477 | -0.45677 | 0.35448 | 0.47455 | -0.79095 | -0.17084 | -0.47038
| 4367 | -0.26156 | 0.16256 | 0.0021523 | 0.043601 | 0.32376 | -0.40797 | -0.42615 | 0.29566 | 0.57023 | -0.32524
| 4368 | 0.17145 | 0.43334 | 0.0077803 | -0.70657 | -0.44098 | 0.0062697 | 0.097171 | -0.096175 | -0.54316 | 0.38024
| 4369 | -0.17314 | 0.044542 | 0.42095 | 0.053058 | -0.3366 | 0.71 | -0.72269 | 0.3662 | 0.062717 | -0.60314
| 4370 | -0.67274 | -0.042555 | -0.38706 | -0.63517 | 0.31597 | -0.20432 | -0.18079 | -0.1597 | 0.71522 | 0.2402
| 4371 | -0.15448 | -0.43777 | 0.65345 | 0.3005 | 0.7504 | -0.25589 | 0.28202 | 0.38526 | -0.058246 | 0.46887
| 4372 | -0.34099 | 0.51348 | -0.13034 | 0.1814 | -0.57233 | -0.32465 | 0.10496 | 0.14648 | -0.52597 | 0.16436
| 4373 | 0.54185 | -0.44045 | 0.78023 | 0.64602 | 0.64293 | -0.094627 | -0.34877 | 0.0044599 | -0.054537 | 0.12541
| 4374 | -0.47684 | -0.67643 | -0.019439 | 0.34846 | 0.2755 | -0.24973 | -0.2484 | 0.37016 | 0.13716 | -0.050316
| 4375 | -0.12679 | -0.23156 | -0.39593 | -0.51225 | -0.25053 | -0.1825 | -0.20634 | 0.13415 | -0.77131 | 0.14812
| 4376 | 0.19086 | 0.10083 | 0.69884 | -0.36762 | 0.5201 | -0.027015 | -0.1221 | -0.10384 | 0.15614 | 0.056761
| 4377 | -0.33947 | 0.56583 | 0.26318 | -0.85613 | 0.22883 | 0.093634 | -0.16137 | 0.1153 | 0.36715 | 0.044856
| 4378 | 0.64265 | -0.31102 | -0.20495 | -0.09839 | 0.55245 | 0.68235 | 0.23508 | 0.70017 | 0.26061 | 0.14918
| 4379 | 0.41017 | 0.58587 | -0.083867 | -0.11552 | -0.51699 | -0.80328 | 0.38218 | 0.00015001 | 0.20156 | 0.43352
| 4380 | 0.068388 | 0.28313 | -0.48785 | 0.28174 | 0.077774 | 0.27481 | -0.66819 | 0.17653 | -0.1308 | -0.54011
| 4381 | -0.35899 | 0.013846 | 0.48493 | -0.29637 | -0.25281 | 0.22767 | -0.52576 | 0.4134 | 0.29651 | -0.18569
| 4382 | 0.42372 | -0.21661 | 0.067101 | 0.71769 | -0.074743 | 0.28509 | -0.23182 | 0.77395 | -0.8739 | -0.01791
| 4383 | 0.46474 | -0.436 | -0.91225 | -0.30942 | -0.081795 | -0.28873 | 0.65547 | -0.22676 | -0.14169 | 0.49572
| 4384 | 0.83907 | 0.22974 | 0.39576 | 0.0016514 | -0.29665 | 0.7504 | -0.25899 | 0.061011 | 0.3309 | -0.14297
| 4385 | -0.67704 | -0.31407 | 0.50776 | 0.3357 | 0.44837 | -0.24495 | -0.64181 | -0.11677 | -0.38543 | 0.12427
| 4386 | 0.64631 | -0.14542 | 0.046113 | 0.12667 | -0.2476 | -0.41511 | -0.0021523 | 0.32228 | 0.54076 | 0.55379
| 4387 | -0.71347 | -0.3882 | -0.60188 | 0.22366 | -0.61542 | 0.58757 | 0.33164 | -0.67891 | -0.40746 | 0.53924
| 4388 | 0.51657 | 0.070538 | 0.72018 | 0.31626 | 0.44782 | -0.17048 | -0.16185 | -0.7735 | 0.07962 | -0.8882
| 4389 | -0.58757 | 0.4392 | 0.25267 | 0.50392 | 0.23954 | 0.042973 | 0.10787 | -0.11101 | 0.71452 | -0.29893
| 4390 | 0.35355 | -0.39296 | 0.31131 | -0.46643 | -0.088682 | -0.14542 | -0.44782 | 0.31305 | -0.27371 | 0.79925
| 4391 | 0.61103 | -0.42199 | -0.15389 | -0.28174 | -0.35758 | 0.17665 | 0.41716 | -0.43742 | 0.063144 | 0.49
| 4392 | -0.16268 | 0.4989 | 0.70251 | -0.79288 | 0.36055 | -0.21215 | -0.18312 | 0.032788 | 0.029794 | 0.054537
| 4393 | -0.1118 | 0.10206 | -0.44045 | 0.91938 | 0.21802 | -0.55134 | 0.035065 | -0.32836 | 0.59245 | 0.27082
| 4394 | -0.20621 | -0.25187 | -0.58083 | -0.35961 | -0.73074 | -0.029794 | -0.53085 | 0.7245 | -0.67 | -0.33841
| 4395 | 0.47531 | -0.022503 | 0.048422 | -0.13669 | -0.030309 | 0.14906 | -0.60415 | 0.27426 | 0.55514 | -0.18373
| 4396 | 0.80277 | -0.045589 | -0.29169 | -0.3132 | 0.10641 | -0.15318 | 0.15236 | 0.26034 | 0.37734 | 0.20798
| 4397 | 0.39925 | -0.05984 | -0.59171 | 0.57468 | -0.03465 | 0.77175 | -0.50695 | -0.27247 | -0.36873 | 0.39527
| 4398 | 0.3727 | -0.42476 | -0.39576 | 0.022606 | -0.20924 | 0.085178 | 0.62597 | -0.031754 | -0.32569 | -0.26686
| 4399 | 0.33479 | 0.1926 | -0.16448 | 0.44493 | -0.36368 | 0.18667 | -0.37622 | 0.34831 | -0.37927 | 0.034133
| 4400 | -0.57047 | 0.7512 | -0.052002 | -0.15106 | 0.41716 | -0.3851 | -0.065816 | -0.59368 | -0.48473 | -0.068496
| 4401 | 0.094185 | -0.062397 | 0.15709 | -0.30884 | 0.6249 | -0.027837 | -0.35092 | -0.29395 | 0.79143 | 0.19806
| 4402 | -0.012731 | -0.52513 | 0.50251 | 0.49334 | -0.14076 | 0.13449 | -0.4337 | -0.87155 | 0.088463 | -0.65897
| 4403 | -0.36164 | 0.39362 | 0.17957 | 0.13611 | -0.39197 | -0.029588 | 0.36715 | 0.19545 | -0.52851 | 0.60491
| 4404 | 0.0911 | 0.16964 | 0.068174 | 0.15177 | 0.31978 | -0.057503 | -0.067101 | 0.17326 | 0.11191 | 0.73149
| 4405 | -0.76484 | 0.46009 | 0.022708 | 0.97764 | 0.19533 | -0.36683 | 0.054643 | 0.5693 | -0.14859 | 0.59368
| 4406 | -0.29452 | -0.14309 | 0.38186 | 0.18189 | 0.4683 | -0.35262 | 0.25334 | 0.062717 | 0.16161 | 0.008486
| 4407 | -0.61412 | -0.22456 | -0.28327 | -0.11451 | -0.50817 | 0.60063 | 0.25845 | 0.047687 | -0.36984 | -0.12943
| 4408 | 0.14484 | 0.60465 | -0.82139 | -0.24522 | 0.35 | -0.23691 | -0.1418 | 0.13762 | -0.32687 | -0.35587
| 4409 | 0.37095 | 0.63135 | 0.24747 | -0.055595 | -0.15247 | 0.54229 | 0.1034 | 0.065816 | -0.033512 | -0.16197
| 4410 | 0.26156 | 0.13936 | 0.11473 | 0.30971 | 0.66221 | 0.71522 | -0.3951 | 0.038491 | -0.024244 | -0.49731
| 4411 | 0.46587 | -0.35758 | -0.86696 | 0.15024 | -0.35494 | 0.63081 | 0.32346 | -0.067423 | 0.60744 | 0.054431
| 4412 | -0.64293 | -0.28691 | -0.38967 | 0.4553 | 0.61987 | -0.047897 | -0.046952 | -0.38836 | 0.10742 | 0.21623
| 4413 | -0.068174 | -0.16221 | 0.043287 | 0.04538 | -0.094738 | 0.50918 | 0.019133 | 0.069248 | 0.43088 | -0.28411
| 4414 | -0.28188 | -0.027323 | 0.34266 | 0.23862 | -0.097282 | -0.41238 | -0.09518 | -0.26617 | -0.1803 | 0.34144
| 4415 | -0.06165 | -0.027426 | 0.27647 | -0.64237 | -0.26536 | -0.75938 | 0.18717 | -0.055913 | -0.079185 | 0.065816
| 4416 | -0.44009 | 0.30193 | -0.064212 | 0.0094951 | 0.23091 | 0.39942 | -0.5608 | -0.66879 | 0.020459 | -0.083758
| 4417 | -0.007075 | -0.58179 | -0.52031 | 0.1729 | 0.085396 | -0.32361 | -0.27509 | 0.12656 | 0.61231 | 0.3419
| 4418 | -0.75 | 0.24853 | 0.36921 | 0.037555 | 0.29395 | 0.039219 | 0.54778 | 0.05549 | -0.01415 | -0.14882
| 4419 | 0.15578 | -0.34266 | 0.35977 | 0.0020521 | -0.2823 | 0.49473 | 0.34724 | 0.040886 | 0.77887 | -0.79975
| 4420 | 0.26332 | 0.075068 | 0.16531 | -0.75322 | 0.84476 | -0.12782 | -0.51082 | 0.36196 | 0.24588 | -0.28523
| 4421 | 0.24614 | -0.056761 | 0.34816 | -0.016283 | -0.11225 | 0.21051 | 0.51927 | 0.33479 | -0.00085036 | 0.32866
| 4422 | 0.10787 | 0.055595 | -0.51678 | -0.61154 | -0.35634 | -0.20069 | 0.33449 | 0.66819 | -0.86252 | -0.41648
| 4423 | 0.72596 | -0.037763 | 0.025167 | -0.052319 | 0.41785 | 0.25656 | 0.45438 | -0.21101 | -0.65402 | 0.16555
| 4424 | 0.35696 | 0.23078 | 0.48922 | 0.13739 | 0.41768 | -0.0058672 | 0.56262 | -0.024346 | -0.085615 | -0.42633
| 4425 | -0.48067 | -0.18852 | -0.70386 | 0.11338 | -0.38559 | -0.5283 | -0.24191 | 0.11259 | 0.47436 | -0.67213
| 4426 | 0.33615 | 0.35432 | 0.6077 | 0.4194 | 0.48804 | 0.41579 | -0.42112 | -0.17362 | -0.082122 | 0.080272
| 4427 | -0.049053 | -0.72852 | 0.24681 | 0.24987 | -0.060585 | -0.15071 | 0.6852 | -0.067101 | -0.32791 | 0.016994
| 4428 | -0.72341 | 0.68583 | -0.14414 | -0.29254 | 0.13681 | -0.81106 | 0.74564 | 0.40108 | 0.82883 | -0.23757
| 4429 | 0.15602 | 0.48668 | 0.22974 | 0.017809 | 0.64801 | -0.057397 | 0.77439 | 0.30423 | 0.30581 | -0.23091
| 4430 | 0.43582 | -0.043601 | 0.039844 | -0.029279 | -0.011415 | 0.63654 | -0.11813 | -0.065495 | 0.3759 | -0.036205
| 4431 | -0.34678 | 0.564 | 0.63599 | 0.4902 | -0.60188 | 0.046533 | -0.35618 | 0.077232 | 0.55267 | -0.11248
| 4432 | 0.83 | -0.057185 | 0.02322 | -0.48863 | -0.53513 | 0.47094 | -0.033512 | -0.11315 | 0.79433 | -0.6233
| 4433 | 0.32376 | 0.30164 | 0.32509 | 0.23691 | 0.15012 | -0.30036 | -0.73789 | 0.15828 | 0.6338 | 0.48241
| 4434 | 0.34555 | -0.37574 | -0.74841 | -0.0094951 | 0.011719 | 0.21165 | 0.43511 | 0.63599 | 0.027735 | 0.10017
| 4435 | -0.61387 | -0.20495 | 0.22534 | 0.37334 | -0.35618 | 0.27868 | 0.27854 | -0.083539 | -0.051791 | 0.1758
| 4436 | 0.069892 | -0.3375 | 0.097947 | -0.40696 | -0.61051 | -0.41613 | 0.37079 | -0.26495 | -0.0032553 | -0.072261
| 4437 | -0.59738 | -0.31597 | 0.16663 | -0.32539 | 0.61231 | 0.064212 | -0.070968 | -0.52073 | 0.73111 | 0.24099
| 4438 | -0.27453 | 0.35154 | 0.39875 | 0.49098 | -0.013339 | -0.3211 | 0.17799 | 0.40511 | 0.20672 | -0.076474
| 4439 | 0.4999 | -0.18104 | 0.68488 | 0.41238 | 0.016689 | -0.14742 | -0.027632 | 0.47952 | 0.066351 | -0.50553
| 4440 | -0.27993 | -0.83538 | 0.35665 | 0.072476 | 0.14965 | 0.98268 | -0.017198 | -0.58419 | 0.085178 | 0.19037
| 4441 | 0.61934 | 0.06496 | -0.17157 | 0.32361 | 0.68298 | 0.067423 | -0.014759 | 0.83357 | 0.3061 | -0.51782
| 4442 | -0.09706 | -0.53535 | 0.85474 | -0.071938 | -0.22315 | 0.12313 | -0.62251 | 0.38461 | 0.05899 | -0.61335
| 4443 | 0.17447 | -0.49118 | 0.081686 | -0.24654 | 0.35665 | 0.13878 | 0.039427 | 0.007075 | -0.68235 | 0.92319
| 4444 | -0.26223 | 0.44837 | -0.18938 | -0.39 | -0.063464 | 0.40949 | 0.013744 | 0.17096 | -0.20533 | 0.18692
| 4445 | -0.042242 | -0.46251 | -0.059309 | 0.21942 | 0.045904 | 0.61051 | 0.028146 | 0.050632 | -0.72341 | -0.45585
| 4446 | -0.43105 | -0.17302 | 0.17145 | -0.60592 | -0.59441 | -0.073771 | -0.27412 | -0.16424 | 0.23862 | 0.094959
| 4447 | -0.65897 | 0.015673 | 0.059415 | -0.16018 | -0.24059 | -0.23482 | -0.55089 | 0.39825 | -0.47894 | 0.36478
| 4448 | -0.14262 | 0.29254 | -0.0025533 | 0.30236 | -0.082449 | -0.73751 | 0.019847 | -0.18778 | -0.035376 | -0.18877
| 4449 | 0.5768 | 0.1706 | -0.28817 | -0.42825 | -0.19632 | 0.38202 | 0.54163 | 0.013238 | 0.074635 | 0.43458
| 4450 | -0.09066 | -0.11372 | -0.55627 | 0.18006 | 0.51761 | 0.20722 | -0.37 | 0.086381 | -0.45695 | 0.12839
| 4451 | 0.1162 | 0.36762 | -0.42633 | 0.3961 | 0.25764 | -0.65316 | 0.4344 | 0.54956 | -0.40932 | -0.82766
| 4452 | -0.041512 | 0.042451 | 0.30021 | -0.45806 | -0.49 | 0.39908 | 0.45622 | 0.099611 | -0.016689 | 0.17447
| 4453 | 0.61987 | 0.49256 | 0.70386 | 0.57515 | 0.1513 | -0.3312 | 0.56838 | -0.47856 | -0.10406 | 0.57774
| 4454 | 0.44475 | -0.15792 | -0.42112 | 0.41922 | 0.5768 | 0.38787 | -0.40814 | -0.49334 | -0.18864 | 0.7496
| 4455 | 0.21917 | -0.20874 | -0.10921 | 0.13553 | -0.27868 | -0.18067 | -0.19806 | -0.28035 | -0.18006 | -0.5663
| 4456 | -0.029691 | -0.00025003 | -0.53021 | 0.0173 | 0.055172 | 0.26128 | -0.29694 | 0.81106 | -0.74212 | -0.60415
| 4457 | -0.19173 | 0.59763 | 0.30036 | 0.66429 | -0.52682 | 0.71452 | 0.29028 | 0.1603 | 0.30222 | -0.6833
| 4458 | -0.37446 | -0.90253 | 0.2081 | -0.1546 | 0.055701 | 0.68488 | -0.22276 | 0.27965 | 0.26686 | 0.37751
| 4459 | 0.24561 | 0.039948 | 0.29608 | 0.49275 | -0.043078 | 0.23901 | -0.17568 | -0.061757 | -0.61961 | -0.32317
| 4460 | 0.18901 | 0.24033 | -0.17945 | 0.077016 | -0.63027 | 0.38186 | 0.027735 | 0.25294 | 0.18926 | -0.22844
| 4461 | 0.21674 | 0.21127 | -0.0085869 | -0.14425 | -0.15071 | 0.60163 | 0.37254 | 0.034029 | 0.20294 | -0.23626
| 4462 | 0.40511 | 0.39759 | -0.57491 | -0.16807 | 0.51164 | 0.57941 | -0.35262 | -0.31495 | 0.40746 | 0.3061
| 4463 | -0.25495 | 0.37462 | -0.12097 | 0.58612 | 0.4265 | 0.74407 | -0.14274 | -0.77175 | -0.43317 | 0.099722
| 4464 | 0.58951 | 0.83969 | -0.5412 | -0.030825 | 0.06678 | 0.070645 | 0.11202 | 0.152 | -0.074959 | -0.56977
| 4465 | 0.2377 | 0.31073 | 0.3025 | 0.35727 | 0.63517 | -0.99 | -0.97 | 0.31174 | 0.14589 | -0.29212
| 4466 | 0.19707 | -0.32851 | -0.064746 | 0.26223 | 0.74603 | 0.4206 | 0.04266 | -0.59318 | -0.58299 | 0.51761
| 4467 | 0.54426 | -0.064105 | -0.34969 | -0.12085 | 0.035583 | 0.053269 | 0.82708 | -0.63408 | 0.38234 | -0.082776
| 4468 | -0.37847 | -0.73149 | -0.025577 | 0.024346 | -0.61725 | -0.26047 | -0.11067 | -0.47798 | 0.41991 | -0.22482
| 4469 | -0.64489 | 0.58443 | -0.18988 | -0.60541 | -0.18827 | -0.50412 | 0.53492 | 0.048948 | 0.26454 | 0.14706
| 4470 | -0.11983 | 0.16615 | 0.90673 | 0.12233 | -0.42598 | 0.13704 | -0.12897 | -0.035479 | 0.30337 | 0.27371
| 4471 | 0.42164 | 0.31568 | -0.27896 | 0.53664 | -0.0085869 | -0.64321 | -0.70487 | -0.059521 | 0.14894 | 0.46288
| 4472 | -0.048422 | 0.2225 | -0.17241 | -0.073339 | -0.22611 | 0.40527 | -0.70184 | 0.080707 | -0.5264 | 0.080054
| 4473 | -0.2402 | 0.62784 | 0.22328 | -0.35883 | -0.5469 | -0.23823 | 0.41068 | 0.49374 | -0.57327 | 0.57421
| 4474 | 0.59024 | 0.28104 | 0.50533 | 0.36494 | 0.22611 | 0.21038 | 0.11779 | -0.61387 | -0.38396 | -0.21738
| 4475 | -0.73827 | -0.52366 | 0.17193 | -0.52851 | 0.085506 | -0.24165 | -0.58419 | -0.34938 | 0.93917 | -0.44601
| 4476 | -0.074203 | -0.60719 | -0.28425 | 0.0076795 | -0.15744 | -0.25845 | 0.31949 | -0.19919 | -0.80843 | -0.10328
| 4477 | -0.1473 | -0.57421 | -0.081577 | -0.14134 | -0.52936 | 0.20634 | 0.72632 | -0.57941 | 0.037451 | -0.002453
| 4478 | -0.1439 | -0.10832 | 0.16904 | -0.15946 | -0.075392 | -0.83969 | -0.38984 | -0.19707 | -0.90151 | -0.33105
| 4479 | -0.42668 | -0.6833 | 0.56791 | 0.38869 | 0.38657 | -0.5017 | 0.16531 | -0.59049 | -0.64153 | 0.48941
| 4480 | -0.28509 | -0.71035 | -0.36794 | -0.37751 | -0.63271 | 0.35712 | -0.11405 | -0.36494 | -0.015774 | -0.52619
| 4481 | 0.77617 | 0.75526 | 0.21853 | 0.11518 | 0.16042 | -0.53277 | -0.28243 | 0.083212 | 0.80125 | 0.65
| 4482 | 0.56791 | 0.50756 | -0.2893 | -0.52408 | -0.058353 | -0.12199 | -0.45401 | 0.5412 | 0.12484 | -0.096839
| 4483 | 0.0035563 | -0.20269 | -0.033718 | -0.30725 | -0.48687 | -0.19806 | 0.43973 | 0.46906 | 0.49334 | -0.019235
| 4484 | -0.17909 | 0.12393 | -0.1353 | 0.39942 | -0.12736 | 0.37718 | -0.14765 | 0.42233 | 0.079402 | 0.3451
| 4485 | 0.017096 | 0.53729 | 0.23404 | -0.27014 | -0.27412 | -0.012427 | -0.22909 | -0.41017 | -0.50311 | -0.0911
| 4486 | 0.32762 | -0.36086 | 0.0866 | 0.39908 | 0.36431 | -0.89753 | -0.33344 | 0.0088895 | 0.77306 | -0.72018
| 4487 | -0.35031 | 0.73486 | -0.042973 | -0.20169 | 0.21254 | 0.19446 | 0.83907 | -0.21203 | -0.013339 | 0.077991
| 4488 | -0.12245 | -0.05253 | 0.11801 | -0.53492 | 0.6637 | -0.33464 | 0.0013509 | 0.536 | 0.12782 | 0.44764
| 4489 | 0.13438 | 0.35417 | -0.042033 | -0.23117 | -0.037763 | -0.21228 | -0.15602 | 0.29779 | 0.082231 | -0.27027
| 4490 | 0.38706 | 0.32866 | -0.68141 | 0.7508 | -0.058884 | -0.070538 | 0.085724 | -0.29325 | -0.43 | 0.28355
| 4491 | 0.15638 | 0.0064709 | -0.24535 | -0.67984 | 0.068067 | -0.49612 | 0.039948 | 0.018114 | 0.4564 | -0.46139
| 4492 | -0.31436 | -0.48882 | 0.5768 | 0.58227 | -0.023117 | 0.42772 | -0.059521 | 0.19956 | -0.55089 | -0.2119
| 4493 | -0.064853 | -0.26034 | 0.056761 | -0.24349 | -0.11847 | -0.37159 | -0.26291 | 0.17278 | 0.071291 | 0.3923
| 4494 | 0.60465 | -0.55469 | -0.23626 | -0.047162 | 0.14671 | -0.22624 | 0.17592 | -0.336 | 0.05158 | 0.33389
| 4495 | 0.41819 | -0.33509 | 0.059309 | 0.49631 | 0.81588 | 0.39643 | 0.41391 | 0.092862 | -0.051686 | -0.57163
| 4496 | 0.31145 | 0.73074 | -0.10451 | -0.034961 | -0.056761 | -0.46699 | -0.52471 | 0.65172 | -0.57397 | -0.026809
| 4497 | 0.53492 | -0.11473 | -0.13219 | -0.9134 | 0.47798 | -0.015267 | -0.33585 | -0.52788 | 0.89276 | 0.20659
| 4498 | -0.003155 | 0.30093 | 0.010202 | 0.37542 | -0.48493 | -0.076041 | -0.55357 | -0.33 | 0.3618 | 0.59392
| 4499 | -0.65 | 0.56171 | 0.38494 | 0.049369 | -0.13046 | -0.51906 | 0.30986 | 0.052424 | -0.40443 | 0.9245
| 4500 | 0.44349 | -0.36478 | -0.15318 | -0.021481 | -0.25993 | 0.39098 | -0.29807 | -0.22276 | 0.17629 | 0.87631
| 4501 | 0.91574 | -0.2287 | 0.015165 | -0.27744 | -0.35572 | 0.17362 | -0.5721 | 0.1034 | -0.26074 | 0.13866
| 4502 | -0.21738 | -0.085287 | -0.11938 | 0.30725 | 0.22961 | -0.79875 | -0.14029 | -0.52767 | 0.2076 | -0.36117
| 4503 | -0.64014 | -0.30899 | 0.39461 | 0.24933 | -0.22225 | 0.75607 | -0.13843 | -0.41562 | -0.42912 | 0.72197
| 4504 | -0.071076 | -0.64153 | -0.14402 | 0.094848 | -0.21089 | -0.1353 | 0.35525 | -0.59269 | 0.31174 | 0.19607
| 4505 | 0.038075 | -0.24947 | 0.30639 | -0.54536 | -0.25939 | 0.46456 | 0.63765 | 0.078751 | -0.44656 | 0.536
| 4506 | -0.52282 | -0.0020521 | 0.30812 | -0.18594 | -0.29807 | 0.49256 | 0.39428 | -0.69685 | -0.44009 | 0.015368
| 4507 | 0.43813 | 0.27882 | 0.083321 | -0.14041 | -0.30164 | -0.17012 | 0.50594 | -0.72233 | -0.40983 | -0.76527
| 4508 | 0.60974 | -0.15839 | 0.22987 | -0.64405 | 0.15342 | 0.61594 | -0.20282 | -0.048107 | -0.35774 | 0.12222
| 4509 | 0.49334 | 0.4531 | 0.58419 | -0.6985 | -0.11869 | 0.65897 | -0.14484 | -0.76612 | -0.4293 | 0.3369
| 4510 | 0.33962 | 0.68078 | 0.52979 | -0.019847 | -0.019439 | 0.1879 | -0.60339 | 0.13461 | 0.018929 | -0.37702
| 4511 | 0.61154 | -0.75363 | -0.15377 | -0.76315 | -0.73713 | 0.8937 | 0.48961 | -0.19161 | 0.15342 | 0.21444
| 4512 | -0.21648 | -0.077883 | -0.12461 | 0.35308 | -0.066565 | -0.73599 | -0.20571 | -0.20558 | -0.20395 | -0.27206
| 4513 | -0.59122 | 0.15531 | -0.45603 | 0.77395 | 0.40511 | -0.098834 | -0.45843 | -0.014657 | -0.42181 | 0.3796
| 4514 | 0.075825 | 0.54668 | 0.12644 | 0.29779 | -0.051369 | 0.21406 | 0.26074 | -0.18043 | -0.43141 | 0.39908
| 4515 | 0.54142 | 0.13322 | 0.12393 | -0.14122 | 0.46812 | 0.10295 | -0.59788 | 0.49354 | -0.77528 | 0.040365
| 4516 | 0.76612 | -0.5663 | -0.44601 | -0.19782 | 0.24151 | -0.21853 | 0.35572 | -0.6985 | -0.46232 | 0.57798
| 4517 | 0.8618 | 0.65201 | -0.41255 | 0.65287 | -0.022912 | 0.38396 | -0.6939 | -0.16507 | -0.076041 | 0.31582
| 4518 | 0.065388 | -0.54142 | -0.11552 | -0.16412 | 0.057291 | -0.25428 | -0.67274 | -0.026501 | -0.30567 | -0.69917
| 4519 | -0.76913 | -0.32391 | -0.48415 | 0.3248 | 0.552 | -0.41819 | 0.63326 | 0.032581 | 0.45824 | -0.23495
| 4520 | -0.16844 | -0.10473 | 0.57727 | 0.64097 | -0.43035 | -0.43246 | -0.93755 | -0.16113 | -0.15887 | -0.28313
| 4521 | 0.63737 | 0.39345 | 0.12782 | 0.62973 | 0.016791 | 0.93917 | -0.71946 | 0.6786 | -0.40225 | 0.14204
| 4522 | 0.19769 | 0.35108 | -0.0067729 | 0.0012508 | -0.19247 | 0.056761 | -0.47914 | 0.53277 | -0.47 | 0.036413
| 4523 | -0.0012508 | 0.13392 | 0.51927 | -0.18312 | -0.00065021 | 0.55424 | 0.076366 | -0.030928 | 0.1926 | 0.16292
| 4524 | -0.23299 | 0.40008 | -0.80584 | 0.53085 | 0.31626 | 0.136 | 0.4991 | 0.0173 | 0.19869 | -0.19446
| 4525 | 0.24112 | 0.32037 | -0.70318 | 0.23091 | -0.4542 | -0.037347 | -0.9219 | 0.40915 | 0.22508 | -0.14624
| 4526 | 0.014454 | 0.67766 | -0.20722 | 0.058246 | 0.42372 | -0.12108 | 0.3248 | -0.20395 | -0.27951 | -0.11259
| 4527 | 0.15946 | -0.47132 | -0.28411 | 0.44529 | 0.45493 | 0.35247 | 0.24178 | -0.34678 | -0.35339 | -0.30337
| 4528 | 0.19682 | -0.61856 | 0.73298 | 0.032891 | -0.26686 | -0.5735 | 0.59813 | -0.17544 | 0.56884 | 0.3312
| 4529 | 0.86036 | 0.0058672 | -0.58131 | -0.60694 | 0.29779 | -0.45787 | 0.35618 | 0.20307 | 0.15899 | -0.35417
| 4530 | -0.5141 | 0.51 | -0.33947 | -0.098723 | 0.75 | -0.60567 | 0.55853 | 0.58131 | -0.63848 | 0.061437
| 4531 | 0.30322 | 0.21101 | -0.49354 | 0.4859 | 0.8043 | -0.43529 | -0.57397 | -0.050105 | 0.54316 | -0.66819
| 4532 | 0.044437 | 0.32007 | -0.058884 | -0.43866 | 0.27027 | -0.53729 | -0.27647 | -0.20798 | -0.053797 | -0.81917
| 4533 | -0.30754 | 0.12267 | 0.1277 | 0.30107 | -0.21279 | -0.36921 | 0.082667 | -0.084085 | -0.47626 | -0.35077
| 4534 | -0.46139 | 0.29381 | -0.45898 | 0.62838 | 0.82479 | 0.02794 | 0.37175 | 0.32037 | 0.31029 | 0.1072
| 4535 | -0.23862 | 0.50959 | -0.44909 | -0.17763 | 0.22935 | -0.48067 | -0.10017 | -0.64914 | -0.61829 | 0.30064
| 4536 | 0.16185 | 0.47379 | 0.15059 | -0.24363 | -0.063571 | 0.16376 | 0.037244 | -0.054749 | 0.30523 | -0.094406
| 4537 | -0.64772 | 0.5608 | -0.79531 | -0.70352 | 0.4983 | 0.54536 | 0.29466 | -0.55807 | -0.21076 | 0.14122
| 4538 | 0.42982 | 0.061011 | -0.10731 | 0.35789 | -0.10139 | 0.23783 | -0.63958 | -0.083103 | -0.2343 | 0.017707
| 4539 | 0.39908 | 0.039011 | -0.39345 | -0.51802 | -0.48843 | -0.36762 | 0.39692 | -0.74682 | 0.28355 | 0.20219
| 4540 | -0.65605 | -0.09022 | -0.20785 | 0.017198 | 0.032684 | 0.59838 | -0.046428 | 0.1338 | 0.27813 | 0.15685
| 4541 | 0.34708 | -0.039427 | -0.0035563 | 0.30007 | 0.2326 | 0.60238 | -0.10172 | 0.30122 | 0.13611 | 0.48415
| 4542 | 0.39692 | -0.39181 | 0.23626 | -0.18729 | -0.38918 | 0.35154 | 0.47094 | -0.36889 | -0.53192 | 0.037867
| 4543 | -0.73904 | 0.7245 | 0.12507 | -0.12816 | 0.063464 | -0.1803 | 0.09165 | -0.056549 | 0.54845 | -0.3727
| 4544 | 0.15567 | 0.034961 | -0.74801 | -0.39164 | -0.28411 | 0.39527 | -0.059734 | -0.31378 | 0.73448 | 0.6407
| 4545 | 0.80075 | 0.028764 | 0.12989 | -0.23809 | 0.18446 | 0.10787 | 0.73675 | -0.7076 | -0.45843 | 0.19012
| 4546 | 0.79875 | 0.43423 | -0.034133 | -0.35774 | 0.080272 | -0.40983 | -0.0922 | -0.33811 | 0.27233 | -0.11745
| 4547 | 0.29282 | 0.30337 | 0.03714 | -0.85405 | 0.68936 | -0.11813 | -0.13994 | 0.39049 | 0.039115 | 0.035583
| 4548 | 0.44045 | 0.0083852 | 0.0033556 | -0.087257 | -0.054008 | 0.14425 | -0.39033 | 0.4258 | 0.67213 | -0.94432
| 4549 | -0.19297 | 0.2147 | -0.78344 | 0.39395 | 0.074203 | -0.27041 | 0.0056661 | -0.36715 | 0.13207 | -0.025988
| 4550 | -0.33539 | -0.46065 | 0.027323 | 0.11915 | 0.70083 | 0.35355 | 0.32332 | 0.14894 | 0.3551 | 0.067637
| 4551 | 0.070645 | -0.031651 | -0.24747 | -0.83969 | -0.1005 | -0.67152 | -0.21584 | 0.62119 | -0.3796 | -0.9089
| 4552 | -0.050737 | -0.035479 | -0.26264 | 0.081142 | -0.42877 | -0.93917 | -0.35743 | 0.47741 | -0.30394 | 0.15035
| 4553 | 0.20319 | 0.19669 | -0.44873 | 0.27082 | 0.1389 | -0.34053 | 0.33434 | -0.46699 | 0.23744 | -0.14484
| 4554 | -0.19844 | -0.67704 | -0.037451 | 0.35572 | -0.20672 | 0.53213 | 0.38024 | -0.19657 | 0.94615 | -0.099722
| 4555 | 0.19458 | -0.17605 | -0.4776 | 0.10395 | -0.13011 | -0.68393 | 0.34908 | 0.11022 | 0.47341 | 0.54536
| 4556 | 0.42407 | -0.66819 | 0.17024 | -0.10675 | 0.55044 | 0.086709 | 0.72779 | -0.19284 | 0.91938 | -0.30495
| 4557 | -0.12839 | -0.040469 | 0.44331 | 0.29608 | 0.50452 | -0.29085 | 0.11598 | -0.14414 | -0.20874 | -0.17411
| 4558 | 0.49631 | 0.3454 | -0.47875 | 0.15828 | 0.25281 | 0.013136 | 0.51472 | 0.2161 | 0.3074 | -0.12633
| 4559 | -0.25 | 0.4163 | -0.80125 | 0.15567 | 0.18177 | -0.025167 | -0.86399 | -0.068496 | 0.024039 | 0.043601
| 4560 | 0.15994 | -0.48843 | -0.26359 | 0.023732 | 0.23182 | -0.35108 | 0.18287 | -0.33494 | 0.23456 | 0.74525
| 4561 | 0.21942 | 0.54098 | 0.22857 | -0.27633 | -0.80125 | 0.0022525 | 0.14157 | 0.88042 | -0.36747 | 0.44964
| 4562 | -0.19869 | -0.097725 | -0.20282 | -0.24455 | 0.61128 | 0.33105 | 0.36431 | 0.61908 | 0.79875 | 0.015165
| 4563 | 0.42337 | 0.60923 | 0.30523 | -0.40343 | -0.61516 | -0.17169 | -0.74603 | 0.47284 | 0.564 | -0.22289
| 4564 | -0.083539 | -0.22444 | -0.58951 | 0.17641 | 0.026398 | 0.3061 | 0.16424 | 0.22444 | 0.42285 | -0.64489
| 4565 | 0.63958 | 0.10608 | -0.52408 | -0.9005 | -0.51575 | 0.098501 | 0.045904 | -0.18422 | -0.5922 | -0.16066
| 4566 | 0.9219 | 0.5583 | 0.43991 | 0.30913 | 0.80226 | 0.31949 | -0.068603 | -0.047477 | 0.17799 | -0.0011507
| 4567 | -0.0016514 | -0.23954 | -0.08485 | -0.3751 | -0.34862 | -0.37079 | 0.50392 | -0.12279 | 0.39444 | 0.19099
| 4568 | 0.076799 | 0.74058 | 0.15982 | -0.059415 | 0.18067 | -0.45548 | 0.27674 | 0.21482 | -0.88126 | 0.6371
| 4569 | -0.50331 | -0.44439 | -0.93755 | 0.52115 | 0.14777 | -0.60643 | -0.42755 | -0.10541 | -0.26754 | 0.75363
| 4570 | -0.33075 | -0.15247 | 0.6546 | -0.48222 | -0.46587 | 0.21177 | -0.34372 | -0.58927 | 0.33841 | -0.0037571
| 4571 | -0.38202 | -0.92584 | -0.087366 | 0.21393 | 0.28579 | 0.70217 | 0.20571 | -0.065709 | 0.086053 | -0.26959
| 4572 | 0.11462 | 0.040782 | -0.21635 | 0.35836 | -0.46755 | 0.31189 | 0.46981 | -0.78068 | -0.78529 | -0.73261
| 4573 | 0.55469 | 0.80947 | -0.40427 | -0.8755 | -0.50412 | -0.61516 | -0.20307 | 0.28509 | -0.17447 | 0.21635
| 4574 | 0.15744 | 0.54054 | -0.76063 | -0.047792 | -0.6634 | -0.044961 | 0.38624 | -0.0013509 | 0.071722 | 0.37064
| 4575 | -0.01263 | -0.54867 | -0.26699 | -0.058246 | 0.97764 | 0.66728 | 0.548 | -0.44746 | -0.63054 | -0.58107
| 4576 | -0.024551 | -0.01415 | 0.14566 | -0.13011 | 0.68839 | 0.11214 | 0.48532 | 0.077991 | -0.14847 | 0.003155
| 4577 | -0.23443 | -0.08136 | -0.054855 | -0.018929 | 0.78344 | 0.55785 | 0.12736 | 0.085506 | 0.14648 | -0.19074
| 4578 | -0.1825 | -0.026604 | -0.53556 | 0.25334 | 0.67182 | -0.23286 | 0.24907 | 0.12279 | -0.68743 | -0.68298
| 4579 | -0.11428 | 0.060692 | 0.66668 | 0.11067 | 0.87233 | -0.029176 | -0.17024 | 0.65316 | -0.34708 | -0.32258
| 4580 | 0.1578 | 0.19894 | -0.77175 | -0.41204 | -0.25321 | 0.10989 | -0.82536 | -0.36937 | 0.62277 | -0.60974
| 4581 | 0.19582 | 0.06165 | 0.74564 | 0.5412 | -0.21215 | 0.14507 | -0.06678 | -0.19086 | 0.25576 | 0.10933
| 4582 | -0.28439 | -0.26413 | 0.60719 | 0.20156 | 0.7512 | -0.48473 | -0.032064 | -0.79048 | -0.73524 | -0.01091
| 4583 | -0.15318 | 0.53149 | -0.23104 | 0.11349 | -0.38024 | -0.84801 | -0.42372 | 0.15012 | 0.22032 | -0.58491
| 4584 | -0.41648 | 0.63027 | -0.10362 | -0.4717 | -0.34433 | -0.49751 | 0.52619 | -0.7042 | -0.06678 | -0.51266
| 4585 | -0.062397 | 0.21878 | -0.15342 | -0.20722 | -0.01547 | 0.38592 | -0.61154 | -0.93 | -0.43387 | 0.59196
| 4586 | -0.17763 | 0.22611 | 0.7245 | 0.032684 | -0.91112 | 0.67091 | 0.15733 | -0.15259 | 0.14871 | -0.4232
| 4587 | 0.18275 | -0.02322 | 0.56239 | 0.0087886 | 0.055913 | 0.54492 | -0.13392 | 0.71911 | -0.074311 | -0.45769
| 4588 | 0.12851 | -0.49315 | -0.038283 | -0.036517 | 0.14064 | -0.12519 | -0.39892 | 0.58419 | -0.27757 | 0.51657
| 4589 | 0.023527 | -0.077774 | 0.3297 | -0.51061 | 0.55785 | -0.14589 | 0.33886 | -0.80687 | -0.26305 | -0.16101
| 4590 | -0.078642 | -0.33254 | 0.31073 | -0.15094 | 0.028558 | 0.071507 | -0.34038 | -0.71104 | 0.31014 | 0.64857
| 4591 | -0.29127 | -0.57023 | 0.51823 | -0.46549 | -0.18067 | 0.076799 | 0.047897 | 0.36715 | -0.064746 | -0.2256
| 4592 | -0.40544 | 0.14215 | -0.09033 | 0.11756 | 0.15899 | 0.8739 | 0.5656 | -0.25482 | -0.51657 | -0.54142
| 4593 | 0.55717 | 0.13808 | -0.60238 | 0.09132 | -0.10395 | -0.11022 | -0.029279 | 0.027015 | -0.30826 | -0.67581
| 4594 | -0.067745 | 0.35836 | 0.19334 | 0.32851 | -0.45991 | -0.58467 | -0.34205 | 0.46083 | -0.21635 | 0.41459
| 4595 | -0.1841 | 0.3551 | -0.79579 | -0.061757 | -0.28285 | 0.91815 | 0.25294 | -0.22238 | 0.14157 | 0.90461
| 4596 | -0.10006 | 0.21853 | -0.57609 | -0.47303 | -0.77572 | -0.045589 | -0.3132 | -0.12507 | 0.77175 | 0.65605
| 4597 | 0.084413 | 0.59294 | -0.093082 | 0.59245 | 0.57917 | 0.54646 | 0.15994 | -0.76357 | 0.35805 | -0.50412
| 4598 | 0.059734 | -0.28944 | -0.34892 | -0.22199 | -0.027426 | 0.78622 | 0.48087 | -0.57727 | 0.2427 | -0.61856
| 4599 | -0.48454 | 0.30595 | 0.26645 | -0.12074 | 0.2924 | 0.82536 | 0.10944 | -0.70251 | 0.1962 | -0.058884
| 4600 | -0.30293 | 0.0089904 | 0.16006 | 0.057397 | -0.46474 | -0.34571 | 0.11338 | 0.088682 | 0.047057 | 0.45036
| 4601 | -0.07183 | -0.086271 | 0.35247 | 0.20395 | -0.1597 | -0.15035 | -0.18104 | 0.25401 | 0.83599 | 0.39279
| 4602 | 0.12302 | 0.43795 | -0.59343 | 0.17121 | -0.16173 | -0.49691 | 0.56676 | 0.73486 | -0.36905 | 0.44439
| 4603 | -0.85 | -0.018522 | -0.35774 | -0.058565 | 0.1533 | -0.54229 | -0.054114 | 0.00055015 | -0.74058 | -0.14531
| 4604 | 0.096175 | -0.25294 | 0.41613 | -0.022401 | 0.66849 | -0.054749 | -0.45917 | -0.46568 | 0.10596 | 0.6634
| 4605 | -0.37143 | -0.28803 | 0.16244 | 0.51246 | 0.4307 | -0.06261 | 0.70555 | 0.86325 | -0.30179 | -0.3864
| 4606 | -0.50614 | -0.96683 | -0.025269 | 0.21802 | 0.70966 | 0.58227 | 0.16472 | -0.017605 | 0.23639 | 0.14496
| 4607 | 0.74058 | -0.16412 | 0.37048 | 0.067208 | 0.018522 | -0.55156 | 0.34923 | -0.12759 | 0.13219 | -0.60567
| 4608 | 0.5199 | 0.66103 | -0.44674 | 0.019541 | -0.42982 | -0.53513 | -0.020153 | 0.072045 | 0.73223 | -0.69357
| 4609 | 0.37992 | 0.020255 | 0.31772 | 0.013035 | 0.21827 | 0.1769 | -0.14064 | 0.10117 | -0.59049 | -0.8043
| 4610 | -0.18581 | -0.0022525 | 0.16675 | -0.93755 | 0.00075028 | 0.18544 | 0.19607 | 0.1196 | -0.098723 | 0.45055
| 4611 | -0.26061 | 0.064318 | 0.32376 | 0.0010506 | -0.32435 | 0.67674 | 0.35836 | 0.20169 | 0.80895 | 0.37927
| 4612 | -0.18975 | -0.072045 | -0.17738 | -0.038283 | -0.68615 | 0.3025 | 0.18373 | 0.082449 | -0.20194 | -0.089561
| 4613 | 0.0010506 | -0.13565 | -0.11214 | 0.021583 | 0.12051 | 0.26727 | -0.43493 | 0.23993 | 0.52703 | 0.28495
| 4614 | -0.069785 | -0.0017515 | 0.29921 | -0.38153 | -0.61987 | 0.252 | 0.89183 | -0.092862 | 0.59788 | 0.10317
| 4615 | -0.30538 | -0.10384 | -0.57186 | -0.39345 | 0.3537 | 0.017707 | -0.33434 | 0.61934 | 0.43053 | 0.045799
| 4616 | 0.29424 | -0.38657 | 0.29694 | -0.73904 | 0.48629 | 0.77751 | -0.11281 | 0.48183 | -0.09176 | -0.087366
| 4617 | 0.36164 | 0.29127 | -0.15911 | -0.49354 | 0.21355 | -0.52471 | -0.3087 | -0.63108 | -0.46362 | 0.74212
| 4618 | -0.26291 | 0.29311 | 0.4265 | 0.14742 | -0.42026 | 0.3005 | -0.3817 | 0.24694 | 0.066887 | -0.13681
| 4619 | -0.22109 | 5.0001e-05 | -0.13184 | -0.36683 | -0.53342 | 0.62092 | -0.66549 | -0.047057 | 0.53128 | -0.027529
| 4620 | -0.43511 | 0.3129 | -0.078751 | -0.48106 | 0.71946 | 0.58036 | 0.038803 | 0.20332 | -0.024039 | 0.43088
| 4621 | -0.28481 | -0.28607 | 0.62013 | -0.90356 | -0.47798 | 0.063677 | -0.077449 | 0.67891 | -0.45292 | 0.16531
| 4622 | 0.016283 | -0.23404 | 0.56954 | 0.16916 | 0.42772 | 0.2744 | -0.38396 | 0.10686 | 0.33645 | -0.85823
| 4623 | -0.10742 | 0.31495 | -0.38056 | -0.80025 | -0.027118 | -0.12279 | -0.15177 | -0.057397 | 0.049684 | 0.31949
| 4624 | 0.059096 | -0.083976 | -0.1786 | -0.42216 | 0.1706 | -0.41374 | 0.23547 | 0.21063 | -0.055384 | 0.46962
| 4625 | -0.17653 | 0.44511 | -0.50776 | -0.019541 | 0.0728 | -0.19831 | -0.56768 | -0.10675 | 0.20722 | -0.53621
| 4626 | 0.73486 | 0.25535 | -0.046952 | -0.040677 | 0.071184 | -0.11507 | -0.033098 | 0.16125 | -0.37718 | 0.031651
| 4627 | -0.25804 | -0.45695 | 0.75566 | 0.085724 | -0.09132 | 0.060266 | 0.10195 | 0.52534 | -0.11813 | 0.16018
| 4628 | -0.23404 | -0.29736 | 0.026296 | 0.054855 | -0.23286 | 0.14941 | 0.3767 | 0.20044 | 0.48843 | -0.72125
| 4629 | 0.31772 | 0.081795 | -0.32717 | -0.55424 | -0.22935 | 0.80895 | 0.0042591 | -0.034236 | -0.070108 | -0.18116
| 4630 | 0.41991 | -0.23143 | -0.44529 | 0.80125 | 0.32925 | 0.071399 | -0.43991 | 0.64181 | -0.10529 | 0.1277
| 4631 | 0.35572 | 0.67213 | 0.42355 | -0.36731 | -0.19806 | -0.64631 | 0.24601 | 0.19074 | 0.22883 | -0.11191
| 4632 | 0.39329 | -0.32169 | 0.030928 | 0.77841 | 0.4293 | -0.24561 | -0.45732 | -0.077666 | 0.020561 | 0.43653
| 4633 | 0.024859 | 0.15673 | -0.10373 | 0.7496 | 0.1072 | -0.45935 | -0.24867 | 0.69751 | 0.11484 | 0.55514
| 4634 | 0.016384 | 0.05253 | 0.34571 | -0.18815 | 0.14906 | 0.12564 | 0.37558 | 0.075933 | 0.41477 | 0.49374
| 4635 | 0.4736 | 0.39643 | 0.21063 | 0.32806 | 0.50715 | 0.05984 | 0.15709 | -0.16137 | -0.42199 | -0.5011
| 4636 | -0.3662 | 0.094848 | -0.4286 | -0.79975 | 0.054114 | 0.29466 | 0.66668 | 0.033925 | -0.23744 | -0.01486
| 4637 | 0.088134 | 0.82593 | -0.10552 | -0.7005 | -0.55245 | 0.12222 | 0.48357 | -0.26061 | -0.48415 | 0.099167
| 4638 | -0.236 | -0.69917 | -0.3372 | -0.53859 | -0.40092 | -0.02609 | -0.10574 | 0.097614 | -0.58323 | 0.33075
| 4639 | 0.1439 | -0.71875 | 0.22547 | 0.12108 | 0.099944 | -0.66015 | -0.13023 | -0.29155 | 0.068496 | -0.0015512
| 4640 | -0.79826 | 0.72742 | -0.085396 | 0.22019 | 0.25683 | -0.0755 | 0.25388 | 0.67922 | -0.30783 | -0.031031
| 4641 | 0.48454 | 0.60719 | -0.3015 | -0.35123 | 0.44295 | 0.2287 | -0.096728 | 0.3309 | 0.093303 | 0.85337
| 4642 | 0.27261 | 0.45954 | 0.14355 | -0.18275 | 0.40025 | -0.38445 | 0.28216 | 0.5436 | -0.22689 | -0.35789
| 4643 | -0.21406 | 0.49196 | -0.12519 | 0.69194 | -0.1546 | -0.44224 | 0.25133 | -0.052002 | -0.015368 | -0.0053644
| 4644 | 0.22083 | -0.36055 | -0.10798 | -0.56722 | 0.30007 | -0.14706 | -0.016486 | 0.48376 | -0.34954 | 0.32598
| 4645 | -0.90151 | 0.37831 | -0.34739 | 0.022503 | 0.87155 | 0.74841 | 0.30064 | 0.1597 | -0.27178 | -0.57727
| 4646 | -0.045694 | 0.00015001 | -0.60567 | 0.12519 | 0.039635 | 0.3767 | 0.32243 | -0.49196 | -0.32155 | 0.77044
| 4647 | 0.084194 | -0.10507 | 0.34144 | -0.49236 | -0.052741 | 0.8747 | -0.20874 | -0.18803 | -0.049158 | 0.25683
| 4648 | 0.76527 | 0.42633 | -0.16197 | -0.053058 | 0.093303 | -0.026809 | -0.19607 | -0.039115 | -0.72378 | -0.16388
| 4649 | -0.12943 | -0.6149 | 0.36541 | -0.26441 | -0.07 | -0.20445 | -0.29014 | 0.25966 | -0.49256 | 0.44457
| 4650 | 0.65868 | -0.23378 | -0.43405 | 0.13565 | 0.031857 | 0.52745 | 0.072369 | 0.26413 | -0.16543 | 0.2773
| 4651 | -0.6631 | -0.11598 | -0.15721 | -0.063677 | 0.57 | -0.38396 | 0.11394 | -0.60238 | 0.2175 | 0.85682
| 4652 | 0.13588 | -0.26061 | -0.13242 | 0.25428 | -0.57515 | -0.78483 | 0.76104 | 0.28873 | 0.17096 | 0.049895
| 4653 | -0.65201 | -0.94432 | -0.6249 | 0.37654 | -0.089121 | -0.75979 | -0.84867 | -0.00035006 | 0.13658 | -0.3537
| 4654 | -0.29113 | -0.1841 | -0.20219 | 0.12897 | -0.051475 | 0.56583 | 0.30322 | 0.11631 | -0.34281 | 0.47837
| 4655 | -0.22896 | 0.14484 | -0.35046 | 0.063037 | -0.64546 | 0.5656 | 0.0080827 | 0.62251 | 0.76612 | 0.67766
| 4656 | 0.26767 | 0.4995 | 0.73789 | -0.58227 | -0.22032 | -0.27619 | 0.014759 | 0.59147 | -0.19346 | -0.2733
| 4657 | 0.12816 | 0.3363 | -0.46456 | -0.58155 | -0.40729 | -0.39759 | -0.10854 | -0.47684 | 0.32214 | 0.76913
| 4658 | 0.39378 | -0.33209 | -0.5663 | 0.44891 | 0.009596 | -0.44782 | 0.2711 | -0.16675 | -0.18446 | -0.16113
| 4659 | 0.49137 | 0.78206 | 0.44027 | 0.47094 | -0.8755 | -0.1841 | -0.0020521 | -0.27014 | 0.35448 | -0.49592
| 4660 | 0.8755 | 0.8937 | -0.52873 | 0.15 | 0.18459 | -0.012731 | -0.29042 | 0.79628 | -0.61646 | 0.15816
| 4661 | 0.21114 | 0.27564 | -0.0029544 | -0.31787 | -0.32672 | 0.29523 | 0.093192 | -0.052424 | 0.003456 | 0.43493
| 4662 | 0.40359 | 0.89464 | 0.30322 | -0.71417 | -0.56171 | 0.19433 | -0.75241 | 0.19483 | 0.40966 | -0.052952
| 4663 | 0.44295 | 0.04381 | 0.81426 | -0.23299 | -0.30567 | -0.36668 | 0.14332 | 0.61987 | -0.59 | -0.14052
| 4664 | 0.35649 | -0.69784 | 0.13646 | -0.48396 | -0.28425 | 0.20144 | -0.21228 | -0.080163 | 0.11575 | -0.63054
| 4665 | -0.84157 | 0.452 | -0.14847 | -0.75161 | -0.054749 | -0.060585 | -0.34647 | 0.17568 | 0.78297 | 0.050421
| 4666 | 0.47512 | 0.32925 | -0.029073 | 0.038075 | -0.01486 | 0.65839 | -0.42216 | -0.23626 | 0.29339 | -0.010606
| 4667 | 0.037451 | 0.0063703 | 0.14648 | -0.20911 | -0.1072 | -0.068281 | -0.32821 | -0.13288 | 0.18495 | 0.80025
| 4668 | -0.82422 | 0.55582 | 0.20533 | -0.89276 | 0.50735 | -0.15519 | -0.81752 | -0.17945 | -0.80226 | 0.23718
| 4669 | -0.52031 | -0.032374 | 0.18006 | 0.75607 | 0.6939 | 0.18263 | 0.16723 | 0.37127 | 0.076041 | -0.45861
| 4670 | 0.64461 | 0.60744 | 0.87233 | -0.25602 | 0.030619 | -0.11745 | -0.25845 | 0.54668 | 0.70794 | 0.62543
| 4671 | -0.19408 | 0.3961 | -0.25401 | 0.12142 | 0.32169 | 0.77572 | -0.0014511 | -0.052319 | 0.50311 | 0.20646
| 4672 | 0.049053 | -0.18263 | -0.67953 | -0.55178 | 0.19582 | -0.75648 | 0.42615 | 0.076041 | 0.58927 | 0.26672
| 4673 | -0.46232 | -0.61542 | -0.43088 | -0.07962 | 0.21508 | 0.67922 | 0.93917 | -0.43902 | 0.28677 | -0.15638
| 4674 | -0.7735 | 0.4564 | 0.19545 | 0.018827 | 0.007075 | 0.12108 | -0.39312 | 0.3477 | 0.38592 | -0.62304
| 4675 | 0.018012 | -0.45622 | -0.31349 | -0.1825 | 0.77087 | -0.31802 | 0.02322 | -0.59639 | 0.85823 | 0.04099
| 4676 | 0.13322 | -0.051791 | -0.053269 | -0.064746 | -0.033718 | -0.10485 | -0.17072 | -0.032788 | -0.47569 | -0.42181
| 4677 | -0.34403 | -0.1277 | -0.61412 | -0.094075 | 0.050316 | 0.14192 | -0.64546 | 0.39279 | -0.58563 | -0.64772
| 4678 | 0.22366 | -0.73599 | -0.35432 | -0.45824 | 0.28887 | 0.52979 | 0.74643 | 0.40393 | 0.017401 | 0.41545
| 4679 | 0.056019 | -0.063784 | -0.64829 | 0.15555 | -0.086709 | 0.28425 | 0.22974 | 0.25495 | -0.92319 | -0.15555
| 4680 | -0.53643 | -0.60694 | 0.52915 | 0.46009 | -0.50715 | -0.048212 | -0.59098 | 0.33105 | -0.52282 | 0.26223
| 4681 | 0.53859 | 0.086053 | 0.61751 | -0.28901 | 0.065923 | -0.36227 | -0.25818 | -0.097947 | -0.41238 | -0.38526
| 4682 | 0.15365 | 0.36368 | -0.10608 | 0.084413 | -0.54076 | -0.17362 | 0.6634 | -0.61516 | 0.69422 | 0.59913
| 4683 | 0.57822 | -0.069355 | -0.71627 | -0.32258 | -0.42807 | -0.33766 | 0.37446 | 0.45237 | 0.52471 | 0.028249
| 4684 | 0.15555 | 0.19421 | 0.32022 | 0.77977 | -0.38575 | 0.7569 | 0.77175 | 0.13542 | 0.42877 | -0.028249
| 4685 | -0.48396 | -0.10429 | 0.37799 | -0.1221 | -0.24244 | 0.15887 | 0.034443 | -0.52809 | -0.058884 | -0.013643
| 4686 | -0.61908 | -0.51948 | -0.080707 | -0.007075 | -0.32776 | 0.69097 | -0.15875 | -0.042764 | 0.42372 | 0.031548
| 4687 | 0.011719 | 0.64744 | -0.094185 | 0.21584 | 0.13 | 0.42598 | 0.061224 | -0.47208 | -0.13994 | -0.21597
| 4688 | -0.29169 | -0.41854 | 0.15756 | -0.043914 | -0.13357 | -0.70251 | 0.21789 | -0.14215 | -0.81972 | 0.55582
| 4689 | -0.34053 | -0.17884 | -0.074635 | -0.054537 | 0.08967 | 0.22909 | -0.49098 | -0.11 | -0.35479 | 0.053903
| 4690 | -0.18864 | -0.28243 | 0.71487 | 0.21814 | 0.6338 | -0.15839 | 0.57893 | 0.016791 | 0.21292 | -0.45806
| 4691 | -0.67366 | 0.49098 | -0.02609 | -0.80379 | -0.10017 | 0.0010506 | 0.33539 | -0.032581 | 0.53213 | 0.13692
| 4692 | -0.2216 | -0.31978 | -0.564 | 0.33932 | 0.53902 | -0.82536 | 0.18079 | -0.50614 | -0.5663 | -0.35339
| 4693 | -0.18655 | 0.25495 | -0.054749 | -0.20558 | 0.24907 | -0.083103 | -0.6546 | 0.028867 | -0.0094951 | -0.087257
| 4694 | -0.36604 | 0.077124 | -0.026912 | 0.73904 | 0.44982 | 0.40932 | -0.32539 | -0.18926 | -0.00065021 | 0.58781
| 4695 | -0.54273 | -0.15733 | 0.31641 | -0.35324 | 0.79776 | 0.060372 | 0.46028 | -0.23836 | -0.30222 | -0.59838
| 4696 | 0.47894 | -0.14111 | -0.29679 | -0.02281 | -0.16543 | -0.023322 | 0.031341 | -0.4531 | -0.082449 | -0.36368
| 4697 | -0.4653 | -0.16904 | 0.0081835 | -0.49216 | 0.23849 | 0.35185 | 0.12553 | -0.17024 | -0.082558 | 0.48202
| 4698 | 0.064425 | -0.046113 | 0.039219 | -0.52429 | 0.38494 | 0.10921 | 0.36227 | 0.42441 | -0.15756 | -0.15283
| 4699 | 0.13646 | 0.45 | 0.20257 | -0.51782 | 0.3375 | -0.15212 | 0.53149 | 0.35603 | -0.083539 | -0.39461
| 4700 | -0.18043 | 0.86472 | 0.61542 | 0.24774 | -0.14414 | 0.25361 | 0.012123 | -0.26795 | -0.80687 | -0.10028
| 4701 | -0.68711 | 0.75282 | 0.019541 | 0.029485 | 0.80895 | 0.2791 | -0.25187 | 0.05899 | -0.29424 | -0.29183
| 4702 | 0.34571 | 0.60163 | -0.06914 | -0.17495 | -0.09154 | 0.58179 | -0.38105 | 0.45127 | 0.21853 | 0.024346
| 4703 | 0.26754 | 0.29608 | 0.041616 | -0.46981 | -0.03974 | 0.53235 | -0.27082 | 0.55717 | 0.27522 | 0.61154
| 4704 | 0.52597 | -0.45475 | 0.55785 | -0.34342 | -0.73037 | 0.96127 | 0.76569 | 0.047372 | 0.68393 | 0.036724
| 4705 | -0.51886 | 0.32821 | -0.76442 | 0.23 | -0.27385 | 0.53772 | -0.00085036 | 0.61412 | -0.4859 | 0.36368
| 4706 | -0.27591 | -0.070108 | -0.17653 | 0.39312 | 0.58179 | 0.041616 | -0.31495 | 0.78952 | 0.91225 | -0.3087
| 4707 | 0.29014 | -0.14064 | -0.46288 | -0.57233 | -0.2193 | -0.49098 | 0.45383 | 0.22611 | 0.1559 | -0.36023
| 4708 | -0.436 | 0.2377 | -0.53406 | 0.05814 | 0.55649 | -0.043496 | 0.20672 | -0.23 | 0.87155 | 0.75282
| 4709 | 0.03974 | -0.19707 | 0.2784 | 0.16651 | 0.21917 | 0.47665 | -0.17386 | -0.17386 | -0.65287 | 0.11034
| 4710 | 0.024346 | -0.59466 | -0.55245 | 0.55044 | -0.32376 | 0.040782 | -0.2809 | 0.43831 | -0.07 | -0.29523
| 4711 | -0.78483 | -0.16244 | -0.062397 | -0.22611 | -0.19856 | -0.29566 | -0.087586 | -0.5954 | -0.60744 | 0.51865
| 4712 | 0.65029 | 0.055807 | 0.81159 | -0.64461 | -0.034029 | -0.065923 | 0.44511 | -0.25589 | -0.55898 | 0.34816
| 4713 | 0.40983 | -0.24827 | -0.73373 | -0.33299 | 0.18018 | -0.5224 | 0.054326 | 0.29395 | -0.3116 | 0.08234
| 4714 | 0.53751 | 0.57397 | -0.34985 | -0.003456 | 0.22508 | -0.16771 | -0.50837 | 0.053269 | 0.61283 | 0.20269
| 4715 | -0.88731 | 0.45751 | 0.083867 | -0.021174 | -0.18287 | -0.050316 | 0.81106 | -0.48961 | 0.41068 | -0.38445
| 4716 | -0.11451 | 0.66758 | -0.019643 | 0.35463 | -0.18938 | -0.18483 | -0.47227 | 0.10854 | -0.26196 | 0.58371
| 4717 | -0.31978 | -0.19384 | -0.1308 | -0.16615 | 0.16173 | 0.32851 | -0.0018517 | -0.3817 | -0.14379 | -0.79143
| 4718 | 0.27082 | -0.59863 | 0.3727 | 0.23718 | -0.39626 | -0.55447 | 0.24575 | 0.72779 | -0.61882 | -0.53924
| 4719 | -0.54251 | 0.0079819 | 0.49552 | 0.075176 | -0.14882 | 0.21687 | 0.91 | 0.83599 | -0.40242 | -0.04266
| 4720 | 0.41221 | -0.14531 | -0.72705 | -0.26386 | 0.78529 | 0.070753 | -0.069033 | 0.16316 | -0.53 | 0.31029
| 4721 | -0.29921 | 0.55267 | 0.1706 | -0.63765 | -0.0059678 | -0.40831 | -0.0056661 | -0.57468 | -0.33464 | -0.26305
| 4722 | -0.16436 | 0.33179 | -0.20458 | -0.30841 | 0.06016 | -0.020766 | -0.3061 | 0.017707 | -0.044751 | -0.17653
| 4723 | -0.70083 | -0.23 | -0.17495 | 0.81642 | -0.55966 | -0.12028 | 0.29651 | 0.01842 | -0.68583 | -0.33149
| 4724 | 0.21393 | 0.22573 | -0.056443 | 0.71627 | -0.8043 | -0.91456 | -0.32169 | 0.16639 | 0.00075028 | 0.24601
| 4725 | -0.009697 | -0.25147 | -0.65868 | 0.25401 | 0.061224 | -0.2958 | -0.4826 | 0.1884 | -0.44547 | 0.51041
| 4726 | 0.51699 | 0.29665 | 0.78576 | 0.047162 | -0.68204 | 0.18938 | 0.48512 | 0.35572 | -0.13334 | -0.47493
| 4727 | -0.56768 | -0.28523 | 0.61934 | -0.26713 | 0.055278 | -0.61335 | -0.79975 | -0.30437 | 0.39643 | -0.23547
| 4728 | -0.08978 | 0.12989 | -0.20144 | -0.22534 | -0.27316 | -0.29226 | 0.18092 | -0.071076 | -0.21942 | -0.45475
| 4729 | 0.26808 | 0.16472 | -0.15958 | -0.046113 | 0.089012 | 0.85752 | 0.27233 | 0.26645 | 0.039531 | 0.064532
| 4730 | 0.30093 | 0.56239 | 0.49256 | 0.14753 | -0.12154 | 0.3372 | 0.89276 | 0.021583 | 0.47741 | 0.36447
| 4731 | -0.25214 | 0.25697 | 0.48668 | 0.39378 | 0.14918 | 0.048212 | -0.10496 | -0.18618 | -0.57988 | 0.3015
| 4732 | 0.46232 | 0.20458 | -0.62357 | 0.40696 | 0.64181 | -0.057928 | 0.75813 | 0.022503 | 0.012832 | -0.30841
| 4733 | -0.30365 | 0.55807 | 0.42703 | 0.44331 | 0.1729 | 0.25939 | 0.39131 | -0.61206 | 0.2508 | -0.51534
| 4734 | -0.096064 | 0.16579 | -0.33856 | 0.56468 | 0.4828 | 0.3294 | -0.20848 | 0.047267 | -0.039531 | 0.039948
| 4735 | 0.24575 | 0.76063 | 0.28299 | -0.24601 | 0.051686 | 0.22379 | 0.2516 | -0.49512 | 0.75772 | -0.15673
| 4736 | 0.48922 | 0.080163 | 0.58203 | 0.37175 | -0.35092 | -0.41785 | 0.18336 | -0.28789 | 0.40578 | 0.55424
| 4737 | 0.9245 | 0.30179 | 0.071076 | -0.19421 | -0.09187 | 0.40713 | 0.25428 | -0.54558 | -0.012528 | -0.5017
| 4738 | -0.4564 | 0.05158 | -0.68393 | 0.2567 | 0.76063 | 0.41204 | 0.34235 | 0.3372 | 0.12347 | 0.59614
| 4739 | 0.15792 | -0.33615 | -0.20899 | 0.0755 | -0.26877 | -0.20483 | 0.32658 | -0.464 | -0.21355 | -0.010303
| 4740 | 0.2161 | 0.24734 | 0.84031 | -0.38984 | 0.66192 | -0.5141 | -0.2755 | -0.26631 | -0.25737 | -0.20144
| 4741 | 0.38478 | 0.20307 | 0.14777 | 0.73599 | -0.1034 | 0.17884 | -0.79 | -0.047162 | 0.021072 | -0.25401
| 4742 | 0.15875 | -0.085506 | 0.27316 | 0.39098 | -0.3551 | 0.74722 | -0.040782 | 0.236 | 0.069892 | 0.60238
| 4743 | 0.44565 | -0.053797 | 0.16831 | -0.27688 | 0.28901 | -0.23954 | -0.2356 | 0.46418 | 0.055701 | 0.2924
| 4744 | 0.35867 | 0.11225 | -0.32911 | -0.06325 | -0.053374 | 0.23286 | -0.436 | -0.38218 | 0.73561 | -0.21827
| 4745 | -0.096396 | -0.00035006 | -0.20395 | 0.22315 | -0.55492 | 0.85405 | -0.64014 | 0.06165 | -0.30021 | 0.75979
| 4746 | -0.25953 | -0.67427 | -0.16316 | 0.081251 | 0.37095 | -0.063357 | 0.78716 | 0.11518 | -0.23117 | 0.32066
| 4747 | -0.47019 | 0.44728 | 0.1952 | 0.34969 | 0.25495 | -0.21648 | 0.31934 | -0.70217 | 0.57374 | 0.4041
| 4748 | 0.78669 | 0.46737 | -0.20332 | 0.20445 | 0.36008 | -0.033098 | 0.047792 | 0.33389 | 0.66668 | 0.18263
| 4749 | -0.16448 | -0.46549 | -0.59196 | -0.14882 | 0.19707 | 0.34555 | 0.4337 | -0.11688 | -0.011112 | -0.033408
| 4750 | -0.19346 | -0.2975 | 0.60617 | -0.67798 | 0.034858 | 0.4993 | -0.55853 | 0.16844 | 0.41528 | -0.014252
| 4751 | 0.28035 | 0.78483 | -0.24389 | -0.023322 | -0.58155 | 0.56653 | 0.13184 | -0.47076 | 0.87712 | -0.036621
| 4752 | 0.67519 | -0.6349 | -0.62543 | 0.26959 | -0.14309 | -0.2398 | 0.70966 | -0.12862 | 0.64744 | -0.47933
| 4753 | -0.38137 | -0.4588 | 0.16952 | 0.12828 | 0.16831 | -0.069463 | 0.35401 | 0.48299 | -0.28663 | -0.18827
| 4754 | 0.36353 | 0.19582 | -0.29637 | 0.80843 | -0.53794 | 0.42372 | 0.37847 | -0.0086877 | -0.081033 | -0.37127
| 4755 | -0.13426 | -0.51492 | -0.061757 | 0.002453 | 0.24747 | 0.13774 | 0.26088 | -0.018114 | 0.73298 | 0.40175
| 4756 | -0.32732 | -0.72161 | 0.012225 | 0.23221 | 0.045484 | 0.13658 | -0.1884 | -0.5021 | -0.18495 | 0.24349
| 4757 | 0.042869 | -0.50311 | -0.24257 | -0.072584 | 0.15519 | 0.48415 | 0.063677 | -0.10328 | 0.14344 | 0.81106
| 4758 | -0.11654 | -0.58781 | -0.069463 | 0.28007 | -0.6697 | -0.24442 | 0.1261 | -0.45511 | -0.35743 | 0.28481
| 4759 | -0.62865 | 0.33149 | -0.48087 | -0.45843 | -0.7492 | -0.66909 | 0.34174 | -0.69553 | 0.27165 | -0.11056
| 4760 | 0.22122 | 0.43229 | -0.11462 | -0.16892 | -0.21725 | -0.28132 | 0.6338 | 0.027529 | 0.24694 | -0.028146
| 4761 | -0.75241 | 0.14613 | -0.18569 | -0.47322 | 0.01 | -0.018216 | 0.27799 | 0.64237 | -0.20583 | -0.26795
| 4762 | 0.1775 | -0.020357 | -0.0040582 | 0.030619 | -0.20395 | 0.073016 | 0.40175 | -0.1136 | -0.2216 | -0.49354
| 4763 | -0.26863 | -0.032271 | 0.28467 | -0.20975 | 0.78905 | 0.11315 | -0.18569 | 0.49118 | -0.18827 | 0.46213
| 4764 | -0.014962 | 0.13843 | 0.34754 | -0.44728 | 0.14835 | 0.057397 | -0.14449 | 0.13346 | 0.30928 | 0.93597
| 4765 | 0.45824 | 0.30841 | -0.0083852 | -0.93144 | -0.043601 | 0.095622 | -0.087366 | 0.38445 | -0.31422 | -0.0090913
| 4766 | -0.36937 | 0.58467 | 0.2621 | 0.05348 | -0.49552 | -0.6407 | -0.10955 | 0.1315 | 0.83538 | -0.052002
| 4767 | 0.18544 | 0.53 | 0.65634 | 0.033305 | -0.023015 | 0.63462 | 0.079728 | -0.18018 | -0.3074 | -0.5199
| 4768 | 0.5245 | 0.15071 | 0.19099 | -0.014454 | -0.17217 | 0.85269 | 0.58903 | 0.22857 | -0.17653 | -0.63517
| 4769 | -0.056125 | 0.26795 | 0.039948 | -0.088902 | -0.45806 | 0.67274 | 0.41785 | 0.65722 | 0.1418 | -0.22276
| 4770 | -0.38869 | -0.62463 | -0.56954 | -0.42528 | 0.1196 | -0.30841 | 0.64943 | 0.034547 | 0.29537 | -0.1323
| 4771 | -0.03974 | 0.82196 | 0.40042 | 0.61 | 0.93597 | -0.41187 | 0.39395 | 0.27096 | 0.41374 | -0.32007
| 4772 | -0.45714 | 0.29964 | -0.39197 | 0.31495 | -0.76188 | 0.15614 | -0.35169 | -0.12176 | -0.65547 | 0.19025
| 4773 | 0.14145 | 0.10888 | 0.13 | -0.0004501 | -0.22741 | 0.050316 | -0.55335 | 0.0032553 | -0.3681 | -0.0083852
| 4774 | 0.80125 | 0.049263 | 0.61646 | 0.436 | 0.59614 | -0.63986 | -0.0043595 | -0.4471 | 0.18116 | 0.063037
| 4775 | 0.025577 | -0.59491 | 0.38885 | -0.13299 | 0.22006 | 0.65 | -0.49433 | 0.12439 | 0.1323 | 0.71698
| 4776 | -0.92859 | 0.84605 | 0.78344 | -0.28845 | -0.22663 | -0.61882 | -0.59196 | -0.17181 | -0.0054649 | 0.49059
| 4777 | -0.18495 | -0.22831 | -0.10017 | 0.61777 | -0.33149 | 0.6703 | -0.38787 | -0.2256 | 0.57397 | -0.15626
| 4778 | 0.27854 | -0.59171 | 0.40008 | 0.3735 | -0.72378 | -0.87712 | 0.056019 | 0.11869 | 0.13322 | -0.80687
| 4779 | 0.25616 | 0.31116 | -0.28986 | -0.043705 | -0.032891 | -0.22754 | -0.49315 | -0.44493 | 0.11722 | -0.12267
| 4780 | -0.34144 | 0.45219 | -0.0063703 | -0.19694 | -0.47933 | -0.3923 | 0.037347 | 0.080924 | 0.23705 | -0.69032
| 4781 | 0.40611 | -0.003155 | 0.30007 | -0.046742 | -0.37911 | -0.065388 | -0.33811 | 0.47303 | 0.60949 | 0.67704
| 4782 | -0.0045604 | 0.39626 | 0.36258 | -0.50898 | 0.69553 | -0.047687 | -0.3735 | -0.2377 | 0.18006 | -0.5332
| 4783 | 0.3132 | 0.10686 | 0.3751 | 0.20019 | -0.19334 | -0.18201 | 0.6044 | 0.34205 | -0.009596 | -0.33344
| 4784 | -0.032581 | -0.14437 | 0.14087 | 0.5283 | 0.17447 | -0.41528 | -0.016384 | -0.34877 | 0.21546 | 0.36747
| 4785 | -0.055807 | 0.79875 | -0.64209 | -0.04172 | -0.69292 | -0.75403 | -0.12256 | -0.50271 | -0.38804 | -0.28677
| 4786 | 0.5007 | 0.0086877 | 0.059096 | 0.43246 | -0.052424 | -0.82365 | -0.27605 | -0.18606 | -0.32896 | -0.045275
| 4787 | -0.16892 | 0.19198 | 0.20219 | 0.32169 | 0.10944 | -0.43671 | 0.88554 | 0.66192 | -0.34144 | 0.35401
| 4788 | -0.41136 | -0.34357 | -0.5172 | -0.60389 | 0.66909 | 0.75 | 0.30122 | -0.62731 | -0.32243 | 0.4117
| 4789 | -0.047057 | -0.10039 | 0.42181 | -0.0044599 | -0.44638 | 0.23954 | -0.80739 | -0.58083 | -0.31597 | 0.27854
| 4790 | -0.073771 | 0.18864 | -0.085287 | -0.30754 | -0.61672 | 0.53149 | 0.20949 | -0.53342 | 0.55582 | -0.033925
| 4791 | 0.33299 | 0.17714 | 0.3211 | -0.10139 | -0.057503 | -0.30957 | 0.053269 | -0.48843 | -0.66668 | -0.39527
| 4792 | -0.015571 | -0.28146 | 0.53578 | -0.17121 | 0.027118 | -0.14052 | 0.12188 | 0.10317 | 0.0071757 | 0.031135
| 4793 | -0.23364 | -0.060905 | -0.024244 | -0.26305 | 0.67735 | -0.15413 | -0.59466 | -0.49493 | 0.53772 | -0.11564
| 4794 | -0.21228 | 0.31524 | -0.04266 | 0.30667 | -0.85337 | -0.064212 | 0.25791 | -0.21038 | 0.47894 | 0.1063
| 4795 | 0.67213 | -0.53902 | -0.36055 | 0.44837 | -0.32406 | -0.22431 | 0.58012 | -0.5201 | 0.7005 | 0.20031
| 4796 | -0.38787 | 0.11983 | -0.028146 | -0.088682 | -0.49671 | 0.045799 | 0.32851 | 0.29537 | 0.46381 | -0.092311
| 4797 | -0.70453 | 0.38575 | -0.65576 | -0.56125 | -0.15911 | 0.13623 | 0.18226 | 0.082122 | 0.59196 | -0.26196
| 4798 | -0.53213 | 0.93597 | -0.16042 | 0.50837 | 0.031444 | 0.059096 | 0.087476 | 0.85405 | 0.41102 | 0.71522
| 4799 | 0.83783 | 0.71417 | 0.73335 | -0.3804 | -0.09176 | 0.72815 | 0.11835 | -0.76784 | 0.53816 | -0.098169
| 4800 | -0.46456 | 0.15543 | 0.69983 | 0.29566 | 0.0094951 | 0.9245 | -0.39809 | -0.31203 | -0.21955 | -0.42164
| 4801 | -0.19719 | 0.50735 | 0.58036 | -0.36747 | 0.35603 | -0.22353 | 0.21712 | 0.19272 | 0.31904 | -0.59614
| 4802 | 0.031444 | 0.28411 | -0.14531 | 0.064639 | 0.18471 | -0.34877 | 0.049789 | 0.67674 | -0.31553 | 0.0086877
| 4803 | 0.19757 | -0.16388 | 0.040052 | 0.21981 | 0.74722 | -0.4046 | -0.079402 | -0.53192 | -0.046218 | -0.40898
| 4804 | 0.53664 | 0.62463 | -0.15413 | 0.56239 | 0.17471 | 0.34785 | 0.49671 | 0.17592 | 0.14566 | -0.024654
| 4805 | -0.18422 | 0.24774 | 0.17423 | 0.089561 | 0.6319 | -0.71417 | -0.80532 | -0.42337 | -0.050737 | -0.41289
| 4806 | 0.32806 | 0.51865 | -0.35556 | -0.18951 | -0.56838 | -0.77087 | -0.32658 | 0.37143 | 0.10529 | -0.30036
| 4807 | -0.12142 | 0.0045604 | -0.61206 | -0.10128 | 0.20874 | -0.1196 | 0.085506 | -0.28831 | 0.36305 | 0.16197
| 4808 | 0.015876 | -0.33389 | 0.45292 | -0.31568 | -0.14274 | -0.72669 | 0.74329 | -0.0082843 | -0.069248 | 0.46906
| 4809 | -0.1597 | -0.51143 | -0.056867 | 0.2791 | -0.5656 | 0.023322 | 0.14461 | -0.87077 | 0.7512 | 0.19744
| 4810 | 0.42268 | -0.12279 | 0.088682 | -0.77977 | -0.21648 | -0.35945 | -0.41836 | -0.56445 | 0.23 | -0.41888
| 4811 | 0.46306 | -0.048107 | -0.71138 | 0.1825 | 0.75363 | 0.31422 | 0.34448 | -0.70623 | 0.26781 | 0.40008
| 4812 | -0.0004501 | 0.88909 | -0.084522 | -0.11248 | 0.23417 | 0.44349 | 0.47894 | 0.3651 | -0.15425 | 0.66578
| 4813 | -0.09077 | 0.19545 | -0.24349 | 0.65114 | 0.18741 | -0.045275 | 0.59863 | 0.18508 | 0.65839 | 0.17799
| 4814 | -0.51782 | 0.17435 | -0.80328 | 0.22289 | -0.62784 | -0.096064 | -0.20094 | -0.2047 | 0.033305 | -0.088353
| 4815 | 0.69784 | 0.027529 | 0.074959 | 0.043705 | -0.31904 | 0.77483 | 0.33 | 0.164 | 0.23117 | -0.064746
| 4816 | -0.59269 | -0.24814 | 0.30222 | 0.0078811 | 0.29879 | 0.026193 | 0.5529 | -0.40797 | -0.65143 | 0.48765
| 4817 | 0.82139 | -0.37478 | 0.047162 | 0.47722 | 0.52915 | 0.072369 | 0.9245 | 0.22135 | 0.54273 | 0.18704
| 4818 | -0.47837 | 0.7429 | -0.051159 | 0.21025 | -0.75731 | -0.1245 | -0.22173 | 0.044437 | -0.62224 | 0.21165
| 4819 | 0.27316 | 0.012326 | -0.47436 | -0.1308 | -0.3923 | -0.35355 | -0.12222 | 0.00065021 | 0.56171 | 0.56262
| 4820 | -0.064318 | -0.37654 | -0.32554 | 0.56034 | -0.17362 | -0.61699 | -0.43688 | -0.096839 | -0.42772 | -0.20899
| 4821 | 0.04099 | -0.35727 | -0.44009 | -0.19794 | -0.44764 | 0.07043 | 0.1353 | -0.17326 | 0.49433 | 0.30581
| 4822 | -0.32613 | -0.097614 | 0.093744 | -0.81106 | 0.11315 | -0.23901 | 0.59515 | -0.51041 | -0.46849 | -0.72742
| 4823 | -0.079077 | 0.26808 | 0.5866 | 0.06753 | 0.075392 | -0.18901 | -0.65431 | 0.67798 | 0.50472 | -0.38657
| 4824 | -0.038283 | 0.29765 | 0.044647 | -0.59245 | 0.60898 | -0.26686 | 0.24933 | -0.49394 | -0.0039578 | 0.071076
| 4825 | -0.2924 | -0.41459 | 0.05814 | 0.252 | -0.32066 | -0.45493 | 0.55447 | -0.39033 | -0.45438 | -0.12336
| 4826 | -0.95877 | -0.13843 | 0.0044599 | 0.29113 | 0.21814 | 0.25214 | -0.080707 | 0.76913 | 0.018827 | 0.026912
| 4827 | 0.050737 | -0.66939 | 0.31116 | -0.068711 | 0.0085869 | -0.38056 | -0.61103 | 0.041825 | 0.84801 | 0.54294
| 4828 | -0.79143 | -0.34479 | -0.093523 | 0.13959 | -0.31349 | -0.38967 | -0.51451 | 0.17193 | 0.038699 | 0.17884
| 4829 | 0.26074 | 0.36133 | -0.28845 | -0.76827 | -0.42912 | 0.0045604 | 0.33917 | -0.41974 | 0.81 | -0.28174
| 4830 | 0.26822 | -0.10295 | -0.36447 | -0.22974 | 0.021992 | 0.20483 | -0.13669 | 0.031754 | -0.040469 | -0.44009
| 4831 | -0.47341 | -0.44385 | 0.37558 | -0.18495 | 0.89851 | -0.78023 | -0.09154 | 0.17799 | 0.33902 | 0.2398
| 4832 | -0.041825 | 0.57656 | -0.14017 | 0.25589 | 0.44674 | -0.0052639 | 0.1118 | 0.16892 | -0.42685 | -0.5174
| 4833 | 0.41751 | -0.20344 | 0.042555 | 0.28958 | 0.15212 | 0.21597 | -0.53256 | -0.0728 | -0.76913 | 0.17084
| 4834 | -0.09165 | -0.27178 | 0.23665 | 0.23783 | 0.39246 | -0.24112 | 0.40276 | -0.45456 | 0.3372 | 0.30423
| 4835 | 0.26781 | 0.031961 | 0.14976 | -0.64943 | 0.13507 | 0.094296 | -0.8937 | 0.44818 | 0.1253 | -0.049789
| 4836 | -0.464 | 0.099389 | -0.47057 | -0.47779 | -0.13913 | 0.81159 | 0.45475 | 0.038387 | 0.59565 | 0.11214
| 4837 | 0.85405 | -0.44891 | -0.029897 | -0.50918 | -0.52767 | -0.16364 | 0.09695 | 0.025474 | -0.55267 | -0.54404
| 4838 | 0.90151 | -0.39164 | -0.30884 | -0.33841 | 0.63627 | 0.86325 | 0.79925 | 0.15982 | 0.10899 | -0.08474
| 4839 | 0.30595 | -0.11439 | -0.19284 | -0.55245 | 0.17374 | 0.66819 | 0.64801 | 0.49039 | -0.56125 | -0.12897
| 4840 | 0.20785 | -0.099611 | -0.057822 | 0.62304 | -0.42199 | -0.32302 | -0.29822 | -0.58203 | 0.80075 | 0.79826
| 4841 | 0.25334 | 0.42164 | 0.13553 | -0.62973 | -0.36762 | -0.27938 | -0.25 | 0.45511 | -0.22482 | -0.29509
| 4842 | 0.35587 | -0.19396 | -0.36573 | -0.50796 | -0.41255 | 0.61803 | -0.94084 | -0.029176 | 0.92319 | 0.1109
| 4843 | 0.052952 | 0.037971 | 0.23836 | -0.44511 | -0.031238 | -0.51575 | -0.33254 | 0.10362 | -0.09 | -0.80379
| 4844 | 0.49651 | 0.58708 | 0.0051633 | -0.47417 | 0.14449 | 0.60592 | -0.098945 | 0.29325 | -0.47914 | 0.53064
| 4845 | 0.017503 | -0.10708 | 0.59441 | -0.60872 | -0.22857 | -0.25 | 0.29127 | 0.11225 | -0.11903 | 0.32613
| 4846 | -0.35046 | -0.80687 | 0.35355 | 0.20785 | -0.21623 | 0.74446 | 0.61777 | -0.72705 | -0.57609 | -0.74329
| 4847 | -0.64829 | -0.20785 | -0.36937 | -0.27274 | 0.5011 | 0.2516 | -0.18385 | 0.47645 | -0.10675 | -0.36478
| 4848 | -0.30437 | 0.88731 | 0.095069 | 0.09066 | -0.18975 | -0.22805 | -0.065174 | 0.69 | -0.064318 | -0.043391
| 4849 | 0.35992 | 0.49592 | -0.24907 | 0.03465 | -0.018929 | -0.20319 | 0.016384 | 0.59938 | 0.40679 | 0.21853
| 4850 | -0.40175 | 0.22032 | 0.4985 | 0.32881 | 0.24165 | -0.80075 | -0.067208 | -0.50796 | -0.31978 | 0.038075
| 4851 | -0.22238 | 0.21051 | 0.35992 | -0.062717 | 0.49256 | 0.52936 | -0.017503 | -0.21444 | 0.19657 | 0.17896
| 4852 | -0.007478 | -0.9078 | 0.76913 | 0.046742 | 0.022503 | -0.48941 | 0.57491 | -0.55537 | -0.36447 | -0.34023
| 4853 | -0.52115 | 0.48454 | 0.36968 | -0.15448 | 0.46269 | 0.44134 | 0.0083852 | -0.13785 | 0.1025 | 0.33404
| 4854 | 0.3211 | -0.38364 | -0.00035006 | 0.2216 | 0.10518 | 0.60744 | -0.53299 | 0.75 | 0.64461 | 0.046847
| 4855 | 0.32346 | 0.25845 | -0.46009 | -0.30423 | -0.24694 | 0.37366 | -0.5529 | -0.32051 | -0.66608 | 0.43
| 4856 | 0.45695 | -0.52031 | -0.44349 | 0.37734 | 0.15236 | -0.46981 | 0.45806 | -0.33464 | 0.25723 | -0.60846
| 4857 | -0.97354 | -0.16723 | -0.43955 | -0.19086 | 0.14531 | -0.06496 | -0.10485 | -0.25602 | -0.10865 | -0.44619
| 4858 | -0.0015512 | -0.18864 | -0.018623 | -0.21139 | -0.25388 | -0.38869 | -0.39164 | 0.42129 | -0.51164 | 0.26754
| 4859 | 0.58708 | -0.23639 | 0.11079 | 0.22045 | 0.31509 | -0.56977 | 0.81318 | -0.63848 | -0.12943 | -0.53363
| 4860 | 0.59392 | 0.047372 | 0.88909 | -0.46962 | -0.2504 | 0.62677 | 0.54668 | 0.51616 | 0.41716 | -0.58251
| 4861 | -0.14484 | 0.9089 | -0.79826 | 0.3419 | -0.43088 | -0.050842 | -0.6634 | 0.46251 | -0.6697 | 0.83783
| 4862 | 0.24721 | -0.12644 | 0.29466 | 0.38008 | 0.11598 | 0.72889 | -0.16006 | 0.27467 | -0.44385 | -0.44638
| 4863 | 0.11315 | -0.40898 | -0.0091922 | -0.61335 | -0.1473 | 0.58563 | -0.38461 | 0.38105 | -0.13322 | 0.74019
| 4864 | 0.4286 | -0.49196 | -0.087586 | 0.64574 | -0.72305 | -0.47779 | 0.56537 | 0.76442 | 0.37831 | 0.22366
| 4865 | 0.73827 | 0.26061 | 0.013947 | -0.57 | 0.54382 | -0.73637 | 0.3015 | -0.026398 | 0.13507 | 0.1797
| 4866 | -0.41836 | 0.58347 | -0.48863 | 0.35712 | 0.55898 | -0.60923 | -0.24429 | -0.76442 | 0.39958 | 0.089451
| 4867 | 0.11225 | 0.10284 | -0.42598 | -0.33314 | 0.015267 | -0.14824 | -0.2193 | 0.3751 | -0.28523 | 0.53235
| 4868 | 0.7245 | -0.23091 | -0.67152 | -0.43564 | -0.50553 | 0.65287 | 0.30365 | -0.54712 | -0.59838 | -0.31392
| 4869 | 0.9078 | 0.25254 | -0.4799 | 0.78763 | 0.059309 | -0.052108 | -0.55649 | 0.46587 | -0.34908 | -0.85337
| 4870 | -0.81752 | 0.40326 | -0.27398 | -0.076258 | 0.31436 | -0.0039578 | 0.20019 | -0.83059 | -0.336 | -0.8454
| 4871 | -0.62171 | 0.77 | 0.0012508 | 0.082122 | 0.35649 | 0.058459 | 0.010505 | 0.82252 | -0.46568 | -0.24933
| 4872 | -0.12165 | 0.53406 | -0.2492 | -0.064425 | -0.48863 | 0.22573 | 0.50513 | 0.40125 | 0.79482 | -0.64153
| 4873 | 0.19396 | 0.3357 | 0.48532 | 0.29921 | -0.038283 | -0.37382 | -0.1814 | 0.32554 | 0.35867 | 0.11813
| 4874 | -0.63217 | 0.20181 | 0.32747 | 0.67829 | 0.46643 | -0.62013 | -0.54426 | 0.81159 | 0.71312 | 0.4426
| 4875 | -0.24099 | 0.18692 | -0.19408 | -0.37944 | 0.85134 | 0.46009 | 0.47607 | 0.15413 | 0.5264 | 0.75403
| 4876 | -0.19819 | -0.71592 | 0.28831 | 0.88909 | -0.13173 | -0.10865 | 0.23351 | 0.70828 | 0.18704 | -0.12461
| 4877 | -0.17629 | -0.15425 | 0.1439 | -0.4999 | 0.62145 | 0.14064 | 0.43529 | -0.29708 | -0.18116 | -0.082667
| 4878 | -0.46325 | 0.28565 | 0.052002 | 0.042033 | 0.033305 | -0.17121 | -0.34985 | 0.33585 | 0.35308 | -0.12747
| 4879 | 0.17787 | 0.62251 | -0.21266 | -0.19371 | 0.93755 | -0.2052 | 0.058246 | -0.09198 | -0.40662 | 0.14449
| 4880 | 0.17653 | 0.087038 | -0.71804 | 0.34053 | -0.4564 | -0.53924 | 0.1382 | -0.40544 | -0.35262 | -0.20937
| 4881 | -0.40932 | 0.07 | -0.19161 | -0.47837 | 0.033925 | -0.97 | -0.16651 | 0.2402 | 0.065923 | -0.1237
| 4882 | -0.10496 | -0.0079819 | 0.32896 | -0.036621 | -0.013846 | 0.026398 | 0.019949 | 0.094296 | -0.0012508 | -0.2941
| 4883 | 0.21699 | 0.061437 | 0.24178 | 0.25495 | 0.50898 | -0.17447 | 0.24165 | 0.78483 | 0.36039 | -0.12885
| 4884 | 0.39 | -0.19446 | -0.4471 | -0.70691 | -0.36873 | 0.36557 | -0.42807 | -0.25858 | -0.52534 | -0.27744
| 4885 | -0.71733 | -0.49 | 0.29325 | -0.56422 | -0.19719 | 0.22935 | -0.76741 | 0.49493 | -0.29836 | -0.18864
| 4886 | -0.0064709 | 0.58805 | -0.34862 | -0.25174 | 0.39692 | -0.36557 | 0.45917 | 0.13646 | 0.37911 | -0.37064
| 4887 | -0.29722 | -0.4232 | -0.31247 | 0.26836 | -0.45018 | -0.5806 | 0.0091922 | -0.065281 | 0.016994 | 0.2816
| 4888 | 0.023117 | 0.39709 | -0.23117 | 0.16519 | -0.17133 | -0.8148 | -0.23417 | 0.89276 | -0.27069 | 0.65693
| 4889 | 0.31495 | -0.96127 | -0.41494 | 0.38804 | 0.85964 | 0.20357 | 0.1432 | -0.079402 | -0.70017 | 0.79095
| 4890 | -0.037244 | -0.019439 | 0.5663 | -0.21241 | -0.70828 | -0.57774 | -0.11881 | -0.28537 | -0.49651 | 0.6995
| 4891 | -0.34464 | 0.049474 | -0.067423 | -0.61 | -0.53427 | 0.13173 | 0.51348 | 0.031444 | 0.62039 | 0.8618
| 4892 | -0.152 | 0.0049623 | 0.12097 | -0.37895 | 0.35185 | -0.52136 | 0.22071 | -0.14718 | -0.24231 | 0.50918
| 4893 | -0.078859 | 0.43617 | -0.77617 | -0.094627 | -0.61103 | -0.79826 | 0.34647 | -0.16603 | -0.39296 | -0.65518
| 4894 | -0.048212 | -0.15024 | 0.28495 | 0.15047 | 0.40595 | 0.548 | -0.13265 | -0.11903 | 0.12473 | 0.76655
| 4895 | -0.57303 | -0.093634 | -0.30942 | 0.18092 | 0.1884 | -0.85893 | -0.088024 | -0.20949 | 0.73827 | -0.17702
| 4896 | -0.072476 | -0.31218 | -0.52429 | -0.052741 | 0.086709 | -0.081033 | 0.35092 | -0.26863 | 0.0030547 | -0.53513
| 4897 | 0.73713 | -0.25737 | -0.080381 | -0.20709 | 0.22045 | -0.15082 | 0.30394 | -0.20081 | -0.40042 | 0.056655
| 4898 | -0.42251 | 0.57374 | 0.073231 | -0.29679 | 0.41357 | -0.11801 | 0.91112 | 0.05496 | 0.59098 | -0.028558
| 4899 | -0.536 | -0.22148 | 0.29765 | -0.57941 | -0.29424 | 0.057928 | -0.2147 | -0.59 | 0.13855 | 0.33164
| 4900 | -0.20006 | 0.56768 | 0.37095 | 0.20006 | 0.25414 | 0.6755 | 0.38202 | -0.58684 | 0.3369 | -0.14859
| 4901 | -0.75403 | 0.37718 | 0.66399 | -0.33239 | 0.34632 | 0.0057666 | 0.66879 | 0.73373 | 0.2941 | 0.50878
| 4902 | -0.32583 | 0.40225 | -0.45585 | 0.64801 | -0.24987 | 0.061224 | 0.89 | -0.65868 | 0.079185 | 0.14765
| 4903 | -0.23065 | 0.13692 | -0.6637 | -0.49118 | -0.20483 | -0.086709 | 0.0051633 | -0.35432 | -0.50533 | 0.49433
| 4904 | 0.44063 | 0.71557 | -0.43141 | -0.46456 | 0.15153 | 0.013947 | -0.71487 | 0.15106 | -0.7492 | 0.31802
| 4905 | -0.17641 | -0.85337 | 0.11338 | -0.71769 | -0.12851 | 0.1353 | 0.22353 | -0.17072 | 0.23482 | 0.019643
| 4906 | 0.25656 | -0.51123 | 0.61987 | 0.30265 | -0.16964 | -0.065602 | -0.25321 | -0.85405 | -0.01 | -0.39082
| 4907 | -0.31392 | 0.38218 | 0.37767 | 0.11169 | -0.35525 | -0.067101 | 0.3851 | 0.21343 | -0.47856 | -0.14355
| 4908 | 0.23534 | 0.38332 | 0.17811 | 0.77887 | 0.21687 | -0.060798 | 0.15839 | -0.6578 | -0.29325 | -0.054114
| 4909 | -0.17495 | -0.22598 | -0.61672 | 0.017707 | 0.59639 | 0.26034 | -0.1797 | -0.54448 | 0.08967 | -0.19694
| 4910 | 0.68936 | -0.26332 | 0.91693 | 0.65927 | 0.20395 | -0.13681 | 0.17399 | -0.09077 | 0.043391 | 0.23273
| 4911 | 0.23456 | 0.51782 | 0.093192 | 0.6162 | 0.30957 | 0.4553 | 0.25267 | 0.16388 | 0.39263 | 0.19694
| 4912 | 0.1841 | 0.55379 | 0.64546 | -0.01547 | -0.3357 | 0.025988 | 0.042347 | 0.22573 | -0.11518 | -0.1921
| 4913 | 0.021787 | 0.39115 | -0.64943 | -0.39049 | 0.14472 | -0.32554 | 0.041825 | -0.2575 | 0.16952 | 0.26727
| 4914 | 0.08967 | 0.21406 | -0.51369 | 0.18385 | -0.069033 | 0.050948 | 0.77044 | -0.62145 | 0.83783 | 0.40865
| 4915 | 0.57233 | 0.26305 | -0.19334 | -0.45073 | 0.5264 | -0.0053644 | 0.30495 | 0.17362 | 0.86546 | -0.34923
| 4916 | -0.20836 | -0.64971 | -0.35401 | -0.21981 | 0.27633 | -0.34785 | 0.057928 | -0.0065716 | -0.6118 | -0.94615
| 4917 | -0.53751 | 0.11191 | -0.015063 | 0.1261 | -0.13438 | -0.12805 | 0.39082 | 0.19682 | -0.01547 | -0.67304
| 4918 | -0.83059 | -0.23169 | -0.50412 | 0.42407 | -0.31524 | -0.76442 | 0.15673 | 0.25683 | 0.82196 | 0.19446
| 4919 | 0.10295 | -0.67213 | -0.51534 | -0.077558 | 0.13184 | -0.45164 | -0.41991 | -0.47933 | -0.64772 | 0.56354
| 4920 | -0.80635 | -0.16627 | -0.17471 | 0.44638 | -0.24628 | 0.65605 | -0.081795 | -0.20445 | 0.30986 | -0.08136
| 4921 | 0.73298 | -0.63353 | 0.25885 | -0.47722 | 0.059521 | -0.040782 | -0.032891 | -0.27785 | -0.056973 | 0.42009
| 4922 | -0.35665 | 0.23469 | -0.077991 | 0.12006 | -0.21444 | 0.46028 | -0.0085869 | 0.38738 | -0.0052639 | -0.66608
| 4923 | 0.0078811 | -0.2516 | -0.91 | 0.092641 | -0.39975 | -0.95204 | 0.20646 | -0.45603 | 0.67488 | -0.68488
| 4924 | -0.15283 | -0.42685 | 0.42147 | -0.070968 | 0.17787 | 0.64209 | -0.58539 | 0.036724 | 0.10172 | -0.19657
| 4925 | 0.006169 | -0.62624 | -0.49059 | -0.013136 | -0.33329 | 0.3074 | 0.033615 | -0.50492 | 0.038907 | 0.48707
| 4926 | -0.69817 | -0.20861 | -0.19844 | -0.11881 | 0.64433 | -0.63682 | -0.55 | 0.077666 | -0.12165 | -0.68968
| 4927 | 0.05496 | 0.77572 | 0.29622 | 0.59049 | -0.045694 | -0.17702 | -0.3116 | 0.34877 | -0.018216 | -0.20344
| 4928 | -0.7429 | -0.33705 | -0.22987 | -0.43193 | 0.59863 | -0.23391 | 0.14285 | 0.19557 | -0.57964 | -0.41238
| 4929 | -0.11858 | 0.31334 | 0.31203 | 0.50351 | 0.7735 | 0.59689 | -0.053058 | -0.15377 | 0.85134 | -0.029485
| 4930 | 0.47417 | -0.88909 | -0.39428 | 0.3593 | -0.14918 | 0.51575 | -0.16089 | -0.29212 | 0.70117 | 0.37879
| 4931 | 0.37751 | -0.5011 | 0.5019 | 0.68711 | -0.28104 | 0.10798 | -0.14087 | 0.55604 | 0.18324 | -0.38934
| 4932 | 0.68488 | -0.019541 | -0.049789 | -0.044647 | 0.67581 | 0.83969 | 0.53 | -0.29099 | -0.033098 | 0.25133
| 4933 | -0.17302 | 0.15994 | 0.88642 | 0.35618 | 0.37159 | -0.35774 | -0.18373 | 0.68615 | 0.64405 | 0.39859
| 4934 | 0.62437 | 0.8618 | -0.47493 | -0.21597 | 0.57421 | -0.248 | -0.2265 | -0.21776 | 0.1868 | 0.91938
| 4935 | 0.41511 | 0.11711 | -0.050526 | -0.042347 | 0.18263 | 0.55044 | -0.009899 | -0.4206 | -0.10184 | -0.35046
| 4936 | 0.40259 | 0.13959 | -0.061224 | -0.59988 | -0.16304 | -0.43405 | -0.08136 | 0.061864 | 0.39494 | -0.77262
| 4937 | -0.67519 | 0.32524 | -0.73751 | 0.47856 | -0.40276 | 0.021992 | -0.045065 | -0.13115 | -0.58805 | -0.22058
| 4938 | -0.67488 | 0.79678 | 0.14601 | 0.42755 | 0.25307 | 0.5707 | 0.68968 | 0.060053 | 0.16519 | 0.29254
| 4939 | -0.3189 | 0.28747 | 0.089121 | -0.83538 | 0.029794 | 0.34403 | -0.72054 | -0.22818 | 0.009899 | 0.71104
| 4940 | -0.45751 | 0.16687 | 0.34617 | 0.065495 | -0.23823 | 0.41017 | 0.13948 | -0.025782 | 0.20596 | -0.41922
| 4941 | 0.44277 | -0.05348 | -0.2508 | -0.32317 | 0.46699 | 0.53967 | 0.32791 | -0.73261 | 0.64518 | -0.83721
| 4942 | 0.77662 | -0.4755 | -0.62224 | 0.87233 | -0.24336 | -0.15911 | -0.14531 | -0.13415 | -0.20823 | -0.56583
| 4943 | -0.21038 | 0.027837 | -0.59147 | 0.21546 | 0.27371 | 0.26973 | 0.26278 | -0.53149 | 0.025269 | -0.17799
| 4944 | -0.080381 | 0.19396 | -0.19956 | 0.37223 | -0.060053 | -0.32169 | -0.2326 | 0.33886 | 0.70453 | 0.27247
| 4945 | 0.057503 | 0.23823 | -0.37366 | -0.74096 | 0.19495 | 0.12805 | 0.4078 | -0.2948 | -0.38836 | 0.61051
| 4946 | 0.61646 | 0.5529 | 0.3186 | 0.14134 | -0.22019 | 0.48183 | 0.21866 | 0.0045604 | -0.54756 | 0.41187
| 4947 | 0.56745 | -0.059947 | -0.43035 | -0.83845 | -0.23678 | 0.0023528 | 0.13588 | -0.79384 | -0.14145 | -0.066565
| 4948 | -0.068281 | 0.074527 | 0.31993 | -0.33615 | -0.24867 | -0.21955 | 0.09088 | 0.067316 | -0.04099 | -0.038491
| 4949 | -0.42825 | -0.62543 | 0.31378 | 0.46605 | 0.5174 | -0.10362 | 0.12359 | -0.29993 | 0.024244 | -0.15389
| 4950 | -0.24165 | 0.35649 | 0.20307 | -0.074635 | 0.40159 | -0.2496 | -0.10273 | -0.39859 | 0.2431 | -0.11439
| 4951 | -0.61725 | -0.094848 | -0.070968 | 0.22637 | -0.17568 | -0.26904 | 0.51369 | -0.81318 | -0.21546 | 0.3363
| 4952 | 0.26278 | 0.067423 | -0.10139 | 0.52094 | -0.1962 | 0.57421 | 0.45292 | 0.12313 | -0.2567 | -0.61128
| 4953 | -0.11824 | -0.67061 | 0.63217 | -0.017401 | 0.16077 | 0.14274 | 0.552 | -0.25966 | -0.27151 | -0.77087
| 4954 | 0.73789 | -0.63654 | -0.66939 | -0.80947 | 0.16507 | 0.54867 | -0.16555 | 0.22328 | 0.21025 | -0.47512
| 4955 | 0.85893 | 0.45456 | -0.6407 | 0.77131 | 0.61077 | -0.024756 | -0.77306 | -0.27688 | -0.60364 | -0.36321
| 4956 | 0.21177 | 0.17982 | 0.75938 | 0.15816 | 0.44583 | -0.73037 | 0.25347 | -0.56583 | -0.31232 | -0.87876
| 4957 | 0.19495 | -0.41819 | -0.01091 | -0.75648 | 0.035894 | 0.1775 | 0.79191 | -0.30193 | -0.63931 | 0.67798
| 4958 | 0.27813 | -0.048633 | 0.21814 | 0.035168 | 0.70555 | 0.32317 | -0.21304 | -0.3248 | -0.17036 | 0.17641
| 4959 | -0.21101 | -0.1432 | 0.047477 | 0.062077 | 0.15507 | 0.63 | -0.093634 | 0.74603 | -0.33359 | 0.41613
| 4960 | 0.60541 | 0.0053644 | -0.015571 | 0.00055015 | 0.11756 | -0.0010506 | 0.052108 | 0.36731 | 0.29722 | 0.20772
| 4961 | -0.21725 | -0.42233 | 0.6703 | 0.30783 | 0.9089 | -0.54163 | -0.68871 | 0.1466 | 0.16448 | 0.18385
| 4962 | -0.47531 | 0.10563 | 0.51844 | 0.19981 | -0.36415 | -0.40443 | -0.31436 | 0.3568 | 0.38186 | -0.25562
| 4963 | 0.27605 | 0.38073 | -0.49118 | 0.13196 | 0.73561 | -0.1597 | 0.051475 | 0.32762 | 0.43955 | 0.14297
| 4964 | -0.37478 | -0.52471 | 0.27591 | 0.18667 | -0.19994 | 0.20407 | -0.37718 | 0.78068 | -0.53427 | 0.033098
| 4965 | -0.68871 | -0.076474 | 0.75 | -0.2985 | -0.22444 | 0.32169 | 0.18471 | 0.29921 | -0.17096 | -0.60138
| 4966 | -0.74761 | -0.36117 | 0.75363 | -0.38202 | 0.043496 | -0.042555 | 0.26577 | -0.40159 | -0.073339 | 0.5714
| 4967 | -0.56838 | 0.20987 | -0.1729 | 0.17617 | 0.42441 | 0.74564 | 0.55943 | 0.53643 | -0.27481 | -0.20621
| 4968 | 0.046428 | -0.33479 | -0.072908 | -0.5656 | -0.34693 | -0.27412 | -0.87233 | -0.012528 | 0.37143 | -0.10206
| 4969 | -0.77528 | -0.19334 | 0.071399 | 0.13797 | -0.33015 | 0.26754 | -0.098723 | -0.30064 | -0.43281 | -0.15863
| 4970 | -0.33 | 0.24681 | 0.34954 | 0.46906 | 0.51266 | -0.15354 | -0.47512 | -0.019235 | 0.12233 | 0.083103
| 4971 | -0.39859 | 0.32494 | 0.24363 | -0.25723 | 0.53924 | 0.68298 | 0.24204 | -0.093192 | -0.48164 | -0.0025533
| 4972 | -0.14145 | 0.028867 | 0.49651 | -0.02897 | 0.67366 | 0.3419 | 0.80895 | -0.05253 | -0.22637 | 0.27302
| 4973 | -0.4987 | 0.70251 | 0.52767 | -0.48882 | 0.33796 | 0.38657 | -0.074095 | -0.33269 | -0.11507 | 0.69422
| 4974 | 0.4717 | 0.17665 | -0.26945 | -0.54054 | 0.64829 | -0.16807 | 0.13115 | -0.27509 | -0.17568 | -0.081251
| 4975 | -0.15425 | -0.44674 | 0.28551 | -0.77483 | 0.71138 | 0.44782 | 0.3551 | -0.0035563 | 0.39131 | -0.11011
| 4976 | -0.35961 | 0.43635 | 0.038387 | -0.23547 | 0.91574 | 0.47265 | 0.16819 | 0.051791 | 0.15318 | 0.1025
| 4977 | 0.44674 | 0.3864 | -0.70862 | -0.083649 | -0.3375 | 0.24614 | -0.32925 | -0.095954 | 0.12416 | -0.73827
| 4978 | 0.60719 | 0.12074 | 0.19446 | -0.48183 | 0.072692 | 0.67766 | -0.84284 | 0.084194 | -0.061544 | -0.34494
| 4979 | -0.82824 | 0.033718 | -0.70623 | -0.033098 | -0.045589 | 0.06165 | -0.33164 | -0.13127 | 0.14918 | 0.17508
| 4980 | -0.033408 | -0.75201 | -0.13346 | 0.16185 | -0.48435 | 0.09187 | -0.22353 | -0.12943 | 0.43211 | 0.12874
| 4981 | -0.079402 | -0.0080827 | -0.63163 | -0.37494 | 0.0053644 | -0.22715 | 0.41528 | 0.66489 | -0.54185 | 0.6319
| 4982 | 0.012225 | -0.56262 | 0.1786 | -0.10608 | 0.69917 | -0.24376 | -0.45127 | 0.13774 | 0.088243 | 0.18128
| 4983 | 0.30653 | 0.031548 | 0.28691 | 0.29212 | 0.73261 | -0.65287 | -0.3681 | 0.14041 | 0.32361 | -0.79628
| 4984 | 0.22883 | 0.95877 | 0.95641 | 0.32317 | 0.011415 | -0.015571 | -0.41238 | -0.18975 | -0.12793 | -0.64744
| 4985 | 0.10273 | 0.48473 | -0.042242 | -0.067208 | 0.63081 | -0.10776 | 0.30567 | -0.24827 | -0.53363 | 0.055066
| 4986 | 0.16916 | -0.23026 | -0.90461 | -0.048212 | -0.59813 | -0.35293 | -0.14753 | -0.53946 | -0.58371 | 0.46737
| 4987 | 0.79048 | -0.78344 | 0.06914 | 0.44098 | -0.53686 | -0.72054 | 0.084085 | -0.41579 | 0.60364 | 0.4799
| 4988 | 0.50432 | 0.094959 | 0.37366 | -0.0020521 | -0.17109 | -0.3245 | -0.35587 | -0.26549 | -0.23364 | 0.60339
| 4989 | 0.19322 | -0.029279 | -0.30812 | -0.10351 | -0.36133 | 0.35262 | 0.25027 | 0.23221 | -0.48087 | 0.34099
| 4990 | 0.62066 | -0.44909 | -0.019337 | 0.083867 | 0.64321 | -0.27536 | -0.67458 | 0.60188 | -0.12119 | -0.32494
| 4991 | -0.58419 | 0.024039 | -0.71452 | -0.20697 | 0.29551 | 0.45511 | 0.24588 | 0.54098 | -0.8366 | 0.53043
| 4992 | 0.032374 | -0.3245 | -0.039219 | 0.051053 | 0.28425 | -0.32776 | -0.27854 | 0.025372 | -0.5009 | -0.7881
| 4993 | -0.27357 | 0.34448 | -0.58107 | 0.56699 | 0.71452 | -0.48707 | 0.32022 | -0.086709 | -0.33917 | 0.14157
| 4994 | -0.23026 | 0.032374 | 0.065709 | 0.52661 | 0.020766 | 0.5005 | 0.80947 | -0.20709 | 0.10865 | 0.16988
| 4995 | 0.38526 | 0.0085869 | 0.14613 | -0.17133 | -0.76957 | 0.40763 | 0.20169 | -0.41888 | 0.63572 | -0.14835
| 4996 | -0.13762 | 0.035065 | 0.50513 | 0.10641 | 0.28369 | 0.12393 | 0.002453 | 0.59 | -0.62543 | -0.01
| 4997 | 0.10072 | 0.14871 | -0.30164 | -0.39593 | 0.62892 | -0.31772 | 0.51492 | 0.48357 | 0.64433 | -0.071507
| 4998 | -0.7488 | 0.14076 | -0.15935 | 0.7623 | -0.28579 | -0.34754 | -0.53535 | 0.42164 | -0.0073772 | -0.34038
| 4999 | -0.24138 | 0.41374 | -0.41922 | -0.14753 | -0.17957 | 0.58708 | -0.66789 | 0.41272 | 0.21355 | -0.2343
| 5000 | -0.64914 | -0.32302 | 0.55966 | -0.032064 | 0.51513 | 0.32732 | 0.17811 | -0.54823 | 0.089231 | -0.46381
| 5001 | 0.23836 | 0.17884 | -0.48222 | -0.26617 | 0.3248 | 0.34159 | -0.57468 | -0.81053 | 0.33464 | -0.25629
| 5002 | 0.38024 | 0.35448 | 0.29864 | 0.67304 | 0.10161 | 0.08485 | -0.46868 | -0.080489 | 0.10832 | 0.037659
| 5003 | -0.14859 | 0.3923 | 0.82308 | 0.16436 | 0.53021 | -0.062397 | 0.43991 | -0.32911 | -0.39775 | 0.14742
| 5004 | -0.57 | -0.084085 | -0.027735 | 0.19819 | -0.81 | -0.69 | -0.43831 | 0.60038 | 0.67674 | -0.43476
| 5005 | 0.71804 | 0.41017 | 0.38755 | 0.19185 | 0.11462 | 0.21063 | -0.13253 | -0.21114 | 0.6044 | -0.12954
| 5006 | 0.17278 | 0.2784 | -0.51328 | 0.1841 | -0.27151 | 0.53299 | 0.65868 | -0.34693 | -0.076258 | -0.45292
| 5007 | -0.30523 | 0.32836 | -0.24007 | -0.3306 | 0.33164 | -0.12885 | -0.6811 | -0.15106 | 0.38121 | -0.71069
| 5008 | 0.069033 | -0.068496 | -0.93 | 0.3375 | -0.48765 | 0.012022 | 0.036828 | -0.45383 | 0.61154 | -0.86847
| 5009 | -0.74135 | -0.32836 | -0.15673 | 0.49118 | -0.085287 | -0.16221 | -0.36984 | -0.3245 | 0.32273 | 0.17544
| 5010 | -0.37254 | -0.10195 | 0.60088 | -0.51657 | 0.037036 | 0.49295 | -0.14613 | -0.053374 | -0.87958 | -0.021685
| 5011 | 0.053058 | -0.03465 | -0.37127 | -0.41 | -0.88381 | -0.21381 | 0.30928 | -0.2744 | -0.35077 | -0.31232
| 5012 | -0.32524 | 0.069677 | -0.017198 | -0.14297 | -0.1634 | 0.62224 | -0.57093 | 0.31029 | -0.099278 | -0.088573
| 5013 | 0.2791 | -0.20949 | 0.17278 | 0.036102 | 0.081577 | 0.10418 | -0.0029544 | -0.44855 | 0.23443 | -0.84736
| 5014 | 0.83538 | 0.077666 | 0.033201 | 0.84801 | 0.070861 | -0.079946 | -0.1513 | -0.82084 | -0.74135 | 0.25
| 5015 | -0.19856 | 0.97764 | -0.11847 | 0.14519 | 0.40008 | 0.18128 | -0.080598 | 0.27605 | -0.71663 | 0.073339
| 5016 | -0.55717 | 0.14847 | -0.13127 | 0.066137 | 0.5098 | -0.47531 | 0.54845 | -0.66489 | -0.77395 | -0.48707
| 5017 | -0.17617 | 0.33585 | 0.16747 | -0.10117 | -0.061331 | -0.77 | 0.27412 | 0.096285 | 0.43352 | 0.40848
| 5018 | -0.44982 | -0.42112 | 0.017503 | 0.44945 | -0.536 | -0.46605 | 0.22805 | 0.73637 | -0.26604 | 0.2175
| 5019 | 0.13173 | 0.22792 | 0.024244 | 0.50573 | 0.12816 | -0.62171 | 0.35432 | 0.43511 | 0.21904 | 0.39164
| 5020 | -0.010808 | 0.5347 | -0.47284 | 0.27854 | 0.032891 | -0.09121 | 0.33826 | -0.11972 | -0.42459 | 0.44638
| 5021 | 0.01263 | 0.21572 | 0.9245 | 0.70318 | -0.19757 | 0.42842 | -0.64602 | -0.43866 | 0.062077 | -0.2326
| 5022 | 0.092421 | -0.57186 | -0.30711 | -0.64744 | 0.067423 | -0.26088 | 0.38478 | 0.8366 | -0.83477 | 0.43281
| 5023 | 0.17096 | -0.0025533 | 0.5728 | -0.02097 | -0.69 | -0.10641 | 0.10094 | 0.41391 | 0.3727 | -0.09529
| 5024 | -0.30667 | -0.50796 | -0.30466 | 0.59294 | -0.67798 | 0.10172 | 0.58083 | 0.082885 | -0.2773 | -0.13346
| 5025 | 0.030516 | 0.37414 | 0.30725 | -0.043496 | -0.21674 | -0.054643 | -0.20395 | -0.2076 | -0.82084 | -0.2744
| 5026 | -0.39543 | 0.32955 | 0.49137 | 0.08343 | 0.78763 | 0.29353 | -0.59392 | 0.36337 | -0.83845 | -0.73942
| 5027 | -0.58155 | -0.52936 | 0.32302 | -0.084085 | -0.29381 | -0.26318 | 0.72705 | 0.31232 | 0.50271 | -0.25899
| 5028 | -0.25818 | 0.39461 | -0.38137 | 0.70966 | 0.026912 | 0.31218 | -0.32896 | 0.51328 | 0.24217 | 0.23495
| 5029 | -0.72705 | -0.55717 | 0.28845 | -0.018012 | -0.074635 | 0.067208 | -0.86847 | 0.022708 | 0.15923 | -0.089341
| 5030 | -0.0078811 | 0.26577 | -0.087038 | 0.10351 | -0.21802 | 0.38218 | -0.023834 | 0.27633 | 0.077341 | 0.067959
| 5031 | -0.022401 | -0.58419 | 0.28986 | 0.29014 | 0.31816 | 0.10563 | 0.18422 | 0.83059 | -0.46906 | 0.13127
| 5032 | 0.10384 | 0.65927 | 0.0018517 | -0.53342 | 0.20924 | -0.086271 | -0.57609 | 0.15377 | -0.15602 | 0.033718
| 5033 | 0.36952 | 0.6044 | -0.35634 | 0.15875 | 0.44873 | -0.18299 | -0.14215 | 0.68235 | 0.041616 | -0.27951
| 5034 | 0.15935 | -0.5529 | -0.28439 | -0.37286 | 0.64546 | -0.70589 | -0.27467 | -0.048633 | -0.29822 | -0.13611
| 5035 | 0.75201 | 0.3074 | 0.31758 | -0.36905 | 0.2052 | -0.51637 | -0.39676 | -0.30466 | -0.16603 | -0.46512
| 5036 | -0.43035 | -0.026501 | 0.41034 | -0.51492 | -0.19086 | 0.034236 | 0.7512 | -0.65663 | 0.096396 | 0.69129
| 5037 | 0.58684 | -0.33105 | -0.13507 | 0.46325 | -0.081251 | 0.046638 | 0.0055655 | -0.29 | 0.03579 | -0.50472
| 5038 | -0.57893 | -0.28035 | -0.29113 | 0.42842 | 0.25214 | -0.46812 | 0.14695 | -0.21981 | 0.26986 | -0.092421
| 5039 | -0.3242 | 0.336 | -0.49691 | -0.37638 | 0.36794 | -0.14472 | -0.6786 | 0.10865 | 0.15 | -0.04538
| 5040 | 0.31349 | -0.7839 | -0.33164 | -0.44619 | 0.19806 | -0.65985 | -0.15377 | 0.55989 | 0.20069 | -0.018929
| 5041 | 0.11372 | 0.22289 | -0.069892 | -0.30021 | -0.23901 | -0.13069 | -0.19272 | 0.35463 | 0.69817 | -0.38218
| 5042 | 0.1315 | -0.43546 | -0.020766 | -0.49691 | -0.19161 | -0.33164 | -0.051159 | 0.24681 | 0.20056 | -0.21495
| 5043 | 0.31247 | -0.72596 | -0.3864 | 0.86325 | 0.48048 | -0.56699 | -0.10978 | -0.64943 | -0.04172 | -0.34205
| 5044 | 0.7816 | 0.32598 | -0.30826 | -0.86546 | 0.56422 | 0.031754 | -0.86252 | 0.041407 | 0.52724 | -0.018623
| 5045 | 0.39875 | 0.21789 | 0.61568 | 0.7816 | 0.73789 | 0.19944 | 0.01842 | -0.2402 | 0.30653 | 0.71946
| 5046 | -0.50412 | 0.30207 | 0.098501 | 0.23796 | 0.45018 | -0.66281 | 0.79 | -0.60821 | 0.55134 | 0.42389
| 5047 | 0.49 | -0.79433 | 0.28369 | -0.47741 | -0.6833 | 0.45548 | -0.2488 | -0.52052 | -0.81588 | -0.29679
| 5048 | 0.14519 | 0.31436 | 0.48048 | -0.73524 | -0.59714 | -0.040677 | 0.97354 | 0.18006 | -0.46718 | 0.47227
| 5049 | -0.077883 | 0.069033 | 0.61231 | 0.1253 | 0.37976 | 0.1706 | 0.1628 | -0.023322 | 0.66103 | -0.20571
| 5050 | 0.20924 | -0.10006 | 0.87 | -0.2602 | 0.15602 | -0.86399 | -0.037867 | -0.54756 | -0.11711 | -0.40159
| 5051 | 0.5015 | 0.10462 | 0.068603 | -0.61646 | -0.21904 | -0.6811 | 0.46362 | 0.2524 | 0.22792 | -0.54185
| 5052 | -0.22702 | 0.50918 | -0.53535 | -0.39692 | 0.37944 | -0.5199 | -0.081142 | 0.0911 | -0.56814 | -0.06496
| 5053 | 0.48668 | 0.41751 | 0.66758 | 0.67121 | 0.039011 | -0.31363 | 0.13577 | -0.2659 | 0.78251 | -0.45146
| 5054 | -0.136 | -0.41974 | -0.011719 | -0.29779 | 0.036724 | -0.16089 | -0.48029 | 0.09077 | 0.19297 | 0.81212
| 5055 | 0.043391 | 0.21866 | -0.62251 | 0.28509 | 0.22199 | 0.58903 | -0.32007 | 0.14589 | 0.060692 | 0.45219
| 5056 | 0.60643 | 0.47132 | 0.19284 | 0.27965 | -0.38445 | 0.037867 | 0.12644 | -0.5009 | -0.21789 | 0.55943
| 5057 | -0.3751 | 0.39527 | -0.13161 | -0.31553 | 0.11609 | -0.36699 | 0.26468 | 0.31247 | -0.31174 | 0.088024
| 5058 | 0.19433 | 0.32273 | 0.13611 | -0.70251 | -0.12782 | 0.079946 | 0.5768 | -0.066137 | -0.067852 | -0.73149
| 5059 | 0.12199 | -0.22353 | -0.22728 | -0.32302 | -0.28719 | 0.12416 | -0.15768 | -0.2791 | -0.20119 | -0.3211
| 5060 | 0.49157 | -0.18116 | 0.1091 | -0.18988 | 0.34816 | -0.58903 | 0.52303 | -0.1072 | 0.54978 | -0.51802
| 5061 | -0.060479 | -0.19732 | -0.55067 | 0.84031 | 0.15472 | -0.60846 | -0.0995 | 0.026398 | -0.38283 | 0.15295
| 5062 | 0.32539 | 0.64574 | 0.21763 | -0.061864 | 0.5412 | 0.30179 | -0.13415 | 0.15354 | -0.14976 | -0.22974
| 5063 | 0.3864 | 0.0866 | 0.055278 | 0.43334 | -0.57327 | 0.16304 | 0.38105 | -0.37654 | -0.11564 | 0.22045
| 5064 | 0.14355 | 0.10574 | 0.08978 | 0.024244 | 0.01547 | -0.62946 | -0.30667 | -0.53427 | 0.077991 | -0.049369
| 5065 | -0.27827 | -0.11417 | -0.19582 | 0.12222 | -0.77 | 0.37175 | 0.079077 | -0.18067 | -0.19396 | 0.62731
| 5066 | -0.87876 | -0.33269 | 0.46849 | 0.56745 | -0.088243 | 0.71035 | 0.09022 | 0.48493 | 0.13415 | -0.0004501
| 5067 | 0.15472 | -0.15413 | 0.1253 | 0.81 | -0.0029544 | 0.74682 | 0.052635 | -0.23013 | -0.032581 | -0.3735
| 5068 | 0.79384 | 0.30423 | 0.48824 | -0.64042 | 0.2773 | -0.4588 | -0.58515 | -0.2356 | -0.29964 | -0.44224
| 5069 | -0.17921 | -0.41957 | -0.39296 | -0.10462 | -0.037036 | -0.35139 | 0.12176 | -0.91 | -0.69259 | -0.4717
| 5070 | -0.23039 | -0.086162 | -0.85543 | -0.21317 | -0.09518 | 0.27178 | 0.24853 | -0.39477 | 0.56907 | -0.5201
| 5071 | 0.11892 | -0.37976 | -0.8618 | -0.57727 | -0.33555 | 0.07 | -0.074203 | 0.13092 | -0.69751 | 0.13196
| 5072 | 0.30236 | 0.059415 | 0.11191 | 0.23338 | 0.23378 | -0.89656 | -0.81053 | 0.53192 | -0.1926 | -0.24973
| 5073 | -0.19906 | -0.34327 | 0.42233 | -0.25147 | 0.63931 | -0.28341 | -0.1389 | -0.035894 | -0.12977 | 0.15365
| 5074 | -0.3735 | -0.1253 | -0.34129 | -0.41648 | -0.032064 | 0.88909 | -0.12074 | -0.021787 | -0.34724 | -0.36747
| 5075 | 0.14017 | 0.47703 | -0.4898 | -0.23443 | 0.51492 | 0.023629 | -0.27055 | -0.25939 | -0.58976 | -0.2484
| 5076 | -0.34357 | -0.23678 | 0.53924 | 0.094075 | 0.2893 | -0.52115 | -0.01 | -0.47741 | 0.53256 | -0.79433
| 5077 | -0.28063 | -0.013846 | -0.2659 | -0.38902 | -0.096175 | 0.14227 | 0.3297 | -0.30682 | 0.24495 | -0.11835
| 5078 | -0.55672 | 0.20357 | -0.6952 | -0.56814 | 0.35108 | 0.034029 | 0.50654 | 0.32287 | 0.70828 | -0.85201
| 5079 | 0.16077 | -0.30064 | -0.63765 | -0.14742 | -0.2431 | -0.59813 | -0.34327 | 0.11564 | 0.15354 | -0.41085
| 5080 | 0.098723 | -0.73827 | 0.23967 | -0.73675 | 0.46868 | -0.40326 | -0.15685 | 0.90253 | -0.89276 | 0.66459
| 5081 | -0.0013509 | 0.7735 | -0.96394 | -0.74761 | 0.14355 | -0.046952 | 0.50231 | -0.14496 | -0.29 | -0.32332
| 5082 | 0.3767 | -0.57822 | -0.39098 | -0.67335 | -0.1221 | -0.48648 | 0.035894 | 0.15283 | -0.1118 | 0.36196
| 5083 | 0.60949 | 0.30971 | 0.48376 | 0.33856 | 0.010808 | 0.32361 | 0.19433 | 0.39148 | 0.052424 | 0.45383
| 5084 | -0.11315 | 0.51451 | -0.46269 | 0.6939 | 0.26373 | 0.56954 | 0.38348 | -0.30351 | -0.14449 | 0.55156
| 5085 | 0.27564 | -0.2225 | -0.0059678 | 0.10585 | -0.47512 | 0.019235 | -0.30179 | 0.28831 | -0.0091922 | -0.70725
| 5086 | -0.47798 | -0.69422 | 0.3804 | 0.19247 | 0.078317 | -0.18116 | -0.62145 | 0.1229 | -0.039844 | -0.32896
| 5087 | 0.14496 | 0.39593 | 0.85337 | 0.024551 | -0.026604 | 0.48338 | -0.68425 | -0.007075 | 0.26617 | 0.16006
| 5088 | 0.23626 | 0.76104 | -0.56606 | 0.27591 | -0.26359 | -0.33134 | 0.95417 | 0.12793 | -0.082667 | -0.09209
| 5089 | -0.29864 | 0.43884 | -0.42912 | -0.50939 | -0.51123 | -0.10462 | 0.3025 | -0.54889 | 0.14134 | 0.16591
| 5090 | -0.067316 | 0.14355 | -0.29964 | -0.18189 | -0.10184 | 0.04381 | 0.69357 | 0.34327 | 0.075284 | 0.49771
| 5091 | -0.35836 | 0.18397 | -0.20257 | -0.39576 | 0.029176 | 0.68456 | 0.13392 | -0.077016 | 0.91693 | 0.43991
| 5092 | -0.33479 | -0.02097 | -0.027426 | -0.58467 | 0.75979 | 0.018929 | 0.60744 | -0.18471 | 0.22379 | -0.16304
| 5093 | 0.049579 | 0.0081835 | 0.19669 | 0.28705 | -0.20382 | 0.23993 | 0.048738 | -0.06914 | -0.18079 | 0.67121
| 5094 | -0.017198 | 0.020868 | 0.57374 | -0.65172 | 0.71522 | -0.11677 | 0.61387 | -0.9272 | -0.41221 | -0.53406
| 5095 | 0.3923 | -0.53859 | 0.25281 | -0.77572 | -0.85474 | -0.2147 | 0.46943 | -0.29183 | 0.12439 | 0.19223
| 5096 | 0.10206 | 0.22676 | -0.29296 | -0.44692 | 0.61464 | -0.73373 | -0.42441 | -0.2326 | 0.12188 | 0.026398
| 5097 | 0.13473 | 0.66578 | -0.1694 | 0.13808 | -0.54294 | -0.68775 | -0.09033 | 0.13519 | -0.34205 | -0.25053
| 5098 | 0.17945 | 0.33932 | -0.14332 | -0.013643 | -0.16952 | -0.092972 | -0.67704 | 0.29438 | -0.3245 | -0.77662
| 5099 | -0.84605 | 0.31145 | 0.71347 | -0.14449 | 0.52052 | 0.59269 | 0.53556 | 0.058565 | -0.010606 | 0.51472
| 5100 | 0.024654 | -0.19062 | -0.59664 | -0.020357 | 0.1162 | 0.35031 | 0.089012 | 0.55514 | -0.27896 | -0.22032
| 5101 | 0.32287 | 0.83118 | -0.29452 | 0.9134 | -0.12416 | -0.47512 | 0.10865 | 0.20094 | -0.18361 | -0.16209
| 5102 | 0.9134 | 0.464 | 0.0062697 | 0.67061 | -0.23 | 0.092531 | 0.8882 | -0.10854 | 0.24814 | 0.0044599
| 5103 | 0.039844 | 0.32791 | 0.85682 | -0.79678 | -0.22109 | 0.32302 | 0.8366 | -0.6044 | 0.0173 | -0.3303
| 5104 | -0.81642 | 0.12943 | -0.58612 | 0.10921 | -0.13449 | 0.3038 | 0.16292 | 0.4983 | 0.69097 | -0.40025
| 5105 | -0.092972 | 0.45935 | 0.31714 | 0.17982 | -0.61464 | 0.81318 | 0.97764 | 0.20697 | 0.83297 | -0.13115
| 5106 | -0.45219 | 0.4999 | 0.39626 | 0.75526 | 0.65229 | 0.35899 | -0.22109 | -0.55357 | -0.53578 | -0.003456
| 5107 | 0.60088 | 0.51534 | 0.013542 | 0.18938 | 0.37398 | 0.52809 | 0.048212 | -0.19931 | -0.23312 | 0.35448
| 5108 | -0.11835 | -0.4553 | -0.35852 | 0.65402 | -0.14824 | -0.30322 | 0.052424 | -0.2133 | 0.67643 | 0.0023528
| 5109 | 0.4828 | 0.63682 | -0.4134 | 0.20207 | 0.24125 | 0.27896 | 0.68298 | 0.2516 | 0.8366 | -0.22508
| 5110 | 0.0075787 | 0.40578 | 0.097503 | -0.36652 | 0.12245 | -0.24125 | 0.49433 | -0.13588 | 0.34831 | -0.5806
| 5111 | 0.56468 | -0.20144 | 0.3366 | -0.8043 | -0.78297 | -0.59343 | 0.3864 | 0.45146 | 0.27274 | -0.47455
| 5112 | 0.052319 | 0.19148 | -0.45073 | 0.64715 | -0.73111 | -0.038699 | 0.064746 | -0.14204 | -0.042242 | -0.10697
| 5113 | -0.22534 | -0.12313 | -0.34099 | 0.067423 | 0.47703 | -0.60872 | 0.09132 | -0.12644 | 0.55537 | 0.23941
| 5114 | 0.5019 | -0.42825 | 0.12267 | 0.16795 | 0.32066 | 0.31758 | 0.3129 | 0.10876 | 0.37783 | -0.20709
| 5115 | 0.30942 | -0.75403 | -0.66251 | -0.32509 | -0.19198 | -0.29212 | 0.26658 | 0.1797 | -0.39809 | -0.29722
| 5116 | 0.22315 | -0.36683 | 0.26986 | 0.30322 | 0.26808 | -0.15661 | 0.95 | 0.12188 | -0.29028 | 0.17302
| 5117 | 0.074527 | -0.48765 | -0.12656 | -0.57798 | -0.18766 | 0.32125 | 0.14671 | -0.23052 | -0.62597 | -0.61206
| 5118 | -0.22598 | 0.62277 | 0.27674 | 0.087366 | 0.1559 | -0.11214 | 0.88381 | 0.29523 | -0.25953 | 0.26631
| 5119 | -0.31073 | -0.31392 | 0.54011 | -0.27123 | -0.010808 | -0.62624 | -0.24641 | -0.31131 | -0.36368 | 0.056973
| 5120 | -0.12713 | 0.16868 | 0.16197 | -0.2773 | 0.11915 | -0.095401 | -0.068067 | -0.45146 | 0.086381 | 0.32911
| 5121 | -0.073555 | 0.6407 | -0.07 | -0.04517 | 0.79384 | 0.5224 | -0.23757 | 0.67612 | 0.23652 | -0.52261
| 5122 | -0.70828 | -0.021787 | -0.53881 | -0.14111 | -0.18201 | 0.14145 | -0.26413 | -0.92584 | -0.53256 | -0.61934
| 5123 | -0.064105 | 0.70487 | -0.66638 | -0.21444 | -0.085943 | 0.077774 | -0.91112 | -0.097836 | 0.069785 | -0.44656
| 5124 | 0.53707 | 0.58131 | -0.15851 | -0.13924 | 0.54778 | 0.79191 | 0.015673 | -0.30107 | 0.45917 | -0.54448
| 5125 | 0.31743 | -0.36196 | -0.23757 | 0.236 | 0.61542 | 0.64349 | -0.35696 | 0.25549 | 0.12839 | 0.54624
| 5126 | -0.46344 | 0.079402 | -0.46251 | 0.54426 | -0.066244 | -0.44098 | -0.86923 | -0.0004501 | -0.43158 | -0.22225
| 5127 | 0.29993 | 0.093854 | 0.53149 | -0.61961 | 0.19969 | 0.097725 | -0.5009 | 0.25013 | -0.38024 | 0.13184
| 5128 | -0.68679 | -0.54734 | -0.29822 | -0.21063 | 0.55492 | 0.5608 | 0.6319 | -0.6149 | 0.19508 | -0.093413
| 5129 | 0.21508 | 0.028661 | -0.18434 | 0.079728 | -0.57303 | -0.093744 | 0.038179 | -0.55156 | 0.074095 | -0.21661
| 5130 | 0.18704 | -0.0087886 | -0.37702 | 0.13634 | 0.20006 | 0.33494 | -0.39709 | -0.71522 | -0.15709 | 0.2326
| 5131 | -0.33239 | 0.36243 | -0.60263 | 0.46344 | -0.014252 | 0.24495 | 0.044333 | -0.13173 | 0.094959 | 0.14976
| 5132 | -0.39049 | -0.22586 | -0.044437 | -0.64914 | 0.13797 | 0.11892 | 0.15828 | -0.15141 | -0.40025 | 0.1533
| 5133 | 0.74174 | -0.041303 | 0.348 | 0.25912 | 0.20219 | -0.2823 | -0.17217 | -0.15059 | -0.54514 | -0.31641
| 5134 | -0.70555 | -0.28007 | 0.60795 | -0.59049 | 0.29268 | -0.4417 | 0.0050628 | 0.0050628 | 0.24522 | -0.77707
| 5135 | 0.26795 | -0.21853 | 0.19794 | 0.79433 | -0.12954 | -0.14437 | -0.13971 | 0.69718 | -0.34601 | 0.030516
| 5136 | 0.085724 | 0.80328 | -0.58347 | 0.76442 | -0.64744 | -0.039531 | 0.81 | -0.25831 | -0.25482 | 0.24747
| 5137 | 0.3451 | -0.32747 | -0.050737 | -0.28635 | -0.31816 | 0.64687 | 0.030516 | 0.61646 | -0.27827 | 0.17036
| 5138 | -0.41255 | -0.24257 | -0.12667 | -0.2823 | -0.43264 | -0.37016 | 0.045694 | 0.41511 | -0.44583 | -0.27702
| 5139 | -0.58467 | 0.4668 | -0.4392 | -0.22212 | -0.72486 | 0.42147 | 0.14624 | 0.13866 | -0.026912 | 0.80635
| 5140 | 0.009899 | 0.1118 | -0.5245 | -0.42737 | 0.29736 | -0.68235 | 0.22444 | -0.24973 | -0.52157 | -0.30322
| 5141 | 0.31611 | -0.58976 | -0.29807 | -0.70083 | 0.32896 | -0.62811 | -0.034029 | 0.18104 | 0.20094 | 0.38267
| 5142 | 0.57047 | -0.16591 | 0.36841 | 0.46362 | -0.015774 | 0.63271 | -0.3422 | -0.59738 | 0.56285 | 0.17253
| 5143 | 0.21533 | -0.25093 | 0.28425 | -0.097725 | 0.59988 | 0.19707 | 0.43546 | -0.47436 | -0.038491 | 0.82824
| 5144 | 0.11881 | 0.75444 | 0.56354 | 0.0026535 | 0.94804 | -0.28467 | -0.41613 | 0.0029544 | -0.18594 | 0.01791
| 5145 | 0.042033 | 0.036724 | -0.40477 | 0.4206 | -0.15899 | 0.13207 | -0.36149 | -0.17229 | -0.19806 | 0.87155
| 5146 | -0.072908 | -0.08343 | -0.54011 | -0.5436 | 0.67643 | -0.079511 | -0.27591 | 0.87631 | 0.53751 | 0.6249
| 5147 | 0.56057 | 0.17169 | -0.16209 | 0.16856 | 0.14169 | 0.14988 | 0.14847 | 0.0048618 | 0.23809 | 0.17823
| 5148 | -0.35525 | 0.23862 | 0.008486 | 0.25966 | -0.4991 | -0.7042 | -0.4828 | -0.12725 | 0.41802 | -0.57538
| 5149 | 0.38234 | -0.43088 | 0.35015 | 0.14636 | -0.66429 | -0.063144 | -0.11665 | -0.44692 | 0.029382 | -0.36762
| 5150 | -0.18446 | 0.41819 | 0.13762 | -0.21393 | 0.32613 | 0.5347 | -0.62811 | 0.30855 | -0.065923 | 0.09154
| 5151 | 0.44493 | -0.64687 | -0.023015 | 0.26754 | 0.35077 | -0.65634 | -0.27522 | -0.61 | -0.14636 | 0.2047
| 5152 | -0.05496 | -0.48863 | 0.5436 | -0.22702 | 0.20722 | 0.11711 | 0.12977 | -0.12656 | -0.37815 | 0.19074
| 5153 | 0.081033 | 0.074095 | 0.46102 | -0.21038 | 0.56907 | 0.70487 | 0.65985 | 0.18422 | 0.1706 | -0.67061
| 5154 | 0.10028 | -0.13253 | -0.35031 | 0.58203 | -0.55223 | -0.38089 | -0.49354 | 0.17483 | 0.13913 | -0.41528
| 5155 | -0.014556 | -0.10764 | -0.0027538 | -0.13426 | -0.87958 | -0.092531 | 0.1879 | -0.82422 | -0.73411 | 0.46981
| 5156 | 0.43973 | -0.69 | -0.074095 | 0.27979 | -0.51369 | 0.23117 | 0.40393 | 0.44583 | 0.27938 | -0.048212
| 5157 | 0.31058 | 0.87311 | 0.33841 | 0.14976 | -0.21025 | -0.21482 | -0.50231 | 0.67091 | -0.18471 | -0.85
| 5158 | 0.39082 | -0.25656 | -0.27288 | 0.22263 | -0.36431 | -0.26264 | 0.97 | 0.041199 | 0.69488 | 0.55223
| 5159 | -0.061437 | -0.20899 | -0.74251 | -0.24389 | -0.46251 | 0.32406 | -0.39082 | 0.29651 | 0.50918 | 0.66429
| 5160 | 0.07183 | 0.017096 | 0.65489 | 0.087805 | -0.53277 | 0.70691 | -0.24787 | -0.095069 | 0.13311 | 0.3186
| 5161 | -0.60289 | 0.019235 | -0.61908 | -0.27868 | -0.087476 | 0.12702 | 0.2985 | 0.8043 | 0.28216 | 0.14309
| 5162 | -0.94432 | -0.17217 | -0.3038 | -0.24283 | 0.00055015 | -0.36415 | -0.016181 | -0.08343 | -0.1879 | 0.71069
| 5163 | -0.14041 | 0.50412 | 0.252 | -0.1072 | 0.61026 | 0.60013 | 0.51657 | 0.4293 | -0.11552 | -0.51554
| 5164 | -0.19508 | 0.17641 | 0.20646 | -0.60238 | 0.56057 | 0.4564 | 0.2941 | 0.4997 | -0.47512 | -0.075716
| 5165 | 0.27619 | 0.059202 | 0.6382 | 0.4993 | -0.43688 | 0.79433 | -0.35712 | -0.1418 | -0.11858 | 0.46661
| 5166 | -0.036932 | -0.16735 | 0.62224 | 0.34296 | -0.33917 | -0.24588 | -0.026912 | -0.0012508 | 0.12862 | 0.51782
| 5167 | -0.22792 | 0.039635 | 0.1769 | 0.22624 | 0.19956 | -0.2076 | -0.72233 | -0.30007 | 0.15484 | 0.013744
| 5168 | 0.31363 | -0.057079 | -0.1269 | 0.055807 | 0.48726 | 0.0014511 | 0.55402 | -0.24667 | -0.031341 | -0.010808
| 5169 | 0.16591 | -0.024859 | -0.71347 | 0.0038574 | -0.052952 | 0.39477 | -0.24363 | 0.86399 | 0.036621 | 0.45917
| 5170 | -0.048738 | -0.0090913 | -0.32169 | 0.068388 | -0.3817 | -0.093413 | -0.28663 | 0.095069 | 0.28481 | -0.5098
| 5171 | -0.07 | -0.1694 | -0.010404 | 0.2356 | 0.14029 | -0.29254 | -0.32643 | -0.69586 | -0.37143 | 0.54558
| 5172 | 0.79531 | 0.34372 | -0.009697 | 0.1752 | -0.39543 | -0.00065021 | -0.49572 | 0.15094 | 0.22495 | 0.15744
| 5173 | -0.4683 | 0.52534 | 0.21279 | -0.30552 | 0.52492 | 0.12644 | 0.030206 | -0.54229 | -0.36857 | 0.45972
| 5174 | -0.35293 | 0.3662 | 0.11711 | 0.13138 | -0.43458 | -0.60364 | -0.61206 | -0.34053 | 0.7569 | 0.15306
| 5175 | 0.075608 | -0.19844 | 0.26604 | -0.62624 | 0.68552 | 0.39775 | 0.55582 | 0.12782 | 0.71173 | 0.75444
| 5176 | 0.18446 | -0.37223 | 0.077232 | -0.31392 | -0.11858 | 0.10429 | -0.28174 | -0.63986 | 0.35899 | 0.70386
| 5177 | 0.36731 | -0.29921 | 0.264 | -0.1082 | 0.76913 | 0.25441 | -0.28285 | 0.13011 | -0.53213 | -0.021174
| 5178 | 0.19025 | -0.50351 | -0.083539 | 0.14099 | -0.34281 | -0.16711 | -0.00025003 | 0.52366 | 0.15792 | -0.01547
| 5179 | 0.37191 | 0.18422 | 0.46587 | 0.37992 | 0.19099 | 0.02568 | -0.38543 | 0.52115 | -0.52703 | -0.30913
| 5180 | 0.19223 | 0.30222 | -0.81053 | -0.077883 | 0.6407 | -0.89464 | -0.65634 | 0.15247 | 0.065281 | -0.32037
| 5181 | 0.37048 | 0.39692 | -0.7005 | 0.3189 | 0.13727 | -0.18055 | -0.015165 | -0.1353 | -0.48299 | 0.3425
| 5182 | -0.32717 | -0.63765 | 0.0173 | 0.049895 | -0.51802 | 0.5883 | -0.21814 | -0.13797 | 0.26386 | 0.011719
| 5183 | -0.071291 | 0.080381 | -0.47019 | 0.14777 | 0.10429 | -0.88731 | -0.27398 | 0.59196 | -0.49098 | 0.34174
| 5184 | -0.59024 | -0.21355 | 0.88467 | -0.63931 | 0.64886 | -0.15638 | 0.82651 | 0.022401 | -0.47875 | -0.16615
| 5185 | -0.16567 | -0.20697 | 0.13832 | -0.20596 | -0.31568 | 0.68141 | 0.31073 | 0.36526 | -0.048422 | 0.46549
| 5186 | -0.18459 | 0.40343 | -0.14437 | -0.06914 | 0.71312 | -0.1277 | -0.60567 | -0.15484 | -0.53772 | 0.072369
| 5187 | 0.25254 | 0.6952 | -0.23039 | -0.54668 | 0.15118 | 0.38673 | 0.37718 | -0.17641 | -0.30451 | 0.0020521
| 5188 | 0.76021 | 0.19657 | -0.90151 | -0.60516 | -0.48668 | -0.62838 | 0.34693 | -0.42615 | -0.30136 | 0.057397
| 5189 | 0.37783 | -0.04538 | 0.5013 | 0.82028 | -0.26088 | -0.4755 | -0.38364 | 0.084959 | -0.0036567 | 0.41051
| 5190 | -0.61934 | -0.51761 | -0.26468 | -0.51823 | 0.32435 | -0.2133 | -0.97764 | -0.80584 | -0.080163 | -0.21051
| 5191 | 0.52555 | -0.20332 | -0.17169 | -0.35665 | -0.39576 | -0.19669 | 0.46139 | 0.31058 | 0.67922 | -0.066244
| 5192 | -0.35743 | 0.23928 | 0.33555 | -0.16292 | -0.09165 | 0.70521 | -0.25872 | -0.060905 | 0.59689 | -0.13069
| 5193 | 0.14309 | 0.039844 | 0.52261 | 0.10451 | -0.044542 | 0.28369 | 0.08989 | -0.039323 | -0.22909 | -0.024449
| 5194 | 0.2492 | 0.68488 | -0.5201 | -0.10876 | -0.14379 | 0.56331 | -0.59614 | -0.93917 | -0.040677 | -0.042973
| 5195 | -0.29296 | -0.03434 | -0.67061 | -0.41153 | 0.11383 | -0.14718 | 0.2427 | -0.020561 | 0.5714 | -0.18312
| 5196 | 0.47208 | -0.29014 | 0.34464 | 0.74801 | -0.5001 | -0.24086 | 5.0001e-05 | 0.79 | -0.11915 | -0.2524
| 5197 | -0.006169 | 0.022606 | 0.35867 | 0.36921 | -0.44619 | -0.57727 | 0.63054 | -0.41613 | 0.014556 | 0.23574
| 5198 | 0.19446 | -0.020459 | 0.069785 | 0.71698 | -0.16113 | 0.15035 | -0.34586 | 0.72341 | 0.22547 | 0.76104
| 5199 | -0.52094 | -0.24231 | 0.54823 | 0.29452 | 0.18287 | 0.42877 | 0.15923 | -0.19557 | 0.35587 | -0.28916
| 5200 | 0.051369 | -0.66638 | 0.20634 | 0.22935 | -0.23626 | 0.14157 | 0.22238 | 0.065709 | 0.15059 | -0.63545
| 5201 | 0.26686 | 0.37366 | -0.17072 | 0.099722 | 0.65 | 0.052741 | 0.46306 | -0.25414 | 0.19719 | 0.43246
| 5202 | 0.45018 | -0.18901 | -0.71417 | 0.19931 | 0.26156 | 0.013542 | -0.04026 | -0.14918 | 0.4828 | -0.66133
| 5203 | -0.23417 | 0.36211 | -0.4344 | -0.11 | -0.64518 | 0.26074 | -0.21635 | -0.04266 | 0.25107 | -0.16352
| 5204 | -0.049263 | 0.32022 | -0.1292 | 0.30595 | 0.58347 | 0.61751 | -0.10384 | -0.44619 | -0.34647 | -0.0073772
| 5205 | 0.16976 | 0.16101 | -0.87712 | -0.12782 | -0.36149 | 0.66698 | 0.40209 | -0.25872 | -0.36431 | -0.43423
| 5206 | -0.5693 | -0.29665 | -0.62597 | 0.52408 | -0.083867 | -0.28063 | -0.66578 | 0.26536 | 0.47626 | 0.39742
| 5207 | -0.045799 | -0.017707 | 0.60389 | -0.019745 | -0.46232 | -0.23993 | -0.27206 | -0.20533 | -0.37944 | -0.46028
| 5208 | -0.32762 | 0.436 | 0.62919 | -0.45511 | -0.29608 | 0.27716 | -0.056337 | -0.34617 | 0.063037 | 0.0075787
| 5209 | -0.22289 | 0.19235 | -0.07962 | -0.68583 | -0.74251 | -0.1797 | -0.77572 | 0.53128 | 0.45677 | -0.095622
| 5210 | -0.027529 | 0.34311 | 0.071507 | -0.080598 | -0.056443 | -0.74485 | -0.17848 | 0.031961 | 0.47227 | 0.59788
| 5211 | -0.38706 | 0.54558 | 0.23928 | 0.045065 | -0.84736 | -0.51948 | -0.12108 | -0.60592 | -0.41289 | 0.92584
| 5212 | 0.67704 | 0.75241 | -0.22844 | 0.28355 | -0.16831 | 0.28104 | -0.12759 | 0.17836 | -0.043705 | 0.25347
| 5213 | -0.020153 | -0.021174 | 0.40983 | 0.15756 | 0.046533 | -0.42633 | 0.38755 | -0.01 | 0.13971 | -0.037763
| 5214 | -0.10955 | 0.6371 | 0.44116 | -0.052635 | -0.55089 | 0.3662 | -0.63765 | 0.33555 | -0.25294 | 0.50817
| 5215 | -0.13 | 0.097947 | -0.46943 | -0.46699 | 0.3074 | 0.72486 | 0.59491 | 0.1432 | -0.1382 | -0.026912
| 5216 | -0.38121 | -0.61128 | 0.031548 | -0.71035 | -0.16699 | -0.13669 | 0.039635 | 0.24217 | -0.79 | -0.32228
| 5217 | 0.49711 | -0.2047 | -0.60163 | -0.80481 | 0.45073 | -0.81372 | -0.2377 | 0.7488 | -0.017809 | 0.09143
| 5218 | 0.22444 | 0.06914 | 0.6265 | -0.30236 | -0.14753 | -0.20508 | 0.096728 | 0.82883 | -0.14134 | 0.12943
| 5219 | 0.43387 | -0.56331 | 0.32096 | -0.23338 | -0.022401 | 0.61103 | -0.027735 | 0.19607 | 0.035998 | 0.5009
| 5220 | -0.62251 | -0.052741 | -0.36826 | -0.18581 | -0.86621 | 0.26604 | 0.10574 | 0.39643 | -0.37079 | 0.016181
| 5221 | -0.78068 | 0.093082 | 0.3214 | 0.7076 | 0.20583 | 0.44224 | 0.26904 | 0.47379 | 0.71487 | -0.57421
| 5222 | 0.61128 | -0.15697 | 0.40427 | -0.065816 | -0.95204 | 0.44945 | -0.47779 | -0.47474 | 0.38804 | -0.22689
| 5223 | 0.5806 | -0.0995 | -0.26291 | -0.029588 | -0.58012 | -0.47417 | -0.38283 | -0.43777 | 0.62145 | 0.56285
| 5224 | -0.39033 | -0.22083 | -0.62198 | -0.31436 | -0.87233 | 0.65172 | -0.044123 | -0.68047 | -0.0063703 | 0.57257
| 5225 | 0.074743 | -0.13034 | -0.25602 | -0.60415 | -0.023424 | -0.60163 | 0.41802 | 0.0030547 | 0.63244 | -0.27343
| 5226 | -0.15188 | 0.19309 | 0.36008 | -0.12943 | -0.36321 | 0.15153 | -0.56331 | -0.33524 | 0.88642 | 0.28425
| 5227 | 0.2598 | -0.44837 | -0.28958 | 0.056337 | 0.041825 | -0.09839 | 0.0021523 | -0.65985 | 0.018012 | -0.4471
| 5228 | 0.16844 | -0.074851 | -0.33494 | -0.09088 | -0.40966 | 0.48473 | 0.11169 | 0.078859 | -0.17133 | 0.32806
| 5229 | 0.10351 | 0.34479 | 0.43493 | 0.28831 | -0.075068 | 0.19819 | 0.59689 | 0.47436 | -0.4755 | -0.3618
| 5230 | -0.34205 | 0.052424 | -0.46437 | -0.22896 | -0.4979 | -0.36857 | 0.51061 | 0.095401 | 0.0064709 | 0.26264
| 5231 | 0.42009 | -0.50857 | 0.35556 | 0.2081 | 0.3451 | -0.53643 | -0.79826 | 0.55111 | 0.018522 | -0.48843
| 5232 | 0.64433 | 0.2402 | -0.62838 | 0.42268 | -0.02897 | 0.18079 | -0.28537 | -0.75896 | 0.52555 | -0.1473
| 5233 | -0.38267 | -0.46288 | 0.45658 | -0.38494 | -0.5959 | 0.62892 | 0.42685 | 0.48687 | -0.86546 | -0.38885
| 5234 | -0.64209 | 0.29028 | 0.11586 | -0.2958 | -0.35401 | -0.19136 | -0.42303 | -0.078968 | 0.22289 | -0.11643
| 5235 | 0.36968 | 0.35883 | 0.072584 | 0.68775 | -0.27979 | -0.88642 | -0.95204 | -0.64125 | -0.56148 | 0.28845
| 5236 | -0.1814 | 0.19297 | 0.72596 | -0.34174 | -0.56977 | 0.2234 | 0.30408 | -0.027632 | -0.3294 | 0.29822
| 5237 | 0.75403 | -0.18766 | -0.3593 | -0.15496 | -0.043705 | -0.13878 | 0.56422 | -0.83599 | 0.13392 | -0.20294
| 5238 | -0.35355 | 0.034133 | -0.64971 | -0.57047 | -0.77617 | -0.06165 | -0.18153 | -0.36039 | 0.51492 | 0.41682
| 5239 | -0.43493 | 0.0173 | 0.64715 | -0.55156 | 0.49453 | -0.67091 | 0.43229 | 0.31582 | -0.26454 | -0.60088
| 5240 | -0.01791 | -0.14344 | 0.66519 | 0.14332 | 0.24522 | 0.020766 | 0.1546 | -0.21853 | 0.6852 | 0.011415
| 5241 | 0.49453 | 0.46474 | -0.3061 | -0.42668 | 0.031135 | 0.13403 | -0.021992 | 0.29979 | 0.61908 | 0.027529
| 5242 | -0.21444 | 0.60113 | -0.73942 | -0.19198 | 0.51657 | 0.81426 | -0.75938 | -0.8937 | -0.25993 | 0.046428
| 5243 | 0.044856 | -0.59714 | 0.14262 | -0.40242 | 0.014252 | -0.4902 | -0.19931 | -0.077991 | -0.18963 | -0.8937
| 5244 | -0.29637 | 0.027118 | 0.16807 | 0.78114 | -0.47057 | 0.22315 | -0.26577 | 0.23967 | 0.70555 | 0.086928
| 5245 | -0.42563 | 0.10217 | 0.47512 | 0.25629 | 0.10485 | 0.33902 | 0.0045604 | -0.80226 | -0.44116 | 0.0091922
| 5246 | 0.31043 | -0.78529 | 0.08343 | 0.23469 | 0.36762 | -0.64461 | 0.19844 | 0.27938 | 0.22624 | 0.24402
| 5247 | -0.37414 | -0.72963 | -0.62677 | 0.54316 | -0.037971 | -0.27316 | -0.085724 | 0.084522 | 0.65201 | -0.5707
| 5248 | 0.31465 | 0.47208 | 0.25723 | 0.42965 | 0.40225 | 0.40393 | -0.38056 | -0.45714 | -0.2823 | -0.66015
| 5249 | -0.96127 | -0.59392 | -0.51266 | 0.21089 | 0.59245 | 0.16904 | -0.41068 | 0.71592 | -0.035687 | 0.76957
| 5250 | 0.10362 | -0.43 | -0.30293 | 0.13716 | 0.15709 | 0.42511 | -0.27027 | 0.19284 | 0.088682 | 0.5583
| 5251 | -0.29879 | 0.14906 | -0.3116 | 0.31087 | 0.083321 | 0.49098 | 0.13461 | 0.25321 | -0.61594 | -0.51761
| 5252 | 0.30639 | 0.099722 | -0.18422 | -0.084194 | 0.059096 | 0.5143 | 0.16687 | -0.70897 | 0.20181 | 0.44027
| 5253 | -0.10585 | 0.15413 | 0.15828 | 0.69292 | -0.076582 | -0.27522 | 0.053163 | 0.01547 | -0.67091 | 0.75201
| 5254 | -0.035479 | 0.062717 | -0.028455 | -0.49651 | -0.093965 | -0.73789 | -0.51823 | 0.23862 | 0.15118 | -0.016588
| 5255 | -0.65345 | 0.10406 | -0.18471 | 0.076907 | 0.3956 | -0.098169 | -0.44547 | -0.71417 | 0.083212 | -0.3629
| 5256 | 0.91456 | 0.0075787 | 0.10172 | -0.21495 | 0.60088 | 0.016181 | -0.30451 | 0.41579 | -0.045589 | -0.39098
| 5257 | 0.30021 | 0.38771 | -0.29907 | -0.44027 | 0.66162 | -0.32007 | -0.0037571 | -0.22328 | 0.62384 | 0.41751
| 5258 | 0.56331 | 0.37574 | -0.3245 | -0.29622 | -0.5332 | 0.24694 | 0.6249 | -0.11813 | -0.46587 | -0.41459
| 5259 | 0.11983 | 0.41477 | 0.47303 | 0.18864 | -0.24614 | -0.064532 | 0.35587 | 0.042555 | 0.17265 | -0.47284
| 5260 | 0.041512 | -0.086053 | 0.09518 | 0.55943 | 0.77796 | -0.97354 | 0.092862 | -0.74446 | -0.68488 | -0.22379
| 5261 | -0.54845 | -0.52261 | 0.25053 | 0.5954 | 0.09529 | -0.77751 | 0.025885 | 0.46139 | -0.79239 | -0.065174
| 5262 | 0.54778 | 0.077341 | -0.14192 | 0.94432 | -0.61699 | -0.063037 | -0.15059 | 0.088463 | -0.32494 | -0.3451
| 5263 | -0.038387 | -0.20207 | 0.16209 | -0.48144 | 0.086819 | 0.38984 | 0.28467 | -0.44277 | 0.27385 | 0.038699
| 5264 | -0.1797 | -0.078317 | 0.40679 | 0.50675 | -0.61128 | -0.83783 | -0.018827 | -0.36227 | -0.028764 | -0.35308
| 5265 | 0.50472 | 0.65143 | 5.0001e-05 | 0.015165 | 0.8937 | -0.31919 | -0.29551 | 0.36841 | -0.27993 | -0.20646
| 5266 | -0.62039 | 0.35169 | -0.6939 | 0.28285 | 0.59073 | -0.37239 | -0.74019 | 0.33209 | 0.44728 | 0.065388
| 5267 | 0.30207 | 0.14169 | -0.19471 | 0.61934 | -0.24046 | 0.31451 | 0.078968 | -0.31728 | 0.16018 | 0.27744
| 5268 | 0.067316 | 0.74841 | 0.051369 | -0.16711 | -0.02568 | 0.42703 | 0.067101 | 0.21177 | 0.23312 | -0.22818
| 5269 | -0.66638 | 0.052108 | 0.37751 | 0.073987 | 0.071938 | 0.32598 | 0.022912 | -0.57303 | 0.6833 | 0.19657
| 5270 | -0.3312 | 0.22418 | -0.12713 | 0.010505 | -0.10955 | 0.73827 | -0.70725 | 0.18459 | 0.034961 | -0.14262
| 5271 | 0.41768 | 0.31655 | 0.77932 | -0.4898 | -0.3681 | -0.3425 | -0.24721 | -0.0067729 | 0.41545 | 0.56057
| 5272 | 0.28188 | 0.35077 | -0.028352 | -0.21712 | -0.27564 | 0.41494 | -0.49512 | -0.48824 | 0.35185 | -0.16496
| 5273 | 0.30855 | -0.11677 | 0.6233 | 0.47019 | 0.012528 | -0.10406 | -0.58636 | -0.037763 | 0.74368 | 0.094517
| 5274 | 0.15082 | -0.33164 | 0.23039 | -0.25885 | -0.41854 | -0.29864 | 0.13092 | 0.27041 | -0.53924 | 0.68393
| 5275 | 0.47398 | -0.24614 | 0.45237 | -0.16484 | -0.39345 | 0.36857 | -0.1952 | -0.13901 | 0.009596 | -0.2356
| 5276 | -0.5009 | -0.29395 | 0.27716 | -0.16209 | 0.35339 | -0.6162 | -0.47265 | 0.17229 | -0.24336 | -0.43546
| 5277 | 0.36494 | 0.14437 | 0.24987 | -0.048317 | 0.0060684 | 0.6985 | 0.31611 | 0.26767 | -0.1253 | 0.065067
| 5278 | 0.040573 | -0.45824 | -0.79727 | 0.54778 | 0.11428 | -0.49493 | 0.31743 | 0.39726 | -0.19533 | 0.34525
| 5279 | 0.69917 | -0.076582 | 0.12622 | 0.93144 | -0.080272 | 0.45127 | -0.053797 | 0.85474 | -0.057822 | -0.40242
| 5280 | 0.21304 | -0.34159 | 0.18275 | -0.011921 | -0.44027 | -0.17799 | 0.31831 | 0.41836 | 0.34464 | -0.47914
| 5281 | -0.077991 | -0.30826 | 0.14835 | -0.11586 | 0.0082843 | -0.54734 | -0.71277 | 0.030206 | 0.61516 | -0.22521
| 5282 | 0.12165 | 0.79095 | -0.2571 | 0.39792 | 0.13785 | 0.018114 | 0.061437 | -0.35293 | -0.85964 | 0.059096
| 5283 | -0.45073 | 0.40477 | 0.42528 | 0.12484 | 0.25107 | 0.3087 | 0.17302 | -0.25926 | -0.094406 | 0.38429
| 5284 | -0.43759 | 0.093965 | 0.76484 | 0.16042 | -0.057397 | 0.11338 | 0.3422 | -0.24561 | -0.0081835 | -0.46362
| 5285 | 0.73942 | -0.59963 | 0.35308 | 0.80739 | -0.05348 | -0.41751 | 0.85964 | -0.39775 | 0.097503 | 0.84412
| 5286 | 0.16663 | -0.41905 | 0.58805 | 0.38738 | -0.79048 | -0.35603 | 0.36921 | 0.21203 | 0.0049623 | -0.011617
| 5287 | 0.80379 | 0.65897 | 0.20546 | -0.42493 | 0.25267 | 0.54338 | -0.42982 | -0.48241 | 0.43458 | -0.11983
| 5288 | -0.2791 | 0.060479 | 0.068067 | -0.27827 | -0.85543 | 0.47455 | -0.056231 | 0.43088 | 0.3189 | 0.029176
| 5289 | 0.22225 | -0.82593 | -0.33105 | -0.11439 | 0.34464 | -0.059947 | -0.50898 | -0.43387 | -0.037347 | 0.11146
| 5290 | -0.40225 | -0.09099 | -0.26645 | 0.043078 | 0.72378 | -0.06293 | 0.69097 | 0.47512 | 0.75444 | 0.4683
| 5291 | -0.58636 | 0.23915 | -0.45109 | 0.4286 | -0.39992 | 0.20194 | -0.0010506 | 0.29141 | 0.35789 | -0.4417
| 5292 | 0.25508 | 0.085506 | -0.059947 | 0.46962 | 0.56977 | -0.26007 | -0.21444 | -0.43546 | 0.40949 | -0.043287
| 5293 | 0.25374 | 0.38008 | 0.043914 | 0.36778 | -0.15614 | -0.42825 | -0.084413 | -0.17665 | 0.44367 | 0.66668
| 5294 | 0.0048618 | 0.5019 | -0.24059 | -0.35386 | 0.071399 | 0.28021 | 0.20106 | -0.10563 | -0.10955 | 0.53149
| 5295 | -0.4293 | -0.2773 | 0.24231 | -0.29099 | 0.60063 | -0.084959 | 0.45935 | -0.016588 | -0.082776 | -0.13774
| 5296 | 0.27288 | -0.28369 | 0.22353 | -0.16663 | -0.19707 | 0.024756 | 0.13774 | 0.76957 | 0.84348 | 0.47038
| 5297 | -0.4857 | -0.19136 | -0.4163 | -0.47019 | 0.098945 | 0.13461 | -0.65722 | -0.46344 | 0.62865 | -0.060372
| 5298 | -0.28271 | -0.41751 | -0.067101 | 0.27785 | 0.44116 | 0.6952 | 0.19408 | 0.32851 | 0.19694 | 0.49552
| 5299 | 0.020868 | 0.19012 | 0.15365 | 0.14835 | 0.1005 | 0.38461 | -0.08474 | 0.32022 | 0.49275 | -0.27924
| 5300 | -0.16687 | -0.6811 | -0.45769 | -0.092311 | 0.80379 | 0.52345 | -0.18938 | -0.074203 | 0.72054 | -0.6631
| 5301 | -0.60694 | 0.40915 | -0.026809 | 0.72125 | -0.29979 | -0.33194 | 0.26115 | -0.21763 | -0.28593 | 0.34311
| 5302 | 0.70017 | -0.038179 | 0.016893 | 0.086162 | 0.31073 | -0.59763 | 0.76021 | 0.043391 | 0.30308 | -0.3297
| 5303 | 0.62892 | -0.24072 | -0.14111 | 0.1603 | 0.28775 | 0.048948 | 0.011719 | 0.012934 | -0.26061 | -0.34555
| 5304 | -0.12416 | 0.43088 | -0.097947 | 0.35432 | 0.57703 | -0.13692 | 0.48707 | -0.12028 | -0.86771 | 0.029382
| 5305 | -0.44349 | 0.60213 | 0.44601 | 0.57774 | -0.15082 | -0.19906 | -0.020868 | -0.040573 | -0.30841 | 0.36305
| 5306 | 0.47626 | 0.18655 | 0.83845 | 0.84348 | 0.084413 | 0.065602 | 0.45055 | -0.24429 | 0.2722 | -0.62224
| 5307 | -0.084631 | 0.23639 | -0.32687 | -0.5199 | -0.069463 | -0.46065 | -0.27 | 0.41323 | 0.15094 | 0.64237
| 5308 | -0.64631 | 0.064853 | 0.018522 | -0.38429 | -0.15141 | 0.69259 | 0.56814 | 0.23391 | 0.32051 | 0.83599
| 5309 | 0.021685 | -0.42216 | 0.13542 | -0.29141 | -0.49473 | 0.74525 | -0.47417 | 0.23534 | -0.2193 | -0.35774
| 5310 | -0.13322 | 0.82028 | -0.14449 | 0.53859 | 0.39197 | -0.020255 | 0.037555 | 0.65489 | -0.23875 | -0.18532
| 5311 | 0.41374 | 0.45732 | -0.064105 | -0.0032553 | -0.28327 | 0.57562 | -0.49059 | 0.28775 | -0.36102 | 0.80176
| 5312 | 0.28845 | -0.20282 | 0.76188 | 0.23443 | -0.22469 | 0.16484 | 0.020561 | -0.92319 | -0.0093941 | 0.2504
| 5313 | 0.70794 | -0.53794 | 0.42877 | 0.93292 | 0.28523 | -0.0027538 | 0.068067 | 0.087257 | 0.35278 | -0.12507
| 5314 | -0.11733 | -0.092751 | 0.53513 | 0.53729 | 0.69065 | -0.071938 | 0.51184 | 0.17508 | 0.068067 | 0.057822
| 5315 | -0.24125 | -0.046742 | -0.22805 | 0.20533 | -0.2598 | 0.024962 | -0.06261 | 0.051159 | -0.19049 | 0.02722
| 5316 | -0.23574 | 0.348 | 0.34586 | -0.11056 | 0.36889 | 0.41751 | 0.64971 | 0.031857 | 0.32911 | -0.086162
| 5317 | 0.38853 | 0.029382 | -0.51554 | -0.034858 | -0.045799 | -0.3074 | 0.49039 | 0.1706 | -0.7015 | -0.1578
| 5318 | -0.09132 | -0.33539 | 0.48512 | 0.39892 | 0.39461 | 0.27938 | -0.078534 | -0.29665 | -0.17362 | -0.50614
| 5319 | -0.35618 | -0.40578 | 0.02097 | -0.78206 | -0.81212 | 0.14976 | 0.22792 | 0.035998 | 0.25602 | 0.27661
| 5320 | -0.04172 | -0.3248 | 0.452 | -0.46887 | -0.68393 | 0.61335 | 0.74801 | -0.36668 | -0.1646 | -0.22006
| 5321 | 0.21076 | -0.76146 | -0.15306 | 0.50634 | -0.56514 | 0.10273 | 0.39709 | -0.19782 | -0.15224 | -0.25522
| 5322 | -0.53881 | -0.4134 | -0.028867 | 0.031031 | 0.12382 | 0.003155 | -0.19062 | 0.23744 | -0.564 | 0.34647
| 5323 | 0.038907 | -0.3727 | -0.42407 | -0.10529 | -0.50251 | -0.5656 | 0.66728 | -0.44027 | 0.43759 | -0.42965
| 5324 | 0.10328 | -0.3751 | -0.40359 | -0.073124 | 0.54316 | -0.36305 | -0.17374 | 0.27799 | 0.04538 | -0.58083
| 5325 | 0.73524 | 0.58733 | 0.38673 | 0.36683 | -0.60038 | 0.6265 | 0.38186 | 0.03974 | 0.12679 | 0.57397
| 5326 | 0.41545 | 0.20874 | -0.96127 | -0.49334 | 0.061118 | 0.45769 | 0.34816 | -0.75485 | 0.48048 | 0.78483
| 5327 | -0.22418 | -0.57047 | -0.61699 | 0.19707 | -0.088902 | 0.78206 | 0.18459 | 0.52094 | -0.57893 | 0.59763
| 5328 | 0.53064 | -0.22637 | 0.079185 | 0.19757 | 0.081142 | -0.41888 | 0.14554 | 0.53299 | 0.041929 | 0.32258
| 5329 | 0.59245 | -0.66044 | -0.065067 | 0.24402 | -0.40763 | 0.12966 | -0.87155 | 0.28299 | -0.54273 | -0.41562
| 5330 | 0.77087 | -0.014454 | 0.40746 | -0.23901 | -0.27371 | -0.3956 | 0.27744 | -0.047792 | -0.23 | -0.28467
| 5331 | 0.30696 | 0.51969 | 0.59368 | -0.049789 | 0.0035563 | 0.50351 | 0.67335 | -0.15472 | 0.39527 | -0.3838
| 5332 | -0.21025 | -0.38984 | -0.22818 | 0.55717 | -0.72963 | -0.094517 | -0.42285 | 0.28118 | 0.06496 | -0.32554
| 5333 | 0.25697 | 0.13669 | -0.51948 | 0.2575 | 0.25388 | 0.073663 | -0.020051 | 0.066887 | 0.45954 | -0.8467
| 5334 | 0.68078 | 0.29 | 0.47436 | 0.01791 | 0.045799 | 0.05899 | -0.42424 | 0.52915 | 0.35992 | -0.45091
| 5335 | -0.11394 | 0.66281 | -0.23508 | 0.51969 | 0.20684 | 0.50654 | -0.23078 | 0.056549 | -0.47588 | 0.31392
| 5336 | -0.078425 | -0.32346 | -0.55022 | -0.23391 | 0.062503 | -0.06325 | -0.81212 | -0.26645 | -0.31582 | -0.44565
| 5337 | -0.69292 | 0.8995 | 0.40865 | -0.43617 | 0.014049 | 0.096507 | 0.22366 | -0.50573 | 0.26495 | -0.61154
| 5338 | -0.14204 | 0.4857 | 0.25549 | 0.044019 | 0.12633 | 0.013643 | -0.42476 | 0.48726 | -0.21013 | 0.24933
| 5339 | 0.25388 | -0.46325 | 0.14099 | 0.20044 | 0.74801 | -0.1688 | -0.11293 | -0.83969 | 0.3167 | 0.68141
| 5340 | -0.050526 | -0.71769 | 0.1063 | -0.048948 | 0.43902 | -0.11473 | 0.31349 | 0.6118 | 0.3735 | -0.10563
| 5341 | -0.35541 | -0.02189 | 0.16137 | 0.59491 | -0.10832 | -0.85405 | 0.55067 | 0.67152 | -0.13173 | -0.4799
| 5342 | 0.33675 | -0.36794 | -0.059202 | -0.35494 | -0.36274 | -0.44027 | -0.16448 | -0.09529 | 0.29226 | -0.66044
| 5343 | -0.16603 | 0.14472 | 0.85543 | -0.13507 | -0.16904 | 0.39692 | 0.10373 | 0.002453 | 0.061864 | 0.21814
| 5344 | -0.029073 | 0.55447 | -0.23482 | -0.58951 | 0.27192 | 0.64857 | -0.2512 | 0.54646 | 0.59 | 0.26291
| 5345 | -0.65258 | 0.28523 | 0.64097 | -0.24987 | -0.77262 | -0.31875 | -0.11586 | 0.5714 | 0.18361 | 0.44619
| 5346 | 0.18889 | 0.11745 | -0.27882 | -0.09176 | 0.75938 | -0.53492 | -0.59 | 0.24455 | 0.027118 | 0.45622
| 5347 | 0.30451 | 0.29893 | 0.60541 | -0.08978 | -0.44045 | 0.018827 | 0.3245 | -0.59714 | 0.2575 | 0.91
| 5348 | 0.38056 | -0.15141 | -0.69324 | -0.10028 | -0.10406 | 0.026912 | -0.18544 | 0.60898 | -0.19433 | 0.0093941
| 5349 | 0.0021523 | 0.62677 | -0.70931 | 0.00075028 | 0.55134 | 0.15994 | -0.044333 | 0.51575 | 0.094627 | 0.081904
| 5350 | 0.64014 | 0.54845 | -0.7816 | -0.024141 | -0.66015 | 0.58636 | 0.29822 | -0.28132 | -0.34418 | 0.068925
| 5351 | 0.65287 | 0.094627 | -0.75161 | -0.19471 | -0.40427 | 0.6578 | 0.16113 | -0.19297 | -0.6634 | -0.082885
| 5352 | 0.084631 | 0.73373 | 0.029382 | 0.18214 | -0.26658 | -0.13115 | -0.21674 | 0.0039578 | -0.48396 | 0.48843
| 5353 | 0.23823 | 0.42511 | 0.23915 | -0.28411 | 0.36447 | 0.12165 | -0.73981 | -0.81862 | 0.1786 | 0.32317
| 5354 | 0.045484 | -0.44009 | 0.21533 | -0.46418 | -0.66251 | -0.022606 | 0.66819 | 0.1786 | 0.068925 | -0.77932
| 5355 | -0.47626 | -0.4041 | 0.29793 | 0.46755 | -0.09143 | 0.033718 | 0.90566 | -0.62973 | 0.37366 | 0.018216
| 5356 | -0.13774 | -0.27274 | 0.56331 | 0.61568 | 0.62304 | -0.49711 | 0.19359 | 0.21648 | -0.47398 | -0.32051
| 5357 | 0.46176 | 0.21304 | -0.23954 | -0.31349 | -0.4653 | 0.69586 | 0.75648 | 0.011213 | 0.45237 | -0.40326
| 5358 | -0.71382 | -0.065602 | 0.31802 | -0.22805 | 0.41854 | -0.35977 | -0.14204 | -0.32037 | 0.046323 | 0.15236
| 5359 | 0.19981 | 0.08343 | 0.42009 | 0.0042591 | 0.27578 | -0.27799 | 0.68711 | 0.69652 | 0.17012 | -0.59491
| 5360 | -0.0040582 | -0.13971 | 0.15733 | 0.4981 | 0.62973 | -0.48087 | 0.26441 | 0.14976 | -0.5954 | 0.80739
| 5361 | -0.24112 | 0.63054 | 0.36826 | 0.37638 | -0.054855 | -0.15024 | -0.6755 | -0.0059678 | 0.65576 | 0.9272
| 5362 | -0.19458 | 0.54142 | -0.51927 | -0.5768 | -0.44134 | 0.20684 | -0.37286 | 0.0015512 | 0.35169 | -0.42372
| 5363 | 0.17036 | -0.22366 | -0.47189 | -0.65345 | -0.33374 | 0.11609 | -0.028352 | 0.1868 | 0.067637 | 0.27702
| 5364 | -0.015774 | -0.77528 | -0.24099 | -0.69357 | 0.17665 | 0.55672 | -0.65751 | -0.75363 | 0.57988 | -0.047372
| 5365 | 0.013238 | -0.23182 | 0.49691 | 0.37526 | -0.44818 | 0.011719 | -0.25629 | -0.65927 | -0.1109 | -0.7245
| 5366 | 0.32199 | -0.43831 | 0.20861 | 0.31597 | 0.66133 | 0.50533 | -0.0017515 | 0.093192 | -0.45475 | 0.49592
| 5367 | 0.72414 | 0.33194 | 0.31743 | -0.16388 | 0.44331 | -0.57869 | -0.74251 | 0.34862 | 0.23875 | -0.51927
| 5368 | 0.67953 | -0.087366 | -0.1162 | 0.26007 | -0.60846 | -0.032374 | 0.042033 | 0.050316 | -0.5199 | -0.50776
| 5369 | -0.93597 | 0.65576 | 0.57633 | 0.2427 | -0.72054 | -0.019235 | -0.17278 | 0.41854 | -0.38559 | 0.16066
| 5370 | 0.0013509 | -0.6786 | -0.15697 | -0.0043595 | -0.44601 | 0.8454 | 0.75444 | -0.19607 | 0.52534 | 0.68647
| 5371 | 0.032994 | 0.5458 | -0.31597 | 0.35992 | 0.27137 | 0.17738 | -0.86696 | 0.2773 | 0.21789 | -0.032994
| 5372 | 0.20697 | -0.49512 | -0.040677 | -0.026501 | 0.018929 | 0.39709 | -0.23849 | 0.10541 | -0.90356 | 0.1957
| 5373 | 0.47436 | -0.17181 | 0.051686 | -0.72233 | 0.38624 | -0.66608 | 0.36652 | 0.46046 | -0.3306 | -0.4531
| 5374 | 0.7504 | -0.51886 | -0.23967 | -0.36431 | 0.22754 | 0.65547 | 0.3306 | -0.38869 | 0.22728 | 0.20156
| 5375 | -0.87958 | -0.24389 | 0.085287 | -0.12256 | 0.073231 | 0.036413 | 0.06957 | -0.3372 | -0.7005 | 0.27951
| 5376 | -0.029382 | -0.30783 | 0.76357 | 0.31422 | -0.021481 | -0.58757 | -0.46251 | -0.48338 | 0.29979 | 0.29665
| 5377 | 0.77131 | 0.52894 | 0.070215 | 0.40628 | 0.41085 | -0.56907 | 0.12324 | -0.67643 | -0.3025 | -0.6995
| 5378 | 0.57257 | 0.47417 | -0.036205 | -0.02609 | -0.0053644 | -0.91225 | -0.12747 | -0.47246 | -0.32332 | -0.13127
| 5379 | -0.67674 | 0.1389 | -0.083976 | 0.21317 | -0.30986 | -0.41459 | 0.14765 | -0.86771 | 0.31116 | 0.0040582
| 5380 | -0.01842 | 0.2133 | 0.79384 | -0.16376 | 0.0052639 | 0.3551 | -0.72669 | 0.28747 | 0.74801 | -0.18422
| 5381 | -0.4265 | 0.37318 | 0.17072 | 0.57869 | -0.25589 | 0.64914 | -0.63244 | 0.91225 | -0.09121 | -0.16771
| 5382 | 0.087257 | 0.51575 | 0.58012 | 0.07962 | -0.31538 | 0.16567 | 0.67953 | -0.36557 | 0.2674 | -0.19582
| 5383 | 0.21866 | 0.029176 | 0.65057 | -0.5141 | -0.041199 | 0.18006 | -0.3759 | 0.79875 | 0.63737 | -0.50251
| 5384 | 0.01 | 0.028146 | 0.043496 | 0.13322 | -0.0087886 | -0.70725 | -0.23221 | 0.04266 | -0.13948 | -0.45438
| 5385 | -0.10708 | -0.21165 | -0.068818 | -0.04538 | 0.058565 | -0.5009 | 0.49651 | 0.01486 | -0.22792 | 0.0046609
| 5386 | 0.1884 | 0.45237 | -0.19707 | -0.12553 | -0.26672 | 0.17 | 0.033822 | -0.16579 | -0.70725 | -0.43352
| 5387 | 0.10184 | -0.073124 | 0.25791 | -0.16916 | 0.065174 | -0.02189 | -0.51102 | 0.13057 | -0.023424 | 0.85269
| 5388 | 0.27993 | 0.057291 | -0.36668 | -0.033512 | -0.051053 | 0.2133 | -0.12382 | 0.64405 | 0.072692 | 0.41579
| 5389 | -0.45475 | -0.1389 | 0.11575 | -0.19508 | 0.46925 | 0.0053644 | 0.63408 | 0.03579 | 0.86771 | -0.45365
| 5390 | 0.29708 | -0.29637 | -0.67091 | 0.57397 | 0.75485 | -0.21802 | 0.31758 | -0.20596 | -0.027632 | -0.96683
| 5391 | 0.65057 | 0.65868 | -0.096839 | -0.61026 | -0.22405 | -0.67612 | -0.61335 | 0.43229 | -0.038803 | 0.2516
| 5392 | -0.23169 | -0.23208 | 0.088024 | -0.14157 | 0.042242 | -0.1628 | -0.36227 | -0.081469 | -0.20861 | 0.11372
| 5393 | 0.38332 | 0.5143 | -0.46812 | 0.10083 | -0.26264 | -0.31934 | 0.6265 | 0.21304 | 0.40443 | -0.12382
| 5394 | 0.5332 | -0.042138 | 0.90253 | -0.70966 | 0.89656 | -0.30337 | 0.67735 | 0.15059 | 0.023117 | 0.30036
| 5395 | 0.51637 | -0.41238 | -0.13322 | 0.52703 | 0.31802 | -0.39908 | 0.30236 | -0.48629 | 0.38008 | 0.29936
| 5396 | 0.081795 | -0.31875 | -0.25321 | -0.01415 | 0.2256 | 0.093303 | 0.29551 | 0.74841 | 0.61103 | 0.20924
| 5397 | -0.18018 | -0.33224 | 0.18508 | -0.33766 | -0.021583 | -0.39131 | -0.061118 | 0.73866 | 0.43158 | 0.36778
| 5398 | -0.23613 | 0.1803 | 0.22883 | 0.11214 | -0.37398 | 0.093523 | -0.25791 | -0.17556 | -0.22328 | 0.30308
| 5399 | 0.27591 | 0.0030547 | 0.042451 | 0.1775 | 0.49196 | 0.18116 | -0.58203 | -0.035583 | -0.070323 | -0.19669
| 5400 | 0.53149 | -0.053586 | -0.52324 | 0.016079 | -0.097947 | -0.057185 | 0.72269 | 0.27055 | -0.41459 | -0.15436
| 5401 | 0.2356 | 0.14285 | 0.464 | -0.69884 | 0.63654 | -0.14882 | 0.51844 | -0.065816 | -0.037244 | -0.52873
| 5402 | 0.49275 | 0.057185 | 0.19632 | 0.67488 | -0.18951 | 0.35945 | 0.14239 | -0.36478 | 0.055384 | 0.31451
| 5403 | -0.25294 | 0.53427 | 0.13288 | 0.008486 | -0.15425 | -0.39958 | -0.18299 | -0.042451 | -0.08978 | 0.87
| 5404 | 0.84284 | -0.36557 | -0.27165 | 0.23901 | -0.28761 | 0.40729 | 0.61 | -0.67091 | 0.083539 | 0.39925
| 5405 | 0.16747 | -0.13913 | -0.43813 | -0.31597 | -0.52555 | 0.28845 | 0.28174 | -0.46587 | -0.069355 | 0.0085869
| 5406 | 0.067208 | 0.32391 | -0.68078 | -0.1758 | 0.29836 | 0.57491 | -0.37799 | -0.89 | -0.13288 | 0.24204
| 5407 | -0.80277 | -0.038699 | -0.65809 | 0.59565 | -0.10295 | 0.17483 | 0.073016 | 0.03714 | 0.13878 | 0.83237
| 5408 | 0.00055015 | 0.62384 | 0.30408 | 0.6833 | 0.59515 | 0.0995 | 0.15413 | -0.16256 | -0.47722 | -0.052846
| 5409 | 0.31116 | -0.50432 | 0.68552 | 0.080163 | 0.65143 | -0.17933 | -0.19533 | -0.30769 | 0.54823 | 0.72414
| 5410 | -0.77 | 0.19944 | -0.20483 | -0.19396 | 0.42078 | -0.17278 | -0.45273 | 0.58107 | -0.66429 | 0.047792
| 5411 | 0.33359 | -0.45898 | -0.61568 | 0.59988 | 0.5172 | -0.45658 | -0.53406 | 0.050211 | -0.64546 | -0.025474
| 5412 | 0.39428 | 0.0094951 | 0.26264 | -0.39279 | -0.73942 | 0.41425 | 0.097947 | -0.31451 | -0.035998 | 0.077016
| 5413 | 0.5003 | -0.73335 | 0.27233 | -0.21955 | -0.24363 | -0.29395 | -0.55739 | 0.007478 | 0.4265 | 0.61464
| 5414 | 0.036309 | -0.5735 | -0.060905 | -0.80687 | -0.099944 | 0.19309 | 0.59245 | 0.34099 | 0.45603 | -0.28537
| 5415 | -0.59049 | -0.23928 | 0.026193 | 0.10106 | 0.048422 | 0.45018 | 0.51 | 0.46288 | 0.064212 | -0.38738
| 5416 | 0.31232 | 0.36778 | -0.083212 | 0.26781 | -0.7881 | 0.5663 | -0.77841 | 0.26549 | -0.19757 | -0.35914
| 5417 | 0.70352 | -0.041512 | 0.033925 | -0.54646 | -0.060372 | -0.30293 | -0.28257 | 0.13785 | 0.14765 | -0.37398
| 5418 | 0.21089 | -0.9272 | -0.33826 | -0.33585 | 0.076149 | 0.18373 | -0.16042 | -0.077558 | 0.29907 | 0.13357
| 5419 | -0.23156 | 0.1034 | 0.46456 | 0.32925 | -0.14041 | 0.44152 | -0.55134 | -0.42372 | -0.67458 | -0.2184
| 5420 | -0.16639 | 0.1237 | 0.52303 | -0.082231 | 0.058671 | 0.41051 | 0.34403 | -0.084522 | 0.24112 | 0.51554
| 5421 | -0.27055 | 0.69586 | -0.23941 | -0.032788 | 0.2975 | 0.79628 | -0.47341 | -0.22624 | -0.61077 | -0.64014
| 5422 | -0.9272 | 0.2343 | -0.16077 | -0.060585 | 0.018827 | -0.7881 | 0.83059 | -0.057079 | -0.10686 | 0.6149
| 5423 | 0.47971 | 0.11417 | 0.56676 | -0.25187 | 0.41 | -0.51225 | 0.15661 | -0.11236 | 0.24707 | 0.99
| 5424 | -0.36541 | 0.38804 | -0.6044 | 0.051264 | 0.46102 | 0.32332 | 0.047267 | -0.026707 | -0.24654 | -0.14636
| 5425 | 0.21025 | 0.48512 | -0.040886 | 0.45806 | 0.44098 | 0.72669 | -0.23364 | 0.16137 | -0.38738 | 0.35618
| 5426 | 0.2571 | -0.68583 | 0.58227 | 0.44692 | 0.72705 | 0.63572 | 0.13565 | -0.35216 | 0.071076 | 0.11225
| 5427 | 0.00075028 | -0.71347 | -0.025988 | 0.51823 | -0.12633 | 0.6077 | 0.48435 | 0.80226 | -0.027735 | -0.30826
| 5428 | -0.58012 | -0.83783 | -0.67427 | 0.26305 | 0.46474 | -0.41391 | -0.21712 | 0.91938 | -0.35634 | 0.88554
| 5429 | 0.067637 | -0.37702 | -0.86399 | 0.071076 | -0.43193 | -0.11598 | 0.46102 | 0.49078 | -0.10921 | 0.062077
| 5430 | -0.034029 | -0.28719 | -0.34311 | -0.15306 | 0.65839 | 0.57023 | 0.075933 | -0.94804 | -0.30682 | -0.13983
| 5431 | 0.68903 | -0.57846 | -0.1473 | -0.21 | -0.0065716 | 0.1292 | -0.59963 | -0.90673 | -0.025372 | -0.21546
| 5432 | 0.65722 | -0.069677 | -0.26074 | 0.43035 | 0.2512 | -0.14145 | -0.91 | -0.085724 | -0.71242 | -0.22263
| 5433 | -0.40865 | -0.26156 | -0.19396 | 0.03974 | 0.10362 | 0.024449 | -0.27096 | -0.099722 | -0.72815 | 0.1921
| 5434 | 0.66162 | -0.3425 | -0.42546 | 0.45073 | 0.0056661 | 0.1179 | 0.42528 | -0.16244 | -0.081251 | 0.42251
| 5435 | 0.29608 | -0.26973 | -0.15923 | 0.47189 | 0.4898 | 0.57163 | -0.16603 | -0.31102 | 0.27896 | -0.38689
| 5436 | 0.41579 | 0.15839 | 0.36715 | 0.41051 | -0.48473 | 0.55898 | 0.17836 | 0.49473 | -0.63462 | 0.12805
| 5437 | 0.060692 | -0.11191 | -0.21725 | 0.43955 | -0.23182 | 0.65576 | 0.58563 | -0.19944 | 0.3363 | 0.22122
| 5438 | 0.81807 | 0.26863 | -0.22624 | 0.15946 | 0.028455 | -0.13542 | 0.59788 | 0.64546 | 0.58323 | 0.18446
| 5439 | 0.075716 | -0.21038 | -0.71242 | 0.079077 | 0.27924 | 0.12599 | -0.26986 | 0.37302 | 0.2313 | -0.21559
| 5440 | 0.06603 | 0.80176 | -0.84605 | -0.19185 | -0.009798 | -0.27661 | -0.33735 | -0.15389 | -0.096064 | -0.0036567
| 5441 | -0.38396 | 0.57047 | 0.061118 | 0.39477 | -0.82308 | 0.051686 | -0.44511 | -0.37783 | 0.12131 | -0.29056
| 5442 | -0.078751 | -0.25281 | -0.27688 | 0.77662 | -0.082231 | 0.020459 | 0.49731 | 0.10641 | -0.49374 | 0.4272
| 5443 | -0.10117 | 0.096839 | -0.65605 | -0.33539 | 0.098058 | 0.33766 | 0.06678 | -0.37799 | -0.39792 | -0.059947
| 5444 | 0.10776 | 0.53707 | -0.13797 | -0.030928 | 0.79875 | 0.25845 | -0.35525 | -0.33284 | 0.2985 | -0.3477
| 5445 | -0.16952 | 0.28174 | -0.025167 | 0.54956 | -0.057185 | -0.16579 | 0.11654 | 0.44009 | -0.3148 | -0.1786
| 5446 | 0.51451 | -0.30552 | -0.021379 | 0.060372 | 0.29014 | -0.039635 | -0.30971 | -0.12154 | 0.096728 | 0.016079
| 5447 | -0.87793 | -0.18975 | 0.68679 | -0.37879 | 0.013238 | 0.016791 | -0.31232 | 0.43211 | -0.29793 | 0.1136
| 5448 | -0.34388 | 0.02189 | -0.053163 | 0.09099 | -0.15567 | -0.097836 | -0.33149 | -0.27578 | 0.10966 | -0.28775
| 5449 | -0.081577 | -0.58878 | -0.48164 | -0.16819 | 0.74407 | -0.14683 | 0.14894 | -0.55966 | -0.18557 | -0.24853
| 5450 | 0.031857 | 0.39576 | -0.31949 | -0.44964 | 0.66758 | 0.47722 | 0.44206 | 0.0079819 | -0.3618 | -0.31174
| 5451 | 0.036517 | -0.40075 | 0.013339 | 0.24165 | -0.25804 | -0.73335 | 0.32096 | -0.2816 | 0.18238 | -0.09077
| 5452 | -0.13161 | -0.25508 | 0.38804 | 0.11202 | 0.12576 | -0.37734 | -0.52661 | -0.46269 | -0.28383 | 0.21994
| 5453 | 0.53427 | 0.15342 | -0.79628 | 0.17084 | 0.44152 | -0.044228 | -0.16125 | 0.26359 | -0.15247 | -0.29367
| 5454 | 0.51492 | 0.55739 | -0.071399 | -0.069463 | -0.51 | 0.042555 | 0.21763 | -0.54536 | 0.65029 | -0.20495
| 5455 | 0.0064709 | -0.34129 | -0.2711 | -0.34448 | 0.55357 | -0.21521 | 0.039115 | -0.10061 | 0.48824 | -0.46699
| 5456 | 0.76655 | 0.26007 | -0.084194 | -0.58491 | 0.25535 | -0.19049 | 0.56034 | 0.51761 | 0.43405 | -0.2985
| 5457 | -0.19645 | -0.21432 | 0.84094 | -0.31802 | -0.32214 | 0.44728 | -0.66728 | 0.4717 | 0.81588 | -0.3956
| 5458 | 0.089121 | 0.09839 | 0.448 | -0.69586 | 0.24336 | 0.66399 | -0.29537 | 0.61594 | -0.23325 | 0.91112
| 5459 | 0.20571 | -0.3074 | 0.19994 | -0.22302 | -0.6755 | 0.09529 | -0.66162 | 0.71452 | 0.058671 | -0.81
| 5460 | 0.28523 | 0.25602 | -0.28341 | 0.70521 | -0.19533 | 0.17787 | 0.080816 | 0.087147 | -0.74841 | -0.29395
| 5461 | 0.17823 | 0.33269 | -0.35479 | 0.65663 | -0.34754 | 0.30986 | 0.52534 | 0.53535 | 0.56676 | 0.45695
| 5462 | -0.058565 | 0.17836 | 0.24561 | 0.65518 | -0.38934 | -0.11496 | -0.013136 | -0.022401 | -0.34235 | -0.3759
| 5463 | 0.18434 | 0.5806 | 0.033512 | -0.25899 | -0.63 | -0.50533 | -0.75566 | -0.078208 | -0.17592 | 0.024654
| 5464 | -0.36415 | -0.4286 | 0.37574 | 0.67891 | -0.3242 | 0.09 | -0.16507 | 0.36102 | 0.59368 | -0.03579
| 5465 | 0.64293 | 0.21215 | -0.0010506 | -0.40092 | 0.23495 | -0.43884 | 0.34144 | 0.22392 | -0.045694 | 0.63765
| 5466 | -0.58323 | 0.038491 | -0.48707 | 0.59813 | 0.072476 | -0.072584 | 0.74019 | -0.40561 | -0.080489 | -0.0045604
| 5467 | 0.30913 | 0.7687 | 0.25307 | 0.19607 | -0.34144 | 0.39082 | -0.36305 | -0.82708 | -0.23574 | 0.38186
| 5468 | 0.22379 | 0.16759 | -0.15436 | 0.32051 | 0.094185 | -0.06957 | -0.49177 | -0.74761 | -0.031651 | 0.93443
| 5469 | -0.23495 | 0.39659 | -0.26672 | 0.60063 | 0.56377 | -0.49196 | 0.088024 | 0.26441 | 0.75485 | -0.52957
| 5470 | -0.57562 | 0.2711 | -0.34617 | 0.63217 | -0.22083 | 0.088243 | 0.12656 | -0.64518 | -0.15768 | 0.55785
| 5471 | 0.1752 | -0.33932 | -0.022401 | -0.64574 | -0.036932 | -0.63903 | 0.30581 | -0.66789 | -0.40092 | 0.048002
| 5472 | -0.42389 | -0.30337 | 0.013238 | -0.66698 | -0.14953 | -0.51369 | -0.044647 | -0.1245 | -0.19669 | 0.14542
| 5473 | 0.51164 | 0.39263 | -0.64914 | 0.079294 | -0.096396 | 0.027015 | -0.70117 | -0.19757 | -0.0075787 | -0.35634
| 5474 | 0.30136 | 0.020459 | 0.1261 | -0.15165 | 0.86108 | 0.44619 | -0.12051 | 0.40292 | 0.15673 | -0.34327
| 5475 | -0.23993 | -0.11394 | 0.40443 | 0.64209 | 0.50796 | 0.4985 | -0.41459 | -0.8454 | 0.44764 | -0.10117
| 5476 | -0.36857 | -0.30696 | 0.67091 | 0.34938 | 0.60719 | -0.17435 | 0.087914 | 0.17823 | 0.36968 | 0.38967
| 5477 | -0.14461 | 0.023117 | -0.35587 | 0.77528 | 0.10317 | -0.17193 | -0.52873 | -0.84157 | 0.43511 | -0.14402
| 5478 | 0.29226 | 0.58612 | -0.032994 | 0.09695 | 0.30064 | 0.64602 | 0.23117 | -0.070861 | 0.42147 | -0.30423
| 5479 | -0.37751 | -0.20458 | -0.077232 | 0.14601 | -0.10094 | 0.46962 | -0.78114 | -0.52345 | -0.31073 | 0.0030547
| 5480 | 0.4801 | -0.45769 | 0.34023 | -0.49572 | -0.27647 | 0.75731 | 0.22469 | -0.10039 | 0.073016 | -0.4117
| 5481 | 0.12966 | 0.40075 | 0.67121 | 0.21381 | -0.33269 | -0.011112 | 0.34892 | -0.31919 | -0.70217 | 0.84933
| 5482 | 0.035687 | 0.29466 | -0.62784 | 0.22689 | 0.62251 | 0.37414 | -0.32346 | 0.1729 | -0.23705 | 0.41511
| 5483 | 0.19969 | -0.27813 | 0.10529 | -0.040052 | -0.06753 | 0.57444 | 0.62357 | -0.20269 | 0.0060684 | 0.26413
| 5484 | -0.04099 | 0.38364 | 0.60898 | 0.28216 | 0.10888 | 0.64097 | 0.24389 | 0.47076 | -0.11949 | 0.1229
| 5485 | -0.48902 | 0.073987 | -0.68047 | -0.26509 | -0.10362 | 0.46624 | -0.42009 | 0.067208 | -0.33374 | 0.49691
| 5486 | -0.1375 | -0.033408 | -0.45237 | 0.21904 | -0.19682 | -0.27965 | 0.16519 | -0.54382 | -0.58733 | -0.043705
| 5487 | -0.25388 | -0.4799 | 0.62624 | 0.12954 | 0.57798 | -0.14461 | 0.5283 | -0.3038 | -0.39925 | 0.022606
| 5488 | -0.28733 | -0.056655 | -0.085615 | 0.33075 | -0.23613 | -0.23052 | -0.39016 | 0.32465 | 0.48629 | 0.1597
| 5489 | 0.037036 | -0.39809 | 0.43246 | -0.6077 | -0.57893 | 0.35339 | -0.063037 | 0.24046 | 0.080054 | -0.136
| 5490 | -0.19944 | -0.21712 | 0.43 | 0.11236 | -0.0015512 | -0.61309 | 0.86325 | 0.081577 | 0.11892 | 0.75648
| 5491 | 0.22045 | 0.13484 | 0.11372 | 0.86621 | 0.12805 | 0.1005 | -0.76315 | 0.30179 | -0.20144 | 0.23404
| 5492 | -0.18667 | -0.14906 | 0.66789 | 0.16125 | 0.50392 | -0.055172 | 0.72089 | 0.53427 | 0.78952 | -0.04381
| 5493 | 0.60038 | 0.18852 | -0.61026 | -0.82308 | 0.044961 | 0.43795 | -0.59245 | 0.025577 | 0.52387 | 0.36133
| 5494 | 0.32672 | -0.56239 | -0.67766 | 0.36889 | -0.10888 | -0.29523 | 0.11983 | -0.6257 | 0.22935 | 0.79384
| 5495 | -0.82479 | -0.2326 | -0.16807 | -0.34923 | 0.20659 | 0.32613 | -0.17326 | -0.80481 | -0.69718 | -0.067852
| 5496 | 0.034133 | 0.4981 | 0.5005 | 0.3477 | -0.34038 | 0.35961 | -0.2941 | 0.042138 | 0.81862 | -0.088463
| 5497 | 0.58012 | 0.13034 | 0.26658 | -0.58443 | 0.83237 | -0.0093941 | 0.27357 | -0.37064 | -0.62919 | -0.56262
| 5498 | 0.86399 | 0.11 | 0.10161 | -0.65029 | 0.16316 | 0.24667 | -0.46474 | 0.32672 | -0.27233 | -0.080054
| 5499 | -0.91815 | -0.054749 | 0.63737 | 0.043914 | -0.79727 | -0.38984 | 0.53535 | -0.33781 | 0.053691 | -0.67674
| 5500 | 0.44982 | 0.23993 | 0.15082 | -0.52534 | 0.54978 | -0.17884 | 0.40628 | 0.56722 | -0.23796 | -0.52513
| 5501 | 0.20483 | -0.24033 | -0.52303 | -0.19769 | -0.2287 | -0.13843 | 0.83297 | 0.10284 | -0.11326 | 0.32643
| 5502 | -0.057291 | -0.055384 | -0.3477 | -0.12541 | -0.78669 | 0.096617 | -0.11248 | -0.015165 | -0.14531 | -0.55357
| 5503 | -0.77044 | -0.21891 | -0.77841 | 0.0062697 | 0.31189 | -0.85337 | 0.5224 | 0.27027 | -0.10978 | -0.16555
| 5504 | -0.028352 | 0.55402 | -0.10206 | 0.15165 | 0.026193 | -0.23013 | -0.20861 | 0.8739 | 0.29594 | -0.031548
| 5505 | -0.14941 | 0.34129 | 0.58251 | 0.36463 | -0.15661 | 0.93144 | 0.09055 | 0.18495 | -0.51927 | 0.41374
| 5506 | -0.68968 | -0.11711 | 0.28049 | 0.048633 | -0.69488 | -0.94615 | 0.45991 | 0.65029 | 0.68647 | -0.26007
| 5507 | 0.50918 | 0.0050628 | -0.48318 | -0.1025 | 0.84157 | -0.29197 | 0.18067 | -0.23065 | 0.33134 | 0.50472
| 5508 | 0.21139 | -0.21572 | -0.53967 | -0.41596 | 0.7839 | 0.17508 | 0.80125 | -0.095401 | -0.72089 | 0.4983
| 5509 | -0.58107 | -0.63848 | 0.031754 | -0.18926 | -0.47436 | -0.19595 | 0.49177 | 0.43884 | -0.13634 | -0.62973
| 5510 | -0.11349 | 0.31582 | 0.14695 | -0.2356 | 0.25455 | 0.39825 | 0.13046 | 0.043182 | 0.65143 | -0.33045
| 5511 | -0.35278 | -0.33359 | -0.11994 | -0.23587 | 0.23691 | 0.25858 | 0.23169 | 0.11383 | 0.45255 | 0.39329
| 5512 | -0.041616 | -0.56194 | 0.1758 | 0.71382 | -0.45695 | -0.17205 | -0.15531 | 0.33509 | -0.030825 | 0.70184
| 5513 | -0.10284 | -0.057716 | -0.035479 | 0.39676 | -0.38364 | -0.44565 | 0.33299 | -0.4553 | 0.20735 | 0.50271
| 5514 | -0.13808 | -0.19819 | -0.16436 | 0.33239 | 0.11293 | 0.17121 | 0.064425 | 0.020051 | 0.45091 | -0.28691
| 5515 | 0.51595 | -0.051686 | 0.51534 | 0.31553 | -0.25013 | 0.10764 | -0.0086877 | -0.23325 | 0.4206 | -0.1688
| 5516 | 0.51307 | 0.30451 | 0.47798 | -0.56768 | -0.13322 | 0.21699 | 0.33796 | 0.52745 | -0.32776 | -0.1425
| 5517 | -0.54889 | 0.31203 | -0.26088 | 0.45055 | 0.0011507 | -0.4542 | 0.016791 | -0.072045 | -0.17181 | -0.44927
| 5518 | -0.11484 | 0.53192 | -0.3087 | 0.06261 | -0.41751 | -0.44547 | 0.33389 | -0.62092 | 0.049789 | -0.56861
| 5519 | 0.42633 | -0.036102 | -0.47722 | 0.46493 | -0.25482 | -0.26932 | -0.20609 | 0.77887 | -0.011921 | 0.17229
| 5520 | 0.42668 | -0.47703 | -0.28035 | 0.27938 | -0.51225 | 0.51287 | -0.66939 | -0.033408 | -0.024654 | -0.41957
| 5521 | 0.10195 | 0.19185 | 0.029485 | -0.31465 | -0.26128 | -0.52597 | -0.36889 | 0.15863 | 0.49453 | -0.014049
| 5522 | 0.061118 | 0.58927 | 0.36164 | 0.57374 | 0.41733 | -0.099944 | -0.02568 | 0.76272 | -0.21419 | 0.11994
| 5523 | 0.73111 | -0.77044 | -0.22366 | -0.28327 | 0.2234 | -0.62704 | 0.09077 | 0.40309 | 0.40259 | 0.66698
| 5524 | -0.057079 | 0.43938 | -0.31846 | -0.045694 | 0.18655 | -0.18189 | -0.80687 | 0.11733 | 0.57515 | 0.039844
| 5525 | -0.077449 | 0.65402 | -0.70589 | 0.4265 | 0.52703 | 0.56216 | -0.0045604 | -0.3211 | -0.48668 | -0.22071
| 5526 | 0.1044 | -0.18422 | 0.065281 | -0.11745 | -0.75161 | 0.3961 | -0.22431 | -0.17799 | 0.12199 | 0.019337
| 5527 | 0.051264 | -0.93917 | 0.024962 | 0.41408 | -0.36384 | 0.14706 | -0.14157 | 0.23351 | 0.21368 | -0.27799
| 5528 | 0.58636 | -0.12576 | -0.12336 | 0.34724 | -0.20458 | -0.06603 | -0.33299 | -0.1439 | 0.41187 | 0.045275
| 5529 | -0.032374 | 0.63792 | 0.27979 | 0.24099 | 0.10072 | 0.4265 | -0.80635 | -0.62677 | 0.40242 | -0.70318
| 5530 | 0.59417 | -0.16603 | 0.18889 | -0.41819 | -0.63654 | 0.14835 | 0.28901 | -0.28021 | 0.45073 | 0.56653
| 5531 | -0.64546 | -0.32243 | -0.21063 | -0.24548 | 0.59913 | 0.20181 | 0.20861 | -0.15756 | 0.43991 | -0.36149
| 5532 | 0.64153 | -0.34494 | -0.032064 | -0.69422 | -0.52408 | 0.1025 | -0.79288 | -0.55 | 0.37064 | 0.52219
| 5533 | -0.17677 | 0.23338 | 0.27014 | 0.039219 | 0.70657 | 0.037555 | -0.92859 | -0.051159 | -0.78251 | -0.38056
| 5534 | -0.38804 | -0.64857 | -0.43423 | 0.63848 | 0.29822 | -0.77977 | 0.70352 | 0.23915 | -0.12063 | 0.63108
| 5535 | -0.44764 | 0.35961 | -0.037763 | 0.74761 | 0.23639 | 0.43299 | -0.66103 | 0.11994 | -0.085834 | -0.1338
| 5536 | -0.81106 | -0.56977 | -0.69488 | -0.13 | 0.024859 | -0.0089904 | 0.2287 | -0.37382 | -0.39908 | -0.10351
| 5537 | 0.52303 | 0.10195 | 0.5001 | 0.29793 | 0.22405 | 0.15365 | 0.06197 | -0.57846 | 0.13046 | 0.031444
| 5538 | 0.32896 | 0.29979 | 0.22805 | -0.20546 | 0.37064 | -0.12943 | -0.31073 | -0.19148 | -0.41528 | 0.69097
| 5539 | -0.7687 | 0.30783 | 0.19124 | -0.29014 | -0.036309 | -0.11067 | 0.35649 | -0.44674 | 0.21203 | -0.40142
| 5540 | 0.084304 | -0.81972 | 0.55875 | -0.054326 | 0.3211 | -0.11722 | -0.019439 | -0.79628 | -0.12473 | -0.078751
| 5541 | 0.41204 | -0.55492 | -0.085724 | -0.13901 | -0.5011 | 0.42441 | 0.67304 | 0.42389 | -0.23417 | -0.36164
| 5542 | -0.82766 | 0.28635 | 0.84736 | 0.41477 | -0.36683 | -0.41922 | 0.052846 | -0.73373 | -0.26332 | 0.44475
| 5543 | 0.59196 | -0.83599 | -0.28271 | -0.68361 | 0.56861 | -0.80481 | 0.097282 | -0.52303 | 0.97354 | 0.39975
| 5544 | -0.014657 | -0.009596 | -0.60314 | 0.17495 | 0.038699 | -0.024962 | 0.42965 | 0.15047 | 0.69983 | -0.31758
| 5545 | -0.11609 | 0.61051 | 0.59738 | -0.038803 | -0.034961 | -0.68903 | -0.083321 | -0.32391 | -0.1315 | -0.37032
| 5546 | 0.8366 | 0.41613 | 0.2722 | -0.16783 | -0.38771 | 0.14017 | 0.055172 | -0.46643 | -0.16077 | 0.52534
| 5547 | -0.54054 | -0.46906 | -0.42807 | 0.28104 | -0.16651 | 0.58927 | -0.20019 | -0.63545 | -0.099944 | -0.10742
| 5548 | -0.56977 | 0.82651 | -0.20445 | 0.035687 | -0.040052 | -0.55245 | -0.47493 | 0.35525 | -0.0071757 | -0.013542
| 5549 | -0.49157 | -0.27979 | 0.42668 | 0.5007 | -0.11169 | -0.59 | 0.75282 | -0.54098 | -0.046847 | -0.077232
| 5550 | 0.50271 | -0.14099 | 0.020153 | 0.32391 | -0.10652 | -0.3681 | 0.30639 | 0.18483 | 0.22767 | 0.29311
| 5551 | 0.26345 | -0.14742 | 0.41665 | 0.35062 | -0.37574 | -0.66162 | 0.22702 | 0.2037 | -0.67396 | -0.12622
| 5552 | -0.19124 | 0.5883 | 0.21025 | -0.42703 | 0.43564 | -0.26061 | -0.10395 | 0.039219 | -0.41102 | -0.40763
| 5553 | 0.12747 | 0.062077 | 0.37111 | 0.64349 | 0.0073772 | 0.079294 | 0.33524 | 0.30308 | -0.37032 | -0.67366
| 5554 | 0.51906 | -0.1044 | -0.3048 | -0.30639 | 0.13115 | -0.26986 | -0.67798 | -0.12484 | 0.54382 | 0.19906
| 5555 | 0.32081 | 0.16161 | 0.13346 | -0.32228 | 0.20861 | -0.57798 | -0.095843 | -0.047687 | -0.29268 | 0.3357
| 5556 | 0.44909 | 0.2985 | 0.12966 | -0.037867 | -0.65663 | -0.72486 | 0.51266 | -0.12622 | -0.1418 | 0.31553
| 5557 | -0.64461 | -0.28481 | -0.22045 | -0.38056 | 0.075608 | 0.49631 | -0.54668 | 0.25791 | 0.084194 | -0.08649
| 5558 | -0.62731 | -0.54033 | 0.71242 | 0.41699 | 0.364 | 0.035479 | -0.77617 | -0.22741 | 0.25831 | -0.43635
| 5559 | -0.19744 | -0.26781 | 0.034858 | -0.3038 | 0.095511 | 0.44116 | 0.2773 | -0.23417 | -0.48941 | 0.17982
| 5560 | 0.18312 | -0.49691 | 0.13357 | 0.26196 | 0.070108 | -0.33992 | -0.83118 | -0.38202 | -0.20344 | 0.14648
| 5561 | 0.99 | 0.82941 | 0.75403 | 0.048843 | 0.052002 | 0.074203 | -0.66015 | -0.16209 | 0.20319 | -0.092531
| 5562 | -0.10697 | 0.01791 | 0.12256 | 0.21266 | 0.47818 | -0.084304 | -0.049579 | 0.20483 | -0.013643 | -0.51184
| 5563 | -0.63931 | 0.24429 | 0.55089 | -0.29893 | 0.43035 | 0.18483 | -0.31509 | 0.2941 | -0.34846 | 0.012022
| 5564 | -0.28579 | -0.41187 | -0.60138 | 0.093634 | 0.20886 | 0.066565 | -0.16687 | -0.35961 | -0.0026535 | -0.4985
| 5565 | 0.12954 | 0.27661 | -0.080272 | -0.31422 | -0.31218 | -0.040886 | 0.16304 | -0.30581 | 0.01842 | -0.20848
| 5566 | -0.018929 | 0.37446 | -0.1277 | -0.73186 | -0.36541 | 0.23182 | 0.3817 | -0.5656 | -0.42424 | -0.011415
| 5567 | -0.57421 | 0.43973 | -0.2488 | 0.248 | 0.67488 | -0.81807 | -0.59639 | 0.71242 | 0.37751 | -0.40058
| 5568 | 0.56239 | -0.62946 | -0.42441 | -0.70623 | -0.56102 | 0.47894 | -0.30064 | -0.76527 | -0.42268 | -0.059309
| 5569 | 0.12793 | -0.63875 | 0.080598 | 0.13971 | -0.56285 | 0.096285 | 0.23678 | 0.43706 | 0.39792 | 0.18753
| 5570 | 0.19719 | 0.53171 | 0.8422 | 0.066887 | -0.43813 | -0.79628 | -0.26795 | -0.45292 | -0.57562 | 0.57964
| 5571 | 0.41408 | 0.021481 | -0.49 | -0.028558 | 0.43211 | -0.12256 | 0.083976 | 0.44764 | -0.18988 | 0.39066
| 5572 | -0.80481 | 0.0036567 | -0.01547 | -0.28663 | 0.31218 | -0.24099 | 0.1245 | 0.15839 | -0.46418 | 0.58299
| 5573 | 0.003456 | 0.32066 | 0.0067729 | 0.030516 | -0.19595 | 0.58083 | 0.15283 | -0.10028 | -0.11835 | -0.31203
| 5574 | 0.32866 | -0.076799 | -0.094627 | 0.22405 | 0.11858 | 0.436 | -0.37863 | 0.12587 | 0.20684 | 0.09066
| 5575 | -0.071507 | -0.053163 | 0.060372 | 0.023015 | 0.11643 | 0.023936 | -0.16268 | 0.44367 | -0.5098 | 0.60138
| 5576 | 0.15153 | -0.50371 | -0.35914 | -0.17556 | -0.20156 | -0.52894 | -0.14285 | -0.039635 | 0.16268 | -0.448
| 5577 | 0.82084 | 0.36447 | -0.8755 | -0.69983 | -0.436 | 0.47741 | 0.53772 | 0.19086 | -0.9272 | 0.039011
| 5578 | 0.38902 | 0.48493 | 0.06957 | 0.1688 | 0.023424 | 0.65489 | -0.51699 | 0.29893 | -0.53021 | -0.8422
| 5579 | 0.18373 | -0.53128 | 0.089561 | 0.45493 | 0.20836 | 0.19185 | -0.016791 | 0.2119 | 0.27993 | -0.24681
| 5580 | -0.061331 | -0.061757 | -0.09529 | -0.11473 | -0.51451 | 0.32096 | 0.18606 | -0.51802 | -0.13577 | 0.97
| 5581 | 0.44692 | -0.22508 | 0.042138 | -0.24072 | 0.02097 | -0.15448 | -0.55875 | -0.32228 | -0.28972 | -0.28035
| 5582 | -0.61751 | -0.40175 | -0.28972 | 0.45917 | 0.014962 | 0.28775 | 0.17702 | -0.7245 | 0.16771 | -0.39709
| 5583 | 0.13611 | -0.9134 | 0.18434 | 0.11609 | 0.63572 | -0.70691 | -0.548 | 0.22263 | -0.075716 | 0.51802
| 5584 | 0.05984 | -0.3451 | -0.42424 | -0.22521 | 0.76527 | 0.68047 | 0.57727 | 0.46381 | 0.13577 | 0.59098
| 5585 | -0.28313 | 0.17326 | 0.034443 | 0.74019 | -0.12599 | 0.68871 | 0.38251 | -0.36762 | 0.80791 | 0.024244
| 5586 | 0.16496 | -0.093523 | -0.75979 | 0.59938 | -0.9089 | 0.80739 | 0.088792 | 0.10608 | -0.57023 | -0.15082
| 5587 | 0.041303 | 0.11383 | 0.0029544 | 0.62704 | -0.39016 | -0.2484 | -0.22238 | 0.62198 | -0.54294 | 0.27591
| 5588 | 0.43193 | -0.50675 | -0.30841 | 0.2161 | -0.54273 | 0.014454 | 0.0011507 | 0.6811 | -0.59888 | 0.041199
| 5589 | 0.038387 | -0.19806 | -0.28523 | 0.72632 | -0.71769 | 0.63108 | 0.26495 | 0.75731 | 0.35262 | -0.12553
| 5590 | -0.45954 | 0.09187 | 0.41289 | -0.092531 | -0.10284 | 0.43529 | 0.009899 | 0.034754 | 0.45567 | -0.49315
| 5591 | -0.025167 | -0.85269 | 0.19235 | 0.42181 | 0.21623 | 0.050211 | 0.31422 | 0.28523 | -0.14589 | 0.49315
| 5592 | 0.87793 | -0.25562 | 0.48863 | 0.15247 | 0.26101 | -0.46549 | 0.22676 | 0.062823 | 0.56491 | -0.26454
| 5593 | -0.030825 | 0.51823 | 0.47779 | -0.65114 | -0.62543 | 0.28439 | -0.65229 | -0.11214 | -0.28551 | -0.074203
| 5594 | -0.0082843 | -0.22431 | 0.42078 | -0.10006 | 0.34235 | 0.17677 | -0.41408 | 0.52809 | -0.93 | 0.36541
| 5595 | 0.44421 | 0.26645 | 0.37143 | 0.66192 | 0.64631 | 0.2492 | -0.20181 | 0.051053 | -0.025269 | -0.57964
| 5596 | 0.82941 | 0.29183 | -0.56468 | 0.16316 | 0.089341 | -0.02722 | 0.34008 | 0.2496 | 0.35696 | 0.42598
| 5597 | -0.27233 | 0.27702 | 0.18741 | -0.055384 | -0.19446 | -0.68172 | -0.40359 | 0.45954 | -0.077232 | -0.47684
| 5598 | 0.39098 | 0.34877 | 0.2402 | 0.56954 | 0.21495 | 0.60188 | 0.10921 | -0.32096 | 0.55943 | 0.48532
| 5599 | -0.45292 | -0.10317 | -0.048422 | 0.38024 | -0.28313 | 0.48668 | -0.097282 | 0.12736 | -0.41957 | 0.25872
| 5600 | 0.47818 | -0.30394 | 0.47 | -0.015876 | 0.081469 | 0.026296 | -0.19669 | 0.27274 | 0.050526 | 0.30451
| 5601 | 0.0046609 | -0.017401 | 0.1015 | 0.1323 | -0.23325 | -0.17763 | -0.37334 | -0.58903 | 0.71627 | 0.22392
| 5602 | -0.20798 | -0.075933 | -0.58371 | 0.39643 | -0.60949 | -0.30523 | -0.088463 | 0.41957 | 0.37191 | -0.033305
| 5603 | 0.28425 | 0.20621 | 0.15626 | 0.5529 | 0.71804 | 0.11293 | -0.39875 | -0.20357 | 0.0020521 | -0.0057666
| 5604 | -0.26808 | 0.080272 | -0.045275 | 0.26318 | 0.37111 | -0.11756 | -0.15626 | -0.071722 | 0.11733 | 0.85543
| 5605 | -0.12461 | 0.71663 | -0.12267 | -0.46493 | -0.34418 | -0.39296 | -0.68456 | -0.012022 | -0.1072 | -0.11677
| 5606 | -0.78114 | 0.50837 | -0.0014511 | -0.72815 | -0.44674 | -0.50231 | -0.3651 | 0.27951 | -0.22379 | 0.36873
| 5607 | 0.50533 | -0.18067 | 0.16519 | 0.70083 | -0.22624 | -0.49413 | -0.44746 | -0.18312 | -0.51472 | -0.52534
| 5608 | 0.041407 | -0.58203 | 0.15224 | -0.80895 | -0.084522 | -0.040573 | 0.17447 | -0.05348 | 0.7492 | -0.71487
| 5609 | -0.31875 | 0.33675 | 0.53989 | 0.19557 | 0.3593 | -0.48415 | -0.09066 | 0.44782 | 0.13127 | 0.20257
| 5610 | -0.56861 | 0.038699 | -0.007075 | 0.19421 | -0.48106 | -0.60314 | -0.47894 | -0.43759 | 0.6697 | 0.46605
| 5611 | -0.8467 | -0.50634 | 0.45018 | -0.30222 | -0.1237 | 0.64546 | -0.19037 | 0.15507 | 0.01344 | -0.78483
| 5612 | 0.58107 | 0.13161 | -0.30971 | -0.29921 | 0.37751 | -0.13034 | -0.70589 | -0.18165 | 0.17326 | -0.3038
| 5613 | 0.5009 | -0.41102 | -0.40628 | -0.041512 | -0.4736 | 0.36984 | -0.18704 | 0.18226 | -0.57257 | 0.02322
| 5614 | -0.59714 | 0.52492 | -0.39263 | -0.052424 | 0.10876 | -0.26522 | -0.56034 | 0.068388 | -0.20975 | -0.58684
| 5615 | -0.0047613 | 0.50796 | 0.013643 | -0.23364 | 0.49295 | -0.21051 | 0.0049623 | -0.11462 | -0.10161 | 0.17109
| 5616 | 0.65605 | -0.5021 | -0.10061 | -0.27467 | -0.09011 | 0.40376 | 0.4426 | -0.14965 | 0.77662 | 0.040677
| 5617 | 0.030309 | 0.27938 | -0.77087 | -0.26577 | -0.2037 | 0.059309 | -0.78206 | 0.44964 | -0.22987 | -0.36243
| 5618 | 0.11191 | -0.75896 | -0.37526 | 0.41136 | 0.17096 | -0.8739 | 0.42511 | -0.24363 | 0.060479 | 0.34785
| 5619 | -0.12507 | -0.27854 | 0.04538 | 0.62517 | -0.32524 | -0.0866 | -0.09022 | 0.20131 | 0.10206 | 0.066458
| 5620 | 0.35 | 0.25414 | 0.43105 | -0.096064 | -0.75896 | 0.29879 | 0.65 | -0.30293 | -0.21127 | -0.58805
| 5621 | 0.0063703 | -0.3297 | -0.11011 | 0.28313 | 0.38689 | 0.27591 | -0.33856 | 0.077883 | -0.79875 | 0.18177
| 5622 | 0.59639 | 0.066458 | -0.013136 | -0.17024 | 0.35015 | 0.59392 | -0.30595 | 0.86771 | 0.034029 | -0.011719
| 5623 | -0.31087 | -0.15047 | -0.4542 | -0.15567 | 0.16639 | -0.48396 | 0.52324 | -0.072908 | -0.30957 | -0.24007
| 5624 | 0.080924 | 0.10529 | 0.037036 | -0.13438 | 0.48202 | -0.31334 | 0.28383 | -0.15555 | -0.63244 | -0.63108
| 5625 | 0.23325 | 0.12165 | 0.56699 | -0.32494 | 0.42216 | -0.09209 | -0.30812 | 0.40544 | 0.31247 | 0.39016
| 5626 | -0.39279 | -0.27096 | 0.20081 | -0.5172 | 0.57751 | -0.6697 | -0.14006 | 0.55966 | -0.49039 | 0.5102
| 5627 | 0.72705 | -0.22857 | -0.65956 | 0.52198 | 0.76146 | 0.16244 | 0.27274 | 0.070215 | -0.10273 | 0.36149
| 5628 | 0.10933 | 0.30136 | -0.71104 | 0.17848 | -0.21152 | -0.37847 | 0.65402 | 0.26169 | -0.236 | 0.59738
| 5629 | -0.6149 | -0.35062 | -0.75322 | 0.15472 | -0.0038574 | 0.53881 | -0.16412 | 0.43493 | -0.81917 | 0.25858
| 5630 | -0.32643 | -0.17133 | -0.32866 | -0.59565 | -0.088353 | 0.007075 | 0.43742 | -0.78344 | 0.055172 | -0.68552
| 5631 | 0.19062 | -0.28076 | -0.029279 | 0.68679 | -0.5714 | -0.34159 | 0.15436 | 0.70083 | 0.49473 | 0.09132
| 5632 | 0.34601 | -0.023117 | 0.73074 | -0.09209 | 0.23 | 0.26332 | 0.51948 | 0.10462 | 0.041825 | 0.23338
| 5633 | 0.13971 | 0.6241 | -0.0051633 | -0.27993 | 0.74841 | 0.32258 | -0.030309 | -0.32717 | 0.35463 | 0.082449
| 5634 | 0.48087 | -0.021276 | -0.48746 | -0.27082 | 0.46065 | -0.48687 | 0.12302 | -0.32007 | -0.17435 | 0.37191
| 5635 | -0.44475 | 0.4993 | -0.43938 | -0.66133 | 0.39494 | -0.29113 | -0.20646 | 0.39444 | -0.10328 | 0.41528
| 5636 | 0.3245 | 0.57988 | -0.31626 | -0.11281 | 0.57468 | -0.44619 | 0.85134 | -0.27716 | 0.65634 | 0.81752
| 5637 | -0.09529 | 0.37207 | 0.48902 | 0.41119 | 0.74525 | 0.080163 | 0.23143 | 0.057397 | 0.0053644 | -0.022503
| 5638 | -0.048107 | -0.14297 | -0.10117 | 0.056231 | -0.31029 | 0.3727 | 0.32569 | 0.32687 | -0.11056 | -0.28593
| 5639 | 0.094296 | 0.55875 | 0.084085 | -0.33194 | 0.31949 | 0.44764 | -0.45383 | 0.050526 | -0.57421 | -0.47569
| 5640 | 0.76827 | 0.59073 | 0.41768 | 0.4991 | 0.074527 | -0.27674 | 0.95204 | -0.09055 | 0.36731 | -0.74096
| 5641 | -0.24588 | 0.10708 | -0.35386 | 0.17994 | -0.38186 | 0.35665 | 0.15318 | -0.017401 | 0.58878 | -0.36008
| 5642 | -0.13496 | -0.70117 | 0.23587 | 0.26795 | -0.78905 | 0.12793 | 0.67922 | 0.28271 | -0.71557 | -0.040573
| 5643 | 0.19471 | 0.4588 | -0.47933 | -0.011213 | -0.15365 | -0.20282 | -0.024244 | -0.64097 | -0.62838 | 0.47798
| 5644 | -0.29268 | 0.20596 | -0.14976 | -0.58203 | 0.53256 | 0.34464 | 0.36384 | -0.1952 | -0.030722 | 0.64125
| 5645 | -0.28565 | -0.16448 | 0.32791 | -0.40376 | 0.069785 | -0.11564 | -0.74485 | 0.24125 | -0.28467 | -0.35541
| 5646 | 0.24867 | 0.18153 | -0.23325 | -0.32791 | 0.076474 | 0.55402 | 0.29779 | 0.19919 | -0.48687 | -0.49711
| 5647 | 0.33134 | 0.51802 | 0.32243 | -0.16735 | 0.47493 | -0.42668 | -0.00075028 | -0.13669 | -0.38934 | -0.15071
| 5648 | 0.63765 | -0.043914 | -0.30337 | -0.36715 | 0.65057 | 0.67891 | 0.53406 | -0.079946 | 0.25267 | 0.068388
| 5649 | 0.42251 | -0.32866 | 0.44098 | 0.033925 | -0.017096 | 0.2175 | -0.41204 | 0.077449 | 0.036828 | -0.33
| 5650 | -0.034547 | -0.57491 | 0.56468 | 0.42685 | 0.60567 | -0.29014 | 0.057291 | 0.42825 | 0.29353 | 0.6044
| 5651 | -0.22663 | 0.2431 | 0.44982 | -0.3061 | -0.58419 | 0.015774 | 0.12245 | 0.30754 | 0.41238 | 0.032167
| 5652 | -0.40058 | -0.22663 | 0.18951 | 0.072908 | -0.59466 | -0.025782 | 0.27371 | -0.21482 | 0.55604 | -0.15141
| 5653 | 0.13415 | 0.16113 | 0.09132 | -0.1775 | 0.25428 | 0.68172 | 0.60063 | 0.11756 | -0.15188 | 0.83
| 5654 | -0.35649 | 0.53902 | 0.17653 | -0.15153 | -0.34235 | 0.015571 | 0.24033 | -0.082231 | 0.3303 | 0.40427
| 5655 | -0.20861 | 0.35603 | -0.23783 | 0.12966 | 0.66608 | 0.40242 | 0.20269 | 0.016486 | -0.19322 | -0.19557
| 5656 | -0.15141 | -0.40326 | -0.26808 | -0.51369 | 0.11236 | 0.067745 | 0.4279 | -0.16904 | -0.062503 | -0.22547
| 5657 | 0.4564 | 0.66819 | -0.27467 | 0.1315 | 0.040365 | 0.41357 | 0.0041586 | -0.57047 | 0.4989 | 0.59269
| 5658 | -0.82365 | 0.16268 | -0.15224 | -0.46083 | 0.11518 | 0.13357 | 0.5001 | -0.37223 | -0.52915 | -0.44188
| 5659 | -0.12541 | 0.136 | 0.076907 | 0.44601 | -0.67766 | -0.24548 | -0.58927 | 0.30783 | -0.4258 | 0.19732
| 5660 | 0.33344 | -0.15531 | -0.098723 | -0.27343 | 0.56308 | -0.26509 | 0.30079 | -0.068067 | 0.081795 | 0.64914
| 5661 | 0.12154 | -0.25885 | -0.45806 | 0.023834 | -0.039219 | 0.25294 | -0.80075 | -0.22495 | 0.41289 | 0.17933
| 5662 | -0.48183 | 0.3061 | 0.58107 | 0.80075 | -0.28663 | -0.26223 | -0.34023 | -0.47038 | -0.5013 | 0.14461
| 5663 | 0.64574 | -0.21635 | -0.76655 | -0.92859 | 0.65518 | 0.40058 | 0.4542 | 0.13484 | -0.28761 | -0.068925
| 5664 | -0.1034 | 0.081033 | 0.18079 | -0.19831 | -0.61882 | 0.74329 | -0.43193 | -0.2234 | 0.24508 | 0.21038
| 5665 | 0.098501 | -0.24973 | -0.19371 | -0.21228 | 0.21228 | 0.083212 | 0.25953 | -0.12074 | -0.16316 | -0.54163
| 5666 | -0.26849 | 0.35401 | -0.47094 | 0.44475 | -0.047162 | 0.039115 | -0.56285 | -0.030103 | -0.061331 | -0.40645
| 5667 | -0.29042 | 0.012427 | 0.4979 | -0.11293 | -0.13069 | -0.01791 | 0.43299 | -0.42233 | 0.30079 | 0.67213
| 5668 | -0.4717 | 0.19359 | 0.26156 | -0.81159 | 0.41648 | -0.027426 | -0.67366 | -0.26973 | -0.20911 | 0.04172
| 5669 | -0.35123 | 0.31978 | 0.38267 | 0.20282 | 0.025782 | -0.031651 | -0.3851 | -0.10462 | 0.015673 | -0.55943
| 5670 | -0.80328 | -0.55267 | 0.0004501 | 0.36604 | -0.70453 | -0.10351 | -0.021685 | 0.53342 | 0.15946 | -0.10239
| 5671 | -0.013136 | 0.33781 | 0.57093 | -0.18459 | -0.44475 | -0.16952 | 0.64209 | -0.73981 | -0.82479 | 0.21127
| 5672 | 0.045904 | 0.082667 | -0.1245 | 0.53643 | 0.11 | 0.19471 | -0.22792 | -0.37558 | -0.71911 | -0.16892
| 5673 | -0.10978 | 0.46624 | 0.26973 | 0.16591 | -0.3759 | -0.15863 | -0.24482 | -0.42216 | 0.54163 | -0.73751
| 5674 | 0.37175 | -0.20621 | 0.65431 | -0.28551 | -0.62677 | -0.45219 | 0.28887 | -0.15295 | 0.79336 | -0.60898
| 5675 | -0.82651 | -0.71946 | 0.087147 | 0.43991 | 0.065067 | -0.25307 | 0.22379 | -0.44583 | 0.075608 | -0.23574
| 5676 | -0.60617 | 0.10507 | -0.36102 | 0.02722 | 0.028043 | 0.081469 | 0.010808 | 0.045275 | 0.11 | -0.052319
| 5677 | 0.27233 | 0.4653 | -0.2133 | -0.48726 | 0.030412 | -0.40175 | 0.56102 | 0.43387 | 0.11552 | -0.28944
| 5678 | 0.057079 | 0.015165 | -0.32524 | 0.55492 | 0.0043595 | 0.0090913 | 0.27398 | 0.0016514 | 0.72197 | -0.13276
| 5679 | 0.1533 | 0.18778 | 0.67061 | -0.49433 | -0.34174 | 0.092972 | 0.042555 | -0.37992 | 0.17229 | 0.53256
| 5680 | 0.57 | 0.038907 | -0.23849 | 0.46139 | 0.24046 | 0.17945 | -0.30423 | 0.27785 | 0.11146 | -0.53686
| 5681 | -0.55402 | 0.79776 | 0.21699 | -0.014252 | -0.16316 | 0.2816 | 0.57163 | 0.59269 | 0.51865 | 0.23796
| 5682 | 0.037659 | -0.13832 | 0.18778 | -0.83118 | -0.34372 | 0.3454 | -0.50594 | 0.69227 | 0.42129 | 0.055384
| 5683 | -0.096839 | 0.55966 | 0.19533 | 0.65693 | 0.33856 | -0.38755 | -0.3767 | 0.24257 | -0.022912 | -0.87155
| 5684 | 0.17181 | -0.19309 | -0.0062697 | -0.45861 | 0.29651 | 0.093965 | -0.62517 | 0.20836 | 0.15911 | -0.3923
| 5685 | 0.032581 | 0.086819 | 0.40595 | -0.46121 | 0.017707 | 0.63217 | 0.048527 | 0.20962 | -0.53385 | -0.03465
| 5686 | 0.74722 | -0.40814 | 0.47094 | 0.059734 | 0.28817 | 0.35417 | 0.31363 | -0.4995 | -0.33389 | -0.29014
| 5687 | 0.04517 | 0.11801 | 0.21866 | 0.042869 | 0.81752 | 0.077232 | 0.0073772 | 0.26631 | 0.23495 | -0.1814
| 5688 | 0.1153 | 0.038179 | -0.16054 | -0.7076 | 0.54734 | -0.062823 | -0.3425 | 0.56262 | -0.15543 | 0.17217
| 5689 | 0.21968 | 0.55514 | -0.51287 | 0.30064 | -0.16687 | 0.1439 | 0.65229 | -0.085834 | -0.39859 | 0.11135
| 5690 | 0.63875 | -0.17702 | -0.64097 | 0.040052 | 0.059734 | -0.35867 | -0.18606 | -0.019949 | -0.0048618 | 0.69983
| 5691 | -0.49731 | 0.0040582 | 0.089231 | 0.43105 | -0.31495 | -0.63958 | 0.25307 | -0.54514 | 0.22469 | 0.28216
| 5692 | -0.33299 | -0.34724 | 0.092862 | -0.63027 | 0.18581 | -0.29311 | -0.29254 | -0.77662 | 0.43688 | 0.22482
| 5693 | -0.12851 | -0.41871 | -0.74525 | -0.3537 | 0.084631 | 0.28467 | -0.27993 | -0.54845 | -0.31802 | -0.20772
| 5694 | -0.38853 | -0.22676 | -0.82365 | 0.35479 | 0.44027 | 0.22922 | 0.095401 | -0.054114 | 0.66192 | -0.20949
| 5695 | 0.15887 | -0.18951 | -0.2377 | 0.17921 | 0.448 | 0.27261 | -0.21942 | -0.64042 | 0.058246 | 0.35712
| 5696 | 0.29028 | 0.5098 | 0.33479 | -0.33359 | -0.0911 | 0.34281 | 0.09121 | 0.1323 | -0.31538 | -0.47722
| 5697 | -0.35185 | -0.53707 | -0.096507 | -0.68078 | -0.39859 | -0.33796 | -0.16519 | -0.1814 | -0.08989 | 0.13322
| 5698 | -0.61856 | 0.058777 | -0.60949 | -0.42285 | 0.79826 | 0.45787 | -0.73866 | 0.13 | 0.28831 | 0.20823
| 5699 | -0.23234 | -0.088573 | -0.05422 | -0.1578 | 0.029485 | -0.31436 | 0.11034 | -0.35649 | 0.10106 | -0.4828
| 5700 | 0.012731 | 0.67581 | -0.22586 | 0.32066 | -0.7488 | 0.30164 | -0.12324 | 0.45787 | -0.29907 | 0.11349
| 5701 | -0.5224 | -0.32287 | -0.5529 | -0.58563 | -0.20571 | -0.2722 | -0.0080827 | -0.4683 | -0.36258 | -0.18128
| 5702 | 0.10139 | -0.56422 | 0.30653 | 0.095401 | -0.66489 | -0.05496 | -0.017707 | 0.41648 | -0.09154 | -0.21
| 5703 | 0.45109 | -0.1868 | -0.10944 | -0.098501 | 0.14578 | 0.46512 | 0.44242 | -0.29679 | 0.17702 | 0.61829
| 5704 | -0.60949 | -0.15887 | -0.72089 | -0.35308 | 0.1277 | -0.72125 | -0.070861 | -0.76399 | 0.0085869 | 0.83297
| 5705 | 0.83237 | 0.15224 | 0.13127 | -0.18827 | 0.2958 | 0.74019 | 0.26713 | -0.54734 | -0.54956 | -0.12519
| 5706 | -0.045484 | 0.52366 | -0.1082 | 0.30986 | 0.65345 | -0.37111 | 0.60088 | -0.61128 | -0.30913 | 0.089231
| 5707 | -0.11496 | -0.053058 | -0.41682 | -0.025885 | 0.62946 | 0.64405 | 0.30279 | 0.072476 | -0.17799 | 0.049369
| 5708 | 0.4553 | 0.2508 | -0.31582 | 0.43264 | -0.17677 | -0.83599 | 0.32524 | 0.050421 | -0.10351 | 0.067208
| 5709 | 0.13855 | 0.21013 | -0.28677 | -0.1425 | -0.85613 | 0.43141 | -0.7623 | -0.72269 | 0.22598 | 0.31189
| 5710 | -0.34235 | -0.18446 | 0.59024 | -0.56194 | 0.094959 | 0.9134 | -0.348 | 0.47113 | 0.12256 | 0.39098
| 5711 | 0.08474 | 0.042138 | -0.56262 | -0.40628 | 0.13542 | -0.76357 | 0.19049 | 0.038075 | -0.30769 | -0.087805
| 5712 | 0.54294 | -0.047687 | -0.20697 | -0.13253 | 0.7005 | -0.080054 | -0.80226 | 0.42199 | -0.3087 | 0.066994
| 5713 | 0.12416 | -0.29679 | 0.60364 | 0.016791 | -0.42965 | 0.076582 | -0.34724 | -0.11552 | 0.19037 | 0.29979
| 5714 | -0.11677 | -0.3851 | -0.536 | 0.66221 | -0.21661 | -0.14941 | 0.87 | -0.40848 | 0.42598 | 0.29836
| 5715 | 0.11677 | -0.74329 | -0.14777 | -0.66668 | -0.21381 | -0.34846 | 0.20583 | 0.72523 | 0.027323 | 0.33811
| 5716 | -0.16496 | 0.28383 | -0.098612 | 0.2773 | 0.60213 | -0.53043 | 0.17435 | -0.60465 | -0.34816 | -0.18336
| 5717 | -0.53128 | 0.15982 | -0.44547 | 0.2147 | -0.17121 | 0.35062 | -0.010606 | 0.31919 | -0.55111 | 0.27799
| 5718 | -0.29708 | -0.37911 | 0.026398 | -0.050211 | 0.16113 | 0.31597 | 0.33494 | -0.13716 | -0.081577 | -0.059415
| 5719 | 0.09143 | -0.0059678 | -0.63027 | -0.16928 | -0.41204 | -0.26631 | 0.88042 | 0.23482 | -0.32302 | -0.34281
| 5720 | 0.034029 | -0.61387 | -0.36905 | 0.016486 | -0.22948 | -0.22495 | 0.16352 | 0.6833 | -0.15685 | -0.55762
| 5721 | -0.54514 | 0.31174 | -0.16952 | -0.47 | 0.94615 | -0.42877 | 0.093744 | 0.20269 | 0.2052 | 0.20458
| 5722 | 0.29964 | -0.39709 | 0.4683 | 0.0083852 | -0.66879 | 0.17629 | 0.62277 | 0.053586 | -0.88731 | -0.057291
| 5723 | 0.026398 | -0.14589 | 0.029691 | -0.058884 | 0.11496 | -0.61777 | 0.54646 | -0.32851 | -0.13878 | -0.34068
| 5724 | 0.30265 | -0.70725 | -0.62437 | 0.12496 | -0.43493 | -0.22302 | -0.55514 | 0.2234 | 0.57727 | -0.21038
| 5725 | -0.12931 | -0.36889 | 0.22032 | 0.24389 | 0.89091 | 0.26142 | 0.20495 | 0.35883 | -0.73751 | -0.55067
| 5726 | -0.086819 | 0.14882 | 0.14918 | 0.47284 | -0.46661 | -0.1646 | -0.14472 | -0.65722 | 0.13692 | 0.27495
| 5727 | 0.68743 | 0.42268 | 0.34099 | -0.65518 | -0.54251 | -0.54712 | -0.48435 | 0.20395 | 0.25133 | -0.43991
| 5728 | 0.15224 | 0.52873 | -0.052424 | 0.29127 | -0.088024 | 0.23796 | -0.33962 | -0.38853 | -0.36337 | -0.11157
| 5729 | 0.23954 | -0.040886 | -0.55 | 0.0911 | -0.37526 | 0.43777 | 0.063464 | 0.49059 | 0.024859 | 0.083649
| 5730 | 0.025885 | -0.26047 | -0.63108 | 0.37254 | 0.17338 | -0.12427 | -0.26658 | 0.59565 | 0.52979 | 0.31714
| 5731 | -0.43973 | -0.2755 | -0.1628 | 0.27192 | -0.48376 | 0.81 | 0.37048 | -0.6634 | 0.09011 | 0.19421
| 5732 | -0.67335 | 0.11813 | 0.073124 | 0.3551 | -0.093634 | -0.10652 | -0.51637 | 0.18177 | -0.79433 | 0.047582
| 5733 | -0.77572 | -0.086709 | 0.099389 | 0.16089 | -0.043287 | 0.82766 | 0.67061 | 0.40645 | 0.0065716 | 0.084413
| 5734 | -0.42982 | 0.29679 | 0.0036567 | 0.10429 | -0.046218 | -0.38202 | 0.52366 | -0.18692 | -0.46774 | 0.22676
| 5735 | 0.3312 | 0.40645 | 0.0040582 | 0.61961 | -0.84605 | -0.54956 | 0.25966 | 0.57822 | -0.43352 | -0.15188
| 5736 | 0.23875 | -0.12142 | -0.44837 | 0.096617 | 0.28313 | 0.40966 | 0.23052 | -0.16519 | -0.44855 | 0.91574
| 5737 | -0.35789 | 0.14965 | -0.53235 | 0.18324 | -0.34662 | 0.081686 | 0.34678 | -0.76569 | -0.083321 | -0.20069
| 5738 | 0.28257 | -0.96394 | -0.10351 | -0.00055015 | 0.0057666 | -0.32081 | 0.087038 | -0.58179 | 0.13866 | -0.10529
| 5739 | -0.43352 | -0.80379 | 0.074851 | 0.11383 | -0.42459 | -0.83721 | -0.12176 | -0.099833 | 0.58805 | -5.0001e-05
| 5740 | -0.57257 | -0.17265 | -0.49552 | -0.33374 | 0.46083 | 0.49216 | -0.63737 | -0.025372 | 0.019847 | 0.012427
| 5741 | -0.33509 | -0.13808 | 0.028352 | 0.41802 | -0.37542 | -0.013238 | -0.051053 | -0.14613 | -0.44313 | 0.37767
| 5742 | -0.74841 | -0.19856 | -0.31993 | 0.098723 | -0.68456 | 0.41511 | -0.33449 | 0.46755 | 0.36541 | -0.035065
| 5743 | 0.15425 | -0.16687 | -0.095511 | 0.91 | 0.062397 | -0.10384 | -0.53924 | 0.45603 | 0.13 | -0.32199
| 5744 | 0.22896 | 0.51328 | 0.11383 | 0.26047 | 0.35556 | 0.0059678 | 0.41323 | 0.50432 | 0.12154 | 0.26577
| 5745 | 0.23286 | -0.61672 | -0.64181 | 0.24469 | 0.22767 | 0.52851 | -0.3211 | 0.21101 | -0.80125 | -0.13692
| 5746 | 0.49236 | -0.21802 | 0.5447 | -0.42164 | -0.31276 | -0.034858 | -0.71452 | -0.24747 | 0.42026 | -0.25589
| 5747 | 0.24522 | -0.30884 | 0.27 | -0.082013 | -0.92584 | 0.050842 | -0.14953 | 0.065174 | -0.83118 | 0.27165
| 5748 | 0.66549 | 0.55943 | -0.18815 | 0.040782 | -0.01182 | -0.44134 | -0.97354 | -0.39213 | -0.35185 | -0.09022
| 5749 | 0.048633 | 0.18275 | -0.60719 | -0.64014 | 0.017096 | -0.28397 | 0.19185 | -0.20458 | -0.032994 | -0.41442
| 5750 | -0.14285 | 0.5707 | -0.20709 | -0.039635 | -0.52513 | 0.30394 | -0.3618 | 0.31218 | -0.60138 | 0.26074
| 5751 | -0.22019 | 0.15401 | 0.40628 | 0.43141 | -0.35649 | 0.16161 | 0.49771 | -0.26237 | -0.89656 | 0.7735
| 5752 | -0.32051 | 0.16412 | -0.18618 | -0.061437 | 0.64518 | -0.080272 | 0.28495 | 0.26754 | -0.04381 | 0.40881
| 5753 | 0.48687 | -0.77662 | 0.81318 | -0.32096 | 0.39626 | 0.030516 | 0.02189 | 0.55402 | -0.18312 | -0.36526
| 5754 | -0.073879 | -0.022299 | 0.10406 | -0.3961 | 0.75813 | 0.024551 | -0.06165 | -0.14578 | 0.054431 | -0.66192
| 5755 | 0.53535 | -0.78763 | 0.32214 | -0.20181 | -0.18655 | 0.31305 | 0.082122 | 0.14706 | -0.4564 | 0.47569
| 5756 | -0.64349 | -0.3477 | 0.21177 | 0.78344 | -0.47094 | 0.4531 | -0.15413 | -0.33179 | 0.46605 | 0.85823
| 5757 | 0.38137 | -0.2621 | 0.60415 | 0.085287 | -0.27799 | 0.22418 | -0.7512 | 0.88554 | -0.11248 | -0.46812
| 5758 | -0.29099 | 0.82536 | 0.010707 | -0.67 | 0.51287 | 0.27757 | -0.087476 | 0.81372 | 0.28467 | -0.4258
| 5759 | -0.21292 | 0.18643 | -0.32896 | -0.43053 | -0.4898 | 0.12097 | -0.14297 | -0.24178 | -0.62463 | -0.30365
| 5760 | -0.80739 | 0.032271 | 0.39148 | 0.20899 | 0.40881 | -0.014556 | 0.29395 | -0.17399 | 0.8747 | 0.31218
| 5761 | 0.18018 | 0.14017 | -0.076907 | 0.12874 | -0.27993 | 0.32955 | 0.062503 | 0.070538 | -0.049053 | 0.75526
| 5762 | 0.54492 | -0.2377 | -0.28313 | 0.24151 | 0.43724 | 0.011011 | 0.40662 | -0.033615 | -0.41306 | 0.51123
| 5763 | -0.13138 | 0.32747 | 0.548 | 0.24641 | -0.4279 | -0.39875 | -0.60592 | -0.42982 | 0.83477 | 0.35649
| 5764 | -0.00015001 | 0.056655 | 0.37992 | 0.40376 | -0.95641 | 0.34372 | -0.1752 | -0.39626 | 0.25321 | 0.048527
| 5765 | 0.041199 | -0.45219 | 0.17872 | -0.015368 | 0.12507 | 0.10306 | -0.7015 | 0.27357 | 0.076149 | 0.77483
| 5766 | 0.35169 | 0.18901 | 0.28873 | -0.079728 | -0.54098 | -0.19732 | 0.31145 | 0.2133 | 0.29085 | -0.29694
| 5767 | -0.66399 | -0.043705 | -0.89276 | 0.27426 | -0.13797 | 0.18532 | -0.31714 | -0.22173 | 0.35092 | 0.33179
| 5768 | -0.28355 | -0.20558 | 0.012022 | 0.0028541 | -0.30928 | -0.59049 | -0.09077 | -0.22225 | -0.61725 | 0.46587
| 5769 | -0.4046 | -0.099278 | 0.052846 | -0.6241 | 0.17411 | 0.38967 | 0.041512 | -0.46139 | 0.40309 | -0.83297
| 5770 | -0.72523 | 0.19136 | 0.19223 | 0.19844 | -0.02722 | -0.55402 | 0.059628 | -0.097282 | 0.029691 | 0.35463
| 5771 | -0.58976 | -0.17012 | -0.27827 | -0.49631 | -0.68016 | -0.6637 | 0.31538 | -0.062397 | 0.25858 | 0.82252
| 5772 | -0.14894 | 0.29452 | -0.24086 | -0.51534 | 0.25629 | -0.5019 | 0.57751 | 0.064746 | 0.068281 | 0.38089
| 5773 | -0.25027 | -0.7881 | 0.11236 | -0.2689 | -0.3419 | -0.038907 | -0.21076 | -0.24191 | -0.49413 | 0.84476
| 5774 | -0.10128 | 0.57798 | 0.28649 | 0.56194 | 0.13196 | 0.58371 | 0.1277 | 0.47531 | -0.25683 | 0.35961
| 5775 | 0.14648 | 0.01 | -0.65057 | -0.21687 | 0.28397 | 0.26836 | -0.37831 | -0.71663 | 0.24297 | 0.013035
| 5776 | -0.27261 | -0.22263 | -0.67581 | -0.29807 | 0.24178 | -0.42737 | -0.065602 | 0.41 | -0.59392 | -0.17677
| 5777 | 0.41802 | -0.31816 | -0.55672 | -0.37318 | 0.31 | 0.56354 | 0.097725 | -0.3116 | 0.20244 | -0.49751
| 5778 | 0.23613 | 0.22173 | 0.085396 | -0.0911 | 0.4801 | 0.1072 | -0.32037 | 0.56308 | -0.42563 | 0.10966
| 5779 | -0.1044 | 0.64715 | -0.23143 | -0.075716 | -0.1044 | 0.24086 | 0.34938 | 0.067745 | 0.10496 | -0.61387
| 5780 | -0.67953 | -0.36164 | -0.1425 | 0.46643 | 0.43352 | 0.13727 | -0.1034 | -0.85269 | 0.23967 | -0.7005
| 5781 | -0.19657 | -0.55022 | 0.10731 | 0.50291 | -0.3568 | 0.43193 | 0.47856 | 0.21942 | 0.02794 | -0.56768
| 5782 | -0.20282 | -0.44873 | 0.42112 | -0.5009 | -0.053903 | 0.57093 | 0.059947 | 0.17423 | -0.5011 | -0.77977
| 5783 | 0.30667 | -0.22482 | -0.12576 | 0.43158 | 0.33254 | -0.02322 | 0.22315 | -0.72963 | 0.12908 | -0.77
| 5784 | 0.36431 | 0.48902 | 0.14496 | -0.25737 | 0.15935 | 0.44206 | 0.30595 | -0.035065 | 0.60846 | -0.079294
| 5785 | 0.2042 | -0.009899 | 0.21968 | 0.19322 | -0.22598 | 0.43991 | 0.22521 | 0.42965 | 0.54033 | -0.034133
| 5786 | 0.37944 | -0.12416 | -0.15614 | 0.59098 | 0.31846 | -0.36211 | -0.26481 | -0.51 | -0.23065 | -0.57988
| 5787 | 0.32925 | 0.076258 | 0.33075 | -0.054008 | -0.16256 | 0.0076795 | 0.14192 | -0.0017515 | -0.2402 | 0.27605
| 5788 | -0.062077 | 0.009596 | -0.61777 | -0.60744 | 0.29907 | 0.19086 | 0.36526 | -0.47341 | -0.098169 | -0.5102
| 5789 | -0.21152 | -0.11564 | 0.44728 | -0.56445 | 0.48902 | 0.23888 | 0.43193 | -0.30509 | 0.22456 | -0.056549
| 5790 | -0.066244 | -0.59888 | 0.1382 | 0.43352 | -0.14718 | 0.79482 | -0.65086 | -0.013643 | 0.21968 | 0.76357
| 5791 | 0.34205 | 0.58636 | -0.22238 | 0.81159 | 0.45917 | 0.32184 | 0.2809 | -0.6241 | 0.6755 | -0.48125
| 5792 | 0.64857 | -0.66429 | 0.1957 | 0.076041 | -0.20332 | -0.25616 | -0.65143 | -0.56125 | 0.36873 | 0.2948
| 5793 | 0.25214 | -0.86546 | 0.20558 | -0.34144 | 0.74682 | 0.46549 | 0.85613 | 0.40075 | -0.029485 | -0.3961
| 5794 | 0.029382 | 0.48746 | -0.0050628 | -0.15709 | 0.46962 | 0.44891 | -0.17872 | -0.10832 | 0.35914 | -0.0043595
| 5795 | -0.76612 | 0.6077 | -0.10317 | -0.097503 | 0.27619 | -0.3363 | 0.50291 | 0.27398 | -0.32361 | 0.18581
| 5796 | 0.63572 | -0.34235 | 0.45714 | 0.47227 | -0.48029 | -0.08234 | 0.20156 | -0.14695 | -0.27965 | -0.54229
| 5797 | -0.43 | -0.46755 | -0.25347 | -0.37 | 0.38673 | -0.32702 | 0.088353 | 0.12541 | 0.032788 | -0.30624
| 5798 | -0.060266 | -0.452 | 0.62384 | -0.031961 | 0.84412 | 0.32806 | 0.0082843 | -0.62277 | -0.038595 | 0.076474
| 5799 | -0.011516 | -0.2816 | 0.087586 | -0.13046 | 0.0038574 | -0.21866 | -0.60088 | 0.14578 | -0.34985 | 0.7816
| 5800 | -0.87233 | 0.61725 | 0.072476 | -0.067959 | 0.22212 | -0.39033 | 0.069463 | -0.44349 | 0.10854 | -0.1015
| 5801 | -0.22302 | 0.26386 | 0.11202 | 0.23325 | -0.17483 | -0.1752 | 0.58419 | -0.011516 | 0.38283 | -0.44873
| 5802 | 0.041929 | -0.35077 | 0.25845 | -0.13692 | -0.058459 | 0.536 | -0.70862 | -0.11417 | -0.47531 | 0.69884
| 5803 | 0.24442 | 0.16627 | -0.20156 | 0.22032 | 0.30928 | 0.040677 | 0.1603 | -0.65172 | 0.048317 | 0.40729
| 5804 | 0.13577 | -0.78297 | 0.52408 | -0.32985 | 0.47113 | -0.66789 | -0.01486 | -0.7508 | 0.051369 | 0.46718
| 5805 | -0.14965 | 0.20156 | -0.58684 | 0.33811 | 0.36652 | 0.71946 | 0.57303 | -0.13484 | 0.46325 | -0.45073
| 5806 | 0.29367 | 0.39197 | -0.78251 | 0.17435 | 0.046952 | 0.12267 | 0.14882 | 0.13704 | -0.014252 | -0.49651
| 5807 | -0.2234 | 0.59963 | -0.20319 | -0.57538 | 0.3116 | -0.42268 | 0.32494 | -0.61335 | -0.2398 | 0.78669
| 5808 | 0.09198 | 0.45347 | -0.16964 | -0.29169 | 0.64489 | -0.24363 | 0.13403 | 0.27261 | 0.12404 | -0.76655
| 5809 | 0.55537 | 0.027323 | -0.13496 | 0.13334 | -0.16436 | 0.11518 | -0.61542 | -0.29822 | -0.44565 | 0.45237
| 5810 | 0.81752 | 0.094406 | -0.49572 | 0.48804 | -0.47914 | -0.46456 | -0.25401 | -0.19844 | -0.84476 | -0.073231
| 5811 | 0.80481 | 0.29424 | -0.021583 | 0.20886 | 0.58903 | 0.17265 | -0.51123 | -0.00085036 | -0.045275 | 0.67182
| 5812 | 0.074635 | -0.1729 | -0.74603 | 0.12633 | 0.11225 | -0.36794 | 0.19919 | 0.61751 | 0.17048 | 0.24853
| 5813 | 0.75241 | 0.17399 | 0.36952 | 0.15377 | 0.052108 | -0.5922 | 0.2047 | 0.24548 | -0.15035 | 0.21393
| 5814 | -0.69194 | 0.29268 | 0.85201 | -0.53192 | 0.048738 | 0.11417 | 0.51451 | -0.45769 | -0.18201 | -0.75648
| 5815 | -0.015165 | -0.11304 | -0.20533 | -0.13392 | -0.093192 | -0.56722 | 0.57468 | -0.09706 | -0.60339 | 0.80379
| 5816 | 0.31714 | 0.13369 | 0.16699 | -0.50756 | -0.24138 | 0.67243 | 0.18926 | 0.13669 | -0.58951 | 0.007478
| 5817 | -0.29907 | -0.068818 | 0.46381 | 0.039011 | -0.33811 | 0.54251 | -0.14976 | 0.60465 | -0.54712 | -0.1797
| 5818 | 0.19533 | -0.20219 | -0.34632 | 0.23404 | 0.29282 | -0.16232 | -0.22586 | 0.22987 | -0.0038574 | -0.71663
| 5819 | -0.25227 | 0.021072 | 0.39131 | 0.69983 | 0.34601 | -0.042764 | 0.14988 | 0.076582 | 0.24349 | -0.25723
| 5820 | 0.66728 | -0.12347 | 0.02189 | -0.49 | -0.76442 | -0.51782 | -0.39692 | -0.49315 | -0.011617 | -0.20194
| 5821 | 0.09187 | 0.36415 | -0.73524 | -0.021583 | 0.38771 | -0.21699 | 0.29113 | -0.2431 | 0.81159 | 0.23417
| 5822 | -0.082122 | -0.85134 | -0.51699 | -0.55717 | -0.13473 | 0.0065716 | 0.48668 | -0.082558 | 0.40142 | -0.34235
| 5823 | 0.17121 | -0.57538 | 0.30293 | -0.024346 | 0.68488 | -0.22844 | -0.55447 | -0.89753 | 0.17338 | -0.29807
| 5824 | -0.0089904 | -0.23469 | -0.18165 | 0.22508 | 0.029897 | 0.072476 | -0.0038574 | 0.18667 | -0.067101 | -0.52597
| 5825 | 0.12074 | -0.43176 | -0.6995 | -0.28021 | -0.548 | 0.69455 | 0.063891 | 0.4206 | 0.10955 | 0.16819
| 5826 | 0.15354 | -0.21419 | 0.28285 | 0.17253 | 0.55604 | 0.052319 | 0.3727 | -0.39181 | 0.33075 | 0.59639
| 5827 | 0.013643 | -0.39842 | 0.41068 | 0.42912 | 0.046742 | -0.67829 | 0.82084 | 0.16484 | -0.075933 | 0.36952
| 5828 | -0.16185 | 0.11892 | -0.81265 | 0.11972 | 0.38202 | -0.35154 | -0.48067 | -0.77439 | 0.32539 | 0.12713
| 5829 | 0.3593 | -0.082776 | -0.43053 | -0.53772 | -0.71592 | -0.1082 | -0.7492 | 0.19869 | 0.33585 | 0.43973
| 5830 | 0.020561 | 0.040677 | 0.61699 | 0.51595 | 0.0013509 | 0.11169 | -0.37558 | 0.092421 | 0.031238 | 0.67274
| 5831 | -0.32598 | 0.074851 | -0.10485 | -0.44565 | -0.26305 | -0.34205 | 0.45714 | 0.40983 | -0.73298 | 0.31728
| 5832 | 0.59515 | 0.16388 | -0.14753 | -0.72161 | 0.34023 | 0.9272 | -0.13046 | 0.20508 | -0.39181 | -0.11598
| 5833 | 0.14134 | -0.5347 | -0.017809 | -0.20634 | 0.46943 | -0.66044 | 0.14309 | 0.41119 | 0.76021 | 0.42755
| 5834 | 0.69553 | -0.61725 | 0.4408 | 0.38202 | -0.047057 | 0.2733 | 0.62946 | 0.17544 | -0.59269 | -0.44909
| 5835 | 0.73149 | -0.36415 | 0.22083 | -0.84284 | 0.40932 | 0.17374 | -0.89464 | -0.54426 | -0.65985 | -0.077016
| 5836 | -0.0023528 | -0.072692 | -0.49275 | 0.5768 | 0.39825 | 0.2711 | 0.084194 | 0.35231 | -0.70487 | 0.4194
| 5837 | -0.034133 | -0.68552 | -0.18446 | 0.17653 | -0.7184 | 0.35883 | -0.14742 | 0.33735 | 0.0015512 | 0.29694
| 5838 | 0.56653 | -0.46232 | 0.78297 | 0.059415 | -0.73637 | 0.2508 | 0.064853 | 0.30696 | 0.28719 | 0.28803
| 5839 | 0.45769 | 0.61103 | -0.33075 | 0.8366 | 0.077666 | -0.59639 | -0.009596 | -0.14683 | 0.46887 | 0.45991
| 5840 | -0.26563 | -0.75607 | -0.59269 | -0.18079 | 0.23796 | 0.15768 | -0.37016 | 0.48922 | -0.80532 | 0.014353
| 5841 | 0.10473 | -0.28313 | 0.2823 | 0.51225 | 0.028249 | -0.46344 | 0.30826 | -0.54778 | -0.26973 | 0.29367
| 5842 | -0.092531 | 0.43955 | -0.39181 | -0.023117 | 0.38218 | 0.4981 | -0.25912 | 0.19582 | -0.7429 | 0.53171
| 5843 | -0.41051 | -0.10161 | -0.047477 | 0.12085 | 0.59196 | 0.14824 | 0.094959 | -0.24442 | -0.47684 | -0.36494
| 5844 | -0.054431 | 0.009798 | -0.28202 | 0.89464 | 0.3242 | -0.35169 | -0.013238 | 0.84605 | -0.65576 | 0.75813
| 5845 | 0.33886 | -0.56606 | -0.2995 | 0.14227 | -0.40477 | 0.67335 | -0.64943 | -0.70386 | 0.028558 | 0.28986
| 5846 | -0.23757 | -0.075392 | 0.57869 | 0.6044 | -0.59024 | -0.07 | 0.37223 | 0.18766 | 0.59171 | 0.52198
| 5847 | -0.021481 | -0.043182 | 0.64433 | 0.072692 | -0.51534 | -0.095954 | -0.072369 | -0.0087886 | 0.47607 | -0.12006
| 5848 | 0.039531 | -0.42129 | -0.69097 | 0.26932 | -0.564 | 0.0072765 | -0.44909 | -0.33209 | 0.21063 | 0.54338
| 5849 | 0.42095 | 0.22728 | 0.28174 | 0.17096 | 0.26522 | -0.3767 | -0.34739 | -0.53406 | -0.80176 | -0.15567
| 5850 | -0.031238 | 0.16018 | 0.46269 | 0.20257 | 0.13716 | -0.0063703 | 0.63435 | -0.43035 | -0.48882 | -0.39362
| 5851 | 0.097171 | 0.69619 | 0.089451 | -0.21089 | -0.48318 | -0.11304 | -0.70083 | 0.20886 | -0.82028 | 0.16856
| 5852 | -0.50452 | -0.29864 | -0.30797 | -0.43299 | -0.2516 | 0.33 | 0.19981 | 0.12553 | 0.364 | -0.76315
| 5853 | 0.74019 | -0.5201 | 0.72486 | 0.38073 | 0.23364 | 0.4859 | 0.10306 | 0.21228 | 0.50351 | -0.063891
| 5854 | -0.65373 | -0.38738 | -0.1688 | -0.24853 | 0.28327 | -0.45146 | 0.0053644 | -0.23652 | 0.83907 | -0.038595
| 5855 | 0.11022 | -0.31524 | -0.3568 | -0.44674 | 0.4993 | 0.21584 | 0.18385 | 0.31451 | 0.034547 | -0.29424
| 5856 | 0.94255 | -0.049263 | -0.33645 | -0.019439 | 0.10899 | 0.24231 | 0.070538 | 0.0022525 | 0.021583 | 0.19346
| 5857 | 0.52513 | 0.17629 | 0.14017 | -0.65576 | 0.60263 | -0.96683 | 0.28916 | -0.34235 | -0.84801 | 0.010505
| 5858 | -0.25093 | 0.45548 | -0.27965 | -0.061118 | 0.21101 | 0.53513 | 0.19235 | -0.34908 | 0.40595 | -0.15685
| 5859 | -0.34038 | 0.56057 | 0.12759 | 0.12713 | 0.77617 | 0.14402 | -0.82028 | 0.21127 | 0.080272 | -0.22019
| 5860 | 0.1196 | 0.69194 | -0.36086 | -0.44945 | -0.1863 | 0.38559 | 0.44945 | -0.021992 | 0.68552 | -0.12725
| 5861 | -0.39692 | -0.11824 | 0.56907 | 0.59466 | 0.14929 | -0.25174 | -0.37751 | 0.056761 | -0.48843 | 0.84801
| 5862 | -0.21127 | -0.16819 | -0.1752 | -0.093192 | -0.10899 | -0.17265 | -0.38137 | -0.046638 | 0.32258 | -0.30279
| 5863 | 0.087147 | -0.23574 | -0.063571 | 0.43831 | 0.058034 | 0.5768 | -0.093854 | -0.63326 | -0.38885 | -0.30308
| 5864 | -0.27813 | 0.17012 | -0.68775 | 0.32628 | -0.43955 | -0.28313 | -0.3309 | -0.35774 | -0.15531 | 0.94432
| 5865 | -0.65172 | -0.27688 | -0.1432 | -0.022299 | -0.022094 | 0.51328 | 0.79336 | -0.42947 | -0.49771 | 0.42424
| 5866 | 0.13878 | -0.34586 | -0.064532 | 0.37191 | 0.24429 | 0.16066 | -0.44116 | -0.28705 | -0.17763 | 0.73904
| 5867 | 0.84031 | 0.79433 | -0.13762 | -0.36102 | -0.23013 | 0.025474 | -0.36557 | 0.44045 | 0.3297 | 0.11022
| 5868 | 0.57585 | 0.0080827 | 0.23052 | -0.40881 | -0.8739 | -0.25791 | 0.29964 | 0.44134 | 0.058034 | -0.148
| 5869 | -0.09154 | -0.42026 | 0.25764 | -0.33992 | 0.19607 | -0.052846 | -0.73827 | -0.23862 | -0.75526 | -0.67335
| 5870 | 0.075933 | -0.15 | -0.032374 | 0.45935 | -0.39378 | 0.060053 | -0.61128 | -0.12416 | -0.52492 | -0.4898
| 5871 | -0.56514 | 0.1338 | -0.0019519 | 0.25281 | 0.061757 | 0.30351 | -0.054643 | 0.72669 | -0.2488 | -0.51164
| 5872 | 0.18422 | 0.70117 | -0.011921 | -0.39131 | -0.4232 | 0.48746 | 0.29212 | 0.10563 | 0.25899 | 0.26563
| 5873 | 0.11439 | 0.73524 | 0.36149 | -0.63572 | 0.24323 | -0.41871 | -0.39213 | 0.44601 | -0.77751 | 0.057079
| 5874 | -0.11915 | 0.21254 | 0.70318 | 0.20169 | 0.2037 | -0.071291 | -0.09706 | 0.34464 | 0.77262 | 0.3309
| 5875 | 0.25683 | -0.015774 | 0.30279 | -0.036413 | -0.67396 | 0.39378 | 0.20899 | 0.11835 | -0.64943 | 0.068711
| 5876 | -0.55694 | -0.031754 | 0.36683 | 0.48882 | 0.2575 | -0.58371 | -0.32851 | 0.23731 | 0.51472 | 0.081251
| 5877 | -0.28621 | 0.019541 | -0.31014 | -0.041199 | 0.042138 | 0.32524 | 0.53924 | 0.14566 | -0.51595 | -0.75731
| 5878 | -0.06957 | -0.60898 | -0.49413 | 0.43088 | -0.20056 | -0.3477 | 0.7184 | -0.22909 | -0.22883 | -0.17471
| 5879 | -0.22212 | 0.085068 | -0.14788 | 0.2476 | 0.28341 | -0.5583 | 0.32717 | 0.07962 | -0.19384 | 0.42912
| 5880 | -0.60643 | -0.18803 | 0.088353 | 0.45018 | -0.36305 | 0.88554 | -0.41289 | -0.0041586 | 0.075825 | -0.45347
| 5881 | -0.22058 | 0.032581 | -0.011415 | 0.43387 | 0.31378 | -0.10933 | -0.20106 | 0.72161 | -0.097614 | -0.3148
| 5882 | 0.35556 | 0.31538 | -0.66221 | -0.2343 | -0.48648 | 0.348 | -0.11722 | -0.23901 | 0.39279 | 0.14414
| 5883 | 0.3961 | 0.003456 | -0.44855 | -0.10429 | 0.085068 | 0.22148 | -0.065923 | 0.11575 | -0.33105 | 0.41238
| 5884 | 0.23417 | 0.50231 | -0.3796 | 0.30841 | -0.034754 | 0.039635 | -0.66608 | 0.1109 | -0.34357 | 0.74174
| 5885 | -0.564 | -0.087805 | 0.32287 | 0.83059 | 0.065388 | 0.18299 | -0.19744 | 0.020868 | -0.48435 | 0.03
| 5886 | -0.046113 | 0.068603 | 0.39345 | 0.59913 | 0.76827 | -0.1229 | 0.82593 | 0.24138 | -0.14367 | -0.31816
| 5887 | 0.28649 | 0.12359 | -0.18483 | -0.4392 | -0.30509 | -0.44945 | -0.22883 | -0.53859 | 0.39049 | 0.16916
| 5888 | -0.54316 | -0.32791 | 0.09176 | 0.19049 | 0.164 | -0.097947 | -0.77932 | 0.0077803 | 0.029588 | -0.37302
| 5889 | 0.49118 | 0.61961 | -0.33149 | -0.43529 | -0.25926 | 0.19769 | 0.65086 | 0.19309 | -0.36826 | -0.56884
| 5890 | -0.45493 | 0.77751 | -0.41306 | -0.051475 | -0.32687 | -0.20357 | -0.27481 | 0.82766 | 0.69 | -0.84801
| 5891 | -0.5469 | 0.23273 | 0.3951 | -0.14835 | -0.033512 | -0.23757 | 0.079511 | -0.55762 | 0.9245 | 0.19297
| 5892 | -0.39875 | -0.59441 | -0.095069 | 0.39082 | -0.029897 | 0.61934 | 0.1005 | -0.36117 | 0.24323 | -0.28257
| 5893 | 0.27868 | 0.40595 | 0.1418 | -0.25482 | 0.28649 | 0.77707 | 0.0052639 | -0.70931 | -0.037763 | -0.18704
| 5894 | -0.019133 | -0.18643 | -0.025064 | -0.089231 | 0.21317 | -0.056125 | -0.13438 | 0.069463 | -0.52957 | 0.26645
| 5895 | 0.22353 | 0.55762 | 0.73037 | 0.025782 | -0.16675 | -0.52873 | -0.11564 | 0.37574 | -0.3804 | -0.041512
| 5896 | -0.64405 | -0.81265 | -0.10933 | -0.12633 | 0.015063 | -0.38902 | -0.11994 | 0.21687 | 0.36652 | -0.038075
| 5897 | 0.19645 | 0.17024 | -0.19669 | 0.05 | 0.013542 | -0.14976 | -0.29268 | -0.061544 | -0.037555 | 0.1269
| 5898 | -0.21776 | 0.059096 | 0.10028 | 0.22586 | 0.47894 | -0.054431 | 0.029794 | -0.14601 | 0.75896 | 0.84867
| 5899 | -0.066887 | -0.248 | 0.33389 | -0.42755 | -0.028146 | 0.2809 | 0.12541 | 0.21699 | 0.43546 | -0.55514
| 5900 | -0.37223 | 0.08978 | -0.6233 | -0.23888 | -0.30064 | 0.58976 | 0.536 | 0.37638 | 0.49216 | -0.36699
| 5901 | -0.19433 | -0.28397 | -0.19757 | 0.18569 | 0.26183 | 0.62463 | 0.05158 | -0.11022 | 0.17896 | 0.15118
| 5902 | 0.027323 | -0.59813 | 0.52788 | -0.80739 | -0.059947 | 0.3451 | 0.12931 | -0.099167 | -0.57186 | -0.37494
| 5903 | -0.84867 | 0.079728 | -0.19223 | -0.3864 | 0.12108 | 0.32672 | -0.47818 | 0.4755 | 0.17145 | -0.58299
| 5904 | 0.60138 | 0.007075 | 0.64886 | 0.069463 | 0.61594 | 0.032581 | 0.23364 | -0.13866 | 0.28958 | -0.74682
| 5905 | -0.061757 | 0.24548 | -0.019541 | 0.37622 | 0.14157 | 0.84736 | 0.21406 | 0.63353 | -0.56606 | 0.088682
| 5906 | 0.13011 | -0.64349 | -0.5866 | 0.22135 | -0.012022 | -0.75731 | -0.36337 | -0.24548 | -0.45127 | 0.22728
| 5907 | -0.39428 | -0.54185 | 0.3372 | 0.037659 | 0.13046 | 0.39362 | 0.47875 | 0.29424 | 0.12085 | -0.4426
| 5908 | -0.0027538 | -0.18926 | 0.24257 | 0.069355 | -0.75282 | -0.23652 | 0.31802 | 0.22767 | 0.40628 | -0.1127
| 5909 | 0.42285 | -0.4392 | -0.5015 | -0.23757 | 0.14788 | 0.76442 | -0.11779 | -0.087038 | 0.10552 | 0.41905
| 5910 | 0.077449 | 0.55424 | 0.2602 | 0.3129 | 0.46139 | 0.12233 | -0.10888 | 0.53149 | -0.15733 | 0.080489
| 5911 | -0.61335 | -0.19124 | 0.10541 | -0.29651 | -0.60567 | -0.18092 | 0.48746 | 0.19994 | -0.035168 | 0.67891
| 5912 | -0.13415 | 0.37734 | -0.87958 | -0.10206 | -0.64153 | -0.3759 | 0.43123 | 0.049369 | 0.11112 | -0.57
| 5913 | -0.8956 | 0.20407 | -0.1957 | -0.34494 | -0.15756 | 0.15342 | 0.18165 | -0.58515 | 0.36008 | -0.1118
| 5914 | -0.40746 | 0.72559 | -0.78905 | -0.93917 | -0.23849 | -0.76272 | -0.4206 | -0.041616 | 0.26468 | 0.27979
| 5915 | -0.14449 | 0.096728 | -0.24827 | -0.48125 | -0.50776 | 0.3245 | 0.82824 | -0.11056 | -0.83177 | -0.46288
| 5916 | -0.011921 | -0.33645 | 0.55492 | -0.074419 | -0.57774 | -0.13288 | -0.29793 | 0.097725 | -0.092972 | -0.39726
| 5917 | -0.49453 | 0.21725 | -0.014454 | 0.4588 | 0.66489 | -0.41854 | -0.42685 | 0.56791 | -0.37286 | 0.34985
| 5918 | -0.62704 | -0.39759 | 0.44367 | -0.12404 | -0.017605 | 0.45347 | -0.037555 | -0.2287 | -0.38461 | -0.41974
| 5919 | 0.71911 | -0.82365 | 0.38315 | -0.17629 | -0.076041 | 0.86472 | 0.43582 | -0.59863 | 0.1466 | -0.12484
| 5920 | -0.055595 | 0.21904 | 0.016588 | 0.63244 | -0.3951 | -0.48843 | -0.053903 | 0.13369 | -0.042138 | 0.45861
| 5921 | 0.17217 | 0.80635 | 0.21572 | -0.12759 | -0.12313 | 0.043705 | 0.28873 | 0.3129 | 0.20634 | -0.67091
| 5922 | 0.18165 | 0.24059 | 0.23574 | -0.38251 | -0.40376 | -0.32258 | 0.91225 | -0.31553 | -0.63572 | 0.047057
| 5923 | -0.17811 | 0.063677 | -0.10832 | -0.083758 | -0.2744 | -0.35015 | 0.1694 | 0.24469 | -0.45383 | 0.42563
| 5924 | -0.10328 | -0.11349 | 0.54382 | 0.64772 | 0.66015 | -0.52534 | -0.51472 | 0.22883 | 0.047372 | -0.71347
| 5925 | -0.37064 | 0.87155 | -0.17763 | -0.012123 | -0.0048618 | -0.57093 | -0.95641 | 0.1204 | 0.44457 | 0.13138
| 5926 | 0.52619 | 0.15188 | -0.58539 | -0.78436 | -0.70184 | 0.0088895 | -0.48785 | -0.058246 | 0.37111 | -0.080489
| 5927 | -0.061544 | 0.11824 | 0.28635 | 0.69917 | 0.36857 | 0.0069743 | 0.032994 | 0.072153 | 0.44313 | 0.13716
| 5928 | -0.48106 | 0.015571 | 0.079837 | -0.26101 | -0.35339 | -0.031857 | -0.18557 | -0.40326 | -0.049789 | 0.4776
| 5929 | 0.53 | 0.093413 | -0.11281 | -0.34632 | 0.20269 | -0.6852 | -0.059096 | 0.12564 | -0.28817 | 0.75938
| 5930 | 0.13692 | -0.35696 | 0.14578 | 0.1868 | 0.0044599 | -0.037451 | 0.45603 | -0.45548 | -0.11225 | -0.85893
| 5931 | -0.65956 | 0.31305 | -0.49651 | 0.47379 | -0.63435 | 0.91112 | 0.98268 | -0.12188 | -0.40595 | 0.18312
| 5932 | -0.010101 | 0.28677 | 0.55762 | 0.2571 | -0.33509 | 0.23691 | 0.39543 | -0.6249 | 0.39942 | -0.070645
| 5933 | -0.3186 | -0.13438 | -0.29014 | -0.5728 | -0.76569 | -0.021481 | -0.26441 | -0.086053 | -0.067423 | 0.23626
| 5934 | -0.048002 | -0.28972 | -0.14519 | -0.14309 | 0.078751 | 0.77662 | -0.11518 | 0.10306 | -0.54978 | -0.19025
| 5935 | -0.12222 | 0.15899 | -0.43529 | 0.32613 | 0.13936 | -0.0081835 | -0.38706 | 0.81265 | -0.84031 | 0.4531
| 5936 | 0.23718 | -0.352 | -0.052319 | -0.18055 | -0.46718 | 0.11598 | 0.18594 | -0.39246 | 0.10083 | 0.26617
| 5937 | 0.11394 | -0.53235 | 0.63792 | -0.29395 | -0.64971 | 0.40746 | -0.24747 | 0.21994 | -0.83357 | -0.64293
| 5938 | -0.16292 | 0.548 | -0.80635 | 0.020868 | 0.12313 | 0.26115 | -0.74174 | 0.11892 | 0.25508 | -0.46195
| 5939 | 0.16807 | 0.11394 | -0.53578 | 0.30928 | -0.13184 | 0.0052639 | 0.22935 | 0.21457 | 0.21661 | 0.35386
| 5940 | 0.35789 | -0.11045 | -0.09099 | -0.12267 | 0.39792 | 0.019541 | 0.17084 | 0.18901 | -0.58854 | 0.30682
| 5941 | 0.5735 | -0.51802 | 0.7512 | 0.021174 | 0.44349 | -0.00015001 | -0.099611 | 0.22831 | -0.31685 | 0.59838
| 5942 | -0.023322 | -0.024449 | 0.5529 | -0.057716 | 0.34662 | -0.52682 | -0.76272 | 0.14157 | -0.29537 | -0.21393
| 5943 | -0.50675 | 0.29822 | -0.55134 | -0.054431 | 0.26061 | -0.0041586 | -0.28677 | -0.57515 | -0.65086 | 0.0073772
| 5944 | -0.90673 | 0.22831 | 0.37895 | 0.20269 | -0.53213 | 0.58612 | 0.07962 | 0.68172 | -0.063784 | -0.23691
| 5945 | 0.85201 | -0.18606 | 0.6697 | 0.32155 | -0.050842 | 0.42493 | -0.65345 | -0.32732 | -0.54867 | -0.27522
| 5946 | 0.61725 | -0.031238 | -0.44063 | -0.59963 | 0.72054 | 0.077991 | -0.19495 | -0.52471 | 0.25683 | 0.40494
| 5947 | -0.08136 | -0.48338 | -0.35293 | 0.18815 | -0.49039 | -0.64349 | 0.30207 | -0.11112 | -0.094959 | -0.41221
| 5948 | 0.57538 | 0.10106 | -0.27578 | -0.080381 | -0.12725 | 0.39 | -0.043705 | 0.12097 | -0.14355 | 0.68936
| 5949 | -0.10384 | 0.68807 | -0.86325 | -0.3923 | -0.19408 | -0.36133 | 0.17205 | 0.44873 | -0.1957 | -0.27371
| 5950 | 0.25993 | 0.32896 | 0.08989 | 0.23065 | -0.017401 | -0.071507 | 0.78576 | -0.028352 | 0.020255 | -0.14918
| 5951 | -0.27785 | -0.58227 | 0.0080827 | -0.57822 | 0.0041586 | 0.43671 | 0.14379 | 0.030309 | -0.20571 | 0.41102
| 5952 | -0.30884 | 0.26264 | 0.025474 | -0.20495 | 0.27082 | -0.58347 | 0.34311 | -0.1261 | -0.16472 | 0.033408
| 5953 | -0.77175 | -0.15923 | 0.17884 | 0.36384 | 0.032271 | 0.0091922 | -0.79628 | 0.39892 | 0.95877 | 0.32509
| 5954 | -0.91574 | -0.049369 | 0.0052639 | 0.058777 | -0.11677 | 0.91938 | -0.67643 | -0.072584 | 0.42633 | -0.72889
| 5955 | 0.42078 | 0.081251 | 0.42164 | -0.025577 | 0.012832 | -0.27896 | 0.54185 | -0.0072765 | -0.43938 | 0.16113
| 5956 | 0.52471 | -0.59368 | -0.030412 | -0.25267 | 0.11824 | 0.21152 | 0.10843 | 0.073124 | -0.19111 | 0.49651
| 5957 | 0.031961 | -0.47531 | -0.30682 | 0.55966 | -0.48067 | -0.78344 | -0.23626 | -0.83477 | -0.072153 | 0.80584
| 5958 | 0.24376 | -0.52408 | -0.51513 | 0.39842 | 0.57047 | 0.013339 | 0.16795 | 0.45622 | 0.87311 | -0.56954
| 5959 | -0.023629 | 0.27233 | -0.21292 | 0.47076 | -0.41357 | 0.41323 | 0.11135 | 0.47322 | 0.30322 | -0.06229
| 5960 | 0.15283 | -0.06325 | -0.53729 | 0.16675 | 0.7508 | -0.23836 | 0.065602 | -0.34418 | -0.36196 | 0.4307
| 5961 | -0.43671 | -0.10261 | 0.11326 | -0.27564 | -0.58203 | 0.64489 | 0.11315 | -0.22032 | -0.70657 | -0.045589
| 5962 | 0.59888 | -0.70521 | 0.14239 | 0.46288 | 0.64209 | -0.62919 | 0.87712 | 0.22896 | 0.64293 | 0.051159
| 5963 | 0.21368 | -0.3366 | -0.0094951 | 0.39925 | -0.71 | -0.087366 | 0.13716 | -0.082122 | -0.21114 | 0.5005
| 5964 | 0.2958 | -0.21623 | -0.43991 | 0.0071757 | 0.14519 | 0.044019 | 0.39825 | 0.53043 | -0.57727 | -0.32406
| 5965 | -0.10462 | 0.26413 | 0.17253 | 0.33434 | 0.14601 | 0.085396 | -0.41374 | -0.22547 | -0.36573 | -0.58131
| 5966 | -0.81917 | 0.65373 | 0.14006 | -0.66459 | -0.57964 | 0.46213 | 0.42737 | -0.29736 | 0.60138 | -0.59714
| 5967 | 0.067852 | 0.15816 | -0.43617 | -0.81053 | -0.77044 | 0.047792 | -0.50878 | 0.27647 | -0.12644 | 0.5447
| 5968 | 0.72305 | 0.2625 | -0.76957 | 0.28761 | 0.3817 | -0.40159 | -0.060266 | -0.41323 | -0.070215 | 0.078859
| 5969 | -0.6044 | 0.39329 | 0.18901 | 0.39296 | 0.41699 | 0.56262 | 0.34846 | 0.16472 | 0.69292 | 0.3132
| 5970 | 0.6703 | 0.054749 | 0.23221 | -0.14941 | 0.1353 | -0.33015 | 0.31218 | 0.21013 | -0.14204 | 0.57303
| 5971 | -0.26332 | -0.83477 | 0.37686 | 0.452 | -0.14157 | -0.65057 | -0.50533 | -0.4991 | -0.080707 | 0.29964
| 5972 | 0.23 | -0.1072 | -0.1005 | -0.15911 | -0.05422 | -0.75485 | -0.38332 | -0.50371 | -0.76146 | -0.50939
| 5973 | -0.29155 | 0.09044 | -0.06678 | 0.52303 | 0.18877 | -0.11439 | 0.023117 | 0.93755 | -0.53664 | -0.15153
| 5974 | -0.77087 | 0.38202 | -0.14087 | 0.6149 | -0.30408 | -0.046218 | -0.049684 | -0.36164 | 0.16868 | 0.10574
| 5975 | 0.84933 | -0.51246 | 0.35062 | 0.39362 | 0.02609 | 0.0025533 | 0.029897 | -0.14648 | 0.039427 | 0.72378
| 5976 | 0.11 | 0.50291 | 0.17544 | -0.48902 | -0.39263 | -0.077666 | 0.0068736 | -0.20219 | 0.33705 | 0.022094
| 5977 | 0.39742 | 0.095401 | 0.4286 | 0.21968 | -0.33977 | 0.053691 | 0.083212 | 0.47837 | 0.014049 | -0.14449
| 5978 | 0.47455 | -0.54426 | -0.031754 | 0.75855 | -0.46009 | 0.61438 | -0.59049 | 0.024962 | 0.43035 | 0.22173
| 5979 | 0.29537 | -0.13577 | -0.58275 | -0.85752 | -0.18312 | -0.45603 | 0.23273 | 0.41034 | 0.23665 | -0.92859
| 5980 | -0.73448 | -0.25174 | -0.16364 | -0.0018517 | 0.37863 | 0.52513 | -0.61516 | 0.42026 | -0.50291 | 0.18938
| 5981 | 0.0036567 | 0.76315 | -0.11631 | -0.39395 | -0.35541 | -0.28607 | -0.0030547 | 0.51699 | 0.36321 | -0.24112
| 5982 | 0.055278 | -0.64943 | 0.1245 | 0.44583 | -0.17665 | 0.30567 | 0.42546 | -0.086819 | -0.6349 | 0.36731
| 5983 | -0.75322 | -0.48106 | 0.19931 | 0.71487 | -0.014657 | -0.092641 | -0.29722 | -0.79433 | 0.17714 | 0.31743
| 5984 | 0.61594 | 0.10664 | -0.24178 | 0.60974 | -0.64097 | -0.2755 | 0.20772 | -0.86108 | -0.009697 | 0.13334
| 5985 | -0.18189 | -0.48551 | -0.20772 | -0.17205 | 0.47607 | -0.12222 | 0.56285 | -0.3477 | -0.061118 | -0.085396
| 5986 | -0.11994 | 0.1323 | 0.12587 | -0.44529 | -0.75566 | 0.26699 | -0.17181 | 0.59963 | -0.012123 | -0.79095
| 5987 | -0.164 | -0.2492 | -0.48067 | 0.35883 | 0.61 | -0.10228 | 0.23718 | -0.80791 | 0.043601 | 0.39296
| 5988 | 0.36873 | 0.4194 | 0.1118 | 0.11157 | 0.16256 | -0.71277 | -0.75444 | -0.57917 | 0.39164 | 0.70828
| 5989 | 0.37398 | -0.065495 | -0.44385 | 0.60821 | -0.36243 | -0.40008 | -0.17495 | 0.11101 | 0.46474 | -0.077774
| 5990 | -0.72414 | 0.26373 | 0.64943 | -0.087366 | -0.35727 | -0.030412 | 0.53902 | 0.21 | 0.57893 | -0.65086
| 5991 | -0.64801 | -0.75648 | -0.32836 | 0.098058 | -0.7569 | -0.48609 | -0.015774 | -0.35015 | -0.10451 | 0.28174
| 5992 | 0.20069 | 0.073879 | -0.30783 | 0.0058672 | -0.77439 | 0.20495 | -0.34678 | -0.31116 | 0.61051 | 0.40898
| 5993 | 0.0029544 | 0.051686 | 0.15188 | 0.0025533 | 0.4826 | -0.085834 | 0.4799 | -0.43671 | 0.09176 | -0.28859
| 5994 | 0.39892 | -0.30667 | -0.27744 | 0.059521 | -0.077341 | -0.5469 | 0.5143 | 0.63054 | -0.33555 | -0.10966
| 5995 | -0.2326 | 0.47779 | -0.39892 | -0.45585 | -0.097836 | 0.29325 | 0.45 | 0.31538 | -0.69162 | 0.13496
| 5996 | 0.31189 | 0.12222 | 0.19012 | -0.15507 | -0.20445 | -0.50251 | -0.1237 | 0.31904 | -0.42737 | 0.12519
| 5997 | -0.054537 | 0.12051 | 0.046428 | -0.63326 | -0.046428 | -0.92319 | 0.41596 | 0.0054649 | -0.30653 | -0.4265
| 5998 | 0.20911 | -0.068281 | 0.42615 | 0.82139 | 0.68968 | 0.14309 | -0.0079819 | 0.33796 | 0.24561 | 0.53277
| 5999 | 0.44367 | 0.20735 | -0.16928 | -0.56653 | -0.49118 | 0.34601 | -0.20508 | 0.28663 | 0.35231 | -0.2975
| 6000 | -0.71627 | -0.33449 | 0.36431 | 0.11938 | 0.34571 | -0.53578 | -0.015571 | -0.17933 | -0.67674 | -0.72559
| 6001 | 0.81697 | -0.1926 | 0.3961 | 0.29296 | 0.16304 | 0.10809 | 0.58587 | -0.20747 | 0.252 | 0.43405
| 6002 | -0.16066 | 0.34266 | -0.074743 | -0.11779 | 0.32317 | -0.17133 | -0.54867 | 0.59913 | 0.030412 | 0.25414
| 6003 | -0.20432 | 0.34647 | -0.079511 | -0.10641 | 0.4531 | -0.18214 | 0.51616 | 0.26727 | 0.44421 | 0.24283
| 6004 | 0.3297 | -0.35123 | -0.48961 | -0.21343 | 0.80176 | 0.67458 | -0.33134 | -0.16531 | 0.83845 | 0.013238
| 6005 | -0.32747 | 0.18581 | 0.40561 | -0.53363 | 0.42181 | 0.18717 | 0.013035 | 0.57023 | 0.64715 | 0.32569
| 6006 | -0.8995 | -0.66728 | -0.39164 | -0.27854 | -0.37783 | 0.23823 | -0.037971 | -0.34129 | 0.14285 | 0.52492
| 6007 | 0.62013 | -0.036517 | -0.2689 | 0.81106 | 0.11056 | -0.22122 | 0.048843 | -0.54668 | -0.19844 | 0.48396
| 6008 | 0.77707 | 0.82139 | 0.86472 | -0.56514 | 0.13138 | -0.22032 | 0.033201 | 0.028352 | -0.17241 | 0.018114
| 6009 | -0.57656 | -0.25777 | 0.040677 | -0.12564 | -0.20344 | 0.016994 | -0.27123 | 0.43334 | 0.13646 | 0.015267
| 6010 | -0.15685 | 0.67891 | 0.17217 | 0.58299 | -0.25616 | 0.35108 | -0.15094 | 0.90673 | 0.53299 | 0.45438
| 6011 | 0.73037 | 0.52703 | -0.028043 | -0.21292 | -0.2081 | 0.15118 | 0.64772 | -0.46437 | 0.82651 | 0.054855
| 6012 | 0.26536 | 0.53859 | -0.088134 | 0.44206 | -0.6077 | -0.37494 | 0.37574 | -0.23915 | -0.35899 | -0.46849
| 6013 | 0.48183 | -0.09121 | 0.36133 | -0.452 | 0.60821 | -0.7245 | -0.035376 | -0.30711 | -0.38105 | 0.010707
| 6014 | 0.042973 | 0.067745 | 0.4531 | 0.081033 | 0.33555 | 0.12085 | -0.40242 | -0.013542 | -0.55312 | 0.4987
| 6015 | 0.91 | 0.41545 | -0.84348 | 0.53192 | -0.37767 | 0.46046 | 0.6985 | -0.32302 | 0.10462 | -0.16137
| 6016 | -0.44027 | -0.048422 | 0.66044 | 0.2755 | -0.3015 | 0.65373 | 0.3294 | -0.75282 | 0.22328 | -0.053374
| 6017 | -0.25616 | 0.59441 | 0.77262 | -0.86923 | -0.25414 | -0.58563 | -0.32376 | 0.57633 | -0.87793 | -0.564
| 6018 | -0.26767 | 0.41562 | 0.10697 | -0.21763 | -0.64433 | -0.13369 | 0.20094 | -0.51369 | 0.61026 | -0.39792
| 6019 | 0.65373 | -0.70386 | -0.5608 | -0.13219 | 0.48473 | -0.15744 | -0.061544 | -0.088463 | -0.77087 | -0.57774
| 6020 | -0.33932 | 0.32243 | -0.29864 | -0.17471 | 0.29311 | 0.62145 | 0.16412 | -0.29509 | -0.50654 | -0.65057
| 6021 | -0.34342 | -0.018318 | -0.39082 | -0.4286 | -0.41836 | -0.080707 | 0.25549 | -0.17629 | -0.71277 | 0.32037
| 6022 | 0.44656 | -0.35185 | -0.098169 | -0.67643 | 5.0001e-05 | -0.36873 | 0.20432 | 0.36968 | -0.097725 | 0.21381
| 6023 | -0.38283 | -0.39345 | 0.52809 | -0.085178 | 0.5922 | -0.013339 | 0.26767 | 0.26986 | 0.18606 | -0.074419
| 6024 | -0.46699 | -0.52682 | -0.7015 | -0.60949 | -0.048107 | -0.90151 | -0.39246 | -0.6233 | -0.3537 | -0.26441
| 6025 | -0.046428 | -0.73373 | -0.57093 | -0.11767 | -0.34479 | 0.74368 | -0.034547 | -0.21165 | -0.44909 | 0.48318
| 6026 | 0.23026 | -0.44331 | -0.33766 | 0.14671 | 0.43423 | -0.64181 | -0.060053 | 0.24178 | -0.030309 | -0.18299
| 6027 | 0.12622 | -0.50594 | -0.25294 | 0.15839 | 0.30236 | 0.67953 | 0.43831 | 0.0087886 | 0.35339 | -0.28817
| 6028 | 0.55559 | 0.56606 | -0.26034 | 0.72963 | -0.84157 | -0.12382 | 0.33705 | 0.0066723 | -0.21101 | 0.30624
| 6029 | -0.41974 | 0.21546 | 0.136 | 0.57116 | -0.4078 | -0.12142 | -0.050421 | -0.64574 | -0.6407 | 0.027015
| 6030 | 0.097725 | 0.25428 | 0.54536 | -0.65927 | -0.35914 | -0.47914 | 0.19161 | 0.5011 | 0.64265 | -0.30957
| 6031 | -0.41665 | 0.33464 | 0.67643 | -0.40075 | -0.3297 | 0.05814 | -0.23809 | -0.074959 | -0.23469 | 0.12496
| 6032 | -0.45055 | 0.61568 | 0.64602 | -0.39942 | 0.34908 | 0.22469 | 0.38706 | -0.68743 | -0.61751 | -0.32851
| 6033 | 0.37159 | 0.045799 | 0.2659 | 0.23928 | -0.029588 | 0.27371 | -0.32302 | 0.012427 | -0.26413 | -0.66399
| 6034 | -0.17872 | -0.18655 | 0.050948 | -0.19 | 0.26413 | 0.79239 | -0.42095 | 0.43123 | -0.06957 | 0.22611
| 6035 | -0.019439 | 0.0066723 | -0.73561 | -0.35046 | 0.6703 | 0.068281 | -0.40696 | 0.16627 | -0.39033 | 0.073879
| 6036 | 0.70589 | -0.35525 | -0.22006 | -0.21674 | 0.0081835 | 0.087914 | -0.4134 | 0.073447 | -0.4117 | 0.057928
| 6037 | 0.10731 | -0.43105 | -0.45401 | 0.32896 | -0.20181 | -0.32881 | -0.49078 | 0.37992 | -0.25616 | -0.041929
| 6038 | -0.083867 | -0.15863 | 0.23013 | -0.050948 | -0.60389 | 0.40159 | -0.21763 | 0.12874 | -0.40343 | 0.06914
| 6039 | -0.29736 | 0.38445 | 0.15661 | 0.3294 | 0.40192 | -0.59245 | 0.45732 | 0.14006 | 0.31655 | 0.63027
| 6040 | 0.57327 | 0.38267 | 0.43938 | 0.29651 | -0.09055 | -0.27357 | 0.86771 | -0.57491 | 0.66133 | 0.79482
| 6041 | 0.80895 | -0.14578 | -0.0080827 | -0.028043 | -0.14965 | -0.15756 | 0.11541 | -0.056973 | -0.081904 | 0.82028
| 6042 | 0.67766 | -0.82308 | 0.17133 | 0.50513 | -0.036413 | -0.38478 | 0.067316 | 0.25133 | 0.66758 | -0.59441
| 6043 | 0.61568 | 0.22818 | 0.55447 | 0.04266 | -0.12553 | -0.086819 | -0.29339 | -0.63435 | 0.053797 | 0.52408
| 6044 | 0.47265 | 0.19757 | -0.058246 | 0.06293 | -0.20558 | 0.44242 | -0.81372 | 0.2265 | 0.44873 | 0.12359
| 6045 | 0.11688 | -0.27702 | -0.26973 | -0.04266 | 0.40326 | -0.055278 | -0.16149 | -0.13704 | 0.23521 | -0.36133
| 6046 | 0.44873 | 0.13611 | 0.83417 | -0.5883 | 0.38478 | 0.51492 | -0.50735 | 0.65201 | 0.065174 | -0.19284
| 6047 | 0.76957 | -0.16436 | -0.14472 | 0.2343 | -0.070215 | 0.27564 | -0.53385 | 0.021174 | 0.12313 | -0.73186
| 6048 | -0.066565 | 0.015978 | 0.40763 | -0.13519 | -0.56354 | 0.16268 | -0.54734 | -0.053269 | -0.2356 | -0.17738
| 6049 | -0.12108 | -0.15673 | 0.028867 | -0.20583 | -0.64405 | 0.03714 | 0.53064 | -0.16964 | 0.72269 | -0.27993
| 6050 | 0.23731 | -0.69488 | -0.40729 | 0.19037 | -0.068711 | -0.85201 | -0.40494 | -0.058353 | -0.3477 | 0.22315
| 6051 | -0.036621 | 0.22109 | -0.69884 | 0.53064 | -0.60289 | -0.39709 | -0.071507 | -0.35603 | 0.085396 | -0.47189
| 6052 | -0.23078 | 0.51184 | 0.49236 | -0.11518 | -0.094406 | 0.26481 | -0.28817 | -0.16185 | 0.38461 | 0.063677
| 6053 | -0.5102 | 0.55134 | -0.063998 | 0.62543 | 0.51225 | -0.28243 | -0.96394 | 0.1578 | -0.040886 | 0.60088
| 6054 | 0.29495 | -0.65287 | 0.21738 | -0.73111 | 0.1375 | 0.28495 | -0.1229 | 0.049053 | -0.79384 | 0.033822
| 6055 | 0.0056661 | -0.68615 | -0.17799 | 0.52073 | 0.12839 | -0.34372 | 0.20445 | -0.024756 | 0.17592 | -0.36841
| 6056 | -0.79288 | -0.015571 | -0.43476 | 0.23547 | 0.74251 | -0.54426 | 0.031651 | 0.2175 | -0.3363 | 0.34877
| 6057 | -0.20609 | -0.8618 | -0.33419 | 0.48687 | -0.060798 | -0.59269 | 0.70017 | 0.27979 | -0.42078 | -0.79776
| 6058 | -0.23 | 0.47019 | -0.75403 | 0.25 | 0.40058 | 0.082776 | 0.11191 | 0.12943 | 0.031444 | -0.1926
| 6059 | -0.25414 | -0.81534 | 0.056973 | -0.28202 | 0.44529 | 0.30122 | -0.40309 | -0.74801 | -0.034858 | -0.23639
| 6060 | 0.25 | -0.22058 | 0.5017 | 0.49651 | -0.36968 | 0.61987 | -0.19111 | 0.079402 | 0.064318 | -0.56216
| 6061 | -0.026398 | -0.17096 | 0.66162 | -0.6265 | 0.48707 | -0.13808 | 0.021583 | -0.03714 | 0.27206 | -0.5141
| 6062 | -0.18128 | -0.8422 | -0.17109 | 0.11881 | 0.78023 | -0.62145 | -0.034133 | 0.28958 | 0.061224 | 0.34357
| 6063 | -0.27605 | -0.63627 | -0.50817 | -0.10787 | 0.09518 | 0.2427 | 0.80791 | 0.098723 | 0.011516 | 0.32791
| 6064 | 0.13092 | -0.06229 | 0.15851 | 0.07043 | -0.019337 | 0.077666 | 0.79628 | -0.16197 | 0.30797 | 0.76741
| 6065 | 0.08485 | -0.088902 | 0.40242 | -0.094185 | 0.23823 | 0.2313 | -0.0032553 | 0.12074 | 0.34281 | 0.95204
| 6066 | -0.23351 | 0.63408 | 0.7076 | 0.52915 | 0.097836 | 0.15318 | -0.79336 | 0.12576 | 0.24151 | 0.11011
| 6067 | 0.47493 | -0.38251 | -0.64772 | 0.81588 | -0.19284 | 0.069785 | -0.26237 | 0.58275 | 0.83059 | -0.80025
| 6068 | 0.50311 | -0.31073 | 0.68871 | -0.24588 | -0.30322 | -0.51678 | 0.11214 | 0.5007 | 0.2133 | 0.11496
| 6069 | -0.55537 | -0.49078 | 0.72559 | -0.7508 | -0.23143 | -0.085396 | -0.0035563 | -0.52703 | 0.68078 | 0.57116
| 6070 | 0.14449 | -0.36921 | 0.12154 | 0.74485 | -0.71208 | 0.21712 | -0.55178 | -0.5017 | -0.20546 | -0.67458
| 6071 | 0.67674 | -0.46046 | -0.33811 | -0.61103 | -0.7015 | -0.76741 | -0.34693 | -0.55402 | 0.15685 | -0.77572
| 6072 | -0.54536 | -0.16892 | -0.21279 | 0.28243 | -0.1559 | -0.095622 | -0.02609 | 0.13242 | -0.26645 | 0.048738
| 6073 | -0.15661 | -0.4993 | 0.099722 | 0.41871 | -0.41905 | 0.32539 | 0.47493 | -0.14542 | 0.31919 | -0.59813
| 6074 | -0.0060684 | 0.093634 | 0.52619 | -0.4991 | 0.42842 | 0.15863 | 0.049263 | 0.1546 | -0.45658 | 0.35293
| 6075 | -0.098169 | 0.66939 | -0.25254 | 0.18434 | -0.45109 | 0.016588 | 0.18483 | 0.60846 | -0.40326 | 0.041512
| 6076 | 0.33149 | -0.33239 | 0.30957 | 0.47971 | -0.49059 | 0.47512 | -0.53492 | -0.028249 | -0.53171 | -0.31378
| 6077 | -0.44511 | 0.040052 | 0.87793 | -0.15863 | -0.364 | 0.24933 | -0.82196 | -0.13011 | 0.39082 | 0.24548
| 6078 | 0.051053 | 0.21802 | -0.45347 | 0.40443 | 0.13265 | -0.71069 | -0.4801 | 0.24947 | 0.30841 | 0.49098
| 6079 | 0.24349 | 0.79628 | 0.70521 | -0.26877 | -0.464 | 0.85613 | 0.09529 | 0.20407 | 0.58951 | 0.41034
| 6080 | 0.16892 | 0.17133 | -0.12541 | 0.84933 | 0.39975 | -0.74251 | -0.034443 | 0.096175 | -0.37863 | -0.22805
| 6081 | -0.051369 | -0.089451 | -0.64461 | -0.18214 | 0.14871 | -0.19881 | 0.38673 | -0.099611 | -0.060798 | -0.42147
| 6082 | -0.033615 | 0.39942 | -0.60668 | 0.057185 | -0.070861 | 0.33962 | -0.11372 | 0.0092932 | -0.25777 | -0.11304
| 6083 | 0.47151 | -0.3817 | -0.51844 | 0.3242 | 0.58781 | 0.015267 | 0.78436 | 0.34754 | 0.19433 | 0.56791
| 6084 | 0.40932 | -0.17921 | 0.24389 | 0.013238 | 0.53363 | 0.033925 | 0.27536 | 0.57988 | 0.28174 | 0.17921
| 6085 | -0.16856 | 0.33209 | 0.2119 | 0.78622 | -0.10641 | -0.10261 | 0.21343 | 0.15519 | -0.40544 | -0.40611
| 6086 | -0.14706 | 0.11326 | -0.13115 | 0.07183 | -0.26413 | -0.48241 | 0.036621 | -0.50231 | -0.19831 | 0.4588
| 6087 | 0.49177 | 0.59392 | -0.73074 | -0.48454 | 0.31772 | -0.17072 | -0.12006 | 0.56814 | -0.28439 | 0.36415
| 6088 | -0.60213 | -0.34525 | -0.47779 | 0.15448 | 0.08989 | -0.36747 | 0.56468 | 0.57609 | 0.061437 | -0.78576
| 6089 | 0.12656 | -0.16125 | 0.47474 | 0.15721 | -0.21853 | -0.073879 | 0.7816 | -0.044751 | 0.16807 | 0.63271
| 6090 | 0.55672 | -0.13346 | 0.070861 | 0.054431 | -0.58371 | 0.14344 | 0.19074 | 0.22469 | 0.24893 | 0.087257
| 6091 | 0.17665 | -0.65 | 0.57023 | -0.070215 | 0.21533 | -0.14777 | -0.36841 | -0.41136 | 0.53107 | -0.051475
| 6092 | -0.21457 | 0.3189 | -0.20621 | 0.11462 | -0.91 | -0.23208 | 0.20357 | 0.30107 | 0.18569 | -0.20156
| 6093 | -0.61646 | 0.018725 | 0.053058 | -0.22767 | -0.18729 | 0.087805 | 0.28425 | -0.011011 | 0.67735 | 0.37686
| 6094 | -0.18201 | -0.026707 | -0.13623 | 0.27371 | 0.11688 | 0.14554 | 0.15082 | -0.14274 | 0.052741 | -0.56676
| 6095 | -0.6349 | 0.35634 | 0.33284 | 0.29893 | 0.39345 | 0.3425 | -0.73149 | 0.7735 | 0.080924 | 0.25777
| 6096 | -0.11813 | 0.27288 | -0.2278 | 0.26441 | 0.27 | -0.083321 | 0.34083 | -0.42825 | 0.48454 | 0.30841
| 6097 | 0.17982 | -0.1884 | -0.81159 | 0.82883 | -0.47 | 0.10585 | 0.033718 | -0.12473 | -0.093634 | -0.12279
| 6098 | -0.19396 | -0.60289 | 0.26196 | 0.28257 | -0.55875 | 0.16916 | -0.83059 | 0.0041586 | 0.49711 | -0.59913
| 6099 | -0.0036567 | -0.74251 | -0.2496 | 0.071507 | -0.63737 | 0.59098 | -0.3312 | -0.45328 | -0.00095045 | 0.11067
| 6100 | 0.1179 | -0.2484 | -0.12222 | 0.065923 | 0.37079 | -0.71522 | -0.55989 | -0.54911 | 0.87233 | -0.12142
| 6101 | -0.33871 | 0.010303 | 0.78068 | 0.018318 | -0.65751 | 0.24987 | -0.19707 | -0.01263 | -0.12656 | 0.26278
| 6102 | -0.57444 | -0.65605 | 0.15389 | -0.24231 | 0.19037 | 0.11248 | 0.41974 | -0.057716 | -0.9089 | -0.86771
| 6103 | 0.56194 | -0.79826 | -5.0001e-05 | -0.35603 | 0.43973 | 0.20081 | -0.59738 | -0.09518 | 0.35961 | 0.93292
| 6104 | -0.60974 | -0.79384 | -0.58903 | 0.012123 | -0.2184 | -0.7015 | 0.66489 | -0.62251 | -0.3312 | 0.52513
| 6105 | 0.46887 | 0.66221 | 0.054643 | -0.24641 | 0.26196 | 0.45073 | 0.13207 | -0.52177 | 0.70487 | -0.50715
| 6106 | 0.53967 | 0.073339 | 0.50837 | 0.79239 | 0.36305 | -0.19682 | 0.13473 | 0.21521 | -0.7504 | 0.45493
| 6107 | -0.30308 | 0.3366 | 0.42476 | -0.094959 | -0.94432 | -0.30107 | 0.2256 | -0.030516 | -0.13046 | -0.25455
| 6108 | 0.32598 | -0.69884 | 0.066994 | -0.46176 | -0.39246 | -0.056973 | 0.45036 | -0.13219 | 0.79925 | 0.11248
| 6109 | -0.21917 | -0.29325 | 0.14812 | 0.37574 | 0.062077 | -0.2377 | 0.61231 | 0.014454 | -0.63903 | -0.32866
| 6110 | 0.24628 | 0.50857 | -0.64405 | 0.41306 | 0.098169 | -0.53 | 0.058777 | -0.10429 | 0.60795 | -0.1025
| 6111 | 0.34083 | -0.27206 | 0.45917 | -0.6257 | -0.075716 | 0.12382 | -0.59024 | 0.058034 | 0.030928 | 0.13219
| 6112 | 0.72963 | -0.57609 | -0.064853 | 0.19483 | 0.23521 | -0.33479 | 0.77707 | 0.52957 | 0.10507 | 0.13808
| 6113 | 0.035272 | -0.73637 | 0.66103 | 0.27688 | -0.032994 | 0.43742 | -0.022606 | 0.10351 | 0.20571 | -0.12679
| 6114 | -0.0037571 | 0.22482 | -0.58419 | 0.46568 | -0.51948 | -0.17096 | 0.7429 | -0.37863 | 0.18988 | 0.24363
| 6115 | -0.57964 | -0.041616 | -0.45018 | -0.097614 | 0.28202 | -0.20621 | 0.059096 | -0.017707 | 0.31189 | 0.30971
| 6116 | 0.096839 | -0.071076 | -0.57656 | 0.34617 | 0.12828 | -0.41494 | 0.26563 | 0.062077 | 0.23783 | -0.15012
| 6117 | -0.60719 | -0.20006 | -0.47798 | 0.37318 | 0.33194 | -0.31378 | -0.11824 | -0.21546 | 0.80176 | 0.29893
| 6118 | 0.2733 | 0.46176 | 0.17012 | -0.53664 | 0.055066 | -0.29099 | 0.17884 | 0.64014 | -0.18128 | 0.012326
| 6119 | 0.64237 | 0.61231 | 0.83118 | 0.12439 | 0.42703 | 0.152 | -0.10373 | 0.036621 | 0.31276 | -0.20508
| 6120 | -0.13646 | -0.17677 | 0.8937 | 0.061437 | -0.12702 | 0.27288 | -0.62865 | -0.58012 | -0.20081 | 0.25214
| 6121 | 0.33105 | 0.0029544 | 0.0053644 | -0.70318 | -0.24283 | 0.084959 | 0.21025 | 0.64097 | 0.010101 | -0.16639
| 6122 | -0.049474 | 0.069355 | -0.099167 | -0.072153 | 0.039948 | 0.13438 | -0.17447 | 0.28049 | -0.26345 | -0.41102
| 6123 | -0.24535 | -0.019337 | 0.38089 | -0.41785 | -0.51164 | -0.58299 | 0.38008 | -0.078642 | 0.39692 | 0.73637
| 6124 | -0.20596 | 0.65809 | -0.061331 | 0.14297 | -0.018725 | 0.60643 | -0.18692 | -0.32332 | -0.29226 | -0.14134
| 6125 | -0.62119 | 0.37638 | 0.27536 | -0.55223 | 0.16928 | -0.20785 | 0.51164 | 0.40175 | 0.25468 | -0.61961
| 6126 | 0.75813 | 0.022299 | -0.012123 | 0.50533 | 0.1962 | -0.35572 | -0.045589 | -0.28327 | -0.37783 | -0.46737
| 6127 | -0.086162 | -0.069785 | -0.53449 | 0.42493 | -0.87077 | 0.037244 | 0.46925 | -0.72089 | 0.20937 | -0.61103
| 6128 | -0.38575 | 0.36008 | -0.3248 | 0.095069 | -0.16747 | 0.031341 | -0.30509 | -0.85067 | -0.7042 | -0.41391
| 6129 | 0.77262 | -0.28453 | -0.16484 | -0.30437 | -0.0021523 | -0.55582 | 0.096617 | -0.64772 | 0.15024 | -0.6755
| 6130 | 0.024962 | 0.27453 | 0.68425 | 0.046323 | -0.11564 | 0.032788 | -0.64659 | 0.083758 | -0.27274 | -0.67704
| 6131 | 0.89183 | 0.35945 | 0.77751 | -0.31934 | -0.43831 | -0.24059 | 0.45146 | -0.21215 | 0.017503 | -0.13623
| 6132 | -0.17036 | -0.065067 | 0.041094 | 0.44439 | 0.41136 | -0.27014 | -0.016079 | -0.044333 | -0.28063 | 0.10161
| 6133 | -0.79433 | 0.45164 | -0.35417 | -0.085287 | 0.069677 | -0.41682 | 0.010707 | -0.61154 | 0.47837 | -0.053797
| 6134 | 0.32851 | 0.38869 | 0.2431 | -0.28719 | 0.48376 | 0.2958 | 0.16448 | 0.11202 | -0.26278 | 0.11949
| 6135 | -0.8454 | 0.63848 | -0.1513 | 0.54054 | 0.079511 | -0.23744 | -0.71769 | 0.046428 | 0.37767 | -0.30509
| 6136 | 0.41494 | 0.084522 | 0.55178 | 0.18926 | 0.40359 | 0.24138 | 0.49691 | 0.63848 | -0.19198 | -0.11169
| 6137 | 0.35463 | 0.10697 | -0.17592 | -0.11711 | 0.10697 | 0.41153 | -0.0011507 | -0.030206 | -0.61387 | -0.43529
| 6138 | -0.083649 | 0.50251 | 0.34969 | -0.05496 | -0.35899 | -0.058565 | -0.12461 | -0.37686 | -0.11586 | 0.58612
| 6139 | 0.80025 | -0.22534 | -0.5332 | -0.78716 | -0.28775 | 0.038491 | -0.19471 | -0.35836 | -0.11191 | 0.049684
| 6140 | 0.016588 | -0.081142 | 0.47151 | -0.3211 | 0.26754 | 0.0038574 | -0.62198 | -0.59466 | -0.2755 | -0.72233
| 6141 | 0.13774 | 0.45365 | -0.077449 | -0.2492 | -0.2791 | -0.033822 | -0.38771 | -0.28747 | -0.31524 | -0.44493
| 6142 | -0.47189 | 0.36683 | 0.18594 | -0.039011 | -0.30899 | 0.52894 | -0.4408 | -0.098169 | -0.52555 | 0.4279
| 6143 | -0.34525 | -0.56445 | -0.40831 | 0.38918 | 0.54668 | 0.01486 | 0.30797 | -0.55875 | -0.04266 | -0.13913
| 6144 | 0.055595 | 0.66251 | -0.49078 | -0.43813 | 0.023527 | 0.29424 | 0.035583 | -0.067852 | -0.50756 | -0.55156
| 6145 | 0.21165 | 0.024551 | -0.87 | -0.05549 | -0.38624 | 0.16042 | 0.11507 | -0.56216 | 0.67366 | 0.71382
| 6146 | 0.58179 | -0.54536 | 0.74841 | 0.036205 | -0.019031 | 0.10955 | 0.42233 | 0.38494 | -0.48726 | 0.37911
| 6147 | 0.038491 | 0.41391 | 0.23547 | 0.5656 | 0.030309 | 0.47189 | -0.42389 | 0.81972 | 0.61803 | 0.51616
| 6148 | -0.40477 | 0.13011 | -0.50878 | -0.53085 | 0.38836 | -0.14192 | 0.12793 | -0.054008 | 0.3568 | -0.61516
| 6149 | -0.39296 | 0.20169 | 0.48299 | 0.33585 | 0.076258 | -0.00055015 | -0.1473 | 0.56285 | 0.47645 | -0.56011
| 6150 | -0.06229 | 0.40763 | -0.18495 | 0.30179 | -0.074311 | -0.56011 | 0.40898 | 0.36604 | -0.34877 | -0.54251
| 6151 | 0.077883 | 0.017198 | 0.75855 | 0.74722 | 0.35977 | -0.54076 | 0.82422 | 0.15887 | -0.13138 | 0.5959
| 6152 | -0.51266 | -0.19894 | -0.058671 | 0.06678 | 0.07962 | -0.35448 | -0.65316 | 0.75444 | -0.15816 | 0.10373
| 6153 | 0.59049 | -0.34053 | -0.018522 | 0.39329 | -0.6631 | 0.20006 | 0.58612 | 0.27495 | 0.28986 | 0.14437
| 6154 | -0.33494 | 0.16819 | -0.67121 | -0.071507 | -0.27137 | 0.54712 | -0.34708 | -0.0866 | -0.54338 | 0.77262
| 6155 | 0.5721 | -0.21292 | -0.38478 | -0.47818 | 0.22019 | -0.14111 | -0.42965 | 0.030825 | -0.64659 | -0.95
| 6156 | -0.34571 | -0.25334 | -0.15012 | -0.087805 | 0.81862 | 0.73599 | -0.3743 | -0.6631 | 0.46232 | 0.24429
| 6157 | -0.3537 | -0.65693 | -0.24363 | -0.85337 | -0.21878 | -0.027529 | -0.24165 | -0.86399 | -0.60389 | 0.30942
| 6158 | 0.29879 | -0.73486 | 0.72161 | 0.13832 | -0.62384 | -0.18815 | 0.007478 | 0.17726 | 0.54889 | 0.65287
| 6159 | 0.62304 | -0.46849 | -0.15994 | 0.75648 | 0.10574 | -0.45018 | -0.31378 | 0.52031 | 0.23182 | -0.48087
| 6160 | 0.2744 | -0.27716 | 0.39181 | -0.31758 | 0.23888 | 0.58347 | -0.18226 | 0.7839 | -0.57444 | -0.23182
| 6161 | 0.13265 | 0.12793 | -0.39842 | 0.34023 | 0.83 | 0.66281 | -0.11484 | -0.21013 | -0.23456 | -0.34448
| 6162 | -0.66608 | -0.17738 | 0.013744 | -0.014657 | -0.63517 | 0.37799 | -0.06603 | -0.2052 | 0.4279 | -0.0016514
| 6163 | -0.087695 | -0.14706 | 0.29353 | 0.0057666 | -0.67922 | 0.23404 | 0.028867 | -0.08967 | 0.15035 | -0.6407
| 6164 | -0.32881 | -0.055172 | -0.25616 | -0.13646 | -0.16807 | 0.25535 | -0.34954 | 0.43176 | -0.86036 | -0.1418
| 6165 | 0.72486 | -0.013136 | -0.22418 | 0.086709 | -0.21393 | 0.34099 | -0.047687 | 0.35479 | 0.02097 | 0.29722
| 6166 | 0.35077 | -0.61206 | -0.60744 | -0.42982 | -0.31189 | 0.021685 | 0.16928 | 0.18938 | -0.15271 | -0.0038574
| 6167 | 0.22212 | -0.264 | -0.65663 | 0.43317 | 0.27785 | 0.16868 | -0.40915 | 0.65345 | 0.40292 | 0.087038
| 6168 | 0.33826 | 0.71769 | -0.14601 | -0.18324 | 0.58951 | -0.045484 | -0.56468 | -0.67152 | -0.5174 | -0.36274
| 6169 | -0.4344 | 0.25576 | 0.75444 | 0.26386 | 0.37654 | 0.25791 | -0.023117 | 0.4426 | 0.092421 | 0.57869
| 6170 | -0.039427 | -0.24099 | 0.25831 | 0.17629 | 0.55853 | 0.59988 | 0.42755 | 0.36668 | -0.30986 | -0.12793
| 6171 | -0.41733 | 0.09121 | -0.83599 | 0.59 | 0.18544 | 0.33419 | -0.23482 | -0.37239 | -0.51369 | 0.46812
| 6172 | -0.037555 | -0.8956 | -0.22922 | 0.02189 | 0.049053 | 0.28243 | 0.056655 | 0.23378 | 0.71698 | 0.31305
| 6173 | 0.51369 | -0.39527 | -0.62517 | 0.68456 | -0.11372 | -0.27233 | -0.63027 | -0.49177 | -0.74485 | -0.35494
| 6174 | -0.91693 | -0.52136 | -0.21699 | 0.011314 | 0.37895 | 0.14601 | 0.044123 | -0.31014 | -0.33344 | -0.18557
| 6175 | 0.37414 | -0.54382 | -0.58854 | -0.70862 | -0.5017 | -0.81212 | 0.6631 | 0.010101 | -0.63 | 0.037555
| 6176 | 0.39942 | 0.35123 | 0.045275 | -0.37927 | 0.69817 | 0.18092 | 0.47132 | -0.73637 | -0.24853 | -0.21419
| 6177 | -0.09099 | 0.33856 | 0.64461 | -0.30812 | 0.43831 | -0.31743 | 0.4232 | -0.15887 | -0.28986 | 0.55447
| 6178 | 0.022299 | -0.12874 | 0.36274 | 0.035065 | -0.19359 | 0.059415 | -0.12839 | 0.35712 | -0.25656 | -0.35062
| 6179 | 0.1082 | 0.41323 | -0.21317 | -0.22379 | -0.089561 | -0.059202 | 0.54624 | 0.17169 | -0.17205 | 0.44063
| 6180 | -0.81534 | 0.20294 | -0.58927 | 0.0049623 | -0.32702 | 0.16892 | 0.56354 | 0.053903 | -0.16244 | -0.14017
| 6181 | 0.058671 | 0.021276 | 0.086271 | 0.47246 | -0.016588 | 0.15082 | -0.1277 | -0.038491 | 0.077883 | -0.57491
| 6182 | -0.44224 | 0.39775 | -0.33299 | 0.19732 | 0.068603 | 0.12439 | 0.44837 | 0.24297 | 0.39626 | -0.50634
| 6183 | 0.34525 | -0.18434 | -0.72963 | 0.1025 | 0.96683 | 0.15165 | -0.080489 | 0.071722 | -0.3369 | 0.39461
| 6184 | -0.14332 | -0.27412 | 0.72815 | 0.3759 | 0.53043 | 0.19595 | 0.26849 | -0.064212 | 0.056655 | -0.10944
| 6185 | 0.50412 | -0.6407 | 0.73524 | -0.28285 | -0.10261 | -0.39263 | 0.86399 | -0.14929 | -0.47113 | 0.30595
| 6186 | -0.11372 | -0.31758 | 0.41255 | -0.58612 | 0.65172 | -0.048317 | 0.74251 | 0.11157 | -0.61568 | 0.52873
| 6187 | 0.19782 | 0.17994 | -0.23744 | -0.58012 | 0.45677 | 0.48222 | 0.038387 | 0.66789 | 0.22418 | -0.16006
| 6188 | -0.1109 | -0.14449 | 0.8995 | 0.22767 | -0.23234 | -0.47019 | 0.5866 | 0.095732 | 0.22186 | 0.24059
| 6189 | 0.17423 | -0.27509 | -0.073124 | 0.76527 | 0.19819 | 0.47626 | -0.06293 | 0.24429 | -0.46868 | -0.080707
| 6190 | 0.34938 | -0.37847 | 0.26128 | 0.31407 | -0.5347 | 0.6786 | 0.12142 | -0.093303 | 0.082667 | -0.24046
| 6191 | 0.43759 | -0.37831 | -0.9245 | -0.36589 | 0.040886 | -0.082013 | 0.24125 | -0.057291 | 0.087805 | -0.41068
| 6192 | -0.0069743 | -0.52492 | 0.79 | -0.033718 | 0.28621 | 0.5283 | -0.20785 | 0.57444 | 0.27453 | 0.55966
| 6193 | 0.085178 | 0.20006 | -0.36494 | -0.3767 | 0.51865 | -0.060692 | -0.67766 | 0.73524 | -0.76315 | 0.29212
| 6194 | -0.2602 | -0.069463 | 0.085943 | 0.63765 | -0.57633 | -0.78436 | 0.28551 | -0.43176 | -0.46793 | -0.59565
| 6195 | 0.70184 | 0.26169 | 0.62597 | -0.53556 | 0.28635 | -0.04517 | -0.64377 | -0.60364 | 0.25027 | -0.69751
| 6196 | 0.27661 | -0.58155 | -0.51472 | 0.62597 | -0.54933 | -0.29679 | 0.10529 | -0.073124 | -0.014657 | -0.02794
| 6197 | -0.13542 | 0.40729 | -0.54076 | -0.0068736 | -0.17302 | 0.14871 | 0.0032553 | -0.61829 | -0.44964 | -0.078534
| 6198 | 0.40544 | -0.2161 | -0.074203 | -0.038387 | 0.18729 | -0.73866 | 0.29979 | 0.13438 | 0.448 | -0.008486
| 6199 | -0.26904 | -0.22469 | -0.061437 | 0.35448 | -0.41119 | -0.010303 | 0.36589 | 0.26264 | -0.31102 | 0.18459
| 6200 | -0.20495 | 0.4408 | 0.05549 | 0.16161 | 0.61335 | 0.46868 | -0.019847 | -0.27661 | -0.44818 | 0.41733
| 6201 | 0.79191 | -0.5469 | 0.39742 | -0.94615 | -0.53816 | 0.62384 | -0.052213 | 0.28285 | 0.081577 | -0.30236
| 6202 | -0.45146 | 0.013643 | 0.5011 | 0.23417 | -0.23574 | -0.0051633 | 0.52492 | 0.11813 | 0.81697 | 0.19322
| 6203 | 0.019643 | -0.17994 | -0.15982 | -0.22366 | 0.44728 | -0.34038 | -0.51761 | -0.26727 | 0.12874 | -0.34311
| 6204 | 0.5013 | -0.80125 | -0.45055 | -0.6939 | 0.023015 | 0.79384 | -0.61961 | 0.19235 | -0.59813 | 0.30826
| 6205 | -0.26115 | -0.52619 | 0.43458 | 0.080598 | 0.21406 | 0.46102 | 0.77087 | 0.05 | 0.49751 | -0.31802
| 6206 | -0.25549 | 0.46587 | -0.55989 | -0.34311 | 0.43813 | -0.17775 | -0.2816 | 0.38202 | -0.22831 | 0.082013
| 6207 | 0.075284 | -0.72341 | -0.4408 | 0.07 | 0.7488 | -0.55785 | -0.0089904 | -0.17592 | -0.32376 | -0.24495
| 6208 | -0.05 | 0.44656 | 0.28944 | 0.74135 | -0.148 | 0.29085 | -0.10641 | 0.44224 | 0.73186 | -0.2516
| 6209 | 0.3537 | 0.50939 | -0.36117 | 0.16543 | 0.035168 | -0.30797 | 0.070108 | 0.24774 | -0.69422 | -0.40075
| 6210 | -0.26754 | -0.48961 | -0.32096 | 0.068925 | 0.18214 | 0.24125 | -0.26142 | -0.28076 | -0.51225 | 0.097725
| 6211 | 0.66281 | 0.59664 | -0.90566 | -0.42095 | -0.36164 | -0.47798 | -0.46325 | -0.19595 | 0.18189 | -0.056019
| 6212 | 0.37927 | 0.41221 | -0.10195 | 0.54845 | -0.59689 | 0.8956 | -0.51865 | 0.60872 | -0.057079 | 0.24628
| 6213 | -0.26522 | -0.85 | 0.095843 | -0.4828 | -0.37478 | 0.43493 | -0.28958 | 0.51041 | -0.70318 | 0.93144
| 6214 | 0.33269 | -0.58443 | -0.53085 | -0.21725 | 0.30826 | -0.3419 | -0.11677 | 0.22586 | -0.68936 | 0.38073
| 6215 | -0.24072 | -0.94804 | -0.37254 | -0.35618 | 0.3294 | 0.68552 | 0.58636 | -0.22315 | -0.20949 | -0.09
| 6216 | -0.50715 | 0.34985 | 0.19732 | 0.23993 | -0.54867 | 0.34327 | 0.31189 | -0.18766 | 0.070215 | 0.40393
| 6217 | -0.85682 | -0.18963 | 0.71875 | 0.72486 | -0.060479 | 0.092311 | 0.2512 | -0.15 | 0.71663 | -0.087586
| 6218 | -0.20558 | -0.59073 | -0.79925 | 0.20772 | -0.0045604 | -0.53816 | -0.1603 | -0.1962 | 0.85067 | 0.084085
| 6219 | 0.21521 | -0.41699 | -0.35821 | 0.54033 | 0.35634 | 0.14929 | -0.096285 | -0.55514 | 0.57093 | 0.63848
| 6220 | 0.80226 | -0.46512 | -0.049895 | 0.096175 | -0.21482 | -0.093965 | -0.61829 | -0.34494 | 0.015876 | 0.028455
| 6221 | -0.03714 | -0.096396 | -0.12233 | 0.59738 | -0.16735 | 0.31145 | -0.20886 | 0.055278 | -0.035894 | -0.21241
| 6222 | 0.51782 | -0.50513 | -0.055807 | 0.0055655 | 0.26945 | 0.40831 | 0.034754 | -0.33902 | 0.41 | -0.3419
| 6223 | -0.66044 | -0.68078 | 0.019643 | 0.8755 | -0.075933 | -0.16304 | 0.22586 | 0.85543 | 0.47189 | 0.38153
| 6224 | -0.84933 | 0.19 | -0.15863 | -0.061544 | -0.2133 | 0.043182 | 0.28007 | 0.58878 | -0.67274 | -0.10317
| 6225 | -0.1269 | -0.74564 | 0.49631 | -0.037451 | 0.89276 | -0.38689 | -0.57562 | -0.0079819 | -0.78669 | 0.047162
| 6226 | 0.088682 | 0.40494 | 0.22792 | -0.26932 | -0.37334 | 0.62013 | -0.010101 | 0.11699 | 0.22974 | -0.09706
| 6227 | -0.094959 | -0.032684 | 0.12897 | -0.40309 | 0.1237 | -0.4272 | 0.6578 | 0.25455 | 0.13924 | -0.6939
| 6228 | 0.17921 | 0.23286 | -0.55649 | 0.37606 | -0.97 | -0.3116 | 0.67766 | -0.81752 | -0.056443 | 0.29183
| 6229 | -0.0055655 | -0.44945 | 0.73261 | -0.19595 | -0.26278 | 0.10888 | 0.003456 | -0.63081 | 0.062503 | -0.49295
| 6230 | -0.098279 | -0.21025 | 0.0050628 | -0.09529 | 0.11983 | 0.12063 | 0.1315 | -0.40527 | 0.053163 | -0.88642
| 6231 | 0.25361 | -0.45658 | 0.041303 | 0.75444 | -0.57917 | 0.50878 | -0.65114 | -0.39016 | -0.28453 | -0.40932
| 6232 | 0.70725 | -0.68871 | -0.29622 | 0.27069 | -0.73751 | 0.91693 | -0.63054 | 0.4163 | -0.039323 | 0.46306
| 6233 | 0.82593 | -0.18373 | 0.017809 | 0.34281 | -0.002453 | 0.13577 | 0.21279 | 0.27481 | 0.15697 | -0.13878
| 6234 | -0.088134 | -0.56057 | -0.076149 | -0.552 | 0.13288 | 0.0094951 | 0.53192 | 0.29594 | -0.094848 | 0.13403
| 6235 | -0.37815 | 0.22922 | 0.15958 | 0.57751 | 0.0089904 | 0.22974 | -0.66192 | 0.020663 | -0.037036 | 0.48609
| 6236 | 0.2948 | -0.29367 | -0.30122 | 0.29979 | 0.48882 | 0.19794 | 0.95877 | -0.068711 | 0.45328 | -0.38755
| 6237 | 0.73448 | -0.32925 | -0.61309 | -0.22495 | 0.15982 | -0.076474 | -0.26713 | -0.98268 | 0.16964 | -0.37911
| 6238 | 0.049789 | 0.046847 | -0.78297 | 0.30466 | 0.42268 | 0.011415 | 0.3477 | -0.032891 | 0.60289 | 0.11326
| 6239 | -0.45456 | 0.45991 | -0.085178 | -0.12828 | -0.47265 | 0.37239 | -0.16244 | 0.40209 | 0.22353 | 0.014454
| 6240 | 0.28439 | 0.48941 | 0.41272 | -0.3662 | -0.013238 | -0.10094 | 0.41957 | 0.68839 | -0.42129 | 0.10117
| 6241 | -0.065602 | -0.23705 | 0.52052 | -0.19062 | -0.59294 | 0.17133 | 0.73942 | 0.27014 | -0.0018517 | 0.093192
| 6242 | -0.57468 | 0.14297 | 0.46437 | -0.50878 | -0.11338 | 0.39115 | 0.23312 | -0.57562 | 0.05496 | -0.84157
| 6243 | 0.90461 | -0.97 | -0.54404 | -0.36133 | -0.035376 | -0.22315 | 0.17568 | 0.51082 | -0.19582 | 0.035687
| 6244 | 0.40966 | 0.34571 | -0.85269 | -0.42337 | -0.11903 | 0.073879 | -0.57515 | 0.67984 | 0.097171 | 0.40042
| 6245 | -0.66819 | 0.018623 | 0.045589 | 0.04381 | -0.082667 | -0.25683 | 0.18692 | 0.73561 | -0.78576 | -0.19359
| 6246 | -0.45732 | 0.18471 | 0.94804 | 0.54011 | 0.047687 | -0.68361 | -0.12165 | -0.52745 | -0.1628 | 0.10854
| 6247 | 0.032684 | -0.4417 | 0.24495 | -0.33555 | -0.033615 | -0.61568 | 0.16663 | 0.63244 | 0.57421 | -0.36258
| 6248 | -0.64602 | 0.28831 | -0.10295 | -0.10899 | -0.11157 | -0.18889 | 0.059415 | 0.31641 | -0.53621 | 0.00035006
| 6249 | -0.22199 | -0.68172 | 0.30236 | -0.46306 | -0.12336 | -0.68267 | -0.38934 | 0.61257 | 0.60188 | -0.32791
| 6250 | -0.0022525 | -0.0088895 | 0.40898 | 0.66608 | 0.047582 | -0.11915 | 0.26264 | 0.051264 | 0.039635 | 0.39659
| 6251 | 0.23143 | 0.32302 | 0.5102 | -0.30957 | -0.28035 | -0.2711 | 0.17921 | -0.4826 | 0.057397 | -0.52157
| 6252 | 0.74564 | 0.24099 | 0.57257 | 0.019745 | -0.40679 | 0.49 | -0.18914 | -0.43511 | 0.85682 | -0.32672
| 6253 | -0.90566 | 0.28188 | -0.088024 | -0.12977 | 0.47436 | 0.67612 | -0.28972 | -0.73599 | -0.88642 | 0.075284
| 6254 | 0.90673 | -0.3025 | -0.48902 | 0.76612 | -0.45146 | 0.47379 | 0.16699 | 0.20533 | 0.4717 | 0.65258
| 6255 | 0.87233 | -0.24933 | 0.10395 | 0.32524 | 0.29807 | -0.64715 | -0.67 | 0.50735 | -0.29694 | -0.81697
| 6256 | 0.073879 | -0.30942 | 0.29907 | 0.53149 | 0.27757 | -0.12461 | -0.48843 | 0.032477 | 0.42459 | -0.23208
| 6257 | -0.11745 | -0.27882 | -0.53751 | 0.48454 | -0.86399 | -0.30855 | -0.18581 | 0.2711 | 0.75813 | -0.033822
| 6258 | 0.017605 | 0.0056661 | 0.056019 | 0.29665 | 0.52198 | -0.036102 | -0.40544 | -0.36305 | 0.0082843 | -0.19334
| 6259 | 0.33449 | 0.1513 | -0.80277 | -0.3048 | -0.18104 | 0.36652 | -0.79875 | -0.15212 | 0.3454 | -0.26522
| 6260 | 0.52282 | 0.78114 | 0.23482 | -0.53149 | 0.34388 | 0.53643 | -0.049369 | 0.54558 | -0.12667 | 0.1735
| 6261 | 0.72779 | -0.28495 | -0.074419 | -0.036724 | -0.56125 | 0.18557 | -0.90151 | -0.60415 | 0.37334 | 0.22083
| 6262 | 0.093854 | 0.63903 | -0.41374 | 0.75161 | 0.28257 | 0.48707 | 0.79095 | 0.37734 | 0.13519 | 0.098945
| 6263 | 0.21228 | 0.033305 | -0.31378 | -0.44656 | -0.67891 | -0.21038 | 0.77932 | 0.19136 | -0.03579 | -0.092972
| 6264 | 0.89 | 0.89656 | -0.72669 | 0.087257 | -0.26795 | -0.17229 | 0.0057666 | -0.16639 | 0.11881 | 0.50311
| 6265 | 0.54536 | -0.67984 | -0.21114 | -0.39842 | -0.24112 | -0.72596 | 0.25147 | 0.10664 | -0.016181 | -0.29979
| 6266 | -0.86847 | -0.52555 | 0.066565 | 0.31934 | 0.27536 | -0.77662 | -0.082667 | -0.064105 | 0.51205 | 0.63054
| 6267 | 0.30495 | -0.11915 | 0.70966 | 0.069785 | 0.14111 | -0.25227 | -0.27924 | -0.71 | -0.352 | 0.21419
| 6268 | 0.17702 | -0.35015 | 0.86847 | 0.056867 | 0.1473 | 0.46755 | -0.56583 | 0.26604 | -0.048843 | 0.15555
| 6269 | -0.053586 | 0.11293 | 0.22006 | 0.26481 | 0.40443 | -0.83177 | 0.3796 | 0.49711 | 0.19931 | 0.6338
| 6270 | 0.59491 | 0.058353 | 0.14064 | -0.11045 | -0.040156 | -0.12359 | 0.71382 | 0.67 | -0.52809 | -0.55785
| 6271 | -0.73866 | -0.17933 | 0.50231 | 0.97354 | 0.45036 | -0.73561 | -0.4683 | 0.16352 | -0.078968 | -0.063357
| 6272 | 0.12085 | -0.23626 | 0.14274 | 0.60188 | -0.21917 | -0.08485 | -0.41136 | -0.66519 | 0.19309 | 0.29325
| 6273 | -0.56907 | -0.21904 | -0.13553 | -0.011415 | -0.20722 | 0.47038 | -0.029382 | 0.009596 | 0.59888 | -0.20319
| 6274 | -0.31014 | 0.26932 | 0.036724 | 0.035998 | 0.41871 | 0.59417 | -0.36968 | 0.030516 | 0.452 | -0.15614
| 6275 | -0.27495 | 0.075392 | -0.2958 | 0.4776 | 0.32465 | -0.15106 | -0.23169 | 0.47132 | 0.19969 | -0.50311
| 6276 | -0.039011 | -0.0040582 | -0.1735 | 0.53299 | -0.43423 | 0.1921 | -0.20596 | 0.31553 | 0.49059 | -0.97764
| 6277 | -0.089341 | -0.26495 | -0.19557 | 0.29028 | -0.28202 | -0.51082 | 0.81972 | -0.29637 | 0.01415 | 0.050737
| 6278 | -0.13832 | 0.013339 | 0.27082 | -0.063784 | 0.63986 | 0.0087886 | 0.021685 | -0.016181 | -0.038075 | 0.81807
| 6279 | -0.041303 | -0.35572 | -0.29523 | -0.06293 | 0.38706 | -0.56491 | 0.10809 | 0.39296 | -0.28411 | -0.071184
| 6280 | 0.15247 | -0.14519 | -0.55379 | 0.31247 | 0.26672 | -0.48454 | 0.42424 | -0.27979 | 0.81372 | -0.1752
| 6281 | -0.15994 | 0.066673 | 0.32702 | -0.12233 | 0.75607 | 0.20508 | 0.048948 | 0.31685 | -0.14274 | 0.10418
| 6282 | -0.13357 | -0.3681 | 0.88731 | 0.4272 | -0.43582 | 0.52408 | 0.31407 | 0.10585 | -0.59245 | 0.086819
| 6283 | 0.29665 | 0.26047 | -0.15035 | 0.075825 | -0.16292 | -0.26959 | -0.40746 | -0.24893 | -0.36243 | -0.25254
| 6284 | 0.05899 | -0.72233 | -0.44818 | 0.0060684 | -0.0077803 | -0.21763 | 0.59368 | -0.2343 | -0.62384 | 0.62277
| 6285 | 0.41528 | 0.16316 | -0.12245 | -0.35108 | -0.17714 | -0.069785 | 0.16807 | -0.10139 | -0.09132 | -0.35727
| 6286 | -0.19272 | -0.57374 | 0.1646 | 0.00095045 | -0.021276 | -0.10028 | -0.2995 | -0.23364 | 0.0017515 | -0.00055015
| 6287 | 0.86325 | 0.33841 | 0.15306 | 0.50715 | 0.068711 | -0.71382 | -0.11903 | 0.13797 | -0.65839 | -0.6319
| 6288 | -0.37239 | -0.23915 | 0.19396 | 0.068496 | 0.21763 | -0.35852 | -0.57585 | -0.55178 | 0.15756 | 0.34571
| 6289 | -0.01486 | 0.47038 | 0.069677 | 0.44313 | 0.081033 | -0.22456 | -0.35572 | 0.059202 | -0.56034 | -0.050948
| 6290 | 0.11124 | -0.69227 | 0.59122 | -0.39494 | -0.14613 | 0.74603 | 0.24099 | 0.64829 | 0.69553 | 0.52682
| 6291 | 0.030412 | 0.41716 | -0.064318 | 0.67458 | 0.3951 | -0.64014 | -0.80584 | 0.39992 | 0.40376 | -0.34114
| 6292 | -0.39082 | -0.65229 | 0.39082 | 0.23678 | 0.68172 | -0.28439 | -0.08234 | -0.3951 | 0.13983 | 0.2711
| 6293 | -0.85823 | -0.36952 | 0.21317 | -0.40679 | 0.54142 | 0.020051 | -0.17229 | -0.071399 | -0.072692 | -0.12564
| 6294 | 0.57093 | 0.12085 | 0.010404 | -0.26631 | -0.03 | -0.21789 | 0.44277 | 0.1353 | 0.051053 | 0.24867
| 6295 | -0.0067729 | -0.3214 | 0.32169 | 0.10328 | 0.018012 | -0.45585 | -0.40949 | -0.46605 | 0.10094 | -0.41596
| 6296 | 0.15673 | -0.0866 | -0.32435 | -0.75 | -0.056549 | -0.15165 | -0.30682 | -0.48318 | -0.7839 | 0.37815
| 6297 | 0.252 | -0.074959 | -0.15578 | 0.48396 | -0.16844 | -0.43334 | -0.68743 | -0.4117 | 0.15661 | -0.17084
| 6298 | 0.097614 | 0.53621 | 0.47417 | 0.91574 | 0.21981 | 0.065816 | -0.19161 | 0.11949 | -0.42947 | 0.059202
| 6299 | 0.39263 | 0.46868 | -0.60795 | 0.15224 | 0.21139 | -0.26481 | 0.43724 | 0.2377 | -0.41613 | -0.044019
| 6300 | -0.42233 | -0.41085 | -0.30986 | 0.20508 | -0.22071 | 0.72197 | -0.19694 | 0.45695 | 0.3005 | -0.25643
| 6301 | -0.79 | -0.47971 | -0.0043595 | -0.46718 | -0.5721 | 0.39263 | 0.20697 | 0.16952 | 0.22741 | -0.5264
| 6302 | -0.34923 | -0.025885 | 0.024346 | -0.072476 | 0.32806 | -0.037036 | 0.24217 | 0.48532 | 0.25067 | 0.54426
| 6303 | 0.35015 | 0.18348 | 0.24721 | -0.39329 | -0.62731 | 0.54054 | 0.23026 | 0.50594 | 0.11383 | 0.012832
| 6304 | -0.43991 | -0.52303 | 0.030825 | -0.62517 | 0.65316 | -0.23325 | -0.11349 | -0.63627 | 0.11972 | 0.0068736
| 6305 | 0.083103 | 0.037451 | 0.087366 | -0.36494 | 0.55694 | 0.13104 | 0.10418 | -0.017198 | -0.71875 | -0.0080827
| 6306 | 0.40679 | 0.073663 | -0.32628 | -0.25616 | -0.27014 | 0.52576 | -0.38429 | -0.44837 | 0.11202 | -0.015774
| 6307 | -0.15012 | 0.59171 | -0.26986 | -0.52767 | 0.236 | 0.061118 | 0.32672 | -0.12222 | 0.13253 | -0.40477
| 6308 | -0.34754 | -0.65576 | -0.14953 | -0.35448 | -0.099722 | 0.051475 | -0.2711 | -0.40729 | 0.71804 | -0.49631
| 6309 | -0.09518 | 0.55156 | -0.088682 | 0.63986 | -0.092641 | 0.018318 | 0.051897 | -0.0050628 | 0.30021 | -0.0018517
| 6310 | 0.0053644 | 0.27343 | -0.22315 | 0.40831 | -0.45475 | -0.91574 | 0.11056 | 0.11858 | -0.46028 | 0.22883
| 6311 | -0.20269 | 0.10753 | 0.23705 | 0.22058 | -0.27771 | -0.75363 | -0.57893 | -0.25576 | -0.30639 | -0.53535
| 6312 | 0.79239 | 0.16042 | -0.12188 | 0.11598 | 0.1323 | 0.15626 | 0.04538 | 0.13115 | -0.013542 | -0.076799
| 6313 | -0.56057 | 0.14111 | 0.27509 | -0.67766 | 0.51616 | 0.02281 | 0.86036 | -0.55627 | 0.24046 | -0.088792
| 6314 | -0.24814 | 0.75607 | 0.15484 | -0.055172 | -0.34296 | -0.37606 | -0.14929 | 0.36573 | 0.00055015 | 0.19136
| 6315 | -0.68903 | -0.1752 | 0.13092 | 0.060266 | 0.72742 | 0.20609 | -0.06197 | 0.099056 | 0.16484 | -0.39263
| 6316 | -0.20144 | 0.56977 | -0.27371 | -0.76527 | 0.87958 | 0.024859 | 0.08978 | -0.54033 | 0.39016 | 0.18043
| 6317 | 0.14578 | -0.32762 | 0.63931 | 0.38755 | -0.061224 | 0.099278 | -0.20672 | -0.17193 | 0.06165 | 0.3759
| 6318 | -0.09839 | -0.045484 | 0.62946 | -0.047372 | 0.6044 | -0.43299 | 0.35541 | 0.60088 | -0.086381 | 0.23286
| 6319 | -0.55943 | -0.28285 | 0.35603 | 0.48493 | -0.20432 | -0.38121 | -0.352 | -0.04099 | -0.29014 | -0.33404
| 6320 | -0.012528 | 0.084413 | -0.61077 | -0.26645 | -0.3038 | -0.25441 | 0.058034 | -0.53686 | -0.33254 | 0.52177
| 6321 | -0.04381 | -0.8454 | 0.077558 | -0.43176 | 0.45255 | 0.30971 | -0.053586 | -0.54251 | 0.16856 | -0.38575
| 6322 | -0.042764 | -0.19408 | 0.51389 | 0.48863 | -0.80843 | 0.336 | -0.11745 | 0.015876 | -0.079077 | 0.6852
| 6323 | 0.45548 | -0.26986 | -0.69784 | -0.30855 | -0.028043 | 0.51389 | 0.31261 | -0.77395 | -0.00025003 | -0.14812
| 6324 | -0.56676 | -0.51102 | 0.31261 | -0.57093 | 0.64097 | 0.22353 | -0.25966 | 0.4981 | 0.56838 | -0.10451
| 6325 | -0.43706 | -0.13161 | -0.1118 | 0.15899 | 0.72269 | -0.29 | 0.148 | 0.74135 | -0.16256 | 0.014252
| 6326 | -0.5412 | 0.70352 | 0.65985 | 0.55514 | -0.073663 | 0.51082 | -0.6338 | -0.15448 | -0.33045 | -0.012832
| 6327 | 0.12176 | -0.29879 | -0.080163 | 0.10284 | -0.08343 | 0.22263 | 0.09198 | 0.24349 | -0.63737 | -0.45493
| 6328 | -0.79727 | 0.0076795 | -0.28705 | -0.28621 | -0.10529 | 0.66849 | 0.33404 | 0.1688 | -0.39312 | 0.067101
| 6329 | -0.73373 | -0.10697 | -0.60063 | -0.034236 | -0.015267 | 0.2512 | 0.45219 | -0.1044 | 0.019541 | 0.2081
| 6330 | 0.086819 | 0.41871 | 0.48318 | -0.54911 | -0.11135 | -0.011213 | 0.55424 | -0.57585 | 0.22818 | -0.071722
| 6331 | 0.46943 | 0.16543 | 0.27938 | 0.18544 | -0.14122 | -0.11315 | 0.073879 | -0.10809 | -0.73981 | -0.36102
| 6332 | -0.54492 | 0.56308 | 0.0041586 | -0.11824 | 0.63875 | 0.19049 | 0.6118 | -0.32866 | -0.66758 | -0.14601
| 6333 | 0.53513 | 0.54712 | -0.45091 | -0.65605 | -0.26454 | 0.54514 | 0.2377 | -0.22019 | -0.088902 | -0.25616
| 6334 | -0.25629 | 0.25966 | 0.048107 | 0.17145 | -0.28495 | -0.24429 | -0.37526 | 0.38315 | -0.24349 | 0.017198
| 6335 | -0.2948 | 0.033408 | -0.017605 | -0.68743 | -0.069785 | -0.23195 | -0.69422 | -0.1204 | -0.39842 | 0.009899
| 6336 | -0.19471 | 0.43458 | 0.44493 | -0.14695 | 0.0091922 | 0.17302 | -0.77131 | 0.0080827 | 0.17556 | -0.65373
| 6337 | 0.051791 | -0.10585 | -0.078425 | -0.38755 | 0.09 | 0.58467 | 0.5141 | -0.7816 | 0.15543 | -0.63271
| 6338 | -0.078534 | -0.32376 | -0.034858 | 0.32569 | -0.7508 | -0.49731 | -0.66281 | 0.37895 | -0.41768 | -0.11214
| 6339 | 0.22767 | -0.74485 | -0.44027 | -0.21827 | 0.85067 | 0.51802 | 0.51802 | 0.48512 | 0.06293 | -0.35262
| 6340 | -0.56537 | 0.41802 | -0.25482 | 0.75938 | -0.38153 | -0.28035 | 0.028455 | 0.60643 | -0.13901 | -0.70386
| 6341 | 0.67798 | 0.55312 | 0.1072 | -0.31949 | 0.49039 | -0.037555 | -0.40042 | 0.32332 | -0.34862 | -0.36984
| 6342 | -0.2823 | 0.13046 | -0.17145 | -0.14788 | -0.32361 | 0.25602 | -0.8821 | 0.064639 | -0.45273 | -0.35977
| 6343 | 0.14601 | -0.79239 | -0.29085 | -0.21177 | -0.61568 | -0.12622 | -0.064318 | -0.37079 | 0.4046 | 0.64801
| 6344 | -0.063357 | -0.076366 | -0.57562 | 0.08234 | 0.23338 | -0.12713 | 0.10217 | 0.22315 | -0.57468 | -0.18324
| 6345 | -0.11248 | 0.79384 | 0.90356 | -0.3148 | 0.6852 | -0.028352 | -0.33329 | -0.30279 | -0.16759 | 0.046952
| 6346 | -0.39246 | 0.082776 | 0.55739 | -0.63875 | 0.33404 | -0.12553 | 0.35448 | 0.66608 | -0.032891 | 0.071722
| 6347 | 0.28607 | 0.66638 | 0.67704 | 0.21917 | -0.12541 | -0.29907 | 0.20207 | -0.62013 | -0.28397 | -0.11824
| 6348 | -0.28761 | 0.6697 | 0.41854 | -0.27096 | 0.17193 | 0.3864 | 0.32643 | -0.22663 | 0.64014 | -0.78763
| 6349 | 0.40848 | 0.080598 | 0.23888 | -0.69292 | -0.24297 | 0.42895 | -0.14566 | -0.30826 | 0.37574 | -0.12028
| 6350 | 0.35123 | 0.43564 | -0.52703 | 0.4417 | 0.11938 | -0.24535 | 0.3759 | -0.032684 | 0.63408 | -0.26183
| 6351 | -0.24336 | -0.16651 | 0.35899 | 0.27757 | 0.47665 | 0.042242 | 0.15602 | -0.17157 | -0.24112 | 0.77528
| 6352 | -0.20257 | 0.048422 | 0.47531 | -0.3116 | -0.50857 | -0.048002 | 0.60516 | 0.18043 | -0.05158 | 0.81265
| 6353 | 0.41459 | 0.074959 | 0.075825 | 0.20294 | 0.39875 | -0.74329 | -0.56354 | 0.40159 | -0.35649 | 0.55335
| 6354 | -0.43884 | 0.60188 | 0.22689 | -0.2809 | 0.30538 | -0.022708 | 0.57964 | -0.042869 | 0.21955 | 0.31963
| 6355 | -0.0017515 | 0.33314 | -0.030722 | -0.56491 | 0.021379 | -0.4801 | -0.30394 | 0.51225 | 0.10061 | -0.61542
| 6356 | -0.63627 | 0.095954 | -0.21623 | -0.27799 | -0.38494 | -0.65722 | -0.27951 | 0.12051 | 0.057185 | -0.064212
| 6357 | 0.19994 | -0.18092 | -0.18312 | -0.064532 | 0.72963 | -0.30466 | 0.65373 | 0.88909 | -0.63299 | -0.039844
| 6358 | 0.21432 | 0.044751 | 0.33359 | 0.33705 | -0.071399 | -0.59714 | -0.50331 | -0.62463 | 0.95 | 0.7184
| 6359 | 0.41034 | -0.34372 | -0.036517 | 0.15733 | 0.45347 | -0.21584 | -0.15047 | -0.15436 | 0.50634 | -0.030928
| 6360 | -0.61882 | -0.55672 | 0.0039578 | 0.040469 | 0.29637 | 0.94255 | -0.21789 | -0.23875 | 0.14742 | 0.66489
| 6361 | 0.51348 | 0.17241 | -0.8422 | -0.052952 | 0.52115 | 0.017198 | 0.2689 | -0.57633 | -0.016791 | -0.19794
| 6362 | 0.47779 | -0.12599 | -0.11101 | -0.11191 | -0.47607 | -0.17483 | -0.20119 | 0.27192 | 0.030516 | 0.31875
| 6363 | -0.12828 | 0.27 | -0.02794 | -0.1513 | -0.19322 | -0.53171 | -0.78763 | 0.59024 | -0.52198 | -0.11462
| 6364 | 0.55943 | -0.37207 | 0.20169 | 0.39411 | 0.79579 | 0.34357 | 0.3956 | 0.55044 | -0.51906 | 0.041303
| 6365 | 0.42459 | -0.47856 | 0.011516 | 0.49731 | -0.11304 | -0.29807 | -0.62437 | -0.19346 | 0.61751 | 0.11101
| 6366 | -0.26386 | -0.13994 | 0.13023 | 0.38934 | 0.24349 | -0.14379 | -0.019031 | -0.26115 | -0.43053 | -0.46344
| 6367 | -0.55178 | 0.25401 | 0.61026 | 0.37414 | -0.32287 | -0.50452 | 0.12131 | -0.40865 | -0.070861 | -0.52408
| 6368 | 0.19408 | -0.053903 | -0.55223 | 0.3743 | 0.69227 | -0.030103 | -0.026809 | -0.71277 | -0.39395 | 0.28104
| 6369 | -0.53385 | 0.64042 | -0.1546 | -0.026604 | 0.57303 | 0.11034 | 0.4997 | 0.41905 | 0.39543 | 0.51082
| 6370 | -0.29694 | -0.44565 | -0.0026535 | 0.21444 | -0.048002 | -0.49671 | 0.43795 | 0.35046 | -0.44529 | -0.040156
| 6371 | -0.02189 | 0.012731 | 0.49118 | 0.034754 | 0.00065021 | 0.079837 | 0.09099 | 0.4078 | -0.0076795 | 0.80125
| 6372 | -0.13219 | -0.052213 | 0.31816 | -0.72414 | 0.52429 | 0.1694 | 0.54823 | 0.35339 | -0.58612 | -0.76399
| 6373 | -0.28202 | 0.77087 | 0.18471 | -0.26945 | 0.37734 | 0.46232 | -0.62463 | 0.023732 | -0.25227 | -0.57116
| 6374 | -0.31349 | -0.17374 | 0.10473 | -0.64153 | -0.026296 | 0.46158 | 0.15555 | 0.35386 | 0.15626 | 0.40443
| 6375 | -0.22909 | 0.68016 | -0.46381 | -0.34954 | -0.31 | -0.41596 | 0.063144 | 0.40966 | 0.16711 | 0.058034
| 6376 | -0.25885 | -0.32509 | 0.15377 | -0.15401 | -0.44063 | 0.1375 | -0.15484 | -0.24204 | -0.55 | -0.2924
| 6377 | -0.1706 | 0.048107 | -0.54316 | -0.12966 | 0.70487 | 0.33164 | 0.38543 | 0.06197 | 0.56102 | 0.21177
| 6378 | -0.75363 | 0.72523 | 0.63271 | 0.015978 | -0.32643 | -0.2508 | 0.56171 | 0.57515 | 0.23731 | 0.56977
| 6379 | 0.19906 | -0.09198 | -0.24853 | -0.436 | -0.13415 | 0.044961 | 0.046113 | -0.30696 | -0.25939 | 0.48629
| 6380 | 0.56814 | 0.45273 | -0.16603 | -0.27027 | 0.27014 | -0.20144 | -0.61568 | -0.056231 | -0.047477 | 0.66015
| 6381 | -0.31451 | 0.24469 | 0.18914 | -0.095401 | 0.43795 | 0.012528 | 0.064639 | 5.0001e-05 | -0.55807 | 0.072261
| 6382 | 0.34923 | 0.35743 | -0.31568 | -0.15958 | 0.2816 | -0.15047 | 0.0017515 | -0.51906 | 0.49256 | -0.73599
| 6383 | 0.042242 | -0.46213 | -0.047162 | -0.15543 | 0.47531 | 0.018522 | 0.071399 | -0.84412 | 0.044542 | 0.27481
| 6384 | 0.26454 | -0.5013 | 0.30797 | 0.84094 | 0.09011 | 0.41613 | -0.23836 | -0.029897 | 0.16185 | -0.034236
| 6385 | -0.3923 | -0.1546 | 0.17714 | -0.3357 | 0.45769 | -0.12908 | 0.088902 | -0.41374 | -0.21878 | 0.10978
| 6386 | 0.49295 | -0.32821 | 0.030309 | -0.0728 | -0.16771 | 0.4117 | -0.34159 | 0.10832 | -0.48746 | -0.14648
| 6387 | 0.32628 | -0.35867 | 0.44529 | 0.61856 | -0.18128 | 0.19645 | 0.55312 | -0.40628 | -0.044856 | 0.61699
| 6388 | -0.18397 | 0.13057 | -0.46906 | 0.37686 | -0.81372 | 0.53794 | -0.56745 | -0.43229 | -0.23351 | -0.24947
| 6389 | 0.11654 | -0.33555 | 0.3425 | 0.37783 | 0.23993 | -0.042033 | -0.58951 | 0.23312 | 0.61777 | -0.019133
| 6390 | 0.036621 | 0.20609 | -0.6578 | -0.11394 | -0.20735 | 0.54098 | 0.24522 | 0.24575 | 0.39296 | -0.87311
| 6391 | 0.5283 | 0.63517 | 0.0046609 | 0.71946 | 0.21381 | 0.12931 | 0.14402 | -0.28481 | 0.0022525 | 0.27453
| 6392 | 0.26291 | 0.084085 | 0.41323 | 0.2431 | -0.51307 | -0.49059 | -0.37207 | 0.4553 | 0.12805 | -0.69652
| 6393 | 0.09154 | 0.61026 | 0.048633 | 0.41102 | -0.028764 | -0.29879 | -0.80791 | 0.21878 | 0.19074 | -0.36921
| 6394 | -0.38755 | 0.93144 | 0.032477 | 0.264 | 0.56125 | 0.33479 | -0.075716 | -0.00075028 | 0.35618 | -0.11112
| 6395 | 0.26727 | 0.28202 | 0.90566 | 0.12977 | -0.5224 | 0.096175 | -0.47952 | 0.60821 | -0.536 | 0.17848
| 6396 | 0.33164 | 0.81972 | 0.39411 | 0.5172 | 0.38348 | 0.66429 | 0.2234 | 0.50311 | 0.031031 | -0.075284
| 6397 | 0.35634 | 0.59614 | 0.051159 | 0.31568 | 0.3629 | -0.20899 | -0.26604 | 0.23195 | 0.35479 | 0.82196
| 6398 | 0.10708 | 0.66849 | 0.21994 | 0.37767 | 0.74174 | -0.068496 | 0.38771 | -0.29424 | -0.30711 | 0.15828
| 6399 | 0.63326 | -0.30928 | -0.44098 | -0.61856 | -0.031135 | -0.43795 | 0.73411 | 0.71627 | -0.37414 | -0.4979
| 6400 | 0.37302 | 0.15804 | -0.10854 | -0.65985 | -0.15318 | 0.25267 | 0.046533 | 0.15756 | -0.059202 | 0.062717
| 6401 | 0.48144 | -0.29424 | -0.64602 | 0.90566 | -0.065923 | -0.20722 | -0.49771 | -0.020459 | -0.13704 | -0.040782
| 6402 | 0.028558 | 0.011921 | -0.10641 | 0.40915 | -0.40494 | 0.38902 | -0.17036 | 0.032167 | 0.065067 | -0.32762
| 6403 | -0.047162 | 0.41991 | -0.74407 | 0.22199 | 0.30581 | -0.78576 | 0.087366 | -0.4307 | 0.76315 | -0.45991
| 6404 | 0.16484 | -0.074203 | 0.1926 | 0.61077 | 0.098834 | -0.38494 | 0.1389 | -0.24151 | -0.52513 | -0.19944
| 6405 | 0.54734 | 0.15911 | -0.48202 | 0.58976 | -0.68047 | -0.17326 | 0.76484 | -0.21025 | 0.15519 | -0.82422
| 6406 | -0.42546 | 0.36321 | 0.26577 | 0.34083 | 0.28174 | 0.088792 | 0.30682 | 0.22276 | -0.28509 | 0.36321
| 6407 | 0.68393 | -0.63135 | 0.058246 | 0.32509 | -0.17157 | 0.36055 | -0.23026 | 0.86252 | 0.6634 | 0.68016
| 6408 | -0.68583 | 0.17909 | 0.27027 | 0.027118 | -0.37032 | 0.18901 | -0.016893 | 0.66103 | 0.050211 | 0.070645
| 6409 | 0.58563 | -0.59196 | 0.59147 | 0.063677 | -0.14566 | -0.14765 | 0.34114 | 0.69032 | 0.12006 | -0.95641
| 6410 | -0.08343 | 0.54076 | -0.013947 | 0.43405 | -0.06603 | -0.038387 | -0.15661 | -0.18889 | 0.66789 | -0.48415
| 6411 | 0.055701 | 0.26223 | -0.53816 | -0.53881 | 0.54076 | 0.83845 | 0.49512 | 0.56583 | -0.48202 | -0.32687
| 6412 | 0.53171 | -0.1323 | -0.05348 | 0.53213 | 0.29566 | 0.52031 | -0.47837 | 0.14601 | 0.2377 | 0.74801
| 6413 | 0.50796 | -0.050526 | 0.00035006 | -0.23169 | 0.37783 | 0.61154 | 0.020459 | 0.77707 | -0.23665 | 0.76063
| 6414 | -0.76569 | -0.067852 | 0.74682 | -0.089341 | -0.07183 | -0.33886 | -0.26196 | -0.15342 | -0.30812 | 0.023936
| 6415 | 0.34023 | 0.46849 | -0.16663 | -0.047267 | -0.48357 | 0.0013509 | -0.43387 | -0.49711 | 0.35046 | 0.46046
| 6416 | 0.15661 | 0.38706 | 0.20269 | -0.52177 | 0.19049 | 0.26413 | -0.26495 | -0.19247 | -0.047897 | -0.89656
| 6417 | -0.51102 | 0.61154 | 0.056231 | 0.41957 | 0.063677 | 0.1277 | -0.32702 | -0.35308 | -0.24867 | -0.37048
| 6418 | -0.71104 | -0.1382 | -0.48882 | -0.10989 | -0.082776 | -0.82593 | -0.066887 | -0.73037 | 0.43529 | 0.024551
| 6419 | -0.06496 | -0.49631 | -0.12828 | -0.10418 | -0.055172 | 0.12188 | 0.82139 | -0.75979 | 0.1127 | 0.14847
| 6420 | -0.060905 | 0.41494 | 0.35139 | -0.31261 | -0.79288 | 0.51472 | 0.22045 | -0.1005 | 0.059947 | -0.43777
| 6421 | -0.01 | -0.26278 | -0.43352 | 0.25764 | 0.49473 | 0.0068736 | -0.58781 | -0.41511 | -0.71769 | -0.37239
| 6422 | 0.72852 | 0.0022525 | 0.34862 | -0.30093 | -0.087257 | -0.28789 | -0.31058 | 0.014657 | 0.059202 | -0.16916
| 6423 | 0.010101 | 0.31465 | 0.22019 | -0.30826 | 0.45658 | 0.21203 | 0.26877 | 0.74643 | 0.79628 | -0.059202
| 6424 | 0.18557 | 0.0025533 | 0.53881 | -0.039219 | 0.49177 | -0.77483 | 0.21419 | -0.053586 | -0.020663 | -0.63217
| 6425 | -0.079294 | 0.50432 | 0.24086 | -0.38089 | -0.76527 | -0.13565 | -0.82708 | -0.33539 | -0.67335 | -0.14076
| 6426 | -0.33404 | -0.3005 | -0.46418 | -0.41102 | 0.49078 | -0.47322 | -0.052846 | -0.54316 | 0.36668 | -0.085834
| 6427 | 0.20094 | 0.27412 | 0.081251 | -0.20319 | 0.17763 | 0.46605 | 0.1841 | -0.24283 | 0.057609 | -0.089012
| 6428 | -0.5143 | -0.15828 | 0.2492 | -0.47665 | -0.55785 | -0.39329 | 0.19099 | 0.30812 | 0.1072 | 0.33977
| 6429 | -0.41785 | 0.05549 | -0.24667 | -0.2907 | -0.88126 | -0.11484 | 0.73074 | -0.51534 | -0.78858 | 0.74485
| 6430 | 0.58203 | 0.30913 | -0.0020521 | -0.3363 | -0.085834 | -0.60491 | -0.017809 | 0.60013 | 0.15295 | 0.42982
| 6431 | 0.19247 | -0.63903 | -0.52052 | 0.49671 | 0.14753 | -0.17605 | -0.73675 | -0.136 | 0.056337 | 0.71035
| 6432 | 0.044333 | 0.45898 | -0.10261 | 0.12805 | 0.59171 | 0.61672 | -0.41751 | 0.7512 | 0.3242 | 0.65985
| 6433 | -0.43635 | -0.12473 | 0.17994 | -0.42009 | 0.058353 | -0.3167 | -0.45824 | 0.42095 | -0.13426 | 0.21802
| 6434 | 0.57893 | 0.066137 | 0.12028 | -0.1814 | -0.68552 | 0.59614 | -0.14262 | 0.01344 | -0.25361 | 0.065495
| 6435 | 0.14894 | 0.16976 | -0.76827 | -0.43884 | -0.16567 | 0.83177 | -0.41102 | -0.48668 | 0.30639 | 0.252
| 6436 | 0.82252 | 0.50654 | 0.73713 | 0.48824 | 0.24947 | 0.53492 | 0.78763 | -0.55379 | 0.40343 | -0.64886
| 6437 | -0.028146 | -0.47189 | -0.19782 | 0.14017 | -0.82708 | -0.068818 | 0.52513 | -0.028867 | 0.64153 | 0.81053
| 6438 | 0.1269 | 0.18092 | -0.10989 | 0.38299 | -0.56907 | -0.25804 | 0.45164 | -0.94615 | 0.056231 | 0.46943
| 6439 | 0.37976 | -0.62013 | 0.25388 | 0.063891 | -0.2755 | -0.35836 | -0.19956 | -0.17145 | -0.056655 | -0.43458
| 6440 | -0.55022 | -0.61934 | -0.042764 | 0.67 | -0.23117 | -0.055913 | 0.58395 | 0.71035 | -0.50492 | -0.13553
| 6441 | -0.19037 | 0.073124 | -0.27785 | -0.10496 | 0.21712 | -0.1153 | 0.56745 | -0.26359 | 0.52303 | 0.36227
| 6442 | 0.39809 | -0.51225 | -0.35743 | -0.031031 | 0.52471 | 0.19458 | -0.24588 | 0.89464 | -0.33134 | -0.0030547
| 6443 | 0.70897 | -0.74682 | 0.40075 | -0.54867 | -0.55111 | -0.73223 | 0.31451 | 0.076366 | 0.38902 | -0.21802
| 6444 | -0.32539 | 0.21432 | -0.24442 | -0.46381 | -0.64265 | -0.51554 | 0.40108 | -0.1957 | 0.50412 | -0.21968
| 6445 | -0.79384 | -0.64914 | -0.078859 | -0.055701 | -0.060266 | 0.25697 | 0.21051 | 0.25993 | -0.050842 | 0.40932
| 6446 | 0.25791 | -0.073016 | -0.47856 | 0.49691 | -0.30222 | -0.025269 | -0.13461 | -0.041094 | -0.41545 | -0.17302
| 6447 | -0.28021 | 0.40058 | 0.37927 | 0.35961 | 0.60846 | -0.63163 | 0.26481 | -0.41922 | -0.6939 | 0.77395
| 6448 | 0.14624 | 0.83237 | -0.026501 | 0.47398 | 0.08343 | 0.4163 | 0.11926 | -0.50432 | -0.3961 | -0.34708
| 6449 | -0.58927 | -0.042033 | -0.20044 | -0.95877 | -0.029794 | 0.50311 | -0.23351 | -0.037555 | -0.15354 | -0.40578
| 6450 | -0.37462 | 0.34923 | -0.15875 | 0.086053 | -0.1277 | -0.034443 | -0.14122 | 0.037555 | 0.099278 | 0.012225
| 6451 | 0.85474 | -0.20684 | 0.84348 | 0.51948 | 0.48106 | -0.0036567 | 0.17133 | 0.18092 | 0.097947 | 0.37286
| 6452 | 0.084959 | -0.20106 | 0.22922 | -0.11034 | -0.088792 | 0.32747 | 0.35231 | -0.1034 | -0.42703 | 0.52094
| 6453 | -0.10619 | 0.043601 | -0.28916 | 0.2941 | -0.51906 | -0.71487 | 0.086709 | -0.041407 | -0.74722 | -0.098279
| 6454 | -0.27578 | 0.11609 | 0.46549 | 0.13646 | -0.10854 | 0.57609 | 0.23901 | 0.33705 | 0.32376 | -0.14414
| 6455 | 0.8467 | -0.31802 | -0.14706 | 0.45695 | 0.37927 | -0.076691 | 0.43176 | 0.50492 | -0.097503 | -0.093854
| 6456 | -0.45677 | 0.62865 | 0.12874 | -0.20672 | -0.21368 | -0.2356 | 0.11248 | 0.83907 | 0.22857 | 0.47113
| 6457 | 0.83721 | -0.31116 | 0.21521 | 0.11451 | 0.56954 | 0.4828 | 0.93144 | 0.14988 | 0.15448 | 0.5021
| 6458 | 0.05 | -0.34754 | 0.16436 | 0.20646 | -0.082885 | 0.52788 | -0.76784 | 0.3607 | -0.088024 | -0.17229
| 6459 | -0.22469 | -0.14624 | 0.36243 | 0.18336 | -0.11983 | 0.55559 | 0.021379 | 0.019133 | 0.30179 | 0.2598
| 6460 | 0.48338 | 0.66698 | -0.0056661 | -0.44457 | -0.52894 | -0.8747 | 0.27813 | -0.71035 | -0.28271 | -0.79048
| 6461 | -0.32658 | -0.53149 | -0.055384 | -0.51082 | 0.054537 | -0.69917 | 0.11045 | -0.14788 | -0.11034 | -0.16747
| 6462 | -0.22754 | 0.30279 | -0.2161 | 0.58708 | 0.19334 | -0.38804 | -0.22225 | 0.8422 | 0.035479 | 0.012123
| 6463 | -0.038699 | 0.71946 | 0.35649 | 0.092311 | 0.014556 | 0.0051633 | 0.034858 | -0.20207 | -0.45219 | 0.025372
| 6464 | -0.37 | -0.38429 | 0.36652 | 0.73866 | 0.14742 | 0.26278 | 0.34433 | -0.63 | -0.37992 | 0.12679
| 6465 | 0.06678 | 0.078642 | 0.30928 | -0.14402 | -0.17836 | -0.36384 | 0.2567 | -0.063891 | -0.30928 | 0.41136
| 6466 | 0.20144 | -0.42947 | 0.63135 | -0.31131 | -0.55989 | -0.12176 | 0.31699 | -0.68968 | 0.33015 | -0.51328
| 6467 | 0.55022 | 0.10541 | 0.85752 | 0.47208 | 0.020255 | -0.21623 | 0.094406 | -0.0037571 | -0.42251 | -0.14274
| 6468 | -0.22173 | 0.54273 | 0.14624 | -0.053374 | 0.35572 | 0.71382 | -0.10876 | -0.28845 | 0.32169 | -0.42737
| 6469 | 0.22148 | -0.57703 | -0.20975 | -0.015673 | 0.22444 | 0.30423 | -0.17933 | -0.15012 | -0.092862 | -0.11124
| 6470 | -0.32258 | 0.33917 | -0.74722 | 0.51678 | -0.14437 | -0.60013 | -0.2948 | 0.70725 | -0.019541 | -0.13253
| 6471 | 0.073231 | 0.17374 | 0.15354 | -0.27771 | 0.56791 | 0.22961 | -0.27274 | -0.64489 | -0.78344 | -0.11779
| 6472 | 0.2689 | -0.28579 | 0.2042 | 0.19334 | -0.0081835 | -0.15685 | -0.26061 | 0.12302 | 0.75526 | -0.075933
| 6473 | 0.54867 | 0.73561 | 0.76957 | -0.10239 | -0.47303 | 0.34969 | -0.13577 | 0.4828 | 0.50959 | -0.54382
| 6474 | -0.33314 | -0.39576 | 0.44134 | -0.30495 | -0.11507 | 0.77528 | -0.83783 | 0.82308 | 0.2504 | -0.53881
| 6475 | -0.57397 | -0.1237 | 0.83059 | 0.15638 | 0.1786 | -0.29608 | 0.23378 | -0.31509 | -0.38722 | 0.43035
| 6476 | -0.34816 | 0.080054 | -0.64153 | -0.31232 | -0.0049623 | 0.20735 | -0.41187 | 0.26196 | 0.23026 | -0.21152
| 6477 | -0.081251 | -0.067959 | 0.025064 | 0.49493 | 0.57609 | 0.28649 | 0.13449 | -0.4272 | -0.66074 | -0.42476
| 6478 | -0.55424 | 0.15035 | 0.48106 | 0.13403 | 0.61777 | -0.24469 | -0.19981 | 0.4668 | -0.20181 | -0.1952
| 6479 | 0.12484 | -0.37 | -0.28607 | -0.56354 | -0.41733 | 0.39659 | -0.17957 | 0.46362 | -0.69817 | -0.63435
| 6480 | -0.42043 | -0.30841 | 0.70217 | -0.40477 | 0.09143 | 0.30437 | 0.60491 | -0.038179 | 0.58467 | 0.49731
| 6481 | -0.3038 | 0.40175 | -0.25147 | 0.70386 | 0.20144 | -0.60719 | 0.55717 | -0.77087 | -0.35092 | 0.22935
| 6482 | 0.39148 | 0.13704 | -0.082885 | 0.20558 | 0.013136 | -0.14297 | -0.37366 | -0.099389 | -0.29551 | 0.35883
| 6483 | -0.12313 | 0.16988 | 0.47607 | 0.55853 | -0.41613 | -0.12393 | 0.25912 | 0.17872 | -0.62865 | 0.52894
| 6484 | 0.3087 | 0.20659 | -0.095843 | -0.51389 | 0.19856 | -0.48726 | -0.051475 | 0.37847 | 0.5959 | 0.16976
| 6485 | -0.56354 | -0.01182 | 0.20344 | 0.26686 | -0.042555 | -0.43158 | -0.9089 | -0.51225 | 0.2924 | 0.32628
| 6486 | 0.56262 | 0.57327 | -0.40242 | -0.094738 | -0.76612 | -0.68679 | 0.34525 | -0.11745 | 0.076691 | -0.89851
| 6487 | 0.152 | -0.51472 | 0.57397 | -0.67891 | 0.020868 | 0.18692 | -0.5001 | -0.66638 | 0.29155 | 0.70251
| 6488 | 0.10596 | 0.34938 | 0.029073 | -0.30986 | -0.17265 | -0.68871 | 0.68615 | 0.61283 | 0.36227 | -0.21254
| 6489 | 0.29523 | -0.31261 | 0.73866 | -0.75403 | -0.18446 | 0.55335 | -0.72305 | -0.07183 | -0.040052 | -0.038283
| 6490 | 0.30394 | 0.021787 | -0.79384 | 0.13288 | -0.14355 | -0.88467 | -0.17544 | -0.04381 | -0.041929 | -0.42337
| 6491 | -0.3651 | -0.06261 | 0.41871 | -0.74801 | -0.68968 | 0.38706 | -0.29127 | 0.10273 | -0.22469 | 0.84348
| 6492 | 0.35541 | 0.5201 | -0.59614 | 0.14076 | 0.80947 | -0.15531 | -0.4542 | -0.52261 | 0.095401 | 0.26373
| 6493 | -0.6852 | 0.15578 | 0.063677 | 0.29254 | -0.013947 | 0.20659 | 0.011011 | 0.080054 | -0.65345 | 0.18889
| 6494 | 0.0057666 | -0.20094 | 0.035894 | 0.19408 | -0.12977 | -0.45511 | -0.54889 | 0.14076 | -0.6786 | 0.77218
| 6495 | -0.67304 | -0.19869 | -0.14076 | -0.20332 | -0.25067 | 0.27882 | -0.028043 | 0.19744 | -0.028867 | -0.11938
| 6496 | -0.099722 | 0.057079 | 0.19037 | 0.37064 | -0.16066 | -0.47741 | -0.49295 | -0.67984 | -0.036309 | -0.90253
| 6497 | 0.43564 | 0.13276 | 0.046638 | -0.0079819 | 0.30855 | -0.46718 | 0.37143 | -0.13403 | -0.020868 | 0.51061
| 6498 | 0.021992 | 0.41153 | 0.59343 | 0.34479 | -0.41477 | 0.83417 | 0.050316 | -0.11067 | -0.078317 | -0.46418
| 6499 | 0.62463 | 0.6546 | -0.36857 | -0.6952 | 0.1063 | -0.1072 | -0.62919 | -0.91938 | -0.05814 | -0.27896
| 6500 | 0.79678 | 0.14367 | -0.10843 | 0.85405 | -0.63326 | 0.17411 | 0.020255 | -0.13913 | -0.2602 | 0.20546
| 6501 | -0.20659 | -0.28551 | -0.24231 | -0.14636 | 0.13253 | -0.14414 | 0.35339 | 0.30064 | 0.90566 | -0.21866
| 6502 | -0.35216 | 0.28887 | 0.62865 | 0.087586 | -0.2326 | -0.1546 | -0.30581 | -0.23928 | 0.34266 | -0.013136
| 6503 | -0.20194 | 0.11248 | -0.44295 | -0.52957 | 0.25791 | 0.50857 | 0.35169 | 0.42633 | -0.47933 | 0.085834
| 6504 | 0.79288 | 0.10117 | -0.72889 | 0.073447 | -0.058034 | 0.2377 | -0.33645 | -0.51102 | 0.19707 | -0.051686
| 6505 | 0.59813 | 0.17957 | -0.18226 | -0.082558 | 0.41459 | 0.91 | 0.264 | 0.19359 | -0.071938 | 0.047687
| 6506 | 0.48222 | -0.56583 | -0.37143 | -0.4078 | -0.22961 | 0.40075 | -0.09044 | -0.11835 | 0.59491 | -0.29708
| 6507 | -0.17957 | 0.14578 | -0.30552 | -0.067852 | -0.056867 | -0.36778 | -0.21687 | -0.18988 | 0.80635 | 0.074203
| 6508 | -0.42877 | 0.073016 | -0.1253 | -0.10094 | -0.19769 | -0.56034 | 0.13739 | -0.15153 | -0.93917 | -0.18655
| 6509 | -0.34068 | -0.28621 | -0.032684 | 0.15614 | -0.27426 | 0.044333 | 0.23836 | -0.4983 | -0.10809 | 0.39626
| 6510 | 0.043182 | -0.33329 | 0.61128 | 0.10608 | -0.38543 | 0.42633 | -0.64042 | -0.21661 | 0.14169 | -0.042764
| 6511 | -0.81372 | -0.41034 | -0.067208 | -0.47038 | 0.37048 | -0.12793 | 0.71277 | -0.61309 | 0.48551 | 0.38738
| 6512 | -0.30841 | -0.22611 | 0.29893 | 0.87311 | -0.25549 | -0.19508 | -0.058777 | -0.30036 | 0.3186 | -0.077666
| 6513 | -0.25966 | -0.073231 | -0.89464 | -0.82766 | -0.080163 | 0.21317 | -0.16856 | -0.32613 | -0.18951 | -0.59763
| 6514 | 0.088902 | -0.17241 | -0.062077 | 0.028043 | 0.056337 | -0.31247 | 0.1926 | -0.030825 | -0.076799 | -0.028043
| 6515 | -0.070323 | -0.32051 | -0.58781 | 0.061544 | -0.16892 | 0.065388 | -0.35649 | -0.3087 | 0.02897 | -0.56148
| 6516 | -0.56722 | 0.14589 | 0.63108 | 0.79336 | -0.36921 | 0.060798 | -0.3375 | -0.66608 | 0.45127 | -0.014556
| 6517 | -0.081904 | 0.23665 | 0.16066 | 0.30639 | -0.72596 | -0.59122 | 0.12097 | 0.78297 | -0.68903 | 0.013339
| 6518 | -0.68298 | -0.83721 | 0.10955 | -0.26604 | 0.25953 | -0.31465 | 0.43423 | -0.17605 | 0.76913 | 0.63572
| 6519 | -0.016384 | -0.60872 | 0.51554 | -0.17982 | -0.20282 | -0.44601 | 0.68235 | -0.18446 | -0.43088 | 0.082231
| 6520 | 0.23104 | -0.34281 | -0.47113 | -0.55537 | 0.028764 | 0.53256 | -0.30093 | -0.57327 | -0.28873 | 0.060585
| 6521 | 0.83118 | 0.22715 | 0.023424 | 0.72889 | 0.054326 | -0.51844 | -0.33615 | 0.21559 | 0.41204 | 0.26904
| 6522 | -0.4588 | -0.014049 | -0.28481 | -0.31728 | -0.4392 | -0.031238 | -0.12622 | 0.068603 | -0.16185 | 0.19124
| 6523 | 0.074959 | 0.39 | 0.025885 | 0.42633 | -0.94084 | -0.56814 | 0.31436 | 0.3303 | 0.22948 | 0.6755
| 6524 | -0.21051 | 0.1432 | -0.1229 | 0.24033 | -0.49177 | -0.37542 | 0.5199 | -0.5005 | 0.41905 | -0.24628
| 6525 | -0.60415 | -0.37815 | -0.14262 | -0.083212 | -0.14496 | -0.073663 | -0.46028 | -0.22482 | -0.8454 | 0.60188
| 6526 | 0.096285 | -0.072369 | 0.13588 | -0.086162 | 0.62517 | -0.32925 | -0.48941 | 0.080598 | 0.54185 | 0.26877
| 6527 | -0.26481 | 0.21955 | -0.16783 | -0.35 | -0.098058 | 0.39576 | 0.17471 | 0.31655 | 0.23836 | -0.7504
| 6528 | 0.86923 | 0.47645 | 0.29594 | 0.61908 | -0.41136 | -0.33434 | 0.87793 | 0.37318 | 0.65229 | -0.52052
| 6529 | 0.0044599 | -0.26522 | 0.52534 | 0.25027 | 0.81807 | -0.1323 | -0.17556 | 0.71522 | 0.36368 | -0.47076
| 6530 | -0.38251 | 0.74603 | 0.43352 | 0.12576 | -0.41391 | 0.079402 | -0.69194 | 0.017096 | 0.50371 | -0.11417
| 6531 | 0.1825 | -0.73448 | 0.064639 | -0.084959 | -0.23156 | -0.28901 | -0.17362 | 0.11824 | 0.16759 | -0.33284
| 6532 | -0.21584 | -0.62704 | 0.29085 | 0.23967 | -0.96683 | -0.15153 | 0.11281 | 0.75282 | 0.72125 | 0.7623
| 6533 | -0.13971 | -0.38299 | -0.49098 | -0.73713 | 0.35867 | -0.066994 | -0.5019 | -0.67396 | 0.75566 | 0.66133
| 6534 | 0.25723 | -0.016181 | 0.62892 | 0.26645 | 0.19346 | 0.70897 | 0.68016 | -0.053163 | -0.026296 | 0.34862
| 6535 | -0.035168 | -0.60465 | 0.91815 | -0.26672 | -0.19 | 0.4989 | -0.59664 | 0.73149 | -0.25 | 0.07962
| 6536 | 0.24827 | 0.67735 | -0.31509 | -0.35789 | -0.042764 | 0.67704 | 0.1884 | 0.42668 | 0.48648 | 0.26836
| 6537 | 0.31949 | 0.048002 | 0.096617 | 0.58733 | 0.087257 | -0.46624 | -0.81588 | 0.44349 | 0.016588 | 0.60719
| 6538 | 0.29197 | -0.60516 | -0.81106 | -0.23156 | 0.2042 | -0.20747 | 0.31276 | -0.13959 | 0.6149 | 0.48164
| 6539 | 0.62784 | -0.60668 | -0.46887 | 0.14029 | -0.058565 | -0.014049 | -0.76484 | 0.0040582 | -0.42372 | -0.33555
| 6540 | 0.25187 | -0.37239 | 0.28509 | -0.78763 | 0.14683 | 0.26713 | 0.039219 | -0.56722 | 0.26536 | -0.29325
| 6541 | -0.27192 | 0.47265 | -0.62277 | -0.59838 | -0.57 | 0.19037 | 0.35961 | -0.096396 | 0.36023 | -0.055807
| 6542 | -0.06197 | -0.18214 | 0.13739 | -0.77306 | 0.33045 | -0.021174 | 0.14953 | 0.055172 | 0.21674 | 0.10072
| 6543 | -0.1603 | 0.60038 | 0.42285 | -0.89091 | 0.45714 | -0.1179 | 0.55989 | -0.39378 | 0.33194 | -0.31772
| 6544 | -0.50878 | 0.054326 | -0.027529 | 0.27357 | -0.58083 | -0.040469 | 0.077558 | 0.041616 | 0.83357 | 0.75566
| 6545 | -0.70017 | 0.12519 | -0.075608 | -0.12702 | -0.53256 | -0.074419 | -0.27357 | 0.30451 | 0.025474 | 0.10865
| 6546 | 0.063784 | -0.14215 | 0.1196 | -0.12576 | 0.77044 | 0.11101 | 0.2598 | -0.073663 | 0.60339 | -0.68047
| 6547 | -0.52576 | -0.24178 | 0.44674 | 0.56861 | -0.4194 | 0.17982 | -0.8618 | 0.24165 | 0.58515 | 0.58636
| 6548 | -0.61568 | 0.16089 | -0.71173 | 0.13704 | 0.73111 | 0.18963 | -0.73111 | -0.62865 | 0.2571 | -0.6265
| 6549 | -0.56011 | -0.58927 | -0.24654 | 0.1952 | 0.12336 | -0.18704 | 0.15697 | -0.42199 | 0.58419 | -0.26877
| 6550 | -0.23652 | -0.00085036 | 0.11677 | -0.8422 | -0.61077 | 0.12747 | 0.023424 | 0.52492 | 0.75938 | -0.10473
| 6551 | -0.54668 | 0.77262 | -0.7488 | -0.54076 | 0.1694 | -0.61751 | -0.22444 | -0.043601 | 0.38105 | 0.15212
| 6552 | 0.35758 | -0.29438 | -0.078642 | -0.12119 | -0.38608 | 0.18434 | -0.67891 | 0.02897 | -0.21712 | 0.11586
| 6553 | -0.50573 | -0.13704 | -0.60415 | 0.13207 | 0.21904 | -0.27868 | -0.38251 | 0.49098 | -0.63545 | -0.79191
| 6554 | -0.22495 | 0.1109 | 0.52177 | -0.09187 | 0.2427 | -0.78952 | 0.66459 | -0.85201 | -0.71946 | 0.1814
| 6555 | -0.26101 | 0.77439 | -0.033512 | 0.28453 | -0.49394 | -0.42043 | -0.24244 | -0.35046 | -0.22238 | -0.73675
| 6556 | 0.22392 | 0.2512 | -0.059096 | -0.026912 | 0.39859 | 0.31524 | 0.63462 | 0.21381 | -0.85823 | 0.3662
| 6557 | 0.53556 | -0.54978 | -0.36984 | 0.44116 | 0.70285 | 0.5954 | 0.2995 | -0.080598 | -0.63627 | -0.6546
| 6558 | 0.09077 | 0.0922 | -0.34693 | 0.055066 | -0.33886 | 0.052424 | -0.75813 | 0.14425 | -0.46981 | -0.5143
| 6559 | -0.16352 | 0.23875 | 0.0728 | 0.26345 | 0.033615 | -0.31392 | -0.43317 | 0.018623 | 0.012528 | -0.65316
| 6560 | 0.44134 | 0.79482 | 0.24323 | -0.44063 | 0.61257 | 0.49572 | 0.75485 | -0.00015001 | 0.057716 | 0.20722
| 6561 | -0.65839 | -0.097836 | -0.24323 | 0.42982 | -0.72852 | -0.083976 | 0.024449 | -0.78206 | 0.88126 | 0.39792
| 6562 | -0.17823 | 0.17447 | -0.10585 | 0.78297 | 0.97 | -0.4286 | 0.14041 | -0.44313 | -0.31407 | 0.48961
| 6563 | -0.047477 | 0.70386 | 0.07 | 0.21533 | 0.078859 | -0.25495 | -0.17909 | 0.41545 | 0.0066723 | 0.097393
| 6564 | 0.050211 | 0.63299 | -0.5098 | -0.23915 | 0.23065 | -0.61542 | -0.6257 | 0.76655 | 0.68903 | -0.054008
| 6565 | -0.47322 | 0.38543 | -0.014759 | -0.69685 | -0.06016 | 0.050526 | -0.41511 | -0.31655 | 0.61077 | -0.60013
| 6566 | -0.30451 | 0.41905 | -0.61725 | 0.12587 | -0.64687 | 0.92319 | -0.29056 | -0.18827 | 0.057928 | 0.28761
| 6567 | -0.44134 | 0.021174 | 0.35914 | -0.0051633 | 0.095843 | -0.072369 | 0.016486 | -0.39082 | 0.76188 | 0.28146
| 6568 | 0.027529 | 0.085287 | -0.43795 | 0.28565 | -0.32184 | 0.38543 | 0.62677 | -0.43105 | -0.91938 | 0.15982
| 6569 | -0.10753 | 0.11473 | -0.73675 | 0.17568 | -0.13843 | -0.56838 | -0.19074 | -0.30495 | 0.047687 | -0.15756
| 6570 | -0.68141 | 0.14496 | -0.66399 | -0.57303 | -0.43546 | 0.28007 | 0.10239 | 0.027837 | -0.0072765 | 0.69065
| 6571 | -0.020459 | -0.049684 | -0.17096 | 0.39246 | -0.62357 | 0.36589 | 0.22961 | -0.25401 | 0.48726 | 0.007075
| 6572 | 0.070323 | -0.72018 | -0.024962 | 0.59122 | -0.35448 | -0.14988 | -0.47703 | -0.19421 | 0.58131 | 0.10217
| 6573 | -0.39942 | 0.051897 | 0.033408 | 0.25053 | -0.43141 | 0.2689 | 0.060479 | -0.036413 | -0.19247 | -0.075825
| 6574 | -0.67182 | 0.48961 | 0.42337 | 0.67366 | 0.68016 | -0.049789 | -0.90461 | 0.029691 | 0.26088 | -0.50898
| 6575 | 0.094959 | -0.35556 | -0.41357 | 0.5245 | -0.75363 | -0.23665 | 0.44764 | 0.079511 | 0.023015 | 0.74603
| 6576 | 0.71347 | -0.028352 | 0.20181 | -0.67152 | 0.16137 | -0.37638 | 0.20609 | -0.043914 | -0.46493 | -0.69194
| 6577 | -0.082994 | -0.23691 | -0.86472 | -0.40175 | -0.047267 | 0.43688 | -0.46065 | 0.19894 | -0.56699 | 0.47246
| 6578 | 0.0019519 | 0.14624 | 0.43653 | -0.72018 | -0.21533 | 0.60491 | 0.18055 | 0.027632 | 0.28607 | 0.0021523
| 6579 | -0.31553 | 0.068067 | 0.3419 | -0.25374 | -0.049895 | 0.10596 | 0.69324 | -0.59838 | -0.14824 | 0.023117
| 6580 | -0.09044 | -0.5007 | 0.43387 | 0.12256 | -0.22302 | 0.23547 | -0.24033 | 0.54251 | 0.32747 | 0.024859
| 6581 | -0.44188 | 0.05899 | 0.66074 | 0.20407 | 0.65634 | -0.097725 | -0.26727 | 0.0922 | 0.61856 | 0.18275
| 6582 | -0.37767 | -0.3312 | 0.042347 | 0.080489 | -0.17702 | 0.43229 | 0.25508 | 0.20219 | -0.59714 | 0.27619
| 6583 | -0.35587 | -0.55335 | 0.12541 | 0.06325 | 0.20432 | 0.59664 | -0.34311 | 0.45164 | -0.91 | -0.4564
| 6584 | 0.24204 | -0.43018 | -0.094296 | 0.5005 | -0.54033 | -0.3451 | 0.25993 | 0.70897 | 0.4983 | -0.55111
| 6585 | -0.11938 | -0.45603 | 0.25441 | 0.77439 | 0.81265 | -0.47455 | 0.71173 | 0.23718 | 0.37863 | -0.67891
| 6586 | -0.4991 | 0.076041 | -0.097725 | -0.1323 | -0.40209 | -0.67798 | -0.068711 | -0.48863 | 0.31392 | -0.066673
| 6587 | 0.41255 | -0.015978 | -0.099389 | 0.14145 | 0.7042 | -0.42947 | -0.82766 | -0.24933 | -0.26822 | 0.75241
| 6588 | 0.61051 | 0.69065 | 0.82883 | -0.76442 | 0.54033 | -0.48202 | -0.11847 | -0.64265 | 0.47493 | 0.29993
| 6589 | 0.078751 | -0.37064 | -0.1153 | 0.042242 | 0.48668 | 0.056125 | 0.27192 | -0.12989 | -0.16783 | -0.14111
| 6590 | 0.35774 | 0.45127 | -0.2816 | 0.9219 | -0.054537 | -0.28958 | -0.45714 | -0.46718 | -0.078534 | 0.37638
| 6591 | 0.38673 | -0.055913 | -0.3294 | -0.62145 | 0.31014 | -0.84031 | -0.10518 | -0.12359 | 0.40225 | -0.35231
| 6592 | 0.33645 | 0.29367 | -0.19944 | 0.10195 | -0.27343 | -0.048948 | -0.65258 | -0.18079 | -0.25321 | 0.30021
| 6593 | -0.22071 | -0.59147 | 0.42633 | -0.9089 | -0.11214 | 0.58854 | -0.11169 | 0.44098 | -0.27979 | 0.59147
| 6594 | -0.054114 | 0.57421 | -0.32702 | -0.10921 | 0.62092 | -0.44692 | -0.051369 | -0.084631 | 0.24853 | -0.44692
| 6595 | -0.31363 | -0.22199 | -0.46083 | 0.38105 | -0.69097 | -0.39213 | -0.10462 | 0.32539 | -0.19471 | -0.23915
| 6596 | -0.32851 | -0.099056 | -0.01263 | 0.26074 | 0.76399 | 0.67984 | -0.27882 | 0.9272 | -0.57 | -0.19099
| 6597 | -0.47 | 0.80379 | 0.12496 | -0.69162 | 0.10764 | 0.28188 | -0.49731 | -0.33766 | 0.44547 | 0.13392
| 6598 | -0.024039 | 0.70184 | 0.67396 | -0.52282 | 0.067745 | -0.085068 | 0.44818 | -0.11079 | -0.1136 | -0.27
| 6599 | -0.19062 | -0.19223 | 0.61516 | -0.62224 | 0.1136 | -0.048527 | 0.24469 | 0.038179 | -0.06165 | -0.4286
| 6600 | -0.21203 | 0.34205 | -0.41871 | -0.16221 | 0.41888 | -0.12267 | 0.35852 | 0.13473 | -0.68968 | -0.12805
| 6601 | -0.41819 | 0.56468 | 0.58903 | 0.39775 | -0.14847 | -0.16603 | -0.65172 | 0.39875 | 0.28076 | -0.66758
| 6602 | -0.10776 | 0.5224 | 0.61309 | -0.23613 | -0.42009 | -0.059734 | -0.12507 | -0.55989 | -0.71698 | 0.43582
| 6603 | 0.71522 | 0.28271 | 0.038595 | -0.23 | -0.67427 | -0.5021 | -0.10843 | 0.1389 | 0.60213 | 0.85134
| 6604 | 0.17411 | 0.47246 | -0.24191 | -0.39676 | -0.60795 | 0.041407 | 0.078208 | -0.94084 | -0.28216 | -0.20886
| 6605 | -0.77262 | -0.33075 | 0.40527 | -0.67829 | 0.6578 | 0.044856 | -0.28369 | 0.47246 | -0.52387 | 0.11236
| 6606 | -0.20937 | -0.050211 | 0.18544 | -0.89753 | -0.12656 | 0.91225 | 0.88295 | -0.31934 | -0.09839 | 0.089561
| 6607 | -0.89656 | 0.14122 | -0.045484 | -0.53043 | -0.077016 | -0.64801 | -0.73186 | 0.36905 | -0.24721 | 0.044437
| 6608 | 0.14379 | 0.037867 | -0.50898 | 0.38706 | -0.3838 | 0.045484 | 0.80226 | 0.29736 | -0.22702 | 0.37494
| 6609 | 0.62357 | 0.18508 | -0.61934 | 0.12119 | -0.29325 | 0.050737 | 0.11915 | -0.31334 | -0.29127 | -0.47837
| 6610 | -0.008486 | 0.08136 | -0.13983 | -0.47607 | 0.82651 | 0.50432 | -0.87311 | -0.077232 | 0.12507 | -0.5412
| 6611 | -0.39576 | 0.25885 | 0.0035563 | -0.0060684 | -0.74603 | 0.063464 | -0.2516 | -0.20483 | -0.29622 | -0.74643
| 6612 | 0.064212 | -0.24046 | -0.97 | -0.061011 | -0.30423 | -0.21712 | 0.2265 | -0.89183 | -0.16484 | -0.64971
| 6613 | 0.76146 | 0.18889 | -0.27453 | 0.14472 | -0.30136 | 0.16795 | 0.19533 | -0.53085 | -0.46269 | -0.24827
| 6614 | -0.14076 | -0.21533 | -0.59988 | -0.55875 | 0.10619 | -0.53535 | 0.44638 | -0.2924 | 0.40008 | -0.11507
| 6615 | -0.50918 | 0.0012508 | -0.044542 | 0.2816 | -0.36826 | -0.22676 | -0.085178 | 0.009798 | 0.23587 | -0.065816
| 6616 | -0.85067 | 0.058459 | -0.10395 | -0.4985 | 0.2492 | 0.25227 | 0.7496 | -0.17811 | -0.56722 | -0.65576
| 6617 | -0.04538 | 0.12828 | 0.74019 | -0.12622 | -0.5707 | -0.15626 | 0.38429 | -0.55067 | -0.63435 | -0.55335
| 6618 | 0.024039 | -0.75282 | 0.20937 | -0.21802 | 0.19645 | -0.55514 | -0.14041 | -0.23705 | -0.23928 | -0.029279
| 6619 | 0.6985 | -0.0086877 | 0.16543 | 0.0032553 | 0.73713 | 0.022299 | 0.23469 | -0.030619 | -0.24442 | -0.44134
| 6620 | -0.85613 | 0.53085 | -0.36337 | -0.53 | 0.32539 | 0.025577 | 0.061011 | 0.16328 | 0.5922 | 0.28397
| 6621 | 0.40713 | 0.40932 | -0.076691 | -0.53946 | 0.19844 | -0.35062 | 0.5174 | -0.66044 | 0.65489 | 0.2975
| 6622 | -0.7496 | -0.033201 | -0.4588 | 0.16101 | -0.39279 | -0.09055 | 0.85893 | -0.19632 | -0.38332 | 0.69292
| 6623 | 0.79727 | 0.32554 | 0.21152 | 0.21495 | -0.23744 | 0.043496 | 0.20131 | 0.13681 | 0.036413 | 0.59714
| 6624 | 0.0027538 | 0.2184 | 0.41477 | -0.1439 | -0.64857 | -0.033718 | 0.23783 | -0.30595 | 0.44403 | 0.21533
| 6625 | 0.18569 | -0.073879 | -0.092311 | -0.083976 | -0.053058 | 0.80843 | -0.18055 | -0.061224 | 0.46009 | -0.62013
| 6626 | -0.61283 | -0.24681 | 0.19819 | 0.09044 | -0.19025 | 0.32007 | -0.03974 | 0.43281 | 0.13901 | -0.25845
| 6627 | 0.24641 | -0.017198 | 0.64518 | -0.63462 | -0.25254 | -0.58203 | -0.79727 | -0.25845 | -0.24667 | 0.3956
| 6628 | -0.31509 | -0.028146 | 0.15875 | 0.81534 | -0.41408 | -0.59988 | -0.11079 | 0.075716 | -0.50695 | -0.25818
| 6629 | -0.29893 | 0.25629 | 0.24947 | -0.66399 | 0.33389 | 0.54382 | 0.22637 | -0.3956 | 0.073987 | -0.66489
| 6630 | 0.10944 | 0.19099 | 0.093082 | -0.37606 | -0.61934 | 0.22754 | -0.6319 | 0.44475 | 0.26767 | 0.73942
| 6631 | 0.24323 | 0.63244 | -0.097282 | -0.34877 | -0.46493 | 0.50331 | 0.28677 | -0.72852 | 0.55762 | -0.57562
| 6632 | 0.82883 | 0.49532 | -0.23378 | -0.023527 | -0.2512 | 0.28859 | 0.15354 | 0.38967 | -0.020459 | -0.5959
| 6633 | 0.17109 | -0.13634 | 0.13219 | -0.35031 | -0.22379 | 0.5102 | -0.085506 | 0.63081 | -0.41085 | 0.096617
| 6634 | 0.027735 | 0.4041 | 0.35712 | 0.1628 | -0.1127 | -0.60974 | 0.062183 | -0.19819 | 0.11824 | -0.43511
| 6635 | -0.5283 | -0.042869 | -0.80176 | 0.25107 | -0.0030547 | 0.31392 | 0.152 | -0.17823 | 0.27426 | -0.65663
| 6636 | -0.66489 | 0.35556 | -0.63353 | -0.22444 | -0.15626 | 0.73261 | 0.070645 | 0.075608 | 0.07183 | -0.25804
| 6637 | -0.45273 | -0.10228 | 0.54889 | -0.072045 | -0.22573 | -0.44421 | -0.19136 | -0.27412 | 0.59938 | 0.17471
| 6638 | 0.11383 | -0.082994 | 0.66939 | -0.1277 | 0.73298 | -0.65927 | -0.36196 | 0.8467 | 0.2948 | -0.5866
| 6639 | -0.5001 | 0.65258 | -0.38396 | -0.65431 | 0.044123 | 0.66939 | -0.26822 | 0.69097 | -0.30696 | 0.78952
| 6640 | 0.79095 | -0.32806 | 0.058034 | 0.0045604 | -0.5199 | 0.52303 | -0.50452 | -0.7839 | 0.49236 | -0.0063703
| 6641 | -0.048948 | 0.061864 | -0.11575 | 0.35899 | 0.43582 | -0.61361 | 0.35789 | -0.67213 | -0.73637 | 0.55
| 6642 | -0.59392 | 0.053058 | 0.15259 | -0.59 | -0.59888 | 0.09022 | 0.12885 | 0.046218 | -0.15958 | 0.17483
| 6643 | -0.17775 | -0.43334 | 0.080924 | 0.6257 | 0.38902 | -0.44403 | -0.42877 | 0.030103 | -0.52576 | -0.013947
| 6644 | 0.98268 | -0.70691 | 0.26849 | 0.17836 | -0.552 | -0.79336 | 0.86621 | -0.27467 | 0.22431 | -0.3309
| 6645 | 0.13346 | -0.32066 | 0.51492 | -0.033822 | -0.067101 | -0.095511 | 0.34617 | 0.59738 | -0.11994 | 0.13311
| 6646 | -0.37526 | 0.85337 | -0.52724 | -0.61908 | 0.16795 | 0.87631 | -0.26549 | 0.18128 | 0.49512 | 0.48902
| 6647 | 0.44206 | 0.082122 | 0.44439 | -0.26658 | -0.36841 | -0.1127 | 0.50271 | -0.22598 | -0.32821 | -0.063571
| 6648 | 0.10106 | -0.48922 | -0.72815 | -0.5098 | 0.64857 | 0.74096 | 0.37016 | -0.22096 | -0.16807 | 0.76827
| 6649 | 0.11903 | 0.28355 | -0.11473 | 0.060905 | 0.099389 | 0.21089 | -0.36937 | -0.33555 | -0.89 | 0.66281
| 6650 | 0.16952 | -0.47798 | -0.11202 | 0.42807 | 0.025167 | -0.13196 | 0.84605 | -0.3419 | -0.078208 | -0.29127
| 6651 | -0.13565 | 0.44746 | -0.18214 | -0.046323 | 0.60795 | 0.14636 | -0.38073 | -0.16627 | 0.2356 | -0.48318
| 6652 | 0.007478 | -0.0030547 | 0.46213 | 0.04172 | -0.88467 | -0.22276 | 0.36762 | -0.64181 | 0.31 | -0.12782
| 6653 | 0.28132 | 0.19086 | -0.42285 | 0.48922 | -0.11881 | -0.5883 | 0.078751 | -0.04517 | -0.10028 | -0.24138
| 6654 | 0.27716 | -0.17592 | -0.035065 | 0.0052639 | 0.35092 | 0.24099 | 0.6703 | 0.75485 | 0.41119 | 0.65201
| 6655 | 0.1005 | 0.60415 | -0.11169 | 0.22083 | 0.64014 | -0.0046609 | 0.74682 | -0.63931 | 0.30207 | 0.72926
| 6656 | -0.3681 | -0.007478 | 0.51 | -0.46737 | -0.016283 | 0.14134 | 0.17629 | 0.18324 | 0.6233 | -0.17459
| 6657 | 0.20294 | 0.46102 | 0.43193 | 0.22754 | -0.53751 | 0.49236 | -0.35603 | 0.0866 | 0.36258 | -0.2313
| 6658 | 0.67643 | -0.36841 | 0.59565 | -0.030516 | 0.095622 | -0.15614 | 0.63108 | -0.044019 | 0.11665 | -0.15507
| 6659 | -0.68172 | 0.08234 | 0.43088 | -0.33419 | 0.55739 | 0.3851 | -0.013846 | -0.3015 | -0.012934 | -0.26672
| 6660 | -0.75201 | -0.29311 | -0.09055 | -0.18238 | -0.055384 | -0.19309 | -0.44009 | 0.18988 | -0.23718 | -0.61464
| 6661 | 0.1729 | 0.27467 | -0.22896 | 0.56262 | 0.22586 | -0.31949 | 0.13173 | 0.083321 | -0.37016 | -0.86923
| 6662 | -0.48687 | 0.46213 | -0.24217 | -0.12439 | -0.23862 | -0.23 | -0.5245 | -0.26686 | -0.28007 | -0.17386
| 6663 | -0.2076 | 0.41768 | 0.21546 | -0.66429 | 0.99 | -0.49651 | -0.49751 | 0.48961 | -0.020561 | -0.11349
| 6664 | 0.085943 | 0.11067 | -0.53213 | 0.02568 | 0.22366 | -0.24336 | -0.69227 | 0.36211 | 0.25562 | 0.062503
| 6665 | 0.48726 | 0.22521 | -0.40527 | 0.3048 | 0.76357 | 0.030206 | -0.33404 | 0.21317 | 0.1852 | 0.61646
| 6666 | 0.45732 | -0.6939 | 0.18581 | -0.53107 | 0.24707 | -0.13727 | -0.29921 | -0.20307 | -0.1375 | 0.31145
| 6667 | 0.42216 | 0.044019 | -0.65722 | -0.018522 | -0.32762 | -0.33962 | -0.5283 | -0.096617 | 0.41511 | 0.32332
| 6668 | 0.050842 | 0.60063 | -0.2575 | -0.46065 | -0.38592 | -0.93 | -0.78952 | -0.38461 | -0.4993 | 0.13242
| 6669 | 0.25562 | 0.82708 | -0.3735 | -0.076907 | 0.13692 | -0.1879 | 0.71698 | -0.19969 | -0.24482 | 0.019031
| 6670 | -0.070215 | 0.2398 | 0.12747 | 0.18692 | -0.79678 | 0.50675 | 0.30523 | 0.36039 | -0.032167 | 0.37702
| 6671 | -0.51657 | -0.28901 | 0.32628 | 0.009899 | -0.37702 | -0.64209 | 0.41289 | 0.27688 | -0.12051 | -0.53729
| 6672 | -0.26645 | 0.12816 | 0.15543 | 0.015571 | 0.4286 | 0.65693 | -0.19508 | 0.13104 | 0.27647 | -0.4859
| 6673 | -0.5866 | -0.24867 | 0.48222 | -0.084522 | 0.28383 | -0.72815 | 0.60364 | -0.54142 | -0.58927 | 0.50231
| 6674 | -0.43546 | -0.33374 | -0.2052 | 0.54251 | 0.59888 | 0.3923 | -0.70897 | 0.91815 | 0.2225 | 0.25361
| 6675 | 0.015368 | -0.65956 | 0.1127 | -0.014049 | 0.43511 | 0.75855 | -0.47569 | 0.11779 | -0.45548 | 0.077232
| 6676 | -0.5656 | 0.092531 | 0.44277 | -0.23849 | 0.31116 | 0.25133 | -0.6371 | -0.74603 | 0.04266 | 0.35417
| 6677 | -0.16735 | 0.52576 | 0.05 | 0.069033 | -0.34739 | 0.5003 | -0.5866 | -0.88381 | -0.077883 | 0.20735
| 6678 | -0.11903 | -0.42615 | -0.30236 | -0.23783 | 0.53816 | -0.85823 | 0.057822 | 0.23013 | 0.073231 | 0.69586
| 6679 | 0.22987 | 0.47933 | 0.33811 | -0.066994 | -0.56537 | -0.060266 | -0.21393 | -0.19124 | 0.22148 | -0.050632
| 6680 | 0.00095045 | 0.62597 | 0.93917 | -0.0010506 | 0.29155 | 0.51927 | 0.095843 | -0.43281 | -0.19894 | -0.83
| 6681 | -0.44945 | 0.6249 | -0.11779 | 0.22909 | -0.14484 | -0.20798 | 0.17145 | -0.74407 | 0.50331 | 0.13011
| 6682 | -0.38657 | 0.15709 | 0.67829 | -0.37622 | -0.5264 | -0.40494 | 0.014657 | 0.13357 | 0.34693 | -0.17872
| 6683 | -0.57093 | -0.63682 | -0.058565 | -0.080816 | 0.17157 | 0.069033 | 0.19334 | 0.15673 | -0.53881 | -0.13704
| 6684 | 0.87077 | -0.3038 | 0.1308 | 0.35867 | -0.34571 | -0.17532 | 0.48687 | -0.75201 | -0.016994 | 0.42807
| 6685 | 0.50634 | 0.19049 | 0.09198 | -0.57633 | -0.25683 | 0.21878 | -0.32955 | 0.045065 | -0.58708 | 0.32985
| 6686 | 0.41068 | 0.41034 | -0.51041 | 0.33766 | 0.45548 | -0.026296 | -0.096839 | -0.97764 | 0.63875 | 0.075608
| 6687 | 0.13184 | -0.40746 | 0.41974 | 0.33947 | -0.64801 | -0.12063 | 0.15365 | 0.78576 | -0.51616 | -0.23
| 6688 | -0.2567 | -0.54602 | 0.8366 | 0.099056 | 0.50695 | -0.29495 | -0.11214 | -0.4799 | 0.51678 | 0.042347
| 6689 | -0.087805 | 0.12977 | 0.49751 | -0.35541 | -0.079294 | -0.1814 | -0.17641 | 0.049158 | -0.5735 | 0.29099
| 6690 | -0.68235 | 0.036828 | -0.57703 | 0.62784 | -0.45898 | -0.43564 | 0.5009 | -0.46925 | -0.58155 | 0.6786
| 6691 | 0.93597 | -0.061437 | 0.55223 | -0.16651 | 0.44764 | -0.50271 | -0.49275 | -0.49592 | -0.035583 | 0.35992
| 6692 | -0.010505 | 0.1884 | 0.45585 | 0.58395 | -0.40983 | 0.13415 | -0.10921 | 0.38056 | 0.28299 | -0.26115
| 6693 | 0.12874 | 0.050316 | -0.23888 | 0.79975 | 0.40292 | -0.05549 | 0.13023 | 0.38657 | -0.08474 | -0.12587
| 6694 | -0.17157 | 0.48241 | 0.73186 | -0.52366 | -0.061011 | -0.68425 | 0.58036 | -0.15578 | -0.28104 | 0.22844
| 6695 | 0.03 | -0.5102 | -0.12633 | 0.18606 | 0.33645 | -0.074743 | 0.78669 | 0.26672 | -0.20937 | -0.72486
| 6696 | 0.59098 | -0.31203 | -0.024859 | -0.36937 | -0.34586 | -0.24007 | -0.43035 | 0.41819 | 0.059096 | -0.63875
| 6697 | -0.10406 | -0.30207 | 0.071722 | 0.022094 | -0.8467 | -0.148 | -0.13127 | 0.08989 | 0.58251 | -0.61908
| 6698 | -0.60364 | -0.083321 | -0.026604 | -0.13092 | -0.22135 | 0.081251 | -0.34816 | -0.17278 | 0.38934 | 0.51927
| 6699 | 0.22689 | 0.51513 | 0.14157 | 0.76655 | 0.044019 | 0.71487 | -0.25535 | 0.5021 | 0.21572 | 0.78344
| 6700 | -0.3451 | 0.1921 | -0.33254 | 0.2047 | -0.26427 | -0.62304 | -0.15507 | 0.87 | -0.087476 | -0.73713
| 6701 | -0.10184 | -0.59938 | -0.25107 | 0.73524 | -0.74174 | 0.20244 | 0.068281 | -0.59913 | 0.2512 | 0.032891
| 6702 | 0.61026 | -0.36353 | 0.44009 | -0.39759 | 0.82252 | 0.52366 | -0.23338 | -0.17 | -0.51699 | 0.25616
| 6703 | -0.54646 | -0.36368 | -0.38543 | 0.33374 | 0.81159 | -0.15567 | 0.0093941 | 0.048738 | 0.31495 | -0.87712
| 6704 | 0.59738 | 0.15851 | -0.27178 | 0.43193 | -0.63765 | -0.38153 | 0.014049 | 0.56125 | 0.34678 | 0.29907
| 6705 | 0.65345 | -0.62251 | -0.27082 | -0.53385 | 0.29424 | 0.15059 | 0.20836 | 0.51307 | 0.059734 | -0.10731
| 6706 | -0.1729 | 0.087366 | -0.26061 | 0.24827 | -0.14215 | 0.014556 | -0.55559 | 0.17495 | 0.018318 | 0.47076
| 6707 | -0.085506 | -0.86771 | -0.29651 | -0.73827 | -0.31919 | 0.33389 | -0.96683 | -0.9219 | 0.46943 | 0.56676
| 6708 | -0.09198 | 0.09198 | -0.38299 | 0.48551 | -0.10753 | -0.073555 | 0.36055 | -0.013339 | 0.48435 | 0.098169
| 6709 | 0.16519 | -0.76399 | -0.51657 | -0.25939 | -0.7504 | 0.61856 | 0.26318 | 0.10731 | 0.34311 | 0.045065
| 6710 | -0.32509 | -0.27 | 0.53772 | 0.26468 | -0.38526 | -0.23247 | 0.61987 | 0.47208 | 0.46028 | 0.4857
| 6711 | -0.15555 | 0.14052 | -0.2773 | 0.49751 | 0.61725 | 0.13924 | -0.18324 | -0.19272 | 0.059628 | 0.71804
| 6712 | -0.71946 | -0.05549 | -0.59 | -0.18569 | -0.52597 | 0.22728 | -0.074311 | 0.14332 | 0.79776 | -0.02097
| 6713 | -0.22431 | 0.18618 | -0.60038 | -0.8937 | 0.11157 | -0.67 | 0.22741 | -0.31875 | 0.90461 | -0.78023
| 6714 | 0.93443 | -0.85201 | -0.11079 | -0.16543 | -0.11191 | -0.32911 | -0.15318 | 0.33524 | -0.71982 | 0.0088895
| 6715 | 0.58927 | 0.30122 | 0.36384 | 0.95641 | 0.22302 | 0.58733 | -0.7429 | 0.032064 | 0.067208 | -0.53299
| 6716 | -0.51802 | 0.11654 | 0.4206 | 0.056549 | -0.23993 | -0.25629 | 0.88731 | 0.38951 | -0.33 | 0.58347
| 6717 | -0.24442 | 0.21891 | 0.24814 | 0.34877 | 0.21127 | -0.0045604 | -0.12017 | -0.15507 | 0.31787 | 0.71487
| 6718 | -0.13242 | -0.16376 | 0.37879 | 0.14484 | 0.26959 | 0.13369 | -0.34174 | -0.44656 | -0.006169 | 0.096396
| 6719 | -0.088353 | -0.71627 | -0.82028 | 0.26061 | -0.37718 | -0.43546 | 0.16747 | 0.5735 | 0.17314 | 0.70897
| 6720 | 0.12461 | 0.27757 | 0.50271 | 0.52513 | -0.11067 | 0.16209 | 0.43866 | 0.17909 | -0.43493 | 0.15318
| 6721 | -0.53946 | -0.23364 | 0.46121 | -0.26332 | -0.83297 | 0.35556 | 0.47189 | -0.082994 | 0.16988 | -0.18397
| 6722 | -0.56814 | 0.10362 | -0.38494 | 0.047897 | -0.73298 | -0.2924 | 0.10473 | 0.05422 | 0.30567 | -0.014759
| 6723 | -0.11191 | -0.38804 | 0.33826 | -0.046533 | 0.28063 | -0.64602 | -0.019643 | 0.29879 | -0.073555 | -0.64377
| 6724 | 0.62731 | -0.14192 | 0.37734 | -0.41306 | -0.12839 | -0.564 | 0.43902 | 0.15567 | 0.84412 | -0.078642
| 6725 | 0.24681 | -0.11552 | -0.16819 | -0.24787 | -0.16042 | -0.46269 | 0.052319 | -0.58323 | -0.62517 | -0.17362
| 6726 | 0.3074 | -0.35649 | 0.24402 | 0.27744 | 0.054855 | -0.59024 | 0.53816 | -0.62838 | 0.029279 | 0.22353
| 6727 | -0.35945 | 0.59813 | 0.79875 | -0.35293 | 0.06603 | 0.10083 | -0.19334 | -0.38008 | 0.43334 | -0.23875
| 6728 | -0.13797 | -0.42493 | 0.10206 | -0.14099 | -0.46269 | -0.54098 | -0.035065 | 0.38299 | 0.1338 | 0.11733
| 6729 | 0.23915 | -0.035272 | -0.1533 | -0.28607 | -0.0027538 | -0.2476 | 0.2784 | -0.6697 | -0.19645 | -0.37606
| 6730 | 0.033305 | 0.032684 | 0.69488 | -0.75607 | -0.014353 | -0.024346 | -0.15153 | 0.024756 | 0.20924 | 0.34693
| 6731 | -0.35324 | -0.2659 | -0.1338 | -0.66789 | 0.64405 | -0.080489 | -0.15935 | 0.53859 | -0.23521 | 0.27578
| 6732 | -0.41221 | -0.49493 | -0.88042 | 0.39527 | -0.49137 | 0.13959 | 0.29141 | -0.81 | 0.9078 | 0.14671
| 6733 | -0.69983 | 0.39494 | 0.84412 | -0.27055 | 0.05814 | 0.2488 | 0.17265 | 0.3735 | 0.13276 | 0.8995
| 6734 | 0.14332 | -0.67458 | 0.15436 | 0.55402 | -0.2161 | 0.083976 | 0.42493 | 0.00095045 | -0.0015512 | -0.43334
| 6735 | 0.24191 | 0.27357 | -0.44152 | -0.54316 | 0.15721 | 0.28817 | 0.42129 | 0.86621 | 0.28369 | 0.14636
| 6736 | -0.78763 | -0.59614 | 0.64293 | -0.64433 | -0.53171 | -0.51513 | -0.82308 | 0.047792 | 0.10563 | 0.96394
| 6737 | 0.73373 | 0.52809 | -0.94432 | 0.78206 | -0.025269 | 0.066673 | -0.58347 | 0.010707 | -0.43211 | -0.5735
| 6738 | 0.44152 | -0.18238 | -0.19458 | 0.74564 | 0.49 | -0.3454 | -0.28299 | -0.1921 | -0.33932 | -0.47057
| 6739 | -0.12989 | -0.7245 | -0.64886 | 0.40042 | -0.13207 | 0.24601 | 0.43105 | -0.16316 | 0.7184 | 0.38461
| 6740 | 0.1418 | -0.012225 | 0.58083 | 0.83477 | -0.81588 | 0.40511 | 0.72596 | 0.28789 | -0.031444 | -0.21279
| 6741 | -0.10787 | -0.36762 | -0.077666 | -0.84933 | -0.43671 | -0.37175 | 0.68743 | 0.84867 | 0.15389 | 0.036517
| 6742 | 0.22831 | -0.035168 | 0.048843 | -0.2184 | -0.13242 | -0.072692 | -0.1957 | 0.34023 | -0.80075 | 0.44224
| 6743 | 0.42737 | -0.047057 | 0.24707 | 0.04517 | 0.61829 | -0.18446 | 0.58251 | 0.12702 | 0.27302 | -0.32096
| 6744 | 0.20106 | 0.64546 | 0.11462 | 0.47914 | 0.43493 | 0.41648 | -0.43724 | -0.13092 | 0.38056 | -0.037347
| 6745 | -0.040782 | 0.36841 | -0.56034 | -0.040782 | -0.12176 | 0.62039 | 0.14437 | 0.075392 | 0.24455 | 0.1204
| 6746 | -0.42598 | 0.71312 | 0.0015512 | -0.20407 | 0.26074 | 0.21904 | 0.20785 | 0.18385 | 0.90253 | -0.40949
| 6747 | 0.56907 | 0.40628 | 0.035998 | 0.30351 | 0.41991 | -0.41068 | -0.2287 | 0.55921 | 0.48922 | 0.016689
| 6748 | -0.6265 | -0.41768 | -0.51823 | 0.33735 | -0.50918 | -0.33917 | -0.075825 | 0.68456 | 0.63792 | -0.38299
| 6749 | -0.086928 | 0.25777 | 0.38869 | -0.025167 | 0.80791 | -0.096507 | -0.63848 | 0.23652 | -0.0011507 | 0.36652
| 6750 | 0.30308 | -0.051053 | -0.55178 | -0.44045 | 0.72305 | -0.15094 | 0.65316 | -0.18594 | -0.058034 | -0.5529
| 6751 | -0.91456 | -0.39958 | 0.5141 | -0.69553 | 0.21674 | -0.038075 | 0.48396 | -0.014454 | -0.55424 | 0.14344
| 6752 | -0.074635 | 0.38967 | 0.63627 | -0.76021 | 0.70352 | 0.24204 | 0.026912 | -0.36778 | -0.57538 | -0.19906
| 6753 | -0.24455 | -0.08649 | -0.61464 | -0.31582 | -0.71875 | -0.035583 | -0.36368 | -0.10764 | -0.21165 | -0.4337
| 6754 | -0.32066 | 0.085943 | 0.12736 | 0.76913 | 0.23875 | -0.12051 | 0.28733 | -0.76315 | 0.35821 | -0.2995
| 6755 | 0.13276 | 0.44224 | 0.32155 | 0.041094 | 0.19 | 0.19732 | -0.35401 | -0.28257 | -0.13461 | -0.3372
| 6756 | 0.042764 | -0.43706 | -0.11688 | 0.69685 | -0.065602 | -0.076799 | -0.23613 | 0.9219 | -0.17994 | 0.71557
| 6757 | -0.44403 | 0.42459 | -0.13611 | -0.093854 | -0.080707 | -0.1315 | 0.42026 | -0.32287 | -0.60188 | -0.52936
| 6758 | -0.62357 | 0.081686 | 0.46512 | -0.042033 | -0.053269 | 0.53578 | -0.064212 | -0.31029 | -0.086709 | -0.47703
| 6759 | -0.12897 | -0.26359 | 0.63682 | -0.13542 | -0.54778 | 0.25616 | 0.2524 | 0.38267 | 0.38202 | -0.19161
| 6760 | -0.41528 | 0.47094 | 0.18877 | -0.1706 | 0.47094 | -0.39477 | -0.24323 | -0.1758 | -0.31699 | 0.27385
| 6761 | 0.16042 | 0.53021 | 0.56491 | 0.18778 | 0.085943 | 0.19533 | -0.48241 | 0.74019 | 0.20044 | 0.066244
| 6762 | 0.75485 | -0.0015512 | 0.12051 | 0.86771 | 0.25831 | -0.12897 | 0.26196 | -0.16771 | -0.42528 | -0.26836
| 6763 | -0.70862 | 0.42372 | 0.49098 | -0.47189 | 0.19906 | 0.26264 | -0.35077 | 0.013947 | 0.60694 | -0.25067
| 6764 | -0.20131 | -0.11926 | -0.48726 | -0.9245 | 0.24827 | 0.30193 | 0.35324 | 0.18864 | 0.5007 | 0.27137
| 6765 | 0.04538 | 0.20546 | -0.64857 | 0.16364 | -0.41323 | -0.3189 | -0.12199 | 0.21165 | 0.1005 | 0.58395
| 6766 | -0.065495 | -0.41408 | -0.23862 | -0.24867 | 0.14239 | 0.20886 | 0.48318 | 0.35977 | -0.81212 | -0.051791
| 6767 | -0.5172 | -0.29622 | 0.10742 | 0.8043 | -0.35743 | 0.1162 | -0.28439 | 0.11315 | 0.67304 | 0.24231
| 6768 | 0.30538 | -0.06678 | -0.058034 | 0.73149 | 0.52873 | -0.047582 | -0.6985 | 0.13832 | -0.29452 | -0.51948
| 6769 | 0.2184 | 0.072584 | -0.013238 | 0.39759 | -0.084631 | 0.30064 | -0.77887 | 0.20861 | 0.65258 | -0.10195
| 6770 | 0.018929 | -0.27951 | 0.4902 | 0.40477 | 0.20911 | -0.40225 | 0.34038 | 0.29807 | -0.54911 | -0.36636
| 6771 | -0.54207 | -0.70083 | 0.010505 | -0.12725 | 0.018318 | 0.64377 | 0.46587 | 0.8937 | -0.97764 | 0.075933
| 6772 | -0.11383 | 0.61128 | -0.20848 | -0.83177 | -0.15496 | -0.21101 | -0.15744 | -0.25214 | -0.50634 | 0.63958
| 6773 | 0.0092932 | -0.17229 | -0.012022 | -0.30265 | 0.31919 | 0.10028 | 0.52703 | -0.74251 | 0.82422 | 0.23091
| 6774 | -0.43018 | -0.14355 | -0.37879 | -0.042555 | 0.6265 | -0.019847 | -0.41323 | 0.015267 | -0.73942 | 0.73866
| 6775 | 0.078425 | -0.10966 | -0.3882 | 0.73486 | 0.39082 | 0.33344 | -0.33479 | -0.18201 | -0.52471 | -0.65258
| 6776 | -0.020357 | -0.7508 | 0.14542 | -0.45972 | 0.076691 | -0.34724 | 0.10161 | 0.094406 | 0.86621 | 0.24787
| 6777 | -0.19198 | 0.83845 | 0.40814 | 0.058034 | -0.57988 | -0.00075028 | -0.27343 | 0.055384 | 0.64321 | 0.60821
| 6778 | 0.0059678 | -0.32628 | 0.23731 | 0.45567 | 0.36937 | -0.90253 | 0.39181 | 0.65057 | -0.24086 | -0.069355
| 6779 | -0.0011507 | -0.35401 | -0.12736 | -0.33705 | -0.33389 | -0.13936 | -0.1269 | 0.80584 | -0.13449 | -0.11903
| 6780 | -0.44367 | 0.094296 | 0.0054649 | 0.070645 | 0.14507 | 0.29651 | 0.2193 | -0.27027 | -0.066137 | -0.31655
| 6781 | -0.15071 | -0.70251 | -0.22792 | -0.054855 | -0.32081 | 0.3129 | -0.43938 | 0.09529 | -0.38218 | 0.49512
| 6782 | 0.10406 | -0.13507 | -0.39643 | -0.33449 | -0.42825 | 0.64772 | 0.72125 | 0.36952 | -0.033615 | 0.09198
| 6783 | 0.48785 | -0.53299 | -0.57798 | -0.81265 | -0.0023528 | -0.38234 | -0.10106 | -0.59122 | -0.47057 | 0.13484
| 6784 | 0.72125 | -0.064212 | -0.29395 | -0.4979 | -0.084959 | -0.013035 | 0.58539 | 0.065067 | 0.34985 | -0.50959
| 6785 | -0.27868 | 0.36227 | -0.13403 | 0.053374 | 0.21343 | -0.30509 | 0.56653 | 0.026604 | -0.24178 | -0.49453
| 6786 | -0.5447 | -0.31349 | -0.63958 | 0.65029 | 0.4902 | 0.29169 | 0.47818 | 0.16424 | 0.17787 | -0.18018
| 6787 | 0.30351 | -0.0085869 | 0.057291 | -0.64489 | -0.68743 | -0.051369 | -0.64097 | -0.1127 | -0.38267 | -0.29765
| 6788 | 0.11598 | -0.14835 | -0.4078 | 0.70352 | -0.44116 | 0.1338 | -0.3372 | -0.47 | 0.0755 | 0.46269
| 6789 | -0.23247 | -0.12954 | 0.76104 | -0.57988 | 0.30193 | 0.0066723 | 0.073771 | -0.34144 | -0.55559 | -0.12324
| 6790 | -0.42947 | 0.67121 | 0.35077 | 0.45219 | 0.34342 | 0.7245 | 0.61856 | 0.046113 | -0.17787 | -0.27661
| 6791 | -0.02609 | 0.25643 | -0.36747 | -0.86472 | -0.80895 | -0.16125 | -0.16795 | -0.56377 | -0.20848 | -0.085287
| 6792 | -0.0080827 | -0.43813 | -0.50675 | -0.080707 | 0.50432 | 0.87876 | -0.85134 | -0.37478 | -0.17157 | 0.094738
| 6793 | -0.72197 | 0.31816 | 0.80947 | 0.19682 | 0.31203 | -0.28663 | 0.23338 | 0.27757 | 0.77528 | 0.40679
| 6794 | -0.37895 | -0.60188 | 0.018827 | -0.41323 | -0.48882 | 0.17435 | 0.38689 | -0.56422 | -0.38137 | 0.48087
| 6795 | 0.72054 | 0.30928 | 0.061757 | 0.50412 | -0.22289 | -0.088682 | 0.025064 | -0.46906 | 0.21942 | -0.049684
| 6796 | 0.28551 | 0.38885 | -0.26863 | 0.23195 | 0.02794 | -0.23928 | 0.34023 | 0.34403 | -0.065709 | 0.31626
| 6797 | 0.45073 | 0.31378 | 0.25576 | -0.015774 | 0.10418 | -0.10843 | -0.023424 | -0.3074 | 0.65663 | -0.23286
| 6798 | -0.42095 | -0.71312 | -0.49216 | 0.1473 | 0.52851 | 0.10284 | 0.30725 | -0.035376 | 0.39709 | -0.23731
| 6799 | 0.17568 | -0.41323 | -0.68204 | -0.11654 | -0.058777 | -0.60213 | 0.21444 | 0.64631 | 0.41957 | -0.06603
| 6800 | -0.77796 | 0.065067 | 0.88126 | 0.66074 | -0.5015 | -0.36604 | 0.46381 | 0.27343 | -0.10944 | 0.7839
| 6801 | 0.17399 | -0.38526 | 0.063784 | 0.2823 | -0.50291 | -0.61961 | 0.26604 | -0.029382 | 0.39033 | -0.083976
| 6802 | -0.29822 | -0.2175 | -0.8995 | -0.16627 | 0.43334 | 0.18778 | 0.35355 | -0.24402 | -0.12507 | -0.37831
| 6803 | -0.80947 | -0.47113 | -0.14824 | 0.61516 | 0.017401 | -0.75161 | 0.59664 | -0.41272 | 0.71104 | -0.44295
| 6804 | 0.27674 | -0.45567 | -0.36368 | 0.0014511 | -0.34555 | 0.1466 | -0.34464 | -0.71242 | -0.75855 | 0.20937
| 6805 | -0.52767 | -0.56861 | -0.087257 | 0.40427 | 0.46437 | 0.71804 | 0.39164 | -0.44206 | -0.82651 | 0.5332
| 6806 | -0.69553 | 0.41579 | 0.11847 | -0.20823 | -0.39329 | -0.029691 | 0.37992 | 0.12324 | 0.56537 | -0.92319
| 6807 | 0.81917 | -0.42303 | 0.38575 | 0.32199 | -0.42078 | -0.64857 | -0.4717 | -0.5768 | -0.43405 | -0.13011
| 6808 | 0.48435 | 0.03434 | 0.11665 | 0.18581 | 0.5019 | -0.38771 | 0.38836 | 0.21968 | -0.52052 | 0.2659
| 6809 | 0.55424 | 0.86108 | 0.39428 | 0.33524 | 0.4553 | 0.55447 | -0.6162 | 0.087695 | 0.82824 | -0.55447
| 6810 | -0.18729 | 0.73713 | 0.1109 | -0.43123 | -0.52915 | -0.32747 | -0.44027 | 0.35665 | -0.064532 | 0.056549
| 6811 | 0.13426 | -0.71522 | 0.64659 | 0.49413 | 0.069463 | 0.36305 | 0.19173 | 0.46774 | -0.32717 | -0.20634
| 6812 | -0.26604 | 0.073555 | -0.09066 | -0.48512 | 0.035272 | -0.087914 | 0.46418 | 0.69619 | -0.49 | 0.59689
| 6813 | 0.19508 | 0.68425 | -0.097393 | 0.64042 | -0.32955 | 0.24548 | -0.51513 | -0.39329 | -0.82883 | 0.58951
| 6814 | 0.13196 | 0.33947 | 0.23351 | 0.66044 | 0.01091 | 0.73411 | 0.55335 | 0.45824 | 0.39213 | 0.38137
| 6815 | -0.59664 | 0.79191 | -0.40343 | -0.61725 | 0.51927 | -0.6833 | -0.012427 | -0.012731 | -0.49552 | -0.78669
| 6816 | 0.48843 | 0.10652 | -0.92859 | -0.83783 | 0.55672 | -0.39942 | -0.17241 | -0.051686 | -0.41187 | -0.023629
| 6817 | 0.061011 | 0.047792 | -0.50654 | -0.24416 | 0.083539 | 0.39543 | 0.71104 | -0.13196 | 0.13553 | -0.32346
| 6818 | -0.16783 | 0.20044 | -0.37032 | -0.73448 | -0.13669 | -0.14227 | -0.36447 | 0.056019 | -0.17836 | -0.43
| 6819 | -0.53427 | -0.51782 | -0.75772 | 0.61438 | -0.30007 | 0.33811 | -0.88126 | -0.43018 | -0.33796 | -0.83417
| 6820 | -0.20294 | 0.48048 | -0.29099 | -0.36211 | 0.18717 | 0.53043 | -0.69488 | -0.10876 | 0.3116 | -0.38267
| 6821 | -0.043182 | 0.17411 | -0.27619 | 0.47684 | 0.41819 | -0.17314 | -0.009798 | -0.074419 | 0.75979 | -0.14332
| 6822 | 0.064105 | 0.49512 | -0.93292 | 0.17362 | -0.43938 | -0.4232 | -0.71627 | -0.82536 | -0.69619 | -0.28649
| 6823 | 0.2402 | -0.82708 | -0.71911 | -0.35977 | 0.25697 | -0.22702 | -0.59368 | -0.46474 | 0.14076 | 0.10006
| 6824 | -0.059947 | -0.14402 | -0.16639 | -0.30797 | 0.36196 | -0.22238 | -0.84605 | 0.59515 | -0.25441 | 0.28453
| 6825 | 0.71663 | -0.10117 | 0.0020521 | 0.6852 | 0.32332 | -0.16663 | -0.30913 | 0.14718 | -0.46549 | 0.36258
| 6826 | -0.063571 | -0.039635 | 0.10865 | 0.78483 | 0.55335 | -0.41905 | -0.14718 | 0.41153 | -0.22935 | 0.1338
| 6827 | 0.052002 | 0.84933 | 0.10384 | -0.47914 | 0.35852 | 0.031135 | -0.30552 | 0.23508 | -0.022708 | -0.0089904
| 6828 | 0.35092 | -0.41391 | 0.46176 | 0.38153 | -0.18581 | 0.089451 | -0.37494 | -0.038075 | -0.14507 | 0.56861
| 6829 | -0.13623 | -0.20307 | 0.22366 | 0.16988 | -0.09044 | 0.12656 | 0.28299 | -0.17921 | 0.027529 | 0.47645
| 6830 | -0.17592 | 0.41102 | 0.82824 | 0.3211 | -0.2225 | -0.69784 | 0.21521 | -0.10017 | -0.48029 | -0.27564
| 6831 | -0.49671 | -0.045275 | -0.57374 | 0.087476 | 0.0050628 | -0.09529 | 0.26918 | -0.6852 | 0.17921 | -0.56514
| 6832 | 0.38283 | -0.096617 | -0.075284 | 0.031548 | -0.66789 | -0.22289 | -0.49493 | -0.58757 | 0.54011 | 0.39148
| 6833 | 0.5017 | -0.53881 | -0.092531 | 0.34388 | -0.33075 | 0.4902 | 0.49196 | 0.65605 | -0.21381 | -0.011516
| 6834 | -0.52429 | -0.28705 | -0.47076 | 0.16388 | -0.14332 | 0.68583 | -0.27813 | -0.38984 | 0.34617 | 0.28439
| 6835 | 0.17726 | 0.26658 | -0.7839 | -0.21457 | -0.10217 | -0.09033 | -0.30322 | 0.041929 | -0.84605 | -0.21304
| 6836 | -0.21215 | 0.39312 | 0.12324 | 0.039323 | -0.60643 | 0.3357 | -0.13219 | 0.046008 | -0.10496 | 0.073016
| 6837 | -0.40696 | 0.12188 | 0.34938 | 0.46121 | -0.077232 | 0.065923 | -0.33374 | -0.62517 | 0.26305 | -0.35324
| 6838 | -0.65868 | 0.1005 | -0.048002 | 0.21355 | -0.45182 | 0.26454 | -0.58155 | -0.20836 | 0.36055 | -0.76698
| 6839 | 0.43848 | -0.75161 | -0.012427 | -0.48415 | -0.16412 | 0.27827 | 0.23091 | 0.34038 | -0.18877 | -0.55717
| 6840 | -0.70117 | 0.72378 | 0.76612 | 0.23182 | -0.24376 | -0.45475 | 0.62811 | 0.20987 | -0.0029544 | -0.071076
| 6841 | -0.34831 | -0.063998 | 0.45164 | 0.32717 | -0.1179 | -0.076582 | 0.2575 | 0.23208 | -0.4653 | 0.28831
| 6842 | 0.17508 | -0.096507 | -0.14589 | -0.70453 | -0.5883 | -0.05984 | 0.65518 | -0.20056 | 0.11915 | -0.10854
| 6843 | 0.31655 | -0.18508 | 0.64237 | 0.34008 | -0.19346 | -0.11552 | -0.048212 | 0.70966 | -0.08649 | 0.069785
| 6844 | 0.67922 | -0.32687 | 0.15946 | -0.6703 | -0.1957 | -0.24522 | -0.22122 | 0.099278 | -0.38089 | 0.035168
| 6845 | -0.45787 | -0.36447 | 0.23954 | -0.17386 | -0.48512 | -0.76612 | 0.12382 | 0.77044 | -0.42895 | -0.29594
| 6846 | -0.46046 | -0.66608 | -0.12313 | -0.25508 | 0.17265 | -0.46755 | 0.45695 | -0.5015 | 0.14906 | -0.36086
| 6847 | -0.21533 | -0.152 | -0.16232 | -0.64125 | -0.23875 | -0.069033 | -0.024449 | -0.39992 | -0.60113 | 0.15071
| 6848 | -0.34418 | -0.78716 | 0.049684 | -0.14871 | 0.62865 | -0.56676 | -0.59988 | -0.9078 | -0.39411 | 0.029073
| 6849 | 0.44891 | -0.47379 | 0.42026 | 0.35 | -0.073339 | -0.81862 | -0.44457 | 0.84031 | -0.24694 | 0.00095045
| 6850 | 0.22663 | -0.24747 | -0.8882 | 0.38251 | 0.28537 | -0.3015 | -0.27771 | -0.031444 | 0.34647 | 0.33494
| 6851 | -0.010202 | -0.32214 | 0.17568 | -0.8747 | 0.15318 | 0.18043 | -0.61934 | 0.55492 | 0.3804 | 0.70555
| 6852 | 0.97764 | 0.42947 | -0.84476 | 0.017503 | 0.16663 | -0.13461 | -0.19359 | -0.30567 | -0.17617 | -0.3214
| 6853 | 0.20181 | -0.47933 | 0.044751 | 0.11779 | -0.53299 | 0.39958 | 0.61646 | -0.08989 | -0.77044 | -0.53342
| 6854 | -0.1786 | -0.31378 | -0.54823 | -0.54956 | -0.41153 | -0.76784 | 0.34099 | -0.019133 | -0.4344 | -0.082013
| 6855 | 0.40242 | 0.11259 | -0.13484 | 0.20094 | -0.83845 | 0.055278 | 0.37831 | -0.34892 | 0.14449 | -0.78344
| 6856 | 0.88042 | 0.17617 | 0.25321 | 0.38984 | 0.69194 | 0.19607 | -0.40276 | 0.37286 | 0.035168 | 0.77662
| 6857 | -0.27385 | -0.21763 | 0.80075 | -0.35062 | 0.038179 | 0.61283 | -0.46925 | -0.46158 | -0.87233 | -0.070538
| 6858 | -0.18471 | -0.74801 | 0.62543 | 0.03714 | -0.59392 | -0.67182 | 0.17605 | -0.020255 | -0.48125 | 0.15958
| 6859 | 0.39197 | -0.37079 | 0.28076 | 0.38575 | 0.55582 | 0.047582 | -0.28509 | 0.55089 | -0.60872 | 0.18238
| 6860 | -0.15887 | -0.11011 | -0.83059 | -0.02322 | 0.17677 | 0.79336 | 0.6162 | 0.72305 | -0.81697 | 0.35789
| 6861 | 0.09165 | -0.031031 | 0.70794 | 0.14344 | -0.41511 | -0.52282 | -0.92063 | 0.46195 | -0.1229 | 0.35031
| 6862 | 0.39775 | 0.39098 | 0.29708 | -0.45991 | 0.77262 | -0.39362 | -0.53342 | 0.054855 | 0.0044599 | 0.71733
| 6863 | -0.38153 | 0.34693 | 0.40259 | -0.42026 | 0.13611 | -0.62092 | 0.3618 | -0.41545 | 0.2402 | 0.5922
| 6864 | -0.14169 | 0.23039 | 0.51969 | 0.01486 | -0.52809 | -0.3796 | 0.25 | 0.136 | 0.087476 | 0.11157
| 6865 | 0.029176 | 0.47341 | 0.56445 | 0.019847 | 0.58107 | 0.21981 | 0.75322 | 0.032891 | 0.67766 | -0.0013509
| 6866 | 0.23574 | 0.11688 | 0.67213 | 0.083758 | -0.38251 | 0.16006 | 0.29879 | -0.16472 | -0.22728 | 0.71417
| 6867 | 0.28677 | -0.046218 | -0.034961 | -0.024039 | -0.052002 | 0.047372 | -0.50553 | 0.16364 | -0.59689 | 0.099611
| 6868 | 0.61516 | 0.50573 | 0.22624 | 0.1758 | -0.9078 | 0.52597 | 0.39809 | -0.52979 | -0.13565 | 0.17278
| 6869 | 0.26088 | 0.37494 | 0.47076 | -0.18471 | -0.38073 | 0.033512 | -0.70931 | 0.025782 | 0.056443 | 0.68583
| 6870 | -0.027426 | 0.6634 | -0.83845 | 0.13415 | 0.57869 | 0.070215 | -0.075176 | 0.38853 | 0.32435 | -0.26727
| 6871 | -0.036102 | -0.3651 | -0.30107 | -0.18177 | -0.56308 | -0.2659 | -0.16735 | 0.18877 | 0.20232 | -0.19869
| 6872 | 0.60364 | -0.89 | -0.42668 | 0.076799 | -0.52429 | -0.58083 | -0.083103 | -0.23299 | -0.49118 | 0.26305
| 6873 | 0.60821 | -0.22225 | 0.26863 | -0.77087 | -0.68172 | -0.083649 | -0.15543 | 0.77218 | 0.02281 | 0.19969
| 6874 | -0.070108 | -0.018725 | -0.070645 | 0.30552 | -0.30624 | -0.70931 | 0.27495 | 0.035479 | 0.065816 | -0.26863
| 6875 | 0.76569 | -0.3551 | -0.43299 | -0.016079 | 0.35432 | -0.20194 | -0.56606 | -0.28049 | -0.33449 | 0.32539
| 6876 | -0.024346 | 0.2175 | -0.14613 | -0.57163 | 0.51534 | -0.067959 | -0.2985 | 0.20081 | -0.33615 | -0.14929
| 6877 | -0.042973 | -0.30624 | -0.11858 | -0.03 | -0.32911 | -0.48532 | 0.10518 | -0.01486 | -0.6149 | 0.66221
| 6878 | 0.40595 | 0.70217 | 0.079077 | -0.035998 | -0.32022 | 0.1546 | -0.12553 | 0.28845 | -0.69652 | 0.26196
| 6879 | 0.063891 | 0.4258 | -0.23495 | -0.053163 | -0.66698 | 0.080381 | -0.19346 | 0.32243 | -0.55989 | 0.22276
| 6880 | -0.057716 | -0.45843 | 0.76527 | 0.16819 | 0.56606 | -0.063784 | 0.78023 | 0.17738 | -0.41836 | 0.23836
| 6881 | -0.69129 | 0.30826 | 0.55312 | -0.27509 | 0.43158 | -0.17386 | -0.65693 | 0.0060684 | -0.1473 | -0.47341
| 6882 | 0.32184 | -0.43671 | 0.064105 | -0.05899 | -0.40561 | -0.46887 | 0.29679 | -0.37095 | 0.019133 | -0.57703
| 6883 | 0.14847 | 0.84157 | 0.17157 | -0.45237 | -0.57609 | 0.13588 | 0.079837 | -0.28063 | -0.30884 | -0.16424
| 6884 | -0.13681 | 0.47113 | 0.50432 | 0.59171 | 0.065602 | 0.28411 | 0.38575 | -0.097725 | 0.24389 | -0.43759
| 6885 | -0.81318 | 0.49631 | -0.72852 | -0.46661 | 0.04538 | -0.28216 | 0.40949 | 0.37 | 0.72926 | -0.25468
| 6886 | -0.2133 | 0.67335 | -0.16256 | 0.22521 | 0.3735 | 0.31407 | 0.20558 | 0.84412 | -0.41 | -0.62677
| 6887 | -0.0173 | 0.16149 | 0.012427 | -0.09143 | 0.025988 | 0.099722 | 0.11101 | -0.68839 | 0.60541 | -0.25912
| 6888 | -0.084959 | 0.70589 | -0.1634 | -0.32346 | -0.35169 | -0.65868 | 0.053797 | -0.52915 | -0.26509 | 0.40326
| 6889 | -0.11631 | 0.26291 | 0.77796 | -0.19111 | -0.13484 | 0.29722 | -0.62946 | -0.22611 | -0.27854 | 0.12736
| 6890 | 0.17 | 0.3425 | 0.040156 | 0.24893 | 0.6241 | -0.47132 | 0.30913 | 0.46009 | -0.028661 | 0.85201
| 6891 | 0.29438 | -0.31993 | 0.54867 | 0.25562 | -0.17145 | -0.039323 | 0.22276 | -0.28761 | -0.046113 | 0.17872
| 6892 | -0.027323 | -0.87155 | -0.13265 | -0.22818 | -0.0017515 | -0.84348 | 0.093413 | 0.5013 | -0.18177 | 0.14192
| 6893 | 0.65985 | -0.91693 | -0.31699 | -0.56239 | -0.051159 | -0.68456 | -0.29311 | -0.23195 | -0.35525 | 0.14145
| 6894 | 0.14683 | 0.61987 | -0.46568 | -0.26808 | -0.51102 | -0.51164 | -0.9005 | 0.65229 | 0.45658 | 0.11767
| 6895 | -0.053797 | 0.0072765 | -0.05984 | -0.034754 | -0.098612 | 0.59714 | -0.084085 | -0.10317 | -0.084413 | -0.46456
| 6896 | 0.34785 | 0.089451 | 0.76315 | -0.13311 | 0.28243 | 0.13716 | -0.085287 | 0.21368 | -0.20031 | 0.021174
| 6897 | -0.46793 | -0.42511 | -0.72779 | -0.11949 | 0.23915 | 0.35231 | 0.53363 | 0.39775 | -0.42825 | -0.45548
| 6898 | 0.34724 | -0.55627 | -0.84157 | 0.20307 | 0.96394 | 0.47645 | -0.049789 | 0.76021 | -0.25401 | -0.39049
| 6899 | 0.00065021 | 0.48863 | 0.51266 | -0.71104 | 0.65868 | -0.25133 | 0.03 | 0.44619 | -0.15911 | 0.63353
| 6900 | -0.61 | 0.47894 | 0.44746 | 0.76063 | 0.7492 | 0.65201 | -0.2431 | 0.3312 | -0.20596 | -0.048422
| 6901 | 0.46325 | -0.13 | -0.041407 | 0.37398 | 0.29296 | -0.46176 | -0.028249 | 0.54978 | 0.085724 | -0.042451
| 6902 | -0.6833 | -0.91456 | 0.15425 | -0.012326 | -0.5141 | -0.24601 | -0.22857 | -0.17169 | -0.051369 | 0.13797
| 6903 | 0.4826 | 0.71173 | -0.10955 | -0.059309 | 0.46493 | -0.085724 | 0.11079 | -0.25227 | 0.2278 | 0.62119
| 6904 | -0.018623 | -0.71911 | 0.24893 | 0.21139 | 0.011617 | -0.16484 | 0.41836 | 0.060266 | 0.47076 | 0.00065021
| 6905 | -0.025474 | 0.5141 | -0.51061 | 0.26877 | -0.39593 | 0.2907 | -0.17302 | 0.55807 | 0.34601 | -0.038387
| 6906 | -0.43123 | -0.34831 | 0.74096 | 0.12324 | -0.15047 | 0.3882 | -0.56148 | -0.26822 | -0.28146 | -0.4902
| 6907 | -0.18092 | 0.60567 | -0.46065 | -0.040156 | -0.51761 | 0.11496 | -0.055172 | 0.30595 | -0.21317 | -0.26481
| 6908 | 0.5347 | 0.42965 | 0.036517 | 0.20848 | 0.90151 | -0.4989 | 0.28537 | -0.094959 | 0.41613 | -0.00035006
| 6909 | -0.90461 | -0.029897 | -0.64265 | 0.23286 | 0.038595 | -0.053797 | 0.7504 | 0.24376 | -0.30107 | -0.021583
| 6910 | 0.91112 | 0.27206 | 0.15472 | 0.39066 | -0.67091 | 0.25281 | 0.80635 | -0.076907 | 0.23417 | 0.24007
| 6911 | -0.19185 | 0.19794 | -0.72486 | -0.4542 | -0.012225 | -0.74058 | 0.34831 | 0.53556 | -0.15638 | 0.24561
| 6912 | -0.079837 | 0.23364 | 0.050211 | 0.90151 | 0.30682 | -0.061437 | 0.35154 | -0.035687 | 0.034236 | -0.014353
| 6913 | -0.61128 | -0.39859 | 0.30711 | 0.25845 | -0.72161 | -0.44188 | -0.45091 | -0.2184 | -0.20307 | -0.18778
| 6914 | -0.31131 | -0.18459 | -0.71522 | -0.31611 | -0.58684 | -0.081469 | 0.5714 | 0.028146 | -0.47322 | -0.31465
| 6915 | -0.15484 | -0.47722 | 0.04266 | -0.098945 | 0.022094 | -0.42199 | 0.051159 | 0.020357 | 0.024141 | 0.76315
| 6916 | -0.13669 | -0.09706 | -0.17229 | 0.57703 | 0.1825 | 0.36541 | -0.40443 | -0.11293 | 0.46139 | 0.45018
| 6917 | -0.076258 | -0.11801 | 0.19607 | -0.18532 | 0.46251 | -0.21406 | 0.72197 | -0.56262 | -0.17738 | -0.17241
| 6918 | 0.19012 | -0.46981 | -0.20937 | 0.36102 | -0.75444 | 0.20207 | -0.075608 | -0.91815 | -0.42303 | 0.23378
| 6919 | 0.3817 | -0.1109 | 0.015368 | -0.26822 | -0.24389 | -0.37686 | 0.0036567 | -0.71911 | -0.2659 | 0.12576
| 6920 | -0.92584 | -0.23391 | -0.0069743 | -0.53578 | 0.077991 | 0.038907 | -0.06016 | 0.26795 | 0.45292 | -0.94255
| 6921 | 0.5005 | -0.12108 | -0.2356 | -0.074311 | 0.14402 | 0.48202 | -0.29523 | -0.28873 | 0.064853 | 0.19508
| 6922 | 0.010505 | -0.3061 | 0.0066723 | 0.78529 | 0.23626 | 0.51969 | -0.16292 | 0.029382 | -0.4989 | -0.13519
| 6923 | -0.07962 | 0.27993 | -0.87155 | -0.085943 | -0.093523 | 0.4134 | -0.64518 | 0.30957 | 0.41648 | 0.12256
| 6924 | -0.4859 | 0.47151 | 0.51637 | -0.28216 | -0.44692 | 0.082013 | 0.013238 | 0.23104 | -0.87311 | 0.25334
| 6925 | 0.61309 | -0.20772 | 0.025269 | -0.32435 | -0.64602 | -0.066565 | -0.34908 | -0.1082 | 0.34892 | -0.12131
| 6926 | -0.033201 | -0.020561 | 0.35479 | -0.39181 | -0.11428 | 0.25414 | 0.73448 | -0.13346 | 0.34877 | -0.10686
| 6927 | 0.46493 | -0.2907 | 0.25818 | 0.45 | 0.13646 | -0.16928 | -0.2689 | -0.78952 | -0.14437 | -0.031135
| 6928 | -0.78622 | -0.64546 | 0.10228 | -0.0092932 | 0.13994 | -0.16615 | -0.44152 | -0.038699 | -0.68711 | -0.17012
| 6929 | -0.51348 | 0.15614 | -0.26522 | 0.25374 | 0.83297 | 0.44475 | -0.29282 | 0.34342 | 0.43105 | -0.52324
| 6930 | -0.85752 | 0.080489 | 0.33902 | -0.83297 | -0.27591 | 0.41187 | -0.37191 | 0.24814 | -0.31116 | 0.0060684
| 6931 | 0.13461 | -0.027529 | 0.19508 | -0.52915 | 0.19657 | 0.086053 | -0.38738 | -0.51637 | 0.33615 | -0.21025
| 6932 | 0.85613 | -0.058777 | -0.548 | 0.87 | 0.65663 | -0.91693 | -0.43635 | -0.11518 | -0.52873 | 0.57585
| 6933 | 0.41051 | 0.16496 | -0.65258 | 0.12097 | 0.57327 | 0.099389 | 0.33209 | 0.61568 | 0.021481 | 0.10328
| 6934 | -0.47665 | 0.38592 | -0.32332 | -0.28439 | 0.47246 | 0.4392 | 0.78529 | 0.42476 | 0.41221 | 0.13577
| 6935 | -0.066673 | -0.50898 | 0.33419 | 0.23626 | -0.81159 | -0.013643 | -0.37927 | 0.54294 | -0.14076 | -0.4307
| 6936 | -0.051475 | -0.31145 | 0.24867 | 0.20962 | 0.352 | -0.52513 | -0.20937 | 0.54867 | 0.20119 | -0.71982
| 6937 | -0.46083 | -0.48183 | -0.33886 | 0.085943 | 0.0054649 | -0.72523 | -0.24416 | -0.15082 | -0.11869 | -0.93755
| 6938 | 0.15911 | 0.81752 | -0.51575 | 0.019235 | -0.27178 | 0.56699 | -0.21114 | -0.46774 | -0.43334 | -0.39975
| 6939 | -0.6338 | -0.5707 | 0.52094 | -0.43 | 0.014454 | 0.00075028 | -0.16424 | 0.12908 | -0.30079 | -0.19124
| 6940 | -0.054643 | 0.62198 | 0.26142 | 0.35852 | -0.11079 | -0.14122 | -0.48804 | -0.029073 | 0.17495 | 0.34038
| 6941 | -0.23941 | -0.2598 | -0.38559 | 0.42355 | -0.14297 | -0.31058 | -0.31611 | -0.30884 | -0.42807 | 0.23143
| 6942 | -0.8739 | 0.22456 | -0.40983 | 0.62624 | 0.68361 | -0.53385 | 0.14227 | -0.14753 | 0.42389 | 0.91225
| 6943 | 0.61542 | 0.0052639 | -0.45567 | -0.86036 | 0.082122 | -0.049369 | 0.28411 | 0.41974 | 0.3662 | -0.74407
| 6944 | 0.58419 | 0.022094 | -0.093192 | -0.13161 | 0.21279 | 0.097503 | 0.61026 | -0.19223 | 0.20533 | 0.21763
| 6945 | 0.082449 | 0.63108 | 0.54033 | 0.21738 | 0.1803 | -0.85964 | -0.17994 | 0.26973 | 0.063464 | -0.13994
| 6946 | 0.16137 | -0.1136 | 0.17483 | -0.17617 | -0.17072 | 0.63765 | 0.026707 | -0.63654 | -0.0062697 | -0.0728
| 6947 | 0.25549 | 0.16424 | -0.15816 | -0.37654 | 0.23731 | -0.27647 | -0.62892 | 0.72632 | -0.75607 | 0.033305
| 6948 | 0.067423 | -0.13415 | 0.23417 | 0.70285 | 0.038803 | 0.071614 | 0.11756 | -0.18741 | -0.53837 | 0.42112
| 6949 | -0.57774 | 0.71733 | 0.48746 | -0.38315 | -0.00025003 | 0.28257 | -0.40662 | 0.1118 | -0.43299 | -0.098612
| 6950 | 0.24125 | 0.12633 | 0.17982 | 0.87155 | 0.17994 | 0.17253 | 0.21661 | -0.64237 | 0.47246 | 0.19632
| 6951 | 0.3735 | -0.054008 | 0.95417 | -0.041094 | -0.29793 | 0.16149 | -0.36636 | -0.46456 | 0.058459 | -0.24774
| 6952 | 0.62704 | 0.74212 | 0.042033 | 0.65634 | 0.18508 | 0.33585 | -0.39643 | 0.34388 | -0.39975 | -0.16018
| 6953 | 0.29056 | 0.20911 | 0.54207 | 0.41562 | -0.30841 | -0.7623 | 0.13011 | -0.077449 | -0.56653 | -0.15259
| 6954 | -0.48532 | -0.24217 | 0.69357 | -0.077341 | -0.27082 | 0.1245 | -0.27536 | 0.53492 | 0.29452 | -0.37879
| 6955 | 0.15531 | 0.35185 | 0.37911 | 0.74174 | 0.12131 | -0.67304 | 0.05422 | 0.24389 | 0.30971 | -0.17048
| 6956 | -0.034858 | 0.73 | -0.41187 | -0.25281 | 0.49354 | -0.27716 | -0.73942 | -0.22702 | -0.5201 | 0.06293
| 6957 | -0.85893 | -0.64602 | -0.77131 | 0.060479 | -0.032271 | -0.29893 | -0.37302 | 0.70453 | 0.49295 | -0.35696
| 6958 | 0.67243 | 0.34403 | -0.13669 | 0.69586 | -0.20583 | -0.093192 | 0.3211 | 0.19371 | 0.18803 | 0.22495
| 6959 | 0.021072 | 0.34754 | 0.081142 | -0.002453 | -0.25495 | -0.042347 | -0.13692 | 0.25067 | -0.25187 | -0.4194
| 6960 | -0.54229 | 0.77932 | -0.0068736 | 0.6546 | -0.75241 | -0.23521 | -0.23574 | -0.16448 | 0.87077 | -0.33826
| 6961 | -0.36227 | 0.0016514 | -0.66849 | -0.51513 | 0.18778 | 0.24336 | -0.0048618 | -0.19408 | 0.28972 | -0.060585
| 6962 | -0.49177 | -0.52115 | 0.79336 | 0.12622 | 0.28972 | 0.32717 | -0.39908 | 0.55898 | 0.20458 | 0.44891
| 6963 | -0.67735 | 0.02568 | -0.23078 | -0.58927 | -0.61751 | -0.72889 | -0.5143 | -0.3242 | -0.014454 | 0.51595
| 6964 | 0.13046 | 0.25 | 0.18643 | 0.4979 | -0.073124 | -0.46251 | 0.40983 | -0.56907 | 0.20282 | -0.010505
| 6965 | 0.29836 | 0.35899 | -0.019133 | -0.57491 | 0.08485 | -0.22135 | -0.22045 | 0.38153 | 0.24933 | 0.12816
| 6966 | -0.10028 | -0.68047 | 0.25508 | -0.14578 | 0.023732 | -0.10172 | 0.94432 | -0.012326 | 0.086928 | 0.018827
| 6967 | -0.034961 | 0.026707 | -0.16101 | 0.49711 | -0.33449 | -0.096617 | 0.25616 | -0.075933 | -0.41425 | 0.087147
| 6968 | 0.78344 | -0.18165 | -0.66044 | 0.28649 | 0.6382 | -0.047162 | -0.14355 | 0.72852 | 0.55178 | 0.32672
| 6969 | 0.18495 | -0.17823 | -0.46325 | -0.52745 | 0.054643 | 0.48454 | 0.21623 | -0.26223 | -0.31758 | 0.51143
| 6970 | -0.46009 | 0.54251 | 0.085724 | -0.11338 | 0.58036 | -0.52345 | -0.51369 | 0.22702 | -0.21725 | 0.14111
| 6971 | 0.32702 | -0.7076 | -0.57421 | -0.67396 | -0.3087 | -0.71557 | 0.013846 | 0.40259 | 0.048422 | 0.20962
| 6972 | 0.53299 | 0.85613 | -0.031857 | 0.7015 | -0.28021 | 0.031961 | 0.29907 | -0.15661 | -0.5959 | -0.64857
| 6973 | -0.039323 | -0.20407 | -0.0060684 | 0.33449 | 0.48454 | 0.028043 | -0.46605 | 0.45109 | 0.28021 | 0.45
| 6974 | 0.071399 | -0.19557 | 0.12519 | -0.026193 | -0.65722 | -0.72414 | -0.48707 | 0.10798 | 0.66939 | 0.62811
| 6975 | -0.097725 | 0.1634 | 0.44818 | 0.16137 | 0.1634 | -0.49512 | -0.10652 | 0.53729 | 0.81426 | -0.0042591
| 6976 | 0.060585 | -0.17556 | -0.27206 | 0.37382 | -0.13196 | -0.063571 | -0.14624 | 0.17702 | -0.13011 | -0.029691
| 6977 | -0.5728 | -0.077232 | 0.012832 | -0.64772 | -0.10921 | 0.14542 | -0.21853 | 0.28383 | 0.09033 | -0.52724
| 6978 | 0.5102 | 0.63081 | -0.57163 | -0.25522 | 0.098279 | -0.58036 | 0.16555 | 0.264 | -0.5436 | -0.39958
| 6979 | -0.87311 | -0.46158 | 0.6371 | 0.15012 | -0.71138 | -0.40276 | 0.2147 | 0.25214 | -0.063037 | 0.38918
| 6980 | 0.8956 | 0.24363 | 0.092421 | 0.3681 | 0.22392 | -0.38024 | -0.050526 | 0.77439 | -0.49196 | -0.17399
| 6981 | 0.20659 | -0.63958 | -0.11315 | -0.20069 | -0.31728 | -0.7076 | -0.75485 | -0.21139 | 0.26658 | -0.91112
| 6982 | -0.80584 | -0.27536 | -0.18532 | 0.0053644 | 0.1926 | 0.13276 | -0.37686 | -0.18348 | -0.034443 | 0.66879
| 6983 | -0.70285 | -0.15614 | 0.36321 | 0.6634 | -0.77841 | 0.083758 | 0.041407 | -0.15401 | -0.0033556 | 0.39362
| 6984 | -0.29651 | -0.34023 | 0.41102 | -0.32391 | 0.39576 | -0.87793 | -0.072476 | 0.25697 | -0.70386 | 0.26536
| 6985 | -0.6249 | -0.0058672 | -0.46718 | 0.32791 | 0.12656 | -0.5458 | 0.16173 | -0.056019 | 0.10485 | 0.65576
| 6986 | -0.62145 | -0.62119 | 0.80481 | -0.40393 | -0.32007 | -0.41648 | 0.71733 | 0.030619 | -0.37558 | -0.57444
| 6987 | -0.41391 | 0.37686 | 0.27495 | -0.58395 | -0.19607 | -0.2791 | -0.4272 | 0.17921 | -0.45806 | 0.41408
| 6988 | -0.15212 | 0.15828 | 0.55111 | 0.22212 | 0.77841 | 0.13611 | -0.21917 | 0.27716 | -0.17459 | -0.27123
| 6989 | 0.13669 | -0.75241 | 0.65751 | 0.34693 | -0.86771 | -0.21139 | 0.10228 | -0.68903 | -0.1323 | -0.93443
| 6990 | 0.32494 | -0.14379 | 0.19719 | 0.16687 | -0.90461 | 0.19657 | -0.21457 | 0.6044 | 0.13994 | 0.19396
| 6991 | 0.10664 | 0.52851 | -0.23915 | -0.14379 | 0.17278 | 0.28887 | 0.44063 | 0.26563 | -0.62039 | 0.47189
| 6992 | 0.074419 | -0.41477 | 0.003456 | 0.52851 | -0.045065 | 0.078751 | -0.62677 | -0.25899 | 0.38689 | 0.1952
| 6993 | -0.030309 | 0.46981 | -0.087476 | 0.21152 | 0.089121 | 0.39859 | 0.46474 | 0.28719 | 0.64237 | -0.0052639
| 6994 | 0.41562 | -0.4979 | 0.73373 | 0.56884 | 0.46232 | -0.22767 | 0.30164 | -0.69652 | -0.51389 | 0.27896
| 6995 | 0.47933 | -0.15059 | 0.25589 | -0.1204 | -0.69422 | -0.0076795 | 0.1634 | -0.0071757 | -0.0090913 | 0.01
| 6996 | -0.19421 | -0.10888 | -0.078317 | -0.049579 | -0.01415 | -0.012934 | 0.22431 | -0.61987 | 0.060053 | 0.68679
| 6997 | -0.18287 | -0.3593 | 0.4653 | -0.18803 | -0.09066 | -0.65114 | 0.17994 | 0.75201 | 0.38299 | 0.067745
| 6998 | 0.48882 | -0.66578 | -0.89753 | 0.31102 | 0.38332 | 0.18361 | -0.24681 | 0.27854 | 0.16054 | 0.057716
| 6999 | 0.056231 | -0.17957 | -0.55898 | -0.05984 | 0.019439 | 0.7005 | -0.31189 | 0.50412 | -0.81 | 0.12473
| 7000 | 0.13507 | 0.35293 | -0.24151 | 0.003155 | -0.08474 | -0.79482 | 0.099167 | 0.76357 | 0.46737 | 0.40142
| 7001 | 0.45475 | -0.43246 | 0.93 | 0.5959 | -0.039531 | -0.037659 | -0.16054 | -0.55335 | 0.10306 | 0.8043
| 7002 | 0.11722 | 0.16651 | 0.16412 | 0.16173 | -0.45401 | 0.059734 | 0.3303 | -0.39263 | 0.17738 | 0.49078
| 7003 | -0.80226 | 0.11541 | -0.48357 | -0.54778 | -0.25562 | -0.74643 | 0.9272 | -0.3451 | 0.21635 | -0.41545
| 7004 | -0.2755 | 0.086709 | 0.62437 | -0.32361 | -0.82883 | -0.69129 | 0.41085 | -0.021276 | -0.5102 | -0.58275
| 7005 | 0.47379 | 0.59417 | 0.25414 | -0.61231 | -0.29296 | -0.31553 | 0.096839 | -0.39411 | 0.27082 | -0.056337
| 7006 | -0.39494 | 0.16292 | 0.32273 | 0.1863 | -0.83237 | 0.6319 | -0.77 | 0.42407 | -0.49137 | -0.10462
| 7007 | 0.16531 | -0.24893 | 0.59639 | -0.096507 | -0.21317 | -0.073447 | -0.17775 | -0.51246 | -0.25831 | 0.06325
| 7008 | -0.19049 | -0.0066723 | -0.36526 | 0.055278 | -0.34068 | 0.60923 | 0.49552 | 0.548 | -0.49711 | 0.29495
| 7009 | 0.96394 | 0.00035006 | -0.038075 | -0.015267 | 0.053586 | 0.43476 | -0.36541 | -0.27591 | 0.34724 | 0.43299
| 7010 | -0.14507 | 0.23195 | 0.39759 | 0.4987 | -0.083649 | 0.48785 | 0.13634 | -0.2081 | 0.69194 | 0.31919
| 7011 | 0.096064 | -0.31626 | 0.6755 | 0.009798 | 0.49592 | -0.16627 | -0.47038 | 0.098279 | -0.23691 | -0.077558
| 7012 | 0.5412 | 0.45695 | -0.64349 | -0.15899 | 0.27274 | 0.88295 | 0.099722 | 0.79678 | -0.33886 | -0.20445
| 7013 | -0.035998 | 0.68552 | -0.18324 | -0.26359 | -0.83357 | 0.23364 | 0.49374 | 0.46699 | 0.67091 | -0.22702
| 7014 | -0.10485 | 0.48202 | -0.16892 | -0.20357 | -0.63931 | -0.37654 | -0.12805 | 0.41785 | -0.70352 | 0.33224
| 7015 | 0.073771 | 0.12897 | 0.35727 | -0.41871 | -0.53149 | -0.5447 | -0.031754 | -0.27178 | 0.16579 | 0.25107
| 7016 | -0.42912 | -0.81588 | 0.1292 | -0.33871 | -0.21177 | -0.44493 | -0.10061 | 0.66015 | 0.57585 | -0.56125
| 7017 | -0.43529 | 0.5264 | -0.23247 | -0.28789 | -0.20987 | 0.12336 | 0.3357 | 0.24641 | 0.49413 | 0.78297
| 7018 | -0.14425 | 0.42009 | -0.092421 | -0.12713 | 0.49731 | 0.38722 | -0.38575 | 0.1634 | -0.032271 | 0.23364
| 7019 | 0.029897 | 0.33359 | -0.3148 | -0.18692 | -0.23443 | 0.3363 | 0.25281 | 0.34479 | 0.1758 | -0.48473
| 7020 | 0.38951 | -0.148 | 0.10619 | -0.89851 | 0.67953 | -0.09011 | -0.31451 | 0.011516 | -0.077449 | 0.5458
| 7021 | 0.095511 | 0.016893 | -0.3303 | -0.53406 | -0.57444 | 0.47341 | -0.5693 | -0.024859 | 0.52661 | 0.59441
| 7022 | -0.59838 | 0.64857 | -0.51865 | -0.24429 | -0.47493 | 0.055913 | 0.075176 | 0.12359 | 0.22212 | 0.31
| 7023 | 0.044961 | 0.13878 | -0.62384 | -0.26495 | -0.42251 | -0.74135 | -0.46849 | -0.11191 | -0.74446 | 0.055172
| 7024 | -0.71557 | -0.38853 | -0.09132 | 0.60263 | -0.46437 | -0.50735 | -0.80947 | 0.30466 | -0.15295 | 0.72852
| 7025 | 0.18864 | 0.030619 | -0.36008 | 0.12507 | -0.1578 | 0.39066 | 0.52894 | -0.92063 | -0.60088 | 0.51451
| 7026 | 0.2225 | 0.2791 | 0.17121 | 0.38137 | -0.4272 | -0.18667 | -0.5021 | -0.21802 | 0.18336 | -0.32066
| 7027 | 0.52261 | -0.056231 | -0.5883 | -0.38836 | -0.50452 | 0.62946 | -0.062397 | 0.092751 | -0.15165 | -0.15816
| 7028 | 0.16771 | -0.20571 | -0.083103 | 0.044542 | -0.33299 | -0.083867 | -0.0173 | -0.049263 | -0.6233 | -0.7184
| 7029 | 0.19136 | -0.42424 | -0.54207 | 0.38689 | -0.039948 | 0.19396 | -0.71804 | 0.037763 | 0.21051 | 0.20836
| 7030 | 0.67091 | 0.032064 | 0.55853 | 0.1694 | -0.65287 | 0.38918 | -0.78068 | 0.052213 | 0.14953 | -0.60617
| 7031 | 0.71487 | 0.042869 | 0.65809 | 0.096507 | -0.8454 | 0.4337 | -0.33494 | 0.013542 | -0.062717 | 0.15638
| 7032 | 0.15982 | -0.74096 | 0.099611 | -0.64518 | 0.34448 | 0.87712 | 0.42825 | -0.07043 | 0.25926 | 0.19086
| 7033 | -0.93755 | -0.26128 | -0.19037 | -0.17411 | -0.15413 | -0.51534 | -0.0088895 | 0.70318 | 0.74722 | 0.19272
| 7034 | 0.33314 | -0.028764 | -0.24165 | 0.15519 | -0.9005 | -0.61672 | -0.0039578 | 0.87311 | 0.15935 | -0.18275
| 7035 | 0.15413 | 0.51225 | 0.43281 | 0.053903 | -0.26727 | -0.66819 | -0.056443 | 0.36117 | 0.42303 | -0.67643
| 7036 | -0.30942 | -0.67 | 0.19322 | -0.43582 | 0.25656 | -0.62224 | 0.15141 | -0.053691 | -0.2476 | 0.43706
| 7037 | -0.28677 | 0.079294 | -0.42825 | -0.060905 | 0.70589 | 0.26877 | 0.02609 | 0.055701 | -0.50735 | 0.31247
| 7038 | 0.77044 | 0.81862 | 0.30696 | 0.1852 | 0.39842 | -0.34023 | -0.152 | 0.059521 | 0.12644 | -0.43264
| 7039 | 0.30036 | 0.37815 | 0.66251 | -0.52219 | 0.13069 | -0.27192 | 0.0029544 | 0.072261 | -0.26183 | 0.8148
| 7040 | -0.20911 | 0.38689 | -0.4194 | 0.41017 | 0.48746 | 0.62973 | -0.22702 | -0.075825 | 0.50452 | -0.047792
| 7041 | 0.27151 | 0.68172 | -0.52555 | 0.096839 | -0.42164 | 0.52198 | -0.47875 | 0.62811 | 0.26291 | -0.80843
| 7042 | 0.35401 | -0.40225 | 0.085068 | 0.72742 | -0.75855 | 0.1597 | -0.56514 | 0.71663 | -0.28705 | -0.060053
| 7043 | -0.81265 | -0.12553 | 0.13727 | 0.4857 | -0.43564 | -0.88126 | -0.29964 | 0.58903 | 0.5143 | -0.62919
| 7044 | -0.60389 | 0.42181 | 0.55989 | 0.54536 | 0.20546 | 0.7512 | -0.37911 | -0.56514 | 0.014454 | 0.60113
| 7045 | -0.15899 | 0.56377 | -0.051897 | 0.27123 | -0.33404 | -0.41665 | -0.039323 | -0.56468 | -0.30667 | 0.70725
| 7046 | 0.05814 | 0.11056 | 0.78952 | 0.20911 | 0.16904 | -0.13971 | -0.64631 | -0.60898 | -0.094075 | 0.092751
| 7047 | -0.33977 | 0.30769 | 0.45475 | -0.19049 | -0.71557 | -0.72305 | -0.54933 | -0.10507 | -0.31 | 0.23534
| 7048 | 0.24933 | -0.28327 | 0.57468 | 0.17217 | 0.085178 | -0.25576 | -0.13011 | 0.67519 | 0.003155 | 0.17205
| 7049 | -0.33902 | -0.32732 | 0.34555 | -0.087695 | 0.24867 | 0.11056 | 0.35914 | 0.38008 | -0.33224 | -0.16964
| 7050 | 0.095401 | -0.74407 | 0.20432 | 0.48299 | -0.18324 | 0.51041 | -0.34862 | 0.39859 | 0.26577 | 0.45401
| 7051 | 0.094406 | -0.35339 | 0.094738 | 0.3537 | 0.31465 | -0.7508 | -0.18434 | 0.10261 | -0.076474 | 0.097503
| 7052 | -0.22328 | 0.37863 | 0.21013 | 0.12188 | -0.81807 | 0.021481 | -0.88554 | -0.15958 | 0.12267 | -0.82593
| 7053 | 0.57468 | -0.81372 | 0.3629 | -0.30064 | -0.66221 | 0.036309 | -0.050842 | 0.32346 | 0.074851 | 0.18926
| 7054 | -0.48435 | -0.2512 | -0.27316 | 0.011516 | 0.44818 | 0.14531 | 0.56907 | -0.0033556 | 0.17811 | -0.40679
| 7055 | 0.26359 | 0.4272 | 0.44295 | -0.15768 | 0.10094 | 0.15721 | 0.73486 | 0.3537 | -0.21495 | 0.27716
| 7056 | -0.59294 | -0.44764 | -0.18263 | -0.26047 | -0.16054 | -0.1863 | 0.79531 | 0.27591 | 0.67704 | -0.37927
| 7057 | -0.74801 | 0.23796 | -0.024756 | 0.63545 | 0.13161 | -0.84605 | 0.63353 | -0.38755 | 0.61361 | 0.069033
| 7058 | 0.15496 | -0.042242 | -0.057291 | -0.033925 | -0.34342 | 0.028764 | 0.63027 | 0.37702 | -0.54823 | 0.68807
| 7059 | 0.33781 | 0.36952 | -0.047582 | 0.11711 | 0.452 | -0.4857 | -0.15247 | -0.3425 | 0.68615 | -0.39875
| 7060 | 0.24747 | 0.38902 | 0.56125 | -0.0065716 | -0.062717 | -0.029897 | -0.44295 | 0.1082 | -0.30523 | 0.10429
| 7061 | 0.33766 | 0.09132 | 0.27371 | 0.65722 | -0.79336 | 0.25374 | 0.53128 | 0.094959 | -0.52788 | 0.21521
| 7062 | -0.10574 | 0.29793 | -0.035376 | -0.07043 | -0.2147 | 0.25495 | -0.062183 | -0.088353 | 0.33947 | -0.13936
| 7063 | -0.40527 | -0.025577 | 0.34985 | -0.1382 | 0.13207 | -0.33254 | -0.18766 | 0.55335 | 0.35494 | -0.50452
| 7064 | 0.93144 | 0.30007 | 0.4078 | -0.47227 | -0.98268 | -0.079728 | 0.18006 | 0.41802 | -0.17229 | 0.30179
| 7065 | 0.41357 | 0.051159 | -0.21406 | -0.81807 | -0.0043595 | -0.00095045 | 0.50412 | -0.4134 | 0.9272 | 0.055278
| 7066 | 0.27522 | -0.2784 | -0.13046 | -0.16089 | -0.11779 | -0.31203 | 0.52261 | 0.055595 | -0.29594 | -0.74801
| 7067 | -0.59171 | -0.69162 | -0.85682 | -0.31174 | 0.75201 | -0.059096 | -0.24933 | 0.59689 | -0.2076 | 0.0058672
| 7068 | -0.31582 | -0.00055015 | 0.076799 | 0.29424 | 0.50351 | -0.12496 | 0.24667 | 0.25174 | -0.18852 | 0.30523
| 7069 | -0.4531 | 0.67243 | -0.38024 | 0.35324 | 0.39066 | -0.20131 | 0.35123 | 0.33856 | 0.27343 | 0.79143
| 7070 | -0.49771 | -0.16868 | -0.057397 | -0.077774 | 0.036309 | 0.74761 | -0.29325 | 0.16735 | 0.36478 | 0.58227
| 7071 | 0.19284 | -0.024141 | 0.15911 | -0.18153 | 0.55089 | 0.84031 | -0.46381 | -0.11767 | -0.38967 | -0.52767
| 7072 | -0.10764 | 0.17702 | -0.53171 | -0.5021 | -0.22547 | -0.22083 | -0.9078 | -0.64801 | 0.45219 | -0.71804
| 7073 | 0.44403 | -0.24588 | 0.31349 | -0.14204 | -0.011719 | 0.24482 | 0.23156 | 0.022912 | -0.25885 | -0.12017
| 7074 | -0.10854 | 0.33615 | -0.25629 | -0.3074 | -0.23078 | -0.030619 | 0.081904 | -0.16831 | -0.26727 | -0.33735
| 7075 | 0.54382 | 0.014657 | -0.089341 | -0.24125 | 0.055384 | 0.87077 | 0.18877 | -0.062823 | -0.2119 | 0.3681
| 7076 | -0.30639 | 0.53578 | -0.44242 | -0.31904 | 0.12519 | -0.032477 | 0.46344 | -0.85682 | -0.060266 | -0.12256
| 7077 | -0.096175 | -0.47645 | 0.0056661 | 0.10217 | 0.32881 | -0.29268 | -0.33284 | 0.21853 | -0.1196 | 0.16388
| 7078 | -0.7504 | 0.0014511 | 0.38706 | 0.19831 | 0.40376 | 0.66221 | 0.32911 | 0.87793 | 0.17109 | 0.28551
| 7079 | 0.29183 | -0.92859 | -0.63545 | -0.77439 | 0.48824 | 0.057503 | 0.39378 | 0.088134 | -0.19694 | -0.073663
| 7080 | -0.076582 | 0.44964 | -0.94255 | 0.052108 | -0.24429 | -0.0055655 | -0.69884 | 0.39428 | -0.57941 | -0.098501
| 7081 | 0.15436 | 0.48765 | -0.19346 | -0.33977 | -0.092972 | -0.12828 | -0.21279 | -0.53924 | 0.48707 | 0.058884
| 7082 | 0.36258 | 0.34342 | -0.41289 | -0.42129 | -0.26959 | 0.63353 | 0.67366 | -0.59343 | 0.2995 | -0.16988
| 7083 | 0.48532 | -0.46381 | 0.16077 | 0.15283 | -0.68267 | -0.23026 | -0.62171 | 0.40881 | 0.66519 | -0.0093941
| 7084 | -0.040052 | 0.30696 | 0.11451 | 0.15401 | 0.42825 | -0.33 | 0.36274 | 0.12416 | 0.54602 | 0.40527
| 7085 | 0.22405 | -0.0065716 | -0.2119 | 0.64433 | 0.46737 | -0.045904 | -0.088792 | 0.78763 | 0.43176 | 0.036932
| 7086 | -0.032684 | 0.66459 | -0.164 | 0.27647 | -0.019541 | -0.37911 | 0.24059 | -0.18852 | -0.1439 | 0.32228
| 7087 | 0.86108 | -0.18348 | -0.60694 | 0.57491 | -0.4985 | 0.34586 | -0.61646 | 0.53772 | 0.029073 | 0.28901
| 7088 | -0.040365 | -0.31641 | 0.58443 | 0.3425 | -0.4668 | -0.015165 | -0.007075 | -0.84094 | 0.23534 | -0.30696
| 7089 | 0.40915 | 0.95641 | 0.75161 | -0.93443 | 0.22315 | -0.65605 | 0.057397 | 0.52177 | -0.36541 | 0.058353
| 7090 | -0.35634 | -0.42598 | 0.19881 | 0.074311 | 0.1091 | -0.26754 | 0.464 | 0.16018 | -0.6265 | -0.49771
| 7091 | 0.076582 | -0.32199 | 0.40326 | -0.81862 | 0.23862 | 0.019133 | -0.42598 | -0.39875 | 0.097725 | -0.27137
| 7092 | -0.62597 | 0.21776 | -0.24138 | -0.48299 | -0.23928 | -0.18165 | -0.015368 | -0.55469 | 0.22366 | -0.36652
| 7093 | 0.14859 | -0.094185 | 0.48551 | 0.2625 | -0.037451 | 0.28663 | -0.58371 | 0.12063 | 0.48493 | -0.20282
| 7094 | -0.27647 | -0.70794 | 0.15 | -0.42633 | -0.22045 | -0.6631 | -0.34129 | -0.19744 | 0.61882 | -0.029897
| 7095 | -0.91938 | -0.5019 | 0.045484 | -0.044961 | 0.46718 | 0.44439 | 0.85823 | -0.45255 | 0.050421 | -0.65634
| 7096 | 0.32613 | -0.45365 | -0.2809 | -0.022606 | -0.34632 | 0.36747 | -0.58275 | 0.44982 | -0.10742 | -0.040052
| 7097 | 0.16244 | 0.3167 | -0.13878 | 0.152 | -0.21687 | -0.19396 | -0.23875 | -0.008486 | 0.095732 | 0.14239
| 7098 | -0.24654 | -0.41425 | -0.34357 | 0.12644 | -0.087805 | -0.90356 | 0.26007 | -0.081142 | 0.11214 | 0.40763
| 7099 | 0.077232 | -0.064318 | -0.58976 | 0.25818 | 0.0069743 | -0.3087 | -0.18618 | 0.63627 | -0.16436 | 0.25549
| 7100 | -0.46568 | -0.77751 | -0.1775 | -0.055807 | -0.27688 | -0.73186 | -0.093965 | -0.27274 | -0.75444 | -0.5245
| 7101 | 0.28972 | 0.41238 | 0.11892 | -0.35758 | -0.26061 | -0.57703 | -0.2674 | -0.72305 | -0.36008 | -0.28958
| 7102 | -0.04266 | 0.15721 | 0.24694 | 0.86847 | 0.21942 | 0.05422 | -0.080816 | 0.23574 | 0.32613 | -0.057609
| 7103 | 0.39759 | -0.20194 | 0.86108 | -0.86847 | -0.015063 | 0.31465 | -0.34053 | 0.080163 | -0.024346 | 0.2119
| 7104 | 0.66758 | 0.63599 | 0.36086 | 0.1063 | -0.24402 | -0.10585 | -0.56653 | -0.34372 | 0.60238 | 0.81917
| 7105 | 0.26007 | 0.2755 | -0.37048 | -0.14437 | -0.40042 | -0.34083 | 0.14648 | 0.13265 | 0.70184 | 0.070323
| 7106 | -0.83417 | -0.55989 | -0.14566 | -0.020663 | -0.18889 | 0.37702 | 0.17374 | 0.067101 | -0.55875 | -0.1072
| 7107 | -0.55357 | -0.68016 | -0.3129 | 0.25482 | 0.18312 | 0.033408 | 0.27716 | 0.24628 | -0.18606 | 0.28243
| 7108 | -0.070968 | 0.35062 | 0.42546 | -0.24469 | -0.60113 | -0.67581 | -0.13207 | 0.56977 | -0.29523 | -0.41272
| 7109 | -0.86252 | 0.17787 | 0.047057 | 0.55694 | -0.13855 | -0.082776 | 0.0028541 | 0.41768 | -0.019337 | -0.30711
| 7110 | -0.77306 | 0.6985 | -0.2037 | 0.18717 | -0.42511 | 0.23508 | 0.46493 | 0.021481 | 0.007478 | 0.24086
| 7111 | 0.57374 | 0.51389 | -0.044751 | -0.11349 | -0.42441 | 0.63054 | -0.11259 | -0.25321 | 0.35432 | -0.022606
| 7112 | 0.39362 | 0.3651 | 0.82651 | -0.34372 | -0.2377 | 0.061757 | 0.2042 | 0.45991 | -0.093303 | 0.66192
| 7113 | -0.78023 | -0.7816 | 0.42965 | -0.24442 | 0.3312 | -0.36258 | 0.33015 | 0.09088 | -0.085396 | -0.31553
| 7114 | 0.10876 | 0.53837 | -0.28719 | -0.50392 | 0.28035 | -0.22857 | 0.39049 | 0.02281 | 0.34418 | -0.2234
| 7115 | -0.21165 | 0.52471 | 0.23849 | 0.66668 | 0.23534 | 0.83783 | 0.35494 | 0.33781 | 0.053058 | 0.28916
| 7116 | -0.39066 | 0.4985 | 0.27343 | 0.31451 | 0.23613 | -0.264 | -0.52408 | -0.2809 | -0.075825 | -0.46065
| 7117 | 0.19919 | -0.41442 | 0.0068736 | 0.82422 | 0.41289 | 0.40865 | -0.12496 | -0.21419 | 0.38967 | -0.28397
| 7118 | 0.42355 | 0.61699 | -0.53256 | 0.13034 | 0.32985 | 0.68936 | 0.040365 | 0.30337 | 0.5883 | -0.056761
| 7119 | 0.23587 | 0.037244 | -0.12989 | -0.67458 | 0.40427 | 0.072908 | -0.14988 | 0.12496 | -0.62811 | -0.2047
| 7120 | 0.026912 | -0.61051 | 0.2256 | -0.10798 | -0.086928 | -0.53859 | 0.13855 | -0.51082 | -0.10596 | 0.65722
| 7121 | -0.36353 | -0.099944 | -0.014556 | 0.068281 | -0.54514 | -0.43511 | -0.24455 | -0.17423 | -0.29979 | 0.048948
| 7122 | 0.69227 | 0.42233 | 0.074743 | -0.0085869 | -0.14402 | -0.20924 | 0.33962 | -0.26196 | 0.16627 | -0.39775
| 7123 | 0.56514 | -0.17775 | -0.32672 | -0.41051 | 0.69619 | 0.029794 | -0.42912 | 0.10061 | 0.11541 | -0.094517
| 7124 | 0.91693 | -0.019133 | -0.44782 | -0.051264 | -0.2119 | 0.21279 | -0.011516 | 0.248 | 0.42043 | 0.19557
| 7125 | 0.19869 | 0.45843 | 0.065495 | -0.48473 | -0.059096 | 0.34708 | -0.46213 | 0.39131 | 0.75282 | -0.098945
| 7126 | -0.34617 | -0.70657 | -0.68456 | -0.62597 | 0.15106 | 0.30769 | -0.27744 | 0.2431 | 0.62304 | 0.048633
| 7127 | -0.16197 | -0.15519 | 0.31334 | 0.71347 | -0.56606 | -0.13855 | 0.14472 | 0.18018 | -0.064853 | 0.10362
| 7128 | 0.0866 | 0.53664 | 0.52324 | 0.17278 | -0.35977 | 0.76784 | 0.74212 | 0.70931 | 0.57941 | -0.27509
| 7129 | -0.62277 | 0.059628 | 0.35448 | -0.60138 | 0.25374 | -0.14344 | 0.4981 | 0.55627 | 0.26713 | -0.015876
| 7130 | 0.30725 | 0.15082 | -0.58443 | -0.3189 | -0.033822 | -0.64042 | 0.36699 | -0.22071 | -0.23404 | 0.19869
| 7131 | -0.50432 | -0.35046 | -0.38902 | 0.37159 | 0.4279 | -0.35494 | 0.13 | 0.52682 | -0.10888 | -0.28495
| 7132 | 0.28635 | 0.65547 | -0.21559 | -0.38543 | 0.76272 | 0.30711 | 0.1863 | 0.048633 | -0.41648 | -0.10228
| 7133 | -0.33209 | 0.79 | 0.13104 | 0.27343 | 0.69784 | 0.22109 | -0.13588 | 0.019337 | 0.59049 | 0.13878
| 7134 | -0.73111 | 0.52031 | 0.32658 | -0.36305 | -0.34647 | -0.16735 | -0.097614 | 0.54382 | -0.59863 | -0.036724
| 7135 | 0.29509 | 0.13092 | -0.02322 | -0.78251 | 0.060266 | 0.31538 | -0.28132 | 0.033822 | 0.067101 | -0.19682
| 7136 | -0.51637 | -0.78952 | 0.26373 | -0.72054 | 0.77528 | -0.74212 | -0.43546 | 0.088243 | -0.61103 | -0.23469
| 7137 | 0.48318 | 0.22663 | -0.42337 | 0.49196 | 0.095954 | 0.36668 | -0.49 | -0.29353 | 0.64125 | -0.54558
| 7138 | -0.088024 | -0.89091 | -0.70017 | -0.8454 | -0.038179 | -0.095732 | 0.53449 | -0.13334 | 0.51802 | -0.13959
| 7139 | -0.22225 | -0.35774 | 0.62677 | -0.080489 | -0.17508 | -0.026398 | -0.19012 | 0.43617 | -0.56262 | 0.65029
| 7140 | -0.4272 | 0.2816 | -0.84933 | -0.17641 | -0.15733 | -0.10429 | -0.35774 | -0.081795 | 0.38267 | 0.08649
| 7141 | 0.11756 | 0.04172 | 0.15118 | 0.27882 | 0.68267 | 0.25107 | 0.37944 | 0.50776 | -0.4801 | 0.1466
| 7142 | 0.2567 | 0.76021 | 0.64042 | -0.16066 | 0.5469 | 0.28453 | 0.35945 | 0.02322 | 0.72233 | 0.23
| 7143 | 0.28887 | 0.16783 | -0.43653 | -0.2377 | 0.22689 | -0.54889 | -0.23823 | 0.15626 | 0.14624 | -0.31349
| 7144 | -0.59614 | -0.011314 | 0.28063 | -0.59318 | -0.69194 | -0.29452 | -0.12028 | 0.46213 | -0.095843 | -0.09121
| 7145 | -0.45622 | 0.3593 | 0.31699 | 0.38771 | 0.36668 | -0.69718 | 0.38332 | -0.25361 | -0.074851 | -0.21981
| 7146 | 0.60567 | -0.38494 | 0.53192 | 0.3864 | 0.29921 | -0.029382 | -0.59565 | -0.55223 | 0.011415 | -0.36668
| 7147 | -0.053058 | -0.56838 | -0.013339 | 0.085615 | -0.2809 | 0.41391 | 0.34877 | 0.08343 | -0.025988 | 0.14017
| 7148 | 0.46065 | -0.045799 | -0.082231 | 0.7245 | -0.25723 | -0.69324 | -0.30653 | -0.010404 | -0.58227 | 0.027323
| 7149 | 0.11236 | 0.42772 | -0.40611 | 0.60592 | 0.09198 | -0.22909 | 0.2893 | -0.22263 | 0.04026 | -0.79336
| 7150 | 0.063677 | -0.058671 | 0.27165 | 0.13924 | -0.336 | 0.12713 | -0.5332 | -0.7492 | -0.13034 | -0.032064
| 7151 | 0.18827 | 0.70897 | 0.37159 | 0.097393 | 0.49433 | 0.55875 | 0.020153 | -0.0078811 | 0.56216 | -0.16484
| 7152 | 0.11326 | -0.54956 | 0.52513 | -0.1628 | 0.51678 | -0.096728 | 0.81752 | 0.34908 | -0.24283 | -0.80075
| 7153 | -0.31465 | 0.44583 | -0.43884 | -0.79191 | 0.38738 | 0.23417 | 0.20219 | -0.67274 | 0.022196 | -0.53967
| 7154 | 0.076907 | -0.25428 | -0.4265 | -0.29113 | 0.51 | 0.060585 | 0.044856 | 0.58083 | -0.24535 | 0.78716
| 7155 | 0.13843 | 0.67396 | 0.5009 | -0.16747 | 0.3681 | 0.52115 | 0.015063 | -0.59988 | 0.047267 | -0.47208
| 7156 | -0.010404 | -0.1597 | -0.29226 | 0.67396 | 0.2287 | 0.49275 | 0.75731 | 0.62543 | -0.13207 | 0.056231
| 7157 | 0.43211 | 0.32717 | 0.022401 | 0.30308 | -0.6786 | -0.044123 | -0.60465 | 0.15638 | -0.41511 | 0.014759
| 7158 | 0.028764 | -0.00075028 | 0.09154 | 0.28299 | 0.16519 | -0.36368 | 0.58179 | 0.43352 | -0.46887 | 0.44873
| 7159 | -0.0995 | 0.33555 | 0.2755 | 0.83357 | 0.22831 | 0.23208 | 0.46605 | 0.26142 | -0.0016514 | 0.093082
| 7160 | 0.73411 | -0.092531 | -0.13 | -0.57609 | 0.0033556 | -0.39461 | 0.41871 | -0.31465 | -0.043078 | -0.59245
| 7161 | -0.39164 | 0.12736 | 0.061011 | 0.44565 | -0.77887 | 0.036621 | 0.38494 | -0.15733 | 0.35077 | 0.11881
| 7162 | -0.52661 | -0.028558 | 0.29509 | -0.1237 | 0.36731 | -0.34862 | 0.043496 | -0.67366 | -0.60821 | -0.19037
| 7163 | -0.33254 | 0.045484 | -0.23456 | -0.85474 | 0.0023528 | -0.35883 | -0.044856 | 0.73186 | -0.27619 | 0.37382
| 7164 | 0.46195 | 0.065816 | 0.3796 | -0.46849 | -0.29893 | 0.16185 | -0.5469 | -0.018522 | 0.5347 | -0.26291
| 7165 | 0.44224 | 0.040573 | 0.67488 | -0.1533 | -0.11767 | 0.20056 | -0.23744 | 0.58155 | 0.11169 | 0.70217
| 7166 | 0.59122 | 0.61803 | -0.14006 | -0.42459 | 0.58587 | -0.019133 | -0.78251 | -0.72414 | 0.13288 | 0.47588
| 7167 | -0.0068736 | -0.44818 | 0.58854 | 0.43423 | 0.026809 | 0.02322 | -0.48493 | -0.010101 | -0.098058 | 0.32717
| 7168 | 0.031135 | 0.23574 | -0.23221 | 0.092972 | -0.43211 | 0.56722 | 0.077016 | 0.081686 | -0.76484 | -0.89464
| 7169 | 0.0081835 | -0.11281 | -0.033305 | 0.40192 | -0.3303 | 0.27165 | 0.032064 | -0.24416 | -0.042033 | -0.76569
| 7170 | -0.11552 | -0.2948 | 0.29155 | -0.60923 | -0.47684 | -0.6249 | 0.3681 | -0.68235 | 0.27178 | -0.0049623
| 7171 | -0.072045 | 0.64602 | 0.082667 | 0.13311 | 0.074851 | -0.448 | -0.38494 | 0.16054 | -0.39049 | 0.0049623
| 7172 | 0.29694 | -0.12233 | -0.031548 | -0.2431 | 0.12931 | -0.022503 | 0.19012 | -0.027426 | -0.38592 | -0.013035
| 7173 | 0.34586 | -0.24734 | -0.028558 | 0.47894 | 0.22495 | 0.63599 | 0.16209 | -0.06325 | -0.1034 | -0.66789
| 7174 | -0.29566 | -0.41017 | -0.068603 | 0.49592 | 0.27096 | 0.19806 | 0.034236 | -0.34464 | -0.19607 | 0.61283
| 7175 | 0.45898 | -0.55762 | -0.53492 | 0.17036 | 0.043705 | 0.4776 | -0.13334 | 0.030928 | -0.2184 | -0.00065021
| 7176 | 0.12564 | 0.73223 | 0.52576 | 0.27096 | -0.12359 | 0.25764 | 0.3312 | 0.41357 | 0.84157 | 0.10083
| 7177 | 0.12119 | -0.27868 | -0.39279 | 0.64914 | -0.17532 | 0.10843 | 0.30007 | 0.7881 | 0.33344 | 0.62384
| 7178 | 0.6338 | 0.81106 | 0.65086 | -0.3651 | -0.27302 | -0.063464 | -0.40848 | 0.57869 | -0.41119 | 0.11858
| 7179 | -0.30021 | 0.020766 | 0.29339 | -0.5174 | -0.66668 | -0.43688 | -0.82479 | 0.50898 | 0.45018 | 0.34159
| 7180 | 0.099833 | -0.71698 | 0.35262 | 0.25926 | -0.038907 | 0.1204 | 0.69884 | -0.016384 | -0.19595 | 0.048107
| 7181 | 0.093192 | -0.038595 | -0.23836 | -0.040573 | 0.18963 | 0.080924 | -0.12679 | -0.54011 | 0.15744 | 0.64715
| 7182 | 0.81534 | 0.37016 | -0.06957 | 0.40242 | -0.20006 | -0.36952 | -0.248 | -0.051369 | 0.47588 | -0.43902
| 7183 | 0.67891 | -0.25374 | -0.36243 | -0.75485 | -0.28355 | 0.0056661 | 0.057716 | 0.34083 | -0.44601 | -0.00015001
| 7184 | 0.039011 | 0.68839 | -0.10876 | 0.32583 | -0.38804 | -0.36652 | -0.40831 | -0.38073 | -0.041616 | -0.62946
| 7185 | -0.48843 | 0.45714 | 0.24416 | -0.12165 | 0.19408 | -0.47113 | 0.080054 | -0.7184 | -0.13646 | 0.1253
| 7186 | 0.61283 | -0.49334 | 0.40544 | 0.10017 | -0.50634 | 0.037347 | -0.099167 | 0.20106 | 0.053586 | -0.12599
| 7187 | -0.34555 | -0.35293 | -0.84736 | 0.10529 | 0.21866 | -0.52324 | -0.087805 | -0.015876 | -0.29155 | 0.13023
| 7188 | 0.042555 | -0.1565 | 0.44692 | 0.23849 | 0.27316 | -0.6952 | 0.054537 | -0.14111 | -0.30971 | 0.50553
| 7189 | -0.12805 | 0.11439 | 0.60949 | 0.10809 | 0.042033 | -0.14332 | -0.034858 | -0.0089904 | -0.65927 | 0.30408
| 7190 | 0.53946 | 0.21635 | -0.039323 | 0.46251 | -0.0091922 | 0.44277 | 0.11 | -0.12897 | 0.86036 | -0.48299
| 7191 | 0.65229 | -0.65722 | -0.21177 | -0.28118 | -0.55853 | 0.10384 | 0.47512 | 0.7015 | 0.6939 | 0.14941
| 7192 | 0.35417 | -0.26604 | 0.45182 | 0.052952 | -0.32851 | -0.71769 | -0.11202 | -0.059628 | 0.040677 | 0.46158
| 7193 | 0.45493 | -0.37143 | -0.03974 | 0.10731 | -0.42563 | -0.55649 | -0.74643 | -0.66015 | -0.12759 | 0.52957
| 7194 | -0.43317 | -0.10921 | 0.21891 | 0.38267 | -0.18815 | -0.059415 | -0.5959 | -0.12347 | 0.2147 | -0.18815
| 7195 | 0.29099 | -0.51266 | 0.63163 | -0.74135 | 0.2791 | -0.30193 | -0.065067 | -0.26427 | 0.81917 | -0.05
| 7196 | 0.42772 | 0.072908 | -0.035168 | -0.4755 | 0.11835 | 0.0026535 | -0.077666 | 0.81426 | -0.012225 | 0.3025
| 7197 | -0.024756 | 0.1153 | -0.21343 | -0.34129 | -0.77796 | -0.29836 | 0.60949 | 0.36368 | -0.10072 | 0.40628
| 7198 | 0.06016 | 0.43246 | -0.46139 | 0.19956 | 0.46456 | 0.60872 | -0.20207 | -0.33224 | 0.056973 | 0.33
| 7199 | 0.059947 | -0.10172 | -0.069677 | -0.41751 | -0.074851 | 0.62357 | 0.30957 | -0.10362 | 0.60415 | -0.19421
| 7200 | 0.48961 | 0.93443 | 0.098169 | 0.066244 | 0.32243 | 0.16831 | -0.45365 | -0.20232 | 0.61987 | 0.23104
| 7201 | -0.025372 | 0.29907 | 0.50756 | -0.06496 | 0.18975 | -0.39279 | -0.32273 | 0.29268 | 0.072476 | -0.12713
| 7202 | -0.63163 | 0.31349 | 0.22948 | -0.16328 | -0.46568 | -0.87311 | 0.29353 | 0.3454 | -0.46962 | 0.26495
| 7203 | 0.38218 | -0.078751 | -0.5174 | 0.20596 | -0.1884 | 0.6249 | 0.038907 | -0.033201 | -0.040365 | -0.21444
| 7204 | -0.26345 | -0.57327 | -0.67674 | 0.16221 | -0.019643 | 0.78716 | 0.72161 | 0.30322 | -0.31743 | -0.26781
| 7205 | -0.55898 | 0.36652 | 0.1775 | -0.51143 | 0.87876 | -0.47076 | 0.31247 | 0.37382 | -0.71627 | 0.20144
| 7206 | -0.54867 | 0.11631 | -0.9005 | 0.50898 | 0.85405 | -0.53213 | 0.085068 | 0.5883 | -0.77218 | 0.54098
| 7207 | -0.71698 | -0.0173 | -0.49039 | 0.2225 | -0.74801 | -0.11779 | 0.36008 | 0.33194 | -0.42598 | -0.24469
| 7208 | -0.70623 | 0.43902 | 0.39098 | 0.52157 | -0.20646 | -0.68936 | 0.041199 | 0.072692 | -0.095622 | -0.7429
| 7209 | 0.082558 | -0.53989 | 0.71592 | -0.0033556 | 0.097725 | -0.10273 | 0.64546 | 0.31422 | 0.35247 | -0.05814
| 7210 | -0.82084 | 0.070215 | -0.070753 | -0.27674 | 0.10832 | 0.30495 | 0.43018 | -0.4078 | -0.73486 | 0.12017
| 7211 | 0.27206 | 0.28007 | 0.28916 | -0.88126 | 0.79925 | -0.0062697 | -0.4857 | 0.69586 | -0.47818 | 0.6631
| 7212 | 0.093965 | 0.76272 | -0.65634 | 0.52894 | 0.25926 | -0.13104 | -0.28944 | 0.22909 | -0.30423 | -0.11541
| 7213 | 0.034858 | -0.26932 | 0.30754 | -0.2791 | 0.063891 | 0.052635 | 0.1204 | 0.31772 | 0.70083 | -0.14753
| 7214 | 0.29339 | 0.18263 | -0.27096 | -0.348 | -0.43176 | -0.51041 | -0.33194 | -0.29979 | -0.3015 | 0.44206
| 7215 | -0.19956 | 0.85405 | 0.79288 | 0.016689 | 0.19223 | -0.44009 | -0.53363 | 0.3048 | -0.51328 | -0.11892
| 7216 | -0.25321 | -0.41545 | -0.045904 | -0.38137 | 0.08136 | 0.0044599 | -0.046742 | -0.68488 | 0.070538 | 0.8747
| 7217 | -0.20069 | 0.43813 | 0.86546 | -0.63353 | -0.13161 | 0.064639 | 0.63654 | -0.45991 | 0.4995 | -0.50231
| 7218 | 0.57988 | -0.26318 | -0.25281 | -0.58854 | 0.348 | 0.60516 | 0.082776 | -0.36431 | -0.60465 | -0.088024
| 7219 | -0.23783 | 0.033615 | -0.95417 | 0.43671 | 0.48144 | -0.019439 | 0.17012 | 0.11326 | -0.23482 | 0.27151
| 7220 | 0.43777 | 0.36968 | -0.62865 | -0.54448 | 0.57893 | -0.17848 | 0.27302 | 0.27771 | 0.051159 | -0.60744
| 7221 | -0.33615 | -0.12074 | -0.38738 | -0.22637 | 0.29864 | -0.58708 | -0.074959 | -0.77932 | -0.74174 | -0.52809
| 7222 | -0.23325 | -0.49473 | 0.088243 | 0.75282 | -0.024346 | -0.50573 | -0.24893 | -0.76741 | 0.58012 | 0.3864
| 7223 | -0.1735 | 0.22058 | 0.0087886 | -0.16531 | -0.020868 | -0.53751 | 0.066887 | 0.46306 | 0.086709 | 0.38008
| 7224 | 0.51472 | 0.27578 | -0.033098 | -0.26142 | -0.23888 | -0.18336 | -0.35899 | -0.40259 | -0.43582 | 0.86696
| 7225 | -0.16101 | 0.16352 | 0.006169 | -0.68141 | 0.21368 | 0.17933 | -0.045799 | -0.11654 | -0.56838 | -0.23338
| 7226 | 0.67396 | 0.50594 | 0.049053 | 0.32821 | -0.54911 | 0.57869 | -0.28916 | -0.40125 | -0.061864 | -0.16256
| 7227 | 0.039635 | 0.58203 | -0.16173 | -0.56057 | -0.04026 | -0.32583 | 0.01091 | 0.0073772 | 0.10239 | -0.16448
| 7228 | 0.32243 | -0.52873 | 0.044856 | 0.72161 | 0.35401 | -0.26101 | -0.094627 | 0.015063 | 0.36526 | -0.030412
| 7229 | 0.12989 | -0.17036 | -0.88467 | 0.029897 | -0.050105 | 0.82422 | -0.013643 | -0.51328 | -0.010505 | -0.29879
| 7230 | 0.16209 | 0.29993 | -0.59441 | 0.29864 | 0.53128 | -0.035065 | 0.050211 | 0.50959 | 0.56768 | 0.45714
| 7231 | -0.62304 | 0.015063 | -0.54294 | 0.15118 | -0.16603 | 0.27688 | 0.16964 | -0.72742 | -0.28621 | -0.33299
| 7232 | -0.68647 | -0.47914 | -0.040573 | 0.41854 | -0.039427 | -0.58805 | 0.10798 | 0.042033 | -0.85337 | -0.09055
| 7233 | -0.12017 | -0.09839 | -0.43018 | -0.24774 | -0.1253 | -0.044333 | 0.46643 | -0.45732 | -0.014759 | 0.30797
| 7234 | -0.20697 | -0.0093941 | -0.83969 | 0.93755 | -0.65 | 0.039011 | 0.66549 | -0.39942 | -0.018318 | -0.48687
| 7235 | -0.83118 | -0.11157 | 0.29056 | 0.057503 | -0.31378 | 0.25549 | 0.03465 | 0.31831 | -0.85 | 0.56768
| 7236 | -0.24614 | -0.070968 | -0.26223 | -0.089561 | 0.11654 | 0.89464 | 0.61882 | -0.13473 | -0.012326 | -0.59639
| 7237 | 0.45237 | -0.17799 | 0.71627 | 0.30538 | 0.17836 | 0.4683 | -0.22366 | 0.53967 | 0.68936 | -0.11654
| 7238 | -0.34494 | 0.80532 | -0.15295 | 0.60617 | 0.30122 | -0.68807 | 0.0030547 | -0.22805 | -0.76957 | -0.25281
| 7239 | 0.78529 | -0.30007 | -0.32762 | 0.32273 | 0.040156 | 0.22135 | -0.59714 | -0.0781 | -0.18434 | 0.31407
| 7240 | 0.39246 | 0.30394 | 0.25361 | 0.12028 | 0.38299 | -0.11079 | 0.066673 | 0.69162 | -0.15342 | -0.48222
| 7241 | 0.47341 | 0.24654 | -0.10083 | -0.65868 | 0.18434 | -0.18557 | 0.24508 | -0.4993 | 0.049369 | -0.23587
| 7242 | 0.14906 | -0.042764 | 0.46925 | 0.14718 | 0.52788 | 0.24522 | -0.11938 | 0.34159 | -0.90566 | 0.26808
| 7243 | -0.48202 | 0.43866 | -0.28579 | 0.31145 | -0.23208 | 0.25804 | 0.38073 | 0.076258 | -0.5721 | 0.68743
| 7244 | 0.10966 | -0.20069 | 0.11688 | -0.38024 | 0.4163 | -0.25347 | -0.055913 | -0.74174 | -0.018725 | -0.05158
| 7245 | -0.76063 | -0.4307 | 0.94255 | -0.4997 | 0.30408 | -0.81917 | -0.51782 | 0.1473 | 0.40831 | 0.25482
| 7246 | 0.18177 | -0.01791 | -0.055595 | -0.32524 | 0.27744 | 0.16507 | 0.40527 | 0.19124 | -0.66192 | -0.34693
| 7247 | -0.069033 | 0.62704 | 0.46699 | -0.43546 | -0.74329 | 0.68807 | 0.3537 | 0.38804 | 0.24601 | 0.084304
| 7248 | 0.20307 | -0.42563 | 0.24588 | 0.37095 | -0.37944 | 0.17459 | 0.19557 | 0.28397 | 0.17024 | -0.51865
| 7249 | 0.47645 | 0.19062 | -0.62919 | -0.50412 | -0.024551 | -0.57893 | 0.27041 | -0.033512 | 0.13334 | -0.3129
| 7250 | -0.36731 | 0.35308 | -0.36274 | -0.20899 | 0.07183 | -0.011921 | -0.28789 | -0.10899 | -0.41819 | 0.53427
| 7251 | -0.30624 | 0.33796 | 0.29836 | 0.66849 | 0.75648 | -0.26074 | -0.028867 | -0.023117 | 0.11518 | 0.17181
| 7252 | -0.28104 | -0.033098 | -0.050948 | -0.60846 | -0.53859 | 0.69488 | -0.54076 | -0.33917 | 0.89753 | -0.80635
| 7253 | -0.37159 | 0.5003 | -0.20407 | -0.49532 | -0.12816 | 0.21738 | 0.41306 | -0.3005 | -0.71382 | 0.39676
| 7254 | 0.16627 | 0.41974 | 0.028249 | -0.37799 | 0.67922 | 0.32776 | -0.11383 | -0.013744 | 0.10787 | 0.34296
| 7255 | 0.078208 | -0.062503 | -0.030825 | -0.042973 | 0.3303 | -0.14484 | 0.15153 | 0.024654 | -0.17386 | 0.12085
| 7256 | -0.40376 | -0.05496 | -0.013846 | 0.06603 | -0.024859 | -0.077774 | -0.33239 | 0.073555 | 0.26945 | -0.17945
| 7257 | 0.37382 | -0.58347 | 0.7816 | 0.41665 | 0.14824 | 0.050105 | -0.52555 | -0.19371 | 0.75403 | -0.4987
| 7258 | -0.61803 | -0.35278 | 0.74368 | 0.54207 | 0.60038 | 0.024654 | 0.33479 | -0.99 | 0.4997 | 0.55022
| 7259 | 0.45036 | -0.13357 | 0.28579 | -0.23836 | -0.17012 | 0.57515 | 0.39975 | 0.096839 | 0.16316 | 0.065923
| 7260 | -0.28299 | -0.72197 | 0.25334 | 0.027632 | -0.056655 | -0.23875 | 0.43476 | 0.63875 | 0.011314 | -0.18975
| 7261 | -0.077232 | -0.136 | -0.48824 | -0.9078 | -0.22883 | -0.42147 | 0.065281 | 0.9005 | -0.23182 | -0.41699
| 7262 | 0.082776 | -0.12862 | -0.552 | -0.66519 | -0.56194 | -0.32762 | -0.37223 | 0.68743 | 0.070968 | 0.05422
| 7263 | -0.13034 | 0.0032553 | -0.2516 | -0.54142 | 0.43387 | 0.27813 | 0.0087886 | -0.52198 | 0.23613 | 0.21648
| 7264 | 0.35525 | 0.023936 | -0.099833 | -0.20194 | 0.11665 | -0.20006 | -0.024141 | -0.58395 | 0.039323 | 0.31436
| 7265 | -0.48785 | -0.077016 | -0.33917 | 0.25576 | -0.46549 | -0.45677 | -0.19632 | -0.23234 | 0.65751 | -0.11022
| 7266 | 0.15958 | -0.31685 | 0.61077 | 0.76188 | -0.79579 | -0.36008 | 0.040156 | 0.32214 | -0.027323 | 0.41562
| 7267 | 0.012934 | -0.12324 | 0.1237 | 0.24376 | -0.06957 | 0.73223 | 0.57397 | 0.32258 | -0.15059 | 0.052635
| 7268 | -0.64715 | 0.11665 | 0.9219 | -0.2047 | 0.097503 | -0.48882 | -0.039115 | 0.28411 | 0.034443 | -0.39016
| 7269 | 0.68047 | 0.1879 | 0.012934 | -0.018827 | -0.70691 | -0.081577 | -0.52513 | 0.062397 | 0.62704 | -0.15946
| 7270 | 0.18803 | 0.74643 | -0.86252 | 0.43018 | -0.28621 | -0.60088 | 0.20294 | 0.52408 | 0.01486 | -0.01415
| 7271 | -0.24601 | -0.79579 | 0.23078 | 0.51782 | -0.14227 | 0.062183 | 0.11767 | 0.27827 | -0.36841 | -0.24907
| 7272 | 0.30957 | 0.35386 | -0.016181 | 0.11496 | -0.5007 | -0.58539 | 0.12279 | -0.2985 | 0.57562 | 0.71982
| 7273 | 0.80739 | -0.098279 | -0.2625 | -0.65722 | 0.33449 | 0.54033 | -0.0059678 | 0.28733 | -0.32732 | -0.73111
| 7274 | -0.10306 | -0.19161 | -0.57047 | -0.252 | -0.47952 | 0.53363 | -0.2773 | 0.024551 | 0.32302 | 0.013643
| 7275 | -0.52851 | 0.57562 | 0.5707 | 0.086381 | -0.033098 | -0.16054 | -0.53107 | -0.025577 | -0.37223 | 0.42181
| 7276 | -0.15923 | -0.22547 | -0.22225 | 0.3372 | -0.1628 | 0.22663 | -0.043914 | -0.3864 | 0.5172 | -0.61
| 7277 | 0.71417 | -0.17205 | -0.53363 | 0.33134 | 0.15816 | 0.21228 | -0.452 | 0.061544 | 0.36699 | 0.20697
| 7278 | -0.31611 | -0.4265 | 0.12805 | -0.25495 | 0.14414 | 0.27633 | -0.73599 | -0.24482 | -0.13473 | 0.84736
| 7279 | -0.66758 | 0.77528 | 0.91225 | -0.030619 | -0.010101 | 0.87958 | 0.25643 | -0.0042591 | 0.436 | -0.29736
| 7280 | -0.46474 | -0.20583 | 0.021992 | 0.26767 | -0.49512 | -0.16759 | 0.31582 | -0.12874 | 0.33826 | -0.24614
| 7281 | 0.67612 | 0.040886 | -0.50231 | 0.086819 | 0.15295 | 0.0728 | 0.088243 | -0.11011 | -0.014962 | -0.42912
| 7282 | -0.018725 | 0.69292 | 0.12553 | -0.77887 | -0.16916 | -0.11541 | -0.10406 | -0.019031 | -0.72852 | 0.47474
| 7283 | 0.0091922 | -0.11124 | -0.083649 | 0.64829 | 0.28593 | -0.68647 | -0.38951 | -0.052846 | 0.74446 | -0.61438
| 7284 | -0.32672 | 0.6382 | -0.39527 | -0.88909 | 0.3796 | -0.22096 | -0.18864 | 0.25307 | 0.17241 | 0.82365
| 7285 | 0.51554 | -0.23587 | 0.38592 | -0.33675 | -0.30365 | 0.78483 | -0.14871 | -0.15673 | 0.54867 | -0.78068
| 7286 | -0.43264 | 0.75731 | 0.09 | -0.28944 | 0.56216 | 0.30523 | -0.70251 | 0.39411 | 0.22611 | -0.55604
| 7287 | 0.7184 | -0.13311 | 0.52429 | 0.87631 | 0.011516 | 0.84801 | -0.56722 | -0.15828 | 0.39312 | 0.30812
| 7288 | -0.36968 | 0.064105 | -0.44421 | -0.14765 | -0.6995 | 0.65229 | -0.67612 | 0.013643 | 0.43884 | 0.60668
| 7289 | -0.31232 | 0.7076 | -0.39066 | -0.14006 | -0.81752 | 0.3242 | -0.20546 | -0.18643 | 0.16892 | 0.23078
| 7290 | 0.70691 | 0.16125 | 0.55717 | 0.40527 | 0.064853 | -0.27467 | -0.79143 | -0.6811 | -0.76357 | -0.1735
| 7291 | -0.52052 | -0.27041 | 0.42895 | 0.36699 | 0.18901 | -0.77617 | -0.042138 | -0.49473 | 0.10664 | -0.49691
| 7292 | 0.42112 | -0.033615 | 0.18446 | 0.32022 | 0.14215 | 0.3148 | -0.0076795 | -0.27965 | 0.13346 | -0.14554
| 7293 | 0.51969 | 0.22896 | -0.15626 | 0.33977 | -0.63217 | 0.40898 | 0.43334 | 0.18741 | -0.6578 | 0.16137
| 7294 | -0.14918 | -0.37446 | -0.023322 | -0.096839 | -0.51205 | 0.65518 | -0.552 | -0.34403 | -0.34923 | 0.045484
| 7295 | -0.3951 | -0.35883 | -0.075825 | -0.58036 | -0.083103 | 0.13971 | -0.14636 | 0.19769 | -0.4337 | -0.11281
| 7296 | 0.25643 | 0.70285 | -0.56653 | -0.17036 | -0.071291 | 0.66192 | -0.62838 | 0.0062697 | -0.08136 | -0.56791
| 7297 | -0.26686 | -0.05158 | 0.55134 | -0.41665 | -0.6939 | -0.19632 | 0.078425 | -0.42459 | -0.1513 | 0.038595
| 7298 | -0.57822 | -0.030206 | -0.055701 | 0.34311 | -0.26034 | 0.16964 | 0.73637 | 0.71382 | -0.35758 | -0.27261
| 7299 | 0.05253 | -0.48415 | 0.03 | 0.7042 | -0.086271 | -0.10451 | -0.34555 | 0.53064 | -0.81265 | 0.10473
| 7300 | 0.012326 | 0.29551 | -0.40025 | 0.61699 | -0.44891 | -0.11609 | 0.47531 | 0.017503 | 0.62919 | -0.18741
| 7301 | 0.099056 | 0.77218 | -0.39942 | -0.10161 | -0.82941 | 0.7508 | -0.094848 | 0.69917 | 0.11631 | 0.096064
| 7302 | -0.14134 | 0.14824 | 0.23678 | 0.29495 | -0.78529 | 0.90566 | 0.15094 | -0.040365 | -0.31993 | 0.35603
| 7303 | 0.45219 | 0.34083 | 0.94615 | 0.39576 | 0.92584 | -0.47703 | 0.29 | 0.12119 | 0.13959 | -0.58951
| 7304 | 0.25174 | 0.17362 | -0.93443 | -0.19384 | -0.64461 | -0.53299 | 0.24442 | -0.60923 | -0.5714 | -0.0866
| 7305 | -0.46102 | -0.40427 | -0.24283 | -0.33269 | 0.44656 | 0.39164 | -0.094517 | 0.41374 | -0.098279 | -0.41819
| 7306 | 0.6546 | 0.43352 | -0.42355 | 0.61257 | -0.50573 | 0.28076 | -0.64971 | 0.25926 | -0.53342 | -0.61987
| 7307 | -0.69917 | 0.33539 | -0.88381 | 0.44045 | 0.11011 | 0.54624 | -0.015673 | -0.064318 | -0.16089 | 0.23039
| 7308 | 0.36211 | -0.17386 | -0.013542 | -0.64546 | -0.11484 | 0.0071757 | 0.12199 | 0.26468 | 0.2343 | -0.71627
| 7309 | -0.2398 | 0.078751 | -0.0017515 | -0.031135 | 0.31029 | 0.32702 | 0.65489 | 0.30007 | -0.03434 | -0.24178
| 7310 | -0.13196 | 0.39296 | -0.70217 | -0.41357 | 0.50857 | -0.099722 | -0.37702 | 0.47341 | 0.10473 | 0.87233
| 7311 | -0.037451 | 0.20432 | 0.071291 | -0.074743 | 0.80584 | -0.9245 | 0.15224 | 0.34846 | -0.59913 | 0.25321
| 7312 | -0.36196 | -0.12119 | -0.41751 | 0.41648 | -0.068388 | 0.64574 | 0.41648 | -0.15425 | -0.51513 | -0.38608
| 7313 | -0.23534 | 0.23678 | 0.74212 | 0.36039 | 0.40092 | 0.1237 | 0.04099 | 0.29353 | -0.64801 | -0.38804
| 7314 | 0.60339 | 0.24694 | 0.0049623 | 0.18889 | 0.46121 | 0.67061 | 0.10072 | -0.35031 | 0.49137 | 0.16699
| 7315 | -0.24522 | 0.25926 | -0.014657 | -0.71911 | 0.51184 | 0.10541 | 0.1162 | -0.24707 | -0.085724 | 0.22456
| 7316 | 0.66489 | 0.20684 | 0.24125 | -0.17072 | 0.37127 | 0.02097 | -0.64405 | -0.48512 | -0.4995 | 0.42095
| 7317 | 0.6241 | -0.17714 | 0.30122 | -0.80176 | 0.35774 | 0.0032553 | 0.077883 | 0.40494 | 0.040365 | 0.042764
| 7318 | 0.1688 | -0.030619 | 0.11983 | -0.15602 | -0.60263 | 0.55156 | 0.78206 | 0.22058 | -0.152 | 0.15851
| 7319 | 0.46158 | -0.75979 | 0.68968 | 0.31978 | 0.24099 | -0.065067 | -0.05253 | -0.037867 | -0.67829 | -0.73448
| 7320 | 0.81053 | -0.71982 | -0.65143 | 0.014962 | -0.015368 | 0.38624 | -0.61387 | -0.60974 | -0.47132 | -0.77439
| 7321 | 0.0033556 | 0.3372 | 0.69751 | -0.22844 | -0.3851 | -0.52429 | 0.43053 | -0.047582 | -0.41922 | -0.1706
| 7322 | 0.32821 | -0.15496 | 0.14344 | 0.26359 | -0.24548 | 0.14519 | -0.56537 | -0.14227 | 0.28789 | -0.33239
| 7323 | 0.33239 | 0.32169 | 0.035479 | -0.77751 | 0.50251 | 0.76357 | 0.10933 | -0.72486 | 0.071614 | 0.82084
| 7324 | 0.11994 | -0.20924 | 0.028146 | -0.27453 | -0.37223 | 0.33299 | -0.1803 | -0.1863 | -0.71522 | -0.07962
| 7325 | -0.045589 | -0.062183 | 0.062823 | 0.21866 | 0.045275 | -0.13785 | -0.28021 | 0.64687 | 0.40042 | -0.22135
| 7326 | -0.053903 | 0.082994 | 0.30079 | 0.41204 | 0.1646 | 0.01182 | -0.12188 | -0.78251 | 0.031961 | -0.54624
| 7327 | 0.14965 | 0.59565 | 0.70897 | 0.43635 | 0.40645 | 0.55537 | -0.38967 | 0.92584 | 0.0091922 | 0.085287
| 7328 | 0.51927 | 0.056549 | -0.32821 | 0.037451 | -0.53902 | -0.29765 | 0.17326 | -0.058459 | 0.34785 | 0.12908
| 7329 | 0.53686 | 0.46755 | -0.12862 | -0.20483 | 0.16424 | 0.53 | -0.19483 | -0.061864 | 0.52052 | -0.035894
| 7330 | 0.13034 | -0.51678 | 0.097725 | -0.21508 | -0.11417 | 0.058353 | -0.35062 | 0.088573 | 0.01791 | 0.19844
| 7331 | 0.13948 | -0.029073 | -0.93597 | 0.3061 | 0.33359 | 0.4588 | -0.6703 | 0.064212 | -0.16173 | 0.38559
| 7332 | 0.54558 | 0.14988 | 0.47818 | 0.33841 | -0.073016 | 0.29268 | -0.95877 | 0.3306 | 0.38559 | -0.015571
| 7333 | -0.010303 | 0.13507 | 0.48067 | 0.00035006 | -0.70217 | -0.29722 | -0.8467 | 0.43018 | 0.68775 | 0.19533
| 7334 | 0.16101 | 0.29722 | 0.045694 | -0.34892 | -0.32465 | -0.81972 | 0.16591 | -0.067316 | -0.14777 | 0.42147
| 7335 | 0.21355 | -0.2193 | -0.52136 | -0.74603 | 0.22148 | -0.11972 | -0.26808 | 0.18889 | 0.26877 | 0.057291
| 7336 | 0.050105 | -0.14204 | -0.29212 | -0.51102 | -0.033201 | -0.79239 | -0.41888 | -0.14953 | 0.32243 | 0.13901
| 7337 | -0.061224 | 0.23443 | 0.15342 | -0.71627 | 0.55921 | -0.52703 | -0.37879 | 0.6371 | 0.85964 | 0.50392
| 7338 | 0.25147 | -0.22328 | 0.043391 | -0.29608 | 0.32096 | -0.73942 | 0.078317 | 0.026193 | -0.55762 | -0.68016
| 7339 | 0.10261 | 0.81 | 0.83599 | -0.28705 | 0.060798 | -0.14894 | 0.5003 | -0.54054 | 0.28593 | -0.27055
| 7340 | -0.50654 | -0.13322 | 0.77218 | 0.51184 | 0.0040582 | -0.092862 | -0.12347 | 0.11293 | 0.024654 | -0.41905
| 7341 | 0.11858 | -0.36573 | 0.22405 | -0.032581 | 0.67091 | 0.58299 | 0.44027 | -0.5011 | -0.22418 | -0.028867
| 7342 | 0.31203 | 0.1786 | -0.60516 | -0.57421 | -0.35108 | 0.41733 | -0.21063 | -0.47952 | 0.47531 | -0.1277
| 7343 | -0.13115 | -0.1803 | -0.05899 | -0.50735 | 0.72889 | -0.016791 | 0.1758 | 0.6149 | -0.2287 | 0.05814
| 7344 | 0.18741 | 0.37064 | 0.80635 | 0.41221 | -0.047792 | -0.02097 | -0.43866 | 0.32866 | 0.52031 | -0.66578
| 7345 | -0.31218 | -0.53085 | 0.22173 | 0.81212 | 0.063571 | 0.18336 | 0.64659 | 0.44692 | -0.10989 | -0.1758
| 7346 | -0.13184 | 0.18434 | -0.14285 | 0.045694 | -0.3248 | 0.09011 | -0.10128 | 0.31043 | -0.58347 | -0.16328
| 7347 | 0.0011507 | -0.25133 | 0.15094 | 0.098501 | 0.12644 | 0.17229 | 0.39 | -0.38494 | -0.23078 | -0.037555
| 7348 | 0.29651 | 0.71911 | -0.053374 | 0.0064709 | 0.58083 | -0.047477 | 0.4265 | -0.072692 | -0.42546 | -0.76957
| 7349 | -0.31758 | 0.52073 | 0.14671 | 0.032064 | 0.49118 | 0.12131 | 0.40142 | -0.39709 | -0.25174 | 0.20232
| 7350 | -0.16819 | 0.57893 | -0.21712 | -0.37207 | -0.012326 | -0.37414 | -0.051686 | -0.088134 | 0.39461 | -0.16603
| 7351 | 0.01791 | -0.91 | -0.63627 | 0.5883 | 0.54558 | 0.10395 | 0.29893 | -0.60491 | -0.56354 | -0.86252
| 7352 | 0.4542 | -0.88381 | -0.086928 | -0.37558 | -0.030619 | 0.51657 | 0.40865 | -0.88731 | -0.58903 | 0.45806
| 7353 | 0.02281 | 0.0011507 | 0.1688 | 0.69784 | -0.45347 | 0.094185 | -0.66459 | -0.31538 | 0.20131 | 0.29622
| 7354 | 0.39016 | -0.58275 | -0.57988 | 0.4799 | 0.47933 | 0.26549 | 0.58976 | 0.4979 | -0.11417 | -0.42199
| 7355 | 0.13207 | 0.17423 | 0.26522 | -0.22405 | 0.83783 | 0.41289 | -0.024039 | 0.23823 | -0.53406 | 0.6349
| 7356 | -0.78858 | -0.10106 | -0.095954 | -0.43973 | 0.10675 | -0.31029 | 0.52809 | -0.3048 | -0.30351 | 0.89851
| 7357 | -0.48144 | 0.56422 | 0.20836 | 0.56491 | 0.41922 | -0.95877 | -0.91693 | -0.3767 | -0.44619 | -0.236
| 7358 | -0.084522 | 0.26686 | -0.40949 | -0.20432 | 0.036621 | 0.15496 | -0.61882 | 0.36447 | -0.67643 | 0.072692
| 7359 | 0.1952 | 0.47227 | -0.34923 | 0.40881 | -0.17399 | -0.24707 | 0.39908 | -0.23391 | 0.15768 | -0.12702
| 7360 | 0.37895 | -0.016689 | -0.19421 | 0.16627 | 0.19446 | -0.4265 | -0.036621 | 0.53902 | -0.18938 | -0.41785
| 7361 | -0.71138 | 0.17084 | 0.20684 | -0.34433 | 0.092972 | 0.046742 | 0.18729 | -0.063357 | -0.052635 | -0.078425
| 7362 | 0.16472 | 0.16448 | -0.43582 | 0.28859 | 0.65086 | 0.16783 | 0.59441 | -0.14029 | 0.087586 | 0.15911
| 7363 | 0.087586 | -0.72559 | -0.42772 | 0.046533 | 0.16531 | 0.47417 | 0.077774 | 0.34494 | 0.26481 | -0.46549
| 7364 | -0.09187 | 0.025064 | -0.5806 | -0.41957 | -0.82084 | 0.21304 | -0.15306 | 0.35 | -0.061224 | -0.020868
| 7365 | -0.041929 | 0.47875 | 0.56011 | 0.53021 | -0.11101 | 0.20747 | -0.10072 | -0.027529 | 0.16555 | -0.41871
| 7366 | -0.44837 | -0.47246 | -0.36463 | -0.27965 | 0.32287 | 0.44511 | 0.38657 | 0.04099 | 0.33329 | 0.26061
| 7367 | 0.18287 | -0.092972 | 0.022606 | -0.53256 | 0.83538 | -0.10966 | 0.65576 | -0.35139 | 0.17677 | -0.05496
| 7368 | -0.40326 | 0.28691 | -0.61542 | -0.59269 | 0.27688 | -0.031961 | -0.053691 | 0.71804 | 0.4117 | 0.60163
| 7369 | 0.3357 | 0.12131 | 0.65956 | -0.3005 | 0.10955 | -0.3951 | 0.16101 | 0.58733 | -0.09143 | -0.0067729
| 7370 | 0.43706 | -0.055807 | -0.44945 | 0.25535 | 0.64659 | -0.17982 | 0.31029 | -0.50756 | -0.19483 | 0.15768
| 7371 | -0.29 | -0.063357 | -0.86923 | -0.70117 | 0.11745 | -0.30365 | -0.34296 | -0.47894 | 0.11056 | 0.083758
| 7372 | -0.41204 | 0.61335 | -0.29141 | -0.59343 | -0.076799 | -0.22948 | 0.22186 | -0.12805 | 0.48376 | -0.82252
| 7373 | 0.58155 | 0.39181 | -0.098279 | -0.37911 | -0.12028 | 0.35169 | -0.53989 | -0.074851 | 0.23195 | -0.05984
| 7374 | -0.73223 | 0.36889 | 0.11779 | 0.054749 | 0.21661 | 0.030309 | -0.10708 | 0.028661 | 0.38494 | 0.48648
| 7375 | -0.72305 | -0.15685 | 0.31524 | 0.44277 | 0.3167 | 0.56239 | -0.081686 | 0.52429 | -0.16795 | -0.44242
| 7376 | 0.13913 | -0.17982 | -0.27343 | -0.078208 | -0.039115 | -0.30884 | -0.22844 | -0.60694 | -0.0080827 | -0.81807
| 7377 | 0.66015 | 0.15377 | -0.35494 | -0.38396 | 0.5013 | -0.23862 | 0.74485 | 0.41306 | -0.24747 | 0.088792
| 7378 | -0.23678 | -0.027015 | -0.71769 | 0.52136 | 0.031754 | 0.095401 | 0.94255 | 0.35108 | 0.6162 | 0.36826
| 7379 | -0.26536 | 0.32051 | 0.10518 | 0.29993 | -0.3167 | -0.21725 | 0.09066 | 0.32096 | 0.41751 | -0.43671
| 7380 | -0.45511 | 0.82766 | -0.68425 | -0.66819 | 0.17592 | -0.56954 | 0.5102 | 0.29509 | 0.26795 | -0.22909
| 7381 | 0.2773 | 0.31641 | -0.67213 | 0.051475 | -0.11439 | -0.099611 | -0.45769 | 0.74174 | -0.68393 | -0.88295
| 7382 | 0.3956 | 0.02722 | 0.79239 | -0.58708 | 0.35494 | -0.46418 | -0.69097 | 0.10172 | -0.25723 | -0.27357
| 7383 | -0.4163 | 0.089012 | -0.38218 | -0.14601 | -0.45073 | -0.34892 | 0.015876 | -0.22521 | -0.68078 | -0.11067
| 7384 | 0.60491 | -0.31436 | -0.21089 | -0.12097 | -0.40645 | 0.50959 | 0.17714 | 0.13023 | -0.063891 | -0.45751
| 7385 | -0.5264 | -0.5714 | -0.46793 | 0.63081 | -0.87876 | -0.41357 | 0.031444 | -0.29921 | -0.015165 | 0.078751
| 7386 | -0.41374 | -0.39082 | 0.23744 | -0.0091922 | -0.33494 | -0.15271 | 0.015774 | -0.23809 | -0.29353 | 0.13115
| 7387 | 0.0060684 | -0.19944 | 0.2225 | 0.44295 | -0.25602 | 0.21994 | -0.40679 | -0.57374 | 0.68204 | -0.38706
| 7388 | -0.11405 | -0.42895 | 0.28035 | 0.2492 | -0.57116 | -0.40932 | -0.44277 | 0.081904 | -0.68456 | 0.1694
| 7389 | -0.19322 | -0.34448 | 0.45 | -0.0040582 | -0.56768 | -0.75526 | -0.29113 | -0.17726 | -0.95 | -0.009697
| 7390 | -0.20735 | 0.38738 | -0.28635 | 0.23888 | -0.098279 | -0.6044 | 0.43635 | 0.096064 | -0.78206 | 0.078534
| 7391 | -0.41562 | 0.37944 | -0.45475 | -0.23351 | -0.27951 | -0.67121 | -0.12885 | -0.48299 | -0.3727 | -0.38105
| 7392 | 0.56102 | 0.10809 | 0.25187 | 0.72089 | 0.37478 | 0.12828 | -0.64433 | -0.53881 | -0.24416 | -0.48765
| 7393 | 0.53342 | 0.13971 | -0.10184 | 0.32911 | 0.52282 | -0.27288 | -0.1308 | 0.23836 | 0.31728 | 0.022196
| 7394 | 0.57751 | 0.013238 | 0.72197 | -0.24933 | 0.28551 | -0.46325 | 0.35696 | -0.51287 | 0.10017 | -0.064532
| 7395 | 0.56377 | 0.1628 | 0.41442 | 0.26604 | 0.44385 | 0.79579 | 0.19881 | 0.16807 | -0.32199 | 0.16149
| 7396 | 0.14941 | 0.53989 | -0.45365 | -0.35572 | -0.45861 | -0.39016 | -0.49196 | -0.84476 | -0.026809 | 0.43423
| 7397 | 0.10228 | 0.065709 | 0.82536 | 0.97 | 0.62677 | -0.20672 | 0.31553 | -0.65897 | -0.82766 | 0.60541
| 7398 | 0.62677 | 0.09176 | 0.024654 | 0.27151 | -0.3189 | -0.48668 | -0.10261 | -0.15413 | -0.67488 | 0.13415
| 7399 | 0.023015 | 0.39444 | -0.49256 | -0.40898 | -0.085068 | 0.28789 | 0.023936 | 0.071507 | -0.75363 | -0.17133
| 7400 | -0.16519 | 0.65634 | -0.43458 | 0.30164 | -0.080816 | -0.041616 | -0.22379 | 0.15946 | 0.52219 | 0.23705
| 7401 | -0.52745 | 0.26142 | 0.27868 | -0.11067 | -0.81697 | 0.32287 | 0.071722 | 0.6257 | -0.34433 | -0.6952
| 7402 | 0.42842 | 0.13577 | -0.70184 | -0.041929 | -0.068067 | 0.34938 | 0.042973 | 0.34068 | -0.79975 | -0.66728
| 7403 | -0.1277 | -0.45328 | 0.79975 | -0.31963 | 0.86252 | 0.094627 | -0.24548 | 0.056125 | -0.10106 | -0.71592
| 7404 | 0.17435 | 0.28986 | -0.53946 | -0.32732 | -0.27633 | -0.061011 | -0.2161 | 0.16579 | -0.10899 | 0.13959
| 7405 | -0.42965 | -0.37016 | -0.26454 | 0.56907 | -0.063357 | 0.1091 | -0.20483 | 0.25723 | 0.010606 | 0.039219
| 7406 | -0.02097 | 0.50614 | 0.044437 | 0.61309 | -0.35789 | 0.039948 | 0.051686 | 0.61 | 0.36494 | -0.023936
| 7407 | 0.74329 | -0.55807 | 0.17799 | -0.36196 | 0.18385 | 0.27578 | 0.58684 | -0.2147 | -0.58781 | -0.90566
| 7408 | 0.39842 | 0.0082843 | -0.43123 | -0.39875 | 0.1338 | 0.037659 | -0.27979 | 0.43848 | -0.32672 | -0.19322
| 7409 | 0.4981 | 0.12302 | -0.086271 | 0.15994 | 0.63163 | 0.2598 | 0.0019519 | -0.015063 | 0.40108 | -0.64405
| 7410 | -0.76698 | -0.36133 | -0.66698 | -0.35914 | -0.35696 | 0.35696 | -0.60617 | 0.80277 | -0.23993 | 0.026604
| 7411 | -0.66789 | -0.27827 | 0.73149 | 0.25899 | 0.41374 | 0.51451 | -0.082885 | -0.081251 | 0.48473 | 0.061544
| 7412 | 0.089231 | -0.20508 | -0.67891 | 0.56653 | -0.17096 | 0.1389 | -0.89276 | -0.31247 | -0.22071 | -0.43141
| 7413 | 0.06165 | -0.56216 | -0.16856 | -0.42424 | -0.29353 | 0.098058 | -0.14906 | -0.20659 | 0.0051633 | -0.18287
| 7414 | -0.11112 | 0.38559 | -0.049684 | -0.4232 | -0.4258 | -0.32214 | 0.058884 | -0.68552 | 0.40326 | -0.68425
| 7415 | 0.32435 | -0.34892 | -0.10473 | 0.7569 | -0.0073772 | 0.30696 | 0.053058 | 0.032271 | 0.55672 | 0.035376
| 7416 | -0.61672 | 0.86847 | 0.076041 | -0.45018 | -0.37 | -0.34388 | -0.44063 | 0.00025003 | -0.67704 | -0.91
| 7417 | -0.60668 | -0.10083 | 0.87712 | -0.077991 | 0.40125 | -0.34342 | -0.8882 | 0.46344 | 0.18692 | -0.55921
| 7418 | -0.66162 | -0.91815 | 0.49612 | 0.023424 | -0.52198 | -0.88554 | 0.053586 | 0.53837 | -0.14262 | -0.0092932
| 7419 | 0.18483 | 0.3242 | 0.63765 | 0.30293 | -0.42493 | 0.14169 | -0.18963 | -0.13692 | 0.080381 | 0.33585
| 7420 | 0.42147 | 0.54033 | 0.7496 | 0.24191 | 0.22909 | -0.25267 | -0.5007 | -0.4286 | 0.29 | 0.14519
| 7421 | 0.70318 | -0.20962 | -0.23521 | -0.081577 | 0.23928 | 0.093854 | -0.37574 | -0.028764 | 0.21381 | 0.26849
| 7422 | -0.37574 | 0.4307 | -0.44638 | 0.15436 | -0.33645 | -0.89851 | 0.0046609 | 0.039531 | -0.24125 | 0.38853
| 7423 | 0.83969 | -0.69718 | -0.37751 | -0.1603 | -0.087147 | -0.54756 | 0.64602 | -0.14099 | 0.070108 | 0.67488
| 7424 | 0.39345 | 0.32258 | 0.11869 | 0.26495 | -0.32332 | -0.052424 | -0.014556 | 0.013136 | 0.35883 | -0.24508
| 7425 | 0.6697 | 0.12713 | 0.40209 | -0.20684 | 0.18373 | -0.86108 | 0.23652 | -0.23796 | -0.62973 | 0.66939
| 7426 | -0.55762 | -0.39197 | 0.17181 | 0.10876 | 0.11439 | 0.56676 | 0.085178 | 0.49532 | 0.71592 | 0.32881
| 7427 | -0.33164 | -0.8366 | 0.83357 | 0.92584 | -0.47151 | 0.057716 | 0.32184 | -0.252 | -0.43635 | -0.60238
| 7428 | -0.10351 | -0.19981 | -0.47645 | -0.06957 | 0.45972 | -0.14309 | -0.20735 | -0.045799 | 0.046113 | -0.26223
| 7429 | -0.64659 | -0.16364 | -0.38073 | -0.53902 | 0.10328 | -0.31218 | -0.048843 | 0.38073 | -0.049579 | -0.51657
| 7430 | -0.80125 | -0.1797 | 0.47113 | 0.70453 | -0.28593 | 0.056337 | 0.44964 | 0.64125 | -0.26945 | -0.52366
| 7431 | -0.23928 | -0.14859 | 0.60974 | -0.60088 | -0.072908 | -0.94084 | -0.12564 | 0.082994 | 0.5332 | 0.4344
| 7432 | -0.42493 | -0.23875 | 0.29169 | 0.19508 | 0.70251 | -0.62463 | 0.1229 | 0.56057 | 0.53277 | -0.37462
| 7433 | 0.74407 | -0.98268 | 0.080163 | 0.061331 | 0.93144 | -0.19025 | -0.94255 | -0.65547 | 0.53686 | 0.69227
| 7434 | 0.43405 | -0.31189 | 0.17435 | -0.28677 | 0.32598 | -0.47837 | -0.38722 | 0.16292 | 0.35139 | 0.5707
| 7435 | -0.77932 | 0.44475 | 0.71104 | -0.32155 | -0.16711 | -0.018114 | 0.2975 | 0.16543 | 0.37398 | 0.67519
| 7436 | 0.1063 | -0.29212 | -0.5707 | -0.38738 | -0.59098 | 0.9005 | 0.62119 | 0.28621 | -0.66909 | 0.59565
| 7437 | -0.049369 | 0.064425 | 0.44385 | -0.015571 | 0.49236 | -0.13473 | 0.30337 | 0.44116 | -0.18532 | 0.49334
| 7438 | 0.47741 | -0.0922 | -0.89851 | 0.026398 | -0.16197 | 0.19969 | 0.42355 | -0.014252 | -0.31655 | 0.072476
| 7439 | 0.13808 | -0.22689 | 0.0086877 | 0.057822 | -0.7839 | -0.20019 | 0.076258 | -0.02568 | 0.36384 | -0.086928
| 7440 | 0.5141 | 0.75 | -0.13808 | 0.10888 | -0.49453 | 0.12782 | 0.37654 | 0.32925 | 0.94084 | 0.56194
| 7441 | -0.31495 | 0.55627 | 0.26754 | -0.72269 | -0.33735 | -0.33856 | 0.32598 | -0.75938 | -0.14157 | -0.09033
| 7442 | -5.0001e-05 | 0.4134 | 0.25939 | -0.32332 | 0.4564 | 0.12028 | -0.0036567 | -0.050948 | 0.42407 | -0.54294
| 7443 | 0.072584 | 0.23783 | -0.31218 | -0.1769 | -0.29509 | 0.18643 | 0.3425 | -0.4232 | 0.0087886 | -0.29226
| 7444 | 0.51575 | 0.098945 | -0.028249 | -0.080272 | -0.39296 | 0.70017 | 0.41153 | -0.64461 | -0.36762 | -0.058353
| 7445 | -0.27082 | -0.20019 | 0.64574 | 0.029073 | 0.78068 | -0.63217 | 0.04172 | -0.039948 | -0.22961 | 0.11191
| 7446 | 0.67427 | 0.19969 | -0.1603 | 0.50432 | 0.34708 | 0.46139 | 0.22225 | -0.26278 | -0.58012 | 0.15673
| 7447 | 0.023834 | 0.27688 | 0.0079819 | -0.036102 | 0.31451 | 0.5141 | -0.096507 | 0.83177 | 0.47284 | -0.34662
| 7448 | 0.0089904 | 0.56722 | 0.46083 | 0.60163 | 0.27247 | -0.3148 | 0.11665 | -0.31145 | 0.0063703 | 0.57751
| 7449 | -0.089451 | 0.65489 | -0.78436 | 0.46232 | -0.20634 | 0.3593 | 0.99 | -0.29085 | 0.61568 | 0.58757
| 7450 | 0.6939 | -0.30725 | -0.012225 | -0.78576 | -0.29936 | 0.29907 | -0.37318 | -0.15118 | -0.35618 | -0.37159
| 7451 | 0.11112 | -0.023527 | 0.71452 | -0.31831 | -0.12473 | 0.11473 | -0.68647 | -0.80635 | 0.38526 | -0.17145
| 7452 | -0.28285 | 0.15638 | -0.80025 | -0.60213 | 0.22328 | 0.40359 | 0.51513 | 0.42355 | -0.31787 | 0.63081
| 7453 | 0.20395 | 0.42476 | 0.1752 | -0.42912 | 0.16292 | 0.065709 | 0.34327 | 0.71138 | 0.1688 | 0.23391
| 7454 | 0.46568 | -0.4989 | 0.52136 | 0.26699 | 0.30986 | -0.27027 | -0.020357 | -0.014353 | 0.17508 | -0.40527
| 7455 | -0.080707 | 0.57023 | 0.74135 | 0.5201 | -0.14988 | -0.23967 | 0.49751 | -0.22379 | -0.10117 | -0.38332
| 7456 | -0.32569 | 0.0057666 | -0.43229 | 0.60213 | -0.34159 | -0.6371 | 0.24007 | -0.31699 | 0.0086877 | 0.045904
| 7457 | 0.063998 | -0.085943 | 0.26278 | 0.066458 | -0.82252 | 0.17084 | 0.55178 | 0.23364 | -0.28803 | -0.25227
| 7458 | 0.048212 | -0.10518 | -0.32406 | 0.23639 | 0.13334 | 0.015978 | -0.18348 | 0.69884 | -0.21776 | -0.089451
| 7459 | 0.22637 | 0.23312 | -0.22328 | 0.35494 | -0.081469 | 0.18471 | -0.15567 | -0.23718 | -0.46699 | -0.68267
| 7460 | -0.1879 | 0.35727 | 0.53859 | 0.58903 | -0.040573 | -0.47952 | 0.59639 | 0.56422 | 0.33389 | 0.14835
| 7461 | -0.68743 | -0.48029 | -0.61231 | -0.0083852 | 0.56011 | 0.25993 | 0.36778 | 0.48241 | 0.71277 | -0.3306
| 7462 | -0.60263 | 0.078317 | 0.91456 | 0.053269 | -0.69983 | 0.029176 | -0.01263 | 0.2621 | 0.86696 | 0.79875
| 7463 | 0.89276 | 0.0092932 | 0.70117 | 0.28887 | -0.52136 | 0.29183 | -0.015063 | -0.13623 | -0.12541 | -0.79288
| 7464 | -0.70217 | -0.44692 | -0.39659 | -0.24402 | -0.11124 | -0.58976 | 0.076799 | -0.3551 | 0.012934 | 0.38348
| 7465 | -0.97764 | 0.42685 | -0.52788 | -0.010202 | -0.41459 | 0.77977 | -0.48473 | 0.77528 | -0.53043 | 0.30711
| 7466 | -0.09695 | 0.48922 | -0.066887 | 0.039531 | 0.35231 | 0.55649 | 0.75979 | 0.16161 | -0.35789 | 0.34327
| 7467 | 0.13057 | -0.25589 | -0.54646 | 0.75363 | -0.60213 | -0.34008 | 0.025782 | 0.07043 | 0.40713 | 0.63408
| 7468 | -0.15165 | -0.056549 | -0.19086 | 0.085068 | -0.074959 | -0.27591 | 0.36164 | -0.60038 | 0.17374 | -0.65956
| 7469 | -0.17326 | -0.47227 | -0.021685 | 0.54668 | -0.20019 | 0.45972 | 0.073555 | 0.10787 | 0.46344 | 0.045694
| 7470 | -0.42147 | 0.63217 | 0.2575 | -0.38657 | -0.17605 | -0.37976 | -0.14683 | -0.23587 | 0.32628 | 0.28944
| 7471 | -0.80075 | -0.12256 | 0.078642 | 0.077124 | -0.0026535 | 0.70589 | 0.73335 | -0.74058 | -0.22857 | -0.19719
| 7472 | -0.3961 | -0.10686 | 0.4293 | -0.66578 | 0.14941 | 0.27316 | 0.43405 | 0.020255 | 0.17 | 0.060266
| 7473 | 0.011415 | -0.85752 | 0.018725 | -0.64321 | 0.060372 | -0.23169 | -0.75855 | 0.069355 | -0.079294 | -0.044228
| 7474 | -0.28035 | -0.32037 | -0.22148 | -0.40595 | -0.36573 | 0.30036 | 0.10585 | -0.18544 | 0.36557 | -0.63765
| 7475 | -0.548 | -0.51657 | -0.61335 | -0.1015 | 0.09044 | -0.24204 | 0.18116 | 0.19856 | -0.29807 | -0.30408
| 7476 | 0.34159 | -0.36668 | 0.27702 | -0.28146 | 0.3477 | 0.40662 | -0.18459 | 0.5003 | -0.060372 | 0.54076
| 7477 | -0.56422 | -0.071291 | 0.23286 | -0.21904 | -0.21559 | -0.29793 | 0.25214 | 0.11586 | 0.30122 | 0.14274
| 7478 | -0.336 | 0.61856 | -0.17641 | 0.15697 | -0.1603 | -0.23718 | 0.64265 | -0.30408 | -0.19297 | 0.32406
| 7479 | -0.62758 | -0.78905 | 0.43955 | 0.32184 | -0.078317 | 0.47132 | -0.35185 | 0.13196 | 0.69586 | 0.35077
| 7480 | -0.67829 | -0.58323 | -0.20571 | 0.1179 | 0.33886 | -0.37879 | 0.57822 | 0.56676 | -0.27137 | 0.20181
| 7481 | -0.16089 | -0.09143 | 0.34448 | -0.25562 | -0.5174 | 0.28733 | -0.28523 | 0.39066 | -0.065281 | -0.29651
| 7482 | -0.19284 | -0.51844 | 0.82479 | -0.044019 | 0.36921 | -0.28733 | 0.16579 | -0.4898 | 0.015774 | -0.046008
| 7483 | -0.030722 | -0.38413 | -0.19632 | 0.47512 | -0.22831 | -0.58927 | -0.003155 | -0.0076795 | 0.5283 | -0.2377
| 7484 | -0.53556 | -0.44367 | -0.48473 | -0.26481 | 0.53277 | -0.55807 | -0.3038 | 0.054114 | 0.63903 | -0.31334
| 7485 | 0.057185 | 0.06957 | 0.39033 | 0.65489 | -0.2659 | 0.20785 | 0.068174 | -0.37016 | 0.20357 | -0.48029
| 7486 | 0.62039 | 0.4078 | -0.068925 | -0.14496 | 0.47569 | -0.57233 | -0.20659 | 0.12427 | -0.0035563 | 0.32243
| 7487 | -0.64181 | 0.14859 | 0.81862 | 0.31655 | -0.76741 | 0.18606 | -0.46176 | -0.77 | -0.09088 | -0.70083
| 7488 | 0.071184 | 0.050842 | -0.024141 | 0.20697 | -0.65693 | 0.51369 | 0.053374 | 0.4588 | 0.32702 | -0.25791
| 7489 | -0.46549 | -0.83059 | -0.21968 | -0.25966 | 0.19161 | -0.024141 | -0.51266 | -0.24495 | -0.31276 | 0.010404
| 7490 | 0.83845 | 0.024654 | -0.053691 | 0.40662 | -0.20621 | -0.003456 | 0.065923 | -0.33615 | 0.34068 | -0.38073
| 7491 | -0.29311 | 0.54602 | 0.20596 | -0.16304 | -0.15094 | -0.41255 | -0.32881 | 0.12393 | 0.063571 | 0.45292
| 7492 | 0.23065 | 0.17799 | -0.088902 | 0.30797 | 0.70623 | -0.37254 | -0.94804 | -0.027015 | 0.37239 | -0.35108
| 7493 | 0.059628 | -0.052002 | -0.20269 | -0.79579 | -0.055278 | -0.081795 | 0.1127 | 0.23809 | 0.056549 | -0.070861
| 7494 | -0.25174 | 0.37398 | 0.44927 | 0.14613 | -0.15935 | 0.60465 | -0.2492 | 0.17896 | -0.3005 | -0.084959
| 7495 | 0.76104 | 0.11949 | -0.17447 | -0.59122 | 0.36873 | 0.48726 | 0.016283 | -0.24641 | -0.27082 | 0.53643
| 7496 | 0.13553 | 0.52408 | -0.70794 | 0.29509 | 0.014353 | -0.37944 | -0.086819 | 0.37159 | 0.59639 | 0.33314
| 7497 | 0.36668 | -0.010404 | 0.022912 | -0.87631 | 0.4755 | -0.54845 | -0.26849 | -0.55022 | 0.078208 | 0.37526
| 7498 | 0.16113 | 0.28972 | 0.0073772 | -0.13866 | 0.24614 | -0.21343 | -0.20558 | 0.20432 | 0.042138 | 0.59024
| 7499 | 0.02097 | 0.13 | -0.51225 | -0.91 | -0.67274 | -0.043391 | 0.41425 | -0.18815 | -0.35324 | -0.32391
| 7500 | -0.30495 | 0.012123 | 0.30351 | -0.11983 | -0.97764 | 0.12176 | 0.80025 | -0.21241 | 0.1825 | -0.26101
| 7501 | -0.36258 | 0.32346 | 0.30667 | -0.089012 | 0.31407 | -0.44295 | 0.041616 | -0.24787 | -0.60238 | 0.22109
| 7502 | 0.20131 | -0.55357 | 0.064746 | -0.12954 | -0.087914 | -0.29651 | -0.38755 | 0.53363 | -0.45603 | 0.15709
| 7503 | 0.3148 | -0.5656 | -0.08978 | -0.063144 | -0.097503 | -0.030825 | 0.65029 | -0.2524 | 0.5412 | 0.17024
| 7504 | 0.14695 | -0.4293 | -0.59098 | 0.33886 | 0.13588 | -0.020153 | 0.34479 | -0.014962 | -0.84933 | 0.020051
| 7505 | -0.37302 | -0.55178 | 0.67366 | 0.13496 | -0.50654 | 0.1814 | 0.044751 | -0.31611 | -0.40949 | 0.12313
| 7506 | 0.68679 | -0.024551 | -0.84867 | 0.30207 | -0.11643 | -0.09154 | 0.564 | 0.071291 | -0.024449 | 0.22702
| 7507 | -0.14566 | -0.70184 | -0.52115 | 0.55089 | -0.095954 | 0.19632 | 0.66192 | 0.09011 | 0.50614 | -0.55627
| 7508 | -0.18827 | 0.12553 | 0.30179 | 0.16484 | 0.035065 | 0.15188 | -0.72632 | 0.34724 | -0.32851 | -0.58203
| 7509 | -0.60465 | 0.80075 | 0.51948 | -0.087038 | -0.57941 | 0.66638 | 0.23731 | 0.33962 | -0.24561 | -0.55402
| 7510 | 0.1473 | -0.025167 | 0.075176 | 0.49473 | 0.54404 | -0.07962 | -0.47856 | -0.3167 | -0.039427 | 0.25993
| 7511 | -0.11869 | 0.15247 | -0.00075028 | 0.47952 | 0.011112 | 0.40343 | -0.20899 | -0.14906 | -0.15448 | -0.020357
| 7512 | 0.47284 | 0.33992 | -0.148 | -0.63244 | 0.39809 | -0.70897 | 0.36668 | -0.06496 | 0.5199 | 0.0043595
| 7513 | -0.54734 | 0.2356 | -0.55111 | -0.42546 | -0.25845 | -0.24191 | -0.11926 | 0.22122 | 0.22058 | -0.44674
| 7514 | -0.34311 | -0.33194 | 0.56308 | -0.13553 | 0.23195 | -0.26291 | -0.0004501 | 0.11451 | 0.52851 | -0.024346
| 7515 | -0.40949 | -0.53772 | -0.35185 | 0.78905 | -0.53881 | 0.20257 | -0.26359 | -0.33585 | 0.51287 | 0.47019
| 7516 | -0.36274 | -0.38056 | 0.27357 | 0.52534 | -0.063784 | 0.12622 | -0.25656 | -0.62384 | 0.49374 | -0.037036
| 7517 | 0.13104 | 0.19744 | 0.073663 | -0.015063 | 0.20319 | 0.31743 | -0.27371 | -0.2674 | -0.6852 | 0.61594
| 7518 | 0.62838 | 0.38429 | 0.0755 | -0.58539 | -0.34617 | 0.47971 | 0.38461 | 0.77977 | -0.27564 | 0.16543
| 7519 | 0.46213 | 0.26904 | -0.69817 | -0.11847 | 0.81917 | -0.17617 | -0.71242 | 0.48609 | -0.071614 | 0.026296
| 7520 | 0.18975 | 0.33239 | -0.39726 | 0.34235 | -0.14742 | -0.22586 | -0.060372 | -0.10787 | -0.47189 | 0.011314
| 7521 | -0.63654 | -0.26959 | 0.69194 | 0.071184 | -0.29594 | -0.37334 | 0.81053 | -0.28383 | -0.75566 | 0.13449
| 7522 | 0.084085 | -0.073663 | -0.26441 | 0.22534 | -0.027735 | -0.07043 | 0.37606 | -0.24336 | 0.43493 | 0.6546
| 7523 | 0.69 | -0.16964 | 0.67274 | 0.027015 | 0.27069 | 0.63986 | 0.65956 | -0.66281 | -0.1269 | 0.27785
| 7524 | -0.067959 | 0.81372 | 0.084413 | -0.84157 | -0.14134 | 0.088463 | -0.34754 | 0.33766 | 0.18434 | 0.26468
| 7525 | -0.28216 | -0.61908 | -0.53043 | -0.25791 | 0.21215 | 0.2052 | 0.60339 | -0.025167 | 0.16244 | -0.29637
| 7526 | -0.31655 | 0.0068736 | 0.26767 | -0.36023 | 0.38461 | -0.47607 | -0.72341 | -0.20785 | -0.041825 | 0.47417
| 7527 | 0.045589 | 0.12656 | 0.31875 | 0.74446 | 0.13299 | -0.34632 | 0.33811 | -0.52387 | 0.38478 | 0.11439
| 7528 | 0.84867 | 0.37879 | -0.5007 | -0.34647 | -0.0028541 | 0.24628 | -0.2175 | 0.89851 | 0.73637 | -0.047267
| 7529 | -0.16831 | -0.37944 | -0.21942 | -0.16006 | -0.52073 | -0.3132 | 0.1153 | 0.77087 | -0.59491 | 0.076041
| 7530 | 0.18471 | 0.12097 | 0.61803 | -0.77395 | 0.040469 | -0.057716 | 0.31203 | 0.5768 | 0.5693 | -0.78905
| 7531 | 0.37622 | 0.30437 | -0.66192 | 0.51123 | 0.06197 | -0.43635 | 0.010606 | -0.085068 | -0.66399 | -0.50533
| 7532 | -0.45548 | -0.04172 | 0.46065 | -0.54294 | 0.020561 | -0.066673 | -0.23013 | 0.66251 | 0.084304 | -0.28355
| 7533 | -0.012022 | -0.47057 | 0.22676 | 0.095622 | 0.66074 | -0.40259 | 0.3005 | -0.21521 | 0.63545 | -0.15318
| 7534 | 0.20257 | -0.039323 | -0.003456 | 0.83721 | 0.22032 | -0.022299 | 0.5005 | -0.19384 | -0.72669 | 0.84031
| 7535 | -0.14683 | -0.37638 | -0.11711 | 0.33 | 0.16627 | -0.13913 | 0.10563 | -0.41991 | -0.16292 | 0.83969
| 7536 | -0.65316 | 0.097503 | 0.17314 | 0.45036 | -0.31058 | 0.51554 | -0.14437 | 0.4337 | 0.035894 | -0.030825
| 7537 | 0.63545 | 0.64971 | -0.066244 | -0.10306 | -0.40511 | 0.76315 | -0.44692 | 0.34678 | -0.049263 | -0.10507
| 7538 | -0.30193 | -0.59838 | 0.29042 | 0.048527 | 0.60694 | 0.032064 | -0.23299 | 0.15911 | 0.24283 | 0.097171
| 7539 | 0.056655 | 0.067852 | 0.30207 | 0.62198 | -0.7512 | 0.57656 | 0.38526 | -0.72161 | 0.04517 | 0.47971
| 7540 | 0.061224 | -0.019235 | 0.25254 | -0.51328 | 0.03974 | 0.78763 | -0.53149 | -0.30523 | 0.20874 | 0.41204
| 7541 | -0.40611 | -0.38315 | -0.37414 | -0.50251 | 0.049895 | -0.16268 | 0.18815 | -0.38934 | -0.0083852 | -0.53492
| 7542 | 0.60389 | 0.50553 | 0.69292 | -0.32169 | -0.049474 | -0.35541 | -0.73411 | 0.054326 | -0.11767 | 0.78905
| 7543 | 0.45182 | 0.050211 | 0.58155 | 0.47588 | 0.9005 | 0.021787 | -0.83721 | -0.041929 | -0.078425 | 0.09209
| 7544 | 0.0020521 | -0.57798 | -0.019847 | -0.080924 | -0.26754 | -0.074635 | 0.54536 | 0.60389 | 0.0046609 | 0.50796
| 7545 | -0.27151 | 0.74019 | -0.0052639 | 0.05422 | 0.18361 | -0.21152 | -0.36604 | 0.89 | -0.27288 | -0.042138
| 7546 | 0.053269 | -0.15484 | -0.5768 | -0.29197 | 0.11869 | 0.16615 | 0.79975 | 0.44529 | -0.029073 | 0.52555
| 7547 | -0.030103 | -0.59788 | -0.48376 | 0.27993 | 0.69032 | 0.036517 | 0.10742 | 0.088902 | 0.3375 | -0.32643
| 7548 | 0.06957 | 0.098501 | 0.14134 | 0.38853 | 0.14227 | 0.79048 | 0.6371 | -0.31846 | -0.0068736 | -0.25576
| 7549 | -0.51948 | -0.35836 | 0.63299 | 0.14379 | 0.3357 | -0.35046 | -0.077774 | -0.20382 | 0.093634 | -0.34678
| 7550 | -0.22456 | -0.21381 | 0.25522 | -0.69718 | 0.81972 | 0.37095 | 0.083103 | -0.34555 | 0.4683 | -0.61231
| 7551 | -0.13369 | 0.69259 | 0.2674 | -0.35417 | 0.15673 | 0.26509 | -0.48087 | 0.70386 | -0.57233 | -0.0922
| 7552 | -0.049579 | -0.42912 | 0.16352 | -0.23534 | -0.41034 | -0.5015 | 0.24429 | 0.12862 | -0.068603 | -0.29608
| 7553 | -0.84412 | 0.91693 | 0.58299 | 0.094185 | 0.42476 | -0.41204 | -0.69586 | 0.30351 | -0.17024 | 0.017809
| 7554 | 0.48648 | 0.088682 | -0.085834 | -0.39643 | 0.066673 | -0.28327 | 0.33856 | 0.67766 | 0.44206 | 0.64042
| 7555 | -0.35712 | 0.33329 | 0.18532 | -0.48707 | 0.71769 | -0.024449 | 0.33841 | -0.53128 | 0.86399 | -0.039011
| 7556 | 0.26305 | -0.09055 | -0.82196 | -0.40225 | -0.74368 | -0.19533 | -0.28607 | 0.40527 | -0.17483 | -0.47151
| 7557 | 0.2907 | 0.52724 | 0.72926 | 0.85752 | -0.070323 | 0.56514 | -0.85269 | -0.64014 | 0.78905 | -0.022196
| 7558 | 0.3629 | -0.22392 | -0.13704 | 0.56768 | -0.29537 | -0.5013 | -0.11858 | -0.54294 | -0.27467 | -0.4989
| 7559 | -0.0062697 | 0.44313 | 0.10006 | -0.081904 | -0.098723 | 0.86399 | 0.41545 | -0.033718 | 0.14192 | 0.17362
| 7560 | 0.37638 | 0.30523 | 0.33329 | -0.071399 | 0.23117 | 0.5009 | -0.48183 | -0.038387 | -0.75896 | -0.00085036
| 7561 | -0.7042 | 0.40292 | 0.40058 | -0.39444 | 0.31831 | 0.4801 | 0.23954 | -0.076149 | 0.20709 | 0.065709
| 7562 | 0.040782 | 0.22212 | 0.20823 | 0.24575 | -0.27965 | -0.28453 | -0.58878 | 0.57186 | 0.71382 | -0.80947
| 7563 | 0.10675 | 0.6118 | 0.33735 | -0.049053 | -0.55921 | -0.42303 | 0.21355 | 0.44206 | 0.11034 | -0.36794
| 7564 | -0.49651 | -0.20546 | 0.54273 | -0.029176 | -0.0039578 | -0.37286 | -0.41306 | -0.028146 | 0.14239 | 0.32302
| 7565 | 0.047897 | -0.74446 | 0.46009 | -0.41974 | -0.43866 | 0.20911 | -0.0012508 | 0.48551 | 0.033822 | 0.73261
| 7566 | -0.076366 | -0.83845 | -0.18128 | 0.39494 | 0.38283 | -0.011011 | 0.33992 | -0.4392 | 0.46661 | -0.46158
| 7567 | 0.17265 | -0.41068 | -0.3629 | -0.60163 | 0.33811 | 0.040469 | -0.60063 | 0.11 | 0.14274 | -0.080924
| 7568 | 0.25926 | -0.084413 | 0.54054 | 0.36573 | 0.33464 | -0.45898 | -0.059628 | -0.039427 | -0.53729 | -0.21355
| 7569 | 0.12977 | -0.20709 | 0.92584 | -0.034547 | -0.37734 | -0.023015 | 0.071076 | -0.7623 | -0.25858 | -0.80226
| 7570 | -0.6233 | 0.097282 | 0.32524 | 0.19856 | 0.7429 | 0.038283 | -0.31626 | -0.036932 | 0.43141 | -0.66162
| 7571 | 0.19557 | -0.77841 | -0.30079 | 0.75566 | -0.49771 | 0.2265 | -0.31816 | -0.35123 | -0.58636 | 0.093965
| 7572 | -0.72089 | -0.552 | 0.1803 | -0.19334 | -0.66074 | 0.37895 | -0.7076 | 0.46325 | 0.18667 | 0.027118
| 7573 | 0.1513 | -0.6382 | 0.22263 | -0.43264 | -0.79975 | 0.35139 | 0.69292 | -0.2119 | -0.40259 | -0.31714
| 7574 | 0.069248 | 0.28509 | 0.10139 | 0.42877 | -0.044019 | 0.054855 | -0.25804 | -0.49295 | 0.31334 | -0.11315
| 7575 | -0.21623 | -0.80843 | 0.25616 | -0.2516 | 0.47341 | 0.10317 | -0.2343 | -0.027735 | 0.13785 | 0.094185
| 7576 | -0.11473 | -0.55853 | -0.28063 | 0.055701 | 0.60872 | -0.19769 | 0.64042 | 0.95417 | -0.33524 | 0.18778
| 7577 | 0.0017515 | -0.57633 | 0.063891 | 0.50371 | 0.027015 | -0.013846 | -0.34235 | 0.74761 | -0.16663 | -0.42825
| 7578 | 0.26264 | 0.16904 | 0.59714 | -0.45146 | 0.20294 | 0.082558 | -0.79239 | -0.13057 | -0.56011 | -0.73
| 7579 | -0.4337 | 0.5172 | 0.80379 | 0.56354 | -0.66162 | -0.74407 | -0.17629 | -0.97 | -0.2047 | -0.78622
| 7580 | -0.86621 | 0.19595 | -0.67335 | 0.14894 | 0.30523 | 0.057822 | -0.10865 | 0.25737 | 0.44909 | 0.25455
| 7581 | -0.015368 | 0.80895 | -0.10284 | -0.33224 | -0.14542 | -0.61283 | -0.55921 | 0.65258 | 0.28063 | 0.44927
| 7582 | 0.29566 | -0.12977 | 0.29523 | -0.051897 | -0.80328 | 0.25093 | -0.36573 | 0.93917 | -0.10619 | 0.16952
| 7583 | 0.13311 | -0.19657 | 0.28565 | -0.17338 | -0.43706 | -0.067852 | 0.66399 | 0.06753 | -0.58587 | 0.040156
| 7584 | -0.79336 | -0.037244 | -0.068711 | 0.11847 | -0.45567 | 0.93597 | -0.30365 | -0.0036567 | 0.4258 | 0.51906
| 7585 | 0.14542 | -0.75485 | -0.1863 | -0.44818 | -0.48609 | 0.0075787 | 0.47379 | 0.56377 | -0.69685 | -0.27647
| 7586 | -0.41187 | -0.36321 | -0.39395 | 0.33389 | 0.45751 | -0.72779 | -0.09121 | -0.53277 | 0.55807 | -0.40831
| 7587 | -0.15626 | -0.063571 | 0.79433 | 0.10239 | 0.49137 | 0.58107 | 0.15935 | -0.152 | -0.25562 | 0.30899
| 7588 | -0.55267 | -0.76527 | -0.18889 | 0.64125 | -0.50392 | 0.16844 | 0.21317 | -0.68775 | 0.47722 | -0.2496
| 7589 | 0.38592 | 0.078208 | 0.79191 | -0.68047 | 0.054431 | -0.38951 | 0.32687 | 0.75855 | -0.76399 | 0.23065
| 7590 | 0.81426 | -0.14671 | 0.082885 | -0.16771 | 0.18226 | 0.25589 | 0.17982 | 0.14297 | 0.23404 | 0.13161
| 7591 | 0.42563 | 0.34099 | 0.28747 | 0.40359 | 0.2402 | -0.069677 | -0.55627 | 0.1044 | 0.5017 | -0.21177
| 7592 | 0.71312 | 0.34831 | 0.5412 | 0.10865 | -0.27924 | 0.56791 | 0.25831 | 0.53578 | -0.15094 | 0.29424
| 7593 | 0.43176 | -0.45438 | 0.32672 | 0.51389 | 0.093082 | -0.24721 | 0.19148 | -0.037036 | -0.41751 | 0.39477
| 7594 | 0.52429 | -0.061224 | 0.7504 | 0.073771 | -0.93292 | 0.33917 | -0.045275 | 0.2567 | -0.089341 | -0.15059
| 7595 | 0.018725 | -0.23443 | 0.54734 | 0.56102 | 0.70897 | -0.0033556 | 0.23234 | -0.03974 | -0.079728 | 0.35355
| 7596 | -0.19757 | 0.13357 | -0.16531 | 0.041616 | 0.39411 | 0.49354 | -0.16591 | -0.071184 | 0.041303 | 0.37111
| 7597 | -0.53277 | 0.22961 | -0.452 | -0.032477 | -0.1353 | 0.028146 | -0.25388 | -0.070323 | -0.94255 | -0.044856
| 7598 | 0.13658 | -0.35899 | -0.82593 | 0.51143 | -0.41682 | -0.27453 | 0.46195 | -0.03579 | -0.096396 | 0.51102
| 7599 | 0.32302 | -0.19483 | 0.18055 | 0.20056 | -0.01842 | -0.60339 | 0.11813 | -0.28397 | 0.10451 | -0.57047
| 7600 | -0.16018 | 0.2427 | -0.15804 | -0.023015 | 0.72596 | 0.35324 | 0.59838 | -0.22431 | 0.2907 | -0.58323
| 7601 | 0.79776 | -0.86847 | 0.7881 | 0.056019 | -0.018623 | -0.40393 | 0.048422 | 0.26061 | -0.58179 | 0.086709
| 7602 | 0.85823 | 0.099278 | -0.75566 | -0.5806 | 0.00025003 | 0.48299 | 0.64433 | -0.16149 | -0.6952 | -0.029073
| 7603 | -0.39775 | -0.16006 | -0.075068 | -0.52936 | 0.30351 | -0.15247 | 0.13415 | 0.15118 | 0.1109 | 0.22689
| 7604 | 0.12507 | -0.12199 | 0.13461 | 0.044856 | 0.010707 | -0.55943 | 0.70623 | 0.074635 | -0.66221 | 0.064212
| 7605 | 0.089451 | 0.11338 | 0.67304 | 0.17423 | -0.18926 | -0.67335 | -0.18852 | 0.060372 | 0.86923 | -0.25602
| 7606 | -0.5174 | 0.32509 | 0.4163 | -0.53235 | 0.19682 | 0.73751 | -0.25067 | -0.86252 | -0.16723 | -0.18766
| 7607 | 0.58612 | 0.83538 | -0.7076 | -0.55267 | -0.13785 | -0.34908 | 0.1323 | 0.0086877 | 0.48941 | 0.019745
| 7608 | -0.20081 | 0.48435 | 0.22909 | 0.55267 | 0.20357 | -0.57585 | 0.01415 | 0.33675 | -0.29085 | -0.25347
| 7609 | -0.44098 | -0.72414 | -0.040052 | 0.23234 | 0.20571 | 0.11564 | 0.1921 | -0.90566 | 0.64971 | -0.45511
| 7610 | -0.30826 | -0.26115 | 0.025782 | 0.21432 | -0.8747 | 0.37767 | 0.016079 | -0.24217 | 0.043182 | 0.38787
| 7611 | -0.72779 | -0.12404 | -0.18079 | 0.63135 | 0.32228 | -0.39626 | 0.13727 | -0.51061 | 0.35525 | -0.036309
| 7612 | 0.022606 | -0.010101 | 0.27096 | 0.58854 | -0.57023 | 0.023527 | -0.82824 | -0.29282 | 0.19806 | 0.12154
| 7613 | 0.0077803 | 0.92319 | 0.13196 | 0.41459 | 0.63135 | 0.19025 | 0.17036 | -0.074311 | 0.2784 | 0.19483
| 7614 | -0.36889 | 0.64153 | -0.8739 | 0.064425 | -0.6952 | -0.18018 | 0.8422 | -0.33675 | 0.34296 | 0.49394
| 7615 | 0.28271 | 0.91225 | -0.56861 | -0.042764 | -0.31978 | 0.34846 | 0.73599 | 0.64857 | 0.26359 | -0.47741
| 7616 | -0.55223 | -0.45493 | 0.034236 | 0.14355 | 0.86923 | 0.064105 | 0.18544 | -0.23456 | 0.20144 | 0.71769
| 7617 | -0.2313 | -0.0064709 | 0.11813 | 0.082667 | 0.18864 | 0.56102 | 0.21101 | -0.60013 | -0.20609 | -0.15875
| 7618 | 0.82766 | 0.049053 | 0.53299 | -0.61882 | 0.19831 | -0.21546 | 0.34571 | -0.0030547 | 0.068174 | 0.33947
| 7619 | 0.016994 | -0.16976 | 0.75648 | 0.40679 | 0.9134 | 0.63244 | -0.564 | -0.58805 | 0.026604 | 0.5283
| 7620 | -0.17229 | -0.72815 | 0.36778 | -0.57374 | 0.084304 | 0.054749 | -0.38089 | 0.10742 | 0.16795 | 0.28021
| 7621 | 0.28789 | 0.34114 | 0.59196 | 0.71911 | 0.32406 | -0.18914 | 0.35867 | 0.86036 | 0.019031 | -0.3363
| 7622 | -0.54294 | -0.24442 | 0.91938 | 0.41442 | -0.74525 | -0.072908 | -0.54294 | -0.69162 | -0.24389 | -0.51492
| 7623 | 0.21789 | -0.17872 | -0.069033 | -0.38559 | 0.56331 | -0.29381 | 0.78622 | 0.025988 | -0.016283 | -0.1375
| 7624 | -0.25993 | -0.32406 | -0.36652 | -0.080054 | -0.53235 | -0.17217 | -0.79433 | 0.3297 | 0.67829 | -0.11586
| 7625 | -0.38918 | 0.60898 | -0.59318 | 0.26727 | -0.34877 | 0.33524 | 0.28049 | 0.4232 | 0.030722 | 0.56377
| 7626 | -0.042555 | 0.055701 | 0.021481 | -0.81426 | -0.69784 | -0.43317 | -0.16675 | -0.72669 | -0.45328 | 0.16844
| 7627 | 0.033408 | 0.59491 | 0.06678 | 0.28986 | -0.33209 | 0.68903 | -0.10798 | -0.021174 | 0.52408 | 0.48222
| 7628 | 0.36573 | -0.25858 | 0.30107 | 0.60846 | 0.053058 | 0.24033 | 0.016689 | -0.43088 | 0.34754 | -0.048107
| 7629 | 0.21203 | -0.14507 | -0.39411 | -0.045275 | -0.009697 | -0.43458 | 0.33947 | -0.56057 | 0.037659 | -0.069892
| 7630 | 0.62597 | -0.42009 | -0.33585 | -0.97 | 0.43759 | -0.16352 | -0.23954 | -0.68871 | -0.24893 | 0.35278
| 7631 | -0.47113 | 0.21152 | 0.34281 | 0.16952 | -0.68298 | 0.69685 | 0.10652 | 0.45456 | 0.3148 | -0.057397
| 7632 | 0.25107 | 0.29141 | -0.44331 | 0.2948 | 0.40915 | -0.42407 | 0.25067 | 0.044019 | -0.04538 | -0.82883
| 7633 | 0.15141 | -0.58299 | 0.54098 | -0.364 | 0.63108 | -0.83845 | -0.12097 | 0.47894 | -0.09044 | 0.40544
| 7634 | -0.20232 | 0.34678 | 0.37542 | 0.20823 | -0.39726 | 0.37334 | -0.063784 | 0.56171 | 0.21127 | -0.53192
| 7635 | -0.56194 | 0.40949 | 0.42407 | 0.6265 | 0.18618 | -0.11733 | 0.022708 | -0.87233 | -0.48922 | 0.17714
| 7636 | 0.52073 | -0.023015 | -0.23026 | -0.82708 | 0.72852 | 0.1153 | -0.34617 | 0.52513 | -0.045484 | -0.24734
| 7637 | 0.72341 | -0.05 | -0.24614 | -0.065067 | -0.46512 | -0.14953 | 0.60668 | -0.12713 | -0.10128 | -0.34053
| 7638 | -0.14613 | -0.1261 | -0.352 | 0.01 | -0.81106 | 0.079511 | -0.44619 | -0.48609 | 0.34008 | -0.2948
| 7639 | 0.1735 | -0.42372 | 0.1229 | -0.55807 | 0.1439 | -0.29637 | 0.52979 | -0.020868 | 0.18963 | -0.45237
| 7640 | -0.79482 | -0.048527 | 0.045799 | 0.27605 | 0.41204 | 0.5245 | -0.31 | 0.35992 | 0.59863 | -0.08343
| 7641 | -0.52597 | 0.026296 | -0.19894 | 0.76827 | -0.67335 | 0.27343 | -0.22805 | -0.27605 | 0.13426 | -0.25147
| 7642 | -0.24707 | -0.5883 | -0.3074 | 0.38608 | -0.04517 | -0.33735 | 0.56722 | 0.19595 | 0.69032 | -0.38364
| 7643 | -0.56239 | 0.26631 | -0.043182 | 0.24867 | 0.3087 | -0.16976 | -0.46362 | 0.27536 | -0.1292 | 0.06016
| 7644 | 0.39676 | 0.34862 | -0.45164 | -0.23495 | -0.56722 | 0.2047 | -0.14542 | 0.3838 | 0.014252 | -0.70794
| 7645 | -0.20886 | 0.61 | 0.46605 | -0.62946 | 0.052846 | -0.16412 | 0.36541 | -0.21393 | 0.16543 | 0.88042
| 7646 | 0.12759 | -0.30509 | -0.43671 | -0.60898 | -0.35603 | 0.048422 | -0.3297 | -0.070538 | -0.4471 | 0.58323
| 7647 | 0.36715 | 0.02609 | -0.22831 | -0.030206 | -0.0052639 | -0.35727 | -0.82883 | 0.22238 | -0.19495 | 0.61908
| 7648 | -0.10273 | -0.31831 | -0.085943 | 0.21063 | 0.17012 | 0.28635 | -0.35852 | 0.15295 | 0.52073 | -0.12908
| 7649 | -0.26822 | -0.17811 | -0.22857 | -0.20508 | 0.49315 | -0.17423 | 0.88642 | -0.0063703 | 0.2689 | -0.081142
| 7650 | -0.51472 | -0.0023528 | 0.06603 | 0.18079 | -0.29282 | -0.30581 | -0.37175 | 0.60974 | -0.4553 | -0.21203
| 7651 | -0.77439 | 0.19284 | -0.069248 | 0.73789 | -0.10798 | -0.22663 | -0.28565 | 0.47818 | -0.5172 | -0.42807
| 7652 | 0.65114 | 0.082013 | 0.80328 | -0.16639 | -0.083758 | -0.16543 | 0.12074 | -0.63875 | 0.59392 | 0.12862
| 7653 | 0.047372 | 0.44764 | -0.059734 | 0.48144 | -0.46962 | -0.036828 | 0.29226 | -0.094627 | -0.6995 | 0.3375
| 7654 | -0.082231 | 0.068496 | 0.2287 | -0.71804 | 0.099056 | -0.66698 | -0.061437 | -0.10529 | 0.31378 | 0.16711
| 7655 | -0.42737 | 0.25455 | -0.19545 | 0.10753 | 0.62384 | 0.096728 | -0.043601 | 0.086928 | 0.096839 | -0.38413
| 7656 | 0.22948 | -0.26549 | -0.27274 | 0.31728 | -0.54558 | 0.88042 | 0.7839 | -0.1852 | -0.51575 | 0.53406
| 7657 | 0.097503 | -0.29296 | -0.10541 | -0.48338 | -0.71627 | -0.57186 | -0.15224 | 0.20634 | -0.33269 | 0.12028
| 7658 | -0.05158 | -0.42982 | -0.36889 | -0.20156 | 0.11248 | 0.70623 | 0.43246 | 0.17884 | -0.90673 | -0.16042
| 7659 | -0.18312 | 0.0043595 | -0.72233 | -0.17653 | -0.41221 | -0.71733 | 0.33359 | -0.088243 | 0.21495 | -0.37254
| 7660 | 0.35899 | -0.28425 | 0.46661 | -0.5001 | 0.17084 | -0.067637 | -0.77175 | -0.17253 | -0.23221 | -0.58587
| 7661 | 0.27744 | -0.24165 | 0.70657 | -0.30107 | -0.18422 | -0.20911 | 0.040677 | 0.081142 | 0.07043 | -0.52915
| 7662 | -0.59988 | -0.21203 | 0.38934 | -0.19124 | -0.3369 | -0.0014511 | 0.077449 | -0.20294 | 0.20836 | 0.01091
| 7663 | -0.35883 | -0.16771 | 0.12461 | 0.21 | 0.4232 | -0.082994 | -0.46774 | 0.75322 | 0.45475 | 0.35852
| 7664 | 0.09706 | 0.70453 | 0.81807 | 0.077232 | 0.50492 | 0.18226 | -0.69685 | 0.72596 | -0.54142 | 0.0011507
| 7665 | -0.16795 | 0.7005 | 0.58275 | 0.76357 | -0.5283 | -0.52303 | -0.71173 | -0.38885 | 0.024756 | -0.1597
| 7666 | 0.79925 | 0.26128 | 0.54712 | -0.84801 | -0.92859 | -0.64574 | 0.73223 | -0.036828 | -0.17677 | -0.10139
| 7667 | 0.40696 | 0.052319 | -0.32155 | -0.09132 | 0.43742 | -0.2175 | -0.8422 | -0.23482 | -0.49078 | -0.0012508
| 7668 | 0.28495 | 0.72779 | 0.21292 | 0.29936 | 0.45182 | 0.063037 | -0.31655 | 0.29864 | 0.022606 | 0.49493
| 7669 | -0.15935 | -0.64829 | 0.47856 | -0.76188 | 0.11881 | -0.25966 | -0.012225 | 0.35031 | 0.66044 | 0.13727
| 7670 | -0.3303 | -0.3211 | -0.6852 | 0.70117 | -0.55379 | 0.82824 | -0.048317 | -0.49552 | -0.41562 | -0.16735
| 7671 | 0.48473 | -0.27453 | 0.57163 | -0.40713 | 0.90461 | -0.31597 | -0.046533 | 0.65086 | -0.27716 | -0.28509
| 7672 | -0.44891 | 0.47914 | 0.53729 | 0.17109 | -0.64489 | 0.59147 | -0.29979 | -0.0029544 | -0.21444 | 0.28076
| 7673 | -0.39213 | -0.65927 | 0.45732 | 0.098834 | -0.71663 | -0.12644 | -0.60238 | 0.43635 | 0.31407 | 0.041407
| 7674 | 0.43991 | 0.20772 | -0.14122 | 0.4163 | 0.5447 | 0.21482 | -0.28551 | 0.36164 | -0.31189 | -0.056867
| 7675 | -0.57798 | -0.45751 | 0.013035 | -0.55067 | 0.71035 | -0.36905 | -0.29936 | 0.52851 | 0.50573 | -0.59863
| 7676 | -0.3369 | 0.18373 | 0.5458 | 0.21763 | -0.65489 | 0.45585 | -0.64914 | 0.47038 | 0.64097 | -0.17447
| 7677 | 0.19037 | -0.55875 | -0.5021 | 0.11405 | 0.20709 | 0.34662 | 0.014252 | 0.20194 | -0.099611 | 0.17
| 7678 | -0.5015 | -0.13242 | 0.3537 | -0.064853 | -0.43635 | -0.024551 | 0.035998 | -0.27868 | -0.0092932 | -0.048002
| 7679 | 0.27509 | 0.020663 | 0.48941 | 0.34464 | -0.026193 | -0.5098 | 0.40025 | 0.30079 | -0.5458 | 0.26345
| 7680 | 0.34388 | -0.13104 | 0.30093 | 0.67643 | 0.25334 | 0.95417 | 0.44313 | -0.88295 | -0.02189 | -0.068281
| 7681 | 0.81372 | -0.033822 | -0.15401 | 0.066673 | 0.046113 | -0.17374 | -0.35479 | -0.65373 | -0.19223 | 0.34555
| 7682 | 0.16268 | 0.063037 | 0.59788 | 0.29 | -0.19272 | -0.036413 | 0.2602 | 0.32717 | 0.009697 | 0.16807
| 7683 | -0.1752 | 0.29155 | 0.7184 | 0.18287 | -0.28369 | 0.46906 | 0.24323 | -0.23941 | 0.31875 | -0.41579
| 7684 | -0.29367 | -0.53 | -0.27014 | -0.26781 | -0.079837 | 0.36211 | 0.41357 | 0.079837 | -0.66819 | -0.27151
| 7685 | -0.50271 | 0.39411 | 0.35231 | -0.37992 | 0.035687 | -0.31276 | 0.77572 | 0.038907 | 0.046952 | -0.71
| 7686 | 0.018114 | -0.077341 | 0.3363 | -0.75813 | -0.048422 | 0.18951 | 0.26863 | 0.65663 | 0.076799 | -0.50513
| 7687 | -0.39925 | -0.11858 | 0.38299 | 0.18201 | 0.10708 | 0.6546 | -0.18753 | -0.49354 | 0.26128 | -0.94084
| 7688 | 0.06229 | -0.69357 | 0.18238 | -0.65402 | -0.4337 | 0.70794 | 0.72054 | -0.27165 | 0.42842 | -0.16173
| 7689 | 0.53192 | -0.20156 | -0.088573 | 0.10552 | -0.67243 | 0.57397 | 0.024654 | -0.076691 | -0.59024 | -0.57893
| 7690 | 0.28761 | 0.99 | 0.48707 | -0.59788 | 0.16759 | 0.099944 | -0.13716 | -0.65229 | 0.20949 | -0.76784
| 7691 | 0.39958 | -0.78483 | -0.17896 | -0.027632 | 0.2484 | -0.77932 | -0.058671 | -0.43264 | -0.10195 | 0.78576
| 7692 | 0.23156 | -0.066244 | 0.20899 | -0.55649 | -0.42337 | -0.2907 | -0.41957 | -0.12977 | -0.26795 | 0.54712
| 7693 | 0.11767 | 0.1758 | 0.60013 | 0.20219 | 0.44134 | 0.11903 | -0.71557 | -0.23091 | 0.69652 | 0.096839
| 7694 | 0.16256 | -0.55067 | 0.5469 | 0.19235 | 0.34525 | 0.3751 | 0.51307 | -0.31582 | -0.073447 | -0.076041
| 7695 | -0.39593 | 0.40561 | -0.18741 | 0.075608 | 0.4799 | 0.17169 | 0.42459 | -0.16783 | -0.77662 | 0.2722
| 7696 | -0.25254 | 0.34494 | 0.12176 | -0.464 | -0.136 | 0.13265 | -0.068388 | -0.057822 | 0.26959 | -0.0094951
| 7697 | 0.17896 | 0.15306 | 0.0094951 | 0.2313 | -0.47626 | 0.14683 | -0.57116 | -0.31626 | 0.33179 | -0.42424
| 7698 | 0.33811 | 0.19919 | -0.39775 | 0.37863 | 0.25643 | 0.83297 | 0.12874 | -0.13646 | -0.036205 | 0.14029
| 7699 | -0.26318 | 0.25334 | 0.085178 | -0.2175 | -0.00015001 | -0.30451 | 0.52177 | -0.66668 | -0.38186 | -0.19744
| 7700 | -0.19 | -0.16844 | 0.41751 | 0.16054 | 0.36557 | 0.030928 | -0.7816 | 0.18201 | 0.4471 | -0.15035
| 7701 | -0.65114 | 0.58251 | 0.4232 | 0.14824 | -0.3214 | -0.41408 | -0.18532 | 0.085943 | 0.57233 | -0.026707
| 7702 | 0.364 | -0.75444 | 0.65316 | 0.042973 | 0.17362 | 0.31919 | 0.5172 | -0.066351 | -0.49157 | 0.50412
| 7703 | -0.30725 | 0.035687 | 0.54316 | -0.25656 | -0.17544 | -0.49216 | -0.010202 | 0.34448 | -0.4392 | -0.046638
| 7704 | 0.12587 | 0.28916 | -0.33615 | 0.079402 | -0.7005 | -0.13646 | 0.4653 | -0.0014511 | -0.45917 | -0.2602
| 7705 | 0.11281 | -0.031135 | 0.56537 | -0.2598 | 0.17326 | -0.13057 | -0.75772 | 0.02568 | -0.04517 | 0.13
| 7706 | -0.11518 | 0.58878 | 0.48202 | 0.61646 | 0.80532 | -0.40343 | -0.17096 | -0.3132 | -0.46176 | 0.22071
| 7707 | 0.82651 | 0.11157 | 0.41579 | 0.7839 | 0.82766 | 0.09165 | -0.025782 | -0.14871 | -0.020153 | -0.38121
| 7708 | -0.40309 | 0.13219 | -0.25926 | 0.34908 | 0.060585 | 0.43246 | 0.45548 | -0.43158 | -0.49334 | -0.14215
| 7709 | -0.26509 | -0.71417 | -0.23169 | -0.72125 | -0.17653 | -0.67891 | -0.10686 | -0.39593 | -0.65897 | -0.41153
| 7710 | 0.11541 | -0.2711 | 0.44638 | -0.37048 | 0.010202 | -0.05253 | -0.19173 | 0.12816 | 0.81752 | -0.27785
| 7711 | 0.31963 | -0.52387 | -0.012528 | 0.57562 | -0.36463 | 0.24827 | 0.065709 | 0.3961 | -0.23783 | -0.16699
| 7712 | 0.37207 | 0.53946 | -0.57 | -0.15816 | 0.073771 | -0.56057 | 0.32007 | -0.045484 | 0.19582 | 0.69817
| 7713 | 0.047162 | 0.95417 | 0.00015001 | 0.22547 | 0.29438 | -0.44873 | 0.12017 | -0.14437 | -0.1752 | -0.085943
| 7714 | -0.25482 | 0.48824 | -0.11236 | -0.28972 | 0.24694 | -0.50918 | 0.46269 | -0.10273 | -0.25107 | 0.12599
| 7715 | 0.095954 | -0.68968 | 0.73942 | -0.79826 | -0.15024 | 0.50939 | -0.61231 | -0.46102 | 0.23928 | -0.34174
| 7716 | -0.58275 | -0.65868 | -0.38121 | 0.66758 | 0.53686 | -0.031444 | -0.15578 | -0.42563 | 0.4859 | -0.39543
| 7717 | 0.31407 | -0.64574 | -0.057609 | -0.34908 | 0.5007 | -0.35665 | 0.45328 | 0.53171 | 0.26441 | -0.077449
| 7718 | -0.13288 | -0.51348 | 0.39726 | 0.28719 | 0.55022 | -0.050948 | 0.78068 | -0.36337 | 0.97764 | 0.30394
| 7719 | -0.31043 | -0.5806 | -0.56768 | -0.27233 | 0.10351 | 0.23495 | -0.46906 | -0.18116 | 0.8467 | 0.13473
| 7720 | 0.56011 | -0.34846 | -0.51637 | 0.011213 | 0.025372 | -0.29042 | -0.0087886 | 0.32896 | 0.20772 | -0.48338
| 7721 | -0.19247 | -0.062823 | 0.41357 | 0.09154 | -0.34464 | -0.16531 | -0.093192 | -0.37254 | 0.013238 | -0.09099
| 7722 | 0.065602 | -0.41562 | 0.045904 | 0.55447 | 0.33977 | 0.51678 | -0.16964 | 0.62224 | 0.11259 | 0.18397
| 7723 | 0.75526 | 0.06229 | 0.1559 | -0.36668 | -0.048633 | -0.32184 | 0.048633 | -0.10206 | -0.66879 | -0.34954
| 7724 | -0.81 | -0.62437 | -0.0037571 | -0.012934 | -0.85964 | -0.74682 | -0.2427 | 0.095622 | -0.45677 | -0.43813
| 7725 | -0.68078 | 0.019031 | 0.13797 | 0.043391 | -0.35805 | 0.52724 | 0.22122 | 0.29466 | -0.18189 | -0.026501
| 7726 | 0.35805 | 0.44619 | 0.26959 | 0.72197 | -0.20269 | -0.40359 | -0.032581 | 0.75607 | 0.62198 | -0.57233
| 7727 | 0.0069743 | -0.22767 | 0.083103 | 0.21292 | -0.31611 | -0.40376 | 0.87876 | -0.57869 | 0.46774 | -0.28747
| 7728 | 0.47076 | 0.041199 | -0.015368 | -0.30036 | 0.41391 | -0.22482 | 0.58927 | -0.34754 | 0.47094 | 0.7504
| 7729 | -0.3759 | 0.29085 | 0.75607 | 0.24178 | 0.73373 | -0.60541 | 0.37478 | -0.61077 | -0.10585 | -0.052424
| 7730 | -0.28747 | -0.47607 | -0.016283 | -0.28299 | -0.16484 | -0.09022 | -0.030928 | 0.55312 | 0.35649 | -0.13808
| 7731 | -0.74174 | 0.12587 | -0.68936 | 0.32762 | -0.028867 | 0.47284 | -0.47741 | -0.73675 | 0.0083852 | 0.48882
| 7732 | 0.12279 | 0.28649 | 0.44909 | 0.2711 | -0.58299 | 0.3629 | -0.12393 | 0.20344 | 0.10518 | -0.20207
| 7733 | 0.31875 | -0.016791 | -0.52198 | -0.44891 | 0.077449 | 0.29381 | -0.3451 | -0.71069 | -0.24947 | 0.29679
| 7734 | 0.061544 | 0.19607 | 0.13392 | -0.09066 | 0.012934 | 0.00025003 | 0.46009 | 0.87876 | -0.1025 | 0.36431
| 7735 | -0.035894 | -0.16579 | 0.49731 | 0.040365 | -0.80075 | -0.37622 | -0.37654 | 0.64349 | 0.4736 | -0.099611
| 7736 | -0.2278 | 0.31218 | 0.63517 | -0.11813 | -0.19049 | -0.59788 | 0.3363 | 0.20747 | -0.68552 | 0.40645
| 7737 | 0.28146 | -0.16519 | -0.53513 | -0.53128 | 0.83357 | -0.79384 | 0.27481 | 0.18926 | 0.30093 | -0.73373
| 7738 | -0.29537 | 0.10017 | 0.47894 | -0.16054 | -0.33359 | 0.0036567 | 0.03714 | -0.11609 | -0.71208 | -0.63
| 7739 | 0.021276 | 0.17205 | -0.0012508 | 0.29722 | -0.2985 | 0.19384 | 0.01486 | -0.41528 | 0.44331 | -0.44277
| 7740 | 0.20445 | -0.09187 | 0.11011 | -0.1752 | -0.036205 | 0.12199 | -0.28411 | -0.27316 | -0.23862 | -0.74446
| 7741 | 0.0076795 | -0.12908 | 0.57846 | 0.51328 | -0.40595 | 0.24442 | -0.21368 | 0.3422 | 0.50654 | -0.11484
| 7742 | -0.048317 | -0.53664 | -0.10028 | 0.0090913 | 0.34433 | 0.32346 | -0.26945 | -0.24138 | -0.31772 | -0.2081
| 7743 | -0.07043 | -0.30365 | -0.48454 | -0.35821 | -0.70589 | -0.098279 | 0.49394 | -0.25174 | 0.28775 | 0.31232
| 7744 | -0.02722 | -0.45 | -0.5714 | 0.94615 | 0.15071 | -0.75 | -0.073124 | -0.11124 | -0.4046 | 0.65172
| 7745 | 0.38073 | 0.11079 | -0.47246 | -0.89464 | 0.10195 | -0.11383 | -0.50715 | 0.02609 | -0.2995 | 0.16675
| 7746 | 0.40494 | -0.41579 | 0.14425 | -0.19956 | 0.16856 | -0.70017 | -0.53235 | 0.28551 | -0.27771 | 0.27041
| 7747 | 0.2722 | -0.26468 | -0.6382 | 0.14169 | 0.16364 | -0.85269 | -0.55312 | -0.24947 | 0.27481 | 0.14589
| 7748 | 0.69292 | -0.70352 | 0.18753 | 0.23875 | 0.6162 | 0.15012 | -0.041929 | 0.35727 | -0.43458 | -0.54098
| 7749 | -0.9134 | 0.5102 | 0.45438 | -0.63163 | 0.59763 | -0.17921 | -0.56125 | 0.54778 | 0.46925 | 0.8454
| 7750 | -0.17121 | -0.040782 | 0.2791 | -0.1127 | 0.20307 | 0.17471 | -0.19148 | -0.30423 | 0.11338 | -0.56606
| 7751 | -0.45898 | 0.23534 | 0.60567 | -0.13334 | -0.38984 | -0.016994 | 0.61464 | 0.41888 | 0.46065 | 0.13588
| 7752 | 0.39825 | -0.41511 | -0.53707 | 0.1338 | 0.3363 | -0.29964 | 0.55111 | 0.041094 | -0.33419 | -0.88467
| 7753 | -0.13577 | -0.50776 | 0.8618 | 0.094738 | -0.012934 | 0.43281 | 0.061757 | -0.35572 | 0.012225 | 0.044123
| 7754 | -0.16976 | 0.35031 | 0.15721 | 0.2484 | 0.040052 | 0.3796 | -0.071184 | -0.053058 | -0.34938 | 0.10921
| 7755 | 0.7569 | -0.43317 | 0.35634 | -0.17169 | 0.4194 | -0.7687 | -0.43281 | 0.20798 | -0.50614 | -0.33254
| 7756 | -0.14355 | -0.16209 | 0.12931 | -0.020766 | 0.3005 | -0.25723 | 0.75607 | 0.38608 | -0.31145 | -0.26713
| 7757 | 0.38348 | 0.50634 | 0.19471 | 0.63408 | -0.2042 | -0.50695 | 0.24349 | 0.28986 | -0.7816 | -0.32569
| 7758 | 0.43546 | -0.12267 | 0.74525 | -0.50432 | 0.17848 | 0.80947 | 0.23013 | 0.76827 | -0.072908 | -0.26631
| 7759 | -0.1578 | 0.96394 | 0.026809 | 0.16904 | -0.42389 | -0.348 | -0.2907 | -0.41802 | 0.58443 | -0.46887
| 7760 | -0.047687 | 0.50311 | -0.46306 | -0.77528 | 0.09077 | -0.16256 | -0.5174 | -0.32643 | -0.26699 | 0.13774
| 7761 | -0.017096 | -0.50654 | -0.044856 | 0.26973 | 0.47057 | -0.12131 | 0.35603 | 0.0049623 | 0.50231 | -0.5922
| 7762 | 0.53989 | 0.075608 | -0.32776 | -0.5019 | -0.30913 | 0.0046609 | 0.46661 | 0.41221 | -0.18581 | -0.74722
| 7763 | -0.38461 | 0.60872 | -0.5728 | -0.37734 | -0.53556 | -0.70217 | 0.079946 | 0.10496 | -0.20332 | 0.48435
| 7764 | 0.12885 | -0.44656 | -0.061544 | -0.05253 | 0.42164 | 0.12302 | 0.13369 | 0.40376 | 0.39428 | 0.35015
| 7765 | 0.1382 | -0.66519 | -0.30179 | 0.10261 | 0.70521 | 0.16687 | 0.20194 | 0.2081 | -0.50371 | 0.63931
| 7766 | 0.023424 | -0.8043 | 0.2184 | -0.33075 | 0.068818 | -0.56171 | 0.38234 | 0.62304 | 0.55022 | -0.30207
| 7767 | 0.65897 | -0.9245 | 0.054114 | -0.72852 | 0.097171 | -0.018929 | 0.28817 | 0.16747 | 0.079511 | -0.76827
| 7768 | 0.24283 | -0.085396 | 0.19495 | 0.42668 | -0.30021 | 0.36258 | 0.2488 | -0.45658 | -0.20445 | -0.76104
| 7769 | -0.10106 | -0.02281 | -0.39131 | -0.41888 | 0.019133 | -0.44964 | -0.18092 | 0.16232 | -0.25067 | 0.1803
| 7770 | -0.2287 | 0.45109 | -0.21495 | 0.4983 | 0.19284 | 0.73448 | -0.1082 | -0.23744 | -0.71173 | -0.42251
| 7771 | 0.28733 | -0.098723 | -0.17629 | 0.075933 | 0.39444 | 0.37815 | 0.1418 | 0.071614 | 0.44098 | 0.64971
| 7772 | 0.67182 | -0.18079 | -0.50492 | -0.29183 | -0.3025 | 0.17109 | -0.00035006 | -0.057928 | -0.09099 | 0.033615
| 7773 | -0.33811 | 0.20975 | 0.42511 | -0.3248 | -0.19557 | 0.24416 | -0.7504 | 0.42303 | 0.19396 | 0.097836
| 7774 | 0.46699 | 0.37558 | 0.69817 | 0.30567 | -0.11146 | -0.082667 | 0.17423 | 0.10373 | 0.10753 | 0.91815
| 7775 | -0.41802 | -0.21814 | -0.64377 | 0.77707 | 0.082449 | -0.11236 | 0.15188 | -0.17338 | 0.31568 | 0.54251
| 7776 | -0.66578 | -0.093082 | 0.15318 | -0.16976 | 0.38251 | 0.084085 | 0.70487 | -0.5174 | 0.099722 | -0.044751
| 7777 | 0.31174 | -0.15106 | -0.30136 | -0.27757 | 0.41836 | 0.15839 | -0.17653 | 0.28355 | -0.79095 | -0.17544
| 7778 | -0.1245 | 0.036621 | -0.11586 | 0.51 | -0.080489 | -0.067745 | 0.003155 | -0.10351 | 0.021992 | -0.48961
| 7779 | -0.0043595 | -0.3306 | -0.63792 | 0.51657 | 0.08649 | -0.46849 | 0.24416 | -0.74525 | 0.32881 | -0.27882
| 7780 | -0.70386 | 0.23731 | 0.23117 | 0.16711 | 0.58299 | 0.48687 | 0.40125 | 0.39975 | 0.18055 | 0.53449
| 7781 | -0.18006 | 0.1082 | 0.092972 | -0.01091 | -0.46849 | -0.36968 | 0.79727 | 0.85337 | -0.43813 | 0.055913
| 7782 | 0.061331 | 0.56148 | 0.16376 | -0.10664 | 0.10017 | 0.27055 | -0.33419 | 0.5102 | 0.28537 | 0.5954
| 7783 | 0.8043 | -0.5332 | -0.61361 | -0.044123 | 0.056973 | -0.59417 | 0.94615 | 0.06229 | -0.29438 | -0.24654
| 7784 | -0.77707 | 0.59269 | -0.40209 | 0.52576 | -0.58515 | -0.40949 | -0.2791 | -0.3454 | 0.20483 | -0.047057
| 7785 | -0.7492 | 0.48396 | 0.010303 | 0.32287 | 0.73524 | -0.13658 | -0.41477 | 0.54756 | -0.047792 | -0.12199
| 7786 | -0.20119 | -0.74135 | -0.26183 | 0.35774 | 0.55989 | -0.28972 | 0.30466 | 0.68775 | 0.40075 | -0.22495
| 7787 | 0.51 | 0.96683 | 0.38218 | 0.016893 | -0.22637 | 0.32821 | 0.41187 | 0.047897 | 0.10641 | -0.30639
| 7788 | 0.15212 | 0.31102 | 0.28188 | -0.56034 | 0.24853 | 0.088902 | 0.28607 | 0.58976 | 0.46718 | -0.32302
| 7789 | -0.63545 | 0.49354 | -0.017096 | 0.17702 | -0.017198 | 0.028352 | -0.040573 | -0.78297 | 0.064425 | 0.11677
| 7790 | 0.12108 | 0.45769 | -0.32732 | -0.25401 | 0.1253 | -0.67458 | -0.10351 | 0.5224 | 0.19421 | -0.19471
| 7791 | 0.25535 | 0.42303 | -0.035272 | 0.064212 | 0.38396 | -0.65086 | 0.27069 | -0.23117 | 0.23915 | 0.42459
| 7792 | -0.34327 | 0.46493 | 0.050632 | 0.45347 | -0.34129 | -0.3297 | -0.87958 | 0.41922 | -0.82196 | 0.79048
| 7793 | 0.41957 | -0.2722 | -0.59838 | 0.16976 | -0.15342 | 0.55807 | 0.52788 | -0.063464 | -0.06603 | 0.50634
| 7794 | -0.62437 | 0.55898 | 0.79628 | -0.2225 | 0.2147 | 0.22611 | -0.74407 | -0.35727 | -0.21738 | 0.36023
| 7795 | 0.24469 | -0.024244 | -0.3132 | 0.17787 | -0.093744 | 0.068818 | -0.45658 | -0.36353 | -0.36652 | -0.34816
| 7796 | -0.18434 | 0.61542 | 0.16113 | -0.58299 | -0.45383 | -0.42285 | -0.095401 | -0.24987 | -0.32509 | 0.25522
| 7797 | -0.82941 | -0.15224 | 0.3923 | -0.038699 | -0.24125 | 0.41854 | -0.48222 | -0.35278 | 0.27619 | 0.1162
| 7798 | 0.6382 | -0.59417 | -0.37895 | -0.15342 | 0.29367 | -0.1091 | -0.51061 | 0.7496 | 0.35743 | -0.040886
| 7799 | 0.68711 | -0.075284 | -0.55537 | -0.13681 | 0.040677 | -0.72559 | -0.38299 | 0.38575 | -0.26101 | 0.15887
| 7800 | -0.0028541 | 0.28439 | 0.40276 | -0.67274 | 0.21521 | 0.1473 | -0.01842 | 0.57233 | 0.079294 | 0.83357
| 7801 | 0.068711 | 0.050632 | 0.12336 | 0.016994 | -0.11541 | -0.48183 | -0.71663 | -0.20156 | -0.56445 | -0.68141
| 7802 | -0.02897 | -0.51637 | 0.31 | 0.42703 | 0.2823 | -0.42685 | -0.06325 | 0.24508 | 0.38543 | -0.10406
| 7803 | -0.49137 | -0.0060684 | 0.14906 | 0.11643 | 0.033512 | 0.7881 | 0.27868 | -0.40142 | 0.94804 | 0.21266
| 7804 | 0.22058 | 0.57964 | -0.016079 | 0.18508 | 0.24535 | -0.19994 | -0.16018 | -0.34023 | -0.079402 | -0.19533
| 7805 | -0.056019 | 0.78023 | 0.26291 | -0.48202 | -0.2356 | 0.35743 | -0.25455 | 0.49512 | -0.67121 | -0.10106
| 7806 | 0.39527 | -0.9005 | 0.69227 | -0.062503 | 0.20508 | 0.0093941 | 0.82308 | -0.13299 | -0.18238 | 0.077666
| 7807 | 0.63244 | 0.69227 | 0.57656 | -0.47284 | 0.11767 | 0.49751 | -0.33314 | -0.019643 | -0.11609 | 0.025474
| 7808 | 0.26918 | 0.0010506 | -0.3751 | 0.48785 | -0.5021 | 0.4997 | 0.0043595 | 0.55943 | 0.24363 | -0.39908
| 7809 | -0.21254 | -0.73 | -0.38461 | 0.4408 | 0.2081 | 0.43582 | 0.40679 | 0.052635 | -0.19086 | -0.25953
| 7810 | 0.076691 | -0.25602 | 0.75485 | 0.057716 | 0.2941 | 0.78344 | 0.056443 | 0.47398 | -0.73 | 0.12074
| 7811 | 0.38396 | -0.51389 | -0.13415 | -0.12839 | -0.021072 | 0.44909 | 0.54054 | -0.4046 | 0.0032553 | -0.78297
| 7812 | 0.064639 | -0.24482 | -0.20659 | -0.10295 | -0.42181 | -0.39049 | 0.31334 | -0.1688 | -0.58275 | 0.53902
| 7813 | 0.19881 | 0.52157 | -0.10776 | 0.029176 | 0.0048618 | 0.10686 | -0.26373 | 0.76484 | -0.84867 | -0.22728
| 7814 | 0.50573 | 0.27951 | 0.068281 | -0.14145 | 0.003456 | 0.63027 | -0.023322 | -0.44601 | 0.030206 | 0.49473
| 7815 | 0.69357 | 0.08474 | 0.33239 | -0.61829 | -0.37143 | 0.65809 | -0.62277 | 0.52555 | 0.40729 | -0.24787
| 7816 | -0.40679 | 0.010101 | 0.062077 | -0.06229 | 0.25858 | -0.20119 | -0.35 | -0.29367 | -0.21661 | 0.53363
| 7817 | 0.21444 | -0.072584 | -0.73223 | -0.08485 | 0.088134 | 0.15543 | -0.61077 | -0.19794 | 0.26413 | -0.089231
| 7818 | -0.080054 | 0.41957 | -0.38429 | 0.8422 | 0.14379 | -0.16988 | -0.32628 | 0.036413 | 0.17544 | 0.23744
| 7819 | -0.023936 | 0.22328 | -0.2512 | -0.17326 | -0.26713 | -0.29509 | 0.55898 | 0.48396 | 0.027426 | -0.59
| 7820 | -0.3248 | 0.49612 | -0.59863 | -0.71592 | -0.24033 | 0.59565 | 0.0866 | 0.36857 | -0.61 | 0.35432
| 7821 | 0.91225 | -0.2924 | 0.77 | -0.8148 | -0.29339 | -0.10061 | 0.00075028 | -0.14332 | 0.5728 | 0.27261
| 7822 | -0.74446 | 0.46046 | -0.30265 | -0.39543 | 0.21025 | 0.61 | -0.010808 | 0.7429 | 0.40427 | 0.72269
| 7823 | -0.49275 | -0.59122 | -0.33735 | -0.28355 | -0.077991 | -0.19645 | -0.073555 | 0.064318 | -0.20672 | 0.20596
| 7824 | -0.53021 | -0.71 | 0.68711 | 0.32214 | -0.17471 | 0.39593 | -0.35448 | -0.18753 | -0.4041 | 0.20975
| 7825 | 0.37606 | 0.56285 | 0.33947 | -0.46605 | -0.013744 | 0.29099 | -0.22987 | 0.88467 | 0.23247 | -0.13311
| 7826 | 0.082994 | 0.21203 | -0.11451 | 0.1204 | -0.56791 | -0.80947 | 0.36463 | 0.5954 | -0.12576 | -0.21139
| 7827 | -0.0014511 | -0.42355 | 0.53751 | 0.61103 | 0.28677 | 0.66668 | -0.30207 | -0.20609 | 0.31949 | 0.61856
| 7828 | -0.36841 | -0.053269 | 0.19384 | 0.48106 | -0.21241 | -0.82941 | -0.54338 | 0.12108 | -0.39892 | 0.00055015
| 7829 | -0.0039578 | 0.33075 | 0.30193 | -0.28579 | -0.74019 | -0.43193 | 0.60795 | 0.96683 | 0.53406 | 0.18667
| 7830 | 0.45622 | -0.14472 | -0.25307 | -0.18704 | -0.30653 | 0.075608 | 0.11124 | 0.089561 | -0.54889 | 0.2744
| 7831 | -0.10507 | 0.45328 | 0.14847 | -0.30365 | -0.30884 | 0.038387 | -0.04172 | -0.35743 | 0.017605 | 0.043496
| 7832 | 0.58371 | -0.33 | 0.3743 | -0.47113 | 0.41562 | -0.1513 | 0.72378 | -0.1706 | 0.70318 | -0.15165
| 7833 | -0.10362 | -0.71277 | 0.62731 | 0.27522 | -0.73789 | -0.0056661 | -0.33932 | 0.19632 | 0.0995 | -0.061544
| 7834 | 0.37654 | -0.53556 | -0.044961 | 0.73981 | 0.29212 | -0.046008 | -0.023732 | 0.32643 | -0.37302 | 0.73561
| 7835 | -0.39726 | -0.0081835 | 0.8956 | -0.30007 | 0.11349 | 0.26863 | -0.056549 | -0.65345 | -0.18336 | 0.042242
| 7836 | 0.71035 | 0.3759 | 0.36857 | 0.23809 | -0.88042 | -0.50492 | 0.41442 | 0.096728 | 0.12427 | -0.6349
| 7837 | 0.13496 | 0.41922 | -0.31407 | 0.18704 | 0.55807 | -0.079077 | -0.077883 | -0.46009 | -0.17374 | 0.0173
| 7838 | -0.046638 | 0.44891 | -0.15024 | -0.54492 | -0.40611 | -0.27261 | -0.054537 | 0.13634 | -0.059096 | -0.72632
| 7839 | -0.37831 | 0.7492 | -0.10563 | -0.13658 | -0.55044 | 0.12908 | 0.30841 | 0.014353 | 0.30942 | -0.31524
| 7840 | -0.26196 | -0.29979 | -0.2524 | -0.17738 | 0.53235 | 0.0040582 | 0.17787 | 0.26183 | 0.1082 | 0.28607
| 7841 | -0.17568 | 0.031238 | 0.28132 | -0.067637 | 0.24204 | -0.24907 | -0.39428 | -0.25522 | -0.49691 | -0.65809
| 7842 | -0.29836 | 0.39164 | -0.4859 | -0.16268 | 0.26604 | -0.86546 | 0.076474 | 0.2598 | -0.23967 | 0.017401
| 7843 | -0.19012 | -0.62973 | -0.29594 | -0.44134 | 0.43688 | -0.80226 | -0.1597 | -0.13855 | -0.094517 | 0.10843
| 7844 | -0.5005 | -0.083103 | 0.38951 | 0.30696 | 0.20483 | -0.78622 | -0.0027538 | 0.21546 | 0.14613 | -0.34601
| 7845 | 0.15318 | 0.14918 | 0.3618 | 0.52471 | 0.13634 | -0.068388 | 0.074635 | 0.38024 | -0.097947 | -0.21572
| 7846 | 0.41648 | 0.8882 | 0.068925 | 0.60415 | -0.18336 | -0.12507 | 0.19657 | -0.34099 | -0.40729 | 0.11552
| 7847 | -0.54426 | 0.35231 | -0.31422 | -0.15673 | -0.023732 | -0.33494 | -0.29495 | -0.51865 | 0.46793 | 0.38624
| 7848 | -0.71663 | 0.44873 | -0.19235 | 0.015673 | 0.098612 | 0.7184 | 0.34266 | 0.36889 | 0.30595 | 0.21508
| 7849 | -0.37398 | -0.20119 | 0.67612 | 0.63353 | 0.63848 | -0.093634 | -0.088573 | 0.1253 | -0.38153 | 0.10139
| 7850 | 0.30337 | 0.37191 | 0.046742 | 0.5436 | 0.15436 | -0.22148 | -0.1315 | 0.49157 | -0.21981 | 0.47493
| 7851 | 0.81972 | -0.021072 | -0.040156 | 0.16735 | 0.34159 | -0.73111 | 0.61103 | 0.1439 | 0.81642 | 0.67735
| 7852 | -0.364 | 0.44009 | -0.64715 | -0.063464 | 0.32199 | 0.21076 | -0.076474 | 0.21814 | -0.041199 | 0.53192
| 7853 | 0.034961 | -0.34662 | -0.27924 | 0.012832 | -0.3537 | 0.081795 | -0.098058 | -0.10664 | -0.3242 | 0.96127
| 7854 | 0.41085 | -0.40092 | -0.31392 | -0.37542 | -0.096728 | -0.2512 | 0.57633 | -0.3923 | 0.084413 | 0.043391
| 7855 | 0.23391 | -0.37783 | 0.16424 | 0.50231 | 0.027632 | 0.43511 | 0.2175 | -0.3882 | -0.1559 | 0.69455
| 7856 | -0.43564 | -0.21508 | -0.63599 | 0.42095 | 0.17024 | -0.28944 | -0.19919 | -0.2225 | 0.55694 | 0.63986
| 7857 | 0.18006 | 0.4799 | 0.45898 | -0.024962 | 0.029279 | 0.049053 | -0.16209 | -0.35386 | 0.01547 | -0.37815
| 7858 | 0.25602 | 0.0087886 | 0.80584 | -0.34083 | -0.016689 | -0.70083 | 0.24827 | -0.13739 | 0.63081 | 0.39892
| 7859 | -0.043391 | -0.31465 | -0.30036 | -0.26007 | 0.22238 | -0.60238 | -0.73 | 0.039115 | -0.20244 | 0.1179
| 7860 | 0.03579 | 0.73981 | -0.89091 | -0.48493 | -0.11518 | -0.64265 | -0.17 | 0.58636 | 0.35154 | -0.055384
| 7861 | 0.63986 | 0.24667 | -0.3662 | 0.0019519 | 0.18766 | -0.47588 | -0.63572 | 0.4776 | -0.12897 | 0.044019
| 7862 | -0.8937 | -0.061331 | -0.11225 | -0.66879 | 0.7816 | -0.34099 | -0.2278 | -0.44098 | 0.0027538 | -0.2621
| 7863 | 0.76063 | 0.13196 | -0.040365 | 0.32658 | -0.15259 | -0.12313 | -0.025269 | -0.78114 | -0.38902 | 0.71875
| 7864 | 0.19359 | -0.041929 | -0.21878 | 0.17302 | 0.82365 | 0.46643 | -0.019235 | 0.38902 | 0.4134 | 0.58708
| 7865 | -0.026604 | -0.17909 | 0.28733 | -0.73223 | 0.0019519 | -0.43848 | 0.61934 | 0.44027 | -0.26672 | 0.40477
| 7866 | -0.022708 | -0.59245 | 0.50675 | -0.44746 | -0.059415 | -0.094296 | 0.16603 | -0.51761 | -0.45073 | 0.30351
| 7867 | -0.37079 | 0.73111 | 0.65029 | 0.3951 | -0.025885 | -0.077883 | -0.7508 | -0.65693 | 0.16352 | -0.22173
| 7868 | 0.12713 | -0.71663 | 0.023322 | 0.10028 | 0.65693 | 0.5201 | 0.085287 | -0.82766 | -0.6985 | -0.24893
| 7869 | 0.72197 | -0.036932 | -0.28859 | 0.55559 | 0.34586 | -0.29936 | 0.043601 | -0.23143 | -0.36164 | -0.2598
| 7870 | -0.16484 | -0.4997 | 0.50695 | -0.53794 | -0.66192 | -0.47645 | -0.50492 | -0.044542 | -0.11338 | 0.36921
| 7871 | 0.60289 | 0.019337 | -0.092862 | 0.35123 | -0.5768 | -0.20395 | -0.24667 | 0.22663 | -0.1091 | 0.47933
| 7872 | 0.35108 | -0.19645 | 0.43671 | 0.47665 | 0.52261 | -0.010808 | 0.37815 | -0.65114 | 0.4417 | 0.56583
| 7873 | -0.45438 | 0.28243 | -0.15709 | 0.50735 | -0.014962 | -0.081686 | -0.25214 | -0.74841 | 0.17121 | -0.18618
| 7874 | -0.29197 | 0.54294 | -0.31261 | -0.42043 | 0.14332 | 0.86847 | 0.019439 | -0.44385 | -0.097393 | 0.6578
| 7875 | -0.059096 | -0.011719 | -0.13774 | 0.24257 | 0.82824 | 0.31334 | -0.69292 | -0.045589 | -0.46381 | 0.29141
| 7876 | -0.62224 | 0.44547 | 0.19136 | -0.73486 | -0.51266 | -0.21089 | -0.24601 | 0.35185 | 0.45622 | 0.38283
| 7877 | -0.40427 | -0.011415 | -0.16268 | 0.44224 | 0.019235 | 0.23967 | -0.53192 | -0.076041 | 0.63271 | 0.099278
| 7878 | 0.77796 | -0.21648 | -0.19906 | 0.12267 | -0.34954 | 0.28202 | 0.068496 | -0.055595 | -0.55853 | -0.42459
| 7879 | -0.49512 | -0.19111 | 0.040782 | -0.62811 | -0.74643 | 0.63545 | -0.078425 | 0.36873 | -0.38251 | 0.05899
| 7880 | 0.60923 | -0.73561 | -0.21584 | 0.34114 | -0.29779 | 0.23378 | 0.18532 | -0.78763 | 0.017809 | 0.33555
| 7881 | 0.552 | -0.41272 | -0.1952 | -0.33796 | 0.44601 | -0.11586 | 0.43759 | 0.28579 | 0.59813 | 0.2508
| 7882 | -0.51 | 0.2567 | -0.54867 | -0.12599 | -0.45622 | 0.54778 | -0.42737 | -0.18299 | -0.23587 | -0.1179
| 7883 | 0.66103 | -0.58854 | -0.65201 | 0.59763 | -0.026398 | -0.2326 | 0.12989 | 0.087914 | 0.29864 | -0.36384
| 7884 | -0.15697 | -0.37286 | 0.10039 | 0.53492 | -0.49413 | 0.46774 | 0.21127 | -0.08136 | -0.28887 | -0.74212
| 7885 | -0.13913 | -0.2184 | -0.079077 | -0.63545 | -0.58347 | 0.18189 | -0.68903 | -0.6077 | 0.21763 | 0.42633
| 7886 | 0.27165 | -0.16747 | 0.73981 | -0.47588 | -0.37446 | -0.53427 | -0.34114 | -0.071507 | 0.82536 | 0.47057
| 7887 | 0.21725 | -0.13069 | -0.025885 | -0.14355 | 0.37414 | -0.13242 | -0.20798 | 0.4272 | -0.79288 | 0.44837
| 7888 | -0.4898 | 0.42112 | 0.07043 | -0.69455 | -0.35262 | -0.10206 | 0.60465 | 0.19408 | -0.21904 | 0.55245
| 7889 | -0.067423 | -0.41289 | -0.35883 | -0.30538 | 0.083212 | 0.078208 | -0.39378 | 0.15994 | -0.038387 | 0.29779
| 7890 | 0.32125 | 0.13785 | -0.59714 | -0.21165 | 0.28104 | -0.3306 | 0.20722 | -0.039219 | -0.4999 | 0.33284
| 7891 | 0.20836 | -0.45273 | 0.021379 | -0.41716 | 0.53664 | 0.14965 | 0.83599 | 0.83297 | -0.29042 | 0.047267
| 7892 | 0.10507 | 0.36039 | -0.57538 | 0.31218 | 0.37032 | 0.95877 | -0.79531 | 0.058353 | 0.27674 | -0.32022
| 7893 | 0.59714 | -0.62304 | 0.27481 | -0.39709 | 0.37366 | 0.29566 | -0.13069 | -0.013846 | -0.30308 | 0.3838
| 7894 | 0.0014511 | -0.93 | -0.83357 | -0.11677 | 0.28789 | 0.42668 | 0.23443 | -0.011415 | -0.18901 | -0.85405
| 7895 | 0.0054649 | -0.17945 | 0.12017 | 0.014657 | -0.097614 | -0.2816 | 0.48765 | -0.55089 | -0.50837 | -0.29864
| 7896 | 0.17544 | 0.90566 | 0.24217 | -0.13948 | -0.011617 | -0.043182 | 0.40292 | -0.17109 | 0.39066 | -0.81862
| 7897 | -0.073231 | 0.18963 | 0.3662 | 0.68968 | -0.15224 | -0.010707 | 0.12747 | 0.065923 | 0.45751 | 0.52366
| 7898 | 0.57186 | -0.29452 | 0.035687 | 0.2621 | 0.17483 | 0.53171 | -0.15994 | 0.4985 | -0.83237 | 0.10944
| 7899 | 0.35914 | 0.048738 | 0.51123 | -0.53686 | 0.2784 | 0.12679 | 0.049158 | 0.037971 | 0.28705 | -0.37574
| 7900 | 0.73637 | 0.21674 | -0.079837 | 0.28271 | -0.51328 | 0.552 | 0.028352 | -0.045694 | -0.0866 | -0.59098
| 7901 | -0.074527 | 0.25294 | -0.030619 | -0.049263 | -0.2816 | 0.25831 | 0.16868 | -0.19956 | -0.15071 | 0.30007
| 7902 | 0.099722 | 0.02794 | 0.007478 | 0.47607 | -0.18508 | -0.57023 | 0.48415 | -0.34205 | -0.21266 | 0.15177
| 7903 | 0.10418 | 0.71138 | 0.34494 | -0.13207 | -0.45164 | -0.58951 | -0.021174 | 0.47569 | -0.33299 | -0.45273
| 7904 | -0.69 | 0.26918 | 0.19161 | 0.46028 | 0.34205 | -0.051475 | 0.19086 | -0.4344 | -0.61934 | 0.38526
| 7905 | -0.71522 | 0.3005 | -0.11881 | -0.2722 | -0.36557 | -0.050421 | 0.76188 | 0.53751 | -0.33404 | 0.42129
| 7906 | 0.2119 | -0.29339 | 0.12599 | 0.73448 | -0.68839 | -0.14367 | 0.038283 | 0.29 | 0.78483 | 0.050526
| 7907 | 0.38251 | 0.69718 | -0.44224 | 0.099389 | 0.56262 | -0.33705 | 0.32881 | -0.1559 | 0.81972 | 0.088243
| 7908 | -0.27274 | 0.6786 | -0.45493 | -0.13127 | -0.34311 | -0.013542 | 0.54294 | -0.44638 | -0.22083 | -0.22096
| 7909 | 0.095622 | 0.39148 | -0.39115 | 0.53578 | -0.44349 | 0.65258 | -0.04517 | -0.57421 | 0.11756 | 0.5883
| 7910 | -0.16364 | 0.60289 | 0.14472 | 0.15626 | -0.3956 | -0.15 | 0.14122 | 0.22715 | 0.30855 | -0.42355
| 7911 | -0.15342 | 0.47398 | 0.54163 | -0.1884 | 0.30899 | 0.27522 | 0.092311 | 0.62145 | 0.69259 | 0.29197
| 7912 | 0.28916 | 0.1315 | 0.41221 | -0.4337 | 0.32273 | -0.53128 | 0.43387 | -0.13577 | -0.15413 | -0.46009
| 7913 | 0.0093941 | -0.035894 | 0.035065 | 0.41819 | 0.56768 | 0.029897 | 0.79384 | -0.148 | 0.22122 | 0.4046
| 7914 | -0.28257 | -0.53643 | -0.55853 | -0.10944 | 0.6985 | -0.14929 | -0.85543 | -0.20282 | -0.15994 | -0.058459
| 7915 | -0.0018517 | 0.0037571 | -0.50311 | 0.064853 | 0.58636 | -0.35805 | 0.48551 | 0.35852 | 0.15271 | 0.49711
| 7916 | -0.086381 | 0.34296 | 0.73 | 0.52261 | -0.75 | -0.31611 | 0.29694 | -0.69129 | -0.11983 | 0.52788
| 7917 | -0.20483 | 0.29509 | 0.34174 | 0.21674 | 0.24987 | 0.89 | -0.81972 | -0.19025 | 0.06753 | 0.10798
| 7918 | 0.7042 | -0.47303 | 0.22225 | 0.031857 | 0.54602 | -0.1034 | -0.51184 | -0.50251 | -0.32465 | -0.5283
| 7919 | -0.3629 | 0.14157 | 0.56838 | 0.12816 | -0.55 | 0.21866 | 0.2659 | -0.52894 | 0.051475 | -0.50291
| 7920 | -0.48941 | -0.76315 | -0.031651 | 0.09011 | -0.86252 | 0.29979 | -0.047582 | 0.17133 | -0.50412 | 0.071938
| 7921 | 0.70966 | 0.60088 | 0.06229 | -0.6578 | 0.65201 | -0.22728 | -0.51657 | -0.10184 | 0.2484 | -0.46906
| 7922 | 0.43511 | -0.0082843 | 0.71911 | -0.4995 | 0.018216 | 0.49118 | 0.90673 | -0.18336 | -0.11541 | 0.028558
| 7923 | 0.31436 | 0.77841 | -0.32317 | -0.26863 | 0.79048 | 0.027118 | -0.21802 | 0.46568 | 0.64574 | 0.11575
| 7924 | -0.22032 | -0.080489 | 0.39543 | 0.59614 | -0.08485 | 0.7492 | -0.54163 | -0.31087 | 0.50817 | -0.46176
| 7925 | -0.25858 | 0.016486 | 0.69129 | -0.25468 | -0.067316 | 0.35836 | -0.41357 | -0.35479 | 0.27192 | 0.45935
| 7926 | -0.53535 | -0.61283 | -0.18803 | -0.18361 | -0.70555 | -0.8956 | 0.44475 | 0.11484 | 0.012326 | -0.03714
| 7927 | -0.29424 | -0.31509 | 0.26509 | 0.18043 | -0.52094 | -0.43387 | 0.74174 | -0.46624 | -0.28021 | -0.053269
| 7928 | -0.24561 | 0.04099 | 0.21623 | -0.52979 | 0.4736 | -0.35417 | -0.82593 | 0.17471 | 0.29042 | 0.33539
| 7929 | 0.15389 | -0.11847 | -0.009899 | 0.17544 | 0.31145 | -0.094075 | -0.10596 | 0.13727 | -0.52094 | 0.70691
| 7930 | -0.36117 | 0.10843 | -0.19025 | -0.56861 | 0.46849 | -0.86252 | -0.2042 | -0.62039 | 0.25482 | -0.2488
| 7931 | -0.037659 | -0.4683 | -0.48609 | -0.60339 | -0.24495 | -0.48512 | 0.10462 | 0.21584 | -0.20483 | 0.010101
| 7932 | 0.74485 | -0.69817 | -0.46605 | 0.44547 | -0.18116 | -0.28986 | 0.56884 | 0.094848 | -0.1277 | -0.10395
| 7933 | 0.39593 | 0.080707 | 0.57917 | -0.45622 | 0.52387 | -0.81642 | 0.045275 | -0.16988 | -0.22844 | 0.26945
| 7934 | 0.79579 | 0.09529 | 0.3568 | -0.065174 | -0.075825 | -0.13716 | 0.12897 | 0.57538 | 0.09187 | 0.36164
| 7935 | -0.78436 | -0.46812 | -0.65373 | 0.46456 | 0.27343 | -0.11938 | -0.12713 | -0.073016 | -0.47798 | 0.29381
| 7936 | 0.71592 | -0.46624 | -0.62624 | -0.27165 | 0.094296 | -0.39825 | -0.16976 | -0.20106 | 0.52576 | 0.0077803
| 7937 | 0.36102 | 0.37911 | 0.13449 | 0.097836 | -0.73675 | 0.85964 | 0.45365 | -0.75444 | 0.63848 | -0.082558
| 7938 | -0.33735 | -0.049895 | 0.027837 | 0.50553 | 0.22624 | 0.37558 | -0.40343 | -0.5458 | -0.24987 | -0.085724
| 7939 | 0.24774 | -0.2042 | -0.079946 | 0.064105 | -0.085506 | -0.32317 | 0.34494 | -0.094075 | 0.10228 | 0.60949
| 7940 | 0.18153 | 0.56861 | 0.16292 | 0.1005 | 0.54492 | -0.62251 | 0.068818 | -0.22974 | 0.15071 | 0.29736
| 7941 | 0.0068736 | -0.19 | -0.46699 | -0.21406 | -0.58733 | -0.6985 | 0.013339 | 0.28327 | 0.22199 | -0.022401
| 7942 | -0.27096 | -0.10675 | 0.66879 | 0.35914 | 0.86036 | 0.14087 | 0.080489 | -0.24046 | -0.23195 | -0.47417
| 7943 | 0.12667 | -0.065388 | -0.38202 | -0.66638 | -0.78436 | -0.39 | -0.84933 | -0.60949 | 0.022299 | -0.50271
| 7944 | 0.24046 | 0.7623 | 0.48415 | -0.47875 | 0.34739 | 0.11835 | 0.024039 | 0.92063 | 0.73524 | 0.43229
| 7945 | 0.44619 | 0.32613 | -0.01791 | 0.74841 | 0.0059678 | 0.16555 | 0.51205 | 0.24072 | 0.084631 | -0.17495
| 7946 | 0.061757 | 0.12119 | 0.73904 | -0.23026 | 0.61699 | -0.59073 | 0.031754 | -0.20987 | -0.081686 | -0.14976
| 7947 | -0.19919 | 0.19272 | -0.1769 | -0.43405 | 0.69259 | -0.32273 | 0.61699 | -0.31816 | -0.25388 | -0.042347
| 7948 | 0.28803 | 0.3817 | -0.14918 | -0.079511 | 0.11417 | -0.2081 | 0.61751 | -0.31949 | 0.14017 | 0.59491
| 7949 | -0.46176 | 0.12507 | -0.10888 | -0.40746 | -0.59318 | -0.60617 | -0.079837 | -0.3189 | -0.68016 | -0.33977
| 7950 | 0.30812 | -0.68298 | -0.64659 | -0.63408 | -0.38429 | 0.48512 | 0.8747 | -0.40225 | -0.26007 | -0.18901
| 7951 | -0.22831 | -0.6118 | 0.55067 | 0.67953 | -0.49612 | 0.62838 | 0.76741 | -0.34923 | -0.54536 | 0.5001
| 7952 | -0.43866 | -0.33585 | 0.45365 | 0.10496 | 0.51123 | 0.36794 | 0.24734 | 0.57047 | 0.39759 | -0.61803
| 7953 | -0.19632 | -0.098058 | -0.071507 | 0.0054649 | 0.73411 | -0.19483 | 0.79678 | -0.046113 | -0.057716 | -0.13658
| 7954 | 0.047477 | 0.68393 | -0.59368 | 0.53043 | -0.097725 | 0.0054649 | 0.38153 | 0.52282 | 0.041199 | 0.48299
| 7955 | 0.37223 | 0.2047 | -0.84801 | -0.049369 | -0.19185 | -0.39181 | -0.2722 | -0.1926 | 0.17447 | 0.15354
| 7956 | 0.33947 | 0.20019 | 0.055384 | 0.21853 | -0.24907 | 0.42164 | -0.10117 | 0.60668 | 0.033408 | -0.13392
| 7957 | -0.2484 | -0.60213 | -0.43334 | 0.44367 | 0.33509 | -0.19346 | 0.8937 | 0.24204 | -0.32096 | -0.66074
| 7958 | 0.22109 | 0.067959 | 0.01842 | 0.043182 | 0.67519 | -0.90566 | 0.017809 | -0.067959 | 0.81053 | -0.14437
| 7959 | 0.18852 | 0.2496 | 0.59 | -0.032994 | 0.36699 | -0.15875 | 0.40376 | 0.32155 | 0.16531 | -0.055172
| 7960 | 0.80584 | 0.43176 | -0.88731 | 0.11994 | -0.27757 | 0.77131 | 0.42807 | -0.61777 | 0.19111 | -0.49059
| 7961 | 0.39477 | -0.29608 | -0.5469 | -0.13288 | 0.31553 | -0.70184 | 0.47284 | -0.083867 | 0.37718 | 0.37654
| 7962 | -0.16711 | 0.26672 | -0.023732 | -0.21101 | 0.1879 | -0.68488 | -0.66638 | 0.64489 | 0.66549 | 0.12725
| 7963 | 0.56838 | 0.26183 | -0.75241 | -0.11699 | 0.51143 | 0.48882 | 0.16711 | 0.10106 | 0.1277 | -0.048948
| 7964 | 0.22844 | 0.30293 | -0.24336 | 0.17483 | -0.40443 | -0.4987 | -0.73486 | 0.057609 | -0.1237 | 0.095401
| 7965 | -0.30986 | -0.022912 | -0.09011 | -0.35463 | -0.18618 | -0.082122 | 0.099944 | -0.25643 | -0.02322 | -0.18459
| 7966 | -0.19309 | -0.53256 | -0.66758 | 0.5011 | 0.51823 | -0.041929 | 0.66939 | 0.48318 | 0.22831 | -0.0055655
| 7967 | 0.014759 | -0.094296 | 0.80791 | -0.01263 | 0.34129 | 0.20432 | 0.0018517 | -0.40058 | 0.035583 | -0.20181
| 7968 | 0.22586 | -0.12519 | -0.56583 | -0.22186 | -0.031031 | -0.078208 | -0.49413 | -0.30207 | -0.44098 | 0.2287
| 7969 | -0.30682 | -0.62919 | 0.71069 | -0.2326 | 0.55111 | 0.036828 | 0.72523 | -0.6939 | 0.25401 | -0.40544
| 7970 | -0.052424 | 0.33962 | -0.032477 | 0.10574 | 0.82028 | 0.44529 | 0.052002 | 0.079294 | 0.28873 | -0.41511
| 7971 | -0.042033 | -0.7496 | -0.24416 | 0.90356 | -0.067423 | -0.55424 | 0.11688 | 0.040469 | -0.21827 | 0.50776
| 7972 | 0.30884 | 0.4776 | 0.0089904 | 0.099833 | -0.13983 | 0.09099 | -0.17157 | -0.38137 | 0.28132 | 0.548
| 7973 | -0.010606 | 0.23052 | 0.30769 | 0.47341 | 0.048633 | -0.57 | 0.28635 | -0.49236 | 0.24099 | -0.64914
| 7974 | 0.84157 | 0.06603 | 0.64153 | -0.72889 | -0.48164 | 0.14812 | -0.58976 | -0.14554 | -0.72486 | 0.088134
| 7975 | 0.060372 | 0.21699 | -0.36431 | -0.79925 | -0.2571 | 0.22637 | 0.19458 | 0.077558 | 0.1308 | -0.014657
| 7976 | -0.18373 | 0.40042 | -0.18006 | 0.023936 | 0.32791 | -0.14812 | -0.17738 | -0.20937 | 0.025372 | -0.056231
| 7977 | 0.46906 | 0.082885 | 0.31247 | 0.30193 | -0.6241 | 0.37 | -0.073879 | 0.23052 | -0.13403 | -0.73981
| 7978 | -0.3477 | -0.68425 | -0.14355 | 0.19012 | -0.15602 | 0.37446 | 0.28369 | 0.82365 | -0.11654 | -0.51287
| 7979 | -0.59515 | -0.083649 | 0.54404 | 0.73037 | 0.29381 | 0.30007 | -0.11304 | 0.27412 | -0.44242 | 0.14953
| 7980 | -0.62066 | -0.37927 | -0.45732 | 0.27398 | -0.078534 | -0.61206 | 0.21559 | -0.63462 | -0.0086877 | -0.079728
| 7981 | -0.48087 | -0.8882 | 0.64209 | -0.12028 | 0.28873 | 0.052108 | -0.55379 | -0.24575 | -0.69097 | 0.49137
| 7982 | 0.2278 | -0.22302 | 0.74446 | 0.17024 | -0.68583 | 0.18508 | -0.53837 | 0.19446 | -0.60592 | -0.62784
| 7983 | 0.54011 | 0.28076 | -0.43866 | 0.11079 | -0.0093941 | -0.6077 | 0.26305 | 0.42615 | -0.62892 | -0.14122
| 7984 | 0.38918 | -0.16856 | -0.14624 | -0.38869 | -0.038595 | -0.023834 | -0.40611 | -0.11915 | -0.15828 | 0.45658
| 7985 | 0.69032 | 0.2575 | -0.18667 | 0.53707 | 0.41511 | -0.31699 | 0.21254 | -0.31422 | -0.1852 | 0.46102
| 7986 | 0.23013 | -0.014556 | -0.066458 | 0.40865 | 0.52094 | -0.21776 | 0.055701 | -0.33871 | -0.080816 | -0.13138
| 7987 | -0.16232 | -0.65985 | 0.063037 | 0.11281 | -0.077124 | -0.77175 | -0.31174 | -0.89851 | -0.14882 | 0.52724
| 7988 | 0.14437 | -0.35169 | 0.72054 | -0.28063 | -0.80739 | -0.30696 | -0.39461 | 0.7623 | -0.18926 | -0.81372
| 7989 | -0.6319 | 0.25858 | 0.3882 | 0.56838 | -0.62463 | 0.29694 | -0.56977 | -0.70725 | 0.27771 | 0.019847
| 7990 | -0.046847 | -0.3568 | 0.4426 | -0.019133 | 0.30365 | 0.41102 | -0.13311 | 0.20244 | -0.3882 | -0.32125
| 7991 | -0.0020521 | -0.43511 | 0.49334 | 0.32332 | 0.63408 | 0.33374 | 0.41511 | -0.14706 | 0.33524 | 0.2234
| 7992 | -0.18177 | -0.20937 | 0.25107 | 0.21955 | 0.15768 | 0.20709 | -0.15141 | -0.24323 | 0.29296 | -0.40225
| 7993 | 0.66668 | 0.48222 | 0.016486 | 0.1269 | 0.12793 | 0.61026 | -0.26918 | -0.11146 | 0.61309 | 0.88909
| 7994 | 0.43423 | -0.24323 | 0.24907 | -0.6995 | 0.40175 | -0.82028 | 0.33314 | 0.20684 | -0.19185 | -0.63848
| 7995 | -0.26631 | -0.55537 | 0.7623 | 0.38234 | -0.029691 | -0.3025 | 0.41102 | -0.17982 | -0.13681 | -0.29793
| 7996 | 0.0073772 | 0.012022 | -0.75 | -0.96127 | -0.021787 | 0.14918 | 0.1868 | 0.43991 | -0.29339 | 0.38413
| 7997 | -0.50837 | -0.059415 | -0.66489 | -0.029691 | -0.012123 | 0.73186 | -0.066351 | 0.015165 | 0.065388 | -0.033201
| 7998 | 0.11405 | -0.14765 | -0.1204 | -0.46344 | -0.15177 | -0.36086 | 0.15578 | -0.069463 | -0.83 | 0.47341
| 7999 | -0.12702 | -0.20886 | -0.19856 | 0.041512 | -0.013035 | 0.80791 | -0.39494 | -0.48164 | -0.22896 | -0.28425
| 8000 | -0.058671 | 0.22083 | -0.1706 | 0.0059678 | 0.38073 | -0.52724 | 0.59938 | -0.28649 | -0.30122 | 0.83177
| 8001 | -0.4993 | -0.61412 | 0.44349 | -0.46868 | -0.050737 | 0.27398 | -0.23967 | 0.1308 | 0.72559 | -0.4206
| 8002 | 0.54978 | 0.12576 | -0.81807 | 0.027735 | -0.00095045 | 0.058884 | 0.32169 | 0.24336 | -0.53064 | -0.18189
| 8003 | -0.21089 | 0.37032 | -0.2823 | -0.012528 | 0.037867 | -0.070753 | -0.53967 | -0.36055 | -0.37 | -0.51061
| 8004 | -0.56445 | 0.57116 | 0.36055 | 0.075716 | 0.21559 | -0.59689 | 0.86847 | 0.69784 | -0.1082 | 0.58251
| 8005 | -0.6407 | 0.47798 | 0.67674 | -0.024244 | 0.23312 | 0.024244 | 0.33419 | 0.3851 | -0.64631 | -0.81265
| 8006 | 0.52345 | 0.51061 | 0.4542 | 0.43813 | -0.23417 | 0.47779 | -0.59073 | 0.60163 | 0.019643 | 0.64546
| 8007 | 0.30711 | -0.43476 | 0.38689 | -0.059202 | 0.38918 | 0.60213 | 0.60567 | 0.017198 | 0.15401 | 0.5693
| 8008 | 0.28285 | 0.2326 | -0.30624 | 0.20836 | 0.73675 | 0.34831 | 0.060905 | -0.164 | 0.051897 | 0.20558
| 8009 | 0.31934 | 0.13658 | -0.35339 | 0.24495 | 0.33735 | 0.24072 | 0.22109 | -0.22289 | 0.7687 | -0.10809
| 8010 | -0.27302 | 0.066887 | -0.15496 | 0.48183 | -0.82651 | -0.6546 | -0.040365 | 0.15899 | 0.26863 | 0.039323
| 8011 | -0.15295 | -0.61026 | 0.29537 | 0.24323 | -0.30437 | 0.1735 | -0.14309 | 0.22173 | 0.056125 | 0.32346
| 8012 | 0.62624 | -0.24112 | -0.03434 | 0.79288 | 0.18815 | -0.24416 | 0.86923 | 0.40662 | -0.068496 | -0.065495
| 8013 | -0.078208 | -0.021379 | -0.18594 | -0.75566 | 0.3306 | -0.21635 | -0.45219 | 0.92319 | 0.43582 | -0.31102
| 8014 | -0.13392 | 0.69 | 0.042869 | 0.48125 | 0.39527 | 0.5529 | -0.032271 | -0.51554 | 0.71 | -0.073124
| 8015 | -0.21317 | -0.38105 | -0.43264 | -0.60465 | 0.92063 | -0.012326 | 0.11405 | 0.43141 | 0.152 | 0.23888
| 8016 | -0.16591 | 0.13184 | 0.86399 | -0.27882 | 0.71982 | -0.20886 | -0.071076 | 0.90461 | -0.3186 | 0.3211
| 8017 | 0.043705 | 0.67798 | -0.58708 | -0.084413 | -0.38105 | 0.37143 | -0.014962 | 0.77751 | 0.44927 | 0.264
| 8018 | 0.083758 | 0.38105 | 0.28146 | 0.05158 | 0.059947 | -0.03579 | 0.19732 | 0.015571 | 0.30899 | -0.44511
| 8019 | 0.71382 | 0.3727 | 0.48454 | -0.16472 | -0.33705 | 0.66015 | 0.31597 | -0.19508 | -0.2042 | -0.76021
| 8020 | 0.27371 | -0.11779 | 0.17205 | 0.16066 | -0.23547 | -0.66519 | 0.21063 | 0.70285 | 0.24628 | 0.20131
| 8021 | 0.62973 | -0.13669 | -0.51451 | 0.14554 | 0.12176 | -0.056337 | 0.4471 | 0.085287 | 0.6546 | 0.24654
| 8022 | -0.018114 | 0.44982 | -0.2184 | -0.49592 | 0.46418 | -0.20244 | -0.021787 | 0.1091 | 0.76698 | 0.22006
| 8023 | 0.11915 | -0.82084 | -0.11259 | 0.76698 | -0.14683 | 0.019847 | 0.20244 | -0.24907 | -0.013238 | 0.67612
| 8024 | -0.40443 | -0.45127 | 0.098058 | 0.47057 | -0.29765 | 0.41255 | -0.28635 | -0.79579 | -0.19136 | -0.18643
| 8025 | 0.87712 | -0.031857 | -0.49157 | 0.3662 | 0.16221 | -0.19931 | -0.011921 | -0.1473 | -0.6811 | 0.52261
| 8026 | 0.52661 | -0.84736 | 0.050842 | -0.12473 | -0.67182 | -0.17836 | 0.44188 | -0.27357 | 0.024346 | -0.066137
| 8027 | -0.25067 | -0.17169 | 0.1323 | 0.49394 | -0.92319 | 0.23678 | -0.49631 | -0.42389 | -0.23443 | -0.17435
| 8028 | 0.5172 | 0.1752 | 0.053163 | -0.1162 | 0.23169 | -0.67061 | -0.16316 | -0.55672 | 0.66879 | -0.28607
| 8029 | -0.41357 | -0.12679 | -0.099722 | 0.15958 | -0.23796 | 0.59441 | 0.32317 | -0.19334 | -0.83297 | -0.044647
| 8030 | -0.29495 | 0.35479 | -0.31043 | -0.25013 | 0.45219 | 0.42947 | -0.09176 | -0.64829 | -0.48785 | -0.93144
| 8031 | 0.46755 | -0.27192 | -0.4046 | -0.46587 | -0.13634 | 0.33826 | 0.031548 | 0.12382 | 0.47057 | 0.26128
| 8032 | 0.074095 | -0.37863 | 0.13369 | 0.20861 | -0.13704 | -0.68743 | 0.3593 | -0.55785 | -0.02568 | -0.018216
| 8033 | 0.36086 | 0.18055 | -0.44583 | -0.40848 | -0.82766 | -0.61231 | -0.32406 | 0.2398 | 0.70862 | -0.35154
| 8034 | 0.065495 | 0.38836 | -0.36952 | -0.14414 | 0.48125 | -0.11926 | -0.33389 | 0.17459 | -0.72233 | -0.63986
| 8035 | 0.85 | 0.65722 | 0.31963 | -0.65201 | 0.029382 | -0.62677 | 0.45787 | 0.048212 | -0.42337 | -0.34739
| 8036 | -0.14414 | -0.0094951 | -0.69227 | -0.25093 | 0.80075 | -0.04099 | -0.13565 | -0.60063 | -0.12736 | 0.0064709
| 8037 | 0.16651 | 0.1221 | 0.12713 | -0.30193 | 0.09033 | 0.51348 | 0.14204 | 0.09044 | 0.82084 | -0.42026
| 8038 | 0.20344 | 0.69324 | -0.97764 | 0.37558 | -0.073879 | 0.40443 | -0.28775 | -0.25737 | 0.14262 | 0.21203
| 8039 | -0.34174 | -0.074527 | -0.14695 | 0.56537 | -0.1565 | 0.8366 | -0.37239 | 0.50513 | -0.72305 | -0.45182
| 8040 | 0.70862 | 0.11779 | -0.26754 | 0.17338 | -0.4163 | -0.73713 | 0.69488 | -0.70017 | 0.077232 | 0.28537
| 8041 | -0.39181 | -0.14262 | -0.14099 | 0.53751 | -0.44385 | -0.19433 | 0.16436 | -0.094738 | -0.015571 | -0.28453
| 8042 | 0.49532 | -0.12747 | -0.027837 | -0.36778 | 0.10496 | -0.13346 | 0.18508 | 0.68393 | 0.45164 | -0.69983
| 8043 | -0.37863 | 0.10742 | -0.45 | -0.4471 | 0.013035 | -0.78068 | 0.19025 | 0.11677 | 0.095069 | 0.076366
| 8044 | -0.094738 | 0.14953 | -0.56239 | -0.13115 | -0.14812 | 0.015673 | 0.040886 | 0.56537 | -0.33645 | -0.19632
| 8045 | -0.37783 | 0.18361 | 0.21038 | -0.47971 | -0.59196 | 0.34023 | -0.48202 | -0.80895 | -0.78716 | 0.22741
| 8046 | -0.57917 | -0.25953 | -0.074311 | -0.68839 | 0.35247 | 0.85134 | -0.32317 | 0.43688 | 0.069248 | 0.020459
| 8047 | 0.09176 | -0.51082 | -0.19136 | -0.6338 | 0.26699 | 0.29893 | 0.16137 | -0.45347 | -0.64265 | -0.2287
| 8048 | 0.39131 | -0.25361 | 0.40696 | -0.87958 | 0.52345 | 0.27027 | -0.032684 | 0.38543 | 0.27398 | -0.015063
| 8049 | 0.44855 | 0.40746 | -0.4531 | 0.22883 | 0.54163 | -0.13184 | -0.24853 | -0.049158 | -0.036102 | -0.3454
| 8050 | 0.1221 | 0.69162 | 0.61464 | 0.1797 | -0.066673 | -0.65402 | -0.05422 | 0.17435 | 0.36937 | 0.5141
| 8051 | -0.13611 | 0.79579 | -0.46362 | 0.12302 | -0.13369 | 0.26577 | -0.74761 | -0.72523 | -0.18422 | -0.053903
| 8052 | -0.34938 | 0.05984 | 0.10328 | -0.45751 | 0.25441 | 0.00065021 | -0.63081 | 0.11903 | 0.19223 | -0.66698
| 8053 | 0.08978 | 0.035168 | -0.87233 | -0.22276 | -0.38967 | 0.44457 | 0.074743 | -0.2496 | -0.23208 | -0.26767
| 8054 | -0.35977 | -0.63931 | 0.2356 | 0.40259 | 0.65431 | 0.58203 | -0.39543 | 0.44746 | 0.25053 | -0.8148
| 8055 | -0.77751 | 0.1308 | 0.25294 | -0.059096 | -0.088463 | -0.42095 | 0.14859 | 0.28341 | 0.3366 | -0.35712
| 8056 | 0.17205 | 0.18177 | 0.27247 | 0.082449 | 0.44964 | -0.18717 | -0.50654 | -0.29495 | 0.34372 | 0.64153
| 8057 | -0.41289 | 0.025988 | -0.19682 | -0.30179 | -0.34831 | 0.3804 | 0.36117 | -0.10172 | -0.29509 | 0.046323
| 8058 | 0.046742 | -0.11101 | 0.43176 | 0.80532 | 0.37847 | 0.42355 | 0.3189 | 0.039635 | 0.079837 | 0.29339
| 8059 | -0.099056 | 0.65605 | -0.72125 | 0.076258 | -0.0069743 | 0.063144 | 0.4776 | -0.88909 | -0.26808 | -0.67121
| 8060 | 0.89753 | -0.60974 | 0.061544 | -0.33735 | 0.082885 | 0.055595 | -0.63135 | -0.040782 | 0.14052 | -0.15994
| 8061 | -0.58684 | -0.17435 | 0.59417 | 0.41272 | 0.29169 | 0.061331 | -0.10039 | -0.023527 | 0.0041586 | 0.2567
| 8062 | -0.35556 | 0.10418 | -0.23052 | -0.52555 | -0.54163 | 0.73713 | 0.12473 | -0.040156 | 0.65373 | -0.81318
| 8063 | -0.32628 | -0.93292 | 0.25093 | -0.58107 | 0.10776 | 0.60567 | 0.087147 | 0.29793 | 0.61829 | -0.49532
| 8064 | 0.022401 | -0.79727 | -0.052108 | -0.26522 | 0.16615 | 0.55134 | -0.10217 | 0.68361 | -0.069785 | -0.48551
| 8065 | 0.15271 | 0.17036 | -0.71946 | 0.39543 | 0.069892 | -0.34985 | -0.18263 | 0.28021 | 0.69455 | -0.10664
| 8066 | 0.236 | 0.6939 | 0.68456 | -0.14519 | -0.47455 | 0.28285 | 0.41 | 0.42947 | -0.16952 | 0.39576
| 8067 | -0.12085 | 0.2234 | -0.65927 | 0.40544 | -0.67519 | 0.2571 | -0.14918 | 0.10944 | -0.021685 | 0.29466
| 8068 | -0.46755 | -0.44511 | -0.020459 | -0.26237 | -0.056337 | 0.11157 | 0.50837 | 0.32569 | 0.3451 | -0.59515
| 8069 | 0.054749 | -0.18385 | 0.45146 | -0.21203 | 0.36905 | -0.014252 | -0.64715 | 0.30971 | 0.18753 | -0.42563
| 8070 | 0.019745 | 0.81642 | 0.50634 | -0.60013 | -0.26781 | -0.18951 | 0.21241 | -0.32199 | -0.52366 | 0.27288
| 8071 | 0.64181 | 0.46661 | 0.35092 | 0.88731 | -0.083212 | 0.46493 | -0.28747 | 0.3116 | -0.33494 | -0.53107
| 8072 | -0.74019 | -0.62092 | -0.14227 | -0.45475 | -0.16448 | -0.38836 | 0.032374 | -0.31218 | 0.28383 | -0.86472
| 8073 | 0.30523 | 0.17921 | -0.050421 | -0.064318 | 0.032374 | -0.057079 | -0.70521 | -0.11372 | -0.13357 | 0.11972
| 8074 | 0.41425 | 0.24072 | 0.71173 | 0.5721 | 0.44891 | -0.24827 | -0.10608 | 0.068711 | -0.11665 | -0.021992
| 8075 | 0.85269 | -0.47512 | 0.18373 | 0.22392 | 0.26836 | 0.29339 | -0.15721 | 0.92859 | -0.099167 | -0.24416
| 8076 | 0.50735 | -0.29268 | 0.33585 | -0.30308 | -0.32302 | 0.12119 | -0.069677 | -0.040052 | -0.66281 | -0.45824
| 8077 | 0.6637 | -0.060585 | 0.13692 | 0.19371 | -0.59515 | -0.49275 | 0.26973 | 0.70521 | -0.41665 | 0.11079
| 8078 | -0.32184 | -0.14636 | 0.18655 | -0.1597 | -0.66909 | -0.077016 | 0.16831 | -0.25953 | 0.23574 | 0.016893
| 8079 | 0.72269 | 0.52661 | 0.15448 | -0.046008 | -0.087038 | -0.52661 | -0.52936 | -0.27 | 0.43653 | 0.0094951
| 8080 | 0.12736 | -0.2496 | -0.27993 | -0.088353 | 0.35262 | 0.72161 | -0.10742 | -0.17036 | 0.53363 | 0.2809
| 8081 | 0.076149 | -0.036621 | -0.38283 | -0.31058 | 0.37702 | 0.31232 | -0.063677 | -0.32896 | -0.22495 | 0.098501
| 8082 | -0.37318 | 0.24007 | 0.52031 | -0.047687 | 0.61751 | 0.53729 | -0.60491 | 0.37718 | -0.061437 | 0.33015
| 8083 | -0.35479 | -0.12336 | -0.60491 | -0.22961 | 0.18926 | -0.15496 | -0.25482 | 0.36699 | -0.48804 | -0.45055
| 8084 | 0.79826 | 0.52429 | 0.071938 | 0.19223 | 0.045589 | -0.30942 | 0.63958 | 0.44493 | 0.23078 | 0.27882
| 8085 | -0.27014 | 0.27398 | -0.0023528 | 0.10742 | -0.19694 | -0.53967 | 0.64181 | 0.31509 | 0.092531 | 0.0090913
| 8086 | 0.086162 | -0.10418 | 0.06325 | 0.35139 | -0.13623 | -0.21457 | -0.1353 | -0.1425 | 0.085615 | 0.26604
| 8087 | -0.48512 | 0.60974 | 0.8454 | 0.41751 | -0.20533 | -0.4826 | -0.06957 | 0.18753 | -0.16579 | 0.2571
| 8088 | -0.17265 | -0.028455 | 0.1863 | 0.28635 | -0.21254 | 0.45055 | 0.55672 | 0.41528 | -0.8618 | 0.63599
| 8089 | -0.26836 | 0.81053 | -0.37398 | 0.11869 | 0.21891 | 0.23482 | -0.41974 | -0.02794 | -0.43848 | -0.73866
| 8090 | 0.12725 | -0.099167 | -0.1034 | 0.24548 | -0.40175 | -0.08967 | 0.75363 | 0.071938 | 0.49157 | 0.18544
| 8091 | 0.85134 | -0.70318 | -0.20307 | 0.1109 | 0.21789 | -0.19719 | 0.065816 | 0.15035 | -0.30293 | -0.30971
| 8092 | -0.064212 | 0.01486 | 0.06293 | 0.083103 | -0.04172 | 0.60949 | 0.43317 | -0.12679 | 0.12063 | -0.079837
| 8093 | -0.6985 | -0.034754 | -0.19359 | 0.33404 | 0.85613 | -0.00025003 | 0.76655 | -0.53664 | 0.336 | 0.31043
| 8094 | -0.01091 | 0.55067 | -0.58227 | 0.0033556 | -0.80025 | 0.062717 | 0.10753 | -0.13311 | 0.54098 | -0.47227
| 8095 | -0.30696 | -0.36526 | 0.19272 | 0.059096 | 0.13866 | 0.42129 | -0.4279 | -0.089341 | -0.45091 | 0.31014
| 8096 | -0.45182 | 0.12747 | 0.58179 | 0.5017 | -0.19433 | 0.38121 | 0.36023 | -0.1803 | -0.088353 | 0.5172
| 8097 | -0.38559 | 0.64349 | 0.62758 | 0.13669 | 0.24667 | -0.7492 | -0.23443 | 0.23639 | -0.096617 | 0.3294
| 8098 | -0.39461 | 0.1559 | -0.014049 | -0.049895 | -0.61335 | -0.78297 | -0.19297 | 0.69422 | 0.69685 | 0.035998
| 8099 | 0.20722 | -0.38722 | 0.54602 | 0.18901 | -0.33524 | -0.29665 | -0.81697 | -0.50959 | 0.27578 | 0.21917
| 8100 | -0.66251 | 0.37 | -0.94084 | 0.37494 | -0.4265 | 0.053903 | 0.29793 | -0.11169 | 0.28649 | -0.37382
| 8101 | -0.63054 | 0.31087 | 0.18287 | -0.10776 | -0.032477 | 0.39809 | -0.2823 | 0.32628 | 0.09121 | -0.59049
| 8102 | -0.49256 | 0.67984 | -0.011011 | -0.032684 | 0.23299 | 0.36494 | 0.72341 | 0.25656 | -0.58467 | -0.054643
| 8103 | -0.24548 | 0.10351 | 0.2571 | -0.54558 | -0.12074 | 0.1229 | -0.68711 | 0.19173 | 0.56308 | -0.61077
| 8104 | 0.019847 | -0.11699 | 0.25535 | -0.6371 | -0.05253 | -0.8422 | -0.028558 | -0.10261 | -0.37462 | -0.44385
| 8105 | 0.65 | 0.61829 | -0.17121 | -0.67304 | 0.26128 | -0.26305 | -0.55604 | -0.13104 | -0.3189 | 0.33254
| 8106 | -0.2047 | 0.54646 | 0.37286 | 0.4826 | -0.30495 | -0.34296 | -0.40797 | 0.39659 | -0.35977 | 0.50898
| 8107 | 0.030722 | -0.56722 | -0.7881 | 0.32776 | -0.53924 | 0.051369 | -0.046323 | 0.31728 | -0.93755 | 0.37622
| 8108 | 0.70386 | -0.58708 | -0.68679 | 0.73561 | -0.32391 | 0.89851 | -0.16928 | 0.30797 | -0.80025 | -0.072908
| 8109 | 0.32791 | 0.9219 | 0.36604 | -0.33434 | -0.10978 | 0.61829 | 0.14297 | 0.37815 | -0.52073 | -0.045484
| 8110 | -0.59491 | 0.23143 | -0.22289 | 0.39825 | -0.67152 | 0.22534 | -0.45109 | 0.26305 | 0.26918 | 0.70487
| 8111 | 0.17459 | 0.014353 | 0.23521 | 0.71277 | 0.14484 | 0.5714 | -0.31363 | -0.48902 | -0.023629 | -0.39345
| 8112 | 0.62865 | 0.79288 | -0.44457 | 0.13242 | -0.15875 | 0.53556 | -0.63353 | -0.36905 | -0.0043595 | 0.15543
| 8113 | -0.21597 | 0.19471 | -0.2941 | -0.19223 | -0.31363 | 0.67488 | 0.2356 | -0.82479 | 0.40025 | 0.48473
| 8114 | -0.81862 | -0.083539 | 0.01263 | 0.68078 | -0.09077 | -0.0067729 | 0.38951 | 0.45658 | -0.048317 | 0.73524
| 8115 | -0.46605 | -0.37398 | -0.10039 | 0.031961 | -0.24774 | -0.086053 | 0.32302 | 0.10239 | -0.52261 | 0.16101
| 8116 | 0.18717 | -0.48609 | -0.024346 | -0.009798 | -0.33179 | -0.71804 | 0.59 | -0.19856 | -0.48648 | -0.15365
| 8117 | -0.19371 | -0.52915 | 0.58395 | 0.2722 | 0.025885 | -0.30093 | 0.32806 | -0.85134 | -0.023322 | 0.28733
| 8118 | -0.57374 | 0.2602 | -0.64518 | -0.23469 | -0.36055 | 0.5922 | -0.13173 | -0.052213 | 0.7015 | 0.4408
| 8119 | -0.75648 | -0.55559 | -0.95641 | -0.40025 | 0.10529 | 0.54076 | 0.73524 | 0.67953 | 0.34969 | -0.086053
| 8120 | -0.12006 | -0.49771 | -0.11869 | 0.67984 | -0.69751 | -0.26156 | 0.16077 | -0.65402 | -0.38575 | 0.69917
| 8121 | 0.28509 | -0.081577 | -0.15259 | 0.20232 | -0.60465 | -0.32199 | -0.39263 | -0.034754 | 0.72523 | 0.27813
| 8122 | 0.083976 | 0.32287 | -0.30308 | 0.10596 | 0.55875 | -0.04538 | 0.63986 | 0.31787 | 0.53729 | -0.20119
| 8123 | -0.52534 | -0.085724 | 0.44891 | -0.46288 | -0.77395 | 0.070108 | -0.038387 | 0.63326 | 0.061544 | 0.33344
| 8124 | 0.39033 | 0.31875 | 0.31568 | -0.45658 | -0.28649 | -0.19956 | 0.2398 | 0.19931 | -0.44152 | 0.41699
| 8125 | 0.44583 | 0.32435 | 0.37016 | 0.16892 | 0.52513 | -0.053691 | -0.15365 | -0.64293 | 0.1015 | -0.55989
| 8126 | 0.31993 | -0.65897 | -0.078968 | 0.077341 | 0.43193 | 0.36353 | -0.29993 | -0.09695 | 0.30236 | 0.60923
| 8127 | 0.25495 | -0.17787 | 0.030103 | 0.10039 | -0.070968 | -0.13901 | 0.16771 | 0.80075 | 0.79288 | 0.17121
| 8128 | -0.08474 | 0.76399 | -0.41579 | -0.70487 | 0.12393 | -0.01091 | 0.25374 | 0.3167 | -0.56954 | -0.15024
| 8129 | 0.23928 | -0.12782 | -0.78858 | 0.64744 | -0.41017 | 0.48396 | 0.73561 | -0.26522 | -0.61464 | 0.23928
| 8130 | -0.26468 | -0.67091 | 0.48804 | -0.79048 | -0.22456 | -0.6578 | 0.96394 | -0.027118 | 0.48882 | -0.46868
| 8131 | -0.90356 | -0.30036 | 0.038491 | -0.29127 | 0.49552 | -0.087257 | 0.032581 | -0.1196 | -0.56884 | 0.12759
| 8132 | 0.30293 | -0.070753 | -0.464 | -0.13369 | -0.054114 | 0.039531 | 0.4717 | 0.77572 | 0.1841 | 0.00025003
| 8133 | -0.094185 | -0.37622 | -0.14554 | 0.59392 | 0.16484 | 0.049789 | 0.8821 | 0.069785 | 0.09088 | -0.085506
| 8134 | 0.65143 | -0.45548 | 0.84801 | 0.49453 | -0.21572 | 0.3167 | -0.15472 | 0.0089904 | -0.64829 | 0.81862
| 8135 | -0.22276 | -0.4206 | -0.12702 | 0.078859 | 0.12199 | -0.13449 | -0.16711 | -0.062717 | 0.60668 | 0.46176
| 8136 | -0.27536 | -0.45109 | 0.028558 | 0.28551 | 0.48067 | -0.01182 | 0.74407 | -0.077341 | -0.63027 | 0.11259
| 8137 | -0.14742 | 0.027632 | -0.35355 | 0.54404 | -0.015978 | 0.036724 | -0.30279 | -0.39115 | 0.42755 | 0.18287
| 8138 | 0.099278 | 0.47952 | -0.60013 | 0.78952 | -0.37847 | -0.4337 | -0.46962 | -0.41238 | -0.21866 | 0.13092
| 8139 | 0.41153 | 0.24614 | -0.029176 | 0.36086 | 0.14344 | 0.16519 | -0.26959 | 0.87958 | 0.44565 | 0.038179
| 8140 | 0.47322 | -0.54668 | 0.6149 | 0.06165 | 0.069033 | -0.452 | 0.54956 | -0.44529 | -0.4985 | 0.37239
| 8141 | 0.15804 | 0.25027 | -0.34296 | -0.14554 | -0.35355 | 0.67581 | 0.7508 | 0.31131 | 0.41357 | 0.51969
| 8142 | -0.46624 | 0.38918 | 0.87077 | -0.18544 | 0.52219 | 0.067959 | 0.26536 | 0.67704 | -0.20069 | 0.61961
| 8143 | 0.29979 | -0.76741 | -0.15519 | 0.1237 | -0.41374 | -0.012832 | -0.34281 | -0.17459 | -0.37318 | -0.10552
| 8144 | -0.73713 | 0.072261 | 0.22495 | -0.05348 | -0.31949 | 0.1603 | -0.69751 | -0.48415 | -0.45401 | -0.57917
| 8145 | 0.038803 | 0.32465 | -0.41068 | -0.15555 | 0.39659 | -0.084194 | -0.23534 | 0.46737 | 0.41391 | -0.15354
| 8146 | -0.40393 | -0.46083 | -0.060585 | 0.24853 | 0.64715 | -0.10496 | 0.084304 | -0.1825 | -0.13 | 0.23013
| 8147 | -0.066137 | -0.56653 | -0.013744 | 0.053691 | -0.28299 | 0.17994 | -0.20975 | 0.56331 | 0.27633 | 0.078317
| 8148 | 0.3454 | -0.20169 | 0.053269 | 0.76272 | 0.011921 | 0.060905 | -0.49453 | 0.052741 | -0.53686 | -0.35
| 8149 | 0.026193 | -0.53924 | 0.079402 | 0.9005 | -0.42528 | 0.34494 | 0.25361 | -0.55267 | 0.038075 | 0.1005
| 8150 | 0.4683 | -0.18275 | -0.13069 | 0.61464 | -0.22173 | 0.24059 | -0.16352 | -0.10006 | -0.70555 | -0.29537
| 8151 | -0.46849 | -0.63326 | -0.28021 | -0.1646 | 0.58708 | 0.60617 | 0.21674 | 0.18692 | -0.52767 | -0.073879
| 8152 | -0.10989 | 0.1025 | -0.56102 | -0.31919 | -0.061757 | 0.49137 | -0.12233 | -0.041512 | 0.082994 | -0.25441
| 8153 | 0.59788 | 0.47569 | 0.16711 | -0.22624 | -0.020663 | 0.42181 | -0.2504 | 0.29694 | -0.85543 | -0.46643
| 8154 | -0.26454 | 0.099611 | 0.31043 | 0.078425 | -0.15271 | 0.26047 | 0.4046 | -0.17532 | -0.3735 | 0.12931
| 8155 | -0.40831 | 0.076366 | 0.71698 | -0.47512 | -0.16976 | -0.32896 | -0.030516 | -0.14894 | 0.21279 | -0.38008
| 8156 | 0.17483 | -0.080816 | 0.23338 | 0.53989 | 0.47875 | 0.34342 | 0.70862 | -0.37895 | -0.15555 | -0.81053
| 8157 | 0.36589 | -0.43653 | 0.019847 | -0.73261 | 0.3189 | 0.31363 | -0.088243 | -0.0995 | -0.30093 | -0.39825
| 8158 | -0.23626 | -0.36541 | 0.11745 | -0.050842 | -0.32747 | -0.19062 | -0.17169 | -0.062183 | -0.25133 | -0.094296
| 8159 | 0.46009 | -0.5959 | -0.01842 | -0.26088 | 0.57822 | 0.17811 | 0.72815 | -0.18704 | -0.095401 | -0.079077
| 8160 | 0.23993 | -0.23195 | 0.86252 | 0.53621 | -0.47227 | -0.69065 | -0.14847 | -0.46849 | 0.6319 | -0.81426
| 8161 | 0.064746 | -0.36699 | -0.3167 | 0.010202 | 0.10239 | -0.12439 | 0.1025 | 0.5656 | 0.046008 | -0.46793
| 8162 | 0.10373 | 0.63 | 0.65868 | 0.56171 | -0.10585 | -0.55966 | 0.91815 | 0.23495 | 0.62543 | 0.82308
| 8163 | -0.034754 | 0.40831 | -0.26713 | -0.48029 | 0.3129 | 0.3303 | -0.043182 | -0.053797 | -0.022503 | 0.39033
| 8164 | -0.046533 | -0.34114 | 0.50817 | 0.034858 | 0.1952 | 0.42199 | 0.19719 | 0.13207 | -0.21343 | 0.51287
| 8165 | -0.10641 | 0.64209 | 0.3551 | -0.10541 | -0.44367 | -0.1565 | -0.80176 | 0.22922 | -0.53492 | 0.10106
| 8166 | -0.03 | 0.29779 | -0.18361 | 0.084522 | -0.26373 | 0.28523 | 0.76913 | 0.09518 | 0.12302 | -0.071614
| 8167 | 0.15295 | -0.30538 | 0.29438 | 0.007478 | -0.047687 | 0.6631 | -0.16615 | 0.23456 | 0.3817 | 0.023732
| 8168 | 0.13565 | 0.75161 | 0.43529 | 0.13127 | 0.59368 | 0.18397 | 0.06165 | -0.035168 | 0.085287 | 0.1353
| 8169 | -0.16771 | 0.1852 | 0.72742 | 0.18877 | -0.46381 | -0.54251 | 0.036309 | 0.30164 | -0.077666 | -0.38787
| 8170 | -0.19707 | -0.1229 | -0.27192 | 0.2175 | -0.19483 | 0.075392 | -0.63108 | -0.68298 | -0.26359 | 0.6265
| 8171 | -0.29325 | -0.38592 | -0.22961 | 0.80481 | -0.4408 | -0.20962 | -0.85337 | 0.95641 | -0.10017 | -0.48863
| 8172 | 0.59913 | -0.63986 | 0.11994 | 0.088573 | -0.33164 | 0.6371 | 0.034961 | -0.46943 | -0.22663 | -0.31305
| 8173 | -0.34862 | -0.15236 | 0.24283 | 0.39279 | -0.93755 | -0.1706 | 0.13959 | 0.044751 | 0.077558 | 0.61725
| 8174 | 0.058034 | -0.36258 | 0.52597 | 0.0079819 | 0.096507 | -0.18043 | 0.030825 | 0.098169 | -0.14894 | -0.31699
| 8175 | 0.51761 | 0.077232 | 0.029279 | 0.1786 | 0.032994 | 0.13127 | -0.082122 | -0.58131 | 0.75201 | -0.7508
| 8176 | 0.40527 | 0.21942 | -0.79433 | 0.52788 | 0.25939 | -0.53621 | -0.47684 | 0.22508 | -0.12256 | -0.40696
| 8177 | 0.062717 | -0.032167 | -0.61283 | -0.78483 | 0.47322 | 0.4542 | 0.18827 | -0.83118 | 0.21266 | -0.22366
| 8178 | 0.2508 | -0.32598 | -0.22508 | -0.28271 | -0.75526 | 0.37686 | -0.34938 | 0.066244 | 0.21648 | -0.164
| 8179 | 0.74525 | -0.64097 | -0.019235 | 0.76784 | 0.51389 | 0.27993 | 0.011516 | -0.081686 | -0.12267 | -0.55022
| 8180 | 0.077016 | -0.23652 | -0.21648 | -0.19757 | -0.10106 | -0.026501 | -0.16699 | -0.34785 | 0.11011 | -0.91574
| 8181 | -0.5003 | -0.0911 | 0.12199 | -0.21738 | 0.65547 | -0.31102 | 0.11733 | -0.69097 | 0.01 | -0.014962
| 8182 | -0.72378 | 0.19994 | -0.097171 | -0.33826 | -0.75648 | 0.20458 | -0.16783 | -0.13069 | -0.074527 | 0.92063
| 8183 | 0.24336 | 0.14566 | -0.14297 | -0.3551 | -0.030928 | 0.065495 | -0.080272 | 0.42009 | 0.46624 | -0.052635
| 8184 | 0.86696 | 0.038803 | 0.020459 | -0.10865 | 0.64602 | 0.21661 | -0.51802 | 0.77 | 0.10395 | 0.24681
| 8185 | -0.34632 | 0.10518 | 0.026501 | -0.40511 | 0.082994 | -0.29183 | 0.32066 | 0.17399 | -0.16268 | -0.3882
| 8186 | -0.33675 | 0.15318 | -0.042138 | 0.21789 | -0.44873 | 0.53707 | -0.59838 | -0.79875 | 0.43229 | -0.29311
| 8187 | -0.35062 | -0.37558 | 0.25602 | 0.31189 | -0.63054 | -0.76957 | 0.89851 | 0.70657 | 0.34083 | -0.44439
| 8188 | -0.60491 | 0.52682 | 0.12347 | -0.0055655 | 0.25966 | -0.0044599 | -0.80481 | -0.022912 | -0.18287 | 0.035065
| 8189 | -0.37799 | 0.26101 | 0.56814 | 0.52745 | 0.44945 | -0.53363 | -0.50675 | -0.021379 | -0.37895 | -0.30812
| 8190 | 0.41391 | 0.19557 | 0.094627 | 0.68172 | -0.26223 | -0.026912 | 0.57233 | -0.55424 | 0.11926 | 0.62517
| 8191 | -0.5922 | -0.54911 | -0.59515 | -0.36463 | -0.10128 | 0.26932 | -0.29651 | -0.49078 | -0.53556 | -0.073771
| 8192 | -0.27771 | -0.29765 | 0.16603 | 0.11575 | -0.078968 | 0.2278 | -0.14496 | -0.1513 | 0.19012 | -0.31978
| 8193 | 0.28243 | -0.71138 | -0.18373 | 0.90461 | 0.12347 | -0.066887 | 0.52408 | -0.248 | -0.083649 | -0.59073
| 8194 | 0.041825 | 0.36023 | -0.26007 | -0.010303 | 0.32717 | 0.27385 | -0.16759 | -0.015978 | -0.053903 | -0.077883
| 8195 | -0.1153 | -0.1315 | 0.95204 | 0.096728 | 0.77218 | -0.50614 | 0.098723 | 0.3148 | -0.42009 | 0.94084
| 8196 | 0.67 | 0.6578 | -0.031961 | 0.14006 | -0.23718 | -0.57047 | -0.36952 | -0.51472 | 0.37223 | 0.53946
| 8197 | 0.42598 | 0.59368 | 0.67953 | -0.0077803 | 0.17799 | 0.78436 | 0.26332 | -0.63163 | -0.20621 | 0.66519
| 8198 | -0.13959 | 0.21508 | -0.50452 | 0.036932 | 0.57163 | 0.035998 | 0.02281 | 0.27316 | 0.60063 | 0.14718
| 8199 | 0.15401 | 0.71104 | 0.1852 | -0.47151 | -0.12931 | -0.52366 | -0.30164 | -0.30093 | 0.052846 | -0.054749
| 8200 | 0.39992 | -0.76357 | -0.28495 | 0.41085 | -0.16388 | 0.44098 | 0.52471 | 0.22006 | 0.25804 | 0.30079
| 8201 | 0.051897 | -0.45182 | 0.49295 | -0.18852 | -0.77707 | 0.75813 | -0.39181 | 0.16964 | 0.12954 | -0.53556
| 8202 | 0.69488 | -0.19545 | 0.13507 | -0.16567 | -0.45091 | 0.29438 | 0.85337 | -0.36258 | 0.1769 | 0.1082
| 8203 | -0.63244 | -0.030412 | 0.023936 | 0.48961 | -0.23338 | 0.37398 | -0.39825 | 0.25347 | 0.49771 | -0.1962
| 8204 | 0.77528 | 0.026501 | 0.22637 | -0.66221 | 0.071076 | -0.47398 | -0.52703 | 0.17338 | -0.044333 | -0.56239
| 8205 | -0.86036 | 0.096285 | 0.11484 | -0.09 | 0.31422 | 0.023424 | 0.29537 | -0.12302 | -0.030619 | 0.2484
| 8206 | -0.6578 | 0.45824 | 0.58612 | 0.24231 | -0.16639 | 0.35774 | 0.45751 | 0.12507 | -0.31626 | 0.65143
| 8207 | -0.083212 | 0.2907 | -0.15094 | -0.68235 | -0.49196 | 0.75201 | -0.32583 | -0.22186 | -0.38413 | 0.05
| 8208 | 0.031341 | -0.23117 | 0.27123 | -0.10328 | 0.5141 | -0.014454 | -0.18336 | -0.5735 | -0.2722 | -0.18153
| 8209 | 0.31758 | -0.24667 | 0.41136 | 0.0068736 | 0.80481 | 0.074095 | -0.48125 | 0.21763 | -0.61026 | -0.38592
| 8210 | -0.47246 | -0.14145 | 0.81372 | 0.14309 | -0.075608 | 0.14777 | 0.26808 | -0.050421 | 0.22987 | 0.10652
| 8211 | -0.7881 | -0.27578 | 0.5021 | -0.18618 | 0.11338 | 0.26563 | 0.1179 | 0.48941 | 0.32199 | 0.33105
| 8212 | -0.49413 | -0.41888 | 0.7492 | -0.55627 | 0.56814 | 0.20282 | -0.26115 | -0.35448 | 0.36984 | 0.56308
| 8213 | -0.15365 | -0.32022 | 0.26386 | -0.12324 | 0.051264 | -0.3817 | -0.070215 | -0.10843 | -0.12006 | -0.37783
| 8214 | -0.75855 | -0.60567 | 0.44547 | -5.0001e-05 | 0.14542 | -0.50959 | 0.027529 | -0.41596 | 0.046533 | 0.044228
| 8215 | 0.049684 | 0.45036 | -0.23705 | -0.46812 | 0.564 | 0.78576 | 0.046428 | 0.0065716 | -0.76021 | -0.065923
| 8216 | -0.65287 | -0.26563 | 0.14332 | -0.30337 | -0.22328 | 0.36905 | -0.55672 | 0.67427 | 0.21878 | -0.00025003
| 8217 | -0.0052639 | -0.75322 | 0.47703 | 0.36274 | -0.19495 | -0.78251 | -0.56861 | 0.5017 | 0.17278 | -0.42772
| 8218 | 0.34311 | -0.56034 | -0.63326 | -0.16256 | 0.78622 | 0.27412 | 0.40595 | 0.003456 | -0.12416 | -0.48882
| 8219 | -0.53256 | -0.19682 | -0.49177 | -0.0025533 | -0.30451 | -0.49137 | 0.2823 | -0.43193 | 0.043705 | 0.27633
| 8220 | -0.43955 | -0.31611 | -0.36604 | 0.32435 | -0.0033556 | -0.27951 | -0.0073772 | -0.61646 | -0.19074 | -0.47379
| 8221 | 0.32747 | 0.76527 | 0.7488 | -0.2265 | 0.91456 | 0.11541 | 0.17314 | -0.84031 | 0.35603 | 0.5201
| 8222 | 0.05549 | -0.66549 | -0.40881 | -0.16904 | 0.24561 | 0.27536 | 0.35821 | -0.40932 | -0.14297 | 0.98268
| 8223 | -0.30122 | 0.050948 | -0.39362 | 0.86472 | 0.6349 | 0.29708 | 0.32955 | -0.15863 | -0.50796 | -0.55582
| 8224 | 0.011516 | -0.3372 | -0.40075 | -0.49039 | -0.17048 | -0.23534 | 0.36826 | -0.26713 | 0.44656 | -0.42129
| 8225 | -0.45972 | -0.058246 | 0.077991 | -0.22135 | -0.77131 | -0.03434 | -0.50756 | -0.2602 | -0.084194 | 0.44493
| 8226 | -0.86399 | 0.13104 | -0.26128 | 0.46176 | 0.0086877 | -0.078859 | 0.44601 | -0.43211 | -0.067637 | -0.83477
| 8227 | 0.21623 | -0.34708 | -0.011617 | 0.67922 | -0.29113 | -0.28845 | 0.054855 | -0.74564 | 0.099389 | -0.61646
| 8228 | 0.536 | -0.24363 | 0.20244 | 0.47493 | 0.33479 | 0.51595 | 0.21853 | -0.79975 | 0.31978 | 0.092531
| 8229 | 0.079837 | 0.088792 | -0.71557 | -0.19074 | 0.51246 | 0.40881 | 0.39016 | 0.3425 | 0.35355 | 0.26973
| 8230 | -0.52136 | 0.24588 | -0.70117 | 0.76315 | -0.1091 | 0.92063 | 0.15519 | -0.11631 | 0.41408 | -0.32155
| 8231 | 0.20081 | 0.49671 | 0.38608 | -0.11124 | -0.28076 | -0.8454 | -0.16221 | 0.068496 | 0.049579 | 0.65927
| 8232 | 0.68267 | -0.14976 | 0.30841 | 0.0063703 | 0.12851 | 0.34892 | -0.75 | 0.80176 | -0.24508 | 0.18153
| 8233 | 0.66044 | 0.75363 | -0.035583 | 0.6578 | 0.10295 | -0.18006 | 0.050105 | 0.26932 | -0.075608 | -0.10989
| 8234 | -0.69586 | -0.39066 | -0.089231 | 0.33269 | -0.66281 | 0.25307 | 0.1253 | 0.68425 | -0.15377 | 0.87958
| 8235 | 0.046008 | 0.070861 | -0.21393 | -0.25214 | 0.18914 | 0.11858 | -0.32228 | -0.56606 | 0.23691 | -0.43246
| 8236 | -0.018318 | -0.065923 | -0.3451 | -0.049158 | 0.20533 | 0.15472 | -0.68204 | 0.49671 | -0.77887 | -0.51575
| 8237 | 0.098279 | 0.39477 | -0.71733 | 0.19744 | -0.23941 | -0.4426 | -0.16256 | -0.93292 | 0.29694 | -0.38559
| 8238 | -0.49118 | -0.18889 | 0.19944 | -0.33209 | 0.72018 | -0.36039 | -0.036932 | -0.86696 | 0.53837 | 0.41991
| 8239 | -0.56331 | -0.25791 | 0.6631 | 0.54514 | -0.452 | -0.14671 | -0.22263 | -0.13253 | -0.060585 | 0.86621
| 8240 | -0.26617 | 0.2823 | 0.38283 | 0.55739 | -0.39 | 0.74212 | 0.37976 | 0.28803 | -0.092311 | -0.024551
| 8241 | 0.0995 | 0.059947 | -0.17568 | 0.8454 | -0.44945 | -0.70794 | 0.71035 | 0.18975 | 0.60617 | -0.49473
| 8242 | 0.73866 | 0.23954 | 0.35216 | -0.12188 | -0.37558 | -0.33299 | -0.53946 | -0.40595 | 0.26345 | -0.16364
| 8243 | 0.50614 | 0.076582 | 0.18177 | 0.38429 | 0.42755 | 0.15804 | -0.21254 | 0.1179 | -0.042555 | 0.57562
| 8244 | -0.092421 | -0.41255 | 0.056337 | 0.83783 | -0.86108 | -0.31582 | 0.10708 | 0.27247 | 0.44349 | -0.034961
| 8245 | -0.38951 | -0.6249 | -0.30007 | 0.8618 | 0.39477 | -0.064105 | 0.22173 | -0.21343 | -0.08967 | 0.19247
| 8246 | 0.011921 | -0.55044 | 0.26441 | 0.64971 | 0.0078811 | 0.52703 | -0.47455 | 0.13808 | -0.11496 | -0.44206
| 8247 | 0.58515 | -0.8739 | 0.1628 | 0.13357 | 0.46362 | -0.035894 | -0.37446 | 0.29226 | -0.44638 | -0.22469
| 8248 | 0.46962 | -0.0048618 | -0.051053 | -0.20006 | -0.94804 | 0.02609 | 0.20319 | -0.056655 | 0.40797 | 0.10485
| 8249 | -0.021787 | -0.42737 | 0.33164 | -0.25993 | -0.52345 | 0.94804 | -0.72852 | -0.80075 | 0.43018 | 0.51844
| 8250 | -0.42772 | 0.12851 | 0.73637 | 0.55989 | 0.55267 | 0.37976 | -0.44927 | 0.30624 | 0.26264 | 0.17811
| 8251 | -0.36023 | -0.19782 | 0.09011 | -0.20244 | 0.15177 | -0.64125 | 0.60415 | -0.031341 | -0.41391 | 0.8937
| 8252 | 0.19669 | -0.28216 | 0.43902 | -0.57917 | 0.47019 | -0.55989 | 0.5959 | 0.11439 | -0.43246 | 0.054114
| 8253 | 0.37542 | -0.25027 | -0.42233 | 0.056973 | 0.24721 | -0.19607 | 0.072045 | -0.48029 | -0.44027 | -0.0091922
| 8254 | -0.20219 | -0.43141 | -0.038699 | -0.71946 | 0.54823 | -0.18104 | -0.033615 | -0.60541 | -0.47151 | 0.54316
| 8255 | -0.058246 | 0.051053 | -0.13173 | -0.093082 | -0.42755 | 0.17763 | -0.2052 | -0.86847 | 0.069033 | -0.5458
| 8256 | 0.44116 | 0.27261 | -0.47303 | -0.51595 | -0.026912 | -0.77306 | 0.55267 | -0.11586 | -0.13496 | -0.84094
| 8257 | 0.30552 | -0.55921 | -0.38445 | -0.032167 | -0.49592 | 0.08978 | -0.40527 | 0.51823 | 0.8043 | -0.30064
| 8258 | 0.46028 | -0.10753 | 0.2985 | 0.40595 | 0.28803 | 0.67643 | 0.2816 | 0.60063 | -0.8755 | 0.032788
| 8259 | -0.89464 | -0.43902 | 0.027735 | -0.50452 | 0.057503 | -0.78716 | -0.036413 | -0.24654 | 0.15259 | 0.24495
| 8260 | 0.26645 | 0.87712 | -0.38575 | 0.25777 | 0.19272 | 0.39181 | -0.5013 | -0.62597 | -0.51287 | -0.27605
| 8261 | -0.54933 | 0.63462 | -0.39742 | 0.11733 | -0.34099 | -0.021583 | 0.13866 | -0.28972 | -0.8148 | 0.62704
| 8262 | 0.37831 | 0.64125 | 0.0032553 | 0.068818 | 0.35479 | 0.06957 | -0.36921 | 0.23078 | -0.35231 | -0.31495
| 8263 | 0.28831 | -0.85613 | -0.10239 | 0.54492 | 0.47741 | 0.088024 | -0.15389 | -0.00055015 | 0.078968 | -0.2037
| 8264 | -0.098834 | -0.7005 | -0.24814 | 0.5003 | -0.38738 | -0.42164 | 0.55223 | 0.2975 | -0.25093 | 0.20056
| 8265 | -0.029176 | -0.038907 | -0.25455 | 0.078642 | 0.23757 | 0.82196 | -0.26617 | 0.47 | 0.12553 | -0.46474
| 8266 | 0.85337 | 0.72305 | 0.058565 | -0.31538 | -0.52324 | 0.083321 | 0.236 | -0.35587 | -0.40192 | 0.25926
| 8267 | 0.75161 | 0.35977 | 0.98268 | -0.30136 | 0.19508 | 0.37048 | 0.10641 | 0.12931 | 0.19025 | 0.50756
| 8268 | 0.26836 | -0.30093 | 0.59392 | 0.024449 | -0.63081 | -0.57846 | -0.28453 | 0.10652 | 0.17665 | 0.70521
| 8269 | 0.69983 | -0.11326 | -0.25777 | -0.39908 | -0.035583 | 0.3132 | -0.57941 | -0.28369 | -0.25804 | 5.0001e-05
| 8270 | -0.67581 | 0.028558 | 0.26918 | -0.3451 | -0.014556 | 0.45273 | 0.45273 | -0.73074 | -0.16519 | -0.72852
| 8271 | -0.452 | -0.48785 | 0.27522 | 0.27481 | -0.6257 | -0.26034 | 0.19707 | 0.21495 | -0.74368 | -0.019541
| 8272 | 0.066351 | 0.16077 | -0.092972 | -0.13878 | 0.91225 | -0.53149 | -0.021481 | -0.33194 | -0.031961 | -0.1034
| 8273 | -0.41085 | -0.34862 | 0.31422 | 0.42895 | 0.15188 | -0.39098 | 0.0020521 | 0.31949 | -0.18544 | 0.06229
| 8274 | -0.35247 | 0.70691 | -0.29042 | 0.0066723 | -0.34525 | -0.30495 | -0.047267 | 0.29296 | -0.2733 | -0.10585
| 8275 | 0.92319 | -0.51575 | -0.32051 | -0.45769 | -0.085724 | 0.41596 | 0.056337 | -0.25133 | 0.45 | 0.25831
| 8276 | -0.6371 | -0.083867 | -0.29537 | -0.28916 | 0.30696 | -0.58323 | -0.0054649 | -0.21866 | 0.34114 | 0.87793
| 8277 | -0.27924 | 0.51844 | 0.32643 | 0.25723 | -0.15035 | -0.033408 | 0.41477 | 0.17665 | 0.28397 | 0.23117
| 8278 | -0.59147 | 0.17556 | -0.50513 | -0.78114 | -0.086381 | 0.7623 | -0.88731 | -0.31743 | -0.32051 | 0.86771
| 8279 | 0.09695 | 0.046113 | -0.3951 | 0.40645 | 0.60491 | -0.0040582 | -0.64574 | -0.32435 | 0.048948 | 0.15733
| 8280 | -0.62463 | 0.14929 | 0.23495 | 0.32081 | -0.19148 | -0.33841 | -0.31802 | -0.48048 | 0.54911 | 0.055807
| 8281 | 0.41323 | -0.65029 | 0.16759 | 0.21368 | -0.3451 | -0.47933 | -0.54624 | -0.15638 | -0.28537 | -0.82708
| 8282 | 0.0755 | 0.57917 | -0.20861 | 0.45658 | -0.38283 | 0.48125 | 0.56125 | -0.62946 | 0.34129 | 0.24588
| 8283 | 0.64321 | 0.61777 | 0.053691 | 0.75813 | 0.1852 | -0.013136 | 0.23705 | -0.35463 | -0.32066 | 0.075068
| 8284 | 0.60846 | -0.20848 | -0.28355 | 0.53128 | -0.6985 | -0.37191 | -0.43955 | -0.21597 | 0.63599 | -0.055278
| 8285 | 0.30079 | -0.2571 | -0.041929 | 0.47818 | -0.12245 | 0.5866 | 0.080598 | 0.27564 | -0.48144 | -0.69162
| 8286 | -0.46661 | 0.34739 | -0.023527 | -0.32702 | -0.84284 | 0.087695 | 0.24455 | 0.63163 | 0.058884 | -0.51205
| 8287 | -0.78952 | 0.43 | 0.36573 | -0.90566 | 0.0911 | 0.21114 | -0.26468 | 0.21152 | -0.17982 | 0.60795
| 8288 | -0.021583 | 0.17386 | -0.043914 | 0.026912 | 0.034029 | 0.42912 | -0.31349 | -0.69917 | 0.26973 | 0.31655
| 8289 | 0.46812 | 0.30079 | -0.23928 | 0.27288 | -0.40326 | -0.09088 | 0.46568 | 0.49 | 0.23391 | -0.3167
| 8290 | -0.46943 | -0.37606 | -0.80791 | 0.065174 | -0.54646 | 0.69751 | -0.20949 | -0.23888 | 0.29879 | -0.31043
| 8291 | 0.22071 | 0.60821 | -0.21994 | 0.22109 | -0.42703 | 0.19136 | -0.57444 | 0.26699 | -0.14041 | 0.24907
| 8292 | -0.54404 | -0.40259 | 0.12131 | -0.2476 | 0.53449 | 0.02897 | 0.0037571 | -0.10933 | -0.61361 | -0.3804
| 8293 | -0.24853 | 0.10776 | 0.38771 | -0.40292 | 0.1841 | 0.22598 | -0.63271 | -0.33134 | -0.36321 | 0.55898
| 8294 | 0.21406 | 0.35789 | -0.40175 | -0.19446 | 0.11214 | 0.1797 | -0.40427 | 0.10619 | 0.43973 | -0.40209
| 8295 | 0.37799 | -0.16197 | -0.264 | 0.48067 | 0.53299 | 0.2575 | -0.033925 | 0.32361 | -0.40814 | 0.31685
| 8296 | 0.44746 | -0.23613 | -0.36762 | -0.18128 | 0.40276 | 0.67304 | -0.40578 | 0.39709 | -0.12097 | -0.31189
| 8297 | -0.46306 | 0.1179 | -0.6371 | -0.10753 | -0.71277 | -0.12862 | 0.18803 | 0.20207 | -0.31087 | 0.052108
| 8298 | 0.029279 | 0.46065 | 0.39329 | 0.10228 | -0.5412 | -0.052635 | 0.71875 | -0.55447 | -0.029794 | 0.35092
| 8299 | 0.36762 | 0.29622 | 0.033305 | 0.46868 | 0.35386 | -0.42807 | -0.30855 | -0.18557 | -0.51554 | 0.33239
| 8300 | -0.035376 | -0.11056 | 0.47322 | 0.54911 | -0.23273 | -0.24667 | 0.14355 | 0.22418 | 0.28859 | -0.074851
| 8301 | 0.47132 | -0.36905 | 0.5172 | -0.38787 | 0.3148 | -0.66192 | 0.44565 | -0.17265 | -0.40209 | 0.51184
| 8302 | -0.14402 | -0.29509 | 0.072261 | 0.078208 | 0.40544 | -0.20156 | 0.73111 | -0.51657 | -0.33826 | -0.77751
| 8303 | 0.56171 | -0.4991 | -0.28509 | -0.59515 | 0.051053 | -0.21981 | 0.64715 | -0.30812 | 0.68743 | -0.22444
| 8304 | -0.4999 | 0.23156 | 0.10239 | -0.41391 | -0.13334 | 0.058777 | -0.87 | 0.20382 | 0.25254 | 0.11451
| 8305 | -0.55989 | -0.23456 | 0.023015 | 0.11056 | 0.16185 | 0.25174 | -0.16952 | 0.0056661 | -0.4987 | -0.68743
| 8306 | -0.72596 | 0.63737 | -0.44206 | -0.2711 | -0.1769 | -0.9134 | -0.092531 | -0.67612 | -0.48048 | 0.53989
| 8307 | -0.33917 | 0.12006 | -0.098058 | 0.10619 | 0.74019 | 0.85823 | -0.16066 | -0.58371 | 0.29665 | -0.21508
| 8308 | 0.45273 | -0.54823 | -0.25267 | -0.079077 | -0.39312 | -0.15283 | 0.061331 | -0.049474 | 0.63353 | 0.17399
| 8309 | -0.73675 | 0.056443 | -0.38251 | -0.63682 | -0.25334 | 0.35401 | -0.24654 | -0.5199 | 0.3025 | -0.74841
| 8310 | 0.66698 | 0.32317 | -0.65518 | 0.65086 | -0.78576 | 0.082994 | 0.53859 | -0.80843 | -0.35494 | 0.13681
| 8311 | -0.6634 | 0.15792 | -0.63875 | 0.080816 | 0.11259 | -0.65809 | -0.11643 | 0.043914 | 0.19782 | 0.19049
| 8312 | -0.32866 | -0.46306 | 0.48648 | -0.33494 | -0.38056 | 0.62517 | -0.19819 | 0.99 | -0.37542 | 0.52052
| 8313 | 0.2343 | 0.19371 | 0.11248 | 0.30812 | 0.6149 | 0.60314 | -0.70966 | 0.24734 | 0.13704 | -0.5693
| 8314 | 0.55134 | -0.64715 | -0.15283 | -0.31495 | 0.14706 | -0.72963 | -0.20495 | 0.061118 | -0.3751 | 0.81642
| 8315 | 0.4993 | -0.11484 | 0.68743 | 0.19719 | 0.18238 | -0.018827 | 0.048002 | 0.33149 | 0.1729 | -0.64546
| 8316 | 0.036205 | -0.49275 | -0.4717 | -0.72779 | 0.25053 | 0.30826 | -0.052424 | 0.22083 | 0.038387 | 0.42895
| 8317 | 0.033201 | 0.3132 | 0.082449 | 0.60643 | -0.68679 | -0.054326 | -0.094075 | 0.1952 | -0.3248 | 0.3189
| 8318 | 0.29311 | 0.84284 | 0.3838 | 0.69032 | 0.027837 | -0.054855 | 0.79776 | 0.084413 | -0.60846 | -0.22922
| 8319 | -0.16161 | 0.21482 | 0.63326 | -0.97354 | 0.20257 | -0.18385 | -0.31772 | 0.48048 | 0.53707 | 0.34739
| 8320 | 0.63599 | -0.030825 | 0.069892 | 0.099278 | -0.077774 | -0.40292 | 0.33902 | 0.15958 | -0.66578 | 0.62251
| 8321 | -0.21521 | -0.15377 | -0.14683 | 0.49354 | -0.63599 | 0.17605 | -0.42563 | -0.17048 | -0.53299 | -0.6637
| 8322 | -0.32007 | 0.32583 | 0.75896 | -0.11372 | -0.38787 | -0.57468 | -0.63408 | -0.4985 | -0.20785 | -0.19049
| 8323 | -0.35417 | -0.43688 | 0.71557 | 0.79095 | 0.31495 | -0.47665 | 0.63217 | 0.23547 | -0.26631 | 0.039635
| 8324 | 0.43476 | -0.098169 | 0.30971 | -0.32598 | -0.56239 | -0.55044 | 0.65345 | 0.11938 | -0.12359 | -0.57798
| 8325 | 0.05422 | 0.17495 | 0.18827 | -0.20219 | -0.54536 | -0.72742 | 0.12222 | 0.14379 | -0.19334 | -0.24244
| 8326 | -0.59938 | -0.25899 | 0.48765 | 0.47531 | -0.51637 | -0.93292 | -0.011415 | -0.0051633 | 0.14695 | 0.30466
| 8327 | -0.53492 | 0.17848 | -0.29708 | -0.16185 | -0.069677 | -0.10328 | -0.51348 | 0.21139 | -0.29765 | 0.23443
| 8328 | 0.45127 | -0.79336 | 0.59491 | 0.098169 | -0.05899 | 0.32658 | 0.52597 | -0.046218 | -0.94084 | -0.72963
| 8329 | 0.44547 | -0.21878 | 0.024449 | -0.39975 | -0.35665 | 0.13832 | 0.18655 | -0.098612 | 0.5011 | 0.34418
| 8330 | 0.69129 | 0.53363 | 0.28972 | 0.29964 | -0.35154 | -0.19856 | 0.25804 | 0.36149 | 0.31699 | -0.32925
| 8331 | 0.070538 | -0.16639 | 0.4041 | -0.10966 | 0.4078 | 0.47531 | -0.036828 | 0.35634 | 0.38024 | 0.60872
| 8332 | -0.58299 | -0.07183 | 0.22289 | -0.031754 | 0.37494 | 0.088573 | 0.12816 | -0.34357 | 0.073879 | 0.25053
| 8333 | -0.28425 | -0.0041586 | -0.016893 | 0.11631 | 0.29183 | 0.38885 | -0.32836 | 0.072369 | 0.3357 | -0.21878
| 8334 | 0.59073 | -0.6265 | 0.1868 | 0.073879 | -0.30942 | 0.051791 | 0.019031 | -0.16844 | -0.067745 | -0.3375
| 8335 | -0.26373 | -0.42668 | 0.25777 | 0.2985 | -0.067852 | 0.36008 | -0.26686 | 0.45073 | 0.79 | -0.059096
| 8336 | 0.19272 | 0.17314 | -0.22212 | 0.52177 | -0.3048 | -0.18938 | 0.46737 | -0.043391 | -0.38202 | -0.13971
| 8337 | 0.02722 | 0.17193 | -0.39148 | 0.16496 | -0.014454 | 0.20319 | -0.2975 | -0.33932 | -0.65029 | -0.60872
| 8338 | 0.26959 | 0.17738 | 0.15685 | 0.015876 | 0.2659 | -0.14648 | -0.74212 | 0.073987 | -0.64405 | -0.49256
| 8339 | 0.53794 | 0.62224 | 0.19025 | 0.14566 | -0.13588 | 0.26305 | -0.27137 | -0.58539 | 0.29438 | 0.564
| 8340 | -0.54142 | 0.081904 | -0.28285 | -0.17994 | -0.35 | 0.16976 | 0.39033 | 0.0028541 | -0.61412 | 0.19831
| 8341 | -0.0025533 | 0.37079 | -0.046428 | -0.39115 | -0.38869 | 0.012832 | 0.20044 | -0.28425 | -0.44782 | 0.50715
| 8342 | 0.22935 | -0.73981 | 0.24933 | 0.26454 | -0.28188 | -0.3735 | 0.22058 | -0.47569 | 0.076258 | -0.32465
| 8343 | -0.18606 | -0.0055655 | 0.24429 | 0.44873 | 0.084959 | 0.34923 | -0.52136 | 0.51595 | -0.29651 | 0.91693
| 8344 | 0.23404 | -0.57515 | 0.37302 | 0.42303 | 0.16579 | 0.13069 | -0.17265 | 0.17084 | -0.085287 | 0.11541
| 8345 | 0.69884 | -0.063677 | 0.27069 | 0.40343 | 0.037763 | 0.16125 | -0.57751 | 0.053797 | -0.11236 | 0.12484
| 8346 | -0.65518 | 0.10966 | -0.75731 | -0.28049 | 0.85337 | 0.11654 | -0.18067 | 0.47474 | -0.64914 | -0.24455
| 8347 | -0.24893 | -0.38706 | 0.054326 | -0.49315 | -0.58107 | 0.65956 | 0.45401 | -0.16412 | -0.6637 | -0.13219
| 8348 | -0.25576 | -0.53406 | 0.85823 | -0.043391 | 0.16711 | 0.56125 | 0.0058672 | 0.29936 | -0.77617 | -0.21994
| 8349 | -0.42268 | -0.39411 | -0.4997 | 0.1418 | 0.028352 | 0.02189 | -0.44242 | -0.21687 | -0.58878 | -0.73298
| 8350 | 0.57491 | -0.14332 | 0.086709 | 0.25602 | 0.16412 | -0.12097 | -0.22974 | 0.040156 | 0.16675 | -0.42982
| 8351 | 0.37016 | 0.27055 | 0.081577 | 0.79628 | -0.73448 | 0.020663 | 0.0066723 | 0.20949 | -0.13507 | 0.24575
| 8352 | -0.20987 | -0.080272 | -0.039115 | 0.34571 | -0.13948 | 0.76272 | -0.37895 | 0.25147 | 0.19533 | -0.9219
| 8353 | 0.20848 | 0.22379 | -0.038387 | 0.79531 | 0.0055655 | -0.77707 | -0.44403 | 0.72705 | 0.056761 | -0.24987
| 8354 | -0.72669 | -0.27661 | 0.33464 | -0.3951 | 0.0067729 | -0.42965 | -0.41153 | 0.58539 | 0.042869 | 0.20571
| 8355 | 0.097947 | -0.11949 | 0.16328 | -0.66074 | 0.52597 | 0.25872 | -0.4995 | 0.19981 | 0.25966 | -0.54845
| 8356 | -0.028764 | -0.26183 | 0.023629 | 0.009697 | -0.082558 | -0.2567 | -0.023629 | -0.61725 | 0.25214 | 0.42476
| 8357 | -0.013744 | 0.32702 | 0.47019 | 0.31073 | 0.47303 | 0.29637 | -0.30841 | 0.00035006 | 0.51102 | 0.37159
| 8358 | 0.564 | 0.52219 | -0.0055655 | -0.22935 | 0.094848 | -0.13832 | 0.015571 | -0.18385 | 0.0089904 | 0.74564
| 8359 | -0.27688 | 0.14064 | 0.00065021 | 0.26142 | 0.031548 | 0.15638 | 0.10006 | 0.28565 | 0.088792 | -0.072045
| 8360 | -0.31699 | -0.564 | 0.020051 | 0.73223 | 0.15389 | -0.043287 | 0.55694 | 0.2823 | -0.19309 | 0.17617
| 8361 | 0.33374 | -0.66192 | -0.42043 | -0.61699 | 0.32821 | 0.51782 | 0.36636 | 0.19099 | -0.49631 | -0.21635
| 8362 | -0.026912 | 0.66133 | -0.66074 | -0.62013 | 0.31993 | 0.031857 | -0.08978 | -0.79 | 0.28202 | -0.10978
| 8363 | -0.071399 | 0.36984 | -0.4307 | -0.18434 | 0.29353 | 0.5199 | -0.1323 | -0.40679 | -0.93597 | 0.21687
| 8364 | -0.13092 | -0.75731 | -0.17265 | 0.038699 | -0.023629 | 0.1315 | 0.083867 | -0.70691 | -0.61154 | 0.42528
| 8365 | 0.63027 | 0.68743 | 0.17229 | 0.085396 | -0.29028 | -0.25872 | 0.36368 | -0.15946 | 0.081142 | 0.67304
| 8366 | -0.54778 | -0.11575 | 0.63654 | -0.2948 | 0.37622 | 0.42389 | 0.065495 | 0.79143 | 0.085834 | -0.095954
| 8367 | 0.41596 | 0.050737 | -0.19495 | -0.61387 | -0.43884 | 0.098612 | -0.71417 | -0.17763 | 0.46269 | 0.32287
| 8368 | -0.6077 | 0.1868 | -0.12404 | -0.26345 | 0.10552 | -0.1775 | 0.05814 | -0.29438 | 0.24867 | -0.91815
| 8369 | 0.11473 | 0.52767 | 0.31509 | 0.18104 | -0.16663 | -0.84476 | -0.35123 | 0.063144 | -0.33239 | -0.082122
| 8370 | -0.31058 | 0.15165 | -0.56699 | -0.18226 | 0.49493 | 0.53859 | 0.31043 | -0.29169 | -0.27453 | -0.19956
| 8371 | -0.30408 | 0.40376 | -0.37574 | -0.12302 | 0.52576 | -0.036621 | -0.43617 | -0.25388 | 0.77796 | 0.032581
| 8372 | 0.68615 | -0.26904 | -0.21368 | 0.20069 | -0.025988 | 0.3248 | -0.57 | -0.28565 | -0.25602 | -0.61725
| 8373 | 0.66608 | -0.007075 | 0.26481 | -0.14965 | 0.024654 | -0.009798 | 0.12759 | -0.31685 | -0.35556 | 0.38121
| 8374 | 0.40376 | -0.64377 | -0.51782 | -0.1044 | -0.77662 | 0.48629 | 0.052213 | 0.26128 | -0.51082 | 0.55089
| 8375 | 0.20269 | -0.64518 | -0.016791 | 0.31203 | 0.22974 | -0.40814 | 0.16316 | 0.27882 | 0.24007 | 0.20987
| 8376 | -0.33992 | 0.75648 | -0.54933 | -0.54712 | -0.63986 | -0.34114 | -0.2733 | -0.26332 | -0.39016 | 0.11869
| 8377 | -0.34281 | 0.30036 | -0.15733 | 0.61206 | -0.42372 | -0.21203 | -0.032994 | 0.6233 | 0.34739 | 0.49453
| 8378 | -0.21763 | 0.041303 | 0.21127 | 0.2278 | 0.56171 | -0.52198 | 0.11067 | 0.19185 | -0.10261 | 0.3366
| 8379 | -0.00035006 | -0.1814 | 0.15177 | -0.53707 | 0.17386 | 0.016384 | -0.27316 | -0.11045 | 0.22805 | 0.049053
| 8380 | 0.52198 | 0.58781 | 0.24535 | -0.67488 | -0.030516 | -0.6995 | 0.20332 | -0.58227 | -0.24297 | 0.17374
| 8381 | -0.25683 | 0.4736 | 0.02722 | -0.036309 | 0.008486 | -0.46793 | -0.44674 | -0.20571 | -0.17048 | 0.6233
| 8382 | -0.50311 | 0.011719 | -0.49453 | -0.31102 | -0.52957 | -0.1533 | 0.17508 | 0.21393 | 0.10217 | 0.3727
| 8383 | 0.020663 | -0.31058 | -0.39 | -0.10686 | -0.15685 | -0.046742 | -0.44045 | 0.36778 | -0.3038 | 0.34129
| 8384 | 0.38804 | -0.16759 | 0.037971 | 0.24628 | -0.15306 | 0.11022 | 0.24297 | 0.45255 | 0.32125 | 0.86399
| 8385 | -0.80379 | -0.15899 | -0.50837 | -0.56583 | -0.18361 | 0.0029544 | 0.23104 | -0.069785 | -0.44873 | -0.029794
| 8386 | -0.15875 | 0.66789 | 0.39527 | -0.056019 | 0.70217 | 0.13484 | 0.25872 | 0.8821 | -0.35836 | -0.2398
| 8387 | -0.12747 | 0.18803 | -0.12931 | -0.15365 | 0.16735 | -0.65373 | 0.55559 | 0.71769 | 0.36905 | -0.29155
| 8388 | 0.13716 | -0.39477 | -0.37927 | -0.45695 | 0.30812 | -0.28271 | -0.58395 | 0.26115 | 0.14812 | 0.5174
| 8389 | 0.22186 | -0.65114 | 0.14742 | 0.70251 | -0.1082 | 0.48922 | 0.22096 | 0.046323 | -0.14425 | -0.70285
| 8390 | 0.63462 | -0.16484 | -0.6985 | -0.68298 | -0.51678 | -0.86696 | 0.20483 | -0.47303 | 0.22135 | 0.4898
| 8391 | -0.40242 | 0.12839 | 0.1962 | 0.53171 | -0.17423 | -0.61154 | -0.24402 | -0.042033 | 0.37414 | -0.59888
| 8392 | 0.23273 | -0.092641 | -0.12644 | 0.40108 | -0.31699 | -0.18926 | -0.05348 | 0.57 | 0.64377 | -0.27165
| 8393 | -0.58443 | -0.062717 | 0.050526 | -0.019643 | -0.48726 | 0.065174 | 0.73789 | 0.64971 | 0.46158 | 0.4859
| 8394 | 0.034443 | 0.73675 | 0.56768 | 0.5009 | 0.9219 | -0.29466 | -0.63986 | -0.12599 | -0.35432 | 0.4991
| 8395 | -0.53171 | 0.24151 | -0.35541 | 0.025269 | 0.37143 | 0.37191 | -0.15638 | 0.25334 | -0.3864 | -0.7839
| 8396 | 0.61387 | 0.097836 | 0.27055 | 0.050737 | 0.022299 | 0.078534 | 0.70691 | 0.066565 | 0.020868 | -0.54956
| 8397 | 0.097393 | -0.52957 | 0.67798 | 0.072153 | -0.34938 | 0.06016 | 0.10429 | -0.29537 | 0.032167 | 0.0083852
| 8398 | -0.12028 | -0.74841 | 0.39016 | 0.60719 | -0.1706 | -0.34281 | 0.1775 | -0.27827 | -0.46046 | 0.060053
| 8399 | -0.17386 | 0.15484 | 0.24482 | 0.58636 | 0.22805 | -0.42615 | 0.38315 | -0.13242 | -0.046428 | -0.26142
| 8400 | -0.43229 | 0.32155 | -0.040469 | 0.033098 | 0.32747 | 0.76913 | 0.057185 | -0.28916 | 0.11847 | 0.12233
| 8401 | -0.041407 | 0.24231 | 0.00075028 | 0.37032 | -0.45 | -0.080598 | 0.41819 | -0.41357 | 0.42216 | 0.35727
| 8402 | -0.63517 | -0.13184 | 0.43476 | -0.28509 | 0.38089 | -0.24947 | 0.1597 | 0.70794 | -0.42842 | 0.61335
| 8403 | 0.022503 | 0.14414 | -0.3211 | 0.29395 | -0.059734 | 0.11631 | 0.12028 | 0.29056 | 0.024962 | 0.89753
| 8404 | 0.34985 | -0.16711 | 0.2476 | -0.58131 | 0.25093 | 0.60541 | -0.49671 | -0.26849 | 0.35665 | 0.049158
| 8405 | 0.48067 | 0.24046 | 0.051264 | -0.058671 | -0.39148 | 0.7076 | 0.57444 | 0.6407 | -0.46661 | 0.43724
| 8406 | 5.0001e-05 | 0.24893 | 0.41017 | 0.59196 | 0.20848 | 0.73524 | 0.09176 | -0.1565 | 0.53449 | -0.10017
| 8407 | -0.67612 | 0.34525 | 0.8043 | -0.18104 | -0.20886 | 0.11112 | -0.32199 | 0.10708 | -0.011011 | 0.38056
| 8408 | 0.19607 | 0.73637 | -0.33 | -0.11926 | -0.62039 | 0.025372 | 0.22302 | -0.11484 | 0.6985 | -0.45622
| 8409 | 0.081251 | -0.10284 | -0.23156 | -0.64631 | -0.011921 | 0.67152 | -0.28063 | 0.74801 | -0.02281 | -0.12404
| 8410 | 0.1308 | 0.28481 | 0.71 | 0.34831 | 0.61154 | 0.030825 | -0.053269 | 0.033408 | -0.20357 | 0.38218
| 8411 | 0.79482 | 0.54229 | -0.5447 | -0.71733 | -0.064425 | -0.042242 | 0.34068 | 0.14087 | 0.29822 | 0.15935
| 8412 | -0.28635 | -0.23823 | -0.63737 | 0.015774 | 0.42737 | 0.1432 | 0.3372 | 0.51369 | 0.037763 | -0.022299
| 8413 | -0.13046 | 0.31743 | -0.21203 | 0.37478 | -0.031651 | -0.51205 | 0.68361 | 0.09695 | 0.19235 | -0.62865
| 8414 | 0.61803 | 0.63271 | -0.7508 | -0.79143 | 0.4134 | -0.46437 | -0.26699 | 0.12633 | 0.19744 | 0.031341
| 8415 | 0.2985 | -0.37686 | -0.083758 | 0.64518 | 0.081251 | -0.13924 | 0.21725 | -0.21533 | 0.39925 | 0.086381
| 8416 | -0.073124 | 0.69032 | 0.033718 | -0.41119 | 0.021787 | -0.56331 | -0.4997 | 0.22032 | 0.12897 | -0.13797
| 8417 | 0.27702 | -0.1063 | 0.82708 | 0.37127 | -0.22521 | 0.3651 | 0.21738 | -0.26156 | 0.66459 | -0.17763
| 8418 | -0.060692 | -0.44134 | 0.0022525 | -0.81318 | 0.039531 | -0.71347 | 0.22083 | 0.26332 | 0.16006 | 0.61777
| 8419 | 0.20156 | -0.18483 | 0.3038 | -0.15 | -0.16591 | -0.31963 | -0.14134 | 0.075176 | 0.06229 | 0.30265
| 8420 | 0.39461 | 0.15935 | -0.28831 | 0.23117 | 0.45 | 0.14788 | 0.12256 | -0.12966 | 0.47208 | -0.43088
| 8421 | 0.24482 | 0.5922 | -0.35525 | -0.0042591 | 0.24601 | -0.66399 | -0.16639 | 0.82536 | 0.27247 | -0.82941
| 8422 | -0.25562 | 0.84412 | 0.066137 | 0.6077 | -0.2621 | -0.15946 | -0.75731 | 0.3593 | 0.25656 | 0.02568
| 8423 | 0.68172 | -0.077124 | -0.6118 | 0.068711 | 0.28188 | -0.45292 | -0.51906 | -0.37847 | -0.2512 | 0.68839
| 8424 | 0.18926 | -0.22032 | -0.12782 | 0.49315 | -0.10384 | 0.055701 | 0.19371 | 0.31978 | 0.29099 | 0.89
| 8425 | -0.29056 | -0.78576 | 0.19682 | -0.15733 | -0.0036567 | -0.64744 | -0.61026 | 0.66698 | -0.11394 | -0.33675
| 8426 | -0.21904 | 0.36573 | 0.10787 | 0.22418 | -0.13311 | -0.27854 | 0.081142 | 0.23404 | -0.0911 | -0.097725
| 8427 | -0.84031 | 0.24257 | -0.58299 | -0.4564 | -0.54492 | -0.06914 | 0.16018 | 0.24867 | -0.54602 | -0.58563
| 8428 | -0.13634 | -0.18018 | -0.85 | 0.43759 | -0.70623 | 0.048107 | 0.07043 | 0.37462 | -0.056337 | 0.0037571
| 8429 | 0.13484 | 0.18189 | 0.18128 | -0.36086 | -0.2575 | 0.34877 | 0.72669 | -0.21063 | 0.12828 | -0.69455
| 8430 | -0.41306 | -0.39246 | 0.33796 | -0.33015 | 0.4987 | -0.63271 | 0.58347 | 0.11598 | -0.18667 | 0.1634
| 8431 | 0.29452 | -0.18336 | -0.38755 | 0.67674 | -0.032684 | -0.026707 | 0.089121 | 0.24787 | 0.24747 | -0.43653
| 8432 | -0.48164 | 0.40242 | -0.47038 | 0.34068 | -0.12222 | 0.28063 | -0.21355 | 0.63135 | 0.052319 | -0.28579
| 8433 | 0.61412 | -0.066351 | -0.77887 | -0.29452 | 0.18336 | 0.63435 | -0.013744 | -0.74212 | -0.39726 | 0.29113
| 8434 | 0.6811 | -0.43635 | -0.74135 | -0.94432 | 0.79482 | -0.36463 | -0.14882 | 0.26278 | 0.65693 | 0.014049
| 8435 | -0.30769 | -0.27744 | -0.20823 | -0.68807 | -0.3727 | 0.33449 | -0.037244 | -0.14017 | 0.095954 | 0.25845
| 8436 | 0.017707 | 0.69917 | -0.51082 | 0.051897 | 0.093523 | 0.80075 | 0.5332 | 0.44656 | -0.028146 | -0.48668
| 8437 | -0.3851 | -0.13011 | -0.22521 | 0.25455 | 0.36353 | 0.36463 | 0.11225 | -0.49751 | -0.42668 | 0.087586
| 8438 | -0.61987 | -0.42755 | 0.015267 | -0.094406 | -0.30179 | -0.37223 | 0.028661 | 0.70184 | 0.052108 | -0.094627
| 8439 | 0.28327 | -0.14695 | -0.12324 | 0.5141 | 0.10172 | 0.22019 | -0.57869 | -0.01842 | -0.33705 | -0.49196
| 8440 | 0.59147 | -0.26088 | 0.055066 | -0.22676 | -0.048738 | -0.45622 | -0.36211 | 0.15472 | 0.49394 | -0.53794
| 8441 | 0.5583 | 0.19645 | 0.10832 | 0.47875 | -0.04538 | -0.30567 | -0.19433 | -0.55898 | 0.063784 | 0.73335
| 8442 | -0.37016 | -0.14988 | -0.071938 | 0.83237 | 0.53837 | 0.64886 | 0.80687 | -0.29793 | -0.60643 | -0.49572
| 8443 | -0.33781 | -0.10406 | -0.21457 | 0.55312 | -0.18717 | -0.099833 | 0.78858 | -0.49374 | 0.51246 | 0.5019
| 8444 | -0.63462 | 0.69097 | -0.3743 | -0.2674 | 0.14976 | -0.51802 | -0.23521 | -0.049369 | 0.55492 | -0.046218
| 8445 | 0.3551 | 0.42043 | 0.80895 | -0.85269 | -0.42668 | 0.64293 | 0.44045 | 0.16101 | -0.05253 | 0.33871
| 8446 | -0.11949 | -0.4826 | 0.17896 | 0.19284 | 0.31582 | -0.15851 | -0.35015 | 0.06496 | 0.12816 | 0.3303
| 8447 | -0.21674 | 0.51492 | 0.27578 | 0.16639 | -0.044961 | 0.23312 | -0.23639 | 0.27 | -0.4902 | 0.49196
| 8448 | 0.32658 | 0.19074 | 0.13161 | -0.50776 | 0.14425 | 0.69917 | -0.53277 | 0.71312 | 0.40848 | 0.3607
| 8449 | -0.10541 | -0.006169 | -0.33179 | 0.6249 | 0.018114 | 0.049158 | -0.23391 | -0.64659 | 0.60821 | 0.40915
| 8450 | 0.012528 | -0.28649 | 0.1565 | 0.33539 | 0.25993 | 0.092641 | 0.08967 | 0.078534 | -0.19272 | -0.39759
| 8451 | 0.1957 | -0.45954 | 0.44224 | 0.10117 | 0.70725 | 0.59938 | -0.5806 | -0.10619 | -0.065388 | -0.059628
| 8452 | -0.46065 | 0.22547 | -0.17193 | 0.2488 | 0.44277 | 0.20987 | -0.20232 | -0.12828 | 0.35977 | -0.61751
| 8453 | 0.74761 | 0.20798 | 0.49592 | -0.19495 | 0.60289 | 0.078642 | 0.14566 | -0.064746 | -5.0001e-05 | -0.12233
| 8454 | 0.4471 | 0.15177 | -0.29339 | 0.38657 | -0.47665 | -0.20169 | 0.50918 | 0.32747 | -0.019847 | -0.86696
| 8455 | -0.071938 | -0.34601 | -0.068067 | -0.073663 | 0.44188 | -0.051264 | -0.98268 | -0.017809 | 0.11643 | -0.19607
| 8456 | -0.13346 | -0.15212 | 0.095954 | 0.30826 | -0.61856 | 0.081142 | 0.062397 | 0.035687 | -0.56861 | -0.063037
| 8457 | -0.12954 | 0.16591 | 0.56745 | 0.098279 | 0.17726 | -0.55111 | 0.14087 | 0.58012 | 0.39362 | -0.52682
| 8458 | -0.37927 | -0.00065021 | -0.78576 | -0.015978 | 0.031031 | 0.7488 | -0.036724 | 0.49256 | -0.3743 | -0.82139
| 8459 | -0.39312 | -0.19099 | 0.061864 | -0.26115 | -0.24973 | -0.57941 | -0.18018 | 0.148 | -0.076149 | 0.013947
| 8460 | 0.6349 | -0.16567 | -0.15071 | -0.17193 | 0.53707 | 0.44927 | 0.14613 | -0.26481 | -0.31392 | -0.54823
| 8461 | -0.15958 | 0.22948 | 0.35696 | -0.5011 | 0.042764 | -0.075608 | 0.075392 | 0.26007 | -0.89091 | 0.79
| 8462 | -0.61103 | 0.91815 | 0.21712 | 0.43653 | -0.53128 | 0.27206 | 0.39842 | 0.063998 | 0.79095 | -0.093303
| 8463 | -0.015267 | -0.094517 | -0.40544 | 0.14461 | 0.58684 | -0.46474 | -0.32598 | 0.24561 | -0.11938 | -0.075176
| 8464 | 0.30193 | -0.36778 | -0.16687 | 0.21076 | 0.13739 | -0.038283 | -0.26631 | -0.15768 | -0.60668 | -0.28803
| 8465 | -0.42285 | 0.54382 | 0.1432 | 0.25067 | -0.22922 | -0.22689 | -0.2893 | -0.26386 | 0.85474 | -0.66879
| 8466 | 0.47703 | -0.39626 | 0.24046 | -0.21584 | 0.25737 | -0.11451 | -0.80895 | 0.27123 | -0.18643 | -0.25374
| 8467 | 0.55582 | 0.036102 | 0.059202 | 0.70589 | -0.43018 | 0.40494 | 0.17532 | 0.24402 | 0.5608 | 0.08485
| 8468 | 0.38575 | -0.61361 | 0.57893 | -0.026398 | 0.15756 | 0.16316 | 0.24257 | -0.20181 | 0.26183 | 0.026707
| 8469 | -0.085287 | 0.23221 | -0.73411 | -0.94084 | -0.76063 | -0.39164 | -0.057609 | -0.078534 | -0.45991 | -0.1513
| 8470 | 0.4755 | -0.79095 | 0.33209 | 0.0047613 | -0.58781 | 0.013035 | -0.4531 | 0.08234 | -0.6703 | -0.24059
| 8471 | 0.0065716 | -0.050105 | 0.36196 | 0.17048 | 0.59491 | 0.83907 | 0.59763 | -0.6371 | -0.26767 | -0.50735
| 8472 | -0.53107 | 0.20571 | -0.072476 | -0.13276 | 0.13461 | -0.30552 | -0.46718 | 0.22495 | 0.4588 | -0.47798
| 8473 | -0.14624 | 0.63931 | 0.47588 | -0.15236 | 0.26318 | -0.16904 | -0.2256 | 0.42268 | 0.40477 | -0.19111
| 8474 | 0.26945 | -0.38202 | -0.082667 | -0.32037 | -0.34053 | 0.49315 | -0.38657 | -0.040886 | -0.4078 | 0.10764
| 8475 | -0.0041586 | 0.045589 | 0.020357 | -0.25818 | 0.42493 | 0.38267 | -0.18667 | -0.45695 | 0.067745 | -0.39659
| 8476 | -0.32243 | 0.0047613 | -0.37191 | 0.82252 | 0.14122 | 0.20395 | -0.31261 | -0.87 | 0.35541 | -0.039323
| 8477 | -0.18889 | -0.022401 | 0.057716 | 0.19272 | -0.9219 | 0.13496 | 0.035272 | 0.3074 | 0.73261 | 0.37302
| 8478 | -0.45018 | -0.10351 | -0.37767 | 0.55469 | 0.62784 | -0.73298 | 0.20798 | 0.83845 | -0.22225 | 0.030206
| 8479 | 0.17994 | 0.45182 | -0.39759 | 0.9245 | -0.0013509 | -0.65751 | -0.0052639 | -0.14344 | 0.29325 | -0.22792
| 8480 | 0.26196 | -0.044123 | -0.51616 | -0.2042 | 0.12587 | 0.047477 | 0.19136 | -0.14402 | -0.11202 | 0.55134
| 8481 | -0.28663 | -0.003456 | -0.18963 | -0.52619 | 0.3838 | -0.21917 | -0.67335 | -0.32243 | -0.2147 | 0.16496
| 8482 | 0.046533 | 0.26822 | 0.63 | 0.34892 | -0.53492 | 0.12496 | 0.036102 | 0.36921 | -0.78297 | -0.65722
| 8483 | -0.4392 | -0.10854 | 0.37207 | 0.037971 | -0.34327 | 0.027529 | 0.69983 | -0.29551 | -0.21063 | -0.17374
| 8484 | 0.32569 | 0.031444 | -0.75607 | 0.036517 | 0.66459 | 0.19161 | -0.6697 | -0.17302 | 0.54492 | -0.45219
| 8485 | -0.20207 | 0.84801 | -0.14215 | -0.053903 | 0.36778 | 0.054008 | -0.10563 | -0.24349 | -0.88381 | -0.025269
| 8486 | -0.55559 | 0.036932 | -0.087805 | 0.27274 | 0.16651 | -0.1957 | 0.051053 | 0.047477 | 0.19545 | 0.88731
| 8487 | -0.14379 | 0.083321 | 0.22844 | 0.59863 | 0.47379 | -0.4258 | 0.25107 | -0.39296 | -0.52429 | -0.2784
| 8488 | -0.48473 | 0.51595 | -0.34023 | 0.21635 | -0.55582 | 0.023834 | 0.019745 | -0.70555 | -0.32881 | -0.10373
| 8489 | 0.35262 | 0.035376 | -0.13253 | 0.73111 | 0.52957 | -0.1109 | 0.42668 | -0.35805 | 0.15994 | -0.28901
| 8490 | -0.20056 | 0.54404 | 0.55694 | -0.62119 | 0.16783 | 0.012934 | 0.66162 | 0.31436 | 0.68047 | -0.14099
| 8491 | -0.69162 | -0.24535 | 0.29566 | -0.42181 | 0.4337 | -0.02897 | 0.51287 | -0.47455 | -0.77262 | -0.064318
| 8492 | 0.29864 | -0.088024 | 0.063357 | -0.17302 | 0.04266 | 0.45861 | -0.19049 | -0.33434 | 0.10195 | 0.50452
| 8493 | 0.32554 | -0.20646 | 0.086162 | 0.6786 | 0.059415 | -0.2492 | 0.82536 | 0.33947 | 0.66221 | 0.23691
| 8494 | 0.62517 | 0.71698 | 0.26223 | -0.41187 | -0.44837 | 0.69324 | -0.54229 | 0.6382 | -0.11067 | -0.15425
| 8495 | 0.13357 | 0.47971 | 0.036413 | 0.55067 | 0.13092 | 0.073555 | -0.099056 | 0.19 | 0.18263 | -0.11847
| 8496 | -0.13127 | 0.29325 | 0.54514 | 0.30523 | -0.012528 | 0.66909 | 0.35463 | 0.24973 | -0.38771 | -0.252
| 8497 | -0.68016 | -0.024039 | 0.11518 | 0.11507 | -0.019745 | -0.3629 | 0.7488 | -0.23678 | -0.13219 | 0.03579
| 8498 | -0.8148 | -0.73111 | 0.57491 | -0.35556 | 0.53171 | -0.036724 | 0.79433 | 0.099944 | -0.29637 | -0.16831
| 8499 | -0.31145 | -0.87793 | -0.40309 | -0.44421 | -0.46906 | -0.14425 | -0.58467 | 0.2958 | -0.41682 | -0.12473
| 8500 | 0.23862 | 0.026193 | -0.56194 | -0.18938 | -0.016994 | -0.72852 | 0.40915 | -0.34985 | 0.32672 | 0.55267
| 8501 | -0.27744 | -0.0053644 | 0.4272 | 0.75 | 0.082776 | -0.006169 | 0.39345 | 0.2512 | 0.32762 | -0.16292
| 8502 | 0.39726 | 0.13461 | 0.46774 | -0.27647 | 0.099278 | -0.10039 | 0.029176 | -0.26836 | -0.17471 | 0.57491
| 8503 | -0.082449 | -0.33902 | -0.15567 | 0.17909 | 0.43141 | 0.59171 | 0.11011 | 0.61699 | 0.3956 | -0.2659
| 8504 | 0.12313 | 0.3038 | -0.79095 | -0.21432 | -0.48087 | 0.28383 | 0.12599 | 0.025167 | -0.26223 | 0.16424
| 8505 | -0.71982 | 0.4337 | -0.55559 | 0.35587 | -0.57822 | -0.17181 | 0.062717 | 0.79975 | 0.068388 | 0.42268
| 8506 | 0.58976 | -0.16543 | -0.13461 | 0.14496 | -0.75201 | -0.24257 | -0.53816 | -0.68456 | -0.68775 | 0.15531
| 8507 | 0.071614 | -0.17447 | 0.70555 | -0.31363 | -0.11824 | -0.37831 | -0.12725 | -0.10596 | 0.32776 | 0.64293
| 8508 | -0.70318 | -0.20735 | -0.12131 | -0.46158 | 0.015978 | -0.29694 | -0.47971 | 0.1646 | 0.08649 | 0.3454
| 8509 | 0.77572 | 0.58036 | -0.76188 | 0.29056 | 0.85474 | 0.049684 | 0.23862 | -0.051791 | -0.025167 | 0.093413
| 8510 | -0.33149 | -0.086381 | 0.55582 | 0.42546 | -0.20848 | -0.099278 | 0.056549 | -0.90253 | -0.010202 | -0.17629
| 8511 | -0.83783 | 0.071184 | -0.21904 | 0.4078 | -0.55402 | 0.85201 | 0.16328 | 0.086271 | 0.13449 | -0.72705
| 8512 | 0.62171 | 0.018318 | 0.74251 | -0.13716 | 0.54867 | 0.36889 | 0.78905 | 0.18729 | 0.52682 | -0.4408
| 8513 | -0.50796 | 0.90461 | -0.18655 | 0.37462 | -0.86472 | 0.22444 | -0.24707 | -0.5529 | -0.10664 | -0.083321
| 8514 | -0.37127 | -0.078642 | -0.065709 | 0.38332 | -0.11248 | 0.23534 | 0.80481 | -0.38332 | 0.40932 | 0.073231
| 8515 | 0.67121 | -0.026398 | 0.51164 | 0.13588 | 0.25549 | 0.061437 | -0.52597 | 0.32806 | -0.17909 | 0.60063
| 8516 | -0.38105 | 0.033925 | -0.35727 | 0.65345 | 0.01344 | -0.19086 | 0.32199 | -0.063998 | -0.23954 | -0.59664
| 8517 | -0.048527 | -0.58636 | 0.36305 | 0.52555 | 0.25468 | 0.30207 | -0.41085 | -0.48922 | -0.70623 | -0.78529
| 8518 | -0.13057 | -0.034133 | -0.77 | 0.078534 | -0.062823 | -0.44511 | 0.14788 | 0.42251 | -0.14753 | 0.79678
| 8519 | -0.14157 | 0.13866 | -0.11372 | -0.48357 | -0.36211 | 0.1863 | 0.48863 | -0.49216 | -0.43105 | 0.042451
| 8520 | -0.35572 | -0.010707 | 0.065816 | -0.10574 | 0.048212 | -0.21013 | 0.67121 | 0.61387 | 0.51225 | -0.15472
| 8521 | 0.28537 | 0.11835 | -0.7496 | 0.1706 | -0.36952 | 0.46195 | 0.39312 | 0.83538 | 0.29637 | 0.10787
| 8522 | -0.62013 | -0.097171 | -0.2784 | 0.41289 | 0.11677 | -0.37927 | 0.41017 | 0.55762 | -0.55134 | -0.83177
| 8523 | 0.44601 | -0.59024 | -0.92063 | -0.42685 | -0.37318 | -0.16185 | 0.14052 | -0.72632 | -0.1786 | 0.11643
| 8524 | 0.30122 | -0.66459 | 0.39378 | 0.43902 | -0.096064 | -0.28509 | -0.55067 | 0.37799 | 0.32406 | 0.65373
| 8525 | -0.087914 | -0.2488 | -0.88642 | -0.17836 | -0.21063 | -0.069892 | 0.49493 | 0.1513 | 0.19359 | 0.050842
| 8526 | -0.37111 | 0.21533 | -0.018318 | -0.27385 | -0.043391 | 0.39792 | -0.68775 | -0.11938 | -0.53085 | 0.030619
| 8527 | -0.03579 | 0.071507 | -0.16089 | 0.12404 | -0.076474 | -0.83059 | -0.11609 | 0.083649 | 0.63462 | -0.48785
| 8528 | -0.076041 | -0.52767 | 0.41836 | -0.76104 | -0.2948 | 0.04026 | 0.23809 | -0.01547 | 0.078534 | 0.039531
| 8529 | 0.17326 | 0.48338 | -0.13901 | 0.50472 | 0.13983 | -0.1292 | 0.089451 | 0.12233 | -0.81159 | 0.098834
| 8530 | -0.16412 | 0.25267 | 0.080489 | 0.33962 | 0.30567 | 0.22032 | -0.5583 | 0.065495 | 0.31363 | 0.48668
| 8531 | -0.32022 | -0.16173 | -0.023117 | -0.054749 | -0.32791 | -0.29594 | 0.35758 | -0.3804 | -0.52136 | 0.073555
| 8532 | 0.31131 | -0.53449 | 0.40494 | -0.63271 | -0.20495 | -0.13138 | 0.044437 | -0.083212 | 0.042973 | 0.092311
| 8533 | 0.08234 | 0.37143 | 0.063998 | -0.11225 | -0.44313 | 0.81862 | 0.29169 | 0.75772 | 0.072908 | 0.59294
| 8534 | -0.2488 | 0.13242 | 0.43211 | -0.65373 | 0.16567 | -0.47971 | -0.72486 | 0.21635 | 0.61412 | 0.61438
| 8535 | -0.28551 | 0.60592 | 0.70487 | 0.1735 | -0.21051 | -0.47208 | 0.083321 | -0.10608 | -0.64237 | 0.30365
| 8536 | -0.67458 | 0.55559 | -0.12851 | -0.0995 | 0.45328 | -0.53881 | 0.2184 | 0.17447 | -0.85405 | 0.15047
| 8537 | -0.0755 | -0.76021 | 0.88042 | 0.18951 | 0.33419 | 0.26849 | 0.71663 | -0.48202 | 0.0043595 | -0.3357
| 8538 | -0.17145 | -0.075716 | 0.39676 | 0.01091 | -0.69586 | 0.38153 | -0.15911 | 0.024449 | 0.10261 | -0.5347
| 8539 | -0.17241 | -0.54316 | 0.12473 | -0.42372 | -0.26849 | -0.042451 | 0.76527 | -0.73111 | -0.11022 | 0.4134
| 8540 | -0.33524 | -0.45347 | -0.51906 | 0.48765 | 0.17605 | 0.77262 | -0.65402 | -0.37175 | 0.33164 | 0.31087
| 8541 | -0.31626 | -0.47626 | -0.52661 | 0.53513 | 0.39742 | -0.55627 | 0.39148 | 0.51492 | 0.51348 | -0.44837
| 8542 | 0.20119 | -0.071614 | -0.39626 | -0.4989 | 0.5866 | -0.089121 | -0.19595 | -0.38153 | 0.42546 | 0.38885
| 8543 | 0.60013 | -0.15472 | -0.81972 | 0.33254 | 0.2431 | 0.048002 | 0.51102 | -0.13878 | 0.05549 | -0.1729
| 8544 | 0.58275 | -0.36463 | 0.56057 | -0.59196 | -0.73261 | 0.46251 | -0.43211 | 0.0057666 | 0.1646 | 0.25281
| 8545 | 0.33494 | 0.44818 | 0.29807 | -0.3851 | -0.1015 | -0.26658 | -0.45146 | -0.29608 | 0.12097 | 0.0062697
| 8546 | -0.31846 | 0.4344 | 0.65839 | 0.065709 | 0.7623 | 0.67396 | 0.015978 | 0.1015 | -0.21559 | -0.69488
| 8547 | -0.00025003 | 0.34892 | 0.2893 | -0.35634 | 0.87077 | -0.043914 | -0.096064 | 0.55447 | -0.24614 | 0.52767
| 8548 | -0.17447 | 0.026398 | -0.38689 | 0.38526 | 0.086162 | 0.025269 | 0.80584 | 0.21789 | -0.010808 | -0.22637
| 8549 | 0.46661 | -0.22961 | 0.24033 | 0.13438 | 0.28986 | -0.62437 | -0.09132 | 0.033615 | 0.57303 | -0.25535
| 8550 | 0.28216 | -0.23351 | -0.24707 | 0.29438 | 0.15567 | 0.85337 | -0.1825 | 0.08978 | -0.11439 | -0.1292
| 8551 | -0.2119 | 0.59913 | -0.059628 | -0.09165 | 0.45511 | -0.2047 | -0.67984 | 0.82139 | -0.046008 | 0.34023
| 8552 | -0.71312 | 0.55335 | 0.43777 | -0.26986 | -0.66758 | 0.32228 | -0.025372 | -0.014759 | 0.031857 | -0.70828
| 8553 | 0.4983 | 0.62304 | -0.52094 | -0.4776 | -0.57656 | -0.21661 | 0.75161 | -0.33374 | 0.85337 | 0.62224
| 8554 | -0.031444 | 0.10485 | 0.23862 | -0.014962 | -0.54448 | 0.23587 | -0.15283 | 0.29099 | -0.27799 | -0.52745
| 8555 | -0.2193 | 0.41699 | 0.71208 | 0.16328 | 0.61361 | -0.055807 | 0.39859 | 0.031651 | -0.04026 | 0.6241
| 8556 | 0.16555 | -0.53171 | 0.14706 | -0.62066 | -0.35077 | -0.33419 | -0.049158 | -0.053903 | -0.8467 | 0.42546
| 8557 | -0.27069 | -0.068388 | -0.12256 | -0.6407 | 0.91 | 0.49532 | 0.60974 | 0.11552 | -0.35852 | -0.59122
| 8558 | -0.016893 | 0.50392 | 0.34403 | 0.19173 | -0.43724 | -0.15472 | 0.18901 | -0.11801 | -0.33539 | -0.06016
| 8559 | 0.076366 | -0.1418 | 0.25562 | 0.60795 | 0.15365 | 0.45843 | 0.12393 | -0.19869 | 0.041407 | -0.13322
| 8560 | -0.39792 | 0.20722 | 0.43973 | 0.50878 | 0.47038 | -0.18963 | 0.50796 | 0.63299 | -0.68839 | -0.53902
| 8561 | 0.050316 | 0.17278 | 0.010606 | -0.19944 | -0.095732 | -0.44063 | 0.44529 | 0.30913 | 0.068603 | 0.08978
| 8562 | -0.36149 | -0.25254 | 0.58733 | 0.046113 | 0.24283 | -0.60465 | -0.10899 | 0.35278 | -0.31568 | 0.16723
| 8563 | 0.15697 | 0.064746 | -0.38608 | 0.21127 | -0.55694 | 0.32925 | 0.063998 | -0.04538 | -0.4206 | -0.39494
| 8564 | 0.24707 | -0.25321 | -0.42528 | -0.31 | 0.38787 | 0.55357 | -0.36384 | 0.14542 | 0.31102 | -0.18201
| 8565 | 0.68235 | -0.34908 | 0.018623 | 0.2784 | 0.21063 | 0.38575 | 0.68583 | -0.39742 | 0.24165 | -0.28007
| 8566 | 0.11847 | -0.21368 | 0.31978 | -0.10742 | -0.53707 | -0.10574 | -0.78622 | -0.21292 | 0.013542 | -0.5007
| 8567 | 0.22238 | -0.36826 | 0.28958 | 0.09 | 0.14099 | -0.049053 | 0.50371 | -0.02609 | 0.19906 | 0.034236
| 8568 | 0.25053 | 0.59515 | 0.20131 | 0.032374 | -0.029485 | -0.33811 | 0.14145 | 0.47722 | 0.30884 | -0.27938
| 8569 | -0.052319 | 0.11236 | 0.17302 | -0.13138 | 0.068174 | 0.64971 | 0.37064 | 0.50918 | -0.12862 | 0.31276
| 8570 | -0.15839 | -0.28916 | 0.11315 | 0.17265 | -0.056231 | -0.54624 | 0.46512 | -0.17872 | 0.45383 | 0.12416
| 8571 | -0.21878 | -0.22418 | -0.42877 | -0.27426 | -0.2524 | 0.14589 | 0.076582 | -0.32066 | -0.58419 | -0.30986
| 8572 | 0.48609 | 0.26617 | 0.69422 | -0.52261 | -0.27467 | -0.054008 | 0.84094 | -0.18951 | 0.41153 | -0.63462
| 8573 | 0.6265 | 0.33374 | 0.64349 | -0.54845 | -0.09209 | -0.16507 | 0.32985 | -0.47703 | 0.15365 | 0.31772
| 8574 | 0.02609 | -0.080163 | 0.1025 | 0.6811 | 0.73866 | 0.13473 | 0.45658 | 0.59614 | -0.62119 | -0.099944
| 8575 | -0.21955 | -0.11338 | 0.3735 | -0.077016 | -0.25831 | 0.19757 | -0.77483 | 0.35247 | 0.28916 | 0.14566
| 8576 | -0.0911 | -0.81642 | 0.51575 | 0.3306 | -0.050316 | 0.053058 | 0.4857 | 0.60364 | 0.69784 | 0.14041
| 8577 | 0.43141 | 0.53256 | -0.038803 | 0.034443 | -0.31743 | 0.53385 | -0.66909 | -0.25791 | 0.16699 | 0.15425
| 8578 | -0.2431 | 0.28467 | -0.04172 | 0.63517 | -0.18753 | -0.27343 | 0.44927 | 0.054431 | 0.16101 | 0.2602
| 8579 | 0.18594 | -0.44728 | 0.077449 | 0.74329 | -0.24522 | -0.009899 | 0.39296 | 0.48746 | -0.14941 | -0.2512
| 8580 | 0.19198 | 0.3751 | -0.85201 | 0.7881 | -0.16627 | -0.49354 | -0.39098 | -0.40075 | -0.10608 | -0.21917
| 8581 | 0.26373 | -0.1879 | 0.41494 | 0.48726 | 0.17217 | -0.45972 | -0.24086 | -0.90461 | -0.12199 | -0.009596
| 8582 | 0.30007 | 0.034029 | 0.30308 | -0.30581 | 0.68047 | -0.10239 | -0.32066 | -0.37462 | 0.52597 | -0.58179
| 8583 | 0.27426 | 0.38478 | -0.076582 | 0.30136 | -0.11011 | 0.085287 | 0.50432 | -0.045275 | -0.003456 | 0.44367
| 8584 | 0.75566 | -0.24469 | -0.32066 | -0.2234 | -0.049369 | -0.30207 | -0.83237 | 0.29183 | 0.30667 | 0.68361
| 8585 | -0.77617 | 0.52387 | -0.52809 | 0.56216 | -0.39395 | -0.42563 | -0.42129 | -0.14589 | -0.86108 | -0.36196
| 8586 | 0.61438 | -0.052424 | -0.063891 | -0.0015512 | -0.16579 | -0.097614 | 0.22289 | 0.36415 | 0.536 | 0.72018
| 8587 | 0.17048 | -0.54273 | 0.66578 | -0.59098 | 0.19136 | 0.026809 | 0.1559 | -0.3751 | 0.55989 | 0.5412
| 8588 | 0.36699 | -0.46718 | -0.2225 | -0.22857 | 0.44063 | -0.11326 | -0.52094 | 0.82479 | -0.044228 | -0.6985
| 8589 | 0.35448 | 0.075284 | 0.68361 | 0.48241 | -0.14519 | 0.25723 | 0.046323 | 0.34586 | 0.15531 | 0.24721
| 8590 | 0.098612 | -0.26291 | 0.25482 | 0.90673 | 0.48941 | -0.36117 | -0.44367 | 0.30193 | 0.2042 | 0.37048
| 8591 | -0.082013 | -0.18914 | 0.61829 | 0.29637 | -0.59838 | -0.38526 | 0.29993 | -0.18508 | -0.040782 | 0.65547
| 8592 | -0.056443 | 0.26427 | 0.57327 | -0.13774 | -0.57163 | 0.81534 | 0.40494 | -0.37815 | -0.093744 | -0.11225
| 8593 | 0.17229 | -0.034858 | -0.13727 | 0.57023 | -0.12142 | 0.054643 | 0.14006 | 0.24059 | -0.65722 | -0.36604
| 8594 | -0.056761 | -0.10989 | -0.70828 | -0.56606 | -0.33932 | 0.34388 | 0.43777 | -0.031857 | 0.0047613 | 0.80843
| 8595 | -0.5458 | 0.14461 | 0.85613 | 0.083976 | -0.53967 | 0.43387 | -0.50271 | 0.40008 | 0.11994 | 0.59343
| 8596 | 0.58323 | -0.011112 | 0.67766 | -0.50715 | -0.1841 | -0.0016514 | 0.23299 | -0.38787 | 0.60567 | 0.2893
| 8597 | -0.39345 | -0.094959 | 0.59988 | -0.23508 | 0.24257 | 0.17592 | -0.52429 | -0.55853 | 0.28285 | 0.71138
| 8598 | 0.048948 | 0.82308 | -0.26767 | 0.56977 | 0.42598 | -0.21687 | 0.5013 | -0.31276 | -0.26237 | -0.23117
| 8599 | 0.7429 | -0.48687 | 0.70352 | -0.81372 | -0.85201 | 0.76741 | -0.4983 | 0.11112 | 0.29779 | 0.47818
| 8600 | -0.12063 | -0.23521 | -0.16543 | 0.3568 | -0.26863 | 0.0077803 | -0.83477 | -0.19669 | 0.051264 | 0.09088
| 8601 | -0.88126 | -0.16699 | 0.26088 | -0.49751 | 0.33675 | 0.32985 | -0.45954 | 0.76741 | -0.55694 | -0.01263
| 8602 | 0.080816 | -0.53213 | -0.0173 | -0.15875 | 0.45824 | -0.19495 | 0.15982 | 0.60339 | -0.10563 | -0.3015
| 8603 | 0.54033 | -0.04099 | -0.53772 | 0.34174 | -0.31465 | 0.58155 | 0.28104 | 0.60263 | 0.55447 | 0.1261
| 8604 | -0.23482 | 0.56653 | 0.15792 | 0.73074 | -0.23809 | 0.63135 | -0.34357 | -0.052952 | 0.34433 | -0.35432
| 8605 | -0.41957 | 0.070323 | -0.2431 | -0.12359 | 0.72523 | -0.2575 | 0.032477 | -0.53578 | 0.44295 | 0.073124
| 8606 | -0.32494 | -0.43211 | -0.20684 | -0.39892 | -0.02281 | -0.66578 | 0.53686 | -0.73335 | -0.72414 | -0.36905
| 8607 | 0.21712 | 0.00075028 | 0.10585 | -0.19136 | 0.40763 | 0.53989 | -0.65897 | -0.016791 | -0.36968 | 0.042973
| 8608 | 0.14169 | -0.40713 | -0.23299 | -0.071614 | -0.072584 | -0.68711 | -0.44873 | -0.66819 | 0.24257 | 0.012731
| 8609 | 0.10306 | -0.37751 | 0.021583 | -0.12416 | -0.68141 | -0.39345 | -0.092421 | 0.39263 | -0.29311 | 0.16783
| 8610 | -0.14906 | 0.010404 | -0.17677 | -0.37446 | -0.28537 | 0.55943 | -0.70657 | 0.20709 | -0.038179 | 0.51205
| 8611 | 0.13959 | 0.32628 | -0.10652 | -0.43671 | -0.037347 | -0.47379 | -0.064105 | -0.67427 | 0.33917 | -0.14461
| 8612 | 0.16735 | -0.1957 | 0.27951 | 0.32732 | -0.20119 | -0.81752 | -0.22328 | -0.52366 | 0.01182 | -0.12359
| 8613 | 0.17193 | 0.32687 | 0.11304 | -0.83417 | 0.14953 | -0.30136 | 0.65605 | 0.36762 | 0.32022 | 0.13346
| 8614 | -0.22122 | -0.057928 | 0.10195 | -0.28859 | -0.82139 | 0.15094 | -0.61725 | -0.34388 | -0.16747 | -0.11045
| 8615 | -0.2784 | -0.11983 | -0.49334 | -0.21917 | 0.69983 | 0.39246 | -0.79925 | -0.45237 | 0.36636 | -0.095843
| 8616 | 0.50654 | 0.49711 | 0.37526 | 0.06957 | -0.30466 | -0.50817 | 0.4683 | 0.0076795 | 0.67953 | -0.015165
| 8617 | 0.6162 | -0.70217 | -0.16771 | 0.14624 | 0.60415 | 0.23195 | 0.59466 | 0.0020521 | -0.074743 | 0.77796
| 8618 | 0.42877 | 0.23117 | 0.15768 | -0.44331 | -0.061118 | 0.077124 | -0.45073 | 0.39345 | -0.052424 | -0.17338
| 8619 | 0.26877 | -0.38559 | 0.20332 | -0.4134 | 0.34083 | -0.61103 | -0.26836 | -0.20861 | -0.42633 | 0.056019
| 8620 | 0.0082843 | 0.50715 | -0.34938 | 0.0046609 | -0.32169 | -0.018012 | -0.15236 | -0.49 | -0.38429 | -0.016893
| 8621 | -0.5019 | 0.48843 | 0.37622 | -0.18753 | 0.49059 | 0.42965 | -0.038803 | -0.52597 | -0.44367 | 0.04381
| 8622 | -0.32096 | -0.27385 | 0.22586 | 0.60138 | 0.22844 | 0.45292 | 0.31846 | 0.56194 | -0.35 | 0.86546
| 8623 | 0.073987 | 0.39958 | -0.54273 | 0.15153 | 0.20823 | 0.15567 | 0.69259 | 0.21419 | 0.44982 | 0.35247
| 8624 | 0.23495 | -0.040365 | 0.29381 | 0.5707 | 0.67335 | 0.064532 | 0.5017 | 0.31743 | -0.10507 | 0.10686
| 8625 | 0.0072765 | -0.36337 | -0.30639 | -0.27785 | -0.44457 | 0.21393 | -0.28621 | 0.02794 | 0.072153 | 0.4902
| 8626 | -0.88295 | 0.16054 | -0.65402 | -0.62304 | 0.37239 | -0.18128 | 0.32866 | 0.14929 | -0.76104 | 0.26115
| 8627 | -0.051897 | 0.17338 | -0.095732 | -0.35262 | -0.88909 | 0.90673 | 0.29864 | 0.40443 | -0.19744 | 0.30495
| 8628 | -0.61961 | 0.14671 | 0.4344 | -0.26686 | -0.5922 | 0.55582 | 0.53342 | 0.60949 | 0.35108 | 0.45127
| 8629 | -0.47132 | 0.33479 | -0.46474 | 0.36321 | -0.16783 | -0.4776 | 0.21648 | -0.88467 | 0.013643 | 0.32155
| 8630 | 0.18951 | -0.82536 | 0.10933 | 0.63737 | -0.2941 | -0.364 | 0.12943 | 0.09022 | 0.69065 | -0.044437
| 8631 | 0.50817 | 0.26318 | 0.18815 | -0.47703 | 0.077016 | -0.80176 | -0.47474 | 0.77662 | -0.15401 | 0.25912
| 8632 | -0.46381 | -0.17848 | 0.6241 | -0.14671 | 0.5199 | 0.41119 | -0.097393 | -0.20772 | 0.60491 | 0.031031
| 8633 | 0.42825 | 0.73866 | 0.0028541 | -0.67182 | 0.083976 | 0.54933 | -0.13797 | -0.38951 | 0.76741 | -0.13855
| 8634 | -0.15638 | -0.09695 | -0.19919 | 0.012022 | -0.28439 | 0.18238 | -0.059947 | 0.23338 | 0.12119 | 0.0039578
| 8635 | -0.16388 | 0.12108 | 0.26631 | 0.033718 | 0.00085036 | -0.1308 | -0.63654 | -0.022094 | 0.018623 | -0.43564
| 8636 | 0.81212 | -0.49157 | -0.23208 | -0.61987 | 0.29099 | -0.17665 | 0.41255 | 0.11926 | -0.071507 | -0.42043
| 8637 | 0.57727 | -0.42441 | 0.33149 | -0.22431 | -0.16519 | 0.55627 | 0.053691 | 0.41425 | -0.0067729 | 0.21368
| 8638 | -0.023015 | 0.40679 | -0.57257 | -0.075176 | -0.48454 | 0.47474 | -0.47284 | -0.71804 | 0.11326 | 0.16747
| 8639 | 0.076474 | 0.88381 | -0.52936 | -0.44116 | -0.50614 | 0.42078 | -0.065388 | 0.033098 | -0.20282 | -0.12644
| 8640 | 0.10865 | 0.52619 | 0.24548 | -0.074527 | 0.26631 | 0.51143 | -0.22728 | -0.13994 | -0.92859 | 0.2133
| 8641 | -0.3838 | 0.21419 | -0.33977 | 0.62437 | -0.1162 | 0.44547 | 0.089561 | -0.4265 | -0.19994 | -0.040365
| 8642 | -0.19931 | 0.44927 | -0.08989 | -0.31218 | 0.18104 | -0.55672 | 0.30653 | 0.089012 | -0.027015 | -0.058777
| 8643 | 0.12576 | -0.28104 | 0.13253 | -0.73149 | 0.26617 | -0.22418 | 0.10619 | 0.42598 | -0.18299 | -0.23836
| 8644 | -0.40042 | 0.34388 | -0.14941 | -0.49137 | -0.0094951 | -0.5714 | 0.02568 | -0.58636 | 0.074959 | -0.39428
| 8645 | -0.062717 | -0.26699 | 0.49196 | -0.264 | -0.42615 | -0.37718 | -0.28146 | -0.075284 | 0.63108 | -0.23783
| 8646 | -0.41238 | 0.57846 | 0.34129 | -0.448 | -0.13496 | 0.55312 | 0.069892 | -0.37542 | -0.063357 | 0.40561
| 8647 | 0.34266 | 0.10798 | 0.38202 | 0.097614 | 0.11733 | 0.24429 | -0.48512 | 0.2985 | 0.56262 | 0.088902
| 8648 | 0.17024 | -0.40159 | -0.5003 | -0.2081 | -0.41871 | 0.17181 | -0.83297 | -0.51123 | -0.54229 | 0.72305
| 8649 | -0.31524 | -0.77707 | 0.31553 | -0.73789 | -0.3477 | -0.47227 | 0.33105 | -0.10496 | 0.31422 | 0.12851
| 8650 | -0.47952 | -0.29113 | 0.18766 | -0.15118 | -0.16089 | -0.27385 | 0.19595 | -0.57988 | 0.6811 | 0.050948
| 8651 | -0.35077 | -0.45237 | -0.1063 | -0.77262 | -0.63163 | -0.53902 | -0.044019 | 0.64433 | -0.084522 | -0.049053
| 8652 | 0.6852 | -0.66668 | -0.59024 | 0.09198 | 0.42807 | -0.2427 | 0.1688 | 0.05814 | -0.22534 | -0.58854
| 8653 | 0.12267 | 0.24244 | -0.076799 | -0.23521 | 0.54098 | -0.17787 | 0.010101 | -0.10117 | 0.56954 | 0.066137
| 8654 | -0.060372 | 0.48726 | -0.58491 | -0.096175 | 0.094627 | -0.57988 | 0.58299 | 0.53794 | 0.29566 | 0.17145
| 8655 | -0.45824 | 0.30365 | 0.08474 | -0.76741 | -0.78483 | -0.60744 | -0.84476 | 0.81588 | -0.5143 | 0.20483
| 8656 | 0.2076 | -0.73866 | 0.35852 | -0.22469 | 0.37799 | 0.45146 | 0.89091 | 0.11349 | -0.27412 | 0.17836
| 8657 | -0.36102 | -0.32081 | 0.11756 | 0.31846 | 0.25187 | 0.4344 | 0.40427 | 0.1957 | -0.1466 | -0.77218
| 8658 | -0.33766 | 0.60013 | 0.20508 | 0.13069 | 0.57491 | -0.2184 | 0.076041 | 0.47933 | 0.58612 | 0.25254
| 8659 | -0.41545 | -0.081469 | -0.00095045 | 0.80025 | -0.33224 | 0.29537 | -0.78669 | -0.065067 | -0.49295 | 0.11112
| 8660 | 0.39164 | -0.66281 | -0.076474 | 0.31524 | 0.45273 | 0.24191 | -0.1025 | 0.045799 | -0.0056661 | 0.30653
| 8661 | 0.20382 | 0.09099 | 0.036205 | -0.43848 | -0.13866 | 0.56308 | 0.20508 | 0.18643 | -0.072045 | 0.41442
| 8662 | -0.21393 | -0.12097 | 0.2689 | -0.21013 | -0.15012 | -0.11011 | 0.11439 | 0.70555 | -0.28257 | 0.78251
| 8663 | 0.20709 | -0.50573 | 0.025372 | 0.35386 | -0.10351 | -0.036517 | -0.17726 | -0.56745 | 0.14824 | -0.13403
| 8664 | 0.70828 | 0.092421 | 0.12839 | 0.47455 | -0.34601 | -0.44656 | 0.58781 | -0.61361 | -0.60541 | -0.40729
| 8665 | 0.32361 | 0.24283 | -0.006169 | 0.020766 | -0.58636 | 0.76021 | 0.47779 | 0.35836 | -0.2575 | 0.023015
| 8666 | 0.48863 | -0.79531 | -0.72632 | -0.0039578 | 0.032581 | -0.12851 | -0.028661 | -0.048317 | -0.062077 | 0.67984
| 8667 | -0.072261 | -0.25468 | 0.073016 | -0.23862 | -0.42285 | 0.22456 | 0.25495 | 0.16244 | 0.13115 | -0.28341
| 8668 | 0.53621 | 0.49731 | -0.062503 | 0.68488 | 0.16161 | -0.010606 | 0.015368 | -0.32925 | 0.55627 | -0.5021
| 8669 | 0.11484 | 0.081577 | -0.062183 | -0.073555 | -0.50371 | 0.11643 | 0.1825 | -0.092972 | 0.4392 | -0.15484
| 8670 | -0.47607 | -0.12839 | -0.76272 | -0.71312 | 0.22122 | 0.13681 | 0.71242 | 0.93144 | -0.47474 | 0.16304
| 8671 | -0.50735 | -0.61987 | -0.0044599 | -0.6631 | -0.3767 | 0.40814 | -0.3751 | -0.48473 | -0.17811 | -0.33539
| 8672 | 0.067959 | -0.41648 | 0.34632 | 0.3629 | 0.32184 | 0.14332 | 0.54867 | -0.012934 | 0.37558 | 0.76569
| 8673 | -0.53621 | 0.15283 | -0.15899 | -0.08967 | -0.34985 | -0.064318 | -0.31978 | -0.09044 | 0.31058 | 0.028352
| 8674 | 0.018216 | 0.44674 | 0.68047 | -0.36826 | 0.61934 | 0.21968 | 0.024756 | 0.39197 | 0.023936 | -0.032477
| 8675 | 0.33015 | -0.28565 | 0.26877 | -0.9219 | -0.13936 | 0.040052 | -0.62784 | 0.47684 | 0.40359 | -0.27633
| 8676 | -0.037971 | -0.82028 | -0.22456 | -0.60643 | 0.47208 | 0.14894 | -0.31904 | -0.14531 | 0.24125 | 0.52115
| 8677 | -0.039635 | 0.26088 | -0.56838 | 0.69455 | 0.13346 | 0.50756 | -0.11146 | 0.35587 | 0.18717 | -0.13577
| 8678 | -0.063677 | 0.77887 | -0.24973 | -0.42772 | 0.25804 | 0.44674 | -0.60038 | 0.39016 | -0.32866 | -0.4776
| 8679 | -0.32925 | 0.59122 | 0.41119 | -0.3419 | 0.3015 | -0.52387 | -0.16077 | -0.15531 | -0.037659 | 0.46437
| 8680 | -0.23744 | 0.12541 | 0.25953 | 0.55111 | -0.55022 | -0.2744 | 0.20382 | 0.1237 | 0.12108 | 0.33992
| 8681 | -0.93292 | 0.76957 | 0.45769 | 0.60923 | 0.67 | -0.087476 | 0.28747 | 0.14204 | 0.38836 | 0.026501
| 8682 | -0.2575 | -0.80481 | -0.24787 | -0.36227 | -0.31407 | -0.2598 | -0.22961 | 0.2602 | 0.02568 | 0.38315
| 8683 | -0.22741 | 0.76827 | 0.36337 | -0.36557 | 0.69422 | 0.56977 | 0.48824 | 0.37751 | 0.24973 | -0.36039
| 8684 | -0.18067 | 0.15212 | -0.67243 | 0.063464 | 0.051791 | -0.43423 | 0.22909 | 0.37686 | -0.08485 | 0.10585
| 8685 | -0.62784 | -0.45036 | 0.27813 | 0.40763 | -0.31131 | -0.71663 | -0.57774 | 0.76527 | -0.25307 | -0.33962
| 8686 | -0.71242 | -0.28063 | -0.65029 | 0.17945 | 0.5806 | -0.28007 | 0.32051 | 0.17848 | -0.008486 | 0.32022
| 8687 | 0.45991 | 0.33811 | 0.40376 | -0.38608 | 0.54207 | -0.11767 | -0.26047 | 0.060479 | -0.18618 | -0.74525
| 8688 | -0.3357 | -0.57869 | 0.22482 | 0.15059 | -0.47076 | 0.34739 | 0.86472 | 0.14122 | 0.12576 | 0.4553
| 8689 | 0.55 | 0.08485 | -0.060053 | 0.3767 | -0.8821 | -0.36337 | 0.38967 | -0.24125 | 0.31073 | 0.50695
| 8690 | 0.68647 | -0.69324 | 0.33344 | 0.73 | 0.084522 | -0.24455 | 0.63848 | -0.48882 | 0.22405 | -0.43387
| 8691 | 0.30754 | 0.64772 | -0.0086877 | -0.028455 | 0.44403 | -0.55357 | 0.14965 | -0.42772 | -0.033925 | 0.075825
| 8692 | 0.14812 | 0.41648 | -0.29197 | -0.36968 | 0.11124 | 0.47914 | -0.91225 | -0.5883 | 0.80532 | -0.25831
| 8693 | 0.63408 | -0.50533 | -0.39709 | -0.72486 | -0.17775 | -0.34662 | -0.48048 | 0.15389 | -0.058565 | -0.069677
| 8694 | 0.052741 | 0.71347 | -0.43158 | 0.13 | 0.022606 | 0.2081 | 0.17048 | -0.20975 | 0.067852 | -0.18226
| 8695 | 0.46102 | -0.30265 | 0.22045 | -0.17714 | 0.8755 | 0.43902 | -0.045904 | 0.25441 | -0.050421 | -0.17568
| 8696 | -0.0033556 | -0.64886 | -0.17556 | -0.0054649 | -0.14367 | 0.19334 | -0.9134 | 0.4799 | 0.51575 | -0.62357
| 8697 | 0.16125 | -0.064425 | 0.061437 | 0.64237 | -0.33464 | 0.2076 | 0.47588 | -0.34311 | -0.025782 | 0.42078
| 8698 | -0.016079 | 0.042973 | 0.40477 | -0.09044 | -0.11926 | -0.61856 | -0.28397 | -0.30957 | 0.47971 | -0.31276
| 8699 | -0.077124 | -0.20319 | 0.40915 | 0.24667 | -0.19111 | -0.24482 | 0.23078 | 0.50817 | 0.010808 | -0.067637
| 8700 | 0.46083 | -0.012731 | 0.30884 | 0.40848 | 0.017503 | -0.039427 | -0.010707 | -0.71452 | 0.18594 | 0.38755
| 8701 | -0.33449 | 0.19931 | -0.23391 | -0.1565 | 0.088243 | 0.33509 | 0.50553 | 0.4117 | 0.023629 | -0.47265
| 8702 | 0.36227 | -0.33434 | -0.29127 | 0.73827 | 0.19025 | -0.3804 | 0.46325 | -0.47914 | -0.52115 | 0.13046
| 8703 | 0.19732 | -0.64772 | -0.00025003 | -0.71242 | 0.2133 | 0.41408 | 0.40763 | 0.37654 | 0.29197 | -0.51513
| 8704 | 0.63792 | 0.21597 | 0.33932 | 0.70555 | -0.089341 | -0.10395 | -0.45567 | 0.0063703 | -0.082231 | 0.096175
| 8705 | -0.61309 | -0.72378 | 0.2193 | -0.047057 | -0.05496 | -0.15935 | -0.5663 | 0.43564 | -0.77 | 0.22508
| 8706 | -0.08234 | -0.042451 | 0.42129 | 0.43229 | 0.47398 | 0.32762 | 0.098279 | -0.094296 | 0.34235 | 0.47703
| 8707 | 0.65927 | -0.74722 | 0.43405 | -0.2488 | -0.10273 | -0.1253 | 0.41034 | -0.42043 | -0.17411 | 0.34235
| 8708 | 0.64772 | -0.060372 | -0.34555 | 0.025577 | 0.25589 | -0.56606 | 0.018522 | -0.34647 | -0.0060684 | 0.65751
| 8709 | -0.34372 | -0.28887 | -0.037347 | 0.22328 | -0.065816 | 0.25926 | -0.32155 | -0.32776 | -0.19657 | -0.48454
| 8710 | 0.45658 | -0.016994 | 0.32925 | -0.27069 | -0.25777 | -0.16101 | 0.20937 | 0.35169 | -0.59938 | 0.51389
| 8711 | -0.39643 | -0.68361 | 0.033615 | 0.89183 | 0.53535 | 0.10117 | 0.048317 | 0.42337 | -0.049369 | 0.40511
| 8712 | -0.34023 | -0.21152 | 0.16735 | -0.39016 | -0.33239 | -0.58612 | 0.51575 | 0.75241 | -0.12702 | -0.66429
| 8713 | 0.31014 | 0.074311 | 0.18926 | 0.38445 | 0.78206 | -0.25549 | 0.24548 | -0.47057 | -0.85134 | -0.30797
| 8714 | 0.58083 | 0.33419 | 0.51761 | 0.1769 | -0.1803 | 0.033822 | 0.18741 | 0.14812 | -0.3568 | 0.32361
| 8715 | 0.52682 | -0.079077 | -0.0039578 | 0.12851 | -0.76357 | 0.29028 | -0.063571 | -0.38251 | -0.10172 | 0.54492
| 8716 | -0.063998 | 0.019745 | 0.23993 | -0.24112 | -0.55627 | 0.34174 | -0.057185 | 0.34632 | 0.58275 | -0.08234
| 8717 | -0.13449 | 0.11858 | 0.39809 | -0.29424 | 0.37254 | 0.4293 | 0.15212 | -0.14239 | 0.60643 | -0.15401
| 8718 | 0.34038 | 0.66909 | 0.20232 | -0.30451 | -0.58951 | 0.78952 | 0.40511 | -0.78905 | 0.031651 | 0.14402
| 8719 | -0.26549 | 0.80584 | 0.57609 | 0.67335 | 0.28132 | 0.031031 | 0.59392 | -0.36102 | -0.22186 | 0.21866
| 8720 | -0.21572 | 0.85893 | -0.18092 | 0.7735 | -0.18006 | -0.44152 | -0.29566 | -0.31758 | 0.11835 | 0.62784
| 8721 | -0.26413 | 0.044437 | 0.072045 | -0.236 | 0.15531 | -0.14449 | -0.30769 | 0.65373 | -0.52979 | -0.32717
| 8722 | -0.63271 | 0.25374 | 0.43759 | -0.17217 | 0.88642 | -0.075392 | -0.53794 | 0.18165 | -0.57116 | 0.85474
| 8723 | 0.19595 | 0.64237 | -0.066351 | -0.20747 | 0.10228 | -0.027735 | 0.7076 | -0.74485 | 0.046847 | 0.09187
| 8724 | -0.62624 | -0.25723 | -0.14671 | 0.24204 | -0.54316 | 0.1082 | -0.92584 | -0.42493 | -0.16699 | -0.057503
| 8725 | 0.27398 | 0.72018 | 0.23508 | 0.11225 | -0.035479 | 0.12839 | 0.55875 | -0.28803 | 0.48202 | -0.46083
| 8726 | -0.098501 | 0.39875 | 0.3129 | 0.32672 | 0.22728 | -0.20207 | -0.068925 | 0.26074 | -0.82536 | 0.059947
| 8727 | 0.15165 | -0.62224 | -0.11157 | 0.14918 | -0.45935 | 0.19272 | -0.16831 | 0.060585 | -0.0085869 | 0.72705
| 8728 | 0.84348 | 0.056973 | 0.088463 | -0.19894 | 0.2476 | 0.33796 | 0.066137 | 0.044333 | 0.26223 | -0.364
| 8729 | -0.28369 | 0.71382 | -0.48106 | -0.11462 | -0.47703 | -0.28049 | 0.36305 | 0.0023528 | -0.21802 | -0.3312
| 8730 | -0.26278 | -0.22922 | 0.19969 | 0.58347 | -0.3651 | 0.78068 | -0.20144 | -0.068388 | 0.6952 | 0.43141
| 8731 | 0.22676 | -0.57163 | 0.10017 | -0.36873 | 0.0022525 | 0.059947 | -0.33917 | -0.46065 | 0.82252 | 0.31465
| 8732 | 0.10753 | -0.2278 | -0.60465 | -0.15531 | 0.53107 | -0.95 | -0.031857 | -0.5707 | -0.33811 | 0.08989
| 8733 | -0.38673 | 0.04538 | 0.46325 | 0.47113 | -0.16018 | 0.26522 | 0.61672 | -0.53794 | 0.21406 | 0.32732
| 8734 | 0.23705 | 0.45603 | 0.17702 | -0.8366 | -0.06229 | -0.27924 | -0.24827 | 0.84933 | 0.24482 | 0.20106
| 8735 | 0.60592 | 0.83907 | 0.26699 | -0.069892 | -0.1375 | 0.40983 | 0.4206 | -0.72018 | -0.28719 | 0.23052
| 8736 | -0.31378 | -0.16916 | 0.17326 | 0.67798 | 0.049579 | -0.31261 | 0.029588 | -0.6952 | -0.25428 | 0.38202
| 8737 | 0.74603 | 0.24402 | -0.47837 | 0.32955 | 0.15377 | 0.69292 | -0.18778 | 0.68047 | 0.51307 | -0.29028
| 8738 | 0.2496 | 0.24178 | -0.52682 | 0.026707 | -0.74446 | 0.46344 | 0.20874 | -0.29893 | -0.010101 | -0.092751
| 8739 | -0.40092 | 0.40966 | 0.93443 | -0.19309 | -0.13611 | 0.45806 | -0.063464 | -0.54273 | -0.27633 | -0.89753
| 8740 | 0.10641 | -0.37895 | -0.26877 | 0.2907 | 0.39593 | -0.23705 | -0.047372 | -0.80947 | 0.25347 | -0.097836
| 8741 | 0.47684 | 0.68047 | 0.27261 | -0.45164 | -0.40915 | -0.50432 | 0.39263 | 0.31363 | 0.061011 | 0.31641
| 8742 | -0.53664 | -0.08967 | -0.25522 | -0.31978 | -0.22006 | 0.43176 | 0.13196 | 0.081251 | 0.1863 | -0.1315
| 8743 | -0.11767 | -0.24125 | -0.69619 | 0.14262 | 0.46887 | 0.49592 | -0.14824 | -0.34969 | 0.14859 | 0.41957
| 8744 | 0.21101 | -0.28817 | -0.19607 | 0.48087 | 0.12954 | -0.47303 | -0.19645 | 0.36227 | 0.26101 | 0.69784
| 8745 | -0.32155 | 0.29566 | -0.67798 | -0.38575 | 0.065281 | -0.16137 | 0.93443 | 0.16089 | -0.032064 | -0.55245
| 8746 | -0.45658 | -0.4078 | -0.91456 | -0.23078 | -0.15792 | -0.52788 | 0.6786 | 0.14918 | 0.089561 | 0.66758
| 8747 | 0.55921 | -0.10306 | -0.90673 | 0.22469 | 0.24654 | -0.42912 | -0.25589 | 0.21623 | -0.44295 | 0.076691
| 8748 | 0.085287 | 0.53794 | 0.24059 | -0.28691 | 0.18079 | 0.25321 | 0.80176 | 0.24853 | -0.58757 | -0.039427
| 8749 | 0.84094 | 0.64886 | 0.20949 | -0.11169 | 0.056867 | 0.046428 | 0.27467 | 0.16197 | 0.38853 | 0.72596
| 8750 | 0.054537 | -0.1466 | -0.22573 | -0.20458 | -0.44656 | 0.69162 | -0.83 | 0.04026 | 0.10429 | -0.10596
| 8751 | 0.87155 | -0.72926 | 0.30682 | -0.09518 | -0.12302 | 0.03579 | -0.29679 | 0.56468 | 0.68141 | -0.67243
| 8752 | 0.72018 | 0.22019 | -0.34235 | -0.29979 | -0.5201 | 0.31073 | -0.49473 | 0.14953 | -0.55245 | -0.23052
| 8753 | -0.13901 | -0.20798 | -0.010202 | -0.25133 | -0.024141 | 0.067637 | -0.33359 | -0.50533 | 0.0013509 | 0.78622
| 8754 | 0.1237 | 0.2119 | 0.87876 | -0.0013509 | 0.21 | -0.74368 | -0.50412 | 0.24112 | -0.85067 | 0.069248
| 8755 | 0.60113 | -0.015063 | 0.17532 | 0.48164 | -0.28481 | -0.77131 | 0.68775 | -0.67243 | 0.36133 | -0.25495
| 8756 | -0.46028 | 0.030722 | 0.10295 | 0.056761 | 0.12233 | 0.36431 | 0.074095 | 0.24601 | 0.5721 | -0.13924
| 8757 | 0.2755 | -0.14918 | 0.83 | -0.28958 | 0.55312 | -0.27151 | 0.26509 | 0.57327 | 0.78622 | -0.6044
| 8758 | 0.51266 | -0.87077 | 0.70285 | -0.068925 | 0.05422 | -0.77044 | -0.097836 | -0.23469 | -0.10395 | 0.20583
| 8759 | -0.55245 | -0.0781 | -0.68743 | 0.003456 | -0.18275 | 0.31816 | -0.56838 | -0.013947 | 0.028249 | 0.2377
| 8760 | -0.3796 | 0.15863 | -0.60113 | 0.53107 | -0.18385 | -0.10697 | -0.20169 | -0.44909 | -0.087147 | 0.53707
| 8761 | -0.34708 | 0.026809 | -0.022299 | -0.23796 | 0.67396 | -0.3593 | 0.5098 | -0.61594 | 0.4293 | -0.35603
| 8762 | 0.49216 | -0.09209 | -0.25993 | 0.14507 | 0.56148 | -0.91938 | 0.09 | -0.60389 | 0.16928 | -0.10764
| 8763 | -0.8882 | -0.38624 | 0.36447 | 0.33902 | 0.3425 | 0.011112 | 0.08136 | -0.018318 | -0.54163 | 0.3537
| 8764 | 0.17763 | -0.44403 | 0.097171 | -0.36274 | 0.40242 | -0.51246 | -0.11225 | -0.56699 | -0.49751 | 0.15094
| 8765 | -0.33962 | 0.12382 | 0.29964 | 0.024859 | -0.31232 | -0.71946 | -0.079185 | 0.4801 | -0.75201 | 0.30696
| 8766 | 0.32317 | 0.1603 | 0.041199 | -0.52703 | -0.086819 | -0.075176 | 0.009697 | 0.10195 | -0.00075028 | 0.028146
| 8767 | -0.38722 | -0.56954 | 0.72125 | 0.34586 | 0.19458 | 0.82308 | 0.35046 | -0.12165 | 0.27412 | 0.32391
| 8768 | 0.071076 | -0.61516 | 0.92859 | 0.11835 | -0.17253 | 0.58805 | -0.34632 | 0.34281 | 0.26563 | 0.32821
| 8769 | 0.27979 | -0.77572 | 0.32776 | 0.48415 | 0.64265 | 0.0866 | -0.24257 | 0.0083852 | 0.19632 | -0.31611
| 8770 | 0.91938 | 0.57703 | 0.09066 | 0.0056661 | -0.24787 | -0.4117 | -0.32361 | 0.38984 | -0.19707 | 0.058459
| 8771 | -0.00085036 | -0.4898 | -0.56216 | -0.51948 | -0.52303 | -0.25401 | 0.26291 | 0.27993 | -0.35417 | 0.1153
| 8772 | -0.32791 | 0.19856 | -0.29694 | -0.23247 | -0.31772 | -0.34479 | 0.50756 | 0.05253 | 0.77087 | -0.21381
| 8773 | 0.37734 | 0.58491 | -0.46774 | 0.015368 | 0.066565 | 0.60415 | 0.96127 | 0.39759 | -0.13588 | 0.56838
| 8774 | -0.027632 | -0.28593 | -0.45751 | -0.17787 | -0.75979 | -0.21393 | -0.3593 | 0.5529 | -0.64321 | 0.3048
| 8775 | 0.060266 | 0.62838 | 0.047372 | 0.25321 | -0.58854 | -0.32866 | 0.35634 | 0.029897 | 0.1425 | -0.19384
| 8776 | 0.10989 | -0.10865 | -0.055913 | 0.28132 | 0.65722 | 0.31626 | 0.37398 | -0.18938 | -0.10541 | 0.3951
| 8777 | 0.0023528 | -0.0019519 | -0.45383 | -0.73561 | 0.68647 | -0.83237 | -0.35293 | 0.94432 | 0.51451 | 0.11824
| 8778 | 0.41854 | 0.3607 | 0.29637 | 0.14087 | 0.10921 | 0.33329 | 0.29495 | 0.65 | -0.12154 | -0.25926
| 8779 | 0.33075 | 0.07043 | 0.77131 | 0.35758 | 0.34494 | 0.32155 | 0.21699 | 0.17314 | -0.23039 | -0.075392
| 8780 | 0.10563 | 0.11847 | 0.29679 | 0.36023 | -0.65547 | -0.29708 | 0.3804 | 0.33359 | -0.16964 | -0.19508
| 8781 | -0.20357 | 0.46288 | -0.25468 | -0.32776 | -0.25899 | 0.40848 | 0.77131 | -0.063037 | 0.12461 | 0.52282
| 8782 | 0.68968 | 0.15946 | 0.13311 | -0.016994 | -0.82196 | 0.05549 | 0.25455 | 0.67274 | 0.0781 | -0.23273
| 8783 | 0.33841 | -0.25831 | 0.54778 | -0.21635 | -0.28453 | -0.14134 | 0.19037 | 0.0728 | 0.18348 | 0.23299
| 8784 | -0.16555 | 0.065388 | -0.20357 | -0.0069743 | -0.0041586 | 0.73789 | -0.26767 | -0.032994 | -0.65 | 0.044647
| 8785 | -0.36494 | 0.57186 | 0.11124 | 0.69097 | 0.82708 | 0.34954 | -0.14941 | 0.11688 | 0.86108 | -0.043182
| 8786 | -0.50392 | 0.2042 | -0.14379 | 0.16868 | -0.55559 | -0.11191 | 0.35977 | -0.09154 | -0.27785 | -0.56057
| 8787 | 0.59689 | -0.22045 | 0.46046 | -0.59294 | 0.8739 | -0.35432 | 0.34464 | -0.44367 | 0.5013 | -0.53751
| 8788 | 0.24151 | -0.23286 | 0.37863 | -0.27896 | 0.63682 | 0.14859 | 0.17872 | -0.30624 | -0.69586 | -0.096396
| 8789 | 0.01486 | 0.24747 | -0.50331 | 0.46981 | -0.1775 | 0.36086 | -0.55785 | -0.27633 | 0.31685 | 0.51266
| 8790 | -0.046323 | -0.2893 | 0.0025533 | -0.49098 | -0.076907 | 0.74058 | 0.32228 | 0.60694 | 0.07 | 0.069892
| 8791 | -0.16054 | -0.67891 | 0.35572 | -0.24482 | -0.52366 | 0.40561 | 0.00025003 | -0.3357 | -0.24973 | 0.49751
| 8792 | 0.33209 | -0.032788 | -0.31978 | 0.78251 | -0.034858 | -0.25361 | -0.39859 | 0.25629 | 0.17386 | -0.048633
| 8793 | -0.24363 | 0.065495 | 0.75241 | 0.037763 | -0.2175 | -0.28635 | -0.75161 | -0.47398 | 0.64489 | -0.1162
| 8794 | 0.032167 | -0.43352 | -0.055066 | -0.068174 | -0.17435 | 0.5017 | -0.83177 | 0.39908 | -0.53816 | 0.47284
| 8795 | -0.1353 | -0.0014511 | 0.21165 | -0.37462 | -0.15709 | 0.020561 | -0.30725 | -0.76698 | 0.02609 | -0.084522
| 8796 | 0.53128 | 0.48318 | -0.048738 | 0.022912 | -0.022299 | 0.39444 | 0.11609 | 0.3294 | -0.058777 | -0.8956
| 8797 | 0.66251 | 0.14777 | 0.28817 | 0.6755 | -0.11349 | -0.58491 | -0.20407 | 0.21572 | -0.36921 | 0.0029544
| 8798 | 0.073663 | 0.56699 | -0.16591 | -0.13184 | -0.34724 | 0.041929 | -0.058353 | -0.236 | -0.42476 | -0.17205
| 8799 | 0.43264 | -0.47265 | -0.46213 | 0.54646 | -0.60617 | -0.71982 | -0.14461 | -0.034029 | 0.20508 | -0.02568
| 8800 | 0.75938 | 0.69488 | -0.13311 | 0.5922 | 0.0063703 | -0.52915 | 0.48222 | -0.20319 | 0.54142 | 0.02897
| 8801 | 0.040469 | -0.4902 | -0.43831 | 0.35015 | -0.1261 | -0.34816 | -0.64125 | -0.59098 | -0.53149 | 0.18655
| 8802 | -0.61257 | 0.6257 | 0.37847 | -0.03465 | -0.5663 | -0.72632 | 0.072584 | -0.38608 | -0.69 | -0.49275
| 8803 | 0.60263 | -0.4046 | -0.51143 | -0.25428 | -0.12828 | 0.070323 | -0.046638 | 0.64518 | -0.23391 | 0.79336
| 8804 | -0.15059 | 0.23208 | 0.5098 | -0.25872 | 0.056125 | 0.70083 | -0.79579 | 0.43955 | -0.0064709 | -0.16651
| 8805 | -0.61077 | -0.30639 | -0.14145 | -0.011314 | 0.95641 | -0.24987 | -0.24628 | 0.59417 | 0.5663 | -0.3116
| 8806 | -0.34601 | -0.44098 | 0.0076795 | -0.65229 | 0.14192 | 0.0042591 | 0.88909 | -0.093523 | 0.4776 | 0.092972
| 8807 | 0.30797 | -0.2402 | 0.44619 | -0.0093941 | 0.48532 | -0.020459 | -0.42147 | -0.23849 | 0.21738 | -0.45
| 8808 | -0.1418 | -0.17157 | -0.95877 | 0.18557 | 0.21584 | 0.4991 | 0.7687 | 0.18914 | -0.017605 | 0.26509
| 8809 | 0.71242 | -0.43158 | 0.82941 | 0.12359 | 0.36258 | 0.32051 | 0.56194 | -0.1533 | -0.3651 | 0.26441
| 8810 | 0.16221 | 0.21763 | -0.31073 | 0.464 | -0.54823 | 0.10039 | 0.63244 | 0.29708 | 0.37526 | 0.82883
| 8811 | 0.264 | -0.083212 | -0.51595 | -0.13623 | 0.6371 | 0.04538 | -0.13774 | -0.026193 | -0.3956 | 0.35525
| 8812 | -0.11575 | 0.62624 | 0.34372 | 0.27771 | 0.27206 | -0.13519 | -0.71069 | 0.80791 | 0.2398 | -0.013238
| 8813 | 0.21038 | 0.39842 | -0.009798 | -0.41255 | 0.27509 | 0.2674 | 0.29424 | 0.18116 | -0.56308 | -0.3568
| 8814 | 0.73675 | 0.28761 | -0.47512 | 0.19309 | -0.31802 | -0.20307 | 0.12862 | -0.16304 | -0.25818 | -0.536
| 8815 | -0.19545 | 0.038595 | 0.29014 | -0.23823 | -0.17278 | -0.49473 | -0.68488 | 0.93 | 0.0033556 | 0.032477
| 8816 | 0.019235 | 0.016588 | -0.31451 | -0.045065 | -0.34678 | -0.00035006 | 0.85405 | 0.32066 | 0.21152 | 0.20282
| 8817 | 0.97354 | -0.084959 | -0.38364 | 0.17374 | 0.48922 | 0.24654 | 0.28845 | -0.011213 | 0.25361 | -0.096175
| 8818 | 0.16304 | 0.30408 | -0.056549 | 0.65868 | -0.036828 | -0.24787 | 0.035687 | 0.18153 | 0.28453 | -0.27385
| 8819 | 0.43105 | 0.54426 | 0.25227 | -0.66103 | -0.10541 | 0.45164 | 0.32613 | -0.22109 | 0.26932 | -0.34862
| 8820 | 0.54889 | -0.66849 | 0.94084 | -0.29936 | -0.20949 | -0.062183 | -0.25697 | 0.58684 | 0.00065021 | -0.21533
| 8821 | -0.098058 | 0.046323 | 0.29651 | -0.26291 | 0.022196 | 0.12017 | 0.5021 | -0.80739 | 0.060585 | -0.23941
| 8822 | 0.22922 | -0.27165 | -0.17994 | -0.40831 | 0.040573 | 0.23039 | 0.31772 | -0.25428 | 0.24614 | 0.61128
| 8823 | 0.7488 | -0.1204 | 0.14859 | 0.12245 | 0.21393 | 0.21432 | 0.83417 | 0.61542 | -0.97 | 0.22058
| 8824 | -0.30595 | 0.27426 | -0.20119 | -0.14824 | 0.46512 | 0.17544 | -0.35727 | 0.26959 | -0.75813 | -0.48804
| 8825 | 0.31 | 0.57751 | 0.48241 | 0.089121 | 0.54889 | -0.48863 | -0.24389 | 0.52894 | -0.0087886 | 0.26522
| 8826 | 0.033822 | 0.26278 | 0.35463 | 0.30899 | 0.64943 | 0.21101 | -0.31582 | 0.30437 | 0.46493 | -0.84476
| 8827 | -0.085396 | 0.056125 | -0.030103 | 0.43281 | -0.80584 | 0.10619 | 0.33149 | 0.45917 | 0.031754 | -0.21013
| 8828 | 0.39049 | 0.28944 | -0.39494 | 0.11045 | -0.14006 | 0.42026 | 0.38738 | 0.82941 | -0.45164 | 0.076258
| 8829 | 0.47094 | -0.20445 | -0.79336 | 0.31919 | 0.57988 | 0.39213 | -0.73298 | 0.23796 | 0.31641 | -0.021481
| 8830 | 0.18324 | -0.096064 | 0.060585 | -0.40865 | -0.52534 | 0.2722 | -0.2037 | 0.1162 | 0.19458 | 0.58587
| 8831 | -0.2995 | 0.85 | -0.13866 | 0.36055 | 0.25872 | 0.61777 | 0.43955 | 0.79433 | -0.4776 | 0.085396
| 8832 | -0.28691 | -0.14847 | -0.030928 | 0.021481 | -0.60238 | -0.29551 | 0.3629 | 0.41051 | 0.62973 | 0.44746
| 8833 | -0.11304 | -0.24907 | -0.03465 | 0.08474 | 0.55402 | -0.54823 | 0.38445 | -0.50837 | 0.37462 | 0.0016514
| 8834 | -0.49433 | 0.29594 | -0.37111 | -0.55762 | 0.056019 | 0.087366 | 0.027015 | 0.67061 | 0.11157 | -0.61051
| 8835 | 0.035065 | -0.089012 | 0.16316 | 0.11801 | 0.0046609 | 0.16448 | -0.07962 | -0.25347 | -0.49612 | 0.17665
| 8836 | -0.24046 | 0.076149 | -0.23731 | 0.28663 | 0.50959 | 0.42251 | 0.71417 | -0.536 | -0.48902 | -0.31963
| 8837 | -0.20949 | -0.31232 | 0.31276 | 0.029588 | -0.83969 | -0.033201 | -0.1118 | 0.44242 | 0.036517 | 0.19956
| 8838 | 0.056549 | 0.37606 | 0.17338 | -0.82028 | -0.10451 | -0.64405 | -0.29395 | 0.23587 | -0.11045 | 0.13207
| 8839 | 0.066244 | 0.1688 | -0.079294 | 0.7504 | 0.34617 | -0.64914 | -0.04099 | -0.53213 | 0.31145 | -0.48144
| 8840 | 0.10451 | 0.4898 | -0.0015512 | 0.070215 | 0.16952 | 0.10362 | 0.49059 | -0.13542 | -0.65057 | 0.8882
| 8841 | 0.46643 | 0.73149 | 0.017401 | -0.90461 | -0.73 | -0.62517 | -0.32258 | -0.14484 | -0.38494 | 0.25966
| 8842 | -0.36762 | 0.38413 | 0.11417 | -0.27951 | -0.19844 | -0.28076 | 0.20407 | -0.12256 | 0.044647 | -0.2508
| 8843 | 0.002453 | 0.57444 | 0.53107 | -0.05158 | -0.016181 | 0.46849 | 0.088682 | -0.33419 | 0.19062 | 0.021787
| 8844 | -0.24191 | 0.083649 | -0.2504 | 0.59269 | -0.45438 | -0.11293 | -0.19309 | -0.37414 | 0.030825 | 0.2052
| 8845 | 0.25321 | 0.10989 | 0.56285 | 0.14882 | 0.2571 | -0.028249 | 0.48843 | -0.40092 | 0.80379 | -0.11146
| 8846 | -0.51761 | -0.1852 | -0.46493 | -0.68204 | -0.09033 | 0.88467 | 0.5347 | -0.080054 | -0.60263 | -0.71173
| 8847 | -0.60846 | -0.79048 | 0.065067 | -0.41442 | 0.40108 | 0.052952 | -0.21725 | -0.10128 | -0.65956 | -0.097614
| 8848 | 0.34433 | -0.17471 | 0.11938 | -0.63627 | -0.74682 | 0.006169 | -0.05984 | 0.30884 | -0.71733 | -0.21699
| 8849 | 0.024141 | 0.48707 | -0.27536 | 0.34985 | -0.33585 | -0.87631 | 0.11631 | -0.12142 | -0.3357 | 0.25267
| 8850 | -0.2689 | 0.16364 | 0.073447 | 0.23941 | -0.28523 | 0.042347 | 0.36557 | -0.027323 | -0.2052 | 0.68456
| 8851 | -0.84284 | 0.78297 | 0.2427 | 0.19471 | 0.24628 | -0.16723 | 0.36873 | -5.0001e-05 | -0.13092 | 0.02097
| 8852 | 0.059415 | -0.2147 | -0.3651 | -0.50675 | 0.43 | 0.59245 | 0.093634 | 0.86923 | 0.53342 | 0.7015
| 8853 | 0.3372 | -0.42251 | -0.66909 | 0.68615 | 0.08234 | -0.50878 | -0.098501 | 0.40343 | 0.08343 | -0.3607
| 8854 | -0.0063703 | 0.34038 | 0.077883 | 0.25993 | 0.20181 | 0.42755 | 0.42303 | 0.27371 | 0.30466 | -0.30581
| 8855 | 0.51802 | 0.049579 | -0.19732 | -0.071184 | -0.46065 | 0.1127 | 0.20119 | 0.46718 | 0.34923 | 0.24191
| 8856 | -0.038595 | 0.25347 | 0.059628 | 0.24747 | 0.35169 | -0.024654 | -0.81159 | 0.71069 | 0.85201 | -0.65839
| 8857 | 0.009697 | 0.47722 | -0.16496 | 0.49433 | 0.33105 | 0.20344 | 0.57988 | 0.059628 | 0.41494 | -0.85682
| 8858 | 0.12188 | 0.19037 | -0.45917 | -0.55492 | 0.18988 | 0.22831 | -0.067423 | -0.7569 | 0.74643 | 0.024141
| 8859 | 0.12256 | 0.32985 | 0.13716 | 0.36526 | 0.031651 | 0.56445 | -0.12908 | 0.41716 | 0.26196 | 0.64405
| 8860 | -0.2356 | 0.1597 | 0.63408 | -0.49612 | -0.064212 | -0.70453 | 0.40343 | 0.27619 | 0.91112 | 0.049579
| 8861 | 0.24257 | -0.21254 | -0.33555 | 0.5806 | -0.59938 | 0.1221 | 0.65839 | -0.16711 | 0.16904 | -0.14227
| 8862 | -0.2512 | -0.096839 | 0.15047 | -0.38267 | 0.8956 | 0.021583 | -0.14425 | -0.79727 | -0.2492 | -0.15804
| 8863 | -0.6637 | -0.34296 | -0.37175 | 0.065067 | 0.41957 | -0.1439 | -0.46195 | -0.59689 | 0.37927 | 0.31934
| 8864 | -0.0050628 | 0.2733 | 0.009596 | -0.20861 | -0.12108 | 0.09132 | -0.43405 | 0.6939 | -0.2377 | 0.57727
| 8865 | 0.022196 | 0.14788 | 0.70017 | 0.53342 | -0.11915 | -0.76399 | 0.46121 | -0.11598 | 0.18581 | -0.69292
| 8866 | 0.64097 | 0.50776 | -0.5011 | 0.31714 | -0.33856 | -0.5436 | 0.59171 | -0.81534 | -0.16496 | 0.41871
| 8867 | 0.088243 | 0.37702 | 0.8821 | -0.063357 | 0.41323 | 0.023015 | -0.012123 | -0.4755 | 0.43671 | -0.50492
| 8868 | 0.058459 | 0.08649 | -0.21763 | -0.31203 | 0.48396 | 0.65663 | 0.62251 | 0.39082 | 0.31553 | -0.4993
| 8869 | 0.36778 | 0.15887 | 0.057079 | -0.2193 | -0.018114 | 0.0067729 | -0.026398 | -0.32317 | 0.34908 | -0.83783
| 8870 | -0.28901 | -0.43955 | -0.12966 | -0.70828 | 0.75444 | -0.10128 | -0.13473 | 0.88731 | -0.16412 | 0.39593
| 8871 | 0.06496 | -0.35386 | 0.46288 | -0.050632 | -0.10742 | 0.68204 | -0.13785 | 0.46158 | -0.80895 | -0.22624
| 8872 | 0.0050628 | 0.20697 | -0.56445 | 0.32836 | -0.87155 | 0.029073 | 0.65057 | 0.14262 | 0.5806 | 0.54867
| 8873 | 0.39181 | -0.33419 | -0.70725 | 0.21419 | 0.64574 | 0.6044 | -0.59913 | 0.62624 | 0.098834 | -0.08978
| 8874 | 0.62198 | 0.1952 | -0.37606 | 0.21254 | 0.14297 | 0.16747 | 0.73186 | 0.031238 | -0.072261 | 0.10172
| 8875 | 0.19856 | 0.83783 | -0.054431 | 0.21597 | -0.12622 | -0.15295 | -0.5768 | 0.16448 | -0.27536 | 0.3743
| 8876 | -0.0091922 | 0.19322 | -0.5009 | 0.10798 | 0.4417 | 0.050421 | 0.42598 | -0.61464 | -0.59343 | 0.22663
| 8877 | 0.60063 | -0.45401 | 0.36889 | -0.55357 | -0.082994 | 0.22521 | 0.17338 | 0.28607 | -0.27357 | 0.10596
| 8878 | -0.76527 | -0.65839 | 0.55379 | 0.35401 | 0.14285 | 0.034961 | -0.11439 | 0.70589 | -0.14087 | 0.3074
| 8879 | 0.036102 | 0.69983 | 0.31831 | 0.15212 | -0.80532 | -0.18471 | 0.19969 | 0.82422 | 0.20621 | -0.3767
| 8880 | 0.38755 | -0.75566 | 0.50472 | 0.66939 | -0.031444 | 0.11575 | -0.46549 | -0.15188 | -0.080598 | -0.21623
| 8881 | -0.21981 | 0.032994 | 0.67735 | -0.1921 | 0.28761 | 0.27619 | 0.39892 | 0.1628 | 0.79531 | 0.45732
| 8882 | -0.12256 | 0.72852 | 0.071614 | 0.18963 | -0.38706 | -0.050211 | -0.3662 | -0.35665 | -0.23091 | 0.062397
| 8883 | -0.044333 | -0.62145 | 0.39992 | 0.49157 | 0.41802 | 0.13739 | -0.38869 | -0.77528 | -0.5728 | -0.47875
| 8884 | -0.65229 | 0.066994 | -0.034547 | 0.04026 | 0.10139 | -0.38429 | -0.1196 | -0.14297 | -0.0173 | 0.79288
| 8885 | 0.015774 | 0.31392 | -0.20646 | 0.18018 | 0.26877 | -0.05 | -0.60795 | -0.26047 | -0.06016 | 0.43123
| 8886 | -0.17896 | 0.89091 | 0.70589 | 0.10362 | 0.31392 | -0.049474 | 0.41221 | 0.056973 | 0.29679 | -0.51823
| 8887 | 0.1926 | 0.42407 | -0.22598 | 0.034236 | -0.20697 | -0.017096 | -0.40729 | -0.22715 | -0.8995 | -0.060798
| 8888 | 0.055807 | -0.4564 | -0.31743 | 0.11304 | 0.21725 | 0.45475 | 0.71138 | -0.1109 | -0.16735 | -0.31846
| 8889 | -0.24482 | 0.24907 | -0.3537 | -0.58587 | -0.03434 | -0.6118 | 0.22818 | -0.24059 | 0.11745 | 0.46381
| 8890 | -0.030206 | 0.60643 | 0.074635 | 0.22071 | 0.41665 | 0.053586 | -0.31087 | -0.11135 | -0.1353 | 0.21228
| 8891 | -0.13924 | -0.0038574 | 0.77528 | 0.12176 | 0.17423 | 0.094075 | -0.13057 | 0.2659 | -0.4417 | 0.081795
| 8892 | -0.17848 | -0.15721 | -0.098501 | -0.3294 | -0.61 | -0.12484 | -0.66489 | 0.12644 | 0.30538 | 0.16089
| 8893 | 0.059309 | 0.76741 | -0.6833 | -0.16436 | -0.27165 | 0.17193 | 0.031238 | 0.20659 | -0.73261 | 0.19794
| 8894 | -0.43299 | -0.010808 | 0.61154 | 0.25656 | -0.20709 | -0.49433 | -0.43158 | -0.26345 | -0.46009 | -0.37622
| 8895 | 0.24033 | -0.25804 | 0.098612 | -0.40763 | 0.42199 | -0.63654 | -0.044961 | -0.058777 | 0.021174 | -0.5608
| 8896 | -0.40142 | 0.044856 | 0.42685 | 0.3956 | 0.23456 | 0.62066 | -0.65956 | 0.3951 | -0.66638 | 0.15472
| 8897 | 0.4799 | 0.51287 | -0.40092 | 0.55379 | -0.48048 | -0.058884 | -0.81 | 0.58179 | 0.09099 | -0.21215
| 8898 | -0.32702 | -0.2733 | -0.36715 | -0.082885 | -0.13959 | 0.41957 | -0.77218 | 0.15543 | -0.11926 | 0.21254
| 8899 | 0.32155 | -0.12897 | -0.034754 | 0.68016 | -0.20257 | 0.38008 | -0.4293 | 0.15188 | 0.49118 | -0.13473
| 8900 | 0.14274 | -0.38461 | 0.38251 | -0.25953 | 0.87631 | -0.015876 | 0.043391 | -0.045904 | 0.20332 | -0.36055
| 8901 | -0.56583 | 0.23482 | 0.34724 | 0.032994 | -0.59988 | 0.30653 | -0.69162 | 0.43795 | 0.33811 | -0.54778
| 8902 | 0.352 | 0.51678 | -0.24774 | 0.27206 | -0.29042 | 0.13808 | -0.40983 | -0.52031 | 0.00025003 | -0.74368
| 8903 | -0.22135 | -0.56537 | 0.6349 | 0.1957 | 0.1432 | -0.25414 | -0.011112 | -0.22689 | -0.55357 | 0.025885
| 8904 | 0.20031 | 0.041512 | 0.041512 | 0.088902 | -0.26617 | 0.18852 | 0.20257 | -0.15935 | -0.36715 | 0.13704
| 8905 | -0.0090913 | -0.076907 | 0.1353 | 0.057609 | -0.70521 | 0.67182 | -0.0053644 | -0.20344 | -0.46456 | -0.010202
| 8906 | 0.64914 | 0.65287 | -0.22444 | 0.067745 | 0.05348 | 0.013744 | 0.31524 | -0.049579 | 0.21802 | 0.152
| 8907 | 0.45511 | -0.2037 | -0.34448 | -0.71 | -0.47818 | -0.0025533 | -0.29424 | 0.34296 | 0.31538 | -0.11518
| 8908 | -0.4232 | 0.7042 | -0.40814 | -0.012427 | -0.1196 | 0.30899 | -0.37095 | -0.72054 | -0.38755 | 0.14262
| 8909 | 0.18877 | 0.85067 | 0.013846 | -0.19272 | 0.53149 | 0.13184 | 0.17665 | 0.17024 | -0.37239 | 0.5098
| 8910 | 0.35278 | 0.78952 | -0.59639 | 0.055384 | 0.44511 | 0.86923 | 0.69685 | -0.025474 | -0.21432 | 0.13173
| 8911 | -0.32214 | -0.24853 | 0.0092932 | -0.35015 | 0.45091 | -0.26617 | -0.148 | 0.8956 | 0.0058672 | -0.0029544
| 8912 | 0.20019 | 0.1825 | -0.40058 | -0.10106 | -0.27096 | -0.33449 | 0.060266 | -0.38299 | -0.097836 | 0.16795
| 8913 | 0.60238 | 0.18165 | 0.364 | -0.10317 | 0.28705 | -0.59515 | 0.87155 | 0.38836 | 0.19086 | 0.22379
| 8914 | 0.22019 | -0.24628 | 0.17617 | 0.2512 | -0.74135 | -0.0021523 | 0.36321 | -0.56653 | -0.054749 | 0.25939
| 8915 | 0.51143 | -0.41357 | -0.27151 | 0.053163 | 0.064212 | -0.72378 | 0.48241 | 0.14449 | -0.32836 | -0.11034
| 8916 | 0.64518 | 0.61646 | -0.22948 | 0.5021 | -0.6249 | -0.53342 | 0.19062 | -0.77977 | 0.19944 | -0.24442
| 8917 | -0.32406 | 0.49453 | -0.28565 | -0.61672 | -0.18018 | 0.66459 | -0.08485 | -0.77306 | -0.45824 | -0.18544
| 8918 | -0.020663 | -0.27522 | 0.098945 | -0.11903 | -0.12519 | -0.061118 | 0.15543 | 0.93292 | 0.71069 | -0.023732
| 8919 | -0.39958 | 0.64631 | -0.71069 | -0.30682 | 0.019337 | -0.43035 | -0.59888 | -0.37111 | 0.093192 | 0.095732
| 8920 | 0.79143 | 0.26849 | -0.53064 | -0.24007 | 0.31904 | -0.21266 | 0.26686 | 0.061757 | -0.17823 | -0.8618
| 8921 | 0.18729 | 0.71 | -0.71382 | -0.53816 | 0.33992 | 0.45383 | -0.35417 | -0.77262 | -0.34083 | -0.34296
| 8922 | -0.2659 | 0.23234 | 0.77662 | -0.85682 | 0.029691 | 0.12553 | 0.83357 | -0.27453 | 0.32687 | -0.30667
| 8923 | 0.061437 | 0.18717 | 0.66819 | -0.69784 | 0.43264 | 0.077449 | 0.36794 | -0.23026 | -0.37494 | -0.42078
| 8924 | -0.54163 | -0.84605 | 0.10686 | -0.50594 | -0.62704 | -0.74019 | -0.024859 | -0.08485 | 0.58708 | -0.73335
| 8925 | -0.42633 | -0.8995 | 0.85134 | 0.078751 | 0.33932 | 0.15982 | -0.78529 | 0.32583 | 0.017096 | -0.38186
| 8926 | 0.49552 | -0.078208 | 0.36794 | 0.61672 | -0.10708 | 0.098723 | -0.099389 | 0.60923 | -0.43423 | 0.50959
| 8927 | -0.021174 | 0.92063 | -0.38951 | 0.51472 | -0.67 | 0.248 | -0.019745 | 0.52724 | -0.19037 | 0.12954
| 8928 | 0.24601 | 0.043914 | -0.28887 | 0.22857 | -0.036621 | 0.47837 | -0.21648 | -0.21891 | -0.33075 | -0.28705
| 8929 | 0.0781 | -0.5009 | -0.65897 | 0.81972 | -0.16496 | -0.049263 | 0.29014 | -0.17471 | 0.040052 | 0.21
| 8930 | 0.28719 | 0.069892 | 0.038283 | -0.39742 | 0.34647 | -0.42389 | 0.077232 | 0.20621 | -0.23495 | -0.3248
| 8931 | 0.51389 | 0.021992 | -0.44656 | -0.62892 | -0.65402 | 0.43955 | -0.21381 | 0.59441 | 0.044437 | 0.15519
| 8932 | 0.007075 | -0.38445 | 0.58757 | -0.032374 | 0.34327 | 0.19931 | -0.41442 | 0.20232 | 0.17205 | 0.15141
| 8933 | 0.068174 | -0.32184 | -0.41408 | 0.36227 | -0.44277 | 0.22676 | 0.16856 | 0.0010506 | -0.093192 | 0.2492
| 8934 | -0.068603 | 0.17459 | -0.52219 | -0.08234 | 0.095069 | -0.28383 | 0.076691 | 0.21738 | 0.8821 | -0.1546
| 8935 | 0.39296 | 0.23247 | -0.066137 | 0.22922 | -0.57585 | -0.36353 | -0.30036 | 0.040573 | 0.56699 | -0.070968
| 8936 | 0.27536 | 0.18926 | 0.0016514 | -0.042242 | 0.3759 | 0.06229 | -0.52809 | 0.75813 | -0.33947 | 0.47914
| 8937 | 0.30783 | -0.3759 | 0.26932 | -0.8821 | -0.48551 | -0.19284 | 0.20987 | 0.63 | -0.53107 | -0.18471
| 8938 | -0.10217 | 0.073771 | 0.11214 | 0.14204 | -0.65927 | 0.40309 | -0.27453 | -0.20722 | -0.12382 | -0.0078811
| 8939 | -0.6241 | -0.34985 | -0.67488 | -0.64181 | -0.11994 | 0.31568 | -0.50311 | 0.36008 | -0.44403 | -0.06261
| 8940 | -0.53 | -0.13473 | 0.052952 | 0.37079 | -0.49731 | 0.46325 | -0.22495 | 0.54404 | -0.41136 | -0.08989
| 8941 | 0.49196 | 0.030516 | 0.36102 | -0.24297 | 0.75161 | -0.15425 | -0.66399 | 0.21674 | 0.16221 | 0.24323
| 8942 | 0.31846 | 0.060798 | 0.84476 | 0.45622 | -0.33992 | 0.10006 | -0.2625 | 0.01791 | 0.065709 | 0.53385
| 8943 | -0.18963 | 0.85474 | -0.2076 | -0.023834 | 0.60314 | -0.72269 | -0.61361 | 0.31073 | -0.053163 | -0.82479
| 8944 | 0.27274 | 0.16436 | -0.20181 | 0.097503 | -0.11665 | -0.52219 | -0.035168 | 0.058459 | 0.25845 | -0.1646
| 8945 | -0.28719 | -0.65809 | -0.50594 | -0.030309 | 0.23052 | -0.35278 | 0.4408 | 0.66519 | 0.4344 | 0.30552
| 8946 | 0.42755 | 0.049895 | -0.022094 | 0.053797 | 0.28747 | -0.022401 | 0.74603 | -0.35324 | -0.21853 | 0.0076795
| 8947 | -0.20571 | 0.035583 | 0.8747 | -0.38445 | 0.37462 | 0.095069 | -0.018725 | 0.37223 | -0.064212 | 0.022503
| 8948 | 0.90356 | 0.33299 | 0.28341 | 0.60013 | 0.17982 | -0.45824 | 0.77528 | 0.49771 | -0.80328 | 0.11665
| 8949 | 0.83599 | 0.3735 | -0.39908 | 0.19632 | -0.11745 | -0.032891 | -0.058034 | -0.40309 | 0.52198 | -0.23809
| 8950 | -0.73789 | 0.12427 | -0.47626 | -0.49473 | 0.13878 | 0.05 | -0.22598 | -0.11564 | 0.27702 | -0.38202
| 8951 | -0.016994 | 0.013136 | -0.082122 | -0.50231 | -0.26169 | 0.65402 | 0.4979 | -0.69227 | -0.33902 | -0.06197
| 8952 | -0.52471 | -0.25643 | -0.47208 | 0.60389 | -0.15673 | -0.040156 | 0.47722 | -0.40511 | 0.55966 | 0.28873
| 8953 | 0.37462 | -0.40696 | -0.42181 | 0.66728 | -0.046323 | 0.34754 | -0.48532 | -0.44152 | 0.27827 | 0.5608
| 8954 | -0.44242 | -0.056125 | 0.79048 | 0.31611 | -0.14578 | 0.1578 | 0.037867 | 0.1735 | 0.90151 | 0.64461
| 8955 | 0.60898 | -0.50553 | 0.91 | 0.028867 | -0.63135 | 0.15899 | -0.52724 | 0.24363 | -0.53794 | -0.096507
| 8956 | 0.86546 | 0.3369 | 0.14461 | 0.44818 | -0.39033 | -0.23091 | 0.54514 | 0.19396 | 0.11699 | -0.18606
| 8957 | 0.77932 | -0.060266 | -0.43742 | -0.94804 | 0.36478 | 0.37494 | -0.10933 | 0.16304 | 0.68583 | -0.77841
| 8958 | -0.021685 | 0.2995 | 0.45383 | -0.19533 | 0.13971 | 0.46083 | -0.27757 | 0.095954 | -0.65114 | 0.037763
| 8959 | -0.52073 | 0.63958 | 0.0042591 | 0.71982 | 0.14566 | -0.0030547 | -0.21266 | -0.18128 | -0.098612 | 0.2995
| 8960 | -0.26713 | -0.15306 | -0.084631 | 0.2287 | 0.71277 | -0.48106 | -0.2476 | 0.0064709 | 0.21584 | 0.16627
| 8961 | -0.33284 | 0.024244 | 0.41051 | 0.088463 | -0.37831 | -0.3618 | 0.68393 | -0.032064 | 0.16292 | -0.12966
| 8962 | 0.16988 | -0.10798 | -0.47952 | -0.54163 | -0.099167 | -0.38364 | 0.38267 | -0.65751 | -0.85893 | -0.32184
| 8963 | 0.17836 | 0.2278 | -0.32925 | 0.7488 | 0.2809 | 0.11011 | -0.43529 | -0.39098 | -0.92584 | 0.1825
| 8964 | -0.17253 | -0.40544 | -0.69357 | -0.50492 | -0.19173 | -0.60289 | -0.45456 | -0.029794 | -0.62357 | 0.26932
| 8965 | -0.10429 | 0.94432 | -0.12028 | -0.09695 | -0.28887 | 0.72341 | 0.35262 | 0.50251 | -0.12439 | -0.19881
| 8966 | -0.24867 | 0.28049 | 0.18459 | -0.24138 | 0.77395 | -0.65897 | -0.4981 | -0.37334 | -0.27027 | 0.45567
| 8967 | 0.94615 | 0.10585 | -0.41733 | -0.024756 | 0.39 | 0.48048 | 0.38608 | 0.076799 | 0.32155 | -0.18963
| 8968 | -0.0866 | -0.62838 | -0.88126 | -0.27702 | 0.63326 | 0.0011507 | -0.13739 | -0.50634 | -0.31014 | -0.28076
| 8969 | -0.025064 | -0.58805 | -0.070108 | 0.29822 | 0.33149 | -0.1269 | -0.17193 | 0.39576 | -0.052002 | 0.3214
| 8970 | 0.088792 | 0.23065 | -0.56148 | -0.43511 | -0.46868 | 0.12725 | 0.21013 | -0.61803 | -0.44475 | -0.60516
| 8971 | 0.35154 | -0.37542 | 0.24349 | -0.40527 | 0.69162 | 0.31043 | 0.11564 | -0.44964 | 0.018725 | -0.13415
| 8972 | -0.84801 | 0.076691 | 0.6985 | -0.38364 | -0.02097 | 0.35977 | 0.51389 | 0.3804 | -0.48863 | 0.16232
| 8973 | -0.0044599 | -0.4717 | -0.1466 | -0.23208 | -0.56216 | 0.47227 | -0.38153 | 0.26617 | 0.42912 | -0.50432
| 8974 | 0.36149 | -0.47398 | -0.15188 | -0.35712 | 0.2398 | 0.20445 | 0.92319 | 0.37366 | -0.31904 | -0.27536
| 8975 | -0.047267 | 0.20382 | -0.20609 | 0.5264 | 0.096617 | -0.81159 | -0.30193 | 0.29113 | 0.68425 | -0.012225
| 8976 | 0.2659 | 0.82883 | 0.21495 | -0.6162 | -0.58708 | 0.26468 | -0.22469 | 0.16759 | 0.28817 | 0.36668
| 8977 | 0.24416 | -0.62865 | -0.16567 | -0.065388 | -0.27247 | -0.42026 | 0.55739 | -0.45843 | -0.32391 | -0.27288
| 8978 | 0.18201 | -0.12587 | -0.49711 | 0.33045 | 0.084085 | -0.040052 | 0.0048618 | -0.076582 | 0.094517 | -0.23078
| 8979 | -0.69324 | 0.085178 | -0.25428 | 0.023117 | -0.65114 | 0.78858 | 0.26522 | 0.026501 | 0.27041 | 0.69357
| 8980 | 0.06261 | -0.73751 | -0.39033 | -0.29 | 0.18803 | 0.21495 | 0.10731 | -0.47512 | -0.076366 | -0.17
| 8981 | 0.55649 | 0.42668 | -0.17848 | -0.17933 | 0.028867 | -0.12656 | -0.23718 | -0.39576 | 0.050105 | 0.10563
| 8982 | 0.26904 | -0.086819 | -0.16795 | 0.22186 | 0.0027538 | 0.29311 | -0.21101 | 0.3956 | 0.14379 | -0.81752
| 8983 | -0.33886 | -0.56768 | 0.099944 | -0.20282 | -0.76021 | -0.60389 | -0.43458 | -0.7496 | -0.35123 | 0.18495
| 8984 | -0.65547 | -0.25227 | -0.0038574 | -0.31626 | 0.18852 | -0.52094 | 0.098501 | -0.70794 | -0.0755 | 0.35867
| 8985 | 0.10686 | -0.082449 | -0.27771 | 0.056125 | 0.12359 | 0.03434 | -0.15295 | 0.28425 | 0.77977 | -0.40628
| 8986 | 0.3607 | -0.044961 | -0.15887 | 0.17193 | 0.22289 | 0.3116 | -0.4902 | 0.048002 | 0.60974 | -0.39692
| 8987 | 0.78068 | 0.029073 | -0.71487 | 0.2184 | 0.1127 | -0.080381 | -0.01344 | 0.3186 | 0.22586 | 0.14882
| 8988 | 0.8747 | -0.19198 | 0.053903 | 0.14788 | 0.49216 | -0.20094 | 0.13311 | 0.18275 | -0.41051 | -0.07
| 8989 | 0.4531 | 0.7015 | 0.41991 | 0.1162 | 0.023629 | 0.22586 | 0.48144 | -0.83 | -0.094627 | -0.13449
| 8990 | -0.56148 | -0.026809 | -0.67182 | 0.26332 | -0.0063703 | 0.38332 | 0.12404 | -0.62304 | -0.015063 | -0.0068736
| 8991 | -0.96683 | -0.17665 | 0.44206 | 0.042347 | 0.09132 | -0.74603 | 0.21533 | -0.83417 | 0.0039578 | -0.26359
| 8992 | -0.072584 | 0.16519 | 0.30064 | -0.60038 | -0.34785 | -0.43617 | -0.16304 | 0.32081 | -0.72779 | 0.42842
| 8993 | 0.2037 | 0.53924 | -0.12839 | -0.24099 | -0.68647 | -0.19185 | -0.088353 | 0.35867 | -0.11473 | 0.34831
| 8994 | -0.69097 | -0.62198 | -0.33464 | 0.41374 | 0.39213 | 0.29594 | 0.020051 | 0.6241 | 0.248 | -0.61283
| 8995 | -0.73751 | -0.13461 | 0.39246 | 0.31582 | 0.17933 | -0.61257 | -0.11949 | -0.61568 | 0.15188 | 0.59171
| 8996 | 0.018827 | 0.4426 | -0.40865 | -0.1688 | 0.10933 | -0.74096 | 0.0072765 | 0.094738 | -0.027529 | 0.34601
| 8997 | -0.69032 | 0.13288 | 0.19757 | 0.051791 | 0.074311 | -0.23574 | 0.22948 | 0.27868 | -0.51266 | -0.09198
| 8998 | -0.38024 | 0.27137 | 0.67581 | 0.21215 | -0.91574 | -0.49039 | 0.48376 | 0.5922 | 0.054114 | -0.22883
| 8999 | 0.020051 | -0.09066 | 0.077016 | 0.074527 | -0.43352 | -0.47856 | 0.011112 | 0.43423 | -0.34159 | 0.27536
| 9000 | -0.024962 | -0.4194 | -0.12439 | -0.10652 | -0.3129 | 0.50898 | -0.066994 | 0.33871 | -0.61777 | -0.076149
| 9001 | -0.59565 | -0.13681 | 0.22935 | -0.22083 | -0.35046 | 0.28049 | 0.22405 | -0.42026 | -0.19235 | -0.1389
| 9002 | -0.30394 | -0.23796 | -0.048527 | -0.76655 | 0.15448 | 0.0039578 | -0.53621 | -0.1879 | -0.81372 | 0.11484
| 9003 | -0.62919 | -0.019643 | 0.060053 | 0.10473 | -0.48183 | 0.31349 | -0.91456 | 0.16831 | -0.0013509 | 0.60567
| 9004 | -0.66429 | -0.81752 | 0.66489 | -0.5693 | -0.094517 | 0.072045 | 0.040052 | 0.035272 | 0.64546 | -0.51969
| 9005 | -0.28118 | 0.28775 | 0.51143 | -0.071291 | 0.57515 | 0.70352 | 0.46812 | -0.37526 | 0.22083 | -0.93917
| 9006 | -0.53924 | -0.4163 | 0.1533 | -0.25912 | 0.099611 | 0.66758 | 0.0015512 | -0.28216 | 0.78529 | 0.2265
| 9007 | 0.45935 | 0.72414 | -0.35231 | -0.72632 | 0.22896 | -0.51328 | -0.094959 | -0.17702 | 0.18385 | 0.16054
| 9008 | 0.10742 | 0.45622 | 0.59913 | 0.40393 | 0.26658 | 0.51534 | 0.49236 | 0.39213 | -0.37799 | 0.049263
| 9009 | 0.37111 | 0.25549 | 0.19173 | -0.24151 | -0.0083852 | -0.43955 | 0.24654 | 0.30236 | -0.15318 | 0.47531
| 9010 | 0.14871 | 0.16844 | -0.036621 | 0.65605 | -0.164 | 0.47151 | 0.21139 | 0.62946 | -0.5883 | -0.63244
| 9011 | -0.78576 | 0.85269 | -0.5019 | 0.31743 | 0.40611 | -0.8043 | 0.67213 | 0.38787 | -0.4799 | -0.16221
| 9012 | 0.18606 | 0.020051 | -0.09077 | -0.15935 | 0.051897 | 0.94084 | 0.86108 | 0.012832 | 0.39908 | 0.39131
| 9013 | -0.56034 | 0.82084 | 0.057503 | -0.45347 | 0.39428 | 0.057609 | 0.077124 | -0.95 | 0.35031 | -0.024141
| 9014 | -0.33269 | -0.26264 | -0.66549 | -0.016893 | -0.32273 | -0.37558 | -0.051897 | -0.15365 | -0.348 | -0.3025
| 9015 | 0.55785 | -0.44982 | 0.13438 | -0.53021 | -0.22199 | -0.09099 | 0.10978 | -0.4999 | -0.057397 | -0.1879
| 9016 | -0.57163 | 0.5663 | -0.054326 | -0.65 | 0.38137 | -0.26359 | -0.25294 | -0.94432 | -0.048738 | -0.81212
| 9017 | 0.36636 | -0.52094 | 0.10608 | -0.59714 | 0.074743 | -0.094406 | -0.56377 | -0.11304 | 0.22909 | 0.23757
| 9018 | -0.74564 | 0.51657 | 0.53837 | -0.62277 | 0.15661 | 0.95 | 0.17823 | 0.80687 | -0.040573 | 0.66399
| 9019 | -0.27288 | 0.16831 | -0.20194 | -0.43831 | -0.056125 | 0.72632 | -0.038075 | 0.45438 | -0.67243 | -0.38396
| 9020 | 0.37879 | -0.19694 | 0.53021 | 0.40511 | 0.47914 | 0.45991 | -0.022401 | -0.25629 | 0.23718 | -0.43035
| 9021 | -0.50231 | -0.8937 | 0.074203 | -0.012225 | -0.49711 | -0.25858 | -0.0016514 | 0.08485 | 0.32985 | -0.44855
| 9022 | 0.3303 | 0.18006 | -0.048633 | 0.75772 | 0.54448 | 0.094959 | -0.30079 | 0.22109 | 0.011921 | 0.43193
| 9023 | 0.45751 | 0.025474 | 0.13924 | 0.62758 | 0.45585 | 0.032374 | -0.50513 | -0.83237 | -0.85752 | -0.44746
| 9024 | 0.20634 | 0.47455 | 0.16507 | -0.11428 | -0.035168 | -0.1868 | -0.40376 | 0.66879 | -0.046742 | -0.081577
| 9025 | -0.88554 | 0.43264 | 0.54426 | -0.39246 | -0.099833 | 0.0047613 | -0.15496 | -0.45036 | 0.086271 | 0.37032
| 9026 | 0.15024 | -0.7504 | -0.8821 | -0.59073 | 0.51328 | 0.15946 | -0.11541 | 0.0067729 | -0.26034 | -0.42877
| 9027 | -0.094627 | 0.22857 | 0.53 | -0.24747 | 0.21177 | 0.71911 | -0.3537 | 0.33045 | 0.064639 | 0.53213
| 9028 | -0.2377 | -0.29893 | 0.72414 | -0.55379 | 0.85543 | 0.60719 | -0.3167 | -0.23351 | 0.025782 | -0.5003
| 9029 | 0.82536 | -0.53967 | -0.034029 | 0.38543 | 0.40662 | 0.1533 | -0.14965 | 0.023015 | -0.41323 | 0.58927
| 9030 | 0.0015512 | -0.15958 | -0.0728 | -0.053586 | 0.64042 | 0.82252 | 0.13553 | 0.58491 | -0.71804 | -0.17933
| 9031 | -0.39395 | 0.46269 | 0.60491 | -0.10619 | 0.068388 | -0.24814 | -0.050737 | 0.0781 | 0.67335 | 0.18717
| 9032 | 0.096728 | 0.36937 | -0.10518 | 0.21648 | -0.79 | 0.092421 | 0.41905 | 0.42755 | -0.37879 | -0.20081
| 9033 | 0.020766 | -0.36968 | 0.019031 | -0.29822 | -0.41545 | 0.37654 | -0.023527 | 0.071184 | -0.15982 | 0.24257
| 9034 | 0.034754 | 0.060053 | 0.41699 | -0.12496 | -0.21597 | -0.93755 | 0.40326 | -0.70521 | 0.31626 | 0.2278
| 9035 | -0.15567 | 0.2256 | -0.40125 | -0.088573 | -0.00035006 | -0.55335 | 0.8467 | 0.38592 | 0.17302 | -0.15224
| 9036 | -0.08649 | 0.09143 | -0.057503 | 0.082013 | -0.16364 | 0.14882 | -0.89091 | 0.37542 | 0.92063 | 0.33524
| 9037 | -0.053691 | -0.27247 | 0.49572 | 0.40276 | -0.29226 | -0.25562 | 0.41922 | -0.77841 | 0.47417 | -0.31087
| 9038 | -0.31772 | -0.52851 | -0.42009 | 0.030412 | 0.69488 | -0.13415 | 0.42372 | 0.32881 | -0.51061 | -0.35899
| 9039 | -0.0083852 | 0.27813 | 0.37478 | -0.13057 | 0.067637 | -0.52555 | -0.66879 | 0.10395 | 0.25589 | -0.97
| 9040 | 0.33977 | -0.21393 | -0.12382 | 0.38364 | -0.21076 | 0.021072 | 0.67274 | 0.11045 | -0.65258 | -0.64574
| 9041 | 0.55335 | -0.037555 | -0.27979 | -0.52661 | 0.2744 | 0.41991 | -0.7005 | -0.088682 | -0.60719 | -0.2823
| 9042 | 0.6044 | -0.29254 | 0.029897 | -0.96394 | 0.078425 | 0.036102 | 0.45898 | -0.70862 | 0.55875 | 0.54734
| 9043 | 0.44837 | -0.79975 | 0.45806 | -0.087914 | -0.10686 | 0.57047 | -0.67953 | -0.57163 | -0.13959 | 0.5529
| 9044 | 0.83357 | 0.82365 | 0.68235 | -0.55989 | -0.60013 | -0.548 | -0.25227 | -0.46362 | 0.04099 | -0.6786
| 9045 | -0.97 | -0.55379 | -0.046638 | -0.096396 | -0.19384 | 0.34632 | -0.58684 | -0.02722 | 0.63027 | -0.09143
| 9046 | 0.40142 | -0.69097 | 0.0072765 | 0.029279 | -0.40881 | -0.43777 | -0.46793 | -0.023629 | 0.55921 | -0.16507
| 9047 | 0.05158 | 0.16484 | 0.64971 | -0.63054 | 0.65985 | -0.41716 | 0.23521 | 0.91456 | 0.73904 | -0.72779
| 9048 | -0.56884 | 0.49751 | 0.30899 | 0.05899 | -0.11326 | 0.39296 | -0.4668 | 0.51865 | 0.26727 | -0.60541
| 9049 | 0.33917 | -0.9219 | 0.51451 | -0.14227 | -0.079511 | 0.058671 | 0.12828 | -0.3735 | 0.74174 | 0.19994
| 9050 | 0.44782 | 0.60668 | 0.83538 | -0.48765 | 0.038907 | -0.098945 | -0.82252 | -0.24165 | -0.48551 | 0.38608
| 9051 | 0.10529 | 0.0028541 | 0.40025 | -0.14718 | -0.015165 | 0.32494 | 0.10351 | -0.34708 | -0.014353 | -0.14941
| 9052 | 0.57562 | 0.13438 | -0.4206 | 0.57163 | -0.32732 | 0.28972 | 0.24046 | -0.79826 | 0.21508 | -0.31363
| 9053 | -0.10675 | -0.06603 | 0.10072 | -0.19969 | -0.47531 | -0.31407 | -0.2081 | 0.56907 | -0.24204 | 0.40209
| 9054 | -0.14601 | 0.62543 | 0.027118 | -0.12897 | -0.018318 | -0.4979 | -0.009697 | -0.22831 | -0.086819 | 0.076907
| 9055 | -0.73599 | 0.21025 | 0.047582 | 0.14531 | 0.16436 | -0.78905 | -0.52115 | -0.18495 | -0.049684 | -0.58781
| 9056 | -0.022094 | -0.37718 | 0.17265 | 0.11541 | 0.033718 | 0.30136 | -0.014353 | -0.32169 | 0.18201 | -0.020153
| 9057 | 0.079077 | 0.38608 | 0.046533 | 0.66879 | -0.45219 | -0.15555 | 0.073124 | 0.12165 | -0.27096 | -0.39742
| 9058 | -0.25845 | -0.47 | 0.52115 | 0.20621 | -0.81972 | -0.02568 | -0.44656 | -0.24072 | -0.87712 | -0.29381
| 9059 | -0.20634 | 0.063784 | -0.68298 | -0.017198 | 0.18532 | -0.4828 | 0.2326 | 0.069892 | 0.29936 | -0.015673
| 9060 | 0.16819 | -0.23967 | 0.27564 | 0.37799 | 0.23039 | -0.30639 | 0.26128 | 0.037036 | 0.3851 | -0.22948
| 9061 | -0.019949 | 0.13681 | -0.1418 | 0.5347 | -0.39164 | -0.10563 | -0.65547 | -0.61882 | -0.70184 | 0.32494
| 9062 | 0.49394 | -0.0032553 | 0.65547 | -0.10362 | 0.4653 | 0.77 | -0.056867 | 0.4344 | -0.33735 | 0.1473
| 9063 | -0.1868 | -0.58539 | 0.57233 | -0.63217 | 0.67766 | -0.067208 | -0.54492 | -0.22199 | 0.05348 | -0.65605
| 9064 | -0.33344 | 0.072369 | -0.69983 | -0.70589 | -0.003456 | 0.08967 | -0.29594 | -0.4337 | -0.46102 | 0.43387
| 9065 | 0.53043 | -0.3796 | 0.14297 | 0.076149 | -0.30971 | -0.64377 | -0.032374 | 0.18471 | -0.35712 | -0.25656
| 9066 | -0.32391 | 0.092972 | -0.63517 | -0.0029544 | 0.10451 | -0.23065 | 0.364 | 0.53213 | 0.45493 | -0.33164
| 9067 | -0.39659 | 0.63627 | -0.48512 | 0.31349 | -0.4286 | 0.30222 | -0.6952 | 0.66399 | -0.40376 | -0.53128
| 9068 | 0.14835 | 0.1277 | 0.78858 | -0.079294 | 0.17617 | -0.039011 | 0.34205 | 0.016384 | 0.2975 | 0.0019519
| 9069 | -0.3132 | -0.014759 | 0.23378 | -0.2133 | 0.27979 | 0.13426 | 0.43141 | -0.21699 | -0.19 | -0.050842
| 9070 | -0.27661 | 0.42285 | -0.29736 | 0.52873 | 0.7184 | -0.13046 | -0.17799 | 0.78344 | 0.1292 | -0.45898
| 9071 | -0.69455 | 0.27619 | -0.30279 | -0.17799 | -0.30351 | 0.11067 | -0.27578 | -0.26932 | 0.1091 | -0.41425
| 9072 | -0.19782 | 0.51927 | 0.12484 | -0.17181 | -0.018522 | 0.38251 | -0.61 | 0.029794 | 0.76827 | -0.22598
| 9073 | -0.9005 | 0.043182 | -0.12725 | 0.5013 | 0.38024 | 0.32628 | -0.10619 | 0.16209 | -0.050211 | -0.50573
| 9074 | -0.50351 | 0.044333 | -0.22482 | 0.13901 | -0.19944 | 0.72596 | -0.10787 | -0.57822 | -0.06293 | -0.0064709
| 9075 | -0.41871 | -0.11067 | 0.034961 | -0.10888 | -0.064639 | -0.10753 | 0.47038 | 0.73713 | -0.3129 | -0.55853
| 9076 | -0.20407 | -0.26672 | -0.19 | -0.39825 | -0.0082843 | -0.083758 | -0.47398 | -0.87876 | -0.3767 | -0.00075028
| 9077 | 0.30624 | -0.12484 | 0.94432 | 0.40292 | -0.72233 | 0.71627 | -0.076258 | -0.16819 | -0.13484 | -0.17265
| 9078 | -0.68204 | -0.59 | 0.094075 | 0.093965 | 0.79678 | -0.1694 | -0.83357 | 0.13577 | 0.164 | -0.30538
| 9079 | -0.21546 | 0.1565 | 0.51513 | 0.55875 | 0.034443 | -0.75322 | -0.17084 | 0.52597 | 0.27854 | 0.71663
| 9080 | -0.069355 | -0.1221 | -0.11926 | -0.74643 | 0.8422 | 0.14742 | 0.088463 | -0.41494 | 0.0023528 | -0.0032553
| 9081 | -0.12496 | 0.14344 | -0.046742 | -0.43211 | 0.033822 | 0.14297 | 0.015267 | 0.32836 | 0.48338 | -0.14847
| 9082 | -0.60188 | 0.51307 | -0.42476 | -0.13808 | -0.17726 | 0.056973 | -0.035479 | -0.20332 | -0.19869 | -0.35758
| 9083 | 0.0016514 | -0.27371 | 0.15271 | -0.18006 | -0.40628 | -0.31978 | -0.2047 | 0.77306 | -0.6833 | 0.48922
| 9084 | -0.85134 | -0.010606 | -0.70251 | 0.13299 | -0.6162 | -0.58854 | 0.37879 | 0.51184 | -0.086928 | -0.79384
| 9085 | 0.43653 | 0.67427 | 0.30581 | 0.41511 | -0.58903 | 0.11462 | 0.37032 | 0.16519 | -0.33479 | 0.89656
| 9086 | -0.14274 | 0.26522 | 0.3309 | 0.35556 | 0.40983 | 0.21127 | 0.2476 | -0.3651 | 0.46981 | -0.85134
| 9087 | -0.83599 | -0.76104 | 0.13138 | 0.85893 | 0.88042 | -0.45954 | -0.36747 | 0.051897 | -0.44134 | 0.10955
| 9088 | 0.52031 | -0.14882 | -0.26101 | -0.025474 | -0.11688 | -0.42476 | -0.3477 | 0.47265 | -0.046638 | 0.12667
| 9089 | 0.71557 | 0.55089 | 0.16627 | 0.1879 | -0.90566 | 0.46925 | 0.19806 | 0.43405 | -0.68141 | 0.41085
| 9090 | -0.83177 | -0.40142 | -0.73904 | 0.038907 | 0.40075 | -0.25388 | -0.7839 | -0.65143 | 0.006169 | -0.4801
| 9091 | 0.033718 | 0.16185 | -0.0045604 | -0.4801 | -0.43317 | 0.19495 | 0.45769 | -0.054326 | 0.30423 | 0.14894
| 9092 | 0.51844 | -0.27495 | -0.33015 | -0.17592 | 0.42511 | 0.56285 | 0.011415 | -0.28453 | 0.35062 | -0.70931
| 9093 | -0.075716 | 0.10921 | 0.16388 | -0.5412 | 0.15306 | 0.13 | -0.59863 | -0.59294 | 0.92859 | 0.42407
| 9094 | 0.02897 | 0.28285 | -0.18459 | 0.78023 | 0.5583 | -0.43141 | 0.74096 | 0.21406 | -0.20006 | 0.52851
| 9095 | 0.34969 | 0.082558 | -0.51307 | 0.31058 | 0.71487 | -0.058671 | -0.8995 | -0.09165 | 0.50291 | 0.86252
| 9096 | 0.14076 | -0.84801 | -0.055172 | 0.014353 | 0.18606 | 0.080707 | -0.09055 | 0.54712 | 0.0062697 | -0.29282
| 9097 | 0.73904 | -0.38218 | 0.44188 | -0.19148 | -0.09121 | -0.74761 | 0.65172 | 0.38186 | -0.084631 | -0.021276
| 9098 | -0.45695 | -0.027118 | 0.64405 | -0.55921 | -0.4826 | -0.034547 | 0.23849 | -0.44134 | -0.1245 | -0.099278
| 9099 | -0.51678 | 0.58155 | 0.23091 | 0.63654 | 0.30322 | -0.14601 | -0.7488 | 0.13994 | 0.14976 | -0.064425
| 9100 | -0.17982 | 0.15259 | -0.23665 | 0.36149 | 0.41442 | 0.20962 | -0.26223 | -0.11248 | 0.10384 | -0.02322
| 9101 | -0.072153 | 0.09055 | -0.82308 | -0.034443 | 0.6257 | 0.39461 | 0.4993 | 0.13739 | 0.33932 | -0.1628
| 9102 | 0.41682 | -0.049789 | 0.080816 | -0.038075 | 0.2488 | 0.23091 | -0.059309 | 0.18312 | 0.099944 | -0.28873
| 9103 | 0.19545 | 0.4826 | -0.041616 | -0.50614 | -0.038075 | 0.30783 | 0.30899 | 0.72486 | -0.13392 | -0.10418
| 9104 | -0.32037 | -0.86108 | -0.78622 | -0.0046609 | -0.06165 | -0.15012 | 0.50533 | -0.14355 | -0.12622 | -0.45954
| 9105 | -0.067852 | 0.029794 | -0.12199 | -0.16795 | 0.44367 | -0.11034 | 0.71347 | -0.036724 | 0.075068 | 0.55312
| 9106 | -0.12188 | -0.035687 | -0.074851 | -0.15792 | -0.62865 | -0.41425 | 0.093082 | 0.16591 | -0.13242 | -0.37207
| 9107 | 0.50331 | -0.93144 | 0.46906 | -0.35154 | 0.66728 | -0.46158 | -0.17411 | 0.17386 | -0.76272 | 0.21968
| 9108 | 0.18361 | -0.037036 | -0.49236 | 0.0781 | -0.12097 | -0.3662 | -0.68361 | -0.28118 | 0.18877 | 0.20508
| 9109 | -0.45567 | 0.009697 | -0.38315 | 0.097947 | -0.23052 | -0.25214 | 0.083649 | 0.23169 | -0.53859 | -0.085178
| 9110 | -0.079185 | -0.28202 | 0.05899 | -0.82196 | -0.39477 | -0.023117 | 0.17362 | 0.38673 | -0.083212 | 0.079402
| 9111 | -0.58878 | -0.076149 | 0.25214 | 0.09088 | 0.47645 | -0.10978 | -0.12473 | -0.05899 | 0.22573 | 0.40595
| 9112 | 0.14402 | 0.45493 | 0.092311 | -0.068603 | -0.96394 | -0.37992 | -0.035998 | -0.8755 | -0.052213 | -0.69553
| 9113 | -0.013542 | 0.047162 | -0.15839 | 0.5458 | -0.20861 | -0.14965 | -0.16819 | 0.070861 | 0.37016 | -0.40393
| 9114 | 0.14882 | 0.83477 | 0.12702 | 0.28397 | 0.11552 | 0.48804 | -0.34571 | 0.1962 | -0.74329 | -0.69097
| 9115 | -0.32081 | -0.2119 | -0.36541 | -0.58515 | 0.17145 | 0.10529 | 0.21981 | -0.28733 | -0.1425 | 0.14695
| 9116 | 0.63654 | -0.7042 | -0.0004501 | -0.76357 | 0.27467 | -0.34969 | -0.03 | 0.11643 | 0.19757 | -0.039115
| 9117 | 0.21955 | -0.35852 | -0.039427 | -0.030722 | 0.44313 | -0.27123 | 0.18324 | -0.26604 | 0.67427 | -0.19458
| 9118 | 0.10608 | -0.91225 | 0.42755 | 0.31509 | 0.15923 | -0.06197 | -0.95 | 0.42078 | -0.80635 | 0.22186
| 9119 | 0.42546 | 0.04266 | 0.75979 | 0.12885 | -0.18864 | -0.46943 | -0.068818 | 0.24323 | -0.035272 | -0.024756
| 9120 | -0.14215 | 0.72889 | 0.50939 | -0.24535 | 0.45567 | -0.076149 | 0.63599 | -0.026296 | 0.0050628 | 0.2674
| 9121 | -0.6995 | 0.24138 | 0.43158 | 0.076474 | 0.29056 | 0.09088 | 0.52682 | 0.7504 | 0.14041 | 0.21981
| 9122 | -0.81972 | -0.26836 | 0.30437 | -0.11643 | 0.10596 | -0.053058 | -0.3369 | 0.46943 | 0.15567 | 0.10675
| 9123 | 0.24973 | -0.51451 | -0.20558 | 0.43529 | 0.5608 | -0.57374 | -0.79048 | -0.39 | 0.23065 | 0.05496
| 9124 | -0.42528 | -0.1758 | -0.68016 | 0.3303 | -0.023936 | 0.23391 | 0.67829 | -0.054431 | 0.12599 | 0.12324
| 9125 | 0.37863 | 0.33389 | -0.48338 | 0.16663 | 0.23574 | 0.1418 | 0.11157 | -0.37207 | -0.55739 | -0.21089
| 9126 | 0.063144 | 0.43511 | 0.4995 | -0.24178 | 0.30624 | -0.11248 | -0.024962 | -0.44224 | -0.48222 | -0.046742
| 9127 | 0.51041 | 0.75485 | 0.12943 | -0.43317 | -0.46046 | 0.086819 | -0.42493 | -0.9245 | -0.26156 | 0.0054649
| 9128 | 0.50715 | -0.54624 | -0.48804 | -0.14648 | 0.60541 | 0.18055 | -0.10451 | 0.65576 | -0.148 | 0.021072
| 9129 | -0.19074 | 0.84736 | -0.57869 | 0.10485 | 0.088024 | 0.047057 | -0.60188 | 0.59098 | 0.03974 | -0.10284
| 9130 | 0.21763 | -0.28341 | 0.32406 | -0.10261 | -0.42233 | -0.0082843 | 0.18446 | 0.10083 | -0.48512 | 0.77087
| 9131 | 0.5714 | -0.64014 | -0.027015 | 0.027323 | 0.19981 | 0.27357 | -0.34433 | 0.45861 | 0.037555 | 0.016486
| 9132 | 0.57656 | -0.087038 | 0.26617 | 0.31949 | 0.25174 | 0.57257 | 0.14262 | 0.014049 | -0.37478 | -0.35618
| 9133 | 0.20583 | -0.63244 | -0.38592 | 0.10787 | 0.22573 | -0.14695 | -0.014454 | -0.10473 | -0.57374 | -0.73561
| 9134 | 0.095069 | 0.0027538 | -0.18201 | -0.42476 | -0.59417 | -0.42009 | -0.39742 | 0.36321 | 0.18618 | 0.37606
| 9135 | 0.16783 | -0.46474 | -0.54492 | 0.31392 | -0.054326 | -0.26441 | 0.39593 | 0.20282 | 0.18766 | 0.80895
| 9136 | 0.31538 | 0.48125 | 0.28453 | -0.039844 | 0.63462 | -0.015978 | -0.40966 | -0.40359 | 0.42737 | 0.21572
| 9137 | 0.80328 | -0.097947 | -0.030309 | 0.13265 | -0.68711 | 0.87233 | 0.038491 | 0.70117 | -0.088682 | -0.47818
| 9138 | -0.05814 | -0.35308 | 0.52894 | 0.58467 | 0.087914 | 0.82941 | -0.20458 | -0.86923 | -0.62758 | -0.62892
| 9139 | 0.37239 | 0.083976 | -0.58515 | 0.48532 | -0.11293 | -0.58636 | -0.30826 | -0.054855 | -0.13253 | -0.28551
| 9140 | -0.0079819 | 0.57233 | -0.26115 | 0.67612 | -0.2975 | -0.25993 | 0.13542 | 0.15484 | -0.35541 | -0.57633
| 9141 | -0.44529 | 0.29537 | -0.14835 | -0.39148 | 0.6077 | -0.16316 | -0.14111 | 0.079728 | -0.24376 | -0.71452
| 9142 | 0.28873 | 0.56745 | 0.44457 | 0.16292 | 0.16543 | 0.65029 | -0.21215 | -0.25468 | 0.52492 | 0.09
| 9143 | -0.11926 | -0.057822 | -0.076366 | -0.027529 | -0.32613 | -0.16831 | -0.03579 | -0.89091 | -0.2711 | 0.34494
| 9144 | -0.17483 | 0.036309 | 0.47057 | 0.1308 | 0.53729 | -0.16868 | 0.43653 | -0.6703 | 0.19844 | 0.10228
| 9145 | 0.071938 | 0.039427 | -0.54624 | -0.16149 | -0.041512 | -0.052741 | 0.047372 | -0.64321 | 0.13242 | 0.036102
| 9146 | -0.37606 | 0.13634 | -0.41716 | -0.06678 | -0.70862 | -0.3864 | -0.13104 | 0.73111 | 0.045904 | 0.30884
| 9147 | -0.58781 | -0.61257 | 0.44045 | 0.28817 | -0.39131 | 0.17568 | 0.25482 | 0.71557 | 0.14636 | -0.16412
| 9148 | 0.68016 | -0.09132 | 0.38722 | -0.43105 | -0.66638 | -0.044542 | 0.037659 | -0.43423 | -0.60213 | 0.88467
| 9149 | -0.28607 | 0.53881 | -0.1261 | -0.61438 | -0.051791 | -0.82308 | 0.12496 | -0.68172 | -0.20432 | -0.14788
| 9150 | -0.018012 | 0.01842 | -0.37911 | 0.11926 | 0.3804 | -0.10017 | 0.5245 | 0.18263 | 0.8618 | 0.80277
| 9151 | 0.21343 | 0.072692 | -0.29836 | -0.62784 | -0.15472 | 0.56814 | -0.21866 | -0.78716 | 0.04172 | 0.55672
| 9152 | 0.47227 | -0.49572 | 0.48726 | 0.43742 | -0.6149 | -0.40679 | -0.71522 | -0.25 | -0.5141 | -0.32658
| 9153 | -0.45401 | 0.46699 | 0.24614 | -0.64886 | 0.54185 | -0.1425 | 0.31495 | -0.67519 | -0.16711 | -0.24707
| 9154 | -0.09033 | 0.068925 | -0.30451 | 0.13994 | 0.76612 | 0.35541 | 0.044019 | -0.36873 | 0.59318 | -0.073339
| 9155 | 0.38771 | -0.22935 | 0.152 | -0.081142 | 0.5959 | 0.45622 | -0.44439 | -0.50452 | -0.22754 | 0.010202
| 9156 | 0.68775 | -0.06957 | -0.68488 | -0.18116 | -0.09529 | 0.86696 | 0.017503 | -0.085943 | 0.29212 | 0.03465
| 9157 | 0.46718 | -0.38121 | -0.46232 | 0.1389 | -0.45917 | -0.3366 | -0.0015512 | 0.067423 | -0.092421 | 0.068603
| 9158 | 0.065174 | -0.48396 | -0.37159 | -0.079402 | 0.051159 | -0.12416 | -0.12644 | 0.13449 | 0.38137 | 0.60846
| 9159 | 0.098169 | -0.039948 | -0.46195 | -0.00065021 | -0.37927 | 0.2119 | -0.4286 | 0.47189 | -0.32911 | 0.2042
| 9160 | 0.14239 | 0.56791 | -0.85405 | -0.39411 | 0.5735 | -0.33404 | 0.68839 | -0.33992 | 0.24787 | -0.548
| 9161 | -0.52219 | -0.0050628 | 0.33179 | -0.70897 | -0.13553 | 0.51102 | 0.66578 | -0.5436 | -0.72125 | 0.29765
| 9162 | 0.32717 | -0.046533 | -0.33509 | 0.75322 | 0.15614 | -0.20294 | 0.19545 | -0.25441 | 0.72669 | -0.56194
| 9163 | -0.69619 | -0.63054 | 0.62092 | -0.074851 | 0.68743 | -0.59196 | 0.35883 | -0.046008 | 0.75731 | 0.39428
| 9164 | -0.29085 | -0.54163 | -0.76315 | 0.0080827 | -0.61829 | -0.71627 | 0.017605 | 0.41682 | -0.0055655 | -0.36731
| 9165 | -0.57941 | -0.13276 | -0.77483 | 0.27385 | 0.047372 | 0.2402 | 0.14215 | 0.034133 | -0.42407 | 0.26101
| 9166 | 0.4078 | -0.51041 | -0.45843 | 0.16555 | 0.32643 | 0.45935 | -0.084631 | 0.059309 | -0.50939 | -0.55875
| 9167 | 0.19384 | 0.079185 | -0.2147 | -0.23993 | 0.2265 | 0.48961 | -0.30884 | -0.43724 | 0.018216 | -0.14706
| 9168 | -0.14519 | -0.0036567 | 0.10899 | 0.96394 | 0.1578 | -0.79975 | -0.042764 | -0.41682 | 0.16412 | 0.11428
| 9169 | -0.67922 | -0.30351 | 0.53664 | 0.17738 | -0.28733 | -0.0047613 | -0.57822 | 0.014962 | -0.28341 | 0.30236
| 9170 | -0.47722 | -0.58012 | 0.41819 | -0.20232 | 0.30079 | 0.82084 | 0.039323 | -0.30913 | 0.548 | 0.35774
| 9171 | -0.025885 | 0.29836 | 0.70083 | 0.23744 | -0.41648 | 0.27274 | -0.17896 | 0.52703 | 0.27123 | 0.18214
| 9172 | 0.72089 | 0.21687 | -0.59294 | -0.52724 | 0.60617 | -0.61387 | -0.22573 | 0.2147 | 0.39411 | -0.1884
| 9173 | 0.40662 | -0.01547 | -0.25953 | 0.050316 | 0.21051 | -0.39411 | -0.063357 | 0.86108 | 0.74407 | -0.41
| 9174 | -0.15118 | -0.062077 | -0.22276 | 0.46195 | 0.037244 | -0.06753 | 0.15342 | 0.048843 | -0.69784 | -0.27619
| 9175 | 0.43035 | 0.37799 | 0.51082 | 0.36478 | -0.78344 | 0.33045 | -0.42199 | -0.2488 | -0.67922 | 0.23312
| 9176 | 0.17677 | 0.09033 | -0.033822 | -0.55853 | 0.23508 | -0.075716 | -0.17982 | 0.55134 | -0.21241 | -0.74019
| 9177 | 0.12897 | -0.066137 | -0.68807 | 0.33224 | 0.41102 | -0.071076 | 0.27385 | 0.48863 | 0.86252 | 0.68968
| 9178 | -0.03465 | -0.28118 | 0.0045604 | 0.2598 | -0.023527 | 0.025782 | -0.45677 | 0.044961 | 0.25307 | -0.58976
| 9179 | 0.62092 | -0.16042 | -0.32569 | 0.10944 | -0.12874 | 0.70862 | -0.46437 | -0.46325 | 0.14965 | 0.27
| 9180 | -0.16316 | -0.65345 | -0.85964 | -0.84348 | -0.57846 | -0.20332 | -0.20684 | 0.095843 | -0.15106 | 0.34114
| 9181 | -0.14472 | -0.055278 | 0.6833 | -0.042869 | 0.17945 | 0.51 | -0.45055 | -0.13265 | 0.16042 | -0.19185
| 9182 | 0.43053 | -0.38137 | 0.064532 | 0.70017 | 0.079294 | -0.63326 | -0.36905 | -0.046533 | -0.21508 | 0.070968
| 9183 | -0.10843 | -0.57727 | 0.4828 | 0.15935 | -0.28859 | 0.43 | 0.6952 | 0.43866 | -0.14683 | 0.085506
| 9184 | -0.11022 | -0.043391 | 0.084304 | -0.0021523 | -0.12966 | 0.1729 | -0.29864 | -0.68583 | -0.30466 | -0.26986
| 9185 | 0.29679 | 0.10473 | -0.33329 | -0.19025 | -0.21968 | -0.80277 | 0.39659 | -0.11983 | 0.42181 | -0.31949
| 9186 | 0.14099 | 0.14601 | 0.25926 | 0.01344 | -0.6044 | 0.45456 | 0.23587 | 0.23613 | 0.2496 | 0.75485
| 9187 | -0.029279 | 0.55044 | 0.61725 | 0.19969 | 0.4985 | 0.074311 | -0.41528 | -0.45861 | -0.14906 | -0.41613
| 9188 | -0.4258 | 0.12885 | 0.3048 | -0.29765 | -0.016893 | -0.14613 | 0.46456 | 0.06678 | -0.16928 | -0.78206
| 9189 | -0.3618 | 0.32881 | 0.027529 | 0.14425 | 0.50918 | -0.064639 | -0.32717 | -0.25495 | -0.065816 | -0.13507
| 9190 | 0.26183 | -0.30769 | -0.18581 | 0.035583 | -0.078642 | -0.084522 | 0.65809 | -0.30971 | 0.10406 | 0.19384
| 9191 | 0.16964 | 0.56125 | 0.35386 | -0.34739 | -0.06496 | -0.28817 | -0.36857 | 0.087586 | -0.30164 | 0.15247
| 9192 | 0.11552 | 0.52979 | -0.063784 | 0.13913 | -0.065709 | 0.15271 | 0.64405 | -0.20019 | -0.073016 | -0.12851
| 9193 | -0.23378 | -0.15401 | -0.29056 | 0.34418 | 0.22431 | 0.51699 | -0.050211 | 0.34662 | -0.13832 | 0.093634
| 9194 | -0.22987 | 0.53128 | -0.12622 | -0.037244 | 0.075933 | 0.075068 | 0.37622 | -0.7015 | 0.1879 | 0.084631
| 9195 | -0.28453 | -0.32332 | -0.23652 | 0.45164 | 0.41905 | 0.61516 | 0.28439 | 0.20181 | -0.09011 | -0.32376
| 9196 | 0.29936 | -0.51616 | 0.9134 | 0.17411 | 0.12324 | -0.5707 | -0.68393 | -0.16484 | 0.45365 | 0.56011
| 9197 | 0.17775 | 0.3087 | 0.080272 | -0.55672 | -0.0995 | -0.37064 | 0.0067729 | 0.26223 | -0.032788 | -0.47952
| 9198 | 0.040156 | -0.27151 | 0.95 | -0.56838 | -0.59913 | -0.75282 | -0.46456 | 0.016994 | -0.28327 | 0.24774
| 9199 | -0.37175 | -0.079294 | 0.54978 | -0.4265 | 0.46981 | -0.31232 | 0.41562 | 0.36133 | -0.031238 | 0.63217
| 9200 | 0.082885 | 0.55 | -0.049263 | -0.046428 | 0.32569 | -0.11665 | -0.098279 | 0.8148 | 0.13936 | -0.4981
| 9201 | 0.050632 | -0.42043 | 0.079946 | 0.57444 | -0.4206 | -0.48551 | 0.4755 | -0.055278 | -0.20836 | 0.35541
| 9202 | 0.057822 | 0.4417 | -0.26795 | 0.13983 | 0.17205 | 0.49177 | -0.30899 | -0.15899 | -0.39494 | -0.0079819
| 9203 | -0.14589 | -0.082122 | 0.27882 | 0.73373 | -0.10552 | 0.2985 | -0.31305 | -0.28691 | -0.14099 | 0.34068
| 9204 | -0.23391 | 0.3294 | 0.84157 | 0.09022 | -0.62171 | -0.47094 | 0.81862 | -0.082013 | 0.48067 | 0.48746
| 9205 | 0.035583 | 0.44457 | -0.53107 | 0.10507 | 0.041094 | 0.69817 | -0.27661 | -0.59963 | -0.32524 | -0.3061
| 9206 | 0.029588 | -0.46737 | 0.21981 | -0.073771 | 0.54294 | 0.1957 | -0.083976 | 0.60516 | 0.42965 | -0.032891
| 9207 | -0.49059 | -0.14227 | -0.45658 | -0.38008 | -0.40746 | -0.34586 | 0.85067 | 0.15614 | -0.46605 | 0.65663
| 9208 | 0.44439 | 0.22508 | -0.39477 | -0.23312 | -0.037244 | 0.11079 | -0.72963 | -0.45164 | -0.077016 | -0.62171
| 9209 | 0.10395 | 0.5436 | -0.27027 | -0.136 | 0.37302 | -0.16555 | -0.67121 | 0.48648 | 0.71911 | 0.22637
| 9210 | 0.74682 | -0.80947 | 0.12828 | 0.10664 | 0.09121 | 0.19247 | 0.60113 | 0.082558 | 0.31465 | -0.14507
| 9211 | -0.64687 | 0.26359 | -0.99 | -0.26904 | -0.33134 | 0.042451 | 0.9134 | 0.34114 | -0.34372 | -0.78952
| 9212 | -0.79531 | -0.90566 | 0.33962 | -0.22883 | -0.63903 | 0.082885 | -0.36243 | -0.53989 | -0.1015 | 0.28958
| 9213 | -0.59466 | 0.010606 | -0.28257 | 0.42476 | 0.35914 | -0.25697 | 0.45347 | 0.57893 | -0.61672 | -0.21776
| 9214 | 0.42424 | -0.69983 | -0.085068 | 0.24416 | -0.18901 | -0.48144 | 0.43035 | 0.26863 | 0.7076 | -0.13288
| 9215 | -0.26128 | -0.37799 | -0.12977 | 0.35231 | 0.45237 | 0.23156 | -0.10989 | -0.95877 | 0.44619 | 0.093523
| 9216 | 0.5098 | -0.73223 | -0.37318 | 0.55357 | -0.51927 | -0.73149 | -0.5707 | -0.11858 | 0.40494 | -0.57303
| 9217 | -0.38332 | -0.19906 | -0.20886 | -0.52094 | -0.25093 | -0.036205 | 0.13322 | 0.52303 | 0.64687 | 0.15578
| 9218 | 0.49572 | -0.070215 | -0.0013509 | -0.2924 | -0.67458 | -0.20609 | 0.6241 | 0.29765 | 0.048738 | -0.068174
| 9219 | 0.92063 | 0.1962 | 0.18165 | -0.23417 | 0.19732 | 0.10094 | 0.40242 | 0.057503 | -0.17399 | 0.023834
| 9220 | 0.25629 | -0.13611 | -0.19744 | 0.80895 | 0.3038 | -0.073339 | -0.060479 | -0.35494 | -0.14695 | 0.52429
| 9221 | -0.054008 | 0.56491 | -0.62892 | 0.52767 | 0.49374 | 0.59368 | 0.12839 | 0.34816 | 0.082558 | -0.64461
| 9222 | 0.66849 | 0.17508 | -0.21381 | -0.19433 | -0.37638 | -0.089231 | -0.35836 | -0.32509 | 0.22896 | 0.41768
| 9223 | -0.5806 | -0.5174 | 0.09099 | -0.027118 | -0.26645 | 0.074419 | 0.013947 | -0.5469 | 0.24416 | -0.2427
| 9224 | 0.08343 | 0.44565 | -0.22122 | 0.0021523 | 0.73981 | 0.42807 | 0.46046 | -0.1797 | 0.2161 | 0.09121
| 9225 | -0.23469 | -0.26427 | 0.34357 | -0.22922 | 0.066458 | 0.12587 | 0.11146 | 0.05348 | 0.14215 | 0.1375
| 9226 | -0.003456 | -0.28132 | 0.57964 | -0.84605 | -0.2602 | -0.45273 | -0.11699 | -0.4564 | 0.61934 | -0.75526
| 9227 | -0.3129 | 0.89753 | 0.76063 | 0.018216 | -0.10317 | -0.10664 | 0.53171 | -0.85337 | -0.60898 | 0.7429
| 9228 | -0.25602 | 0.30567 | 0.28327 | -0.17109 | 0.61908 | 0.73486 | -0.6631 | 0.17775 | 0.85269 | -0.66459
| 9229 | -0.36211 | -0.03974 | 0.22728 | -0.43759 | -0.31963 | -0.0060684 | -0.29141 | -0.60617 | 0.0080827 | 0.24138
| 9230 | -0.024859 | 0.025167 | 0.56514 | -0.067316 | -0.40159 | -0.071399 | 0.15531 | -0.0077803 | 0.36415 | 0.61206
| 9231 | -0.69652 | -0.50231 | 0.01791 | -0.28873 | 0.015368 | 0.1646 | -0.25468 | 0.028764 | -0.87077 | -0.51472
| 9232 | -0.015876 | 0.87631 | 0.11733 | 0.69488 | 0.14087 | 0.0060684 | 0.31714 | 0.55379 | 0.53902 | -0.093082
| 9233 | -0.71208 | -0.6077 | -0.073016 | 0.21521 | -0.19062 | -0.28859 | 0.34969 | 0.012731 | -0.1634 | -0.096064
| 9234 | -0.28593 | -0.47588 | -0.61882 | 0.089231 | 0.37638 | -0.12165 | 0.57 | -0.27993 | -0.2625 | 0.43476
| 9235 | -0.17 | 0.63353 | 0.035272 | 0.58805 | -0.22689 | -0.38332 | 0.67704 | -0.63353 | 0.032684 | 0.37558
| 9236 | 0.41888 | -0.33796 | -0.33134 | 0.29836 | 0.74058 | 0.13762 | -0.43848 | 0.24191 | -0.12725 | -0.57846
| 9237 | 0.21814 | -0.16807 | 0.05422 | 0.14648 | 0.13843 | 0.14578 | 0.59147 | -0.09 | 0.54624 | 0.60694
| 9238 | 0.014962 | 0.30942 | 0.71035 | -0.085615 | 0.38853 | -0.13994 | 0.4902 | -0.50392 | 0.18397 | -0.35805
| 9239 | 0.11835 | 0.16376 | 0.40831 | 0.33284 | -0.40848 | 0.43831 | -0.025577 | 0.086819 | 0.59269 | -0.60389
| 9240 | 0.67984 | 0.74135 | 0.38153 | 0.61051 | 0.29694 | -0.59838 | -0.099722 | 0.56102 | -0.16567 | 0.28747
| 9241 | -0.64744 | 0.6233 | -0.3312 | -0.33811 | 0.91815 | 0.46887 | -0.20697 | -0.73713 | -0.36794 | -0.038699
| 9242 | 0.12599 | 0.11677 | 0.10429 | 0.72852 | 0.63958 | 0.34724 | 0.22547 | -0.45677 | -0.037971 | -0.19732
| 9243 | 0.021583 | 0.6265 | -0.26196 | -0.14192 | -0.24416 | 0.29197 | 0.6382 | 0.41017 | -0.11688 | -0.62437
| 9244 | 0.13994 | -0.10944 | -0.041512 | 0.18263 | 0.44619 | 0.86108 | -0.041512 | -0.068603 | 0.18422 | -0.051053
| 9245 | 0.60415 | 0.14894 | 0.69162 | -0.21482 | -0.77528 | -0.18275 | 0.13832 | 0.78905 | 0.14988 | 0.24178
| 9246 | 0.64349 | -0.47208 | 0.17738 | 0.11903 | 0.11067 | 0.13553 | 0.57421 | -0.43848 | 0.21699 | -0.62758
| 9247 | -0.38089 | 0.12233 | 0.011617 | 0.37927 | -0.58878 | 0.18581 | 0.33871 | 0.15496 | -0.12908 | -0.82365
| 9248 | -0.22547 | 0.21279 | -0.61987 | -0.91574 | 0.72779 | 0.33179 | -0.21127 | -0.11326 | 0.62784 | -0.5656
| 9249 | -0.76021 | -0.38934 | 0.025988 | 0.26264 | -0.44403 | 0.51637 | 0.03579 | 0.017401 | -0.62145 | -0.076691
| 9250 | 0.030103 | 0.69129 | 0.50331 | 0.3817 | -0.095511 | -0.10284 | -0.3186 | 0.69553 | 0.27564 | -0.16125
| 9251 | 0.69065 | 0.048212 | -0.54163 | -0.2052 | -0.86847 | -0.33509 | 0.54712 | -0.20006 | 0.08136 | -0.29921
| 9252 | 0.5883 | 0.5412 | 0.19297 | 0.24681 | -0.53449 | -0.13797 | -0.07183 | -0.44242 | 0.63299 | -0.074959
| 9253 | -0.70966 | 0.43493 | 0.29226 | -0.32287 | 0.50311 | -0.82196 | -0.16232 | -0.35062 | -0.58107 | 0.69162
| 9254 | -0.59368 | -0.13173 | 0.82365 | -0.19346 | -0.75772 | 0.10451 | -0.083649 | -0.38105 | 0.36604 | 0.48106
| 9255 | 0.55966 | 0.18606 | -0.16125 | -0.11869 | 0.52324 | 0.47798 | 0.22689 | 0.23928 | -0.55627 | -0.86036
| 9256 | -0.25831 | -0.26808 | -0.46102 | 0.55604 | 0.20031 | 0.15935 | -0.37815 | -0.28859 | 0.030103 | 0.17169
| 9257 | 0.70117 | 0.10328 | 0.20583 | -0.25027 | -0.27123 | -0.54404 | 0.008486 | 0.16436 | -0.0059678 | -0.67984
| 9258 | 0.54229 | 0.051264 | 0.36039 | 0.2744 | 0.54273 | 0.39992 | -0.1375 | 0.018929 | -0.32539 | 0.15342
| 9259 | -0.79875 | -0.6233 | 0.49078 | -0.18667 | 0.5102 | 0.0016514 | 0.06016 | 0.31349 | -0.80277 | 0.37398
| 9260 | -0.1005 | 0.1769 | 0.021685 | 0.047057 | 0.70691 | -0.11405 | 0.37 | 0.054008 | -0.41579 | -0.062717
| 9261 | -0.14882 | -0.33856 | 0.65143 | -0.35092 | 0.077558 | -0.63931 | 0.68488 | -0.35899 | -0.92063 | 0.062823
| 9262 | -0.39742 | -0.27674 | -0.14041 | -0.91112 | -0.73866 | -0.098723 | -0.74329 | -0.10697 | 0.14554 | 0.37478
| 9263 | -0.28986 | 0.0044599 | 0.27688 | -0.058034 | -0.60719 | 0.37254 | 0.062823 | -0.26959 | 0.54536 | 0.19408
| 9264 | -0.41905 | 0.39279 | -0.13577 | 0.58515 | 0.42528 | 0.46121 | -0.53881 | 0.28495 | -0.51041 | -0.34938
| 9265 | 0.28299 | 0.54867 | 0.42216 | -0.42807 | 0.47474 | -0.55537 | -0.29637 | -0.17884 | -0.10418 | 0.42372
| 9266 | -0.019847 | 0.088134 | 0.42947 | 0.070538 | 0.11169 | -0.33314 | 0.1473 | -0.13 | -0.26877 | -0.27716
| 9267 | -0.81697 | 0.31014 | -0.42147 | -0.61283 | 0.57585 | -0.43018 | -0.22624 | -0.2773 | -0.44457 | -0.16567
| 9268 | -0.10809 | -0.46661 | 0.36353 | 0.20483 | -0.69553 | 0.38348 | -0.60289 | -0.49433 | -0.57751 | 0.6939
| 9269 | 0.16352 | 0.035272 | -0.42459 | -0.34053 | -0.0072765 | -0.42493 | 0.29268 | 0.060905 | -0.18914 | -0.34846
| 9270 | -0.63792 | -0.88554 | -0.22058 | -0.62039 | 0.49413 | 0.26386 | -0.19657 | -0.056761 | -0.31043 | 0.4717
| 9271 | 0.83177 | 0.28397 | -0.064639 | -0.31378 | 0.35696 | -0.1473 | -0.32214 | -0.19533 | 0.15212 | -0.64631
| 9272 | -0.0087886 | -0.17495 | 0.25858 | 0.5728 | 0.5003 | -0.44818 | 0.28509 | 0.18827 | -0.55582 | 0.28593
| 9273 | 0.20735 | 0.33134 | -0.40008 | 0.77218 | -0.84933 | -0.1005 | -0.13832 | 0.75161 | -0.20558 | -0.097171
| 9274 | 0.25093 | 0.64518 | -0.18926 | -0.5013 | 0.83721 | 0.75979 | 0.164 | 0.54229 | 0.4898 | 0.50573
| 9275 | 0.13866 | 0.10239 | 0.30552 | 0.27813 | -0.3662 | 0.084522 | 0.29056 | -0.71946 | -0.16232 | -0.63299
| 9276 | 0.2326 | -0.13334 | 0.13403 | -0.79628 | 0.22598 | 0.041094 | 0.10451 | 0.34785 | -0.11745 | 0.35046
| 9277 | -0.3167 | -0.25388 | 0.50898 | 0.22276 | 0.24495 | -0.02794 | -0.15 | -0.8366 | 0.17848 | 0.12267
| 9278 | -0.014049 | 0.59318 | -0.12747 | 0.38967 | 0.66251 | -0.63765 | 0.61908 | 0.26918 | -0.13069 | -0.47856
| 9279 | -0.060585 | 0.53686 | -0.38008 | 0.046218 | -0.037659 | 0.19111 | 0.55357 | -0.77617 | -0.81862 | 0.33705
| 9280 | 0.64687 | 0.59639 | -0.21355 | 0.38836 | 0.59813 | -0.37462 | 0.85682 | -0.56954 | 0.093744 | 0.61987
| 9281 | -0.52894 | -0.21584 | 0.078751 | 0.30855 | 0.52979 | -0.80635 | -0.52282 | -0.32376 | 0.53535 | 0.31102
| 9282 | -0.58563 | 0.025885 | -0.4683 | -0.36841 | 0.24814 | 0.01547 | -0.061224 | -0.64715 | 0.53664 | -0.051159
| 9283 | -0.56606 | 0.94804 | 0.6257 | 0.5693 | 0.30913 | 0.39312 | 0.18643 | 0.2488 | 0.14006 | 0.62624
| 9284 | -0.16807 | -0.075176 | 0.6578 | 0.68267 | -0.49256 | 0.012326 | -0.11428 | -0.40713 | 0.89 | 0.46344
| 9285 | -0.0781 | -0.44964 | 0.037244 | 0.17181 | -0.39213 | 0.97 | 0.29155 | -0.081904 | -0.65634 | 0.53772
| 9286 | 0.60668 | 0.55672 | 0.28481 | 0.89276 | 0.25067 | -0.068174 | -0.22456 | -0.37606 | 0.19198 | -0.87077
| 9287 | -0.19669 | -0.044751 | 0.085834 | -0.48376 | -0.31934 | -0.14169 | -0.037451 | 0.46643 | -0.18655 | -0.34099
| 9288 | -0.22728 | -0.40595 | -0.56884 | -0.011719 | 0.38056 | -0.16844 | 0.31655 | 0.18852 | 0.65086 | -0.45109
| 9289 | -0.28958 | -0.0046609 | -0.25361 | -0.22045 | -0.25428 | -0.085506 | 0.85201 | 0.34235 | -0.6631 | 0.81318
| 9290 | 0.3167 | -0.6546 | 0.15413 | -0.42389 | -0.51969 | -0.031031 | 0.51865 | -0.09187 | -0.084959 | 0.57186
| 9291 | 0.23364 | -0.54251 | -0.5954 | 0.18459 | 0.45954 | -0.60949 | -0.55469 | -0.13681 | 0.37032 | 0.28789
| 9292 | 0.23247 | -0.06914 | 0.076258 | -0.0014511 | 0.54624 | -0.23587 | 0.7042 | 0.14906 | 0.46699 | 0.021583
| 9293 | 0.025782 | 0.57515 | 0.015774 | -0.0089904 | -0.025474 | 0.33434 | -0.025474 | -0.53751 | 0.26754 | -0.16149
| 9294 | -0.70589 | -0.27633 | -0.47607 | -0.0087886 | 0.38869 | -0.26795 | -0.053163 | -0.15923 | 0.069463 | 0.10552
| 9295 | 0.3015 | 0.13588 | -0.34266 | 0.10006 | 0.86325 | 0.04099 | -0.27302 | 0.35123 | 0.27688 | -0.56699
| 9296 | -0.2975 | -0.20836 | -0.9219 | -0.58684 | -0.44746 | 0.17872 | 0.30711 | -0.29056 | 0.20407 | -0.12736
| 9297 | -0.66519 | -0.088134 | -0.78483 | -0.15519 | 0.88909 | -0.82766 | -0.054008 | -0.42251 | 0.5174 | -0.10798
| 9298 | 0.25441 | 0.12622 | 0.049895 | 0.41579 | 0.22083 | 0.3306 | 0.29282 | 0.62919 | 0.12074 | -0.22611
| 9299 | -0.70657 | -0.58467 | 0.47132 | -0.37302 | 0.10731 | -0.21177 | -0.60113 | -0.33299 | 0.64886 | -0.10865
| 9300 | 0.093634 | 0.3477 | -0.4826 | -0.33344 | 0.18951 | 0.19545 | 0.022094 | -0.36857 | -0.5332 | 0.464
| 9301 | -0.2958 | 0.35618 | 0.12063 | -0.095622 | -0.0012508 | 0.40225 | -0.38608 | -0.30308 | -0.065067 | 0.79776
| 9302 | 0.20558 | 0.72705 | 0.10989 | -0.041407 | -0.32583 | -0.50715 | 0.39197 | -0.69357 | 0.25953 | -0.71733
| 9303 | 0.11949 | -0.19669 | -0.032167 | 0.85613 | 0.4588 | 0.59963 | 0.46624 | 0.50291 | -0.21304 | 0.10742
| 9304 | -0.13588 | -0.44475 | 0.078208 | -0.31305 | 0.26007 | 0.20583 | -0.66698 | -0.33344 | 0.22238 | 0.16209
| 9305 | 0.76357 | -0.22096 | -0.3607 | -0.28747 | 0.0781 | -0.41562 | 0.50331 | -0.66939 | -0.46812 | 0.15259
| 9306 | 0.025474 | 0.048633 | 0.81534 | -0.15377 | 0.75526 | -0.62892 | 0.2791 | -0.41648 | 0.21177 | -0.36337
| 9307 | 0.73561 | -0.4272 | -0.24641 | -0.035168 | 0.044647 | -0.3568 | -0.90253 | 0.41068 | -0.12931 | 0.059734
| 9308 | 0.55807 | -0.52219 | -0.15744 | -0.67243 | -0.19545 | 0.83237 | -0.0082843 | -0.35339 | 0.23888 | 0.12279
| 9309 | -0.22948 | -0.33871 | 0.42389 | -0.16197 | 0.1382 | -0.35899 | -0.60263 | -0.52157 | 0.46755 | -0.72378
| 9310 | 0.49671 | 0.6755 | -0.10742 | 0.085506 | 0.45292 | 0.51865 | 0.56445 | -0.0016514 | -0.05549 | -0.50817
| 9311 | 0.0028541 | -0.11994 | -0.54448 | -0.43018 | 0.63435 | -0.6319 | -0.76146 | -0.53256 | 0.46849 | 0.53664
| 9312 | -0.16507 | 0.06016 | -0.043287 | -0.24165 | -0.15188 | -0.38657 | -0.08343 | 0.1063 | -0.30036 | -0.15899
| 9313 | 0.55447 | 0.40511 | -0.4755 | 0.1196 | 0.020051 | -0.1758 | 0.64489 | -0.25093 | 0.31934 | 0.82593
| 9314 | -0.4826 | -0.025064 | 0.29268 | 0.65229 | 0.1957 | -0.9005 | 0.37414 | 0.79191 | -0.7488 | -0.56445
| 9315 | -0.11892 | 0.047687 | 0.7015 | -0.47436 | -0.2256 | -0.61051 | -0.95417 | -0.041199 | -0.30552 | -0.16868
| 9316 | -0.8366 | 0.9005 | -0.044333 | 0.57047 | -0.7816 | 0.33464 | -0.13948 | -0.34846 | -0.031135 | 0.36055
| 9317 | -0.1015 | -0.24654 | -0.24508 | -0.1229 | -0.19819 | -0.19421 | 0.44403 | 0.12017 | 0.20257 | 0.64772
| 9318 | -0.23143 | 0.12313 | 0.33194 | -0.052108 | -0.094185 | -0.034029 | -0.46699 | 0.29197 | -0.06914 | 0.44403
| 9319 | 0.23221 | -0.17399 | 0.65229 | -0.49493 | -0.17848 | -0.048107 | -0.5003 | 0.4826 | -0.018114 | 0.47779
| 9320 | 0.22909 | 0.4997 | -0.24402 | -0.79336 | -0.66608 | 0.076691 | -0.18165 | -0.25683 | 0.27979 | -0.24033
| 9321 | -0.0081835 | 0.58275 | -0.15638 | -0.1292 | 0.19074 | 0.34985 | -0.23731 | 0.10028 | -0.75403 | -0.20659
| 9322 | 0.1353 | -0.17109 | 0.60643 | 0.14812 | -0.29993 | -0.067423 | 0.71946 | 0.44295 | 0.21304 | 0.22431
| 9323 | -0.099167 | 0.38396 | -0.25818 | 0.09176 | -0.020255 | -0.022196 | -0.72523 | 0.64153 | 0.1179 | -0.10843
| 9324 | -0.50634 | -0.55402 | -0.67704 | 0.89 | -0.17036 | -0.29141 | 0.55134 | -0.81697 | 0.58491 | -0.1565
| 9325 | 0.43671 | -0.3629 | 0.35821 | 0.011617 | -0.81265 | -0.028558 | -0.33766 | -0.24814 | 0.27371 | 0.51823
| 9326 | -0.21814 | -0.73789 | 0.22096 | -0.46925 | -0.050421 | 0.20069 | 0.21968 | -0.14367 | -0.54778 | 0.84094
| 9327 | -0.53989 | 0.01415 | 0.14041 | 0.45237 | 0.59565 | 0.094517 | 0.63572 | 0.09154 | -0.72018 | -0.67798
| 9328 | 0.4991 | -0.10664 | 0.083539 | -0.33149 | -0.044751 | 0.27151 | 0.0044599 | -0.47837 | 0.29921 | -0.28202
| 9329 | -0.31963 | -0.2504 | 0.12222 | 0.037347 | -0.67213 | -0.0050628 | -0.72779 | -0.78436 | 0.063357 | 0.01842
| 9330 | -0.12885 | -0.068067 | -0.11191 | -0.66162 | 0.09839 | 0.27 | 0.46232 | -0.10106 | -0.03974 | 0.27674
| 9331 | -0.95 | 0.040469 | -0.084304 | -0.10585 | -0.25267 | -0.25818 | 0.24561 | 0.09706 | -0.18729 | 0.16077
| 9332 | 0.48629 | -0.069248 | 0.17775 | -0.4163 | 0.73 | 0.50291 | 0.087586 | -0.46046 | 0.16364 | -0.020766
| 9333 | -0.27757 | 0.5005 | 0.054537 | -0.16173 | 0.30466 | -0.40898 | -0.5005 | 0.17994 | -0.056019 | 0.09165
| 9334 | -0.85474 | 0.47837 | 0.31174 | -0.78297 | -0.37462 | 0.076907 | 0.17169 | -0.40242 | 0.33856 | -0.24283
| 9335 | -0.12576 | -0.55312 | -0.26658 | -0.19582 | -0.35386 | 0.33856 | 0.5883 | -0.74722 | 0.59838 | -0.29665
| 9336 | 0.77483 | -0.14601 | 0.27633 | 0.72523 | -0.71417 | -0.25093 | -0.0091922 | 0.81862 | 0.15721 | -0.39859
| 9337 | 0.65201 | 0.29395 | 0.71663 | -0.11315 | 0.8618 | -0.20848 | -0.40025 | -0.6382 | 0.093523 | -0.61026
| 9338 | 0.22508 | 0.16531 | -0.32376 | 0.57727 | 0.20194 | 0.5011 | 0.26549 | 0.094517 | -0.49177 | -0.60592
| 9339 | -0.66074 | -0.41494 | -0.23195 | 0.69619 | 0.25723 | -0.21114 | -0.34266 | -0.53064 | 0.25093 | 0.19669
| 9340 | 0.063464 | -0.41221 | -0.18385 | -0.015165 | 0.01415 | 0.23169 | -0.35278 | -0.11157 | 0.069355 | -0.61594
| 9341 | -0.030928 | -0.022606 | -0.43493 | -0.1735 | 0.025064 | -0.68552 | -0.036102 | -0.55582 | 0.12336 | -0.32243
| 9342 | 0.48125 | -0.30754 | -0.15177 | 0.23104 | -0.038491 | 0.18214 | 0.71627 | -0.14449 | 0.01263 | 0.17909
| 9343 | 0.33224 | -0.79776 | 0.10809 | -0.31116 | 0.12119 | 0.43317 | 0.042242 | 0.15141 | 0.13161 | 0.67643
| 9344 | 0.5224 | -0.28271 | -0.099278 | -0.49256 | -0.252 | 0.4194 | 0.6939 | 0.023834 | 0.2184 | -0.61882
| 9345 | 0.2081 | -0.24283 | -0.033615 | -0.23875 | -0.13762 | 0.034133 | -0.7735 | 0.87712 | -0.14648 | -0.018012
| 9346 | -0.53578 | 0.10128 | -0.98268 | -0.014759 | -0.36857 | -0.28021 | 0.26986 | -0.32598 | -0.32406 | -0.62277
| 9347 | -0.25723 | -0.40983 | 0.038907 | -0.14976 | -0.69917 | 0.77617 | 0.40814 | -0.25535 | -0.57303 | -0.037971
| 9348 | 0.080054 | 0.050526 | 0.21674 | -0.13403 | -0.45714 | -0.69292 | -0.43141 | 0.13971 | -0.014049 | 0.0048618
| 9349 | -0.095954 | 0.80481 | -0.34662 | 0.80791 | -0.49275 | 0.45695 | -0.42895 | -0.048422 | -0.046323 | 0.73074
| 9350 | -0.17665 | -5.0001e-05 | 0.85067 | 0.10697 | 0.080381 | 0.1852 | -0.15448 | 0.8454 | -0.14285 | 0.0995
| 9351 | 0.61777 | -0.16232 | -0.38869 | 0.067637 | 0.33826 | -0.10888 | 0.044228 | 0.52873 | -0.096285 | 0.063464
| 9352 | 0.27178 | -0.4985 | -0.47132 | 0.71138 | -0.80947 | 0.24112 | -0.082231 | -0.348 | -0.60063 | 0.078642
| 9353 | -0.34479 | -0.62039 | -0.081142 | 0.17605 | 0.24416 | -0.13959 | -0.33555 | -0.90151 | 0.28635 | -0.12989
| 9354 | -0.11146 | 0.39992 | -0.51389 | 0.6985 | -0.10933 | 0.22405 | -0.85405 | 0.66849 | -0.53449 | 0.034754
| 9355 | -0.10451 | 0.73335 | 0.14076 | 0.40209 | 0.046218 | -0.35712 | -0.097725 | -0.029691 | 0.73335 | 0.58733
| 9356 | 0.53406 | 0.42982 | -0.7504 | -0.77707 | 0.10083 | -0.20823 | 0.49631 | 0.45972 | -0.48338 | 0.68615
| 9357 | -0.51041 | 0.30957 | -0.32081 | 0.57421 | -0.8422 | -0.32732 | 0.12519 | 0.049789 | -0.64349 | 0.040886
| 9358 | -0.30007 | 0.14812 | 0.51802 | -0.46624 | -0.10083 | -0.69652 | -0.04538 | 0.48454 | 0.38332 | -0.18055
| 9359 | 0.25013 | -0.5954 | -0.25885 | -0.41511 | -0.0068736 | -0.78206 | -0.20257 | -0.22122 | -0.3167 | 0.076149
| 9360 | -0.34008 | 0.41272 | -0.29765 | 0.21406 | -0.26441 | 0.63792 | -0.24561 | 0.17605 | 0.16436 | -0.070108
| 9361 | 0.053163 | 0.080816 | -0.4828 | 0.029691 | 0.1863 | -0.10306 | -0.031961 | -0.60719 | -0.32985 | -0.57585
| 9362 | 0.064318 | -0.67612 | 0.16042 | -0.008486 | 0.15047 | 0.37462 | 0.018827 | -0.088573 | -0.91112 | 0.336
| 9363 | -0.17012 | -0.045904 | 0.35836 | -0.29836 | 0.29452 | 0.070861 | -0.48765 | 0.82824 | 0.16687 | 0.19719
| 9364 | -0.2184 | -0.12245 | -0.63654 | 0.53427 | -0.7623 | 0.13311 | 0.17217 | 0.23117 | 0.080163 | -0.42268
| 9365 | 0.3804 | 0.13415 | 0.32881 | -0.37847 | -0.20798 | -0.70966 | 0.13983 | -0.55111 | -0.010707 | 0.60364
| 9366 | -0.12074 | -0.54845 | -0.0054649 | -0.48164 | -0.099389 | -0.19844 | -0.33224 | 0.42737 | 0.1546 | 0.33134
| 9367 | 0.43123 | -0.3961 | 0.33494 | -0.23482 | -0.053586 | 0.25912 | -0.26034 | 0.14274 | 0.3129 | -0.56331
| 9368 | -0.3375 | 0.28369 | -0.49612 | 0.18275 | -0.53 | -0.15507 | -0.4564 | 0.009899 | -0.087366 | -0.55089
| 9369 | 0.35247 | 0.058565 | -0.0011507 | 0.33675 | 0.81 | -0.074095 | -0.31334 | -0.21674 | 0.20006 | 0.16161
| 9370 | -0.41854 | -0.023424 | -0.76357 | -0.028352 | 0.1044 | 0.264 | -0.55694 | 0.15851 | -0.60013 | -0.25508
| 9371 | -0.35805 | 0.45401 | 0.049158 | -0.2402 | -0.036517 | -0.33902 | -0.78576 | -0.16807 | -0.55514 | 0.31699
| 9372 | -0.087476 | 0.49078 | -0.64546 | -0.063571 | -0.72889 | 0.098169 | -0.11056 | 0.71208 | -0.30509 | 0.15448
| 9373 | -0.042347 | 0.21355 | -0.13392 | 0.038595 | -0.14111 | 0.37111 | 0.13808 | -0.46737 | -0.7512 | 0.44277
| 9374 | -0.47379 | -0.014657 | 0.38836 | 0.094517 | -0.41579 | -0.22019 | -0.55223 | -0.3061 | 0.24827 | 0.352
| 9375 | 0.086381 | 0.58323 | 0.43706 | -0.037971 | -0.12805 | -0.21 | -0.14017 | -0.37398 | -0.068388 | 0.72559
| 9376 | -0.094296 | -0.38478 | -0.29438 | -0.48922 | 0.19359 | 0.83721 | 0.38869 | -0.38267 | 0.57 | -0.29551
| 9377 | 0.23665 | 0.52345 | 0.13415 | 0.019949 | -0.068818 | -0.020561 | 0.14578 | -0.44945 | 0.69619 | 0.15271
| 9378 | -0.31116 | 0.1196 | -0.081469 | 0.012326 | 0.72161 | -0.41579 | 0.75403 | 0.1136 | -0.40713 | -0.019847
| 9379 | -0.073339 | -0.15271 | -0.40696 | -0.52809 | -0.20911 | -0.55559 | -0.11135 | 0.15697 | 0.61725 | 0.20445
| 9380 | -0.18766 | -0.31904 | -0.12063 | -0.051686 | 0.46344 | 0.72705 | 0.77 | 0.27896 | -0.14871 | -0.0023528
| 9381 | 0.55067 | 0.65172 | -0.62731 | -0.41905 | 0.02568 | 0.64744 | 0.48473 | -0.26563 | 0.22961 | 0.45073
| 9382 | 0.074311 | -0.36984 | 0.10507 | -0.17508 | 0.19483 | 0.73637 | -0.45806 | 0.16256 | -0.28299 | -0.51246
| 9383 | 0.34448 | 0.60339 | 0.083976 | -0.18889 | -0.1646 | 0.42303 | 0.070215 | -0.31 | 0.52767 | 0.061757
| 9384 | 0.13369 | -0.13553 | -0.53149 | -0.11079 | 0.17169 | 0.4653 | -0.63517 | 0.67182 | 0.46306 | 0.011921
| 9385 | 0.14976 | -0.079402 | 0.22431 | -0.17096 | -0.51143 | 0.10195 | 0.84736 | 0.035065 | 0.43706 | -0.041616
| 9386 | -0.1466 | 0.21381 | 0.48396 | -0.68679 | -0.31875 | 0.12074 | -0.14344 | 0.30365 | -0.21687 | -0.73789
| 9387 | -0.25374 | -0.11248 | -0.40276 | -0.13855 | -0.92063 | 0.042138 | 0.19483 | 0.63903 | -0.40966 | 0.085943
| 9388 | -0.43141 | -0.15082 | 0.5201 | 0.46943 | -0.64659 | 0.6939 | 0.35185 | 0.14871 | 0.15839 | 0.50837
| 9389 | -0.61594 | -0.64489 | 0.60846 | 0.22844 | -0.27536 | 0.17012 | -0.4985 | 0.14472 | -0.0079819 | 0.236
| 9390 | 0.081577 | -0.47684 | 0.27924 | -0.56331 | -0.20596 | 0.40578 | 0.23534 | -0.32184 | 0.041512 | -0.0026535
| 9391 | -0.28817 | -0.88042 | 0.12245 | 0.16149 | -0.13057 | -0.25053 | -0.18177 | -0.1118 | -0.029382 | -0.12119
| 9392 | 0.16448 | -0.4426 | 0.4997 | 0.93597 | 0.31568 | 0.097171 | -0.44982 | 0.24007 | 0.37494 | -0.027632
| 9393 | 0.1565 | 0.31963 | 0.016994 | -0.025988 | 0.71347 | -0.15342 | 0.019643 | 0.031135 | 0.17435 | 0.079837
| 9394 | -0.18263 | -0.31655 | 0.58131 | -0.1091 | 0.20207 | -0.63081 | 0.21177 | -0.19881 | 0.41888 | -0.30394
| 9395 | -0.43688 | 0.55785 | 0.31934 | 0.16603 | -0.59 | 0.7429 | 0.32821 | 0.42982 | 0.13797 | -0.47665
| 9396 | 0.84736 | -0.63271 | -0.45695 | -0.40932 | 0.25347 | -0.16795 | 0.026604 | -0.27799 | 0.26699 | -0.58036
| 9397 | -0.10798 | 0.24508 | -0.42251 | -0.43795 | 0.39543 | -0.19707 | 0.436 | 0.2722 | 0.5098 | 0.022401
| 9398 | 0.016689 | -0.18189 | 0.31495 | 0.38461 | -0.1868 | 0.048317 | 0.082885 | 0.86472 | -0.06197 | -0.39992
| 9399 | 0.14929 | -0.59763 | 0.28887 | -0.28831 | 0.56745 | 0.62865 | 0.22754 | 0.22974 | -0.16221 | 0.68775
| 9400 | -0.15946 | -0.085615 | -0.70966 | -0.7569 | 0.56285 | 0.20533 | 0.54011 | 0.20722 | 0.52177 | -0.62092
| 9401 | 0.49098 | 0.16747 | -0.022503 | -0.44188 | -0.16555 | -0.38608 | 0.29099 | -0.10585 | 0.21101 | -0.15887
| 9402 | 0.68839 | -0.11745 | -0.54845 | 0.34159 | 0.91938 | -0.052319 | -0.45548 | 0.81534 | 0.71982 | 0.43617
| 9403 | -0.63135 | -0.25401 | -0.29608 | -0.09099 | 0.15401 | -0.37143 | 0.18569 | 0.58854 | 0.30408 | 0.071399
| 9404 | -0.17338 | -0.13936 | 0.34739 | 0.019439 | -0.29395 | -0.70862 | 0.19322 | -0.1775 | 0.89851 | 0.60643
| 9405 | -0.15377 | -0.061864 | 0.018216 | -0.44855 | -0.15851 | -0.002453 | 0.62543 | -0.15685 | -0.034236 | -0.48941
| 9406 | -0.24033 | 0.36905 | 0.41425 | 0.088792 | 0.32583 | -0.10072 | -0.41699 | 0.30653 | -0.15212 | -0.37
| 9407 | 0.044647 | 0.54011 | -0.56514 | 0.15259 | -0.43742 | -0.12679 | 0.30971 | 0.16268 | 0.27924 | 0.1389
| 9408 | 0.57515 | -0.88295 | 0.57515 | -0.52894 | 0.10306 | -0.76021 | -0.59147 | -0.27096 | -0.070645 | -0.016689
| 9409 | -0.10899 | 0.16952 | 0.33539 | 0.62171 | 0.75403 | -0.41136 | -0.4979 | -0.80532 | 0.13265 | 0.054326
| 9410 | 0.23809 | -0.45456 | -0.51102 | 0.58131 | -0.13542 | 0.38089 | -0.21878 | -0.21254 | -0.036621 | 0.35169
| 9411 | -0.36039 | -0.48804 | -0.11598 | -0.92319 | -0.048317 | 0.27965 | -0.72089 | -0.043287 | -0.54845 | 0.54382
| 9412 | -0.15106 | 0.096064 | -0.65985 | 0.70828 | -0.056019 | -0.026604 | -0.25428 | 0.021787 | 0.31203 | -0.61777
| 9413 | -0.60038 | -0.33962 | 0.15994 | 0.10764 | 0.38592 | 0.30942 | -0.0083852 | 0.092531 | -0.54646 | 0.48144
| 9414 | -0.089012 | 0.54911 | -0.19595 | -0.10552 | -0.65985 | 0.36274 | 0.59269 | -0.75731 | -0.35448 | -0.52788
| 9415 | -0.30036 | -0.09088 | -0.53859 | -0.67612 | -0.57798 | 0.24787 | 0.62198 | -0.38089 | 0.67612 | -0.25388
| 9416 | -0.41596 | 0.087914 | -0.58179 | 0.54558 | -0.0035563 | -0.13334 | 0.5458 | 0.30207 | 0.2287 | 0.033201
| 9417 | -0.17508 | 0.26973 | -0.35572 | -0.009596 | 0.036102 | -0.22637 | 0.019235 | 0.27702 | 0.49631 | -0.20962
| 9418 | 0.74096 | -0.48318 | -0.057716 | 0.63682 | -0.53837 | 0.13196 | 0.038699 | -0.54185 | 0.6631 | 0.27014
| 9419 | 0.30509 | -0.30322 | -0.025372 | 0.54712 | -0.22431 | -0.23351 | -0.59813 | -0.073231 | -0.77796 | 0.7042
| 9420 | -0.031857 | -0.59913 | 0.58781 | 0.09187 | -0.20975 | -0.027323 | -0.089561 | 0.11405 | -0.75 | -0.72596
| 9421 | 0.20508 | 0.74446 | 0.29127 | 0.1044 | 0.58612 | -0.051053 | -0.35386 | -0.62437 | 0.072369 | -0.31568
| 9422 | 0.81862 | 0.35139 | 0.34831 | 0.4828 | -0.052108 | 0.03974 | -0.65985 | -0.16868 | -0.094296 | 0.38543
| 9423 | -0.010707 | 0.53043 | -0.16651 | -0.32747 | 0.020357 | -0.2625 | -0.69784 | -0.4828 | 0.082885 | 0.07
| 9424 | -0.12782 | -0.68839 | 0.22276 | -0.43141 | 0.8467 | 0.37223 | -0.47076 | -0.66192 | -0.40915 | -0.17714
| 9425 | -0.0038574 | 0.20131 | -0.29282 | 0.69324 | -0.030103 | -0.10899 | 0.17229 | -0.91574 | 0.75648 | -0.36353
| 9426 | -0.70521 | 0.065281 | 0.064212 | 0.60541 | -0.11045 | 0.32866 | -0.30265 | -0.40376 | 0.016079 | 0.47607
| 9427 | 0.24535 | 0.76913 | 0.014353 | -0.039948 | 0.39131 | -0.75201 | 0.04026 | 0.23469 | 0.30769 | 0.27178
| 9428 | 0.29622 | -0.26918 | 0.52282 | -0.68775 | 0.0065716 | 0.17823 | -0.03434 | -0.30797 | 0.47914 | -0.27481
| 9429 | -0.38526 | 0.21368 | -0.12108 | 0.44619 | -0.45843 | -0.064746 | -0.4046 | -0.42511 | 0.44945 | 0.53881
| 9430 | 0.12063 | -0.18877 | -0.15153 | 0.51102 | -0.4531 | -0.72705 | 0.047477 | 0.23626 | -0.74525 | 0.84284
| 9431 | 0.3681 | -0.39692 | 0.1513 | 0.14906 | -0.25468 | -0.38186 | -0.13681 | -0.075716 | 0.70691 | 0.033512
| 9432 | 0.12131 | 0.44349 | -0.6786 | -0.86399 | -0.44982 | -0.48765 | 0.59049 | 0.16531 | -0.14344 | -0.19408
| 9433 | -0.55785 | 0.66608 | -0.47151 | -0.17048 | -0.05814 | -0.32435 | 0.06914 | 0.053058 | -0.15567 | -0.063464
| 9434 | -0.085724 | -0.81106 | 0.17665 | 0.26863 | -0.031857 | -0.19657 | -0.10195 | 0.24244 | 0.29495 | 0.18827
| 9435 | 0.9089 | 0.046638 | -0.24893 | -0.012731 | -0.4999 | 0.32509 | -0.15342 | 0.043705 | -0.20219 | -0.75896
| 9436 | 0.084522 | 0.89851 | 0.12656 | 0.16579 | 0.24007 | -0.44982 | 0.76784 | -0.80176 | 0.18643 | -0.15602
| 9437 | 0.48804 | -0.01842 | 0.026604 | 0.21661 | -0.13092 | 0.76827 | -0.22818 | 0.45548 | -0.042451 | 0.19148
| 9438 | -0.009798 | -0.57468 | 0.094296 | 0.19495 | 0.38934 | 0.62543 | 0.60872 | 0.66909 | -0.66939 | -0.038907
| 9439 | 0.77841 | 0.40865 | -0.00065021 | 0.24707 | -0.44728 | 0.38024 | -0.12576 | 0.52788 | 0.32509 | -0.56838
| 9440 | 0.27453 | -0.5172 | 0.16579 | 0.26373 | -0.84412 | -0.37127 | 0.57798 | 0.53989 | 0.015165 | 0.25764
| 9441 | 0.12324 | -0.348 | -0.50472 | -0.6852 | -0.12862 | 0.098945 | -0.13449 | -0.29765 | 0.5005 | -0.079511
| 9442 | 0.1432 | 0.34235 | 0.69917 | 0.65547 | -0.1269 | 0.22173 | -0.0068736 | 0.015368 | -0.62784 | -0.33705
| 9443 | 0.63435 | 0.66399 | 0.60113 | -0.070645 | 0.066887 | -0.98268 | 0.016893 | 0.12851 | 0.16137 | 0.06603
| 9444 | -0.12519 | 0.1269 | 0.4564 | 0.15804 | 0.54956 | 0.34816 | -0.75363 | -0.19682 | 0.53064 | 0.17096
| 9445 | -0.035583 | -0.2216 | 0.38332 | -0.51554 | 0.17072 | -0.42129 | -0.87077 | 0.56354 | 0.38771 | 0.14871
| 9446 | 0.071507 | -0.94615 | -0.11304 | 0.57585 | 0.23156 | 0.36227 | -0.033408 | -0.42965 | -0.43511 | -0.0040582
| 9447 | -0.34433 | -0.61646 | -0.56285 | 0.24721 | -0.098834 | 0.56907 | 0.073339 | -0.46418 | -0.31131 | -0.020663
| 9448 | 0.69422 | 0.13115 | -0.19297 | 0.81752 | 0.23247 | 0.16077 | -0.24217 | -0.27854 | -0.0037571 | 0.63462
| 9449 | 0.19844 | -0.12943 | 0.17933 | 0.22792 | 0.4117 | 0.021379 | -0.09011 | -0.44045 | 0.16747 | 0.040573
| 9450 | -0.23052 | -0.10139 | 0.12188 | -0.17544 | -0.050211 | 0.77218 | 0.63792 | 0.25508 | 0.15851 | 0.64014
| 9451 | 0.67274 | -0.28733 | -0.086819 | -0.31993 | 0.39115 | 0.77932 | -0.45695 | 0.11507 | 0.014962 | -0.14087
| 9452 | 0.15721 | -0.30408 | -0.59245 | 0.39164 | -0.17181 | -0.52576 | -0.04381 | 0.048107 | 0.15875 | -0.0050628
| 9453 | -0.12176 | 0.31919 | -0.65316 | 0.050211 | 0.17399 | -0.44728 | 0.056867 | 0.97 | -0.13762 | 0.28649
| 9454 | 0.17253 | -0.5001 | -0.097836 | -0.7488 | 0.006169 | -0.14871 | 0.068925 | 0.64293 | -0.16125 | 0.74329
| 9455 | -0.079946 | 0.30552 | 0.4046 | 0.26278 | 0.12725 | 0.1952 | -0.058459 | -0.22534 | -0.50817 | -0.84031
| 9456 | -0.54382 | 0.58299 | -0.64744 | -0.030103 | -0.58227 | -0.019337 | -0.66251 | -0.30164 | 0.044333 | 0.2216
| 9457 | 0.09066 | 0.15567 | 0.007075 | -0.2975 | 0.51472 | -0.40242 | 0.20975 | -0.70083 | -0.26932 | 0.0728
| 9458 | 0.16364 | -0.21674 | 0.3369 | 0.29551 | -0.30797 | 0.5693 | -0.11 | -0.044437 | -0.14671 | 0.32762
| 9459 | -0.009596 | 0.70555 | -0.25214 | 0.12051 | -0.44295 | 0.38934 | 0.16675 | -0.13565 | 0.80277 | -0.6241
| 9460 | -0.23208 | 0.28789 | -0.11022 | -0.18717 | -0.084085 | 0.4417 | 0.0038574 | -0.47665 | -0.12679 | -0.39892
| 9461 | 0.033098 | 0.20207 | -0.06165 | -0.164 | -0.37751 | -0.22987 | 0.4286 | 0.12599 | -0.22148 | 0.087914
| 9462 | 0.28411 | 0.083212 | -0.1814 | -0.19408 | 0.31538 | -0.66133 | 0.52936 | 0.35417 | -0.06753 | -0.02722
| 9463 | -0.65057 | 0.24389 | -0.09143 | 0.70217 | 0.18153 | 0.72523 | 0.57186 | 0.015978 | -0.64125 | -0.93292
| 9464 | -0.36652 | -0.26454 | -0.65229 | -0.83599 | -0.0078811 | 0.41716 | -0.077558 | -0.064639 | 0.14099 | 0.43902
| 9465 | -0.40814 | 0.017707 | 0.083649 | -0.055278 | -0.2343 | -0.33585 | -0.38008 | 0.79776 | -0.009899 | -0.29141
| 9466 | 0.27799 | -0.095954 | 0.71804 | 0.16531 | 0.010303 | 0.09209 | 0.63081 | 0.364 | 0.51927 | -0.23796
| 9467 | 0.95417 | -0.51184 | -0.25872 | -0.36149 | 0.013744 | -0.17157 | 0.19782 | 0.66758 | -0.7687 | 0.048843
| 9468 | -0.38364 | 0.29523 | -0.15 | -0.25107 | -0.17823 | 0.085724 | -0.49216 | -0.41871 | -0.56468 | 0.56239
| 9469 | 0.032788 | -0.67519 | -0.11767 | 0.44457 | -0.42147 | 0.10139 | 0.71 | 0.40898 | -0.19919 | 0.22238
| 9470 | -0.20244 | -0.79628 | 0.92063 | -0.93 | 0.45109 | 0.25053 | -0.2184 | -0.45898 | 0.095511 | 0.2755
| 9471 | -0.18348 | -0.86036 | 0.20848 | 0.11484 | -0.19794 | 0.8821 | -0.21292 | 0.0017515 | 0.5583 | 0.094627
| 9472 | -0.18901 | 0.36149 | -0.72341 | -0.69097 | -0.45511 | -0.26183 | 0.38299 | -0.063677 | 0.053269 | -0.10161
| 9473 | -0.17945 | -0.5245 | 0.51184 | 0.065602 | -0.21955 | 0.64265 | 0.11722 | -0.21968 | -0.39825 | -0.29268
| 9474 | 0.17532 | -0.44601 | 0.99 | 0.40092 | -0.034133 | -0.35758 | 0.3061 | -0.018725 | 0.073771 | -0.1109
| 9475 | 0.40276 | -0.24429 | 0.22456 | 0.047477 | -0.43387 | -0.6382 | 0.12622 | 0.37207 | -0.035479 | -0.20874
| 9476 | 0.2175 | -0.22844 | 0.031444 | 0.75896 | 0.24363 | -0.056549 | -0.50817 | -0.94255 | 0.015267 | 0.41922
| 9477 | -0.2496 | -0.055701 | -0.52619 | 0.48473 | 0.23665 | 0.01842 | 0.14718 | 0.39 | 0.46362 | 0.82941
| 9478 | 0.6077 | 0.057822 | -0.31305 | -0.33902 | 0.13276 | -0.79727 | 0.42251 | -0.0092932 | 0.042033 | 0.20119
| 9479 | -0.30711 | 0.75855 | -0.47531 | 0.81917 | -0.10966 | -0.099056 | -0.54514 | -0.65576 | -0.043496 | -0.073987
| 9480 | -0.43742 | -0.44027 | 0.22135 | -0.0057666 | -0.49651 | -0.31014 | -0.22831 | -0.45622 | 0.49592 | 0.20949
| 9481 | 0.36023 | -0.44619 | -0.32851 | -0.32465 | 0.059628 | -0.16892 | -0.73561 | -0.6349 | -0.047162 | 0.038387
| 9482 | -0.086271 | 0.3451 | 0.014962 | -0.0062697 | -0.11892 | -0.41272 | -0.83538 | 0.41751 | -0.36384 | -0.17811
| 9483 | 0.15306 | -0.10373 | 0.2924 | -0.45438 | 0.32554 | 0.74801 | -0.236 | -0.25307 | -0.52894 | 0.5015
| 9484 | 0.11801 | 0.8043 | -0.33389 | 0.21994 | 0.75896 | 0.1063 | 0.18238 | 0.26373 | 0.36337 | 0.45843
| 9485 | 0.66133 | -0.1603 | 0.64489 | 0.72596 | -0.10061 | 0.19 | 0.058353 | -0.40831 | 0.0054649 | 0.065174
| 9486 | -0.70725 | 0.61882 | 0.78483 | 0.40949 | -0.072153 | 0.2659 | -0.12119 | -0.97354 | 0.75607 | 0.084194
| 9487 | 0.84412 | -0.18988 | -0.20911 | -0.12484 | 0.22663 | 0.081904 | 0.74368 | 0.5009 | 0.81318 | -0.436
| 9488 | 0.49751 | -0.31728 | 0.6634 | 0.55537 | 0.016893 | -0.38543 | -0.43742 | 0.037244 | -0.55402 | 0.27192
| 9489 | 0.65576 | 0.06325 | 0.37191 | 0.26617 | 0.336 | 0.80277 | -0.41119 | 0.82028 | 0.76442 | 0.19944
| 9490 | 0.31305 | -0.046323 | -0.1382 | -0.50533 | 0.15555 | 0.16256 | 0.14531 | -0.16567 | -0.67213 | -0.24867
| 9491 | 0.52724 | 0.53449 | 0.85405 | 0.010808 | -0.021992 | -0.37702 | -0.76399 | 0.42459 | 0.11586 | -0.069248
| 9492 | -0.59639 | 0.42389 | 0.015673 | 0.60872 | 0.13959 | -0.52261 | 0.28063 | -0.49731 | 0.13069 | 0.14215
| 9493 | 0.51823 | 0.74329 | -0.03 | 0.21623 | -0.65576 | 0.50695 | -0.073016 | 0.1375 | -0.56422 | -0.068818
| 9494 | 0.81159 | 0.46195 | -0.14871 | 0.0027538 | -0.078208 | 0.68775 | -0.52387 | -0.49453 | 0.1803 | -0.38089
| 9495 | -0.097614 | 0.77306 | 0.73751 | -0.26034 | 0.2602 | -0.59565 | 0.029279 | -0.47626 | -0.46755 | 0.39213
| 9496 | 0.036932 | -0.65751 | -0.43 | 0.22353 | 0.12782 | 0.11439 | -0.71698 | 0.7005 | 0.15436 | 0.66789
| 9497 | -0.2744 | -0.56884 | -0.38787 | -0.71173 | 0.39164 | 0.45438 | 0.12679 | 0.099167 | -0.56194 | -0.62463
| 9498 | -0.28873 | 0.57941 | 0.11349 | -0.043287 | -0.0080827 | 0.0020521 | -0.13242 | 0.29311 | -0.16054 | -0.66668
| 9499 | -0.4078 | 0.33 | 0.40511 | 0.26128 | 0.25777 | 0.53085 | 0.27055 | -0.2893 | 0.71138 | 0.57917
| 9500 | -0.17096 | -0.22186 | 0.21254 | 0.67274 | -0.33434 | 0.23731 | -0.51492 | 0.10485 | -0.44746 | -0.081686
| 9501 | 0.5663 | 0.22844 | -0.51123 | 0.2402 | -0.25187 | -0.3727 | 0.059734 | -0.32687 | 0.097836 | -0.66849
| 9502 | -0.28132 | 0.47512 | 0.33224 | -0.10373 | 0.18422 | 0.19956 | -0.21776 | -0.3148 | -0.3593 | -0.40359
| 9503 | 0.76741 | 0.021583 | 0.24853 | 0.093413 | 0.24774 | -0.15141 | -0.69259 | 0.79336 | 0.41871 | -0.72669
| 9504 | -0.21304 | -0.17145 | 0.49177 | -0.44385 | 0.060053 | -0.17024 | 0.34985 | 0.34372 | 0.2893 | -0.38543
| 9505 | 0.37574 | -0.56676 | 0.21917 | -0.41374 | -0.41665 | 0.1758 | 0.24707 | 0.47588 | -0.23626 | -0.43229
| 9506 | -0.28146 | -0.64293 | -0.068496 | 0.14041 | -0.49631 | -0.72018 | 0.0060684 | -0.1735 | 0.0090913 | -0.20533
| 9507 | -0.27979 | 0.28216 | -0.29424 | 0.16699 | 0.32851 | 0.33015 | 0.29325 | -0.79482 | -0.64433 | -0.69619
| 9508 | -0.023527 | 0.59 | -0.18348 | -0.11722 | 0.51102 | -0.4859 | 0.33766 | -0.27536 | 0.15153 | 0.10899
| 9509 | 0.53363 | 0.26959 | 0.0059678 | -0.43458 | -0.41 | -0.16819 | 0.45493 | -0.27385 | -0.023015 | 0.3804
| 9510 | 0.14507 | 0.086271 | 0.25013 | -0.54404 | -0.20508 | 0.31772 | 0.028043 | 0.13959 | -0.22805 | -0.59988
| 9511 | -0.051686 | -0.37111 | 0.38787 | -0.45365 | 0.022401 | 0.61257 | 0.84157 | -0.52661 | 0.17399 | -0.40662
| 9512 | -0.29779 | -0.43724 | 0.22663 | 0.025885 | -0.44009 | 0.14484 | 0.69718 | -0.23273 | 0.49651 | -0.11394
| 9513 | 0.37318 | 0.79143 | 0.14449 | -0.047582 | 0.70184 | -0.31116 | 0.27027 | -0.51348 | 0.13542 | 0.24734
| 9514 | -0.21482 | 0.31276 | -0.11677 | -0.36604 | -0.032374 | 0.62704 | -0.014252 | -0.11575 | -0.30279 | 0.13542
| 9515 | -0.068925 | 0.10675 | 0.38902 | -0.39378 | 0.41306 | 0.37382 | -0.57703 | -0.29879 | 0.30036 | 0.41068
| 9516 | -0.7005 | 0.4801 | 0.19074 | -0.20081 | 0.42877 | -0.09695 | 0.11858 | -0.25107 | -0.58036 | -0.58539
| 9517 | -0.13843 | -0.048738 | 0.34418 | 0.21891 | -0.47398 | 0.13994 | 0.27426 | 0.48029 | 0.7429 | 0.0014511
| 9518 | 0.3186 | -0.34388 | 0.97764 | 0.38315 | -0.50231 | 0.1962 | -0.13878 | -0.041825 | 0.19471 | 0.10284
| 9519 | 0.64042 | 0.2492 | -0.16328 | -0.20019 | -0.39411 | 0.056231 | 0.052952 | 0.96394 | -0.37526 | 0.18104
| 9520 | -0.60113 | -0.13878 | 0.23104 | -0.26536 | 0.22186 | 0.44818 | -0.14589 | 0.31276 | 0.076366 | 0.0012508
| 9521 | 0.88642 | 0.010707 | -0.49137 | 0.15354 | -0.36747 | -0.63737 | -0.34923 | 0.021379 | -0.082013 | 0.11847
| 9522 | 0.63299 | 0.18324 | -0.8043 | -0.14706 | 0.7687 | -0.10619 | 0.69 | -0.29226 | 0.1118 | 0.10619
| 9523 | -0.19806 | 0.56034 | -0.32184 | 0.020051 | 0.43229 | 0.18348 | 0.093523 | -0.22418 | -0.13774 | 0.47303
| 9524 | -0.10094 | 0.070968 | 0.4981 | 0.21165 | -0.60088 | 0.39428 | 0.48202 | -0.30322 | 0.52809 | -0.78858
| 9525 | -0.020766 | -0.80176 | -0.25174 | -0.49177 | -0.4755 | -0.2037 | 0.59073 | -0.06957 | -0.3923 | -0.30855
| 9526 | -0.53513 | -0.0011507 | -0.076258 | -0.29551 | -0.77306 | -0.36321 | 0.23613 | 0.68488 | -0.76063 | 0.059628
| 9527 | 0.36652 | -0.24774 | -0.24561 | 0.66251 | -0.48415 | 0.42685 | -0.32554 | -0.88042 | 0.27055 | -0.17787
| 9528 | 0.39279 | 0.41854 | -0.33344 | 0.51616 | 0.075068 | -0.3961 | 0.69784 | 0.66133 | 0.08474 | 0.38364
| 9529 | 0.18914 | -0.56468 | -0.47265 | 0.23665 | 0.56102 | -0.67984 | -0.41562 | -0.35883 | -0.13184 | -0.42216
| 9530 | -0.26658 | -0.080924 | 0.34296 | 0.29466 | -0.094075 | 0.10664 | 0.40443 | -0.09099 | -0.027426 | 0.56745
| 9531 | 0.026501 | -0.40376 | -0.65287 | 0.09077 | 0.021174 | -0.48338 | -0.48318 | 0.31714 | -0.16591 | -0.13866
| 9532 | 0.8454 | 0.062503 | -0.69586 | 0.29155 | -0.1432 | -0.20232 | -0.43088 | -0.058884 | 0.39892 | -0.1439
| 9533 | -0.55 | 0.55921 | 0.44855 | -0.060479 | -0.2265 | -0.43724 | 0.47436 | 0.57374 | 0.029897 | -0.46102
| 9534 | -0.14578 | 0.1533 | -0.26577 | -0.026809 | -0.67612 | 0.29608 | -0.15733 | 0.68679 | -0.1565 | 0.46065
| 9535 | 0.51534 | -0.0047613 | 0.56884 | 0.035479 | 0.12736 | 0.15531 | -0.67674 | 0.042973 | 0.4426 | -0.44982
| 9536 | 0.057291 | -0.71733 | -0.43387 | -0.67427 | 0.057079 | 0.24244 | 0.034133 | 0.43 | 0.33 | 0.18006
| 9537 | -0.033822 | 0.047897 | 0.71417 | 0.8995 | -0.10228 | 0.11451 | -0.12633 | -0.18667 | -0.30725 | 0.93
| 9538 | 0.164 | 0.7184 | -0.66728 | -0.027323 | 0.36952 | 0.31685 | -0.32776 | 0.16663 | -0.74407 | 0.20709
| 9539 | 0.088353 | -0.1162 | -0.046323 | -0.022912 | 0.052741 | -0.094185 | -0.098169 | -0.0058672 | 0.55067 | 0.74058
| 9540 | -0.40729 | -0.37462 | -0.35758 | -0.32687 | -0.73904 | -0.035168 | 0.43671 | -0.23613 | 0.28257 | -0.28049
| 9541 | 0.28691 | 0.43777 | 0.38445 | -0.3882 | -0.24007 | -0.31993 | 0.02897 | 0.36636 | 0.19981 | 0.11383
| 9542 | -0.051264 | -0.19495 | -0.11124 | 0.20571 | -0.019235 | -0.5172 | 0.04381 | -0.59147 | -0.11135 | 0.52324
| 9543 | -0.12267 | 0.11586 | 0.26468 | 0.66399 | 0.23325 | 0.26495 | -0.74135 | -0.16436 | -0.19148 | 0.32747
| 9544 | -0.77887 | 0.42095 | 0.18299 | 0.21827 | 0.58733 | -0.28355 | 0.012225 | -0.010505 | -0.18778 | 0.32096
| 9545 | 0.67488 | -0.18667 | -0.002453 | 0.13484 | 0.096728 | -0.1237 | 0.1513 | 0.73942 | -0.57656 | 0.86036
| 9546 | -0.30136 | 0.45787 | 0.30986 | 0.20747 | -0.62597 | -0.35185 | 0.42912 | 0.038803 | 0.55424 | -0.32287
| 9547 | -0.37622 | 0.33015 | -0.11326 | -0.24893 | -0.47038 | -0.087805 | -0.38526 | -0.61856 | 0.4991 | -0.57609
| 9548 | 0.36384 | 0.19247 | -0.12427 | -0.87 | -0.092751 | 0.41221 | -0.136 | -0.75855 | -0.22058 | 0.43938
| 9549 | 0.48824 | 0.36921 | 0.060905 | 0.058459 | 0.21089 | 0.71663 | -0.35977 | 0.26291 | 0.13808 | -0.17957
| 9550 | -0.49295 | -0.48532 | 0.019949 | 0.46158 | 0.34174 | -0.2621 | 0.0010506 | -0.34083 | 0.41768 | 0.39543
| 9551 | 0.26142 | -0.79191 | -0.30928 | 0.0922 | -0.33314 | -0.05348 | -0.26074 | 0.50614 | -0.66251 | 0.40983
| 9552 | 0.45806 | -0.66074 | -0.30567 | -0.13913 | -0.31626 | -0.37207 | 0.20848 | 0.7687 | -0.20798 | -0.39676
| 9553 | -0.57988 | -0.084304 | -0.31728 | -0.30207 | -0.071184 | 0.35479 | -0.014049 | -0.46661 | 0.2216 | 0.61309
| 9554 | 0.21584 | -0.26386 | 0.061331 | 0.013744 | 0.41613 | 0.23849 | -0.14788 | -0.32554 | 0.19794 | 0.11417
| 9555 | 0.046847 | -0.045694 | 0.43141 | 0.60668 | 0.09165 | -0.0019519 | -0.13646 | -0.13161 | 0.066137 | -0.50857
| 9556 | 0.21635 | -0.012022 | 0.081795 | -0.04026 | -0.029176 | 0.39892 | 0.26754 | -0.024039 | 0.073124 | -0.32702
| 9557 | -0.088792 | -0.067423 | 0.11631 | -0.60364 | 0.39049 | -0.027118 | 0.18434 | 0.37622 | 0.44009 | -0.23417
| 9558 | 0.46549 | 0.49651 | -0.27591 | -0.26413 | 0.31963 | -0.80843 | 0.074203 | 0.83417 | -0.95877 | -0.40848
| 9559 | 0.074203 | -0.58371 | 0.11293 | -0.12199 | -0.57538 | 0.40276 | -0.47246 | 0.40628 | 0.09209 | -0.48241
| 9560 | -0.40966 | 0.074743 | -0.35092 | 0.13023 | -0.52387 | -0.69097 | 0.22883 | 0.59466 | 0.39842 | 0.24482
| 9561 | 0.46121 | -0.33675 | 0.17084 | 0.31305 | 0.23143 | 0.55022 | -0.15259 | -0.25562 | -0.42216 | 0.61103
| 9562 | 0.30365 | -0.21482 | -0.42095 | -0.031341 | -0.58443 | -0.099389 | -0.37398 | 0.78858 | -0.10753 | -0.19396
| 9563 | -0.38429 | 0.36478 | 0.1729 | 0.062823 | -0.53989 | 0.12142 | -0.78858 | -0.087476 | -0.097171 | -0.012731
| 9564 | 0.52324 | -0.58587 | -0.15484 | -0.56011 | -0.33 | 0.12519 | 0.2625 | -0.39825 | 0.036102 | 0.40713
| 9565 | -0.24469 | 0.44782 | -0.029691 | 0.36968 | -0.068174 | -0.13577 | -0.34008 | 0.57941 | -0.40898 | 0.11473
| 9566 | -0.79628 | 0.26986 | -0.23718 | -0.48824 | 0.25818 | 0.30754 | 0.31116 | -0.4417 | -0.17326 | -0.49334
| 9567 | -0.22883 | -0.68488 | -0.3297 | -0.0038574 | 0.32125 | -0.13634 | 0.16639 | -0.16687 | 0.13403 | -0.43053
| 9568 | 0.064853 | -0.25482 | -0.15448 | 0.03 | -0.49751 | -0.59392 | 0.42982 | 0.3038 | -0.28958 | -0.31247
| 9569 | 0.55739 | 0.27247 | -0.37976 | -0.33179 | 0.048948 | 0.2975 | -0.17314 | -0.36604 | 0.52429 | -0.30164
| 9570 | 0.46437 | 0.10552 | -0.023936 | -0.44242 | -0.021685 | 0.15828 | -0.2496 | 0.023117 | -0.45714 | 0.66162
| 9571 | -0.59813 | 0.55223 | 0.61908 | -0.32613 | -0.8366 | 0.25334 | -0.70352 | 0.6985 | 0.25281 | 0.35231
| 9572 | -0.18361 | -0.54448 | 0.62304 | 0.073124 | 0.53064 | 0.54294 | 0.09154 | 0.20571 | -0.072369 | 0.5656
| 9573 | 0.0090913 | -0.0010506 | 0.90151 | -0.0036567 | -0.12897 | -0.65201 | -0.2621 | 0.029073 | -0.32346 | -0.13023
| 9574 | -0.052846 | -0.22818 | -0.38526 | -0.15744 | -0.25374 | -0.17508 | 0.15259 | 0.2326 | -0.01344 | 0.037451
| 9575 | -0.69884 | 0.024859 | -0.23312 | 0.1127 | -0.69718 | -0.21572 | 0.078642 | -0.23691 | 0.51041 | 0.027735
| 9576 | 0.48164 | 0.25013 | 0.552 | 0.10072 | -0.33539 | -0.093854 | -0.56884 | 0.32125 | -0.048948 | 0.010808
| 9577 | 0.46624 | -0.3186 | 0.30337 | 0.084304 | 0.67612 | 0.20596 | 0.17909 | 0.3743 | 0.035272 | -0.14613
| 9578 | 0.2924 | 0.57727 | 0.58323 | 0.079837 | -0.56034 | 0.16627 | -0.60821 | 0.32051 | -0.20747 | 0.029691
| 9579 | 0.17314 | 0.37767 | -0.20131 | -0.032271 | -0.02609 | 0.074743 | -0.59491 | -0.37 | -0.83969 | 0.24125
| 9580 | -0.083758 | 0.17592 | -0.58395 | -0.027837 | 0.54229 | -0.65839 | -0.81265 | -0.23665 | -0.12176 | -0.038179
| 9581 | -0.67243 | -0.43973 | 0.012731 | -0.5458 | 0.16976 | -0.11869 | 0.10184 | -0.06165 | 0.15496 | -0.54646
| 9582 | -0.059309 | -0.39395 | -0.052741 | 0.28439 | 0.024551 | 0.28174 | 0.24283 | -0.18532 | 0.59714 | -0.35665
| 9583 | -0.32985 | -0.048212 | -0.23469 | -0.17677 | -0.40075 | -0.016283 | 0.28257 | 0.074419 | 0.2193 | -0.072584
| 9584 | 0.71627 | -0.4344 | -0.11383 | 0.24588 | -0.38137 | 0.049895 | 0.39626 | 0.66638 | -0.063464 | 0.077883
| 9585 | -0.30466 | 0.51102 | -0.082558 | 0.4344 | 0.19309 | -0.30769 | 0.028558 | -0.72779 | 0.11983 | -0.75282
| 9586 | 0.65431 | 0.0017515 | -0.65489 | -0.1952 | 0.23836 | -0.50311 | 0.51761 | 0.17205 | 0.38251 | 0.10541
| 9587 | 0.32776 | -0.024962 | -0.36211 | -0.082776 | -0.035272 | -0.54867 | 0.0059678 | -0.036621 | 0.22096 | 0.37542
| 9588 | -0.46493 | 0.10306 | 0.47493 | 0.0029544 | -0.0173 | 0.00055015 | 0.43264 | 0.13392 | -0.55785 | 0.61
| 9589 | 0.22006 | 0.84867 | 0.89276 | 0.83118 | 0.072261 | 0.26986 | 0.22598 | 0.17556 | 0.007075 | -0.39115
| 9590 | -0.30552 | -0.096728 | 0.64801 | -0.070323 | 0.41119 | -0.47818 | 0.18263 | -0.10921 | -0.38056 | 0.35308
| 9591 | -0.46718 | -0.91938 | -0.62119 | 0.49 | -0.25656 | 0.43759 | -0.448 | -0.27261 | 0.2625 | 0.29637
| 9592 | -0.11779 | -0.17278 | -0.35324 | 0.37207 | -0.33254 | 0.29254 | -0.10731 | -0.548 | 0.47952 | -0.41187
| 9593 | -0.35386 | -0.60389 | -0.50695 | -0.58323 | -0.33841 | -0.61725 | 0.89464 | -0.55739 | 0.52115 | -0.348
| 9594 | -0.064425 | -0.035376 | 0.72632 | -0.032891 | -0.30754 | -0.052213 | -0.11869 | -0.37302 | 0.31305 | 0.25656
| 9595 | 0.2621 | 0.31043 | 0.37032 | 0.73751 | 0.20119 | 0.14953 | -0.4344 | -0.37032 | 0.47798 | -0.3751
| 9596 | -0.76784 | 0.11011 | -0.072261 | -0.43229 | 0.35324 | 0.22715 | 0.1109 | 0.014556 | 0.58299 | -0.31626
| 9597 | -0.72161 | 0.39082 | -0.82883 | -0.24217 | 0.030206 | -0.44313 | 0.01547 | -0.52492 | 0.33781 | -0.84412
| 9598 | 0.11564 | -0.019745 | 0.36747 | 0.46381 | -0.0040582 | -0.31174 | 0.55044 | 0.30222 | -0.1338 | 0.17629
| 9599 | -0.52915 | -0.33811 | 0.40309 | 0.096285 | 0.32361 | -0.436 | -0.50918 | -0.098058 | -0.38234 | 0.20019
| 9600 | 0.17714 | 0.26156 | 0.41374 | 0.034133 | -0.91693 | 0.73904 | 0.61257 | 0.22212 | -0.65201 | -0.046113
| 9601 | -0.099389 | 0.5768 | 0.23143 | 0.17169 | 0.31102 | 0.45732 | 0.014556 | 0.60592 | -0.63326 | 0.27924
| 9602 | 0.36794 | -0.25535 | 0.74407 | 0.38787 | 0.14765 | -0.65693 | -0.15035 | 0.3629 | -0.3425 | -0.058671
| 9603 | -0.022912 | 0.043287 | 0.023834 | -0.47246 | -0.25872 | 0.14461 | -0.24987 | -0.26754 | 0.22689 | -0.23156
| 9604 | 0.49691 | 0.44188 | -0.036309 | -0.64857 | -0.25307 | 0.28355 | -0.037036 | 0.55649 | -0.39329 | 0.20432
| 9605 | -0.13994 | 0.078425 | 0.38137 | -0.57562 | 0.016384 | -0.12473 | -0.75403 | 0.57774 | 0.17617 | -0.42441
| 9606 | -0.2147 | 0.29864 | 0.57988 | -0.81588 | 0.083758 | 0.22328 | -0.029073 | 0.6578 | -0.021992 | 0.2427
| 9607 | -0.51492 | 0.42703 | 0.2941 | -0.22741 | 0.72486 | 0.34129 | -0.2398 | -0.26767 | -0.4286 | -0.13901
| 9608 | -0.52324 | 0.014252 | -0.5005 | -0.32628 | 0.53751 | 0.40611 | -0.39049 | 0.030412 | -0.044542 | 0.46849
| 9609 | -0.20546 | 0.24442 | 0.61856 | -0.59639 | 0.4046 | 0.18104 | 0.42147 | 0.044542 | -0.28425 | 0.046113
| 9610 | 0.39494 | -0.44638 | -0.0911 | -0.22096 | 0.13519 | 0.18275 | -0.056125 | 0.09066 | -0.46251 | 0.76698
| 9611 | 0.37767 | 0.18532 | -0.55875 | 0.11315 | 0.22715 | -0.67427 | 0.018623 | -0.14941 | -0.57846 | 0.023322
| 9612 | 0.60617 | -0.43938 | 0.60516 | 0.4755 | -0.018216 | -0.3369 | 0.40848 | 0.058884 | 0.24033 | 0.22586
| 9613 | 0.19894 | -0.58612 | 0.24774 | -0.42199 | -0.074419 | -0.20735 | 0.1797 | 0.078208 | -0.1729 | 0.23547
| 9614 | 0.74212 | 0.31949 | -0.052213 | 0.50452 | -0.22715 | 0.89753 | 0.19869 | -0.60668 | 0.33796 | 0.39312
| 9615 | 0.38008 | -0.058459 | -0.14988 | 0.18827 | 0.15259 | 0.84933 | 0.18618 | 0.035583 | -0.45365 | 0.49216
| 9616 | -0.30913 | -0.60364 | -0.096064 | 0.28076 | -0.72125 | 0.57917 | -0.19223 | -0.01091 | -0.36952 | 0.36039
| 9617 | 0.21254 | -0.45714 | -0.24495 | 0.6319 | 0.22818 | -0.25334 | -0.01547 | -0.3025 | 0.1229 | 0.20634
| 9618 | -0.14297 | -0.19086 | -0.36873 | -0.21114 | 0.24681 | -0.086381 | -0.37944 | 0.003155 | 0.31261 | -0.73904
| 9619 | -0.58612 | 0.16209 | 0.29495 | 0.099167 | 0.029073 | 0.41085 | 0.19682 | 0.018216 | -0.23888 | -0.0044599
| 9620 | -0.74643 | 0.023732 | 0.56653 | 0.015063 | 0.037451 | -0.32494 | -0.47665 | -0.084304 | -0.6249 | -0.26386
| 9621 | -0.39825 | -0.046008 | -0.28649 | 0.20344 | -0.9272 | 0.17314 | -0.24614 | 0.78529 | 0.44855 | 0.25013
| 9622 | 0.84801 | -0.38267 | -0.0033556 | 0.25468 | 0.71069 | 0.26007 | -0.10944 | -0.81917 | -0.32643 | -0.1382
| 9623 | -0.033305 | -0.48824 | -0.065281 | -0.093965 | 0.84031 | 0.21013 | 0.47837 | 0.12966 | 0.4979 | -0.92584
| 9624 | 0.10172 | 0.62357 | 0.61 | 0.59639 | -0.87631 | 0.55267 | -0.62731 | -0.09066 | -0.23143 | 0.012528
| 9625 | -0.41408 | -0.55089 | 0.23718 | 0.077558 | 0.048527 | -0.061864 | -0.34479 | 0.46849 | -0.5245 | -0.18692
| 9626 | -0.016486 | 0.27082 | 0.66849 | -0.336 | 0.021583 | -0.66489 | 0.12085 | -0.6407 | -0.46288 | 0.037244
| 9627 | -0.252 | -0.21304 | 0.032374 | 0.38673 | -0.35123 | 0.70386 | 0.01263 | -0.27674 | 0.45511 | -0.3851
| 9628 | 0.16316 | 0.22315 | -0.073771 | -0.28481 | 0.081795 | 0.15283 | -0.77796 | -0.50654 | 0.054326 | 0.33962
| 9629 | -0.17556 | 0.25764 | -0.40966 | 0.45438 | -0.05 | -0.32643 | 0.11112 | -0.36463 | -0.023117 | -0.16531
| 9630 | 0.1204 | -0.070645 | -0.37334 | 0.23273 | 0.066351 | -0.35463 | 0.13334 | 0.05158 | 0.24721 | -0.55379
| 9631 | -0.17217 | 0.69553 | 0.0010506 | 0.23836 | 0.15496 | -0.36494 | -0.41733 | -0.77044 | 0.49572 | -0.63408
| 9632 | -0.39709 | 0.020561 | 0.1814 | 0.56676 | -0.37494 | 0.63326 | 0.3074 | -0.53021 | 0.087914 | -0.6257
| 9633 | -0.46251 | 0.66074 | -0.020868 | 0.6118 | 0.88731 | -0.32836 | 0.37318 | -0.30552 | -0.078859 | -0.42389
| 9634 | 0.78114 | 0.91112 | 0.017707 | -0.13484 | -0.13461 | -0.55223 | -0.39659 | -0.13843 | -0.15946 | -0.89183
| 9635 | 0.35743 | -0.084631 | -0.45438 | 0.28467 | -0.38755 | 0.044437 | 0.26156 | -0.59788 | -0.25589 | -0.12347
| 9636 | -0.11214 | -0.46774 | -0.10161 | 0.38951 | -0.10876 | 0.49771 | -0.36731 | 0.50271 | 0.28845 | 0.3297
| 9637 | 0.39975 | 0.18104 | -0.21521 | 0.48202 | -0.64125 | 0.70285 | 0.48029 | 0.51844 | 0.12176 | 0.15756
| 9638 | 0.1879 | -0.60088 | 0.79143 | 0.2133 | -0.29014 | 0.085506 | -0.22508 | 0.53816 | -0.29296 | -0.67182
| 9639 | -0.85269 | 0.089231 | 0.16723 | -0.34693 | -0.24086 | 0.28327 | 0.14636 | -0.71733 | 0.1565 | 0.66103
| 9640 | -0.22935 | -0.8747 | 0.38738 | -0.31524 | -0.21355 | 0.020255 | -0.40932 | -0.20407 | -0.59664 | -0.22431
| 9641 | 0.47303 | -0.2052 | -0.045799 | 0.44728 | -0.048212 | 0.40628 | -0.73037 | -0.0081835 | -0.47303 | -0.22418
| 9642 | 0.024449 | 0.26454 | -0.36557 | 0.448 | -0.0014511 | 0.164 | -0.44385 | 0.58036 | 0.24178 | 0.85405
| 9643 | 0.54273 | -0.50331 | 0.49354 | 0.61751 | 0.14613 | 0.058246 | -0.2216 | 0.13611 | -0.40881 | 0.1868
| 9644 | -0.17084 | 0.35 | 0.29879 | 0.42147 | -0.40242 | -0.7184 | 0.79143 | 0.27069 | 0.044961 | 0.56125
| 9645 | 0.10117 | -0.0044599 | 0.032891 | 0.86036 | -0.84031 | -0.010101 | -0.52261 | 0.11169 | -0.10306 | 0.38332
| 9646 | -0.68552 | 0.236 | 0.057609 | -0.1694 | -0.074527 | 0.36023 | -0.33179 | 0.69065 | 0.09695 | -0.39477
| 9647 | 0.20823 | 0.11462 | 0.097614 | -0.58251 | 0.17181 | 0.77087 | -0.38348 | 0.58251 | 0.12222 | -0.026398
| 9648 | 0.94432 | 0.3767 | -0.57727 | 0.030309 | -0.073447 | 0.089561 | 0.12051 | -0.19806 | -0.033822 | -0.19981
| 9649 | -0.12862 | -0.79482 | -0.73037 | -0.31014 | -0.8995 | -0.2689 | -0.62357 | -0.34296 | -0.33284 | -0.17423
| 9650 | -0.76399 | 0.49413 | -0.011516 | -0.33886 | 0.62171 | -0.50939 | 0.56239 | 0.18951 | 0.31509 | 0.27233
| 9651 | -0.1082 | 0.25441 | 0.69619 | 0.56722 | -0.026707 | -0.47341 | -0.33509 | -0.38673 | 0.29113 | 0.25697
| 9652 | -0.35696 | -0.39942 | -0.15946 | -0.056973 | 0.58203 | -0.56354 | 0.37462 | -0.42147 | -0.41871 | 0.23195
| 9653 | -0.43053 | 0.29197 | -0.15236 | -0.048527 | 0.39181 | -0.67953 | -0.69 | 0.74525 | -0.13692 | 0.10518
| 9654 | 0.3477 | -0.20911 | 0.22611 | -0.14918 | -0.25912 | -0.69455 | -0.93144 | -0.0073772 | -0.28076 | -0.32955
| 9655 | -0.064532 | 0.36431 | 0.21955 | 0.006169 | -0.34846 | -0.33871 | -0.54054 | -0.46962 | 0.018114 | 0.026809
| 9656 | 0.083867 | 0.63163 | 0.0058672 | 0.21725 | -0.011213 | -0.38918 | -0.038699 | -0.9089 | 0.38073 | 0.029794
| 9657 | -0.16723 | 0.88554 | -0.62145 | 0.21228 | 0.19557 | 0.10373 | -0.5735 | -0.10195 | 0.13774 | 0.12507
| 9658 | -0.55111 | -0.51534 | -0.0058672 | -0.79384 | -0.46362 | 0.31174 | -0.38624 | -0.22006 | -0.11259 | 0.081142
| 9659 | 0.11745 | 0.030103 | 0.26945 | 0.55178 | -0.41768 | 0.43105 | -0.10228 | 0.071076 | -0.28831 | -0.6077
| 9660 | -0.19483 | 0.071614 | 0.077666 | 0.25939 | 0.049789 | 0.19744 | 0.12233 | -0.23823 | -0.030412 | 0.28859
| 9661 | 0.0058672 | -0.35587 | -0.096175 | -0.6382 | -0.022196 | -0.43053 | -0.42337 | 0.22431 | 0.43938 | -0.51616
| 9662 | 0.35231 | 0.43299 | 0.28411 | 0.19657 | 0.43955 | -0.80025 | -0.21051 | -0.63244 | -0.02794 | 0.62066
| 9663 | -0.48609 | -0.014252 | 0.16928 | 0.87712 | 0.40729 | -0.35587 | -0.086053 | -0.19309 | -0.22586 | -0.44547
| 9664 | -0.4206 | -0.33045 | -0.85893 | -0.30079 | -0.71804 | -0.15543 | -0.59269 | 0.17145 | -0.20019 | 0.071291
| 9665 | 0.4408 | -0.57585 | -0.41238 | -0.12793 | 0.58443 | -0.22379 | -0.48648 | 0.027323 | -0.43264 | -0.51906
| 9666 | -0.65722 | 0.57633 | -0.014353 | -0.4206 | 0.0090913 | 0.18988 | -0.53449 | -0.10094 | -0.34571 | -0.034754
| 9667 | 0.76484 | 0.29708 | 0.40359 | 0.45898 | 0.62838 | -0.20583 | -0.57303 | -0.32494 | 0.41323 | 0.36794
| 9668 | 0.19956 | -0.16352 | 0.095732 | -0.13565 | 0.26713 | 0.0079819 | 0.14414 | -0.16232 | 0.43848 | 0.031238
| 9669 | 0.45365 | -0.37992 | -0.23404 | 0.86399 | -0.58805 | 0.89276 | 0.82941 | -0.61934 | 0.17909 | 0.09022
| 9670 | -0.0077803 | -0.12154 | 0.71382 | 0.552 | -0.36102 | -0.039115 | -0.15899 | 0.46102 | 0.55156 | -0.50796
| 9671 | -0.11157 | 0.83297 | 0.28271 | -0.4344 | -0.73524 | 0.17447 | -0.1072 | 0.48067 | 0.10585 | -0.6382
| 9672 | 0.62251 | -0.23273 | 0.29282 | -0.55402 | -0.50878 | -0.072153 | 0.013643 | -0.54933 | -0.43229 | 0.35696
| 9673 | 0.09033 | -0.15389 | 0.70453 | -0.34479 | 0.37191 | 0.76484 | 0.5663 | -0.46028 | -0.39676 | 0.20747
| 9674 | 0.52745 | 0.34464 | 0.039427 | -0.048422 | -0.16759 | -0.4653 | 0.32214 | 0.14227 | -0.74801 | -0.0019519
| 9675 | 0.37446 | 0.36274 | 0.42424 | 0.77087 | -0.50756 | -0.3248 | -0.24907 | 0.64715 | -0.83417 | 0.59417
| 9676 | -0.11169 | 0.14941 | -0.51205 | -0.76063 | -0.10462 | 0.14847 | -0.32184 | 0.0046609 | -0.84284 | 0.35108
| 9677 | -0.38478 | 0.48299 | -0.60364 | -0.55022 | -0.24469 | -0.15602 | -0.35992 | 0.010505 | 0.56445 | 0.12108
| 9678 | -0.6703 | 0.65693 | -0.0081835 | -0.19247 | -0.80791 | 0.09695 | 0.54492 | -0.31904 | 0.39593 | 0.57444
| 9679 | 0.11101 | -0.34693 | -0.34954 | 0.6952 | -0.70017 | 0.022912 | 0.49572 | -0.09022 | 0.48183 | -0.56907
| 9680 | 0.15839 | 0.25214 | -0.27357 | 0.22702 | 0.2076 | 0.21533 | 0.29296 | -0.50857 | -0.52745 | -0.57257
| 9681 | 0.50675 | -0.67243 | -0.45328 | -0.54207 | 0.2907 | -0.21674 | -0.13184 | 0.33299 | -0.18753 | 0.04266
| 9682 | -0.29807 | 0.5011 | -0.31641 | -0.91815 | 0.63765 | -0.51287 | -0.37478 | 0.25053 | -0.27674 | -0.084085
| 9683 | 0.023629 | -0.31087 | -0.2733 | -0.065281 | -0.06197 | -0.018725 | -0.36133 | 0.11135 | -0.47094 | -0.45383
| 9684 | 0.12028 | -0.42147 | 0.49453 | -0.23013 | -0.1323 | 0.061864 | 0.009596 | 0.098501 | 0.33766 | 0.54514
| 9685 | 0.11938 | -0.45164 | -0.015876 | 0.63435 | 0.31611 | 0.48106 | 0.1786 | -0.64377 | -0.71069 | -0.11915
| 9686 | -0.032477 | -0.16328 | 0.17459 | -0.33781 | -0.79143 | -0.26237 | -0.18926 | 0.22844 | -0.27702 | -0.18594
| 9687 | 0.34418 | 0.042764 | 0.42199 | 0.68204 | 0.23744 | 0.30812 | -0.11011 | 0.14052 | 0.097282 | 0.0017515
| 9688 | 0.1559 | 0.68235 | -0.56011 | 0.19595 | 0.76698 | -0.0080827 | -0.41854 | 0.055913 | 0.032581 | 0.11835
| 9689 | -0.099833 | 0.37542 | 0.073771 | 0.17872 | -0.25133 | -0.033925 | 0.021276 | 0.2047 | -0.16555 | 0.34908
| 9690 | -0.13438 | 0.58903 | 0.54956 | 0.45861 | 0.12966 | -0.017809 | -0.8043 | 0.073879 | 0.48609 | -0.2402
| 9691 | 0.032477 | 0.38137 | 0.21228 | -0.36984 | 0.22676 | -0.80532 | -0.71104 | 0.62892 | 0.19346 | 0.70352
| 9692 | -0.3956 | -0.84157 | 0.10362 | -0.4553 | 0.33344 | 0.44565 | 0.61335 | 0.2256 | -0.026193 | -0.69884
| 9693 | -0.2081 | -0.030722 | -0.43281 | -0.13994 | 0.53406 | 0.09121 | 0.18397 | 0.21432 | -0.31363 | -0.32836
| 9694 | -0.25791 | 0.29056 | -0.2621 | -0.0076795 | 0.45164 | -0.69586 | -0.43759 | 0.0082843 | -0.020255 | 0.17677
| 9695 | 0.26047 | 0.56514 | 0.68393 | -0.46046 | -0.24707 | 0.54956 | 0.084522 | -0.45438 | -0.077991 | 0.1852
| 9696 | -0.2711 | -0.14414 | -0.20634 | -0.25576 | -0.37016 | -0.65229 | -0.19 | -0.22987 | -0.31919 | 0.031754
| 9697 | -0.2773 | -0.21 | 0.09165 | -0.79433 | -0.43973 | -0.088134 | -0.26754 | -0.09176 | 0.4531 | 0.26481
| 9698 | 0.63054 | 0.55469 | 0.71769 | -0.08136 | 0.40393 | 0.62597 | 0.3375 | 0.81212 | 0.16783 | 0.2147
| 9699 | 0.15863 | -0.57964 | -0.09209 | 0.24654 | -0.83721 | -0.34555 | 0.64744 | 0.51472 | -0.43176 | 0.009798
| 9700 | 0.42181 | -0.39016 | -0.41528 | 0.021685 | 0.41425 | 0.48532 | -0.48824 | -0.57233 | -0.074635 | -0.13762
| 9701 | -0.52408 | 0.29807 | 0.33314 | 0.12599 | -0.051264 | -0.47875 | 0.027426 | 0.47914 | 0.24947 | 0.45787
| 9702 | -0.043705 | -0.52345 | -0.25899 | -0.40443 | -0.48961 | -0.45695 | -0.75979 | -0.48804 | 0.3923 | -0.17921
| 9703 | 0.088463 | -0.40494 | -0.20672 | 0.22805 | -0.066458 | -0.73486 | -0.2524 | -0.39461 | 0.15472 | -0.45255
| 9704 | -0.075608 | 0.63986 | 0.17447 | -0.61777 | 0.16149 | 0.21215 | 0.70794 | -0.072476 | 0.21038 | -0.075608
| 9705 | 0.054326 | -0.59294 | -0.0866 | 0.41425 | -0.42424 | 0.076258 | -0.17012 | -0.47607 | 0.49354 | 0.88642
| 9706 | 0.23744 | 0.57774 | -0.73637 | 0.23247 | 0.075716 | 0.58539 | -0.58491 | 0.49315 | 0.2602 | -0.49098
| 9707 | -0.54712 | -0.41374 | 0.049789 | 0.019643 | 0.27896 | 0.38413 | -0.48902 | -0.25267 | 0.4993 | 0.39444
| 9708 | 0.38299 | 0.041929 | 0.65114 | 0.4999 | 0.08978 | 0.2567 | 0.17483 | -0.059309 | -0.05348 | -0.62838
| 9709 | -0.18385 | 0.12416 | 0.63903 | 0.18766 | -0.4041 | -0.11338 | 0.13669 | -0.76655 | -0.40108 | -0.40746
| 9710 | 0.17169 | 0.22702 | -0.0088895 | 0.41682 | -0.46643 | -0.55267 | -0.1559 | 0.076691 | -0.38657 | -0.28216
| 9711 | -0.4902 | 0.47189 | 0.22508 | -0.0063703 | 0.10406 | 0.16472 | 0.39362 | 0.079185 | -0.26686 | 0.67427
| 9712 | -0.19359 | 0.70931 | 0.14941 | 0.40025 | 0.2119 | 0.69065 | 0.21546 | 0.41613 | 0.09066 | 0.45603
| 9713 | 0.072045 | 0.41204 | 0.41 | 0.33179 | -0.14777 | -0.4981 | -0.68172 | -0.35247 | 0.33735 | 0.31334
| 9714 | -0.047372 | -0.47818 | 0.28523 | -0.63599 | -0.16723 | 0.085068 | 0.80328 | -0.78669 | 0.27027 | 0.49118
| 9715 | 0.1863 | 0.18914 | 0.3148 | 0.53794 | 0.57374 | -0.17471 | -0.31538 | 0.24495 | -0.37446 | 0.448
| 9716 | -0.72269 | -0.14941 | 0.19919 | -0.093303 | -0.28216 | 0.36921 | 0.82883 | -0.19645 | -0.21215 | -0.29353
| 9717 | -0.3087 | 0.59245 | -0.08234 | 0.54978 | -0.66399 | 0.44313 | 0.21814 | 0.46176 | -0.62624 | 0.3568
| 9718 | 0.40175 | -0.22495 | 0.6249 | 0.75731 | -0.18643 | 0.81053 | 0.67243 | 0.16916 | 0.25885 | -0.35386
| 9719 | -0.0049623 | 0.11733 | -0.28453 | 0.16077 | -0.65086 | 0.09518 | -0.5201 | 0.46437 | -0.054114 | 0.65489
| 9720 | -0.12725 | 0.057397 | 0.18422 | 0.47322 | 0.41596 | 0.11813 | 0.39792 | 0.1814 | -0.075176 | 0.064746
| 9721 | 0.48707 | -0.17617 | 0.01547 | 0.094406 | 0.51205 | -0.14566 | 0.2496 | -0.54076 | 0.25912 | 0.38575
| 9722 | -0.044019 | -0.31743 | -0.19819 | -0.5663 | 0.81372 | -0.40042 | 0.5583 | 0.0078811 | -0.087257 | -0.24522
| 9723 | 0.21495 | -0.28174 | 0.31087 | -0.0056661 | 0.33134 | -0.09706 | 0.49137 | 0.31626 | -0.099389 | 0.36589
| 9724 | -0.93 | 0.81318 | 0.2733 | -0.11405 | -0.54207 | -0.23039 | 0.44674 | 0.011415 | -0.53513 | -0.054431
| 9725 | -0.66549 | -0.17326 | -0.31553 | 0.36715 | 0.19881 | 0.048527 | -0.063998 | -0.028455 | -0.75322 | -0.32081
| 9726 | 0.73074 | -0.50412 | 0.14122 | 0.36243 | 0.66789 | -0.164 | 0.41238 | -0.10217 | 0.58757 | -0.080381
| 9727 | -0.33856 | -0.048317 | -0.26047 | 0.066351 | -0.049263 | -0.79579 | 0.32628 | -0.1729 | -0.12028 | 0.03714
| 9728 | 0.95877 | 0.51123 | -0.13519 | -0.50553 | 0.0064709 | 0.47322 | 0.72486 | -0.56676 | 0.41017 | -0.88554
| 9729 | 0.24734 | -0.027632 | 0.20735 | -0.54033 | 0.087366 | -0.57515 | -0.252 | 0.021685 | 0.33314 | 0.1439
| 9730 | 0.51886 | -0.14285 | -0.34908 | -0.53751 | 0.60389 | -0.62597 | 0.46793 | -0.096728 | 0.78669 | -0.0075787
| 9731 | 0.11507 | 0.36668 | 0.74722 | -0.65316 | 0.21432 | -0.0004501 | 0.11972 | -0.44331 | -0.62731 | -0.054855
| 9732 | -0.17024 | -0.01091 | 0.015876 | 0.29183 | -0.35231 | -0.42703 | -0.054431 | -0.22058 | 0.042764 | 0.35914
| 9733 | -0.45806 | 0.25468 | -0.55966 | -0.25227 | -0.1814 | -0.49295 | 0.70828 | 0.074203 | 0.10028 | 0.82708
| 9734 | -0.019745 | 0.21994 | 0.39942 | -0.069677 | 0.20081 | -0.36431 | 0.47971 | -0.009596 | -0.47665 | -0.42233
| 9735 | -0.62677 | -0.25495 | 0.11609 | -0.48785 | -0.46139 | -0.20949 | -0.39345 | -0.61257 | 0.17933 | 0.071614
| 9736 | -0.1628 | 0.52136 | 0.13669 | -0.83 | 0.071507 | -0.65345 | 0.69751 | 0.11146 | -0.68615 | -0.037451
| 9737 | -0.033098 | 0.52303 | -0.82708 | 0.46512 | 0.11191 | -0.15377 | -0.18508 | 0.23691 | 0.61257 | 0.041929
| 9738 | -0.043601 | -0.60592 | 0.55807 | -0.04381 | 0.51307 | -0.50776 | -0.12656 | 0.65634 | 0.24667 | -0.09132
| 9739 | 0.056125 | -0.053691 | 0.54338 | 0.093854 | 0.84867 | 0.50776 | -0.69357 | 0.37879 | 0.1237 | -0.77306
| 9740 | -0.081795 | -0.11293 | 0.15578 | 0.96683 | 0.8882 | 0.31875 | 0.84933 | 0.14695 | 0.80328 | -0.53772
| 9741 | -0.63958 | -0.40192 | -0.1127 | 0.36164 | 0.12702 | -0.018318 | 0.70725 | 0.23678 | 0.62066 | -0.078208
| 9742 | 0.29353 | 0.21738 | -0.03579 | -0.54229 | 0.36274 | -0.22974 | 0.39279 | -0.34448 | 0.26156 | 0.55067
| 9743 | 0.46362 | 0.20119 | -0.13948 | -0.17265 | 0.077341 | -0.015368 | 0.066244 | -0.51948 | 0.50715 | -0.13046
| 9744 | -0.083321 | -0.39875 | -0.22715 | 0.81807 | -0.11022 | 0.019439 | 0.24973 | -0.3309 | 0.87958 | 0.30567
| 9745 | 0.31553 | -0.2343 | -0.4857 | -0.038491 | -0.68235 | -0.20861 | -0.22534 | -0.12199 | 0.53513 | 0.44421
| 9746 | -0.48882 | 0.34008 | 0.1694 | 0.58587 | -0.4981 | 0.79531 | 0.136 | -0.092751 | -0.53967 | 0.0082843
| 9747 | 0.17338 | -0.1825 | -0.68615 | 0.0004501 | -0.89656 | 0.06603 | 0.018114 | -0.84933 | -0.34693 | -0.38461
| 9748 | -0.61206 | -0.052952 | 0.16054 | 0.42009 | -0.51472 | -0.017401 | -0.3214 | 0.075068 | 0.083321 | 0.11609
| 9749 | -0.056867 | -0.2575 | -0.9089 | 0.51369 | -0.38413 | -0.32806 | -0.062503 | -0.53363 | 0.23273 | 0.4995
| 9750 | 0.1852 | 0.60364 | 0.72705 | -0.62677 | 0.55424 | -0.45091 | -0.53707 | 0.0059678 | -0.14519 | 0.18373
| 9751 | 0.71 | -0.14496 | 0.8739 | 0.56814 | -0.13034 | -0.40628 | 0.23823 | 0.034236 | -0.9245 | 0.13253
| 9752 | -0.33419 | 0.008486 | -0.078208 | -0.1432 | -0.027632 | -0.19223 | 0.51123 | -0.27938 | 0.11688 | -0.41034
| 9753 | 0.089561 | -0.29708 | 0.062183 | 0.09055 | 0.22135 | -0.25455 | -0.41819 | -0.050526 | 0.14671 | -0.452
| 9754 | 0.30423 | 0.66044 | 0.10273 | 0.15094 | -0.006169 | 0.24947 | 0.13161 | -0.70184 | -0.062183 | 0.24389
| 9755 | -0.036517 | -0.17836 | -0.13588 | -0.062397 | 0.13449 | -0.11417 | -0.50371 | 0.19049 | -0.49532 | -0.20975
| 9756 | 0.21661 | 0.24165 | -0.36478 | -0.14169 | 0.40527 | -0.40865 | 0.28972 | -0.61026 | 0.43317 | -0.2216
| 9757 | 0.84605 | 0.30351 | -0.59763 | 0.038387 | 0.083103 | -0.1063 | -0.14192 | 0.73 | -0.30595 | 0.081469
| 9758 | 0.037555 | -0.51307 | 0.28859 | 0.43 | 0.65809 | -0.32717 | -0.48863 | -0.83721 | 0.57327 | 0.083321
| 9759 | -0.41716 | 0.24561 | -0.38624 | -0.031444 | -0.49236 | 0.45954 | -0.031651 | 0.80635 | 0.5436 | -0.19856
| 9760 | -0.42216 | 0.3186 | -0.47971 | -0.52073 | -0.63108 | 0.64801 | 0.42877 | 0.028558 | -0.55672 | -0.46925
| 9761 | 0.48551 | -0.0045604 | -0.14894 | 0.087695 | -0.37654 | 0.82479 | 0.15507 | 0.62437 | 0.10139 | -0.14496
| 9762 | 0.43299 | -0.43759 | -0.58563 | 0.009596 | -0.61908 | -0.37 | 0.30884 | -0.21304 | -0.13785 | -0.09154
| 9763 | 0.78206 | 0.10854 | -0.056655 | -0.87233 | -0.38885 | -0.58131 | -0.71312 | 0.21444 | 0.53043 | -0.28439
| 9764 | 0.019439 | -0.50492 | -0.25414 | 0.54889 | 0.51802 | -0.75566 | 0.40259 | 0.20546 | 0.352 | 0.54756
| 9765 | -0.77218 | -0.46456 | -0.36196 | -0.3297 | 0.029588 | 0.59294 | -0.36668 | 0.18815 | 0.11439 | 0.46362
| 9766 | -0.097171 | -0.38575 | -0.52894 | 0.13727 | 0.38722 | -0.014657 | -0.43653 | -0.85823 | -0.30064 | -0.48629
| 9767 | -0.065281 | 0.42807 | 0.84933 | 0.59147 | -0.4471 | 0.24151 | -0.28887 | 0.52767 | -0.21584 | -0.79
| 9768 | 0.54448 | -0.50472 | 0.055595 | 0.53406 | 0.11847 | -0.22818 | -0.69455 | -0.21584 | -0.90253 | -0.018827
| 9769 | -0.53406 | 0.083867 | -0.30064 | 0.1962 | 0.17253 | -0.21559 | -0.93443 | 0.23234 | -0.51348 | 0.28257
| 9770 | 0.38364 | 0.10184 | -0.61961 | -0.59763 | -0.44909 | -0.038595 | 0.0047613 | -0.18914 | 0.021787 | -0.037867
| 9771 | -0.42615 | 0.80843 | -0.49295 | -0.035272 | -0.41289 | 0.29395 | 0.59098 | 0.25899 | -0.47455 | -0.96127
| 9772 | -0.056337 | 0.23626 | -0.52261 | 0.28775 | -0.18299 | -0.85682 | 0.45456 | 0.69983 | -0.086053 | -0.087038
| 9773 | 0.70251 | 0.6995 | -0.12484 | 0.79727 | 0.082667 | 0.20823 | -0.40108 | -0.036205 | -0.12393 | -0.016486
| 9774 | -0.39148 | -0.11112 | 0.082558 | 0.1153 | -0.80635 | 0.003456 | 0.0033556 | 0.53946 | -0.5015 | 0.48125
| 9775 | -0.2265 | -0.1118 | -0.35062 | 0.5098 | 0.136 | 0.044647 | 0.029691 | -0.10776 | 0.17459 | 0.39049
| 9776 | 0.16436 | 0.23 | -0.49433 | -0.40662 | 0.82536 | 0.49039 | -0.85682 | -0.42703 | -0.51451 | -0.17217
| 9777 | -0.77395 | 0.4755 | -0.55447 | 0.23026 | -0.26007 | 0.13669 | 0.2722 | 0.52219 | -0.63353 | -0.026296
| 9778 | -0.29979 | -0.42285 | 0.047792 | 0.40898 | -0.0058672 | -0.43229 | 0.53085 | -0.41957 | -0.50959 | 0.099056
| 9779 | -0.11439 | -0.1578 | -0.40915 | -0.22792 | -0.41528 | 0.048633 | -0.53556 | 0.48902 | -0.038907 | 0.15804
| 9780 | 0.029485 | 0.07962 | 0.096064 | -0.010707 | 0.48843 | 0.57774 | -0.55762 | -0.10574 | -0.3662 | -0.10832
| 9781 | 0.17157 | -0.13449 | 0.34662 | -0.12805 | -0.3186 | -0.71312 | -0.39362 | -0.094848 | -0.088243 | 0.032064
| 9782 | -0.34739 | 0.16507 | -0.41888 | 0.022708 | -0.77087 | 0.46981 | -0.042033 | 0.75526 | -0.5529 | -0.48532
| 9783 | 0.7512 | 0.11484 | 0.1466 | 0.21177 | -0.71698 | -0.086162 | -0.36683 | -0.0045604 | -0.011516 | 0.0004501
| 9784 | -0.72486 | 0.0065716 | 0.35 | -0.17399 | 0.15851 | 0.3838 | -0.002453 | -0.4194 | 0.15177 | 0.21215
| 9785 | 0.079946 | 0.25093 | 0.074419 | 0.019031 | 0.57538 | 0.59738 | 0.27082 | 0.46624 | 0.29056 | -0.48202
| 9786 | -0.25589 | -0.13138 | 0.044123 | -0.32243 | -0.27578 | 0.11847 | 0.44782 | -0.33826 | 0.06016 | -0.65201
| 9787 | -0.14648 | 0.59049 | -0.3759 | 0.20609 | -0.58976 | 0.50837 | 0.26034 | 0.21254 | 0.43777 | 0.15484
| 9788 | -0.12908 | 0.013542 | -0.082776 | 0.52957 | 0.63737 | -0.3309 | 0.022299 | -0.65086 | 0.80481 | 0.29537
| 9789 | 0.10652 | 0.086928 | -0.59963 | 0.66819 | -0.30394 | 0.30308 | 0.22922 | -0.62119 | -0.72705 | -0.31422
| 9790 | 0.68552 | -0.48726 | -0.64293 | -0.17241 | -0.028661 | 0.11722 | -0.17399 | 0.74407 | 0.58347 | -0.24323
| 9791 | -0.44385 | 0.073447 | 0.48338 | 0.83538 | 0.10966 | -0.53772 | 0.30538 | -0.1786 | 0.74019 | 0.39115
| 9792 | 0.63848 | -0.31334 | 0.30164 | -0.013947 | 0.1546 | -0.46568 | -0.09198 | 0.047057 | -0.026604 | 0.63545
| 9793 | 0.35432 | 0.10094 | 0.23456 | 0.30122 | -0.17326 | -0.21419 | 0.072476 | -0.65 | -0.17314 | -0.43848
| 9794 | -0.38902 | 0.64405 | 0.19806 | -0.53064 | 0.095401 | -0.3551 | 0.73298 | -0.17836 | 0.37638 | 0.6811
| 9795 | -0.6697 | -0.15567 | -0.1879 | -0.22148 | 0.45732 | -0.0071757 | 0.082994 | 0.33 | 0.30826 | -0.32985
| 9796 | -0.13727 | -0.36274 | 0.27785 | -0.2941 | -0.59171 | 0.13046 | 0.26795 | 0.28635 | -0.16376 | -0.34754
| 9797 | -0.2508 | -0.60949 | 0.37976 | -0.23273 | -0.33826 | -0.094848 | -0.56907 | -0.0083852 | -0.40175 | -0.36227
| 9798 | -0.83721 | -0.55514 | 0.12416 | -0.45127 | -0.51657 | -0.46195 | 0.2571 | -0.84801 | 0.045589 | 0.33735
| 9799 | 0.87311 | 0.28705 | -0.54054 | -0.26223 | -0.74841 | 0.26945 | 0.11417 | -0.45365 | 0.093413 | 0.14507
| 9800 | -0.22482 | 0.075176 | 0.19906 | 0.61128 | 0.1153 | 0.64181 | 0.65287 | 0.03465 | 0.53946 | 0.51164
| 9801 | 0.27771 | -0.099722 | 0.60163 | -0.10473 | 0.12679 | 0.010606 | -0.12131 | -0.57538 | 0.38869 | -0.096285
| 9802 | -0.36478 | -0.036828 | -0.76612 | 0.68141 | 0.76315 | 0.14437 | 0.2744 | -0.18263 | -0.62677 | 0.15413
| 9803 | 0.4857 | -0.031961 | -0.31963 | -0.25777 | 0.52303 | -0.6233 | 0.22135 | -0.51266 | 0.14367 | -0.47626
| 9804 | -0.62892 | -0.49751 | 0.2147 | -0.49413 | -0.27785 | 0.13253 | -0.57163 | -0.78622 | -0.13161 | 0.59245
| 9805 | 0.28467 | 0.32911 | -0.09 | -0.32199 | 0.44692 | -0.10764 | -0.45751 | -0.13207 | 0.19124 | -0.35015
| 9806 | -0.64097 | 0.085834 | -0.2216 | 0.0051633 | 0.26918 | -0.17109 | 0.66044 | -0.60163 | -0.41699 | 0.54823
| 9807 | 0.96127 | 0.69422 | 0.59863 | 0.40983 | 0.12006 | 0.31582 | 0.050526 | 0.12954 | 0.45769 | 0.38902
| 9808 | -0.17787 | 0.61594 | -0.48029 | -0.060692 | 0.41477 | -0.16173 | 0.3923 | -0.3366 | -0.4426 | 0.12564
| 9809 | -0.3015 | -0.19931 | -0.016486 | -0.33856 | -0.8148 | 0.11259 | 0.79288 | -0.11383 | -0.69227 | -0.5728
| 9810 | 0.13334 | -0.27343 | -0.071614 | -0.0073772 | 0.46661 | 0.56034 | -0.45255 | 0.88642 | 0.18104 | 0.12006
| 9811 | -0.31934 | -0.73675 | 0.45109 | -0.34662 | -0.12644 | -0.44367 | 0.12165 | 0.64659 | -0.5224 | -0.34372
| 9812 | -0.16376 | -0.40125 | 0.031238 | -0.29993 | 0.038387 | -0.025064 | -0.44601 | 0.22792 | 0.79579 | 0.62838
| 9813 | 0.092862 | -0.11643 | -0.18901 | -0.23941 | 0.20282 | 0.027323 | -0.65 | -0.26699 | -0.056125 | -0.25697
| 9814 | 0.17641 | -0.044228 | -0.47474 | 0.18852 | 0.2621 | -0.65172 | 0.69586 | 0.77932 | -0.14578 | 0.62013
| 9815 | 0.38267 | -0.40831 | -0.22883 | -0.45292 | 0.031961 | 0.09044 | -0.47303 | 0.50351 | -0.22263 | -0.074311
| 9816 | 0.5001 | -0.2313 | -0.55089 | -0.058353 | -0.064853 | 0.6833 | 0.50878 | 0.1005 | -0.73599 | -0.11801
| 9817 | -0.055384 | 0.18753 | 0.36211 | -0.89183 | -0.55537 | 0.66879 | -0.83845 | -0.065388 | 0.77483 | 0.71242
| 9818 | 0.80176 | -0.52703 | -0.55785 | 0.16771 | 0.0021523 | -0.12074 | -0.22392 | 0.90566 | -0.18692 | -0.34647
| 9819 | -0.65663 | -0.013339 | -0.65693 | 0.6631 | -0.1153 | 0.44746 | 0.080381 | 0.13138 | 0.19322 | 0.41802
| 9820 | 0.025269 | 0.70862 | -0.1962 | -0.22909 | 0.087147 | -0.37302 | -0.44638 | 0.79727 | -0.13542 | 0.14624
| 9821 | 0.32643 | -0.44277 | 0.57 | 0.74096 | 0.09099 | -0.12816 | 0.23639 | -0.71592 | -0.51823 | 0.67335
| 9822 | -0.17374 | 0.85682 | -0.056337 | 0.049053 | 0.47626 | -0.17411 | 0.71982 | -0.032477 | 0.019337 | -0.29438
| 9823 | 0.41119 | -0.021685 | 0.25872 | 0.033512 | 0.10184 | 0.36873 | -0.044542 | 0.42528 | 0.23169 | 0.59
| 9824 | -0.25147 | 0.09088 | 0.39049 | -0.15141 | 0.34144 | -0.021072 | -0.027426 | -0.30928 | -0.21025 | -0.0054649
| 9825 | 0.57116 | 0.02281 | 0.23875 | -0.24681 | -0.10373 | 0.2621 | -0.47626 | -0.44764 | 0.0012508 | 0.61672
| 9826 | -0.027118 | 0.62731 | -0.31232 | -0.23195 | 0.68871 | 0.42476 | -0.5017 | 0.046847 | 0.54207 | -0.035376
| 9827 | 0.24059 | -0.078534 | -0.54426 | 0.038283 | 0.18692 | -0.5529 | -0.35945 | -0.21904 | -0.11304 | 0.48029
| 9828 | -0.8755 | 0.25562 | 0.19782 | 0.080381 | -0.0755 | -0.33374 | -0.13704 | -0.27371 | 0.03465 | -0.2052
| 9829 | -0.30337 | 0.59738 | -0.78763 | -0.36055 | 0.059202 | -0.32985 | -0.069892 | 0.0043595 | -0.18104 | 0.34923
| 9830 | -0.26877 | 0.061331 | -0.060479 | -0.45091 | 0.15626 | 0.3214 | 0.25187 | 0.34555 | 0.18287 | -0.43688
| 9831 | -0.1884 | 0.4983 | -0.17338 | -0.075608 | -0.35587 | 0.37751 | -0.18116 | 0.51266 | -0.42389 | 0.55469
| 9832 | 0.65693 | -0.25616 | 0.5922 | 0.083321 | 0.092641 | 0.24376 | -0.0078811 | 0.49453 | 0.053374 | -0.024039
| 9833 | 0.31802 | 0.30308 | 0.35185 | -0.1353 | 0.58227 | 0.25777 | 0.23967 | -0.31392 | 0.70386 | -0.34008
| 9834 | 0.22715 | 0.71487 | -0.16221 | -0.0866 | -0.40662 | 0.025885 | -0.047057 | 0.061331 | 0.83 | 0.31073
| 9835 | -0.95417 | 0.6631 | 0.54845 | 0.50594 | -0.32925 | 0.54845 | -0.1735 | -0.71487 | 0.30754 | -0.23234
| 9836 | 0.41306 | -0.65547 | -0.016994 | 0.17957 | 0.022912 | -0.17495 | -0.3357 | -0.14192 | -0.46158 | -0.13843
| 9837 | -0.3743 | 0.74761 | -0.42895 | 0.23208 | -0.052319 | -0.47894 | -0.24204 | -0.45917 | -0.61987 | -0.50331
| 9838 | 0.14765 | 0.29438 | 0.35278 | -0.17702 | -0.057928 | 0.018012 | -0.5102 | 0.78251 | -0.21 | -0.41733
| 9839 | 0.8882 | -0.009697 | 0.40159 | 0.48707 | 0.54011 | 0.83118 | 0.060372 | 0.5174 | -0.45567 | -0.70453
| 9840 | -0.31993 | 0.40611 | 0.46981 | -0.16856 | 0.80635 | 0.022606 | -0.41665 | -0.068818 | 0.26808 | 0.43831
| 9841 | 0.039323 | -0.35463 | 0.019745 | 0.14578 | 0.17872 | 0.21674 | -0.10295 | -0.73789 | -0.11405 | -0.33389
| 9842 | 0.3951 | -0.18717 | 0.2175 | -0.1729 | 0.4041 | 0.10184 | -0.35883 | 0.3727 | -0.045065 | 0.1196
| 9843 | -0.037867 | -0.35541 | -0.48144 | 0.39726 | 0.20069 | -0.66549 | -0.52324 | -0.035272 | 0.011213 | -0.30928
| 9844 | -0.41119 | 0.034754 | -0.69917 | 0.25549 | 0.088902 | 0.12404 | -0.55245 | 0.0019519 | 0.083976 | -0.2076
| 9845 | -0.38771 | 0.54448 | 0.45273 | 0.81697 | -0.2076 | -0.30667 | 0.34418 | 0.74564 | -0.17702 | -0.21114
| 9846 | 0.5954 | -0.16292 | 0.78669 | 0.46925 | 0.63545 | 0.73675 | 0.28705 | 0.29665 | -0.10139 | -0.35463
| 9847 | 0.47038 | -0.09044 | 0.009697 | 0.12839 | 0.08474 | -0.79776 | 0.41119 | -0.2516 | -0.78023 | 0.095069
| 9848 | 0.52873 | 0.019643 | -0.77751 | -0.81917 | -0.19669 | 0.010808 | 0.83118 | 0.29014 | 0.18901 | -0.27467
| 9849 | 0.5011 | 0.79239 | -0.57444 | -0.6319 | -0.83538 | 0.095954 | 0.36102 | 0.49592 | 0.061118 | -0.25214
| 9850 | -0.28859 | -0.18201 | -0.28104 | -0.11417 | 0.23901 | 0.27799 | 0.42947 | -0.31568 | -0.75979 | -0.66909
| 9851 | 0.079185 | -0.23547 | -0.27041 | -0.7735 | -0.23783 | -0.27274 | 0.46437 | -0.098279 | -0.39659 | -0.5768
| 9852 | 0.43866 | -0.054855 | 0.6338 | -0.061224 | 0.030825 | -0.2161 | -0.10083 | 0.47227 | 0.63054 | 0.088463
| 9853 | 0.17872 | -0.18495 | 0.10798 | 0.12279 | 0.73074 | -0.20106 | 0.013136 | 0.24614 | 0.30265 | -0.10541
| 9854 | -0.51513 | 0.11022 | -0.61803 | -0.094296 | 0.55717 | 0.13843 | -0.00055015 | -0.82196 | -0.28747 | 0.86325
| 9855 | 0.16831 | -0.088243 | -0.047057 | -0.27247 | 0.14076 | 0.45182 | -0.25683 | -0.16388 | 0.65316 | -0.69065
| 9856 | -0.25926 | 0.38089 | -0.21814 | 0.16844 | -0.16077 | -0.31758 | 0.17181 | -0.19769 | 0.10295 | -0.19433
| 9857 | -0.4989 | -0.24548 | 0.46812 | 0.44656 | 0.092311 | 0.46737 | 0.59988 | -0.034443 | -0.15614 | 0.44565
| 9858 | 0.25428 | 0.045275 | -0.042451 | -0.38689 | 0.28146 | -0.18975 | -0.45438 | 0.71 | -0.46121 | -0.18165
| 9859 | 0.22495 | -0.66015 | -0.23234 | 0.27896 | -0.26481 | -0.11847 | 0.18128 | -0.038907 | 0.13681 | 0.67
| 9860 | -0.16759 | -0.28467 | 0.053586 | 0.5102 | -0.0066723 | 0.12633 | -0.51678 | -0.20684 | 0.6371 | 0.12165
| 9861 | 0.31978 | 0.18238 | 0.47645 | -0.095511 | 0.0028541 | 0.20119 | 0.35774 | -0.64209 | -0.10641 | -0.37686
| 9862 | -0.25334 | -0.11507 | 0.026707 | -0.21789 | 0.35154 | -0.52052 | 0.1063 | -0.087366 | 0.3607 | -0.68903
| 9863 | -0.68047 | 0.48648 | -0.067745 | 0.6233 | -0.15958 | -0.15177 | 0.065174 | 0.28007 | -0.077341 | 0.75161
| 9864 | 0.12839 | 0.15448 | 0.82196 | -0.09022 | 0.58275 | -0.80125 | -0.51164 | 0.44728 | 0.032271 | -0.4392
| 9865 | -0.68425 | -0.77262 | 0.028455 | 0.056443 | 0.28271 | -0.19074 | -0.3366 | -0.43564 | 0.020357 | -0.19919
| 9866 | 0.3651 | 0.16066 | 0.030619 | -0.77841 | 0.18055 | -0.041199 | -0.24112 | -0.35262 | 0.19682 | -0.11688
| 9867 | 0.75772 | 0.38624 | 0.80532 | -0.77 | -0.30337 | -0.042973 | 0.075716 | 0.17641 | 0.10809 | -0.06753
| 9868 | 0.067745 | 0.15153 | 0.03465 | 0.25214 | 0.30179 | 0.059628 | -0.4392 | 0.39329 | -0.12519 | 0.13924
| 9869 | -0.58587 | -0.13207 | 0.05253 | 0.66549 | -0.50351 | 0.24363 | 0.007075 | 0.53406 | -0.81807 | 0.072153
| 9870 | -0.079728 | 0.058884 | -0.75938 | -0.14367 | 0.06165 | -0.36731 | -0.39115 | 0.40058 | 0.31131 | 0.25227
| 9871 | 0.08989 | -0.68393 | 0.003155 | 0.35278 | -0.73373 | -0.048843 | -0.77395 | 0.19508 | 0.042451 | 0.74096
| 9872 | 0.23195 | -0.61751 | -0.46549 | -0.20344 | 0.76442 | 0.63875 | -0.19545 | -0.72559 | -0.25374 | 0.23731
| 9873 | 0.030619 | -0.0018517 | 0.11022 | -0.09055 | -0.20684 | 0.44045 | -0.071399 | -0.17653 | 0.21521 | -0.022094
| 9874 | -0.10317 | -0.18299 | 0.77483 | -0.080163 | 0.20949 | -0.20874 | -0.47645 | 0.71487 | -0.49275 | -0.63326
| 9875 | 0.22302 | -0.40932 | -0.037036 | -0.07 | 0.53794 | -0.22469 | 0.76827 | 0.11034 | 0.15709 | 0.68552
| 9876 | 0.015267 | -0.68711 | -0.66133 | 0.026809 | 0.36321 | -0.4408 | 0.4307 | 0.74485 | -0.26386 | -0.16519
| 9877 | -0.37207 | -0.21076 | -0.17508 | -0.53449 | 0.19124 | 0.47019 | -0.3956 | 0.54492 | 0.63163 | 0.37895
| 9878 | 0.06914 | -0.52198 | -0.068388 | 0.41323 | 0.19433 | -0.2343 | 0.62517 | -0.35401 | -0.35216 | 0.009697
| 9879 | -0.92063 | 0.18544 | -0.080924 | 0.22096 | -0.0092932 | 0.5436 | 0.18704 | 0.4736 | 0.70589 | 0.18018
| 9880 | -0.1646 | -0.40309 | 0.29 | 0.1118 | 0.092751 | -0.083212 | -0.36353 | -0.58155 | 0.23378 | 0.7687
| 9881 | -0.11756 | -0.15935 | -0.09176 | -0.15271 | 0.75566 | 0.51886 | 0.29921 | -0.0027538 | -0.20044 | -0.53837
| 9882 | -0.16256 | -0.065816 | 0.6786 | 0.92319 | -0.29722 | 0.10876 | 0.022196 | 0.54602 | 0.31802 | -0.55469
| 9883 | -0.45164 | 0.014454 | -0.048212 | -0.33284 | 0.034547 | -0.92063 | -0.19794 | -0.19173 | -0.5469 | -0.15094
| 9884 | 0.12142 | -0.40008 | -0.0046609 | 0.35649 | -0.26577 | 0.31655 | -0.060905 | -0.16328 | 0.57917 | 0.12131
| 9885 | 0.18766 | 0.037763 | 0.34114 | -0.03714 | 0.49157 | 0.26918 | -0.26156 | 0.52619 | -0.32583 | -0.089121
| 9886 | -0.02568 | 0.64433 | 0.21635 | -0.40259 | 0.14052 | -0.15401 | 0.23417 | -0.076799 | -0.35355 | -0.15106
| 9887 | -0.10944 | 0.23744 | -0.02189 | 0.25187 | 0.30164 | 0.38234 | -0.78344 | 0.39925 | 0.62811 | 0.46456
| 9888 | 0.54646 | 0.81697 | 0.54229 | -0.15354 | 0.30093 | -0.80687 | 0.14601 | 0.16795 | -0.30437 | 0.018725
| 9889 | 0.52157 | -0.095843 | -0.32258 | -0.52576 | -0.40831 | 0.67829 | -0.3864 | 0.034858 | 0.22444 | -0.025577
| 9890 | 0.036724 | 0.070108 | -0.15141 | 0.40729 | -0.60821 | 0.46269 | -0.48551 | 0.36353 | 0.19607 | -0.13785
| 9891 | 0.4898 | -0.31247 | 0.13623 | 0.39181 | -0.24231 | -0.52767 | -0.72889 | -0.0054649 | 0.50837 | -0.3422
| 9892 | 0.57846 | 0.61077 | -0.25683 | -0.05 | -0.25697 | 0.65316 | 0.48785 | 0.52979 | 0.09077 | -0.097503
| 9893 | -0.18336 | -0.5768 | -0.058459 | -0.57515 | -0.068496 | 0.77044 | 0.58951 | -0.42685 | -0.36039 | -0.43299
| 9894 | 0.32022 | -0.14052 | 0.35339 | -0.77932 | 0.51595 | -0.83417 | -0.33781 | -0.01791 | 0.038179 | -0.43211
| 9895 | 0.40578 | 0.31451 | 0.031135 | -0.72523 | 0.22534 | 0.45036 | -0.9272 | 0.40679 | 0.38575 | 0.32776
| 9896 | 0.079402 | -0.3956 | -0.19384 | -0.5447 | 0.26264 | -0.0995 | 0.1221 | -0.56354 | 0.089012 | -0.36557
| 9897 | 0.21904 | -0.48144 | -0.81372 | -0.21623 | 0.59 | 0.13092 | -0.056655 | -0.8821 | 0.58539 | -0.46774
| 9898 | 0.51102 | -0.24641 | 0.61594 | -0.51246 | -0.86546 | -0.18422 | -0.038491 | 0.27744 | -0.18889 | -0.10753
| 9899 | -0.56285 | 0.1229 | 0.089341 | -0.21076 | -0.19136 | -0.3048 | -0.18201 | -0.45824 | 0.14087 | -0.085615
| 9900 | -0.085178 | 0.28341 | 0.062397 | 0.077883 | -0.82536 | -0.038803 | -0.28216 | 0.31145 | -0.33992 | 0.2356
| 9901 | 0.10585 | 0.044647 | -0.1315 | 0.2809 | 0.29523 | 0.54273 | 0.18975 | -0.21725 | -0.087695 | -0.43955
| 9902 | -0.67 | 0.24323 | 0.43635 | -0.22418 | 0.06496 | 0.68968 | -0.61051 | -0.014556 | -0.027837 | 0.81534
| 9903 | -0.42424 | -0.87876 | 0.17763 | -0.056655 | -0.3735 | -0.32628 | 0.45511 | 0.40729 | 0.82028 | -0.66519
| 9904 | 0.14742 | 0.11034 | -0.17665 | -0.88042 | -0.66459 | -0.68016 | -0.070538 | -0.36368 | -0.4991 | 0.046742
| 9905 | -0.13011 | -0.12382 | -0.013035 | 0.4232 | 0.22547 | 0.25388 | -0.70386 | 0.85682 | 0.37159 | 0.29864
| 9906 | 0.1389 | 0.28958 | 0.19111 | 0.09165 | -0.69227 | 0.8422 | -0.036205 | 0.33329 | 0.57163 | -0.33917
| 9907 | -0.41102 | 0.00085036 | -0.24548 | -0.20094 | -0.33871 | 0.10351 | -0.3242 | 0.097282 | -0.65489 | 0.4989
| 9908 | 0.0032553 | 0.094517 | -0.063037 | 0.29141 | 0.012326 | 0.51307 | 0.0086877 | -0.34327 | -0.33314 | 0.64744
| 9909 | -0.21368 | 0.43724 | 0.083758 | 0.17823 | -0.3743 | -0.082558 | 0.76612 | -0.041303 | 0.52873 | 0.47151
| 9910 | 0.19694 | 0.47741 | -0.25334 | -0.078642 | -0.35852 | 0.16221 | -0.29381 | -0.31787 | -0.3951 | 0.20533
| 9911 | -0.28383 | -0.53621 | -0.74643 | 0.16268 | -0.50796 | 0.06496 | -0.0090913 | -0.37751 | 0.022912 | -0.11079
| 9912 | 0.55312 | -0.54492 | -0.27854 | 0.08136 | -0.26468 | 0.46306 | -0.51844 | -0.11711 | 0.5768 | 0.30538
| 9913 | 0.26386 | 0.7839 | 0.056125 | 0.02281 | -0.39643 | -0.23456 | 0.069033 | 0.064425 | 0.74251 | 0.029485
| 9914 | -0.20899 | 0.095622 | -0.19247 | -0.074203 | -0.2484 | 0.3312 | 0.25858 | 0.010606 | -0.28565 | -0.47588
| 9915 | -0.40159 | -0.18778 | -0.51348 | 0.78576 | -0.63299 | -0.019643 | 0.13843 | -0.75566 | 0.95204 | 0.15283
| 9916 | -0.0030547 | -0.17024 | -0.053797 | 0.064318 | -0.87793 | 0.00085036 | 0.29608 | -0.78483 | -0.65605 | 0.61231
| 9917 | 0.4279 | -0.11034 | -0.31174 | 0.084959 | 0.074959 | -0.32672 | 0.69032 | 0.78669 | -0.0027538 | -0.061864
| 9918 | 0.09011 | -0.20722 | -0.52513 | 0.084194 | 0.23104 | 0.038179 | -0.32509 | 0.61154 | 0.033615 | 0.69324
| 9919 | 0.69097 | 0.53385 | 0.51678 | -0.36368 | -0.72632 | 0.65927 | -0.14706 | 0.9078 | -0.19719 | -0.25174
| 9920 | -0.065388 | -0.78206 | -0.32791 | -0.51348 | -0.53664 | -0.088024 | 0.49256 | -0.48493 | -0.82941 | -0.64042
| 9921 | -0.088243 | 0.84031 | -0.072584 | -0.27578 | 0.20495 | -0.56583 | 0.067208 | 0.37111 | 0.2733 | 0.33434
| 9922 | 0.45438 | -0.21013 | 0.034754 | -0.044228 | 0.36589 | 0.87311 | -0.17253 | 0.6852 | -0.56791 | 0.94804
| 9923 | 0.052108 | 0.6637 | -0.0028541 | 0.22896 | -0.13288 | 0.53064 | 0.70184 | -0.028043 | -0.50251 | 0.0013509
| 9924 | -0.46418 | -0.40276 | -0.16412 | -0.17447 | 0.1735 | 0.24508 | -0.078968 | 0.5469 | 0.23208 | -0.39593
| 9925 | -0.23312 | -0.12702 | -0.35108 | 0.40932 | -0.28972 | 0.38526 | 0.093965 | -0.46251 | 0.1221 | -0.33645
| 9926 | 0.62758 | 0.60617 | 0.12576 | 0.39809 | 0.78114 | 0.39329 | -0.7184 | -0.14671 | -0.17556 | -0.36873
| 9927 | -0.86325 | -0.71382 | 0.61103 | -0.75979 | -0.47741 | -0.37478 | 0.62731 | 0.39164 | -0.013744 | 0.0755
| 9928 | -0.81159 | -0.68235 | -0.78952 | -0.093744 | -0.1308 | 0.84094 | -0.29509 | -0.77572 | -0.45237 | 0.74251
| 9929 | -0.075176 | 0.45146 | -0.54889 | -0.33105 | -0.49216 | 0.14613 | 0.57703 | 0.53513 | -0.17945 | -0.14472
| 9930 | -0.46906 | 0.13948 | -0.11665 | -0.52198 | 0.19545 | 0.20874 | 0.7005 | -0.29622 | -0.2133 | -0.97354
| 9931 | 0.27385 | -0.42389 | -0.073231 | 0.57656 | -0.12793 | 0.57468 | 0.014454 | 0.62357 | -0.24628 | 0.080598
| 9932 | -0.75485 | 0.36826 | -0.16976 | -0.20772 | 0.015876 | -0.44638 | 0.24336 | -0.64971 | 0.11462 | -0.018725
| 9933 | -0.49315 | -0.34008 | 0.24455 | -0.19483 | -0.72414 | -0.077558 | 0.55 | 0.012528 | 0.71035 | -0.28635
| 9934 | 0.29296 | -0.67121 | 0.076582 | -0.73 | 0.43317 | -0.6349 | -0.18643 | 0.1245 | -0.36211 | 0.46418
| 9935 | 0.029691 | -0.43866 | -0.0089904 | 0.52492 | 0.34724 | 0.8467 | -0.087038 | 0.12461 | -0.37831 | 0.4206
| 9936 | -0.23849 | -0.35712 | 0.38478 | 0.4337 | -0.17763 | -0.070861 | 0.032167 | 0.68711 | -0.24681 | 0.3767
| 9937 | -0.37944 | 0.025577 | 0.25027 | 0.24455 | -0.086053 | 0.65431 | 0.18189 | 0.63271 | 0.55853 | 0.21304
| 9938 | -0.082558 | 0.46381 | 0.18618 | -0.2119 | 0.54426 | 0.13785 | 0.0911 | -0.085178 | -0.028043 | -0.035272
| 9939 | 0.53924 | -0.69619 | 0.32583 | 0.20119 | -0.52052 | 0.28621 | -0.30783 | -0.22302 | 0.34448 | -0.22405
| 9940 | -0.63903 | 0.14531 | -0.29993 | 0.55627 | -0.59614 | -0.14029 | -0.22754 | -0.60795 | 0.33404 | 0.25576
| 9941 | 0.32096 | 0.2924 | 0.016689 | 0.17677 | -0.20899 | -0.8618 | -0.26427 | -0.097171 | -0.66549 | -0.044961
| 9942 | 0.32687 | -0.22276 | 0.7508 | -0.23954 | -0.14788 | 0.063891 | -0.0071757 | 0.6338 | -0.019235 | 0.14285
| 9943 | -0.44045 | -0.90356 | -0.46755 | -0.21866 | -0.66578 | -0.12541 | 0.46906 | -0.26101 | -0.32007 | -0.19247
| 9944 | 0.081469 | 0.1375 | -0.33224 | -0.33947 | -0.19782 | 0.11994 | -0.064532 | 0.41596 | 0.3312 | 0.71347
| 9945 | -0.08485 | 0.14041 | 0.11225 | -0.68016 | 0.27647 | 0.11326 | 0.49592 | 0.71104 | -0.3851 | -0.12085
| 9946 | -0.93144 | 0.15141 | -0.52345 | 0.14695 | -0.55807 | -0.15673 | -0.19682 | -0.63682 | 0.09 | -0.79875
| 9947 | 0.12439 | -0.050316 | -0.18778 | -0.32821 | -0.75607 | 0.22071 | -0.10585 | -0.073447 | -0.38689 | -0.22663
| 9948 | -0.60163 | -0.67922 | -0.69751 | -0.16759 | 0.88295 | 0.6811 | -0.11326 | -0.2265 | -0.10731 | -0.00095045
| 9949 | -0.14531 | -0.49552 | 0.16976 | -0.049684 | 0.13426 | -0.17641 | -0.50857 | -0.30394 | 0.27785 | -0.34357
| 9950 | -0.37048 | -0.11631 | -0.38348 | 0.43724 | -0.068281 | 0.61908 | 0.30754 | -0.15709 | 0.20975 | -0.18079
| 9951 | -0.44439 | -0.074419 | 0.031961 | -0.052846 | -0.077449 | 0.20861 | -0.55807 | -0.3851 | -0.1735 | -0.21482
| 9952 | 0.41974 | 0.15923 | 0.15165 | 0.84605 | -0.21203 | 0.36604 | -0.43123 | -0.6833 | 0.010505 | 0.48493
| 9953 | -0.42459 | -0.31963 | 0.29736 | -0.5245 | 0.079077 | -0.34311 | -0.50959 | 0.60213 | -0.10485 | -0.11473
| 9954 | -0.4426 | -0.080707 | -0.52576 | 0.095954 | 0.76484 | 0.4995 | -0.56954 | -0.42737 | -0.24033 | 0.58203
| 9955 | 0.34632 | 0.44403 | -0.18299 | -0.1957 | -0.41494 | -0.44764 | -0.074743 | -0.81106 | -0.41494 | -0.10006
| 9956 | 0.64715 | 0.053269 | -0.074959 | 0.54734 | -0.13265 | -0.71104 | -0.082449 | -0.80277 | 0.4857 | -0.22586
| 9957 | 0.12382 | -0.54514 | -0.55921 | 0.074851 | 0.25321 | -0.32821 | 0.17459 | 0.61438 | 0.079728 | 0.066565
| 9958 | -0.49612 | -0.3363 | -0.69162 | -0.17374 | 0.22058 | 0.14718 | 0.068603 | 0.4307 | -0.51123 | 0.80328
| 9959 | 0.094627 | 0.23849 | 0.19049 | 0.17314 | -0.67304 | 0.59515 | -0.12851 | 0.73599 | -0.77572 | 0.098279
| 9960 | -0.6755 | 0.69357 | -0.75855 | -0.55134 | 0.1269 | -0.79 | -0.1863 | -0.42528 | 0.20962 | -0.53643
| 9961 | -0.039948 | -0.26142 | 0.64321 | 0.20181 | -0.22482 | 0.24893 | -0.097947 | 0.0014511 | 0.47933 | 0.19284
| 9962 | -0.40292 | 0.1578 | 0.23299 | -0.548 | 0.19086 | 0.15224 | 0.2431 | -0.44421 | 0.10184 | 0.68047
| 9963 | -0.50251 | -0.23941 | -0.29879 | 0.50796 | -0.11756 | 0.045589 | -0.049263 | -0.059947 | 0.4272 | -0.029176
| 9964 | -0.43334 | -0.44206 | -0.34586 | -0.29282 | -0.66044 | 0.022094 | -0.28691 | 0.078425 | -0.52177 | 0.50492
| 9965 | 0.2784 | 0.16795 | -0.018929 | -0.18385 | 0.80277 | 0.19148 | 0.63903 | -0.73149 | 0.11858 | 0.14531
| 9966 | -0.33705 | 0.46437 | -0.19111 | -0.31772 | 0.31247 | -0.33389 | -0.072692 | 0.45219 | -0.31436 | 0.096728
| 9967 | 0.65402 | 0.27509 | 0.44656 | 0.93443 | 0.20106 | 0.2216 | -0.32332 | -0.43352 | -0.31509 | 0.072045
| 9968 | -0.74407 | -0.65086 | -0.16555 | -0.3375 | 0.60465 | 0.6241 | 0.29367 | -0.10295 | -0.07962 | 0.015774
| 9969 | 0.38186 | 0.14379 | -0.15365 | 0.011011 | 0.010404 | -0.56445 | -0.23378 | 0.44439 | -0.32762 | -0.46269
| 9970 | 0.20432 | -0.64433 | -0.18544 | 0.051369 | -0.1694 | 0.9089 | 0.35293 | 0.016181 | 0.19881 | -0.084631
| 9971 | 0.18643 | 0.1466 | -0.18606 | 0.46549 | -0.27744 | 0.5735 | 0.0071757 | -0.18177 | -0.12017 | -0.30942
| 9972 | -0.21802 | 0.093523 | -0.6338 | -0.33389 | -0.45548 | -0.51307 | -0.61856 | -0.036102 | -0.054008 | 0.72632
| 9973 | -0.11124 | 0.0038574 | -0.056125 | -0.54933 | 0.50533 | 0.42563 | -0.10764 | 0.018725 | 0.11677 | -0.54076
| 9974 | 0.087914 | 0.39742 | 0.12165 | 0.1634 | 0.64461 | 0.37574 | -0.37542 | 0.13588 | 0.2621 | -0.75322
| 9975 | -0.56308 | -0.049053 | -0.18287 | -0.26427 | 0.032064 | 0.31699 | 0.44367 | 0.14765 | 0.59294 | 0.046008
| 9976 | -0.91225 | -0.38755 | 0.0019519 | -0.14017 | -0.71312 | 0.14367 | 0.16783 | 0.46661 | -0.20207 | -0.41255
| 9977 | 0.53449 | -0.01486 | -0.49731 | -0.74485 | -0.41562 | 0.073231 | -0.65489 | 0.012326 | -0.45585 | 0.013846
| 9978 | 0.0039578 | -0.15507 | 0.11722 | 0.09121 | -0.25764 | 0.07962 | 0.43938 | 0.22741 | -0.70117 | -0.45935
| 9979 | -0.3372 | 0.058034 | 0.20772 | -0.075068 | 0.1688 | -0.85613 | -0.30538 | -0.42755 | -0.055913 | 0.020561
| 9980 | -0.18988 | 0.32199 | -0.22096 | -0.0022525 | -0.36117 | 0.054431 | -0.43777 | 0.20609 | -0.64602 | 0.36494
| 9981 | 0.30971 | 0.33886 | -0.089121 | -0.27192 | -0.052846 | -0.77796 | 0.027118 | -0.64405 | -0.11892 | 0.35062
| 9982 | -0.33841 | 0.55694 | -0.031444 | 0.35185 | -0.10072 | -0.14285 | 0.4417 | -0.21994 | 0.53794 | 0.63792
| 9983 | 0.40443 | 0.010808 | 0.1315 | 0.48648 | 0.30036 | 0.19124 | 0.3309 | 0.39676 | -0.016079 | -0.22961
| 9984 | -0.42703 | -0.15555 | 0.14765 | -0.062823 | -0.038699 | 0.69032 | -0.74096 | 0.70487 | 0.4553 | -0.029382
| 9985 | 0.36921 | 0.57822 | -0.3961 | -0.71557 | -0.32346 | -0.71138 | -0.5447 | -0.76146 | 0.41136 | -0.077124
| 9986 | 0.4997 | -0.30293 | 0.58587 | 0.097282 | -0.17229 | -0.23273 | 0.2508 | 0.45751 | -0.31203 | 0.34083
| 9987 | -0.55514 | -0.52894 | 0.46251 | -0.014556 | -0.90356 | 0.3477 | 0.36133 | 0.032994 | -0.12074 | 0.36857
| 9988 | -0.37911 | 0.17605 | 0.20621 | 0.27702 | -0.5806 | 0.27041 | 0.012934 | 0.49651 | 0.37622 | 0.10876
| 9989 | -0.26699 | 0.51761 | -0.020255 | 0.36196 | -0.060905 | 0.20621 | 0.26237 | 0.15816 | -0.48493 | 0.12644
| 9990 | -0.47436 | 0.26549 | -0.13785 | -0.14064 | 0.024756 | -0.40511 | 0.027632 | 0.42285 | 0.26047 | 0.55357
| 9991 | 0.55223 | 0.23299 | -0.63 | 0.91456 | -0.29694 | -0.4985 | 0.0014511 | 0.52936 | -0.20722 | 0.75855
| 9992 | 0.59763 | 0.21712 | 0.82028 | 0.65143 | -0.6811 | 0.066458 | 0.13299 | -0.44063 | -0.30236 | -0.65229
| 9993 | 0.13403 | 0.28299 | 0.62039 | 0.056655 | 0.25227 | 0.20031 | 0.18778 | -0.47113 | -0.44927 | -0.68172
| 9994 | -0.81588 | 0.2193 | 0.041825 | -0.3422 | 0.35448 | 0.2476 | 0.67519 | 0.3061 | -0.01263 | -0.23351
| 9995 | 0.18532 | 0.18988 | 0.17787 | -0.72669 | -0.21165 | 0.15354 | -0.28425 | -0.59171 | 0.13588 | -0.1269
| 9996 | -0.0053644 | -0.051897 | 0.86036 | -0.3727 | 0.27151 | 0.072692 | 0.71487 | 0.037659 | -0.50675 | 0.10697
| 9997 | 0.01415 | 0.0042591 | 0.65663 | 0.47265 | 0.12553 | 0.48318 | -0.4755 | 0.45055 | 0.6249 | 0.7245
| 9998 | 0.31029 | -0.1025 | 0.39908 | 0.54624 | -0.45036 | -0.73827 | 0.21228 | -0.71698 | 0.29014 | -0.70217
| 9999 | -0.2504 | -0.32096 | -0.71 | 0.26183 | -0.15212 | -0.15887 | 0.05496 | -0.62543 | -0.25549 | -0.59738
| 10000 | -0.063037 | -0.46925 | -0.26932 | -0.42563 | 0.30971 | 0.80125 | 0.43688 | 0.26345 | -0.24059 | -0.37558
| Average | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## PMTable (hidden)
10001 | Trial Number
| Index | Completion
| Values | 6
| 1 | 7.8884
| 2 | 6.7936
| 3 | 8.0489
| 4 | 7.9466
| 5 | 6.4511
| 6 | 6.9166
| 7 | 7.8231
| 8 | 7.3359
| 9 | 8.2732
| 10 | 7.7598
| 11 | 8.9005
| 12 | 7.2168
| 13 | 6.9536
| 14 | 8.0594
| 15 | 8.5116
| 16 | 8.1945
| 17 | 7.2748
| 18 | 8.1085
| 19 | 7.4038
| 20 | 7.9254
| 21 | 8.2001
| 22 | 8.6031
| 23 | 8.2794
| 24 | 8.7437
| 25 | 8.1627
| 26 | 7.5824
| 27 | 8.91
| 28 | 7.7569
| 29 | 7.2916
| 30 | 8.4813
| 31 | 8.4726
| 32 | 7.0723
| 33 | 7.4872
| 34 | 7.4151
| 35 | 8.1436
| 36 | 7.0835
| 37 | 8.3352
| 38 | 7.0741
| 39 | 8.2229
| 40 | 7.7163
| 41 | 7.1524
| 42 | 7.4571
| 43 | 7.5154
| 44 | 7.9534
| 45 | 7.9902
| 46 | 8.1768
| 47 | 8.4935
| 48 | 8.2682
| 49 | 7.9673
| 50 | 7.2382
| 51 | 7.7569
| 52 | 7.4536
| 53 | 7.7017
| 54 | 7.9246
| 55 | 7.5105
| 56 | 7.6906
| 57 | 7.8557
| 58 | 7.5572
| 59 | 8.6727
| 60 | 8.1956
| 61 | 7.6654
| 62 | 7.6348
| 63 | 7.65
| 64 | 8.2719
| 65 | 8.8175
| 66 | 7.4089
| 67 | 8.0758
| 68 | 7.7693
| 69 | 8.292
| 70 | 8.0671
| 71 | 7.3925
| 72 | 8.8763
| 73 | 8.6463
| 74 | 8.617
| 75 | 8.6783
| 76 | 7.4038
| 77 | 7.6009
| 78 | 7.442
| 79 | 8.2806
| 80 | 8.033
| 81 | 7.3742
| 82 | 8.0127
| 83 | 8.6265
| 84 | 8.216
| 85 | 7.8941
| 86 | 8.2381
| 87 | 8.5043
| 88 | 7.7803
| 89 | 7.8439
| 90 | 8.6489
| 91 | 7.2422
| 92 | 8.1867
| 93 | 8.4709
| 94 | 6.5245
| 95 | 7.3408
| 96 | 7.7685
| 97 | 8.2171
| 98 | 8.6897
| 99 | 8.0423
| 100 | 7.9398
| 101 | 8.3245
| 102 | 8.1106
| 103 | 7.4197
| 104 | 8.4068
| 105 | 8.4865
| 106 | 7.7447
| 107 | 7.8644
| 108 | 8.5986
| 109 | 7.9947
| 110 | 7.3566
| 111 | 7.5773
| 112 | 8.1605
| 113 | 7.0602
| 114 | 7.231
| 115 | 7.8884
| 116 | 7.8731
| 117 | 7.3831
| 118 | 7.0854
| 119 | 8.231
| 120 | 7.9372
| 121 | 7.6975
| 122 | 7.7205
| 123 | 7.9804
| 124 | 7.7065
| 125 | 7.3085
| 126 | 8.7107
| 127 | 7.5009
| 128 | 6.6445
| 129 | 8.4493
| 130 | 7.0202
| 131 | 7.3353
| 132 | 7.1205
| 133 | 8.0489
| 134 | 8.6123
| 135 | 8.1823
| 136 | 8.97
| 137 | 8.6009
| 138 | 7.3714
| 139 | 8.0585
| 140 | 6.6349
| 141 | 7.7788
| 142 | 7.546
| 143 | 8.1573
| 144 | 7.4299
| 145 | 7.4724
| 146 | 7.4671
| 147 | 7.3747
| 148 | 6.9405
| 149 | 7.8155
| 150 | 7.9543
| 151 | 7.729
| 152 | 7.8541
| 153 | 6.9413
| 154 | 7.5111
| 155 | 7.7361
| 156 | 7.8916
| 157 | 8.0866
| 158 | 8.6217
| 159 | 8.5098
| 160 | 8.4971
| 161 | 7.3792
| 162 | 7.362
| 163 | 8.6727
| 164 | 8.0433
| 165 | 7.7233
| 166 | 8.224
| 167 | 7.599
| 168 | 8.5768
| 169 | 6.8981
| 170 | 7.6341
| 171 | 8.3285
| 172 | 8.0118
| 173 | 7.984
| 174 | 7.6947
| 175 | 7.5136
| 176 | 8.4692
| 177 | 8.5811
| 178 | 8.1967
| 179 | 7.8819
| 180 | 7.7951
| 181 | 8.1531
| 182 | 7.6824
| 183 | 6.1321
| 184 | 8.2476
| 185 | 7.7447
| 186 | 7.0166
| 187 | 8.2137
| 188 | 7.1705
| 189 | 7.9866
| 190 | 8.2984
| 191 | 8.4542
| 192 | 8.2275
| 193 | 7.4311
| 194 | 8.3517
| 195 | 7.7959
| 196 | 7.4688
| 197 | 7.6394
| 198 | 8.4659
| 199 | 7.5553
| 200 | 8.6388
| 201 | 8.4396
| 202 | 7.1465
| 203 | 7.2884
| 204 | 7.6447
| 205 | 7.2984
| 206 | 8.2945
| 207 | 7.7325
| 208 | 8.7735
| 209 | 7.8868
| 210 | 7.7959
| 211 | 6.4852
| 212 | 8.1156
| 213 | 8.8838
| 214 | 8.0896
| 215 | 8.6673
| 216 | 8.4332
| 217 | 8.6646
| 218 | 8.552
| 219 | 7.9088
| 220 | 8.4253
| 221 | 8.4726
| 222 | 8.0064
| 223 | 8.0358
| 224 | 8.2299
| 225 | 8.25
| 226 | 7.2387
| 227 | 7.486
| 228 | 7.1963
| 229 | 7.9238
| 230 | 7.6735
| 231 | 7.4967
| 232 | 8.0461
| 233 | 7.3043
| 234 | 7.7149
| 235 | 8.7775
| 236 | 8.7076
| 237 | 8.1075
| 238 | 8.179
| 239 | 7.3037
| 240 | 7.5374
| 241 | 8.5421
| 242 | 7.0321
| 243 | 8.19
| 244 | 7.5729
| 245 | 8.1584
| 246 | 7.6553
| 247 | 7.3337
| 248 | 7.71
| 249 | 7.597
| 250 | 7.41
| 251 | 8.1331
| 252 | 8.6868
| 253 | 7.7759
| 254 | 7.5697
| 255 | 8.0768
| 256 | 8.3859
| 257 | 7.0505
| 258 | 8.1373
| 259 | 8.9005
| 260 | 7.1958
| 261 | 8.1457
| 262 | 8.4316
| 263 | 8.2572
| 264 | 8.1035
| 265 | 7.7656
| 266 | 7.7086
| 267 | 8.0945
| 268 | 8.1383
| 269 | 8.4795
| 270 | 8.3587
| 271 | 7.6407
| 272 | 7.3566
| 273 | 7.8185
| 274 | 7.7311
| 275 | 7.2239
| 276 | 8.0965
| 277 | 7.4872
| 278 | 7.9129
| 279 | 8.6193
| 280 | 7.8223
| 281 | 8.1478
| 282 | 7.7598
| 283 | 8.2488
| 284 | 7.3353
| 285 | 8.0442
| 286 | 7.8892
| 287 | 8.9005
| 288 | 7.8424
| 289 | 8.0499
| 290 | 7.7862
| 291 | 6.719
| 292 | 8.3299
| 293 | 8.0284
| 294 | 8.6619
| 295 | 7.6975
| 296 | 8.9005
| 297 | 8.0652
| 298 | 8.2819
| 299 | 7.5202
| 300 | 7.9974
| 301 | 7.3914
| 302 | 7.6892
| 303 | 7.1651
| 304 | 8.483
| 305 | 7.4554
| 306 | 7.8079
| 307 | 7.9517
| 308 | 8.1248
| 309 | 8.8127
| 310 | 7.9389
| 311 | 8.0965
| 312 | 7.5503
| 313 | 8.2001
| 314 | 7.3289
| 315 | 8.3312
| 316 | 8.0749
| 317 | 8.1834
| 318 | 7.367
| 319 | 8.5684
| 320 | 7.5491
| 321 | 8.6054
| 322 | 7.7788
| 323 | 8.2932
| 324 | 7.9956
| 325 | 7.8346
| 326 | 7.6145
| 327 | 7.2525
| 328 | 8.4364
| 329 | 8.3933
| 330 | 8.8692
| 331 | 7.7832
| 332 | 7.6729
| 333 | 8.556
| 334 | 7.8636
| 335 | 8.1362
| 336 | 7.2402
| 337 | 8.0037
| 338 | 7.0062
| 339 | 7.6295
| 340 | 7.2879
| 341 | 8.2971
| 342 | 8.7015
| 343 | 8.6868
| 344 | 8.5942
| 345 | 6.9365
| 346 | 7.7511
| 347 | 6.7628
| 348 | 8.8441
| 349 | 7.2916
| 350 | 7.1431
| 351 | 7.1903
| 352 | 8.8127
| 353 | 8.1096
| 354 | 7.4507
| 355 | 7.8354
| 356 | 6.4275
| 357 | 7.7219
| 358 | 8.3462
| 359 | 7.4403
| 360 | 7.9902
| 361 | 7.7354
| 362 | 8.3325
| 363 | 7.4973
| 364 | 8.6077
| 365 | 7.5628
| 366 | 7.2053
| 367 | 8.4396
| 368 | 8.2744
| 369 | 7.9752
| 370 | 7.1451
| 371 | 7.7877
| 372 | 8.416
| 373 | 8.2334
| 374 | 7.2453
| 375 | 7.9171
| 376 | 7.4345
| 377 | 7.8541
| 378 | 8.6193
| 379 | 8.1834
| 380 | 7.6086
| 381 | 7.7198
| 382 | 7.3825
| 383 | 8.3475
| 384 | 7.3577
| 385 | 7.2325
| 386 | 8.1015
| 387 | 7.7247
| 388 | 7.0925
| 389 | 7.3758
| 390 | 8.0091
| 391 | 7.8683
| 392 | 8.4114
| 393 | 8.3903
| 394 | 8.2794
| 395 | 7.7634
| 396 | 8.9005
| 397 | 6.6939
| 398 | 7.6295
| 399 | 8.483
| 400 | 6.5878
| 401 | 7.9577
| 402 | 8.3366
| 403 | 7.5233
| 404 | 7.8827
| 405 | 7.1441
| 406 | 7.1631
| 407 | 8.2464
| 408 | 8.7472
| 409 | 8.2756
| 410 | 7.7276
| 411 | 7.7869
| 412 | 6.8704
| 413 | 7.7649
| 414 | 7.0312
| 415 | 8.6054
| 416 | 7.7332
| 417 | 7.7966
| 418 | 8.483
| 419 | 7.0826
| 420 | 7.2974
| 421 | 7.9743
| 422 | 7.9204
| 423 | 7.5318
| 424 | 8.5266
| 425 | 6.7774
| 426 | 7.5609
| 427 | 7.903
| 428 | 8.131
| 429 | 8.7657
| 430 | 7.6968
| 431 | 8.4918
| 432 | 7.9063
| 433 | 7.3993
| 434 | 8.416
| 435 | 7.7156
| 436 | 7.4043
| 437 | 8.4778
| 438 | 7.5368
| 439 | 7.6367
| 440 | 8.1238
| 441 | 7.1095
| 442 | 7.2003
| 443 | 8.1106
| 444 | 8.0836
| 445 | 7.5063
| 446 | 7.4299
| 447 | 7.7339
| 448 | 8.0256
| 449 | 8.1956
| 450 | 7.231
| 451 | 6.7345
| 452 | 6.7333
| 453 | 8.6413
| 454 | 7.8667
| 455 | 7.784
| 456 | 6.7985
| 457 | 7.3814
| 458 | 7.7184
| 459 | 7.5703
| 460 | 6.4695
| 461 | 8.2572
| 462 | 7.3842
| 463 | 8.49
| 464 | 8.556
| 465 | 6.7064
| 466 | 8.6926
| 467 | 7.7396
| 468 | 8.0758
| 469 | 8.5098
| 470 | 8.2597
| 471 | 8.2971
| 472 | 8.3218
| 473 | 7.9552
| 474 | 8.292
| 475 | 8.1595
| 476 | 8.0499
| 477 | 8.4526
| 478 | 7.0435
| 479 | 8.0055
| 480 | 7.3391
| 481 | 6.9931
| 482 | 8.5172
| 483 | 8.0091
| 484 | 8.4332
| 485 | 6.6729
| 486 | 8.7657
| 487 | 8.3139
| 488 | 8.3393
| 489 | 7.7605
| 490 | 8.2416
| 491 | 7.5996
| 492 | 7.8612
| 493 | 7.299
| 494 | 8.0423
| 495 | 7.4357
| 496 | 8.6985
| 497 | 7.538
| 498 | 8.1659
| 499 | 6.9409
| 500 | 8.0471
| 501 | 8.6217
| 502 | 8.0265
| 503 | 7.9271
| 504 | 6.7452
| 505 | 7.5906
| 506 | 8.4129
| 507 | 7.9621
| 508 | 8.3686
| 509 | 8.416
| 510 | 7.2634
| 511 | 8.3232
| 512 | 7.1316
| 513 | 8.3035
| 514 | 6.5053
| 515 | 8.1911
| 516 | 7.0723
| 517 | 8.6193
| 518 | 7.5312
| 519 | 7.9406
| 520 | 7.3892
| 521 | 7.5081
| 522 | 7.944
| 523 | 7.2428
| 524 | 8.1801
| 525 | 8.0537
| 526 | 7.956
| 527 | 8.4098
| 528 | 7.6507
| 529 | 8.7015
| 530 | 7.9769
| 531 | 7.2422
| 532 | 7.3626
| 533 | 7.8549
| 534 | 7.3085
| 535 | 7.89
| 536 | 8.8277
| 537 | 7.2239
| 538 | 7.018
| 539 | 7.6695
| 540 | 8.1823
| 541 | 7.8178
| 542 | 8.4592
| 543 | 7.9543
| 544 | 8.6755
| 545 | 7.8494
| 546 | 8.1279
| 547 | 7.847
| 548 | 7.4151
| 549 | 7.8416
| 550 | 8.7234
| 551 | 8.3743
| 552 | 7.4653
| 553 | 7.8819
| 554 | 8.0945
| 555 | 8.0349
| 556 | 8.6514
| 557 | 8.0585
| 558 | 7.814
| 559 | 7.8787
| 560 | 8.55
| 561 | 7.1124
| 562 | 6.8785
| 563 | 8.6985
| 564 | 7.6236
| 565 | 8.4625
| 566 | 7.2722
| 567 | 7.8393
| 568 | 7.64
| 569 | 8.3671
| 570 | 7.8604
| 571 | 8.2882
| 572 | 7.387
| 573 | 7.644
| 574 | 8.3312
| 575 | 7.6831
| 576 | 8.267
| 577 | 8.8384
| 578 | 8.1218
| 579 | 6.9887
| 580 | 7.5843
| 581 | 8.1856
| 582 | 8.3874
| 583 | 7.5124
| 584 | 8.4692
| 585 | 7.5817
| 586 | 8.7858
| 587 | 7.6015
| 588 | 7.9965
| 589 | 7.7191
| 590 | 7.3219
| 591 | 7.5003
| 592 | 8.5726
| 593 | 7.6831
| 594 | 7.8079
| 595 | 7.7547
| 596 | 8.7076
| 597 | 8.8625
| 598 | 8.544
| 599 | 7.9629
| 600 | 7.2753
| 601 | 8.4989
| 602 | 7.6041
| 603 | 8.1911
| 604 | 8.0395
| 605 | 7.8739
| 606 | 7.8811
| 607 | 7.9787
| 608 | 7.5227
| 609 | 8.1911
| 610 | 7.9822
| 611 | 6.6281
| 612 | 8.1563
| 613 | 6.8955
| 614 | 6.5325
| 615 | 7.5767
| 616 | 8.5135
| 617 | 8.6438
| 618 | 7.7072
| 619 | 7.6125
| 620 | 8.0019
| 621 | 8.3615
| 622 | 8.3232
| 623 | 8.3815
| 624 | 7.3337
| 625 | 8.3434
| 626 | 7.8246
| 627 | 8.5343
| 628 | 6.8603
| 629 | 7.71
| 630 | 6.4913
| 631 | 7.5202
| 632 | 7.5392
| 633 | 8.2958
| 634 | 8.4237
| 635 | 8.0729
| 636 | 8.4813
| 637 | 7.8178
| 638 | 8.7107
| 639 | 6.937
| 640 | 8.4778
| 641 | 7.9787
| 642 | 7.9022
| 643 | 7.1636
| 644 | 6.9348
| 645 | 8.3559
| 646 | 8.7988
| 647 | 7.9796
| 648 | 7.8771
| 649 | 8.2023
| 650 | 7.6587
| 651 | 7.1119
| 652 | 7.5178
| 653 | 7.6407
| 654 | 7.4168
| 655 | 7.5202
| 656 | 8.3192
| 657 | 8.1207
| 658 | 7.9974
| 659 | 8.3815
| 660 | 6.5013
| 661 | 8.1768
| 662 | 8.5116
| 663 | 8.654
| 664 | 8.6241
| 665 | 7.6844
| 666 | 7.3456
| 667 | 8.6463
| 668 | 8.2945
| 669 | 8.7234
| 670 | 7.7368
| 671 | 8.43
| 672 | 7.0523
| 673 | 8.2844
| 674 | 7.7404
| 675 | 7.6742
| 676 | 8.167
| 677 | 7.1446
| 678 | 8.7619
| 679 | 7.9129
| 680 | 6.6346
| 681 | 7.7907
| 682 | 7.1043
| 683 | 8.1692
| 684 | 8.25
| 685 | 8.1467
| 686 | 8.8225
| 687 | 7.3544
| 688 | 7.453
| 689 | 6.958
| 690 | 6.7293
| 691 | 7.5591
| 692 | 7.5485
| 693 | 7.9006
| 694 | 7.9947
| 695 | 8.0452
| 696 | 8.3845
| 697 | 7.2764
| 698 | 8.1911
| 699 | 7.6567
| 700 | 8.5043
| 701 | 8.2252
| 702 | 7.8715
| 703 | 7.6783
| 704 | 8.3531
| 705 | 7.6295
| 706 | 7.7511
| 707 | 6.8406
| 708 | 8.7045
| 709 | 8.5362
| 710 | 7.1071
| 711 | 8.0247
| 712 | 7.0198
| 713 | 7.5811
| 714 | 8.2034
| 715 | 7.7899
| 716 | 7.6927
| 717 | 8.1126
| 718 | 8.0975
| 719 | 8.6146
| 720 | 8.2464
| 721 | 8.4083
| 722 | 7.9322
| 723 | 8.5747
| 724 | 8.5726
| 725 | 8.4083
| 726 | 8.208
| 727 | 7.3112
| 728 | 8.4642
| 729 | 7.9096
| 730 | 8.1681
| 731 | 8.2958
| 732 | 8.1425
| 733 | 7.5522
| 734 | 8.1279
| 735 | 7.063
| 736 | 8.1383
| 737 | 7.0435
| 738 | 8.1735
| 739 | 7.7361
| 740 | 7.8377
| 741 | 8.617
| 742 | 7.4985
| 743 | 7.606
| 744 | 7.8416
| 745 | 8.5362
| 746 | 7.4718
| 747 | 7.0057
| 748 | 8.6489
| 749 | 8.7544
| 750 | 7.3272
| 751 | 7.0312
| 752 | 7.3
| 753 | 7.3753
| 754 | 7.9322
| 755 | 7.8811
| 756 | 7.3478
| 757 | 7.7121
| 758 | 8.4348
| 759 | 6.8133
| 760 | 7.2148
| 761 | 8.6338
| 762 | 6.4823
| 763 | 8.25
| 764 | 6.7508
| 765 | 8.2001
| 766 | 8.0073
| 767 | 6.5733
| 768 | 7.0445
| 769 | 8.7581
| 770 | 7.2785
| 771 | 8.071
| 772 | 8.208
| 773 | 8.2658
| 774 | 8.2114
| 775 | 7.0486
| 776 | 8.7858
| 777 | 7.4432
| 778 | 8.5986
| 779 | 7.5227
| 780 | 7.6803
| 781 | 7.168
| 782 | 7.2837
| 783 | 8.654
| 784 | 8.0091
| 785 | 7.9577
| 786 | 7.8691
| 787 | 7.3446
| 788 | 8.3352
| 789 | 7.9787
| 790 | 7.4854
| 791 | 7.1431
| 792 | 7.6394
| 793 | 6.9638
| 794 | 6.1834
| 795 | 7.8739
| 796 | 7.6702
| 797 | 6.7084
| 798 | 7.5148
| 799 | 8.224
| 800 | 7.8525
| 801 | 7.0362
| 802 | 7.9313
| 803 | 8.2907
| 804 | 8.544
| 805 | 8.55
| 806 | 7.2879
| 807 | 7.9121
| 808 | 8.5382
| 809 | 7.7744
| 810 | 7.9088
| 811 | 7.6197
| 812 | 8.3475
| 813 | 8.342
| 814 | 7.3321
| 815 | 7.6708
| 816 | 7.5653
| 817 | 7.3462
| 818 | 6.4507
| 819 | 8.1238
| 820 | 7.5938
| 821 | 8.61
| 822 | 8.7045
| 823 | 6.8844
| 824 | 7.5685
| 825 | 6.4924
| 826 | 7.7877
| 827 | 8.8277
| 828 | 8.0633
| 829 | 8.6241
| 830 | 7.7729
| 831 | 8.3587
| 832 | 7.2551
| 833 | 7.7744
| 834 | 7.7569
| 835 | 7.2448
| 836 | 8.1989
| 837 | 8.5663
| 838 | 8.2984
| 839 | 7.5051
| 840 | 7.1243
| 841 | 7.2153
| 842 | 7.4391
| 843 | 7.3424
| 844 | 8.2275
| 845 | 7.1978
| 846 | 7.5817
| 847 | 7.7715
| 848 | 7.8628
| 849 | 7.0298
| 850 | 7.092
| 851 | 8.1627
| 852 | 7.4466
| 853 | 8.4918
| 854 | 7.4317
| 855 | 7.2748
| 856 | 8.5811
| 857 | 8.4642
| 858 | 7.9179
| 859 | 8.0807
| 860 | 7.7715
| 861 | 8.2125
| 862 | 7.5003
| 863 | 8.6388
| 864 | 7.8408
| 865 | 7.2053
| 866 | 8.8175
| 867 | 7.1538
| 868 | 8.5266
| 869 | 7.7936
| 870 | 7.6493
| 871 | 8.5726
| 872 | 7.7432
| 873 | 7.8416
| 874 | 8.2229
| 875 | 8.2806
| 876 | 7.4461
| 877 | 8.1768
| 878 | 8.1867
| 879 | 6.5733
| 880 | 7.4089
| 881 | 7.12
| 882 | 7.6968
| 883 | 6.5774
| 884 | 8.4284
| 885 | 7.171
| 886 | 6.9357
| 887 | 8.0367
| 888 | 7.0509
| 889 | 7.8827
| 890 | 8.49
| 891 | 7.9483
| 892 | 7.2244
| 893 | 8.5304
| 894 | 8.231
| 895 | 7.5647
| 896 | 8.7472
| 897 | 7.5263
| 898 | 8.6514
| 899 | 7.6374
| 900 | 7.862
| 901 | 8.0155
| 902 | 8.6265
| 903 | 8.4493
| 904 | 8.3601
| 905 | 7.5881
| 906 | 7.0477
| 907 | 7.7375
| 908 | 8.152
| 909 | 8.2416
| 910 | 8.5043
| 911 | 7.717
| 912 | 7.9039
| 913 | 8.1269
| 914 | 7.8056
| 915 | 7.7562
| 916 | 7.9121
| 917 | 7.5368
| 918 | 8.416
| 919 | 7.2686
| 920 | 7.9381
| 921 | 8.833
| 922 | 7.406
| 923 | 8.508
| 924 | 8.0985
| 925 | 7.8612
| 926 | 7.5491
| 927 | 7.2194
| 928 | 6.779
| 929 | 7.3446
| 930 | 8.55
| 931 | 8.1563
| 932 | 8.1085
| 933 | 8.6955
| 934 | 7.847
| 935 | 8.0604
| 936 | 7.9146
| 937 | 7.3598
| 938 | 8.1394
| 939 | 7.9355
| 940 | 8.5025
| 941 | 7.8525
| 942 | 7.0574
| 943 | 8.4847
| 944 | 8.1713
| 945 | 7.5735
| 946 | 6.6323
| 947 | 8.1563
| 948 | 8.7581
| 949 | 8.4316
| 950 | 8.2781
| 951 | 8.4008
| 952 | 8.001
| 953 | 8.6955
| 954 | 8.7267
| 955 | 8.3801
| 956 | 7.6587
| 957 | 7.5628
| 958 | 8.6077
| 959 | 7.5184
| 960 | 6.8704
| 961 | 8.1425
| 962 | 8.1595
| 963 | 8.6438
| 964 | 7.8117
| 965 | 7.6145
| 966 | 7.7142
| 967 | 7.7803
| 968 | 7.8691
| 969 | 8.8692
| 970 | 6.6085
| 971 | 8.7076
| 972 | 8.1605
| 973 | 6.75
| 974 | 7.9804
| 975 | 8.6985
| 976 | 7.9423
| 977 | 7.8377
| 978 | 7.9406
| 979 | 8.1035
| 980 | 7.7825
| 981 | 8.67
| 982 | 7.6453
| 983 | 7.6387
| 984 | 7.7468
| 985 | 5.9016
| 986 | 6.738
| 987 | 8.5663
| 988 | 7.5374
| 989 | 8.0146
| 990 | 7.0901
| 991 | 7.6387
| 992 | 8.6926
| 993 | 7.7156
| 994 | 7.3375
| 995 | 7.7283
| 996 | 8.4144
| 997 | 8.2476
| 998 | 8.6338
| 999 | 8.3889
| 1000 | 7.6776
| 1001 | 7.6348
| 1002 | 7.7497
| 1003 | 7.6447
| 1004 | 7.7862
| 1005 | 7.4276
| 1006 | 7.8533
| 1007 | 8.7076
| 1008 | 7.6158
| 1009 | 7.862
| 1010 | 7.9849
| 1011 | 7.6054
| 1012 | 7.546
| 1013 | 8.1436
| 1014 | 7.8385
| 1015 | 7.6695
| 1016 | 8.3393
| 1017 | 8.0807
| 1018 | 8.5898
| 1019 | 8.5285
| 1020 | 8.4053
| 1021 | 7.6275
| 1022 | 8.4709
| 1023 | 7.008
| 1024 | 8.1436
| 1025 | 7.7598
| 1026 | 7.7511
| 1027 | 6.9904
| 1028 | 8.91
| 1029 | 6.8641
| 1030 | 7.8208
| 1031 | 8.8127
| 1032 | 8.4253
| 1033 | 7.4895
| 1034 | 8.0321
| 1035 | 7.2816
| 1036 | 7.571
| 1037 | 6.7863
| 1038 | 8.9206
| 1039 | 8.338
| 1040 | 8.0489
| 1041 | 7.6507
| 1042 | 7.6913
| 1043 | 8.5942
| 1044 | 7.3489
| 1045 | 7.6947
| 1046 | 6.93
| 1047 | 8.6489
| 1048 | 8.1436
| 1049 | 8.1228
| 1050 | 7.6381
| 1051 | 6.8641
| 1052 | 8.8561
| 1053 | 8.1681
| 1054 | 6.9313
| 1055 | 8.1648
| 1056 | 7.9014
| 1057 | 8.0127
| 1058 | 7.2346
| 1059 | 7.4583
| 1060 | 8.79
| 1061 | 8.3615
| 1062 | 7.7627
| 1063 | 7.9965
| 1064 | 8.069
| 1065 | 8.5228
| 1066 | 8.1713
| 1067 | 7.9911
| 1068 | 8.5768
| 1069 | 7.1607
| 1070 | 8.3352
| 1071 | 7.7518
| 1072 | 7.0948
| 1073 | 8.3903
| 1074 | 8.8225
| 1075 | 7.5081
| 1076 | 8.0945
| 1077 | 8.1197
| 1078 | 8.85
| 1079 | 7.5045
| 1080 | 7.1373
| 1081 | 7.9831
| 1082 | 8.0925
| 1083 | 8.8225
| 1084 | 8.1956
| 1085 | 8.3245
| 1086 | 8.1845
| 1087 | 7.9449
| 1088 | 7.84
| 1089 | 8.833
| 1090 | 7.6729
| 1091 | 8.85
| 1092 | 7.8455
| 1093 | 8.1978
| 1094 | 8.3462
| 1095 | 7.4788
| 1096 | 8.5266
| 1097 | 7.5294
| 1098 | 8.0136
| 1099 | 7.5257
| 1100 | 8.6489
| 1101 | 7.28
| 1102 | 7.8957
| 1103 | 8.0719
| 1104 | 8.3859
| 1105 | 7.7375
| 1106 | 8.3232
| 1107 | 6.7766
| 1108 | 8.6514
| 1109 | 8.5854
| 1110 | 6.8034
| 1111 | 8.4709
| 1112 | 8.3978
| 1113 | 8.3232
| 1114 | 7.7121
| 1115 | 7.1993
| 1116 | 7.7981
| 1117 | 7.9163
| 1118 | 8.5876
| 1119 | 8.8625
| 1120 | 7.8667
| 1121 | 8.1187
| 1122 | 8.1373
| 1123 | 7.252
| 1124 | 8.6727
| 1125 | 7.9313
| 1126 | 8.0461
| 1127 | 7.8941
| 1128 | 7.8851
| 1129 | 8.6566
| 1130 | 8.0527
| 1131 | 7.6374
| 1132 | 7.9699
| 1133 | 8.0471
| 1134 | 7.1296
| 1135 | 7.7003
| 1136 | 8.1878
| 1137 | 8.2287
| 1138 | 7.6654
| 1139 | 8.6593
| 1140 | 8.4493
| 1141 | 8.446
| 1142 | 7.6151
| 1143 | 7.8424
| 1144 | 6.7273
| 1145 | 7.6614
| 1146 | 8.5705
| 1147 | 8.231
| 1148 | 6.8043
| 1149 | 8.3205
| 1150 | 8.91
| 1151 | 7.762
| 1152 | 8.73
| 1153 | 8.1692
| 1154 | 8.3948
| 1155 | 8.3272
| 1156 | 8.2012
| 1157 | 6.8934
| 1158 | 7.4134
| 1159 | 7.3484
| 1160 | 7.9483
| 1161 | 7.7576
| 1162 | 7.2701
| 1163 | 6.8348
| 1164 | 7.8868
| 1165 | 7.3703
| 1166 | 7.0148
| 1167 | 8.8277
| 1168 | 8.1373
| 1169 | 7.7425
| 1170 | 8.7988
| 1171 | 6.9762
| 1172 | 7.6177
| 1173 | 8.1967
| 1174 | 8.5789
| 1175 | 8.19
| 1176 | 7.8502
| 1177 | 8.5323
| 1178 | 8.3245
| 1179 | 7.8102
| 1180 | 8.4038
| 1181 | 7.4004
| 1182 | 7.3637
| 1183 | 7.0435
| 1184 | 6.8544
| 1185 | 8.383
| 1186 | 8.446
| 1187 | 8.244
| 1188 | 7.7656
| 1189 | 8.1136
| 1190 | 7.1335
| 1191 | 7.7795
| 1192 | 7.4594
| 1193 | 8.4795
| 1194 | 8.4364
| 1195 | 7.6769
| 1196 | 8.4068
| 1197 | 7.0093
| 1198 | 8.1478
| 1199 | 7.5312
| 1200 | 7.6858
| 1201 | 6.8569
| 1202 | 7.0616
| 1203 | 7.8041
| 1204 | 8.0311
| 1205 | 8.438
| 1206 | 7.8424
| 1207 | 7.6763
| 1208 | 7.6387
| 1209 | 8.0905
| 1210 | 6.6721
| 1211 | 8.1362
| 1212 | 8.5581
| 1213 | 7.0751
| 1214 | 8.1692
| 1215 | 7.4883
| 1216 | 7.7339
| 1217 | 8.1197
| 1218 | 8.129
| 1219 | 8.0575
| 1220 | 7.9072
| 1221 | 7.9163
| 1222 | 7.9263
| 1223 | 8.4222
| 1224 | 7.434
| 1225 | 7.9163
| 1226 | 8.8838
| 1227 | 7.95
| 1228 | 7.2234
| 1229 | 7.6414
| 1230 | 7.933
| 1231 | 7.7093
| 1232 | 8.6123
| 1233 | 8.6463
| 1234 | 7.9364
| 1235 | 8.3772
| 1236 | 7.0093
| 1237 | 7.7533
| 1238 | 8.1834
| 1239 | 7.6695
| 1240 | 8.8079
| 1241 | 7.8034
| 1242 | 7.0873
| 1243 | 7.7715
| 1244 | 8.2452
| 1245 | 8.4509
| 1246 | 6.9567
| 1247 | 8.3489
| 1248 | 8.6514
| 1249 | 8.8175
| 1250 | 8.292
| 1251 | 8.55
| 1252 | 7.4771
| 1253 | 7.59
| 1254 | 7.1754
| 1255 | 8.1834
| 1256 | 7.0528
| 1257 | 8.6123
| 1258 | 6.4209
| 1259 | 8.948
| 1260 | 7.5659
| 1261 | 7.9787
| 1262 | 6.8797
| 1263 | 7.6797
| 1264 | 7.6641
| 1265 | 8.2945
| 1266 | 8.2844
| 1267 | 7.9577
| 1268 | 7.8998
| 1269 | 7.5392
| 1270 | 8.4795
| 1271 | 8.1627
| 1272 | 7.3982
| 1273 | 8.654
| 1274 | 6.8448
| 1275 | 7.969
| 1276 | 7.9992
| 1277 | 7.4824
| 1278 | 7.692
| 1279 | 8.2217
| 1280 | 8.7858
| 1281 | 7.0053
| 1282 | 8.3918
| 1283 | 8.4222
| 1284 | 7.5111
| 1285 | 8.3232
| 1286 | 7.1427
| 1287 | 6.193
| 1288 | 8.5876
| 1289 | 8.0788
| 1290 | 7.6553
| 1291 | 7.8517
| 1292 | 8.8225
| 1293 | 8.8561
| 1294 | 7.1612
| 1295 | 7.6164
| 1296 | 8.3531
| 1297 | 7.5647
| 1298 | 7.2433
| 1299 | 7.8779
| 1300 | 7.4305
| 1301 | 7.9974
| 1302 | 7.8193
| 1303 | 8.2001
| 1304 | 7.5805
| 1305 | 7.2224
| 1306 | 6.456
| 1307 | 8.3874
| 1308 | 7.8408
| 1309 | 8.5116
| 1310 | 7.7959
| 1311 | 7.2654
| 1312 | 8.0247
| 1313 | 8.2769
| 1314 | 7.4967
| 1315 | 7.8949
| 1316 | 7.6661
| 1317 | 7.7598
| 1318 | 7.9629
| 1319 | 8.2524
| 1320 | 7.7269
| 1321 | 7.2058
| 1322 | 6.7709
| 1323 | 6.5267
| 1324 | 8.3671
| 1325 | 7.7656
| 1326 | 8.483
| 1327 | 7.6627
| 1328 | 6.9878
| 1329 | 8.2597
| 1330 | 8.6338
| 1331 | 7.1354
| 1332 | 7.6886
| 1333 | 8.5726
| 1334 | 7.9179
| 1335 | 7.1898
| 1336 | 7.6374
| 1337 | 7.1913
| 1338 | 8.6811
| 1339 | 8.2091
| 1340 | 8.1425
| 1341 | 8.4191
| 1342 | 7.4937
| 1343 | 7.8463
| 1344 | 8.2148
| 1345 | 8.0191
| 1346 | 8.2183
| 1347 | 7.6473
| 1348 | 8.9329
| 1349 | 6.6521
| 1350 | 7.5603
| 1351 | 7.8636
| 1352 | 7.7297
| 1353 | 7.2214
| 1354 | 8.6413
| 1355 | 8.1404
| 1356 | 7.8876
| 1357 | 8.1746
| 1358 | 8.0896
| 1359 | 8.6619
| 1360 | 7.5196
| 1361 | 8.0556
| 1362 | 8.592
| 1363 | 7.8755
| 1364 | 7.4231
| 1365 | 6.6919
| 1366 | 8.3312
| 1367 | 7.453
| 1368 | 8.2756
| 1369 | 8.2633
| 1370 | 8.4526
| 1371 | 6.9519
| 1372 | 7.6507
| 1373 | 7.9884
| 1374 | 7.6216
| 1375 | 8.1702
| 1376 | 8.0896
| 1377 | 8.0109
| 1378 | 7.3842
| 1379 | 7.0565
| 1380 | 7.6054
| 1381 | 7.4128
| 1382 | 8.2171
| 1383 | 7.3278
| 1384 | 8.0985
| 1385 | 7.9849
| 1386 | 8.292
| 1387 | 7.2535
| 1388 | 7.6177
| 1389 | 7.2515
| 1390 | 7.0699
| 1391 | 7.597
| 1392 | 7.9229
| 1393 | 7.4179
| 1394 | 8.3448
| 1395 | 6.699
| 1396 | 8.0661
| 1397 | 8.1383
| 1398 | 7.6872
| 1399 | 8.8277
| 1400 | 7.5117
| 1401 | 8.0836
| 1402 | 7.3803
| 1403 | 8.2819
| 1404 | 7.084
| 1405 | 8.3933
| 1406 | 7.5239
| 1407 | 7.2613
| 1408 | 7.8803
| 1409 | 8.2831
| 1410 | 7.2088
| 1411 | 7.8628
| 1412 | 8.0719
| 1413 | 7.9415
| 1414 | 8.5382
| 1415 | 8.7267
| 1416 | 7.1407
| 1417 | 7.9866
| 1418 | 6.79
| 1419 | 7.5932
| 1420 | 7.6858
| 1421 | 8.4316
| 1422 | 7.5404
| 1423 | 7.7518
| 1424 | 8.3272
| 1425 | 8.5401
| 1426 | 7.1417
| 1427 | 7.2748
| 1428 | 8.0642
| 1429 | 8.8127
| 1430 | 8.6338
| 1431 | 8.1659
| 1432 | 8.55
| 1433 | 8.7076
| 1434 | 8.1801
| 1435 | 7.9866
| 1436 | 6.1327
| 1437 | 6.7096
| 1438 | 7.2397
| 1439 | 8.4509
| 1440 | 8.4989
| 1441 | 8.0896
| 1442 | 7.9699
| 1443 | 7.6223
| 1444 | 7.6028
| 1445 | 8.3772
| 1446 | 7.7526
| 1447 | 7.6269
| 1448 | 8.3657
| 1449 | 8.0642
| 1450 | 7.7598
| 1451 | 8.292
| 1452 | 7.6614
| 1453 | 7.7685
| 1454 | 6.4995
| 1455 | 7.9778
| 1456 | 8.216
| 1457 | 7.1024
| 1458 | 8.0613
| 1459 | 8.1187
| 1460 | 8.37
| 1461 | 6.7998
| 1462 | 8.1218
| 1463 | 8.2476
| 1464 | 8.3772
| 1465 | 8.3475
| 1466 | 7.0672
| 1467 | 7.646
| 1468 | 7.4554
| 1469 | 7.9055
| 1470 | 7.6216
| 1471 | 7.9355
| 1472 | 8.79
| 1473 | 8.7657
| 1474 | 8.292
| 1475 | 8.1126
| 1476 | 7.8377
| 1477 | 7.7671
| 1478 | 8.7735
| 1479 | 7.1162
| 1480 | 8.2137
| 1481 | 8.0127
| 1482 | 8.0461
| 1483 | 7.7907
| 1484 | 7.903
| 1485 | 8.8838
| 1486 | 8.1509
| 1487 | 8.6566
| 1488 | 7.9466
| 1489 | 8.31
| 1490 | 7.644
| 1491 | 8.292
| 1492 | 8.0339
| 1493 | 8.7816
| 1494 | 7.2701
| 1495 | 8.37
| 1496 | 8.3859
| 1497 | 8.1845
| 1498 | 7.083
| 1499 | 8.3889
| 1500 | 7.1973
| 1501 | 7.4357
| 1502 | 7.0695
| 1503 | 7.6594
| 1504 | 8.1989
| 1505 | 8.3601
| 1506 | 6.8306
| 1507 | 7.7017
| 1508 | 8.948
| 1509 | 7.6164
| 1510 | 7.2412
| 1511 | 6.8215
| 1512 | 8.7657
| 1513 | 8.4778
| 1514 | 6.738
| 1515 | 8.4726
| 1516 | 7.3598
| 1517 | 8.4882
| 1518 | 8.6566
| 1519 | 7.8239
| 1520 | 7.9221
| 1521 | 8.5007
| 1522 | 7.7936
| 1523 | 8.7076
| 1524 | 8.2183
| 1525 | 8.9206
| 1526 | 7.0873
| 1527 | 7.4949
| 1528 | 8.8561
| 1529 | 8.0827
| 1530 | 8.7334
| 1531 | 7.0532
| 1532 | 8.1724
| 1533 | 6.7155
| 1534 | 7.5325
| 1535 | 8.1352
| 1536 | 7.7079
| 1537 | 7.5263
| 1538 | 7.6048
| 1539 | 7.597
| 1540 | 7.4438
| 1541 | 7.267
| 1542 | 7.3626
| 1543 | 6.9985
| 1544 | 8.07
| 1545 | 7.7663
| 1546 | 7.9552
| 1547 | 7.4055
| 1548 | 7.7325
| 1549 | 8.8561
| 1550 | 8.6926
| 1551 | 8.1478
| 1552 | 8.7107
| 1553 | 8.1509
| 1554 | 7.8868
| 1555 | 8.7234
| 1556 | 7.9088
| 1557 | 7.7482
| 1558 | 7.9313
| 1559 | 7.576
| 1560 | 8.4575
| 1561 | 6.9602
| 1562 | 7.2463
| 1563 | 8.3993
| 1564 | 7.6093
| 1565 | 8.7858
| 1566 | 7.6934
| 1567 | 8.3009
| 1568 | 7.9246
| 1569 | 7.486
| 1570 | 8.4935
| 1571 | 7.6067
| 1572 | 6.781
| 1573 | 8.1541
| 1574 | 8.8033
| 1575 | 8.1531
| 1576 | 8.7816
| 1577 | 7.4077
| 1578 | 7.5983
| 1579 | 7.4724
| 1580 | 7.6308
| 1581 | 7.4735
| 1582 | 7.9752
| 1583 | 8.4008
| 1584 | 8.4253
| 1585 | 8.1085
| 1586 | 7.3604
| 1587 | 7.2103
| 1588 | 8.7202
| 1589 | 8.0146
| 1590 | 7.8362
| 1591 | 8.7234
| 1592 | 8.0037
| 1593 | 7.5553
| 1594 | 7.6493
| 1595 | 8.7544
| 1596 | 8.3166
| 1597 | 8.0046
| 1598 | 7.5331
| 1599 | 6.777
| 1600 | 7.0509
| 1601 | 7.7922
| 1602 | 7.1043
| 1603 | 7.9381
| 1604 | 7.4594
| 1605 | 8.6123
| 1606 | 8.0896
| 1607 | 7.2204
| 1608 | 8.6438
| 1609 | 7.7354
| 1610 | 7.3224
| 1611 | 8.2621
| 1612 | 7.2053
| 1613 | 8.2609
| 1614 | 7.5855
| 1615 | 8.6755
| 1616 | 7.2499
| 1617 | 6.2608
| 1618 | 7.8079
| 1619 | 7.6073
| 1620 | 7.9296
| 1621 | 7.4455
| 1622 | 7.71
| 1623 | 7.8739
| 1624 | 8.1269
| 1625 | 7.5325
| 1626 | 7.4919
| 1627 | 7.6756
| 1628 | 7.551
| 1629 | 7.449
| 1630 | 7.9483
| 1631 | 8.4692
| 1632 | 7.3533
| 1633 | 8.3009
| 1634 | 7.0835
| 1635 | 7.89
| 1636 | 8.43
| 1637 | 7.7634
| 1638 | 7.9381
| 1639 | 8.9206
| 1640 | 7.4901
| 1641 | 7.2093
| 1642 | 7.2163
| 1643 | 7.9778
| 1644 | 6.7544
| 1645 | 7.9629
| 1646 | 7.1388
| 1647 | 7.0727
| 1648 | 7.5343
| 1649 | 8.4253
| 1650 | 7.0662
| 1651 | 7.9138
| 1652 | 7.4426
| 1653 | 7.5245
| 1654 | 7.0325
| 1655 | 7.7432
| 1656 | 8.5343
| 1657 | 8.5172
| 1658 | 8.67
| 1659 | 8.8692
| 1660 | 8.2621
| 1661 | 6.9918
| 1662 | 8.6619
| 1663 | 7.6164
| 1664 | 8.0274
| 1665 | 7.84
| 1666 | 6.7588
| 1667 | 7.5977
| 1668 | 7.0704
| 1669 | 7.9655
| 1670 | 8.0856
| 1671 | 8.5768
| 1672 | 8.2621
| 1673 | 7.66
| 1674 | 8.3629
| 1675 | 7.1715
| 1676 | 8.1889
| 1677 | 7.1119
| 1678 | 6.6388
| 1679 | 8.1867
| 1680 | 8.55
| 1681 | 8.31
| 1682 | 7.9474
| 1683 | 7.9884
| 1684 | 8.6054
| 1685 | 8.5285
| 1686 | 8.0001
| 1687 | 7.9603
| 1688 | 8.7735
| 1689 | 7.0835
| 1690 | 8.6289
| 1691 | 8.6783
| 1692 | 8.2137
| 1693 | 7.4641
| 1694 | 8.5343
| 1695 | 8.0965
| 1696 | 8.4412
| 1697 | 7.4472
| 1698 | 8.43
| 1699 | 8.1509
| 1700 | 8.6388
| 1701 | 8.4744
| 1702 | 7.1568
| 1703 | 8.3714
| 1704 | 6.6514
| 1705 | 8.0671
| 1706 | 6.6058
| 1707 | 7.2597
| 1708 | 8.3179
| 1709 | 7.656
| 1710 | 7.5881
| 1711 | 8.5343
| 1712 | 7.5919
| 1713 | 6.9461
| 1714 | 8.1768
| 1715 | 8.0518
| 1716 | 7.8034
| 1717 | 7.5779
| 1718 | 8.6514
| 1719 | 8.8838
| 1720 | 8.5266
| 1721 | 6.8912
| 1722 | 7.7404
| 1723 | 7.1943
| 1724 | 7.8965
| 1725 | 7.9655
| 1726 | 8.2148
| 1727 | 8.4476
| 1728 | 7.2178
| 1729 | 7.6865
| 1730 | 8.1584
| 1731 | 7.8216
| 1732 | 7.132
| 1733 | 8.5061
| 1734 | 7.6838
| 1735 | 7.4027
| 1736 | 8.3948
| 1737 | 6.5413
| 1738 | 8.8763
| 1739 | 8.2932
| 1740 | 6.3917
| 1741 | 8.7619
| 1742 | 8.8441
| 1743 | 7.8308
| 1744 | 8.3545
| 1745 | 7.3123
| 1746 | 7.9517
| 1747 | 6.7965
| 1748 | 8.73
| 1749 | 7.1592
| 1750 | 7.7989
| 1751 | 7.5196
| 1752 | 7.3155
| 1753 | 7.4374
| 1754 | 8.3035
| 1755 | 7.9983
| 1756 | 8.0127
| 1757 | 7.3954
| 1758 | 8.0064
| 1759 | 8.5172
| 1760 | 7.2244
| 1761 | 8.1383
| 1762 | 8.6241
| 1763 | 8.2217
| 1764 | 8.61
| 1765 | 8.1989
| 1766 | 8.6363
| 1767 | 8.6241
| 1768 | 7.0408
| 1769 | 8.8384
| 1770 | 7.1485
| 1771 | 7.3736
| 1772 | 8.4882
| 1773 | 7.0243
| 1774 | 7.4985
| 1775 | 7.9552
| 1776 | 7.4004
| 1777 | 7.8369
| 1778 | 6.6783
| 1779 | 7.8683
| 1780 | 8.8763
| 1781 | 8.5768
| 1782 | 6.6869
| 1783 | 7.6776
| 1784 | 8.6338
| 1785 | 8.2103
| 1786 | 7.5386
| 1787 | 8.167
| 1788 | 7.1393
| 1789 | 7.5958
| 1790 | 8.0489
| 1791 | 7.9449
| 1792 | 8.6031
| 1793 | 8.1584
| 1794 | 8.7988
| 1795 | 8.4625
| 1796 | 6.7875
| 1797 | 8.2572
| 1798 | 6.4422
| 1799 | 7.9406
| 1800 | 8.4191
| 1801 | 7.6407
| 1802 | 8.0915
| 1803 | 6.6594
| 1804 | 8.2512
| 1805 | 6.8561
| 1806 | 7.3965
| 1807 | 7.0741
| 1808 | 7.7318
| 1809 | 7.6647
| 1810 | 8.0311
| 1811 | 8.8033
| 1812 | 7.0658
| 1813 | 7.8827
| 1814 | 8.4206
| 1815 | 7.1863
| 1816 | 7.6086
| 1817 | 7.4478
| 1818 | 7.619
| 1819 | 8.3245
| 1820 | 7.7121
| 1821 | 6.3145
| 1822 | 6.8104
| 1823 | 8.85
| 1824 | 7.2346
| 1825 | 7.5559
| 1826 | 8.4428
| 1827 | 8.0652
| 1828 | 7.483
| 1829 | 7.5697
| 1830 | 7.7832
| 1831 | 8.6413
| 1832 | 8.3218
| 1833 | 8.4493
| 1834 | 7.0812
| 1835 | 7.6387
| 1836 | 7.6361
| 1837 | 6.501
| 1838 | 8.3434
| 1839 | 8.1279
| 1840 | 8.3629
| 1841 | 8.0681
| 1842 | 7.7583
| 1843 | 8.2194
| 1844 | 8.1867
| 1845 | 7.5767
| 1846 | 7.7177
| 1847 | 8.6438
| 1848 | 8.717
| 1849 | 7.5099
| 1850 | 7.1152
| 1851 | 8.3061
| 1852 | 7.7869
| 1853 | 8.2907
| 1854 | 7.7966
| 1855 | 8.416
| 1856 | 7.5528
| 1857 | 7.862
| 1858 | 7.8876
| 1859 | 7.5559
| 1860 | 8.654
| 1861 | 8.6077
| 1862 | 8.4083
| 1863 | 8.3729
| 1864 | 8.4608
| 1865 | 8.6123
| 1866 | 7.8827
| 1867 | 8.5832
| 1868 | 6.7198
| 1869 | 7.9831
| 1870 | 7.7389
| 1871 | 7.1848
| 1872 | 7.0271
| 1873 | 7.4179
| 1874 | 7.3
| 1875 | 8.2334
| 1876 | 7.6627
| 1877 | 8.383
| 1878 | 7.372
| 1879 | 8.0836
| 1880 | 6.6133
| 1881 | 7.9179
| 1882 | 7.7261
| 1883 | 7.7781
| 1884 | 7.956
| 1885 | 8.2707
| 1886 | 7.8041
| 1887 | 8.5622
| 1888 | 8.3993
| 1889 | 7.7974
| 1890 | 7.0704
| 1891 | 7.5045
| 1892 | 8.2114
| 1893 | 7.8239
| 1894 | 8.0321
| 1895 | 7.658
| 1896 | 8.5768
| 1897 | 8.2658
| 1898 | 8.1259
| 1899 | 7.6138
| 1900 | 7.5767
| 1901 | 8.4509
| 1902 | 7.3819
| 1903 | 8.5362
| 1904 | 8.8763
| 1905 | 6.526
| 1906 | 7.7759
| 1907 | 7.8771
| 1908 | 8.1659
| 1909 | 7.5849
| 1910 | 7.862
| 1911 | 7.8432
| 1912 | 7.6954
| 1913 | 8.1065
| 1914 | 7.729
| 1915 | 7.7461
| 1916 | 8.9329
| 1917 | 8.2034
| 1918 | 7.8604
| 1919 | 7.1617
| 1920 | 6.6629
| 1921 | 8.1563
| 1922 | 8.342
| 1923 | 8.3022
| 1924 | 7.3203
| 1925 | 6.6563
| 1926 | 8.4428
| 1927 | 7.9534
| 1928 | 6.7524
| 1929 | 7.6614
| 1930 | 8.0386
| 1931 | 7.8331
| 1932 | 7.8315
| 1933 | 8.1801
| 1934 | 7.8262
| 1935 | 7.9179
| 1936 | 7.6328
| 1937 | 7.8094
| 1938 | 7.4501
| 1939 | 7.5142
| 1940 | 7.9296
| 1941 | 8.0565
| 1942 | 8.3714
| 1943 | 6.497
| 1944 | 8.0019
| 1945 | 8.2844
| 1946 | 7.4542
| 1947 | 7.5411
| 1948 | 8.19
| 1949 | 6.8224
| 1950 | 8.3918
| 1951 | 7.2128
| 1952 | 7.8957
| 1953 | 7.1504
| 1954 | 8.6514
| 1955 | 7.7605
| 1956 | 7.6015
| 1957 | 7.7634
| 1958 | 8.1823
| 1959 | 7.0779
| 1960 | 7.4842
| 1961 | 8.79
| 1962 | 8.231
| 1963 | 8.069
| 1964 | 8.2996
| 1965 | 7.7533
| 1966 | 7.6158
| 1967 | 7.4495
| 1968 | 7.717
| 1969 | 7.9938
| 1970 | 6.1712
| 1971 | 7.2743
| 1972 | 8.5247
| 1973 | 7.8803
| 1974 | 8.6265
| 1975 | 7.8604
| 1976 | 7.1043
| 1977 | 8.8127
| 1978 | 7.4729
| 1979 | 8.2346
| 1980 | 6.8047
| 1981 | 7.519
| 1982 | 8.7816
| 1983 | 7.6879
| 1984 | 7.077
| 1985 | 8.3714
| 1986 | 5.5323
| 1987 | 7.89
| 1988 | 8.6755
| 1989 | 6.6266
| 1990 | 7.9664
| 1991 | 7.3898
| 1992 | 8.3113
| 1993 | 7.2953
| 1994 | 7.6216
| 1995 | 7.9254
| 1996 | 8.2597
| 1997 | 7.1963
| 1998 | 8.3573
| 1999 | 8.0778
| 2000 | 8.2958
| 2001 | 8.2984
| 2002 | 7.6229
| 2003 | 8.4396
| 2004 | 7.0713
| 2005 | 7.9965
| 2006 | 7.7855
| 2007 | 8.2103
| 2008 | 8.3009
| 2009 | 8.1702
| 2010 | 7.9717
| 2011 | 8.048
| 2012 | 7.6668
| 2013 | 7.8667
| 2014 | 7.3881
| 2015 | 7.0211
| 2016 | 6.6537
| 2017 | 8.2819
| 2018 | 8.13
| 2019 | 7.2407
| 2020 | 8.4625
| 2021 | 8.2597
| 2022 | 8.3643
| 2023 | 8.0807
| 2024 | 8.8441
| 2025 | 8.0739
| 2026 | 7.267
| 2027 | 8.3729
| 2028 | 7.6844
| 2029 | 7.3364
| 2030 | 8.0739
| 2031 | 7.3626
| 2032 | 7.8731
| 2033 | 8.8225
| 2034 | 8.6566
| 2035 | 7.7142
| 2036 | 7.5572
| 2037 | 8.3615
| 2038 | 7.1124
| 2039 | 7.5836
| 2040 | 8.1746
| 2041 | 8.0905
| 2042 | 8.3009
| 2043 | 7.4565
| 2044 | 7.4907
| 2045 | 7.3598
| 2046 | 7.6899
| 2047 | 8.85
| 2048 | 8.244
| 2049 | 8.3218
| 2050 | 7.8771
| 2051 | 7.0431
| 2052 | 7.7432
| 2053 | 8.4692
| 2054 | 8.6314
| 2055 | 7.9875
| 2056 | 7.7555
| 2057 | 7.3251
| 2058 | 8.1801
| 2059 | 8.1584
| 2060 | 7.1138
| 2061 | 7.3435
| 2062 | 8.0191
| 2063 | 7.8675
| 2064 | 7.8715
| 2065 | 8.224
| 2066 | 7.2285
| 2067 | 7.7432
| 2068 | 8.7508
| 2069 | 7.5653
| 2070 | 7.9296
| 2071 | 7.6844
| 2072 | 8.3978
| 2073 | 7.7339
| 2074 | 8.3531
| 2075 | 7.8973
| 2076 | 8.6289
| 2077 | 8.4558
| 2078 | 8.3531
| 2079 | 8.1436
| 2080 | 8.4592
| 2081 | 7.0962
| 2082 | 8.97
| 2083 | 6.6846
| 2084 | 7.3473
| 2085 | 7.2422
| 2086 | 8.0681
| 2087 | 7.9055
| 2088 | 8.3845
| 2089 | 6.6694
| 2090 | 7.2249
| 2091 | 7.8541
| 2092 | 7.2361
| 2093 | 8.4444
| 2094 | 8.1702
| 2095 | 8.0623
| 2096 | 7.703
| 2097 | 7.7693
| 2098 | 8.1015
| 2099 | 8.654
| 2100 | 8.1956
| 2101 | 8.4412
| 2102 | 8.3903
| 2103 | 8.0091
| 2104 | 8.7544
| 2105 | 6.7194
| 2106 | 8.1933
| 2107 | 8.7437
| 2108 | 7.2743
| 2109 | 7.4055
| 2110 | 7.5824
| 2111 | 7.2785
| 2112 | 8.8384
| 2113 | 8.0508
| 2114 | 7.3451
| 2115 | 8.2769
| 2116 | 8.5191
| 2117 | 8.4129
| 2118 | 8.1248
| 2119 | 8.0164
| 2120 | 8.7943
| 2121 | 8.617
| 2122 | 8.3559
| 2123 | 7.6989
| 2124 | 7.3085
| 2125 | 8.1681
| 2126 | 6.7721
| 2127 | 8.1467
| 2128 | 6.962
| 2129 | 7.7569
| 2130 | 8.6489
| 2131 | 7.6467
| 2132 | 7.4225
| 2133 | 7.2974
| 2134 | 7.2649
| 2135 | 7.5862
| 2136 | 7.5057
| 2137 | 8.7234
| 2138 | 8.6217
| 2139 | 7.5015
| 2140 | 7.3527
| 2141 | 8.3933
| 2142 | 8.592
| 2143 | 8.1116
| 2144 | 7.4665
| 2145 | 7.4004
| 2146 | 7.2748
| 2147 | 8.0985
| 2148 | 8.0985
| 2149 | 8.1457
| 2150 | 8.8918
| 2151 | 8.5876
| 2152 | 7.9992
| 2153 | 7.5282
| 2154 | 6.752
| 2155 | 8.6388
| 2156 | 7.4513
| 2157 | 7.6427
| 2158 | 8.0896
| 2159 | 7.9355
| 2160 | 8.5581
| 2161 | 7.5958
| 2162 | 8.2476
| 2163 | 8.0827
| 2164 | 8.3139
| 2165 | 8.1156
| 2166 | 8.3629
| 2167 | 8.0377
| 2168 | 8.1595
| 2169 | 7.8932
| 2170 | 8.2488
| 2171 | 8.1638
| 2172 | 7.2832
| 2173 | 8.2393
| 2174 | 8.0256
| 2175 | 8.1616
| 2176 | 6.9532
| 2177 | 8.4813
| 2178 | 7.2356
| 2179 | 8.4608
| 2180 | 8.0349
| 2181 | 7.9313
| 2182 | 8.4206
| 2183 | 7.7627
| 2184 | 8.4332
| 2185 | 8.6897
| 2186 | 7.3133
| 2187 | 7.2244
| 2188 | 7.5566
| 2189 | 8.2831
| 2190 | 8.2744
| 2191 | 8.1889
| 2192 | 8.3657
| 2193 | 8.4237
| 2194 | 8.3285
| 2195 | 7.1258
| 2196 | 7.9154
| 2197 | 7.4883
| 2198 | 8.5135
| 2199 | 7.8208
| 2200 | 7.1124
| 2201 | 7.0116
| 2202 | 8.1724
| 2203 | 8.3232
| 2204 | 8.7437
| 2205 | 8.3889
| 2206 | 7.4913
| 2207 | 7.2921
| 2208 | 8.2794
| 2209 | 7.9534
| 2210 | 7.606
| 2211 | 7.8269
| 2212 | 7.4032
| 2213 | 7.251
| 2214 | 7.9717
| 2215 | 8.3393
| 2216 | 8.67
| 2217 | 8.6727
| 2218 | 8.3657
| 2219 | 8.1856
| 2220 | 6.8964
| 2221 | 7.8651
| 2222 | 8.7437
| 2223 | 8.1065
| 2224 | 6.744
| 2225 | 8.152
| 2226 | 7.4299
| 2227 | 8.1713
| 2228 | 7.5641
| 2229 | 6.8887
| 2230 | 7.6668
| 2231 | 6.7017
| 2232 | 8.4332
| 2233 | 7.9204
| 2234 | 8.4935
| 2235 | 7.0468
| 2236 | 8.1321
| 2237 | 8.3407
| 2238 | 7.3516
| 2239 | 7.6865
| 2240 | 7.4386
| 2241 | 7.3577
| 2242 | 8.1563
| 2243 | 8.4476
| 2244 | 8.1197
| 2245 | 8.5747
| 2246 | 7.8323
| 2247 | 7.0528
| 2248 | 8.5964
| 2249 | 7.6934
| 2250 | 7.5318
| 2251 | 8.2183
| 2252 | 8.1228
| 2253 | 6.962
| 2254 | 7.571
| 2255 | 7.847
| 2256 | 7.9047
| 2257 | 8.0339
| 2258 | 8.3963
| 2259 | 8.3035
| 2260 | 7.7526
| 2261 | 6.6308
| 2262 | 7.1661
| 2263 | 7.6184
| 2264 | 8.3489
| 2265 | 7.7311
| 2266 | 7.4191
| 2267 | 7.4949
| 2268 | 7.7518
| 2269 | 7.9055
| 2270 | 7.7605
| 2271 | 8.0442
| 2272 | 8.546
| 2273 | 8.0386
| 2274 | 7.4525
| 2275 | 7.4671
| 2276 | 7.9992
| 2277 | 7.9769
| 2278 | 8.7437
| 2279 | 8.01
| 2280 | 7.9534
| 2281 | 7.5906
| 2282 | 8.0367
| 2283 | 7.5227
| 2284 | 7.8323
| 2285 | 7.8723
| 2286 | 7.5441
| 2287 | 8.2769
| 2288 | 7.12
| 2289 | 6.5808
| 2290 | 7.8254
| 2291 | 7.9612
| 2292 | 7.8094
| 2293 | 7.6334
| 2294 | 8.5876
| 2295 | 7.5849
| 2296 | 8.9206
| 2297 | 8.3299
| 2298 | 6.7725
| 2299 | 7.4907
| 2300 | 6.8435
| 2301 | 8.6009
| 2302 | 7.4866
| 2303 | 8.6438
| 2304 | 7.7707
| 2305 | 8.3587
| 2306 | 7.2984
| 2307 | 7.9655
| 2308 | 8.7045
| 2309 | 8.5663
| 2310 | 7.5154
| 2311 | 6.6671
| 2312 | 8.0915
| 2313 | 7.3251
| 2314 | 8.1823
| 2315 | 6.676
| 2316 | 7.7803
| 2317 | 8.1757
| 2318 | 7.5541
| 2319 | 7.8973
| 2320 | 7.9171
| 2321 | 8.0155
| 2322 | 7.6223
| 2323 | 8.2584
| 2324 | 8.3448
| 2325 | 8.0866
| 2326 | 8.4709
| 2327 | 7.3703
| 2328 | 7.2926
| 2329 | 7.5572
| 2330 | 7.1033
| 2331 | 8.79
| 2332 | 8.208
| 2333 | 8.6593
| 2334 | 7.2183
| 2335 | 6.9058
| 2336 | 8.3152
| 2337 | 7.8795
| 2338 | 7.3413
| 2339 | 8.1638
| 2340 | 8.1167
| 2341 | 7.7634
| 2342 | 7.7418
| 2343 | 7.2958
| 2344 | 7.8636
| 2345 | 7.4913
| 2346 | 8.4778
| 2347 | 8.0633
| 2348 | 7.7605
| 2349 | 8.0856
| 2350 | 8.6755
| 2351 | 7.3736
| 2352 | 8.2148
| 2353 | 8.5343
| 2354 | 8.2856
| 2355 | 7.4265
| 2356 | 7.362
| 2357 | 7.3219
| 2358 | 7.6899
| 2359 | 7.8699
| 2360 | 8.048
| 2361 | 7.0216
| 2362 | 8.5684
| 2363 | 8.2299
| 2364 | 7.7966
| 2365 | 7.8424
| 2366 | 7.449
| 2367 | 7.9313
| 2368 | 7.7382
| 2369 | 7.8102
| 2370 | 6.6111
| 2371 | 7.2168
| 2372 | 7.0972
| 2373 | 7.1968
| 2374 | 7.232
| 2375 | 7.2691
| 2376 | 8.2452
| 2377 | 7.7439
| 2378 | 7.8049
| 2379 | 7.8323
| 2380 | 8.4098
| 2381 | 7.5111
| 2382 | 7.7065
| 2383 | 8.4642
| 2384 | 6.9431
| 2385 | 8.2769
| 2386 | 7.8588
| 2387 | 7.8087
| 2388 | 8.5043
| 2389 | 8.6755
| 2390 | 7.344
| 2391 | 6.8806
| 2392 | 8.37
| 2393 | 7.648
| 2394 | 7.9577
| 2395 | 8.5191
| 2396 | 8.2217
| 2397 | 6.8713
| 2398 | 7.5659
| 2399 | 8.1352
| 2400 | 8.61
| 2401 | 8.1207
| 2402 | 7.7847
| 2403 | 8.1768
| 2404 | 8.2572
| 2405 | 8.5421
| 2406 | 8.0537
| 2407 | 8.2034
| 2408 | 8.3035
| 2409 | 8.4989
| 2410 | 7.1186
| 2411 | 8.3918
| 2412 | 8.0146
| 2413 | 8.7775
| 2414 | 7.4236
| 2415 | 8.2633
| 2416 | 8.6839
| 2417 | 8.1692
| 2418 | 8.1467
| 2419 | 8.6289
| 2420 | 8.5854
| 2421 | 8.3352
| 2422 | 8.2869
| 2423 | 8.3963
| 2424 | 8.4023
| 2425 | 7.7497
| 2426 | 8.0395
| 2427 | 7.2995
| 2428 | 8.2229
| 2429 | 7.1162
| 2430 | 7.7347
| 2431 | 7.8502
| 2432 | 7.5535
| 2433 | 8.5421
| 2434 | 8.5247
| 2435 | 7.3326
| 2436 | 8.4676
| 2437 | 7.2753
| 2438 | 8.7775
| 2439 | 8.6868
| 2440 | 8.7472
| 2441 | 8.0995
| 2442 | 6.4585
| 2443 | 7.013
| 2444 | 7.9796
| 2445 | 8.5789
| 2446 | 7.6844
| 2447 | 8.2732
| 2448 | 8.4918
| 2449 | 7.9621
| 2450 | 7.1918
| 2451 | 7.851
| 2452 | 7.7114
| 2453 | 7.5798
| 2454 | 7.2249
| 2455 | 6.8365
| 2456 | 6.5808
| 2457 | 6.6861
| 2458 | 6.5578
| 2459 | 7.4848
| 2460 | 7.4066
| 2461 | 7.3139
| 2462 | 8.79
| 2463 | 8.3312
| 2464 | 8.1362
| 2465 | 7.701
| 2466 | 6.7029
| 2467 | 7.8308
| 2468 | 7.8755
| 2469 | 7.6262
| 2470 | 8.0925
| 2471 | 7.0906
| 2472 | 8.2932
| 2473 | 7.6028
| 2474 | 7.8439
| 2475 | 8.3113
| 2476 | 7.7439
| 2477 | 8.4882
| 2478 | 7.692
| 2479 | 6.7705
| 2480 | 6.2441
| 2481 | 8.5964
| 2482 | 8.5043
| 2483 | 8.0302
| 2484 | 7.5868
| 2485 | 7.2644
| 2486 | 8.1933
| 2487 | 7.8292
| 2488 | 8.6755
| 2489 | 8.2114
| 2490 | 8.0237
| 2491 | 7.729
| 2492 | 7.7899
| 2493 | 7.1918
| 2494 | 8.8033
| 2495 | 7.6151
| 2496 | 7.4967
| 2497 | 7.7803
| 2498 | 8.0219
| 2499 | 7.5136
| 2500 | 7.8667
| 2501 | 7.9364
| 2502 | 7.5466
| 2503 | 7.5215
| 2504 | 8.31
| 2505 | 8.1478
| 2506 | 7.9096
| 2507 | 8.2645
| 2508 | 8.8441
| 2509 | 7.8155
| 2510 | 7.2194
| 2511 | 7.1898
| 2512 | 8.4676
| 2513 | 8.7988
| 2514 | 7.8155
| 2515 | 7.5045
| 2516 | 7.6295
| 2517 | 8.0028
| 2518 | 7.9246
| 2519 | 7.2639
| 2520 | 8.1085
| 2521 | 7.48
| 2522 | 7.7795
| 2523 | 8.5964
| 2524 | 8.5153
| 2525 | 7.4889
| 2526 | 7.7922
| 2527 | 8.6811
| 2528 | 8.2609
| 2529 | 7.2984
| 2530 | 7.5027
| 2531 | 8.2584
| 2532 | 7.5166
| 2533 | 7.6262
| 2534 | 8.0377
| 2535 | 8.554
| 2536 | 7.6269
| 2537 | 7.9347
| 2538 | 8.1352
| 2539 | 6.7045
| 2540 | 7.23
| 2541 | 7.8549
| 2542 | 7.6715
| 2543 | 8.4038
| 2544 | 8.79
| 2545 | 7.4032
| 2546 | 8.2322
| 2547 | 7.7533
| 2548 | 7.4854
| 2549 | 8.4642
| 2550 | 7.7411
| 2551 | 8.231
| 2552 | 7.8124
| 2553 | 7.0583
| 2554 | 7.5874
| 2555 | 8.1499
| 2556 | 8.5323
| 2557 | 7.9432
| 2558 | 8.4778
| 2559 | 8.4222
| 2560 | 7.2239
| 2561 | 8.717
| 2562 | 6.9976
| 2563 | 7.7795
| 2564 | 7.4848
| 2565 | 8.4253
| 2566 | 8.5304
| 2567 | 6.9161
| 2568 | 7.434
| 2569 | 7.8408
| 2570 | 8.0118
| 2571 | 7.1052
| 2572 | 7.6073
| 2573 | 7.6184
| 2574 | 7.969
| 2575 | 7.5678
| 2576 | 7.7936
| 2577 | 8.37
| 2578 | 7.6607
| 2579 | 7.6308
| 2580 | 7.7482
| 2581 | 8.5228
| 2582 | 7.1172
| 2583 | 7.9006
| 2584 | 7.6913
| 2585 | 8.5401
| 2586 | 7.3875
| 2587 | 6.9457
| 2588 | 6.1834
| 2589 | 8.2856
| 2590 | 8.5061
| 2591 | 8.3366
| 2592 | 7.7511
| 2593 | 7.3027
| 2594 | 6.7123
| 2595 | 8.5209
| 2596 | 8.7015
| 2597 | 8.4865
| 2598 | 7.2407
| 2599 | 8.4476
| 2600 | 7.2937
| 2601 | 8.0846
| 2602 | 8.6363
| 2603 | 8.8079
| 2604 | 8.3035
| 2605 | 8.2416
| 2606 | 7.5343
| 2607 | 8.0037
| 2608 | 8.2428
| 2609 | 7.4783
| 2610 | 8.2719
| 2611 | 7.1853
| 2612 | 7.6627
| 2613 | 7.8354
| 2614 | 7.3825
| 2615 | 8.2756
| 2616 | 7.8941
| 2617 | 7.9526
| 2618 | 7.9725
| 2619 | 8.0019
| 2620 | 6.9457
| 2621 | 8.2428
| 2622 | 7.8162
| 2623 | 8.1005
| 2624 | 7.0495
| 2625 | 8.8277
| 2626 | 8.4575
| 2627 | 8.2819
| 2628 | 8.2405
| 2629 | 7.8478
| 2630 | 7.9708
| 2631 | 8.0915
| 2632 | 7.2123
| 2633 | 8.544
| 2634 | 7.7163
| 2635 | 7.9992
| 2636 | 7.3675
| 2637 | 7.9213
| 2638 | 7.8246
| 2639 | 8.8692
| 2640 | 8.73
| 2641 | 7.9088
| 2642 | 7.5666
| 2643 | 7.4818
| 2644 | 8.0546
| 2645 | 8.2536
| 2646 | 7.2582
| 2647 | 7.5862
| 2648 | 6.8532
| 2649 | 7.6394
| 2650 | 8.0284
| 2651 | 7.4895
| 2652 | 8.0293
| 2653 | 8.0661
| 2654 | 8.4175
| 2655 | 7.9238
| 2656 | 7.9708
| 2657 | 8.55
| 2658 | 8.2264
| 2659 | 8.552
| 2660 | 8.7334
| 2661 | 8.5098
| 2662 | 7.0344
| 2663 | 8.8175
| 2664 | 7.5337
| 2665 | 8.1341
| 2666 | 7.8739
| 2667 | 8.1457
| 2668 | 7.976
| 2669 | 7.9526
| 2670 | 8.2719
| 2671 | 8.0461
| 2672 | 8.6009
| 2673 | 7.3155
| 2674 | 7.7439
| 2675 | 6.9985
| 2676 | 6.9317
| 2677 | 6.6039
| 2678 | 8.1779
| 2679 | 8.2524
| 2680 | 6.3917
| 2681 | 7.814
| 2682 | 7.1005
| 2683 | 8.3714
| 2684 | 7.8541
| 2685 | 7.8408
| 2686 | 7.6171
| 2687 | 8.3192
| 2688 | 8.1801
| 2689 | 8.7943
| 2690 | 7.9629
| 2691 | 6.7851
| 2692 | 8.3407
| 2693 | 7.7404
| 2694 | 8.7076
| 2695 | 7.251
| 2696 | 7.2947
| 2697 | 6.9695
| 2698 | 7.7773
| 2699 | 7.7562
| 2700 | 8.5401
| 2701 | 8.4364
| 2702 | 8.6289
| 2703 | 8.1573
| 2704 | 7.576
| 2705 | 8.1978
| 2706 | 8.3152
| 2707 | 8.383
| 2708 | 7.0376
| 2709 | 7.5741
| 2710 | 8.167
| 2711 | 8.5135
| 2712 | 7.7996
| 2713 | 8.0905
| 2714 | 8.5684
| 2715 | 7.7737
| 2716 | 7.6824
| 2717 | 8.0499
| 2718 | 6.5427
| 2719 | 8.1331
| 2720 | 7.3792
| 2721 | 7.5221
| 2722 | 7.6865
| 2723 | 7.5932
| 2724 | 7.7981
| 2725 | 8.6217
| 2726 | 7.9875
| 2727 | 6.6884
| 2728 | 7.2173
| 2729 | 8.7858
| 2730 | 7.5136
| 2731 | 8.0349
| 2732 | 8.2695
| 2733 | 6.6714
| 2734 | 8.3948
| 2735 | 8.0073
| 2736 | 7.1651
| 2737 | 7.8691
| 2738 | 7.8147
| 2739 | 7.1504
| 2740 | 7.6851
| 2741 | 8.556
| 2742 | 7.4747
| 2743 | 8.2882
| 2744 | 7.3037
| 2745 | 7.9638
| 2746 | 7.3192
| 2747 | 7.7454
| 2748 | 7.3588
| 2749 | 7.1631
| 2750 | 7.1779
| 2751 | 7.1978
| 2752 | 8.7107
| 2753 | 7.6858
| 2754 | 7.8941
| 2755 | 7.7311
| 2756 | 7.4961
| 2757 | 7.4688
| 2758 | 6.8641
| 2759 | 8.4364
| 2760 | 8.0896
| 2761 | 8.048
| 2762 | 7.5566
| 2763 | 8.0508
| 2764 | 7.4712
| 2765 | 8.4068
| 2766 | 8.2806
| 2767 | 7.4123
| 2768 | 7.0008
| 2769 | 8.3366
| 2770 | 6.9326
| 2771 | 8.6755
| 2772 | 8.6868
| 2773 | 6.6675
| 2774 | 7.7707
| 2775 | 7.8147
| 2776 | 7.3246
| 2777 | 7.0103
| 2778 | 8.1856
| 2779 | 7.6054
| 2780 | 7.5491
| 2781 | 8.6009
| 2782 | 7.3478
| 2783 | 8.7334
| 2784 | 6.7052
| 2785 | 8.3786
| 2786 | 7.4618
| 2787 | 8.0965
| 2788 | 8.167
| 2789 | 8.3339
| 2790 | 7.6256
| 2791 | 7.7361
| 2792 | 8.7858
| 2793 | 8.5642
| 2794 | 8.6363
| 2795 | 7.7332
| 2796 | 7.7678
| 2797 | 8.2707
| 2798 | 7.762
| 2799 | 8.2769
| 2800 | 7.2675
| 2801 | 8.2103
| 2802 | 7.8763
| 2803 | 8.1341
| 2804 | 7.5148
| 2805 | 7.5117
| 2806 | 7.8707
| 2807 | 8.0876
| 2808 | 8.3993
| 2809 | 6.8679
| 2810 | 6.5789
| 2811 | 8.438
| 2812 | 7.5874
| 2813 | 7.8588
| 2814 | 7.7149
| 2815 | 8.1065
| 2816 | 7.5033
| 2817 | 8.85
| 2818 | 8.3531
| 2819 | 7.648
| 2820 | 7.9047
| 2821 | 8.0671
| 2822 | 8.0876
| 2823 | 8.2357
| 2824 | 8.4364
| 2825 | 7.9039
| 2826 | 8.1834
| 2827 | 6.9079
| 2828 | 7.8612
| 2829 | 7.4919
| 2830 | 6.6729
| 2831 | 8.1605
| 2832 | 8.4348
| 2833 | 7.6989
| 2834 | 8.0237
| 2835 | 7.9398
| 2836 | 8.0807
| 2837 | 8.1146
| 2838 | 7.4117
| 2839 | 7.5722
| 2840 | 7.4426
| 2841 | 8.1248
| 2842 | 8.0201
| 2843 | 7.3954
| 2844 | 8.0237
| 2845 | 7.1675
| 2846 | 8.0935
| 2847 | 7.0532
| 2848 | 7.2806
| 2849 | 7.0606
| 2850 | 7.7128
| 2851 | 6.666
| 2852 | 8.2393
| 2853 | 8.0001
| 2854 | 8.79
| 2855 | 7.8385
| 2856 | 8.3113
| 2857 | 8.129
| 2858 | 7.038
| 2859 | 8.1911
| 2860 | 8.1531
| 2861 | 6.6002
| 2862 | 8.8175
| 2863 | 7.0765
| 2864 | 8.0575
| 2865 | 8.0642
| 2866 | 8.1922
| 2867 | 6.8084
| 2868 | 7.0431
| 2869 | 8.3743
| 2870 | 7.7729
| 2871 | 7.7447
| 2872 | 8.2584
| 2873 | 5.9236
| 2874 | 8.3139
| 2875 | 7.4123
| 2876 | 7.4771
| 2877 | 8.1616
| 2878 | 7.8755
| 2879 | 8.61
| 2880 | 7.8362
| 2881 | 8.0739
| 2882 | 8.3963
| 2883 | 7.5485
| 2884 | 8.0082
| 2885 | 8.2428
| 2886 | 7.1968
| 2887 | 7.5454
| 2888 | 7.8455
| 2889 | 7.9992
| 2890 | 8.1638
| 2891 | 7.0413
| 2892 | 8.231
| 2893 | 7.5666
| 2894 | 8.2346
| 2895 | 7.7996
| 2896 | 7.3283
| 2897 | 7.9902
| 2898 | 8.5854
| 2899 | 8.3657
| 2900 | 7.8004
| 2901 | 7.8965
| 2902 | 7.9474
| 2903 | 8.5898
| 2904 | 8.1467
| 2905 | 8.1096
| 2906 | 6.4261
| 2907 | 8.1541
| 2908 | 6.9235
| 2909 | 7.1291
| 2910 | 7.5805
| 2911 | 7.4397
| 2912 | 7.8239
| 2913 | 7.858
| 2914 | 7.2068
| 2915 | 8.2524
| 2916 | 8.0377
| 2917 | 5.7884
| 2918 | 7.1509
| 2919 | 8.2707
| 2920 | 7.9769
| 2921 | 8.3671
| 2922 | 7.5881
| 2923 | 7.7803
| 2924 | 7.3429
| 2925 | 7.8162
| 2926 | 6.8302
| 2927 | 8.2572
| 2928 | 8.1488
| 2929 | 7.5142
| 2930 | 8.2597
| 2931 | 7.7634
| 2932 | 8.3786
| 2933 | 7.8835
| 2934 | 7.3764
| 2935 | 7.438
| 2936 | 7.8884
| 2937 | 7.2613
| 2938 | 8.1136
| 2939 | 8.7508
| 2940 | 7.7425
| 2941 | 8.6985
| 2942 | 8.0729
| 2943 | 8.3434
| 2944 | 8.1096
| 2945 | 7.8787
| 2946 | 7.8463
| 2947 | 8.1801
| 2948 | 7.7418
| 2949 | 6.8047
| 2950 | 7.9778
| 2951 | 7.5983
| 2952 | 7.8699
| 2953 | 8.167
| 2954 | 7.5318
| 2955 | 7.9778
| 2956 | 7.3703
| 2957 | 8.4444
| 2958 | 7.9105
| 2959 | 7.3272
| 2960 | 7.3637
| 2961 | 7.4577
| 2962 | 7.6275
| 2963 | 7.7803
| 2964 | 8.4008
| 2965 | 8.4744
| 2966 | 7.3571
| 2967 | 7.1888
| 2968 | 7.9055
| 2969 | 8.0442
| 2970 | 8.3615
| 2971 | 7.4818
| 2972 | 7.9474
| 2973 | 8.2275
| 2974 | 7.1514
| 2975 | 7.3165
| 2976 | 8.1341
| 2977 | 8.2658
| 2978 | 7.3937
| 2979 | 7.7198
| 2980 | 7.1504
| 2981 | 7.0835
| 2982 | 7.5792
| 2983 | 7.6513
| 2984 | 8.8918
| 2985 | 8.3629
| 2986 | 7.8109
| 2987 | 7.703
| 2988 | 7.9449
| 2989 | 8.3192
| 2990 | 7.7707
| 2991 | 7.7656
| 2992 | 8.1394
| 2993 | 8.0671
| 2994 | 7.267
| 2995 | 7.84
| 2996 | 7.8369
| 2997 | 8.1075
| 2998 | 7.2093
| 2999 | 6.849
| 3000 | 8.179
| 3001 | 6.8708
| 3002 | 8.0856
| 3003 | 8.6727
| 3004 | 6.9633
| 3005 | 8.4175
| 3006 | 8.1616
| 3007 | 8.1713
| 3008 | 8.2357
| 3009 | 7.4901
| 3010 | 8.7267
| 3011 | 8.0758
| 3012 | 7.9163
| 3013 | 7.3747
| 3014 | 8.0423
| 3015 | 8.7816
| 3016 | 8.508
| 3017 | 8.0164
| 3018 | 8.1065
| 3019 | 7.8432
| 3020 | 8.3573
| 3021 | 7.9129
| 3022 | 8.0661
| 3023 | 8.0164
| 3024 | 7.7163
| 3025 | 7.8747
| 3026 | 8.6839
| 3027 | 8.2405
| 3028 | 8.5228
| 3029 | 8.152
| 3030 | 7.9893
| 3031 | 8.6839
| 3032 | 8.2856
| 3033 | 7.648
| 3034 | 7.3462
| 3035 | 7.356
| 3036 | 8.2907
| 3037 | 7.2103
| 3038 | 6.9501
| 3039 | 7.299
| 3040 | 7.9146
| 3041 | 8.6646
| 3042 | 7.8109
| 3043 | 8.0604
| 3044 | 7.0394
| 3045 | 7.6668
| 3046 | 7.0944
| 3047 | 8.5986
| 3048 | 8.0237
| 3049 | 8.552
| 3050 | 7.227
| 3051 | 7.5257
| 3052 | 7.0112
| 3053 | 7.2623
| 3054 | 6.3859
| 3055 | 6.8998
| 3056 | 8.3087
| 3057 | 7.8447
| 3058 | 7.1993
| 3059 | 8.3087
| 3060 | 8.0836
| 3061 | 7.7818
| 3062 | 8.6897
| 3063 | 8.717
| 3064 | 8.3393
| 3065 | 8.3339
| 3066 | 6.8908
| 3067 | 8.048
| 3068 | 7.8908
| 3069 | 8.2125
| 3070 | 7.9534
| 3071 | 8.5172
| 3072 | 7.4955
| 3073 | 7.5288
| 3074 | 8.2695
| 3075 | 7.5435
| 3076 | 7.5597
| 3077 | 8.5705
| 3078 | 7.5343
| 3079 | 7.6641
| 3080 | 8.552
| 3081 | 8.4412
| 3082 | 6.1299
| 3083 | 7.4038
| 3084 | 7.648
| 3085 | 8.5323
| 3086 | 7.308
| 3087 | 7.6527
| 3088 | 8.2524
| 3089 | 8.5663
| 3090 | 8.6868
| 3091 | 6.9828
| 3092 | 7.7389
| 3093 | 7.4765
| 3094 | 8.3686
| 3095 | 7.6763
| 3096 | 7.8628
| 3097 | 7.5584
| 3098 | 7.5792
| 3099 | 8.0925
| 3100 | 8.0452
| 3101 | 8.7015
| 3102 | 7.7884
| 3103 | 8.3166
| 3104 | 7.2727
| 3105 | 7.1306
| 3106 | 8.0461
| 3107 | 7.3544
| 3108 | 8.4476
| 3109 | 8.1681
| 3110 | 8.3407
| 3111 | 8.338
| 3112 | 7.8011
| 3113 | 8.292
| 3114 | 7.5491
| 3115 | 8.4206
| 3116 | 7.5417
| 3117 | 7.8565
| 3118 | 8.152
| 3119 | 7.8949
| 3120 | 8.5581
| 3121 | 8.5191
| 3122 | 7.3598
| 3123 | 8.2252
| 3124 | 8.1197
| 3125 | 8.556
| 3126 | 7.5773
| 3127 | 7.023
| 3128 | 8.5832
| 3129 | 7.7547
| 3130 | 8.2183
| 3131 | 8.1768
| 3132 | 8.1187
| 3133 | 7.1607
| 3134 | 7.4391
| 3135 | 8.438
| 3136 | 6.8742
| 3137 | 7.6473
| 3138 | 8.4509
| 3139 | 8.2882
| 3140 | 7.0098
| 3141 | 8.2023
| 3142 | 6.5931
| 3143 | 6.5241
| 3144 | 7.9483
| 3145 | 8.4813
| 3146 | 7.6354
| 3147 | 6.8561
| 3148 | 7.4955
| 3149 | 7.2889
| 3150 | 7.969
| 3151 | 7.9965
| 3152 | 7.5003
| 3153 | 8.85
| 3154 | 8.4191
| 3155 | 8.4206
| 3156 | 7.6688
| 3157 | 7.1162
| 3158 | 8.0768
| 3159 | 7.4624
| 3160 | 8.2322
| 3161 | 8.4144
| 3162 | 6.9011
| 3163 | 7.3942
| 3164 | 7.7914
| 3165 | 8.1845
| 3166 | 8.8561
| 3167 | 6.4356
| 3168 | 7.7086
| 3169 | 8.5116
| 3170 | 6.9731
| 3171 | 8.3531
| 3172 | 6.7644
| 3173 | 7.7832
| 3174 | 8.5343
| 3175 | 8.2996
| 3176 | 7.2048
| 3177 | 6.8125
| 3178 | 8.0146
| 3179 | 8.01
| 3180 | 6.7512
| 3181 | 7.59
| 3182 | 8.2393
| 3183 | 7.9884
| 3184 | 7.0261
| 3185 | 7.681
| 3186 | 8.3903
| 3187 | 8.5285
| 3188 | 7.3478
| 3189 | 7.7715
| 3190 | 7.5111
| 3191 | 8.3152
| 3192 | 8.3475
| 3193 | 7.6553
| 3194 | 8.4726
| 3195 | 7.9673
| 3196 | 6.5785
| 3197 | 8.3192
| 3198 | 7.2133
| 3199 | 8.4348
| 3200 | 7.3987
| 3201 | 7.7247
| 3202 | 7.3675
| 3203 | 7.7128
| 3204 | 7.0727
| 3205 | 8.4428
| 3206 | 7.0098
| 3207 | 8.6146
| 3208 | 8.5642
| 3209 | 8.0019
| 3210 | 7.5932
| 3211 | 6.9611
| 3212 | 7.8892
| 3213 | 8.1404
| 3214 | 7.8231
| 3215 | 8.0556
| 3216 | 7.8604
| 3217 | 8.4509
| 3218 | 8.49
| 3219 | 8.2597
| 3220 | 8.6646
| 3221 | 7.8667
| 3222 | 7.0121
| 3223 | 7.3588
| 3224 | 8.8838
| 3225 | 7.3096
| 3226 | 7.5559
| 3227 | 7.7981
| 3228 | 8.5061
| 3229 | 8.6897
| 3230 | 7.1858
| 3231 | 7.9313
| 3232 | 7.4328
| 3233 | 8.4476
| 3234 | 6.6426
| 3235 | 7.6288
| 3236 | 8.2334
| 3237 | 8.5581
| 3238 | 7.71
| 3239 | 7.3305
| 3240 | 8.7138
| 3241 | 6.1617
| 3242 | 7.5926
| 3243 | 6.7957
| 3244 | 7.9279
| 3245 | 7.5716
| 3246 | 7.9796
| 3247 | 8.5043
| 3248 | 7.9577
| 3249 | 7.9288
| 3250 | 8.0082
| 3251 | 7.8908
| 3252 | 7.3533
| 3253 | 6.5841
| 3254 | 8.0055
| 3255 | 6.8344
| 3256 | 7.8779
| 3257 | 8.216
| 3258 | 8.0749
| 3259 | 7.8771
| 3260 | 7.8424
| 3261 | 8.6054
| 3262 | 7.6242
| 3263 | 8.3948
| 3264 | 8.7775
| 3265 | 8.7138
| 3266 | 7.8416
| 3267 | 8.2125
| 3268 | 8.7267
| 3269 | 7.5245
| 3270 | 8.1425
| 3271 | 8.5153
| 3272 | 7.7497
| 3273 | 8.1259
| 3274 | 7.6493
| 3275 | 8.3352
| 3276 | 8.3559
| 3277 | 7.5887
| 3278 | 8.2781
| 3279 | 8.6009
| 3280 | 7.8285
| 3281 | 7.1534
| 3282 | 8.4953
| 3283 | 8.4396
| 3284 | 7.4134
| 3285 | 7.7951
| 3286 | 7.9655
| 3287 | 7.6708
| 3288 | 7.4077
| 3289 | 6.7814
| 3290 | 8.4918
| 3291 | 8.91
| 3292 | 7.267
| 3293 | 7.0523
| 3294 | 7.8981
| 3295 | 7.9929
| 3296 | 7.9121
| 3297 | 7.8502
| 3298 | 8.4659
| 3299 | 7.3343
| 3300 | 7.4961
| 3301 | 7.7347
| 3302 | 7.6587
| 3303 | 8.9329
| 3304 | 8.0155
| 3305 | 7.5288
| 3306 | 8.6265
| 3307 | 8.1055
| 3308 | 8.0256
| 3309 | 7.3326
| 3310 | 6.5737
| 3311 | 8.2732
| 3312 | 8.6463
| 3313 | 8.6363
| 3314 | 8.0508
| 3315 | 8.0302
| 3316 | 8.7402
| 3317 | 7.4583
| 3318 | 7.8811
| 3319 | 8.3531
| 3320 | 8.7138
| 3321 | 8.1627
| 3322 | 7.9673
| 3323 | 8.2068
| 3324 | 7.9664
| 3325 | 7.817
| 3326 | 8.2125
| 3327 | 7.8731
| 3328 | 8.6514
| 3329 | 7.9449
| 3330 | 8.1889
| 3331 | 8.8763
| 3332 | 7.9595
| 3333 | 7.8262
| 3334 | 8.0905
| 3335 | 6.5292
| 3336 | 7.4765
| 3337 | 7.9449
| 3338 | 8.7988
| 3339 | 7.1181
| 3340 | 7.6968
| 3341 | 8.13
| 3342 | 7.8455
| 3343 | 8.1075
| 3344 | 7.7079
| 3345 | 8.7045
| 3346 | 8.2068
| 3347 | 7.9474
| 3348 | 7.3213
| 3349 | 8.8918
| 3350 | 7.1267
| 3351 | 6.8461
| 3352 | 7.8393
| 3353 | 7.4478
| 3354 | 7.9983
| 3355 | 8.1552
| 3356 | 8.3087
| 3357 | 8.8277
| 3358 | 6.8599
| 3359 | 7.9586
| 3360 | 7.6354
| 3361 | 8.6265
| 3362 | 8.5964
| 3363 | 6.8972
| 3364 | 8.3601
| 3365 | 8.25
| 3366 | 8.7234
| 3367 | 7.8315
| 3368 | 8.3948
| 3369 | 7.3948
| 3370 | 8.1362
| 3371 | 7.4151
| 3372 | 7.3925
| 3373 | 7.4242
| 3374 | 7.6295
| 3375 | 7.6982
| 3376 | 8.0527
| 3377 | 8.4206
| 3378 | 7.5081
| 3379 | 7.5634
| 3380 | 7.8231
| 3381 | 7.3725
| 3382 | 7.3316
| 3383 | 8.3918
| 3384 | 8.8127
| 3385 | 7.1253
| 3386 | 6.9682
| 3387 | 7.8208
| 3388 | 7.8102
| 3389 | 8.4412
| 3390 | 8.4847
| 3391 | 8.5285
| 3392 | 6.2271
| 3393 | 8.61
| 3394 | 7.82
| 3395 | 8.2334
| 3396 | 7.5716
| 3397 | 8.4778
| 3398 | 7.2806
| 3399 | 7.899
| 3400 | 8.6463
| 3401 | 6.9717
| 3402 | 8.3339
| 3403 | 8.3074
| 3404 | 8.0055
| 3405 | 7.4753
| 3406 | 7.1057
| 3407 | 8.6811
| 3408 | 7.7297
| 3409 | 7.82
| 3410 | 8.2125
| 3411 | 7.9055
| 3412 | 7.9974
| 3413 | 6.9735
| 3414 | 8.6646
| 3415 | 7.8439
| 3416 | 7.3965
| 3417 | 8.3087
| 3418 | 7.1715
| 3419 | 8.2148
| 3420 | 8.2381
| 3421 | 6.94
| 3422 | 8.1187
| 3423 | 7.6661
| 3424 | 6.756
| 3425 | 8.9206
| 3426 | 8.3978
| 3427 | 7.6769
| 3428 | 7.8819
| 3429 | 7.6269
| 3430 | 7.1543
| 3431 | 8.1735
| 3432 | 8.0594
| 3433 | 7.6872
| 3434 | 8.2732
| 3435 | 7.7233
| 3436 | 8.3407
| 3437 | 8.0499
| 3438 | 7.5245
| 3439 | 8.0201
| 3440 | 7.3359
| 3441 | 7.9787
| 3442 | 8.1478
| 3443 | 7.9279
| 3444 | 8.5285
| 3445 | 7.4955
| 3446 | 8.6265
| 3447 | 8.0452
| 3448 | 7.9398
| 3449 | 8.0661
| 3450 | 7.8455
| 3451 | 6.9028
| 3452 | 8.1779
| 3453 | 8.1075
| 3454 | 6.7802
| 3455 | 7.2382
| 3456 | 8.4476
| 3457 | 8.5285
| 3458 | 8.0339
| 3459 | 7.1983
| 3460 | 8.001
| 3461 | 8.5209
| 3462 | 7.65
| 3463 | 7.1695
| 3464 | 7.7283
| 3465 | 8.6489
| 3466 | 7.5516
| 3467 | 7.2535
| 3468 | 6.87
| 3469 | 8.4008
| 3470 | 8.0633
| 3471 | 8.483
| 3472 | 7.2219
| 3473 | 7.2073
| 3474 | 7.5404
| 3475 | 8.3192
| 3476 | 7.8216
| 3477 | 8.3218
| 3478 | 7.3123
| 3479 | 7.546
| 3480 | 7.0784
| 3481 | 7.28
| 3482 | 7.7996
| 3483 | 8.4284
| 3484 | 7.5824
| 3485 | 8.4761
| 3486 | 6.6472
| 3487 | 7.9238
| 3488 | 8.2732
| 3489 | 7.5441
| 3490 | 8.0886
| 3491 | 7.9655
| 3492 | 7.899
| 3493 | 8.4428
| 3494 | 7.9263
| 3495 | 8.1757
| 3496 | 6.7904
| 3497 | 7.5932
| 3498 | 8.1823
| 3499 | 8.1259
| 3500 | 7.9238
| 3501 | 8.6009
| 3502 | 8.6314
| 3503 | 7.0486
| 3504 | 7.8315
| 3505 | 8.546
| 3506 | 7.6394
| 3507 | 7.5312
| 3508 | 7.6467
| 3509 | 7.6553
| 3510 | 8.3152
| 3511 | 8.5581
| 3512 | 7.8393
| 3513 | 7.7693
| 3514 | 8.3339
| 3515 | 8.2299
| 3516 | 8.5601
| 3517 | 7.3836
| 3518 | 8.3757
| 3519 | 8.3152
| 3520 | 8.7202
| 3521 | 8.7472
| 3522 | 8.4444
| 3523 | 7.2103
| 3524 | 6.7163
| 3525 | 6.351
| 3526 | 8.4284
| 3527 | 8.948
| 3528 | 7.4208
| 3529 | 7.3128
| 3530 | 8.3179
| 3531 | 8.948
| 3532 | 7.3213
| 3533 | 7.6354
| 3534 | 8.2719
| 3535 | 7.6941
| 3536 | 7.847
| 3537 | 7.3413
| 3538 | 7.5263
| 3539 | 7.6106
| 3540 | 7.754
| 3541 | 7.2587
| 3542 | 7.7128
| 3543 | 7.7751
| 3544 | 7.1636
| 3545 | 8.1845
| 3546 | 8.3874
| 3547 | 7.7135
| 3548 | 7.6844
| 3549 | 8.4542
| 3550 | 7.4432
| 3551 | 8.256
| 3552 | 7.9884
| 3553 | 7.5136
| 3554 | 8.0604
| 3555 | 8.49
| 3556 | 8.1259
| 3557 | 7.538
| 3558 | 8.4316
| 3559 | 6.6652
| 3560 | 6.7766
| 3561 | 7.5497
| 3562 | 8.0827
| 3563 | 7.984
| 3564 | 8.0623
| 3565 | 7.8354
| 3566 | 6.6498
| 3567 | 8.5726
| 3568 | 8.01
| 3569 | 6.7238
| 3570 | 8.4726
| 3571 | 8.5025
| 3572 | 7.7944
| 3573 | 8.2464
| 3574 | 7.3495
| 3575 | 7.5124
| 3576 | 8.2012
| 3577 | 8.1724
| 3578 | 7.2995
| 3579 | 7.0084
| 3580 | 8.0896
| 3581 | 6.8481
| 3582 | 7.9457
| 3583 | 7.9849
| 3584 | 8.438
| 3585 | 6.5719
| 3586 | 8.267
| 3587 | 7.2525
| 3588 | 7.6934
| 3589 | 8.5964
| 3590 | 8.5191
| 3591 | 8.0274
| 3592 | 7.7555
| 3593 | 8.0237
| 3594 | 6.8921
| 3595 | 8.1978
| 3596 | 8.2125
| 3597 | 7.0704
| 3598 | 6.7512
| 3599 | 8.8561
| 3600 | 7.1219
| 3601 | 8.3657
| 3602 | 8.5285
| 3603 | 7.8572
| 3604 | 7.5497
| 3605 | 8.1967
| 3606 | 8.5986
| 3607 | 8.2452
| 3608 | 8.1922
| 3609 | 6.4021
| 3610 | 8.1563
| 3611 | 6.8427
| 3612 | 8.8625
| 3613 | 6.9655
| 3614 | 8.3061
| 3615 | 7.89
| 3616 | 7.0505
| 3617 | 6.4809
| 3618 | 8.0797
| 3619 | 8.0876
| 3620 | 8.5025
| 3621 | 8.5789
| 3622 | 7.538
| 3623 | 7.1417
| 3624 | 7.6934
| 3625 | 8.3489
| 3626 | 7.7163
| 3627 | 8.1146
| 3628 | 8.7472
| 3629 | 8.2393
| 3630 | 8.1945
| 3631 | 8.3859
| 3632 | 7.8819
| 3633 | 7.4236
| 3634 | 7.7058
| 3635 | 8.6438
| 3636 | 7.2295
| 3637 | 7.2392
| 3638 | 7.8178
| 3639 | 7.7678
| 3640 | 7.5233
| 3641 | 8.4542
| 3642 | 7.8628
| 3643 | 7.0859
| 3644 | 6.6062
| 3645 | 7.6467
| 3646 | 8.3845
| 3647 | 8.3048
| 3648 | 7.9022
| 3649 | 7.0854
| 3650 | 8.0935
| 3651 | 8.5789
| 3652 | 8.2369
| 3653 | 7.6756
| 3654 | 8.2844
| 3655 | 7.5919
| 3656 | 7.5429
| 3657 | 8.3272
| 3658 | 7.7914
| 3659 | 7.5874
| 3660 | 7.6067
| 3661 | 8.2971
| 3662 | 7.8957
| 3663 | 7.5178
| 3664 | 7.5647
| 3665 | 6.7376
| 3666 | 8.4269
| 3667 | 7.5926
| 3668 | 7.9389
| 3669 | 7.7079
| 3670 | 8.2023
| 3671 | 7.9406
| 3672 | 8.3009
| 3673 | 8.152
| 3674 | 8.4953
| 3675 | 7.851
| 3676 | 7.3615
| 3677 | 8.3743
| 3678 | 7.9121
| 3679 | 6.444
| 3680 | 7.8998
| 3681 | 8.4744
| 3682 | 6.7669
| 3683 | 7.3914
| 3684 | 7.6145
| 3685 | 8.1746
| 3686 | 7.0257
| 3687 | 8.2023
| 3688 | 7.4197
| 3689 | 7.7627
| 3690 | 8.438
| 3691 | 7.8949
| 3692 | 8.3205
| 3693 | 6.6277
| 3694 | 6.7432
| 3695 | 7.7177
| 3696 | 8.5642
| 3697 | 7.6256
| 3698 | 8.5382
| 3699 | 7.6961
| 3700 | 7.3709
| 3701 | 6.9887
| 3702 | 8.4642
| 3703 | 8.3643
| 3704 | 8.0173
| 3705 | 6.5637
| 3706 | 8.4068
| 3707 | 8.4953
| 3708 | 8.1724
| 3709 | 7.9457
| 3710 | 8.3545
| 3711 | 6.7111
| 3712 | 8.0797
| 3713 | 7.858
| 3714 | 7.5282
| 3715 | 8.6077
| 3716 | 8.1156
| 3717 | 8.3503
| 3718 | 8.0442
| 3719 | 6.7325
| 3720 | 7.6838
| 3721 | 8.4935
| 3722 | 8.0256
| 3723 | 8.1383
| 3724 | 7.7722
| 3725 | 7.1913
| 3726 | 7.1744
| 3727 | 8.1207
| 3728 | 8.1878
| 3729 | 8.1025
| 3730 | 7.2566
| 3731 | 7.4794
| 3732 | 7.9725
| 3733 | 8.0719
| 3734 | 8.7816
| 3735 | 8.3272
| 3736 | 6.744
| 3737 | 6.8887
| 3738 | 7.8747
| 3739 | 8.6897
| 3740 | 7.2063
| 3741 | 7.8965
| 3742 | 6.4913
| 3743 | 6.5994
| 3744 | 8.2512
| 3745 | 8.0613
| 3746 | 6.9788
| 3747 | 7.5245
| 3748 | 7.2053
| 3749 | 6.3139
| 3750 | 6.9891
| 3751 | 6.7084
| 3752 | 7.8549
| 3753 | 8.5382
| 3754 | 8.8079
| 3755 | 7.4525
| 3756 | 7.9483
| 3757 | 7.7555
| 3758 | 8.208
| 3759 | 7.6099
| 3760 | 8.6031
| 3761 | 8.1989
| 3762 | 6.9304
| 3763 | 7.7142
| 3764 | 8.7402
| 3765 | 8.6926
| 3766 | 8.0778
| 3767 | 7.6301
| 3768 | 8.7402
| 3769 | 7.4554
| 3770 | 7.1441
| 3771 | 8.1823
| 3772 | 7.6282
| 3773 | 7.7511
| 3774 | 7.8385
| 3775 | 7.9347
| 3776 | 8.129
| 3777 | 7.0542
| 3778 | 8.4444
| 3779 | 8.1321
| 3780 | 8.1218
| 3781 | 7.8393
| 3782 | 7.0882
| 3783 | 8.9005
| 3784 | 8.0985
| 3785 | 8.0758
| 3786 | 7.8019
| 3787 | 7.0991
| 3788 | 7.7389
| 3789 | 7.3664
| 3790 | 8.2645
| 3791 | 8.3339
| 3792 | 7.0972
| 3793 | 8.0395
| 3794 | 8.4761
| 3795 | 6.1491
| 3796 | 7.5666
| 3797 | 7.6947
| 3798 | 7.3914
| 3799 | 7.0542
| 3800 | 8.4083
| 3801 | 7.0667
| 3802 | 7.8323
| 3803 | 8.7202
| 3804 | 7.1804
| 3805 | 7.1641
| 3806 | 8.2264
| 3807 | 8.548
| 3808 | 8.6673
| 3809 | 8.7267
| 3810 | 7.4759
| 3811 | 8.2171
| 3812 | 8.2275
| 3813 | 8.244
| 3814 | 8.0652
| 3815 | 8.4526
| 3816 | 8.3948
| 3817 | 7.0986
| 3818 | 6.836
| 3819 | 8.3407
| 3820 | 8.3366
| 3821 | 7.6927
| 3822 | 8.5964
| 3823 | 7.7929
| 3824 | 7.6621
| 3825 | 6.8398
| 3826 | 8.43
| 3827 | 7.992
| 3828 | 7.2868
| 3829 | 7.1062
| 3830 | 8.3559
| 3831 | 7.9432
| 3832 | 7.5672
| 3833 | 7.9612
| 3834 | 7.3208
| 3835 | 7.862
| 3836 | 7.7707
| 3837 | 8.1352
| 3838 | 8.0807
| 3839 | 7.316
| 3840 | 8.7368
| 3841 | 6.5659
| 3842 | 8.5007
| 3843 | 8.6955
| 3844 | 7.3085
| 3845 | 8.4953
| 3846 | 7.681
| 3847 | 7.5215
| 3848 | 7.7461
| 3849 | 7.406
| 3850 | 7.1582
| 3851 | 7.8094
| 3852 | 8.4575
| 3853 | 6.7404
| 3854 | 8.1005
| 3855 | 8.5726
| 3856 | 6.9967
| 3857 | 7.8699
| 3858 | 8.6363
| 3859 | 7.1948
| 3860 | 7.9849
| 3861 | 8.2707
| 3862 | 7.5202
| 3863 | 6.7524
| 3864 | 8.6489
| 3865 | 8.546
| 3866 | 7.9769
| 3867 | 7.6151
| 3868 | 7.2382
| 3869 | 8.224
| 3870 | 6.9806
| 3871 | 8.0613
| 3872 | 8.5705
| 3873 | 8.2524
| 3874 | 8.167
| 3875 | 7.3637
| 3876 | 8.4332
| 3877 | 8.8079
| 3878 | 8.2894
| 3879 | 8.6566
| 3880 | 8.1197
| 3881 | 7.7475
| 3882 | 8.6727
| 3883 | 7.2315
| 3884 | 7.6913
| 3885 | 8.5191
| 3886 | 7.9804
| 3887 | 8.9206
| 3888 | 7.7899
| 3889 | 7.1779
| 3890 | 8.2299
| 3891 | 8.1724
| 3892 | 7.7663
| 3893 | 7.5148
| 3894 | 8.2584
| 3895 | 7.8731
| 3896 | 6.7214
| 3897 | 7.4004
| 3898 | 7.8628
| 3899 | 7.9992
| 3900 | 7.8892
| 3901 | 7.9279
| 3902 | 7.4197
| 3903 | 7.397
| 3904 | 8.0109
| 3905 | 8.8625
| 3906 | 7.7737
| 3907 | 7.9483
| 3908 | 7.9734
| 3909 | 8.7858
| 3910 | 6.7285
| 3911 | 7.3064
| 3912 | 7.453
| 3913 | 7.2163
| 3914 | 7.0882
| 3915 | 7.2244
| 3916 | 7.749
| 3917 | 6.6205
| 3918 | 7.2356
| 3919 | 8.0661
| 3920 | 7.8447
| 3921 | 8.1126
| 3922 | 7.7051
| 3923 | 7.5522
| 3924 | 6.9735
| 3925 | 8.0405
| 3926 | 7.6865
| 3927 | 7.9743
| 3928 | 8.3139
| 3929 | 7.8026
| 3930 | 7.6256
| 3931 | 8.8838
| 3932 | 8.5401
| 3933 | 7.5566
| 3934 | 8.1845
| 3935 | 8.654
| 3936 | 6.9339
| 3937 | 7.6427
| 3938 | 7.5584
| 3939 | 8.1025
| 3940 | 7.9956
| 3941 | 8.2844
| 3942 | 6.8043
| 3943 | 8.4625
| 3944 | 6.4021
| 3945 | 6.7847
| 3946 | 8.1457
| 3947 | 8.438
| 3948 | 8.1279
| 3949 | 7.5251
| 3950 | 7.5404
| 3951 | 7.9006
| 3952 | 8.7508
| 3953 | 8.2137
| 3954 | 8.7107
| 3955 | 8.3993
| 3956 | 8.1279
| 3957 | 7.3875
| 3958 | 8.5304
| 3959 | 8.5421
| 3960 | 8.2369
| 3961 | 7.1744
| 3962 | 7.9621
| 3963 | 7.6427
| 3964 | 8.2869
| 3965 | 7.6722
| 3966 | 6.8645
| 3967 | 6.4156
| 3968 | 7.2315
| 3969 | 7.8478
| 3970 | 8.6727
| 3971 | 8.5768
| 3972 | 8.4444
| 3973 | 8.4493
| 3974 | 8.3285
| 3975 | 7.4635
| 3976 | 8.1713
| 3977 | 7.2469
| 3978 | 7.4712
| 3979 | 7.0371
| 3980 | 7.851
| 3981 | 8.1197
| 3982 | 8.2416
| 3983 | 8.1595
| 3984 | 7.4351
| 3985 | 7.044
| 3986 | 8.3993
| 3987 | 8.7045
| 3988 | 8.3859
| 3989 | 7.1626
| 3990 | 6.523
| 3991 | 7.4507
| 3992 | 7.5208
| 3993 | 6.9779
| 3994 | 7.46
| 3995 | 7.0271
| 3996 | 8.0442
| 3997 | 7.3133
| 3998 | 7.5767
| 3999 | 8.4053
| 4000 | 8.3757
| 4001 | 7.442
| 4002 | 8.6926
| 4003 | 8.0182
| 4004 | 8.5705
| 4005 | 8.0046
| 4006 | 7.8124
| 4007 | 7.652
| 4008 | 8.2488
| 4009 | 8.3139
| 4010 | 7.1364
| 4011 | 8.6438
| 4012 | 8.0423
| 4013 | 7.0491
| 4014 | 7.9389
| 4015 | 7.4991
| 4016 | 7.2013
| 4017 | 8.6265
| 4018 | 8.0556
| 4019 | 8.0594
| 4020 | 8.3801
| 4021 | 7.9974
| 4022 | 8.4918
| 4023 | 8.1259
| 4024 | 7.2942
| 4025 | 8.1404
| 4026 | 7.2063
| 4027 | 8.2183
| 4028 | 7.2649
| 4029 | 7.6321
| 4030 | 7.5374
| 4031 | 7.513
| 4032 | 7.781
| 4033 | 8.7267
| 4034 | 8.1989
| 4035 | 7.018
| 4036 | 6.958
| 4037 | 7.8041
| 4038 | 8.2984
| 4039 | 8.4222
| 4040 | 6.4282
| 4041 | 6.333
| 4042 | 8.7775
| 4043 | 6.8607
| 4044 | 8.4659
| 4045 | 7.2018
| 4046 | 7.6574
| 4047 | 7.0491
| 4048 | 8.2114
| 4049 | 8.7472
| 4050 | 6.8294
| 4051 | 7.9552
| 4052 | 8.0228
| 4053 | 8.3517
| 4054 | 7.5045
| 4055 | 8.2148
| 4056 | 8.8384
| 4057 | 7.7781
| 4058 | 8.4542
| 4059 | 7.7547
| 4060 | 7.4214
| 4061 | 6.4289
| 4062 | 7.0021
| 4063 | 7.8385
| 4064 | 7.8908
| 4065 | 8.546
| 4066 | 7.6892
| 4067 | 8.6031
| 4068 | 6.4877
| 4069 | 7.8155
| 4070 | 8.2194
| 4071 | 8.8225
| 4072 | 7.9188
| 4073 | 7.2953
| 4074 | 7.4191
| 4075 | 7.2979
| 4076 | 7.1349
| 4077 | 6.911
| 4078 | 6.9127
| 4079 | 7.1893
| 4080 | 7.8572
| 4081 | 7.0741
| 4082 | 8.1812
| 4083 | 7.7737
| 4084 | 8.1812
| 4085 | 7.648
| 4086 | 7.6776
| 4087 | 8.3462
| 4088 | 8.3978
| 4089 | 7.5926
| 4090 | 7.279
| 4091 | 8.5986
| 4092 | 7.1759
| 4093 | 7.4919
| 4094 | 7.1568
| 4095 | 8.3462
| 4096 | 8.4744
| 4097 | 7.7907
| 4098 | 7.9457
| 4099 | 8.6031
| 4100 | 8.071
| 4101 | 8.1702
| 4102 | 7.7722
| 4103 | 8.1218
| 4104 | 8.4971
| 4105 | 7.401
| 4106 | 8.1045
| 4107 | 7.9822
| 4108 | 7.7212
| 4109 | 8.5747
| 4110 | 8.2023
| 4111 | 7.597
| 4112 | 7.5221
| 4113 | 7.1813
| 4114 | 7.6803
| 4115 | 7.5392
| 4116 | 8.5191
| 4117 | 8.3325
| 4118 | 8.3918
| 4119 | 7.069
| 4120 | 8.3729
| 4121 | 6.7928
| 4122 | 7.8644
| 4123 | 7.7325
| 4124 | 7.9822
| 4125 | 7.6433
| 4126 | 7.2686
| 4127 | 7.8659
| 4128 | 8.2287
| 4129 | 7.6041
| 4130 | 7.9146
| 4131 | 7.3123
| 4132 | 8.2346
| 4133 | 8.0527
| 4134 | 8.0925
| 4135 | 8.3285
| 4136 | 7.5685
| 4137 | 8.3615
| 4138 | 7.6749
| 4139 | 7.8362
| 4140 | 8.6839
| 4141 | 7.1828
| 4142 | 8.2806
| 4143 | 8.0508
| 4144 | 8.5025
| 4145 | 8.6514
| 4146 | 7.5099
| 4147 | 8.4953
| 4148 | 7.4322
| 4149 | 8.2844
| 4150 | 7.9423
| 4151 | 8.1945
| 4152 | 7.2916
| 4153 | 7.7219
| 4154 | 7.899
| 4155 | 7.7989
| 4156 | 7.5221
| 4157 | 8.5876
| 4158 | 7.7212
| 4159 | 7.6262
| 4160 | 7.8354
| 4161 | 8.4114
| 4162 | 8.0405
| 4163 | 8.4493
| 4164 | 8.5942
| 4165 | 7.9893
| 4166 | 8.5247
| 4167 | 7.0981
| 4168 | 7.8835
| 4169 | 8.5153
| 4170 | 7.6099
| 4171 | 7.8094
| 4172 | 7.8362
| 4173 | 7.8851
| 4174 | 8.5789
| 4175 | 8.0661
| 4176 | 8.2932
| 4177 | 8.4971
| 4178 | 6.6667
| 4179 | 8.1096
| 4180 | 7.8843
| 4181 | 6.7496
| 4182 | 6.9444
| 4183 | 7.3987
| 4184 | 7.6301
| 4185 | 7.9664
| 4186 | 8.0118
| 4187 | 7.9072
| 4188 | 7.232
| 4189 | 7.4282
| 4190 | 8.0136
| 4191 | 7.717
| 4192 | 8.5747
| 4193 | 8.7234
| 4194 | 6.9624
| 4195 | 8.3352
| 4196 | 8.7988
| 4197 | 8.1238
| 4198 | 7.6467
| 4199 | 7.4334
| 4200 | 7.7205
| 4201 | 8.048
| 4202 | 7.8362
| 4203 | 8.6839
| 4204 | 8.97
| 4205 | 8.7402
| 4206 | 7.621
| 4207 | 7.2932
| 4208 | 7.53
| 4209 | 8.1552
| 4210 | 7.3858
| 4211 | 8.2194
| 4212 | 8.0182
| 4213 | 7.4682
| 4214 | 8.3325
| 4215 | 8.2148
| 4216 | 8.1005
| 4217 | 7.3364
| 4218 | 8.8692
| 4219 | 8.0797
| 4220 | 7.9347
| 4221 | 8.4237
| 4222 | 8.4008
| 4223 | 7.3703
| 4224 | 8.001
| 4225 | 7.7233
| 4226 | 7.4305
| 4227 | 8.4098
| 4228 | 8.5663
| 4229 | 8.7988
| 4230 | 8.2732
| 4231 | 7.7547
| 4232 | 7.0216
| 4233 | 8.2381
| 4234 | 8.3801
| 4235 | 7.5404
| 4236 | 7.7361
| 4237 | 6.638
| 4238 | 8.4971
| 4239 | 7.2853
| 4240 | 8.0146
| 4241 | 8.4813
| 4242 | 8.4364
| 4243 | 7.6547
| 4244 | 8.948
| 4245 | 8.0836
| 4246 | 7.9221
| 4247 | 8.2488
| 4248 | 7.4866
| 4249 | 7.2376
| 4250 | 7.8707
| 4251 | 8.2894
| 4252 | 7.8981
| 4253 | 8.508
| 4254 | 6.8112
| 4255 | 6.4289
| 4256 | 6.817
| 4257 | 8.833
| 4258 | 6.917
| 4259 | 7.1893
| 4260 | 7.0357
| 4261 | 7.6106
| 4262 | 7.2336
| 4263 | 7.4589
| 4264 | 8.0778
| 4265 | 7.3976
| 4266 | 7.5703
| 4267 | 8.3325
| 4268 | 7.8843
| 4269 | 7.7404
| 4270 | 7.7191
| 4271 | 8.0661
| 4272 | 8.3815
| 4273 | 7.7914
| 4274 | 8.3434
| 4275 | 8.1648
| 4276 | 8.3772
| 4277 | 8.0109
| 4278 | 7.9526
| 4279 | 8.8127
| 4280 | 7.8998
| 4281 | 7.7332
| 4282 | 8.1415
| 4283 | 8.7015
| 4284 | 7.0672
| 4285 | 7.4759
| 4286 | 8.6985
| 4287 | 8.0073
| 4288 | 7.5906
| 4289 | 7.2018
| 4290 | 8.179
| 4291 | 7.8651
| 4292 | 8.3918
| 4293 | 7.5522
| 4294 | 8.4284
| 4295 | 7.0225
| 4296 | 8.0228
| 4297 | 7.1739
| 4298 | 8.4575
| 4299 | 7.3495
| 4300 | 7.66
| 4301 | 8.6146
| 4302 | 7.7261
| 4303 | 8.7334
| 4304 | 6.6013
| 4305 | 7.4889
| 4306 | 7.7989
| 4307 | 7.9595
| 4308 | 8.3531
| 4309 | 7.0376
| 4310 | 7.5454
| 4311 | 7.2402
| 4312 | 7.4937
| 4313 | 8.224
| 4314 | 8.0302
| 4315 | 7.7966
| 4316 | 8.6438
| 4317 | 8.0414
| 4318 | 8.5153
| 4319 | 7.9725
| 4320 | 8.548
| 4321 | 7.6028
| 4322 | 8.7107
| 4323 | 7.3091
| 4324 | 7.5641
| 4325 | 7.9398
| 4326 | 7.1014
| 4327 | 7.486
| 4328 | 7.9263
| 4329 | 8.5043
| 4330 | 8.1055
| 4331 | 7.7432
| 4332 | 6.9084
| 4333 | 7.0189
| 4334 | 7.9221
| 4335 | 8.1978
| 4336 | 8.6217
| 4337 | 8.3772
| 4338 | 7.5678
| 4339 | 7.5184
| 4340 | 7.3112
| 4341 | 7.6407
| 4342 | 8.7696
| 4343 | 7.4027
| 4344 | 7.2143
| 4345 | 8.0274
| 4346 | 7.6681
| 4347 | 7.597
| 4348 | 8.3948
| 4349 | 8.4206
| 4350 | 8.338
| 4351 | 7.1646
| 4352 | 7.5154
| 4353 | 7.7562
| 4354 | 7.7191
| 4355 | 7.7389
| 4356 | 7.6715
| 4357 | 7.387
| 4358 | 7.8892
| 4359 | 7.134
| 4360 | 8.1595
| 4361 | 7.0266
| 4362 | 7.5318
| 4363 | 8.5116
| 4364 | 8.3434
| 4365 | 8.4114
| 4366 | 7.7547
| 4367 | 7.7107
| 4368 | 7.3
| 4369 | 8.13
| 4370 | 8.1457
| 4371 | 8.2512
| 4372 | 7.5404
| 4373 | 8.3407
| 4374 | 7.1105
| 4375 | 6.4444
| 4376 | 8.0965
| 4377 | 7.6975
| 4378 | 8.1005
| 4379 | 7.7576
| 4380 | 6.8494
| 4381 | 7.4548
| 4382 | 8.3218
| 4383 | 7.9664
| 4384 | 8.5172
| 4385 | 7.5233
| 4386 | 7.9389
| 4387 | 7.7627
| 4388 | 8.1605
| 4389 | 8.1436
| 4390 | 8.3978
| 4391 | 7.8331
| 4392 | 8.1075
| 4393 | 8.7581
| 4394 | 8.1735
| 4395 | 7.6654
| 4396 | 8.4083
| 4397 | 8.3152
| 4398 | 7.8779
| 4399 | 7.3348
| 4400 | 8.2536
| 4401 | 8.3743
| 4402 | 7.5075
| 4403 | 7.8147
| 4404 | 8.1945
| 4405 | 8.9329
| 4406 | 7.4049
| 4407 | 7.8019
| 4408 | 7.814
| 4409 | 7.8941
| 4410 | 8.1457
| 4411 | 7.8924
| 4412 | 7.8596
| 4413 | 7.5276
| 4414 | 7.028
| 4415 | 6.8294
| 4416 | 7.1983
| 4417 | 7.8369
| 4418 | 7.6433
| 4419 | 8.3366
| 4420 | 8.5343
| 4421 | 7.5578
| 4422 | 8.0046
| 4423 | 8.1779
| 4424 | 7.6879
| 4425 | 7.4231
| 4426 | 7.8231
| 4427 | 8.0556
| 4428 | 8.4865
| 4429 | 8.3232
| 4430 | 7.9096
| 4431 | 7.908
| 4432 | 8.49
| 4433 | 7.9014
| 4434 | 7.908
| 4435 | 7.12
| 4436 | 7.1124
| 4437 | 8.1933
| 4438 | 7.4729
| 4439 | 8.0546
| 4440 | 8.948
| 4441 | 8.5007
| 4442 | 8.5642
| 4443 | 8.7696
| 4444 | 7.3451
| 4445 | 7.8315
| 4446 | 6.7159
| 4447 | 7.1948
| 4448 | 6.9071
| 4449 | 7.7304
| 4450 | 7.5528
| 4451 | 7.6487
| 4452 | 7.3687
| 4453 | 8.1116
| 4454 | 8.2488
| 4455 | 6.6575
| 4456 | 8.4332
| 4457 | 8.1436
| 4458 | 8.0546
| 4459 | 7.4783
| 4460 | 7.1456
| 4461 | 7.8049
| 4462 | 7.7382
| 4463 | 8.2322
| 4464 | 8.5191
| 4465 | 7.9055
| 4466 | 8.2381
| 4467 | 8.4813
| 4468 | 7.2597
| 4469 | 7.7533
| 4470 | 8.7202
| 4471 | 7.6099
| 4472 | 7.2158
| 4473 | 7.8835
| 4474 | 7.7707
| 4475 | 8.8175
| 4476 | 6.9585
| 4477 | 8.179
| 4478 | 6.5071
| 4479 | 7.7037
| 4480 | 7.0713
| 4481 | 8.4038
| 4482 | 7.7037
| 4483 | 7.48
| 4484 | 7.267
| 4485 | 7.6119
| 4486 | 8.3192
| 4487 | 8.5172
| 4488 | 7.9911
| 4489 | 7.0625
| 4490 | 8.2524
| 4491 | 7.3692
| 4492 | 7.7468
| 4493 | 7.1769
| 4494 | 7.814
| 4495 | 8.4476
| 4496 | 8.1922
| 4497 | 8.6783
| 4498 | 7.7818
| 4499 | 8.7735
| 4500 | 8.6289
| 4501 | 8.7472
| 4502 | 6.9218
| 4503 | 8.2682
| 4504 | 7.0658
| 4505 | 7.9129
| 4506 | 7.4777
| 4507 | 7.5178
| 4508 | 7.8478
| 4509 | 7.9769
| 4510 | 8.0423
| 4511 | 8.6811
| 4512 | 7.0593
| 4513 | 8.3218
| 4514 | 7.64
| 4515 | 7.6242
| 4516 | 8.2984
| 4517 | 8.5854
| 4518 | 6.1962
| 4519 | 7.8998
| 4520 | 7.9229
| 4521 | 8.8175
| 4522 | 7.5983
| 4523 | 7.6627
| 4524 | 7.5926
| 4525 | 7.2275
| 4526 | 8.033
| 4527 | 7.3648
| 4528 | 8.1989
| 4529 | 8.5811
| 4530 | 8.25
| 4531 | 8.4129
| 4532 | 6.9602
| 4533 | 6.9032
| 4534 | 8.4744
| 4535 | 7.5288
| 4536 | 7.4214
| 4537 | 7.6824
| 4538 | 7.2895
| 4539 | 7.1973
| 4540 | 7.7951
| 4541 | 7.8071
| 4542 | 7.4128
| 4543 | 8.1735
| 4544 | 8.2034
| 4545 | 8.4023
| 4546 | 8.3963
| 4547 | 8.0681
| 4548 | 8.0164
| 4549 | 7.1818
| 4550 | 8.1025
| 4551 | 7.8636
| 4552 | 7.4322
| 4553 | 7.003
| 4554 | 8.8384
| 4555 | 7.6361
| 4556 | 8.7581
| 4557 | 7.5136
| 4558 | 7.5441
| 4559 | 7.2489
| 4560 | 8.2357
| 4561 | 8.6413
| 4562 | 8.3963
| 4563 | 7.8277
| 4564 | 7.2686
| 4565 | 7.9188
| 4566 | 8.7657
| 4567 | 7.5117
| 4568 | 8.2217
| 4569 | 8.2609
| 4570 | 7.9638
| 4571 | 8.1065
| 4572 | 7.4094
| 4573 | 8.4284
| 4574 | 7.6216
| 4575 | 8.9329
| 4576 | 8.0652
| 4577 | 8.3503
| 4578 | 8.0155
| 4579 | 8.617
| 4580 | 7.8683
| 4581 | 8.2369
| 4582 | 8.2536
| 4583 | 7.5945
| 4584 | 7.8908
| 4585 | 7.7759
| 4586 | 8.1735
| 4587 | 8.1573
| 4588 | 7.7526
| 4589 | 7.6735
| 4590 | 7.9457
| 4591 | 7.5547
| 4592 | 8.6217
| 4593 | 7.6715
| 4594 | 7.3825
| 4595 | 8.7544
| 4596 | 8.3152
| 4597 | 7.7788
| 4598 | 8.3587
| 4599 | 8.4761
| 4600 | 7.3511
| 4601 | 8.508
| 4602 | 8.2046
| 4603 | 6.4599
| 4604 | 8.0055
| 4605 | 8.5898
| 4606 | 8.129
| 4607 | 8.2217
| 4608 | 8.1967
| 4609 | 7.1398
| 4610 | 7.3516
| 4611 | 8.4269
| 4612 | 6.9075
| 4613 | 7.5811
| 4614 | 8.6755
| 4615 | 7.858
| 4616 | 8.3325
| 4617 | 8.2264
| 4618 | 7.2795
| 4619 | 7.8628
| 4620 | 8.1584
| 4621 | 8.0367
| 4622 | 7.7086
| 4623 | 6.9585
| 4624 | 7.4089
| 4625 | 7.3353
| 4626 | 8.2046
| 4627 | 8.267
| 4628 | 7.4653
| 4629 | 8.4269
| 4630 | 8.4038
| 4631 | 8.0164
| 4632 | 8.3352
| 4633 | 8.2488
| 4634 | 7.4812
| 4635 | 7.5215
| 4636 | 8.0001
| 4637 | 8.4778
| 4638 | 6.9922
| 4639 | 6.6764
| 4640 | 8.1823
| 4641 | 8.5601
| 4642 | 7.6308
| 4643 | 8.0758
| 4644 | 7.4513
| 4645 | 8.6146
| 4646 | 8.3113
| 4647 | 8.6241
| 4648 | 8.2958
| 4649 | 7.3337
| 4650 | 7.976
| 4651 | 8.5705
| 4652 | 8.2831
| 4653 | 7.1296
| 4654 | 7.6975
| 4655 | 8.2984
| 4656 | 8.2137
| 4657 | 8.3074
| 4658 | 7.3467
| 4659 | 8.3462
| 4660 | 8.6811
| 4661 | 7.3048
| 4662 | 8.6839
| 4663 | 8.4428
| 4664 | 7.0695
| 4665 | 8.3489
| 4666 | 7.9752
| 4667 | 8.4008
| 4668 | 7.6674
| 4669 | 8.2682
| 4670 | 8.617
| 4671 | 8.3272
| 4672 | 7.7678
| 4673 | 8.8175
| 4674 | 7.3692
| 4675 | 8.5747
| 4676 | 6.3997
| 4677 | 7.1784
| 4678 | 8.2393
| 4679 | 6.8527
| 4680 | 7.5874
| 4681 | 7.8525
| 4682 | 8.0827
| 4683 | 7.7347
| 4684 | 8.3393
| 4685 | 7.134
| 4686 | 8.0729
| 4687 | 7.9423
| 4688 | 7.6674
| 4689 | 6.6873
| 4690 | 8.1446
| 4691 | 7.5964
| 4692 | 7.6171
| 4693 | 6.7648
| 4694 | 8.2171
| 4695 | 8.3933
| 4696 | 7.4368
| 4697 | 7.4461
| 4698 | 7.2732
| 4699 | 7.5945
| 4700 | 8.5942
| 4701 | 8.4269
| 4702 | 7.8049
| 4703 | 7.8346
| 4704 | 8.8838
| 4705 | 7.8424
| 4706 | 8.7368
| 4707 | 7.3615
| 4708 | 8.6146
| 4709 | 7.4299
| 4710 | 7.6513
| 4711 | 7.5559
| 4712 | 8.4348
| 4713 | 7.2295
| 4714 | 7.8385
| 4715 | 8.4332
| 4716 | 8.0028
| 4717 | 6.9855
| 4718 | 8.1834
| 4719 | 8.73
| 4720 | 8.3559
| 4721 | 7.658
| 4722 | 6.9954
| 4723 | 8.4493
| 4724 | 8.1488
| 4725 | 7.5312
| 4726 | 8.3573
| 4727 | 7.858
| 4728 | 6.5427
| 4729 | 8.5726
| 4730 | 8.6783
| 4731 | 7.46
| 4732 | 8.2744
| 4733 | 7.6742
| 4734 | 7.6941
| 4735 | 8.2819
| 4736 | 7.7461
| 4737 | 8.7735
| 4738 | 8.2819
| 4739 | 6.9797
| 4740 | 8.5209
| 4741 | 8.208
| 4742 | 8.2416
| 4743 | 7.3925
| 4744 | 8.2068
| 4745 | 8.5622
| 4746 | 8.3615
| 4747 | 7.7212
| 4748 | 8.3601
| 4749 | 7.3011
| 4750 | 7.8185
| 4751 | 8.6314
| 4752 | 8.129
| 4753 | 7.449
| 4754 | 8.4253
| 4755 | 8.1989
| 4756 | 6.7305
| 4757 | 8.4332
| 4758 | 6.8544
| 4759 | 7.0252
| 4760 | 7.9014
| 4761 | 7.9271
| 4762 | 7.2053
| 4763 | 8.3671
| 4764 | 8.8079
| 4765 | 7.3747
| 4766 | 8.5061
| 4767 | 7.969
| 4768 | 8.5581
| 4769 | 8.0182
| 4770 | 7.9483
| 4771 | 8.8079
| 4772 | 6.9448
| 4773 | 6.4244
| 4774 | 8.4038
| 4775 | 8.1509
| 4776 | 8.5382
| 4777 | 8.0109
| 4778 | 7.2003
| 4779 | 6.9335
| 4780 | 7.3566
| 4781 | 8.0311
| 4782 | 8.0866
| 4783 | 7.8132
| 4784 | 7.5849
| 4785 | 8.3963
| 4786 | 7.5021
| 4787 | 8.6566
| 4788 | 8.25
| 4789 | 7.2654
| 4790 | 7.6674
| 4791 | 6.999
| 4792 | 7.6073
| 4793 | 8.0321
| 4794 | 7.4368
| 4795 | 8.1015
| 4796 | 7.3914
| 4797 | 7.7759
| 4798 | 8.8079
| 4799 | 8.5135
| 4800 | 8.7735
| 4801 | 7.7411
| 4802 | 8.0302
| 4803 | 8.2416
| 4804 | 7.8739
| 4805 | 7.8957
| 4806 | 7.5559
| 4807 | 7.0892
| 4808 | 8.2299
| 4809 | 8.2536
| 4810 | 7.268
| 4811 | 8.2609
| 4812 | 8.6673
| 4813 | 7.9752
| 4814 | 6.6687
| 4815 | 8.3245
| 4816 | 7.6587
| 4817 | 8.7735
| 4818 | 8.2287
| 4819 | 7.6879
| 4820 | 7.681
| 4821 | 7.483
| 4822 | 7.7855
| 4823 | 8.0339
| 4824 | 7.8269
| 4825 | 7.6634
| 4826 | 8.3074
| 4827 | 8.544
| 4828 | 6.5365
| 4829 | 8.43
| 4830 | 6.8047
| 4831 | 8.6955
| 4832 | 7.7297
| 4833 | 7.2525
| 4834 | 7.2083
| 4835 | 7.3446
| 4836 | 8.4348
| 4837 | 8.5622
| 4838 | 8.7045
| 4839 | 8.0046
| 4840 | 8.4023
| 4841 | 7.3653
| 4842 | 8.7696
| 4843 | 6.7151
| 4844 | 7.8178
| 4845 | 7.7832
| 4846 | 8.2334
| 4847 | 7.5033
| 4848 | 8.6619
| 4849 | 7.7981
| 4850 | 7.4955
| 4851 | 7.5881
| 4852 | 8.3074
| 4853 | 7.4536
| 4854 | 8.25
| 4855 | 7.29
| 4856 | 7.3742
| 4857 | 6.4359
| 4858 | 7.2639
| 4859 | 8.4396
| 4860 | 8.6673
| 4861 | 8.7267
| 4862 | 8.1867
| 4863 | 8.2206
| 4864 | 8.2932
| 4865 | 8.2148
| 4866 | 7.7504
| 4867 | 7.597
| 4868 | 8.1735
| 4869 | 8.7234
| 4870 | 7.2098
| 4871 | 8.4676
| 4872 | 8.3845
| 4873 | 7.4559
| 4874 | 8.4348
| 4875 | 8.554
| 4876 | 8.6673
| 4877 | 7.8644
| 4878 | 7.0593
| 4879 | 8.8127
| 4880 | 7.0216
| 4881 | 6.7206
| 4882 | 6.9869
| 4883 | 8.3545
| 4884 | 7.17
| 4885 | 7.4848
| 4886 | 7.7642
| 4887 | 6.8448
| 4888 | 8.6783
| 4889 | 8.5789
| 4890 | 8.0985
| 4891 | 8.5854
| 4892 | 7.5276
| 4893 | 7.3085
| 4894 | 8.2996
| 4895 | 8.2148
| 4896 | 7.0528
| 4897 | 8.2114
| 4898 | 8.7334
| 4899 | 6.9949
| 4900 | 8.0265
| 4901 | 8.2012
| 4902 | 8.67
| 4903 | 7.483
| 4904 | 8.1467
| 4905 | 6.7045
| 4906 | 7.8596
| 4907 | 7.1553
| 4908 | 8.3366
| 4909 | 7.7892
| 4910 | 8.7508
| 4911 | 7.8486
| 4912 | 7.9364
| 4913 | 7.1734
| 4914 | 8.5135
| 4915 | 8.5964
| 4916 | 6.829
| 4917 | 7.1725
| 4918 | 8.4659
| 4919 | 7.6906
| 4920 | 7.9682
| 4921 | 8.1989
| 4922 | 7.3808
| 4923 | 8.0247
| 4924 | 7.9263
| 4925 | 7.4612
| 4926 | 7.933
| 4927 | 8.3272
| 4928 | 7.7959
| 4929 | 8.554
| 4930 | 8.1035
| 4931 | 8.0613
| 4932 | 8.5191
| 4933 | 8.6593
| 4934 | 8.7581
| 4935 | 7.6513
| 4936 | 7.2078
| 4937 | 7.4357
| 4938 | 8.3903
| 4939 | 8.1331
| 4940 | 7.2305
| 4941 | 7.9355
| 4942 | 8.617
| 4943 | 6.8211
| 4944 | 8.1136
| 4945 | 7.8315
| 4946 | 7.8494
| 4947 | 7.7023
| 4948 | 6.9598
| 4949 | 7.5522
| 4950 | 7.2048
| 4951 | 7.5411
| 4952 | 7.7226
| 4953 | 7.8965
| 4954 | 8.2137
| 4955 | 8.5768
| 4956 | 8.2781
| 4957 | 8.3757
| 4958 | 8.1167
| 4959 | 8.2381
| 4960 | 7.8162
| 4961 | 8.7267
| 4962 | 7.5553
| 4963 | 8.2068
| 4964 | 8.342
| 4965 | 8.25
| 4966 | 8.2609
| 4967 | 8.2369
| 4968 | 7.1143
| 4969 | 6.8026
| 4970 | 7.538
| 4971 | 8.0489
| 4972 | 8.4269
| 4973 | 8.1075
| 4974 | 7.9449
| 4975 | 8.1341
| 4976 | 8.7472
| 4977 | 7.3402
| 4978 | 8.033
| 4979 | 6.5252
| 4980 | 7.2963
| 4981 | 7.9947
| 4982 | 8.0975
| 4983 | 8.1978
| 4984 | 8.8763
| 4985 | 7.8924
| 4986 | 7.4021
| 4987 | 8.3714
| 4988 | 7.8102
| 4989 | 7.0579
| 4990 | 7.9296
| 4991 | 7.6229
| 4992 | 6.8527
| 4993 | 8.1436
| 4994 | 8.4284
| 4995 | 7.9072
| 4996 | 7.77
| 4997 | 7.933
| 4998 | 8.2869
| 4999 | 7.7613
| 5000 | 7.679
| 5001 | 7.0248
| 5002 | 8.0191
| 5003 | 8.4692
| 5004 | 8.0302
| 5005 | 8.1541
| 5006 | 7.976
| 5007 | 7.1436
| 5008 | 7.8346
| 5009 | 7.4735
| 5010 | 7.8026
| 5011 | 6.9278
| 5012 | 7.8667
| 5013 | 6.8373
| 5014 | 8.544
| 5015 | 8.9329
| 5016 | 7.6453
| 5017 | 7.3006
| 5018 | 8.2091
| 5019 | 7.5172
| 5020 | 7.6041
| 5021 | 8.7735
| 5022 | 8.5098
| 5023 | 7.7184
| 5024 | 7.7788
| 5025 | 7.1224
| 5026 | 8.3629
| 5027 | 8.1812
| 5028 | 8.129
| 5029 | 6.8654
| 5030 | 7.1465
| 5031 | 8.4918
| 5032 | 7.9778
| 5033 | 8.0471
| 5034 | 7.9364
| 5035 | 8.256
| 5036 | 8.2536
| 5037 | 7.7605
| 5038 | 7.2853
| 5039 | 7.1038
| 5040 | 7.6797
| 5041 | 8.0945
| 5042 | 6.7404
| 5043 | 8.5898
| 5044 | 8.3448
| 5045 | 8.3448
| 5046 | 8.37
| 5047 | 7.47
| 5048 | 8.9206
| 5049 | 7.9831
| 5050 | 8.61
| 5051 | 7.5045
| 5052 | 7.5276
| 5053 | 8.3475
| 5054 | 8.4364
| 5055 | 7.7671
| 5056 | 7.8193
| 5057 | 7.1858
| 5058 | 7.7304
| 5059 | 6.3725
| 5060 | 7.6493
| 5061 | 8.5209
| 5062 | 7.9372
| 5063 | 7.3
| 5064 | 6.4307
| 5065 | 7.8819
| 5066 | 8.131
| 5067 | 8.43
| 5068 | 8.3815
| 5069 | 6.3653
| 5070 | 7.7072
| 5071 | 6.3959
| 5072 | 7.5958
| 5073 | 7.9179
| 5074 | 8.6673
| 5075 | 7.5448
| 5076 | 7.6177
| 5077 | 6.9891
| 5078 | 8.1248
| 5079 | 6.4823
| 5080 | 8.7076
| 5081 | 8.3205
| 5082 | 7.1301
| 5083 | 7.8285
| 5084 | 8.0817
| 5085 | 6.8649
| 5086 | 7.1412
| 5087 | 8.5601
| 5088 | 8.8625
| 5089 | 7.3165
| 5090 | 8.0807
| 5091 | 8.7508
| 5092 | 8.2794
| 5093 | 8.0136
| 5094 | 8.1457
| 5095 | 7.4083
| 5096 | 7.8439
| 5097 | 7.9974
| 5098 | 7.018
| 5099 | 8.1404
| 5100 | 7.6654
| 5101 | 8.7402
| 5102 | 8.7402
| 5103 | 8.5705
| 5104 | 8.0729
| 5105 | 8.9329
| 5106 | 8.2658
| 5107 | 7.8026
| 5108 | 8.0293
| 5109 | 8.5098
| 5110 | 7.483
| 5111 | 7.6941
| 5112 | 7.9415
| 5113 | 7.6661
| 5114 | 7.5057
| 5115 | 6.9283
| 5116 | 8.85
| 5117 | 6.9638
| 5118 | 8.6514
| 5119 | 7.6203
| 5120 | 6.9873
| 5121 | 8.3815
| 5122 | 6.4244
| 5123 | 8.1146
| 5124 | 8.3757
| 5125 | 7.9305
| 5126 | 7.6328
| 5127 | 7.5945
| 5128 | 7.8957
| 5129 | 6.6452
| 5130 | 7.0048
| 5131 | 7.3903
| 5132 | 6.4748
| 5133 | 8.2252
| 5134 | 7.8239
| 5135 | 8.383
| 5136 | 8.43
| 5137 | 7.9406
| 5138 | 7.2453
| 5139 | 8.4191
| 5140 | 6.8921
| 5141 | 7.148
| 5142 | 7.8981
| 5143 | 8.4847
| 5144 | 8.8441
| 5145 | 8.6146
| 5146 | 8.6289
| 5147 | 7.6817
| 5148 | 7.2541
| 5149 | 7.147
| 5150 | 7.6041
| 5151 | 7.3348
| 5152 | 7.6308
| 5153 | 8.1146
| 5154 | 7.7461
| 5155 | 7.4094
| 5156 | 7.3375
| 5157 | 8.6193
| 5158 | 8.91
| 5159 | 7.9929
| 5160 | 8.1207
| 5161 | 8.4129
| 5162 | 8.1321
| 5163 | 7.8308
| 5164 | 7.6817
| 5165 | 8.383
| 5166 | 7.8667
| 5167 | 6.6787
| 5168 | 7.6621
| 5169 | 8.592
| 5170 | 6.8544
| 5171 | 7.6367
| 5172 | 8.3859
| 5173 | 7.576
| 5174 | 8.2707
| 5175 | 8.2633
| 5176 | 8.1116
| 5177 | 8.3074
| 5178 | 7.571
| 5179 | 7.5634
| 5180 | 7.9221
| 5181 | 7.1908
| 5182 | 7.7649
| 5183 | 7.7759
| 5184 | 8.654
| 5185 | 8.0442
| 5186 | 8.1394
| 5187 | 8.0856
| 5188 | 8.2806
| 5189 | 8.4608
| 5190 | 6.9731
| 5191 | 8.0377
| 5192 | 8.1156
| 5193 | 7.5678
| 5194 | 8.0546
| 5195 | 7.7142
| 5196 | 8.37
| 5197 | 7.8916
| 5198 | 8.2831
| 5199 | 7.6447
| 5200 | 6.6881
| 5201 | 7.95
| 5202 | 7.4484
| 5203 | 7.0863
| 5204 | 7.8525
| 5205 | 8.001
| 5206 | 7.5722
| 5207 | 7.8117
| 5208 | 7.8876
| 5209 | 7.5938
| 5210 | 7.7936
| 5211 | 8.7775
| 5212 | 8.2572
| 5213 | 7.2295
| 5214 | 7.9113
| 5215 | 8.1746
| 5216 | 6.7265
| 5217 | 8.2464
| 5218 | 8.4865
| 5219 | 7.8331
| 5220 | 7.1893
| 5221 | 8.1446
| 5222 | 7.8339
| 5223 | 7.8644
| 5224 | 7.9552
| 5225 | 7.8973
| 5226 | 8.6593
| 5227 | 6.7794
| 5228 | 7.4542
| 5229 | 7.7907
| 5230 | 7.5318
| 5231 | 7.6533
| 5232 | 7.933
| 5233 | 7.8868
| 5234 | 6.8708
| 5235 | 8.0633
| 5236 | 8.1779
| 5237 | 8.2621
| 5238 | 7.5448
| 5239 | 7.9415
| 5240 | 8.0556
| 5241 | 7.8572
| 5242 | 8.4428
| 5243 | 6.4279
| 5244 | 8.3434
| 5245 | 7.4254
| 5246 | 7.1029
| 5247 | 7.956
| 5248 | 7.4162
| 5249 | 8.3087
| 5250 | 7.6749
| 5251 | 7.4729
| 5252 | 7.5429
| 5253 | 8.256
| 5254 | 6.7159
| 5255 | 7.1868
| 5256 | 8.7437
| 5257 | 7.9849
| 5258 | 7.8747
| 5259 | 7.4191
| 5260 | 8.3339
| 5261 | 7.7862
| 5262 | 8.833
| 5263 | 7.1695
| 5264 | 7.5202
| 5265 | 8.6811
| 5266 | 7.7722
| 5267 | 7.858
| 5268 | 8.2452
| 5269 | 8.0499
| 5270 | 8.2148
| 5271 | 8.338
| 5272 | 7.2448
| 5273 | 8.231
| 5274 | 8.0518
| 5275 | 7.4219
| 5276 | 7.0602
| 5277 | 8.0955
| 5278 | 7.6433
| 5279 | 8.7943
| 5280 | 7.2551
| 5281 | 7.8455
| 5282 | 8.3729
| 5283 | 7.2758
| 5284 | 8.2945
| 5285 | 8.5789
| 5286 | 7.7642
| 5287 | 8.4114
| 5288 | 7.4236
| 5289 | 7.0339
| 5290 | 8.2633
| 5291 | 7.2858
| 5292 | 7.7093
| 5293 | 8.0001
| 5294 | 7.5945
| 5295 | 7.8019
| 5296 | 8.5304
| 5297 | 7.886
| 5298 | 8.0856
| 5299 | 7.4783
| 5300 | 8.4114
| 5301 | 8.1638
| 5302 | 8.2806
| 5303 | 7.8868
| 5304 | 7.7311
| 5305 | 7.8064
| 5306 | 8.5304
| 5307 | 7.9271
| 5308 | 8.508
| 5309 | 8.2357
| 5310 | 8.4608
| 5311 | 8.4053
| 5312 | 8.2856
| 5313 | 8.7988
| 5314 | 8.0719
| 5315 | 6.616
| 5316 | 7.9491
| 5317 | 7.4712
| 5318 | 7.4554
| 5319 | 6.8298
| 5320 | 8.244
| 5321 | 7.519
| 5322 | 7.0394
| 5323 | 8.0019
| 5324 | 7.6295
| 5325 | 8.2057
| 5326 | 8.3545
| 5327 | 8.3462
| 5328 | 7.599
| 5329 | 7.7773
| 5330 | 8.3126
| 5331 | 8.0201
| 5332 | 7.6715
| 5333 | 7.3786
| 5334 | 8.0423
| 5335 | 7.9884
| 5336 | 6.1875
| 5337 | 8.6985
| 5338 | 7.4618
| 5339 | 8.244
| 5340 | 7.8354
| 5341 | 8.0146
| 5342 | 7.0103
| 5343 | 8.5663
| 5344 | 7.9457
| 5345 | 7.9229
| 5346 | 8.2781
| 5347 | 8.73
| 5348 | 7.8269
| 5349 | 7.8803
| 5350 | 7.9204
| 5351 | 7.9734
| 5352 | 8.2012
| 5353 | 7.2753
| 5354 | 8.0046
| 5355 | 8.717
| 5356 | 7.8691
| 5357 | 8.2695
| 5358 | 7.2556
| 5359 | 8.0896
| 5360 | 8.4222
| 5361 | 8.7816
| 5362 | 7.6242
| 5363 | 6.8311
| 5364 | 7.7396
| 5365 | 7.4907
| 5366 | 7.984
| 5367 | 8.1724
| 5368 | 8.0386
| 5369 | 7.9673
| 5370 | 8.5362
| 5371 | 7.6374
| 5372 | 7.1913
| 5373 | 7.4231
| 5374 | 8.2512
| 5375 | 6.8385
| 5376 | 8.2907
| 5377 | 8.3139
| 5378 | 7.7177
| 5379 | 6.9335
| 5380 | 8.3815
| 5381 | 8.7368
| 5382 | 8.0386
| 5383 | 8.3963
| 5384 | 6.3997
| 5385 | 7.4895
| 5386 | 7.3571
| 5387 | 8.5581
| 5388 | 7.9322
| 5389 | 8.6031
| 5390 | 8.2645
| 5391 | 7.976
| 5392 | 6.3411
| 5393 | 7.8795
| 5394 | 8.7076
| 5395 | 7.5811
| 5396 | 8.2452
| 5397 | 8.216
| 5398 | 6.9092
| 5399 | 7.4759
| 5400 | 8.1681
| 5401 | 7.9096
| 5402 | 8.0247
| 5403 | 8.61
| 5404 | 8.5285
| 5405 | 6.8654
| 5406 | 7.7247
| 5407 | 8.4971
| 5408 | 8.0499
| 5409 | 8.1724
| 5410 | 7.7432
| 5411 | 7.7996
| 5412 | 7.2428
| 5413 | 7.8439
| 5414 | 7.7773
| 5415 | 7.53
| 5416 | 7.6989
| 5417 | 8.1106
| 5418 | 6.8972
| 5419 | 7.3937
| 5420 | 7.5691
| 5421 | 8.3889
| 5422 | 8.4918
| 5423 | 8.97
| 5424 | 7.3831
| 5425 | 8.1801
| 5426 | 8.1812
| 5427 | 8.4068
| 5428 | 8.7581
| 5429 | 7.4724
| 5430 | 7.9752
| 5431 | 8.0671
| 5432 | 7.9717
| 5433 | 6.5763
| 5434 | 7.9849
| 5435 | 7.7149
| 5436 | 7.6769
| 5437 | 7.9673
| 5438 | 8.4542
| 5439 | 7.1191
| 5440 | 8.4053
| 5441 | 7.7114
| 5442 | 8.3299
| 5443 | 7.013
| 5444 | 8.3963
| 5445 | 7.6487
| 5446 | 7.5435
| 5447 | 8.0604
| 5448 | 6.329
| 5449 | 8.2322
| 5450 | 8.0028
| 5451 | 6.9629
| 5452 | 7.1641
| 5453 | 7.6028
| 5454 | 7.9509
| 5455 | 7.6607
| 5456 | 8.2996
| 5457 | 8.5228
| 5458 | 8.7334
| 5459 | 8.1436
| 5460 | 8.1156
| 5461 | 7.9699
| 5462 | 7.9655
| 5463 | 7.7418
| 5464 | 8.0367
| 5465 | 7.9288
| 5466 | 8.2206
| 5467 | 8.3061
| 5468 | 8.8033
| 5469 | 8.2645
| 5470 | 7.8965
| 5471 | 6.9174
| 5472 | 6.4363
| 5473 | 7.5349
| 5474 | 8.5832
| 5475 | 7.9263
| 5476 | 8.0127
| 5477 | 8.3258
| 5478 | 7.9381
| 5479 | 7.4089
| 5480 | 8.2719
| 5481 | 8.548
| 5482 | 7.8675
| 5483 | 7.8707
| 5484 | 7.9229
| 5485 | 7.4907
| 5486 | 6.6571
| 5487 | 7.8787
| 5488 | 7.4589
| 5489 | 7.2974
| 5490 | 8.5898
| 5491 | 8.5986
| 5492 | 8.3686
| 5493 | 7.8011
| 5494 | 8.3815
| 5495 | 6.9784
| 5496 | 8.4558
| 5497 | 8.4971
| 5498 | 8.592
| 5499 | 7.9121
| 5500 | 7.7017
| 5501 | 8.4989
| 5502 | 6.2899
| 5503 | 7.5672
| 5504 | 8.6217
| 5505 | 8.7943
| 5506 | 8.0594
| 5507 | 8.5247
| 5508 | 8.4038
| 5509 | 7.4753
| 5510 | 7.9543
| 5511 | 7.3577
| 5512 | 8.1415
| 5513 | 7.5081
| 5514 | 7.3527
| 5515 | 7.5479
| 5516 | 7.5824
| 5517 | 7.3516
| 5518 | 7.5958
| 5519 | 8.3366
| 5520 | 7.5386
| 5521 | 7.4836
| 5522 | 8.2882
| 5523 | 8.1933
| 5524 | 7.7254
| 5525 | 7.9621
| 5526 | 7.1883
| 5527 | 7.2422
| 5528 | 7.7591
| 5529 | 7.9138
| 5530 | 7.7825
| 5531 | 7.7974
| 5532 | 7.9246
| 5533 | 8.1197
| 5534 | 8.1106
| 5535 | 8.2428
| 5536 | 6.6861
| 5537 | 7.5691
| 5538 | 8.0729
| 5539 | 7.0695
| 5540 | 7.6763
| 5541 | 8.0191
| 5542 | 8.5421
| 5543 | 8.9206
| 5544 | 8.0995
| 5545 | 7.8315
| 5546 | 8.5098
| 5547 | 7.7678
| 5548 | 8.4795
| 5549 | 8.2584
| 5550 | 7.5081
| 5551 | 7.2499
| 5552 | 7.7649
| 5553 | 7.9305
| 5554 | 7.6315
| 5555 | 7.0071
| 5556 | 7.538
| 5557 | 7.4889
| 5558 | 8.1373
| 5559 | 7.3235
| 5560 | 6.7859
| 5561 | 8.97
| 5562 | 7.4345
| 5563 | 7.6527
| 5564 | 6.6266
| 5565 | 6.8298
| 5566 | 7.1451
| 5567 | 8.1373
| 5568 | 7.6872
| 5569 | 7.3112
| 5570 | 8.5266
| 5571 | 7.3429
| 5572 | 7.749
| 5573 | 7.7425
| 5574 | 7.308
| 5575 | 7.8041
| 5576 | 6.488
| 5577 | 8.4625
| 5578 | 7.9647
| 5579 | 7.3648
| 5580 | 8.91
| 5581 | 7.3408
| 5582 | 7.3775
| 5583 | 7.9072
| 5584 | 8.2958
| 5585 | 8.4237
| 5586 | 8.4222
| 5587 | 7.8811
| 5588 | 8.0433
| 5589 | 8.2719
| 5590 | 7.367
| 5591 | 7.4794
| 5592 | 8.6338
| 5593 | 7.5547
| 5594 | 7.5843
| 5595 | 7.9858
| 5596 | 8.4882
| 5597 | 7.3786
| 5598 | 7.8056
| 5599 | 7.46
| 5600 | 7.4345
| 5601 | 8.1488
| 5602 | 7.2587
| 5603 | 8.1541
| 5604 | 8.5663
| 5605 | 8.1499
| 5606 | 7.5251
| 5607 | 8.1025
| 5608 | 8.2476
| 5609 | 7.6197
| 5610 | 8.0091
| 5611 | 7.9364
| 5612 | 7.7432
| 5613 | 7.5027
| 5614 | 7.5748
| 5615 | 7.5239
| 5616 | 8.3299
| 5617 | 7.3489
| 5618 | 7.2753
| 5619 | 7.8755
| 5620 | 7.95
| 5621 | 7.1607
| 5622 | 8.6031
| 5623 | 7.5697
| 5624 | 7.4461
| 5625 | 7.701
| 5626 | 7.7325
| 5627 | 8.2844
| 5628 | 7.9621
| 5629 | 7.6164
| 5630 | 7.3123
| 5631 | 8.1025
| 5632 | 8.1922
| 5633 | 8.2452
| 5634 | 7.4426
| 5635 | 7.4979
| 5636 | 8.554
| 5637 | 8.2357
| 5638 | 7.1181
| 5639 | 7.6763
| 5640 | 8.8561
| 5641 | 7.7663
| 5642 | 8.0377
| 5643 | 7.434
| 5644 | 7.9238
| 5645 | 6.9837
| 5646 | 7.6621
| 5647 | 7.5541
| 5648 | 8.0367
| 5649 | 7.3229
| 5650 | 7.817
| 5651 | 7.3495
| 5652 | 7.6681
| 5653 | 8.49
| 5654 | 7.6171
| 5655 | 7.9983
| 5656 | 7.2837
| 5657 | 8.0046
| 5658 | 7.5003
| 5659 | 7.338
| 5660 | 7.9474
| 5661 | 7.2387
| 5662 | 8.4023
| 5663 | 7.9655
| 5664 | 8.2299
| 5665 | 6.7786
| 5666 | 7.3343
| 5667 | 8.0164
| 5668 | 7.2494
| 5669 | 7.148
| 5670 | 7.6003
| 5671 | 7.9263
| 5672 | 7.6093
| 5673 | 7.6249
| 5674 | 8.3801
| 5675 | 7.3197
| 5676 | 6.33
| 5677 | 7.6831
| 5678 | 8.1659
| 5679 | 8.0118
| 5680 | 7.71
| 5681 | 8.3933
| 5682 | 8.0768
| 5683 | 7.9708
| 5684 | 6.8895
| 5685 | 7.8965
| 5686 | 8.2416
| 5687 | 8.4526
| 5688 | 7.6879
| 5689 | 7.9569
| 5690 | 8.0995
| 5691 | 7.2932
| 5692 | 7.3107
| 5693 | 6.854
| 5694 | 7.9858
| 5695 | 7.344
| 5696 | 7.5294
| 5697 | 6.3997
| 5698 | 8.3948
| 5699 | 6.331
| 5700 | 8.0274
| 5701 | 5.9758
| 5702 | 7.2494
| 5703 | 7.8549
| 5704 | 8.4989
| 5705 | 8.4971
| 5706 | 7.9603
| 5707 | 7.9322
| 5708 | 7.3659
| 5709 | 7.2942
| 5710 | 8.7402
| 5711 | 6.5715
| 5712 | 8.1015
| 5713 | 7.8109
| 5714 | 8.61
| 5715 | 8.1757
| 5716 | 7.8064
| 5717 | 7.0518
| 5718 | 7.0048
| 5719 | 8.6413
| 5720 | 8.0499
| 5721 | 8.8384
| 5722 | 7.8683
| 5723 | 7.6394
| 5724 | 7.7318
| 5725 | 8.6727
| 5726 | 7.4185
| 5727 | 8.0623
| 5728 | 7.5862
| 5729 | 7.4718
| 5730 | 7.7869
| 5731 | 8.43
| 5732 | 7.0653
| 5733 | 8.483
| 5734 | 7.571
| 5735 | 7.8588
| 5736 | 8.7472
| 5737 | 7.0403
| 5738 | 6.8477
| 5739 | 7.7642
| 5740 | 7.4765
| 5741 | 7.2541
| 5742 | 7.4027
| 5743 | 8.73
| 5744 | 7.5398
| 5745 | 7.5855
| 5746 | 7.6341
| 5747 | 6.8149
| 5748 | 7.9965
| 5749 | 6.5756
| 5750 | 7.7121
| 5751 | 8.3205
| 5752 | 7.9355
| 5753 | 8.4396
| 5754 | 8.2744
| 5755 | 7.606
| 5756 | 8.5747
| 5757 | 8.6566
| 5758 | 8.4761
| 5759 | 6.5593
| 5760 | 8.6241
| 5761 | 8.2658
| 5762 | 7.6348
| 5763 | 8.5043
| 5764 | 7.2113
| 5765 | 8.3245
| 5766 | 7.0551
| 5767 | 7.0528
| 5768 | 7.3976
| 5769 | 7.2093
| 5770 | 7.0639
| 5771 | 8.4676
| 5772 | 7.7325
| 5773 | 8.5343
| 5774 | 7.7511
| 5775 | 6.8519
| 5776 | 7.23
| 5777 | 7.6906
| 5778 | 7.6892
| 5779 | 7.9415
| 5780 | 7.3993
| 5781 | 7.5087
| 5782 | 7.7128
| 5783 | 7.2947
| 5784 | 7.8254
| 5785 | 7.621
| 5786 | 7.7729
| 5787 | 6.9922
| 5788 | 7.0958
| 5789 | 7.4671
| 5790 | 8.3845
| 5791 | 8.4348
| 5792 | 7.9457
| 5793 | 8.5684
| 5794 | 7.4624
| 5795 | 7.8231
| 5796 | 7.9072
| 5797 | 7.1602
| 5798 | 8.5323
| 5799 | 8.3448
| 5800 | 7.8517
| 5801 | 7.7526
| 5802 | 8.0965
| 5803 | 7.2219
| 5804 | 7.5722
| 5805 | 8.1584
| 5806 | 7.1759
| 5807 | 8.3601
| 5808 | 7.9347
| 5809 | 7.6661
| 5810 | 8.4526
| 5811 | 8.4144
| 5812 | 7.8525
| 5813 | 8.2572
| 5814 | 8.556
| 5815 | 8.4114
| 5816 | 8.0173
| 5817 | 7.814
| 5818 | 6.8785
| 5819 | 8.0995
| 5820 | 8.0019
| 5821 | 8.4348
| 5822 | 7.46
| 5823 | 8.0546
| 5824 | 6.6752
| 5825 | 8.0836
| 5826 | 7.7892
| 5827 | 8.4625
| 5828 | 7.1461
| 5829 | 7.3192
| 5830 | 8.0182
| 5831 | 7.3714
| 5832 | 8.7816
| 5833 | 8.2806
| 5834 | 8.0866
| 5835 | 8.1945
| 5836 | 7.7304
| 5837 | 7.0765
| 5838 | 8.3489
| 5839 | 8.5098
| 5840 | 7.4676
| 5841 | 7.5368
| 5842 | 7.5951
| 5843 | 7.7759
| 5844 | 8.6839
| 5845 | 8.0201
| 5846 | 7.8132
| 5847 | 7.933
| 5848 | 7.6301
| 5849 | 7.2628
| 5850 | 7.903
| 5851 | 8.0886
| 5852 | 7.092
| 5853 | 8.2206
| 5854 | 8.5172
| 5855 | 7.4979
| 5856 | 8.8277
| 5857 | 7.8079
| 5858 | 7.6054
| 5859 | 8.3285
| 5860 | 8.0758
| 5861 | 8.544
| 5862 | 6.9677
| 5863 | 7.7304
| 5864 | 8.833
| 5865 | 8.3801
| 5866 | 8.2171
| 5867 | 8.5209
| 5868 | 7.7276
| 5869 | 6.7729
| 5870 | 7.3781
| 5871 | 8.1801
| 5872 | 8.1035
| 5873 | 8.2057
| 5874 | 8.3179
| 5875 | 7.1813
| 5876 | 7.5441
| 5877 | 7.6177
| 5878 | 8.1552
| 5879 | 7.2874
| 5880 | 8.6566
| 5881 | 8.1648
| 5882 | 7.1784
| 5883 | 7.2371
| 5884 | 8.2252
| 5885 | 8.4918
| 5886 | 8.4778
| 5887 | 7.1715
| 5888 | 6.5715
| 5889 | 7.9526
| 5890 | 8.483
| 5891 | 8.7735
| 5892 | 7.858
| 5893 | 8.3312
| 5894 | 6.7993
| 5895 | 8.1911
| 5896 | 7.0996
| 5897 | 6.5893
| 5898 | 8.546
| 5899 | 7.3064
| 5900 | 7.7693
| 5901 | 7.8739
| 5902 | 7.5836
| 5903 | 7.4265
| 5904 | 7.9466
| 5905 | 8.5421
| 5906 | 6.6818
| 5907 | 7.4363
| 5908 | 7.2188
| 5909 | 8.2932
| 5910 | 7.6627
| 5911 | 8.0367
| 5912 | 7.2937
| 5913 | 7.0802
| 5914 | 8.1768
| 5915 | 8.4847
| 5916 | 7.6647
| 5917 | 7.9947
| 5918 | 7.3604
| 5919 | 8.5942
| 5920 | 7.8973
| 5921 | 8.4191
| 5922 | 8.7368
| 5923 | 7.2769
| 5924 | 7.9804
| 5925 | 8.6146
| 5926 | 7.5786
| 5927 | 8.0975
| 5928 | 7.4328
| 5929 | 8.2781
| 5930 | 7.3681
| 5931 | 8.948
| 5932 | 7.6729
| 5933 | 6.7088
| 5934 | 8.3299
| 5935 | 8.438
| 5936 | 6.7985
| 5937 | 7.9138
| 5938 | 7.644
| 5939 | 7.0616
| 5940 | 7.1938
| 5941 | 8.2536
| 5942 | 7.6587
| 5943 | 6.8946
| 5944 | 8.0452
| 5945 | 8.556
| 5946 | 8.1616
| 5947 | 6.9062
| 5948 | 8.0681
| 5949 | 8.0642
| 5950 | 8.3573
| 5951 | 7.3101
| 5952 | 7.0293
| 5953 | 8.8763
| 5954 | 8.7581
| 5955 | 7.6256
| 5956 | 7.5741
| 5957 | 8.4175
| 5958 | 8.6193
| 5959 | 7.4197
| 5960 | 8.2524
| 5961 | 7.9347
| 5962 | 8.6314
| 5963 | 7.5015
| 5964 | 7.5913
| 5965 | 7.003
| 5966 | 7.9612
| 5967 | 7.6341
| 5968 | 8.1692
| 5969 | 8.0788
| 5970 | 8.0109
| 5971 | 7.356
| 5972 | 6.69
| 5973 | 8.8127
| 5974 | 7.8447
| 5975 | 8.548
| 5976 | 7.5087
| 5977 | 7.4351
| 5978 | 8.2756
| 5979 | 7.231
| 5980 | 7.5754
| 5981 | 8.2894
| 5982 | 7.3375
| 5983 | 8.1446
| 5984 | 7.8478
| 5985 | 7.6886
| 5986 | 7.7989
| 5987 | 7.83
| 5988 | 8.1248
| 5989 | 7.8246
| 5990 | 7.9483
| 5991 | 6.8452
| 5992 | 7.8315
| 5993 | 7.4478
| 5994 | 7.8916
| 5995 | 7.4334
| 5996 | 6.9571
| 5997 | 7.2479
| 5998 | 8.4642
| 5999 | 7.331
| 6000 | 7.0929
| 6001 | 8.4509
| 6002 | 7.7974
| 6003 | 7.5485
| 6004 | 8.5153
| 6005 | 7.9415
| 6006 | 7.5748
| 6007 | 8.4332
| 6008 | 8.5942
| 6009 | 7.3
| 6010 | 8.7202
| 6011 | 8.4795
| 6012 | 7.6158
| 6013 | 7.8246
| 6014 | 7.4961
| 6015 | 8.73
| 6016 | 7.9813
| 6017 | 8.3179
| 6018 | 7.8308
| 6019 | 7.9612
| 6020 | 7.8644
| 6021 | 6.9611
| 6022 | 7.3397
| 6023 | 7.7766
| 6024 | 5.8557
| 6025 | 8.231
| 6026 | 7.3027
| 6027 | 8.0386
| 6028 | 8.1889
| 6029 | 7.7135
| 6030 | 7.9279
| 6031 | 8.0293
| 6032 | 7.9381
| 6033 | 7.1148
| 6034 | 8.3772
| 6035 | 8.0109
| 6036 | 8.1177
| 6037 | 7.1398
| 6038 | 7.2048
| 6039 | 7.8908
| 6040 | 8.6031
| 6041 | 8.4608
| 6042 | 8.033
| 6043 | 7.847
| 6044 | 7.4179
| 6045 | 7.2098
| 6046 | 8.5025
| 6047 | 8.3087
| 6048 | 7.2229
| 6049 | 8.1681
| 6050 | 6.7119
| 6051 | 7.5919
| 6052 | 7.5355
| 6053 | 7.8763
| 6054 | 6.8848
| 6055 | 7.5622
| 6056 | 8.2275
| 6057 | 8.1005
| 6058 | 7.4106
| 6059 | 7.3359
| 6060 | 7.8596
| 6061 | 7.9849
| 6062 | 8.3407
| 6063 | 8.4237
| 6064 | 8.3889
| 6065 | 8.8561
| 6066 | 8.1228
| 6067 | 8.4918
| 6068 | 8.0661
| 6069 | 8.1768
| 6070 | 8.2346
| 6071 | 8.0302
| 6072 | 6.8473
| 6073 | 7.4248
| 6074 | 7.5786
| 6075 | 8.0082
| 6076 | 7.4391
| 6077 | 8.6338
| 6078 | 7.4729
| 6079 | 8.5684
| 6080 | 8.548
| 6081 | 7.1602
| 6082 | 7.1983
| 6083 | 8.3531
| 6084 | 7.7396
| 6085 | 8.3587
| 6086 | 7.3764
| 6087 | 7.7818
| 6088 | 7.7283
| 6089 | 8.3448
| 6090 | 7.6702
| 6091 | 7.7107
| 6092 | 6.9567
| 6093 | 8.0321
| 6094 | 6.8211
| 6095 | 8.3205
| 6096 | 7.4536
| 6097 | 8.4865
| 6098 | 7.4913
| 6099 | 7.7729
| 6100 | 8.617
| 6101 | 8.342
| 6102 | 7.2592
| 6103 | 8.7988
| 6104 | 7.9947
| 6105 | 8.1146
| 6106 | 8.3772
| 6107 | 7.2743
| 6108 | 8.3978
| 6109 | 7.8369
| 6110 | 7.8239
| 6111 | 7.3775
| 6112 | 8.3312
| 6113 | 7.9831
| 6114 | 8.2287
| 6115 | 6.9357
| 6116 | 7.0385
| 6117 | 8.4053
| 6118 | 7.9204
| 6119 | 8.4935
| 6120 | 8.6811
| 6121 | 7.9229
| 6122 | 6.8415
| 6123 | 8.2091
| 6124 | 7.9743
| 6125 | 7.5349
| 6126 | 8.2744
| 6127 | 7.4077
| 6128 | 7.0802
| 6129 | 8.3179
| 6130 | 8.0527
| 6131 | 8.6755
| 6132 | 7.3332
| 6133 | 7.4351
| 6134 | 7.4513
| 6135 | 7.9154
| 6136 | 7.9154
| 6137 | 7.2346
| 6138 | 7.7583
| 6139 | 8.4008
| 6140 | 7.4145
| 6141 | 7.3609
| 6142 | 7.5868
| 6143 | 7.64
| 6144 | 7.9875
| 6145 | 8.1415
| 6146 | 8.2452
| 6147 | 8.4592
| 6148 | 7.1651
| 6149 | 7.6886
| 6150 | 7.227
| 6151 | 8.4726
| 6152 | 8.2633
| 6153 | 7.7715
| 6154 | 8.3179
| 6155 | 7.7163
| 6156 | 8.4558
| 6157 | 6.9283
| 6158 | 8.1648
| 6159 | 8.2695
| 6160 | 8.3517
| 6161 | 8.49
| 6162 | 7.2837
| 6163 | 6.8806
| 6164 | 7.2953
| 6165 | 8.1746
| 6166 | 7.0523
| 6167 | 7.9603
| 6168 | 8.1531
| 6169 | 8.2633
| 6170 | 7.7996
| 6171 | 7.77
| 6172 | 8.1509
| 6173 | 8.0537
| 6174 | 7.1369
| 6175 | 7.9893
| 6176 | 8.0945
| 6177 | 7.9338
| 6178 | 7.0882
| 6179 | 7.6387
| 6180 | 7.6906
| 6181 | 7.4174
| 6182 | 7.3451
| 6183 | 8.9005
| 6184 | 8.1845
| 6185 | 8.592
| 6186 | 8.2275
| 6187 | 8.0037
| 6188 | 8.6985
| 6189 | 8.2958
| 6190 | 8.0358
| 6191 | 7.3128
| 6192 | 8.37
| 6193 | 8.2057
| 6194 | 7.9129
| 6195 | 8.1055
| 6196 | 7.8779
| 6197 | 7.2219
| 6198 | 7.344
| 6199 | 7.0977
| 6200 | 7.84
| 6201 | 8.3757
| 6202 | 8.4509
| 6203 | 7.3418
| 6204 | 8.3815
| 6205 | 8.3126
| 6206 | 7.3976
| 6207 | 8.2464
| 6208 | 8.224
| 6209 | 7.5282
| 6210 | 6.7238
| 6211 | 7.9884
| 6212 | 8.6868
| 6213 | 8.7943
| 6214 | 7.1422
| 6215 | 8.0565
| 6216 | 7.2118
| 6217 | 8.1746
| 6218 | 8.552
| 6219 | 7.9154
| 6220 | 8.4068
| 6221 | 7.7922
| 6222 | 7.5535
| 6223 | 8.6265
| 6224 | 7.7663
| 6225 | 8.6783
| 6226 | 7.8604
| 6227 | 7.9734
| 6228 | 8.033
| 6229 | 8.1978
| 6230 | 6.3945
| 6231 | 8.2633
| 6232 | 8.7508
| 6233 | 8.4778
| 6234 | 7.5958
| 6235 | 7.7325
| 6236 | 8.8763
| 6237 | 8.2034
| 6238 | 7.8087
| 6239 | 7.3797
| 6240 | 8.0652
| 6241 | 8.2183
| 6242 | 7.3931
| 6243 | 8.7138
| 6244 | 8.0395
| 6245 | 8.2068
| 6246 | 8.8441
| 6247 | 7.8973
| 6248 | 6.9492
| 6249 | 7.8377
| 6250 | 7.9983
| 6251 | 7.5306
| 6252 | 8.5705
| 6253 | 8.0284
| 6254 | 8.7202
| 6255 | 8.617
| 6256 | 7.5945
| 6257 | 8.2744
| 6258 | 7.5659
| 6259 | 7.0996
| 6260 | 8.3434
| 6261 | 8.1834
| 6262 | 8.3729
| 6263 | 8.338
| 6264 | 8.6897
| 6265 | 7.6361
| 6266 | 7.8916
| 6267 | 8.129
| 6268 | 8.6054
| 6269 | 7.9014
| 6270 | 8.1415
| 6271 | 8.9206
| 6272 | 7.8056
| 6273 | 7.7966
| 6274 | 7.7825
| 6275 | 7.4328
| 6276 | 7.599
| 6277 | 8.4592
| 6278 | 8.4542
| 6279 | 7.1789
| 6280 | 8.4412
| 6281 | 8.2682
| 6282 | 8.6619
| 6283 | 6.89
| 6284 | 7.8683
| 6285 | 7.2458
| 6286 | 6.4938
| 6287 | 8.5898
| 6288 | 7.0371
| 6289 | 7.4111
| 6290 | 8.2381
| 6291 | 8.0237
| 6292 | 8.0452
| 6293 | 7.6242
| 6294 | 7.7128
| 6295 | 6.9651
| 6296 | 7.1344
| 6297 | 7.4519
| 6298 | 8.7472
| 6299 | 7.406
| 6300 | 8.1659
| 6301 | 7.1779
| 6302 | 7.6328
| 6303 | 7.6216
| 6304 | 7.9595
| 6305 | 7.6708
| 6306 | 7.5773
| 6307 | 7.7751
| 6308 | 8.1541
| 6309 | 7.9196
| 6310 | 7.2249
| 6311 | 6.7111
| 6312 | 8.3772
| 6313 | 8.5811
| 6314 | 8.2682
| 6315 | 8.1823
| 6316 | 8.6388
| 6317 | 7.9179
| 6318 | 7.8884
| 6319 | 7.4548
| 6320 | 7.5653
| 6321 | 7.3577
| 6322 | 8.0556
| 6323 | 7.5417
| 6324 | 7.9229
| 6325 | 8.224
| 6326 | 8.1106
| 6327 | 6.7305
| 6328 | 8.0055
| 6329 | 7.3566
| 6330 | 7.6627
| 6331 | 7.4083
| 6332 | 7.9163
| 6333 | 7.6414
| 6334 | 7.1495
| 6335 | 6.1002
| 6336 | 7.3348
| 6337 | 7.754
| 6338 | 7.1369
| 6339 | 8.552
| 6340 | 8.2781
| 6341 | 8.0339
| 6342 | 6.7681
| 6343 | 7.944
| 6344 | 6.7002
| 6345 | 8.7107
| 6346 | 7.9983
| 6347 | 8.0311
| 6348 | 8.0091
| 6349 | 7.2868
| 6350 | 7.9022
| 6351 | 8.3258
| 6352 | 8.438
| 6353 | 7.66
| 6354 | 7.8056
| 6355 | 7.5368
| 6356 | 6.3615
| 6357 | 8.6673
| 6358 | 8.85
| 6359 | 7.519
| 6360 | 8.8277
| 6361 | 7.5634
| 6362 | 7.4334
| 6363 | 7.7707
| 6364 | 8.3874
| 6365 | 7.8525
| 6366 | 7.168
| 6367 | 7.8308
| 6368 | 8.0768
| 6369 | 7.9213
| 6370 | 7.3139
| 6371 | 8.4038
| 6372 | 7.6447
| 6373 | 8.3126
| 6374 | 7.3847
| 6375 | 8.0405
| 6376 | 6.4613
| 6377 | 8.1146
| 6378 | 8.1757
| 6379 | 7.4589
| 6380 | 7.9804
| 6381 | 7.3139
| 6382 | 7.4777
| 6383 | 7.4259
| 6384 | 8.5228
| 6385 | 7.3731
| 6386 | 7.4788
| 6387 | 7.8557
| 6388 | 7.6138
| 6389 | 7.8533
| 6390 | 7.6229
| 6391 | 8.1584
| 6392 | 7.3659
| 6393 | 7.8308
| 6394 | 8.7943
| 6395 | 8.717
| 6396 | 8.4592
| 6397 | 8.4659
| 6398 | 8.2252
| 6399 | 8.2023
| 6400 | 7.1191
| 6401 | 8.717
| 6402 | 7.2275
| 6403 | 8.2894
| 6404 | 7.8323
| 6405 | 8.2945
| 6406 | 7.0896
| 6407 | 8.5876
| 6408 | 7.9831
| 6409 | 8.071
| 6410 | 8.0037
| 6411 | 8.5153
| 6412 | 8.244
| 6413 | 8.3312
| 6414 | 8.2405
| 6415 | 7.4055
| 6416 | 7.1612
| 6417 | 7.8346
| 6418 | 7.3059
| 6419 | 8.4642
| 6420 | 7.5441
| 6421 | 7.4842
| 6422 | 8.1856
| 6423 | 8.3889
| 6424 | 7.6164
| 6425 | 7.513
| 6426 | 7.4724
| 6427 | 7.3982
| 6428 | 7.0193
| 6429 | 8.2346
| 6430 | 7.8004
| 6431 | 8.131
| 6432 | 8.2536
| 6433 | 7.2628
| 6434 | 7.7884
| 6435 | 8.4953
| 6436 | 8.4676
| 6437 | 8.4316
| 6438 | 7.4083
| 6439 | 7.1393
| 6440 | 8.131
| 6441 | 7.7023
| 6442 | 8.6839
| 6443 | 8.1269
| 6444 | 7.5124
| 6445 | 7.228
| 6446 | 7.4907
| 6447 | 8.3218
| 6448 | 8.4971
| 6449 | 7.5093
| 6450 | 7.0477
| 6451 | 8.5642
| 6452 | 7.5628
| 6453 | 6.8823
| 6454 | 7.7283
| 6455 | 8.5401
| 6456 | 8.5172
| 6457 | 8.7943
| 6458 | 7.5836
| 6459 | 7.6668
| 6460 | 8.001
| 6461 | 6.3313
| 6462 | 8.5266
| 6463 | 8.1584
| 6464 | 8.216
| 6465 | 7.2341
| 6466 | 7.8941
| 6467 | 8.5726
| 6468 | 8.1415
| 6469 | 6.9127
| 6470 | 8.1218
| 6471 | 7.7037
| 6472 | 8.2658
| 6473 | 8.3087
| 6474 | 8.4692
| 6475 | 8.4918
| 6476 | 6.7859
| 6477 | 7.7283
| 6478 | 7.8533
| 6479 | 7.3909
| 6480 | 8.1065
| 6481 | 8.1116
| 6482 | 7.1744
| 6483 | 7.6756
| 6484 | 7.7877
| 6485 | 6.9788
| 6486 | 7.7198
| 6487 | 8.1075
| 6488 | 8.0585
| 6489 | 8.216
| 6490 | 6.9118
| 6491 | 8.5304
| 6492 | 8.4284
| 6493 | 6.8776
| 6494 | 8.3166
| 6495 | 6.8365
| 6496 | 7.1119
| 6497 | 7.5318
| 6498 | 8.5025
| 6499 | 7.9638
| 6500 | 8.5622
| 6501 | 8.717
| 6502 | 7.886
| 6503 | 7.5257
| 6504 | 8.3786
| 6505 | 8.73
| 6506 | 7.7847
| 6507 | 8.4191
| 6508 | 6.4122
| 6509 | 7.1888
| 6510 | 7.8339
| 6511 | 8.1383
| 6512 | 8.6193
| 6513 | 6.6395
| 6514 | 6.5778
| 6515 | 6.1962
| 6516 | 8.3801
| 6517 | 8.3489
| 6518 | 8.3074
| 6519 | 8.0471
| 6520 | 7.5977
| 6521 | 8.4935
| 6522 | 6.5737
| 6523 | 8.0265
| 6524 | 7.5597
| 6525 | 7.8056
| 6526 | 7.8755
| 6527 | 7.1873
| 6528 | 8.6338
| 6529 | 8.4542
| 6530 | 8.2381
| 6531 | 6.5475
| 6532 | 8.2869
| 6533 | 8.267
| 6534 | 8.1269
| 6535 | 8.7544
| 6536 | 8.0321
| 6537 | 7.8216
| 6538 | 7.8447
| 6539 | 7.8835
| 6540 | 6.8553
| 6541 | 7.4179
| 6542 | 6.9913
| 6543 | 7.8011
| 6544 | 8.5007
| 6545 | 6.9135
| 6546 | 8.3113
| 6547 | 7.7591
| 6548 | 8.1933
| 6549 | 7.7526
| 6550 | 8.2781
| 6551 | 8.3179
| 6552 | 7.0727
| 6553 | 7.4729
| 6554 | 7.9938
| 6555 | 8.3232
| 6556 | 7.9039
| 6557 | 8.1085
| 6558 | 6.4328
| 6559 | 6.7904
| 6560 | 8.3845
| 6561 | 8.6438
| 6562 | 8.91
| 6563 | 8.1116
| 6564 | 8.2996
| 6565 | 7.8323
| 6566 | 8.7696
| 6567 | 8.2856
| 6568 | 7.8803
| 6569 | 6.527
| 6570 | 8.0719
| 6571 | 7.4618
| 6572 | 7.7737
| 6573 | 6.8067
| 6574 | 8.0405
| 6575 | 8.2381
| 6576 | 8.1404
| 6577 | 7.4174
| 6578 | 7.8147
| 6579 | 8.0797
| 6580 | 7.6275
| 6581 | 7.9822
| 6582 | 7.2969
| 6583 | 7.7899
| 6584 | 8.1269
| 6585 | 8.438
| 6586 | 6.9418
| 6587 | 8.2572
| 6588 | 8.4865
| 6589 | 7.46
| 6590 | 8.7657
| 6591 | 7.2068
| 6592 | 7.0093
| 6593 | 7.7744
| 6594 | 7.8628
| 6595 | 7.1431
| 6596 | 8.7816
| 6597 | 8.4114
| 6598 | 8.1055
| 6599 | 7.8455
| 6600 | 7.2566
| 6601 | 7.7671
| 6602 | 7.8393
| 6603 | 8.554
| 6604 | 7.4174
| 6605 | 7.9734
| 6606 | 8.7368
| 6607 | 7.1071
| 6608 | 8.4068
| 6609 | 7.8707
| 6610 | 8.4795
| 6611 | 6.7766
| 6612 | 6.6795
| 6613 | 8.2844
| 6614 | 7.3391
| 6615 | 6.8448
| 6616 | 8.2488
| 6617 | 8.2206
| 6618 | 6.6281
| 6619 | 8.2114
| 6620 | 7.7766
| 6621 | 7.9647
| 6622 | 8.5768
| 6623 | 8.3918
| 6624 | 7.3321
| 6625 | 8.4253
| 6626 | 7.2984
| 6627 | 7.9355
| 6628 | 8.446
| 6629 | 7.6315
| 6630 | 8.2183
| 6631 | 7.8973
| 6632 | 8.4865
| 6633 | 7.8924
| 6634 | 7.2123
| 6635 | 6.9418
| 6636 | 8.1978
| 6637 | 7.7981
| 6638 | 8.5401
| 6639 | 8.3686
| 6640 | 8.3729
| 6641 | 7.65
| 6642 | 6.5245
| 6643 | 7.8771
| 6644 | 8.948
| 6645 | 7.7922
| 6646 | 8.6289
| 6647 | 7.5081
| 6648 | 8.3048
| 6649 | 7.9884
| 6650 | 8.5382
| 6651 | 7.8239
| 6652 | 7.3864
| 6653 | 7.4676
| 6654 | 8.2645
| 6655 | 8.2405
| 6656 | 7.8699
| 6657 | 7.4771
| 6658 | 8.0293
| 6659 | 7.6722
| 6660 | 6.5696
| 6661 | 7.6879
| 6662 | 7.3864
| 6663 | 8.97
| 6664 | 7.0863
| 6665 | 8.2907
| 6666 | 7.372
| 6667 | 7.2665
| 6668 | 7.8019
| 6669 | 8.4813
| 6670 | 7.5202
| 6671 | 7.2387
| 6672 | 7.9708
| 6673 | 7.8109
| 6674 | 8.7544
| 6675 | 8.2756
| 6676 | 7.3283
| 6677 | 7.5773
| 6678 | 8.0876
| 6679 | 7.438
| 6680 | 8.8175
| 6681 | 7.8747
| 6682 | 8.0349
| 6683 | 6.58
| 6684 | 8.6123
| 6685 | 7.519
| 6686 | 7.9163
| 6687 | 8.3573
| 6688 | 8.5098
| 6689 | 7.4925
| 6690 | 8.0358
| 6691 | 8.8079
| 6692 | 7.7518
| 6693 | 8.3993
| 6694 | 8.1956
| 6695 | 8.3601
| 6696 | 7.7729
| 6697 | 7.7475
| 6698 | 7.5578
| 6699 | 8.3503
| 6700 | 8.61
| 6701 | 8.2057
| 6702 | 8.4676
| 6703 | 8.4348
| 6704 | 7.7922
| 6705 | 7.9603
| 6706 | 7.4123
| 6707 | 7.7003
| 6708 | 7.4565
| 6709 | 7.8557
| 6710 | 7.8596
| 6711 | 8.1541
| 6712 | 8.3933
| 6713 | 8.7138
| 6714 | 8.8033
| 6715 | 8.8692
| 6716 | 8.6619
| 6717 | 8.1446
| 6718 | 7.1364
| 6719 | 8.1269
| 6720 | 7.5754
| 6721 | 7.4157
| 6722 | 6.917
| 6723 | 7.0148
| 6724 | 8.5323
| 6725 | 6.7404
| 6726 | 7.6145
| 6727 | 8.3963
| 6728 | 7.149
| 6729 | 6.8352
| 6730 | 8.0846
| 6731 | 7.9322
| 6732 | 8.7234
| 6733 | 8.6985
| 6734 | 7.6621
| 6735 | 8.5986
| 6736 | 8.8918
| 6737 | 8.3462
| 6738 | 8.2369
| 6739 | 8.1552
| 6740 | 8.5043
| 6741 | 8.546
| 6742 | 7.3267
| 6743 | 7.8549
| 6744 | 7.9364
| 6745 | 7.8612
| 6746 | 8.7076
| 6747 | 7.7072
| 6748 | 8.0537
| 6749 | 8.4237
| 6750 | 8.1692
| 6751 | 7.5423
| 6752 | 8.1106
| 6753 | 5.8933
| 6754 | 8.3074
| 6755 | 7.3267
| 6756 | 8.7657
| 6757 | 7.2738
| 6758 | 7.6073
| 6759 | 7.9105
| 6760 | 7.4128
| 6761 | 8.2206
| 6762 | 8.6031
| 6763 | 7.8208
| 6764 | 7.5021
| 6765 | 7.7518
| 6766 | 7.4495
| 6767 | 8.4129
| 6768 | 8.1945
| 6769 | 7.9577
| 6770 | 7.4706
| 6771 | 8.6811
| 6772 | 7.9188
| 6773 | 8.4726
| 6774 | 8.216
| 6775 | 8.2046
| 6776 | 8.5986
| 6777 | 8.5153
| 6778 | 7.9517
| 6779 | 8.4175
| 6780 | 6.8895
| 6781 | 7.4854
| 6782 | 8.1638
| 6783 | 7.4635
| 6784 | 8.1638
| 6785 | 7.6996
| 6786 | 7.9509
| 6787 | 6.9105
| 6788 | 8.1106
| 6789 | 8.2831
| 6790 | 8.1735
| 6791 | 6.7693
| 6792 | 8.6363
| 6793 | 8.4284
| 6794 | 7.4426
| 6795 | 8.1616
| 6796 | 7.1666
| 6797 | 7.9699
| 6798 | 7.5855
| 6799 | 7.9389
| 6800 | 8.6438
| 6801 | 7.171
| 6802 | 7.3
| 6803 | 8.1331
| 6804 | 6.8302
| 6805 | 8.1541
| 6806 | 7.6961
| 6807 | 8.4575
| 6808 | 7.5057
| 6809 | 8.5832
| 6810 | 8.2114
| 6811 | 7.9398
| 6812 | 8.0886
| 6813 | 8.0527
| 6814 | 8.2023
| 6815 | 8.3757
| 6816 | 7.6702
| 6817 | 8.1331
| 6818 | 6.6013
| 6819 | 7.8432
| 6820 | 7.5913
| 6821 | 8.2794
| 6822 | 7.4854
| 6823 | 6.7709
| 6824 | 7.7855
| 6825 | 8.1499
| 6826 | 8.3545
| 6827 | 8.548
| 6828 | 7.7058
| 6829 | 7.4294
| 6830 | 8.4847
| 6831 | 6.8075
| 6832 | 7.6203
| 6833 | 7.9682
| 6834 | 8.0575
| 6835 | 6.7998
| 6836 | 7.1794
| 6837 | 7.3836
| 6838 | 7.0816
| 6839 | 7.3155
| 6840 | 8.2984
| 6841 | 7.3549
| 6842 | 7.9655
| 6843 | 8.129
| 6844 | 8.0377
| 6845 | 8.3113
| 6846 | 7.3709
| 6847 | 6.4521
| 6848 | 7.886
| 6849 | 8.5209
| 6850 | 7.1475
| 6851 | 8.1167
| 6852 | 8.9329
| 6853 | 7.8494
| 6854 | 7.023
| 6855 | 7.2073
| 6856 | 8.6413
| 6857 | 8.4023
| 6858 | 7.8763
| 6859 | 7.6674
| 6860 | 8.3801
| 6861 | 8.1238
| 6862 | 8.3179
| 6863 | 7.7766
| 6864 | 7.5591
| 6865 | 8.2597
| 6866 | 8.1425
| 6867 | 6.8603
| 6868 | 7.8455
| 6869 | 8.0575
| 6870 | 7.9902
| 6871 | 6.6069
| 6872 | 7.8109
| 6873 | 8.3166
| 6874 | 6.9166
| 6875 | 8.2971
| 6876 | 7.546
| 6877 | 7.9866
| 6878 | 8.1065
| 6879 | 7.2774
| 6880 | 8.3407
| 6881 | 7.6594
| 6882 | 6.9655
| 6883 | 8.5247
| 6884 | 7.7751
| 6885 | 8.1878
| 6886 | 8.5323
| 6887 | 7.8162
| 6888 | 8.1177
| 6889 | 8.3339
| 6890 | 8.556
| 6891 | 7.646
| 6892 | 7.5039
| 6893 | 7.9796
| 6894 | 7.9569
| 6895 | 7.7914
| 6896 | 8.2894
| 6897 | 7.6009
| 6898 | 8.8918
| 6899 | 7.976
| 6900 | 8.2819
| 6901 | 7.6493
| 6902 | 6.4627
| 6903 | 8.1352
| 6904 | 7.4123
| 6905 | 7.6742
| 6906 | 8.2229
| 6907 | 7.817
| 6908 | 8.7045
| 6909 | 8.2512
| 6910 | 8.7334
| 6911 | 7.6067
| 6912 | 8.7045
| 6913 | 6.9213
| 6914 | 7.7142
| 6915 | 8.2894
| 6916 | 7.7311
| 6917 | 8.1659
| 6918 | 7.083
| 6919 | 7.1451
| 6920 | 7.3588
| 6921 | 7.5015
| 6922 | 8.3559
| 6923 | 7.2494
| 6924 | 7.5491
| 6925 | 7.8393
| 6926 | 8.2034
| 6927 | 7.3948
| 6928 | 6.4198
| 6929 | 8.4989
| 6930 | 7.2356
| 6931 | 7.0084
| 6932 | 8.61
| 6933 | 7.847
| 6934 | 8.3559
| 6935 | 7.6288
| 6936 | 7.646
| 6937 | 6.2578
| 6938 | 8.4526
| 6939 | 7.5628
| 6940 | 7.8659
| 6941 | 7.2706
| 6942 | 8.7368
| 6943 | 7.8463
| 6944 | 7.8308
| 6945 | 7.8932
| 6946 | 7.9129
| 6947 | 8.179
| 6948 | 8.1085
| 6949 | 8.152
| 6950 | 8.6146
| 6951 | 8.8625
| 6952 | 8.2264
| 6953 | 7.6262
| 6954 | 8.0807
| 6955 | 8.2252
| 6956 | 8.19
| 6957 | 8.1136
| 6958 | 8.0876
| 6959 | 7.0426
| 6960 | 8.6123
| 6961 | 6.8692
| 6962 | 8.3801
| 6963 | 7.5479
| 6964 | 7.4937
| 6965 | 7.1446
| 6966 | 8.833
| 6967 | 7.4913
| 6968 | 8.3503
| 6969 | 7.5343
| 6970 | 7.7411
| 6971 | 7.2078
| 6972 | 8.5684
| 6973 | 7.4536
| 6974 | 8.0082
| 6975 | 8.4428
| 6976 | 7.1215
| 6977 | 6.8515
| 6978 | 7.8924
| 6979 | 7.9113
| 6980 | 8.6868
| 6981 | 6.7998
| 6982 | 8.0064
| 6983 | 7.9902
| 6984 | 7.2331
| 6985 | 7.9673
| 6986 | 8.4144
| 6987 | 7.2422
| 6988 | 8.3352
| 6989 | 7.9725
| 6990 | 7.8132
| 6991 | 7.5855
| 6992 | 7.5855
| 6993 | 7.9271
| 6994 | 8.2012
| 6995 | 7.438
| 6996 | 8.0604
| 6997 | 8.256
| 6998 | 7.4665
| 6999 | 8.1015
| 7000 | 8.2907
| 7001 | 8.79
| 7002 | 7.4724
| 7003 | 8.7816
| 7004 | 7.8731
| 7005 | 7.7825
| 7006 | 7.8957
| 7007 | 7.7892
| 7008 | 7.8277
| 7009 | 8.8918
| 7010 | 8.0758
| 7011 | 8.0265
| 7012 | 8.6489
| 7013 | 8.0565
| 7014 | 7.4461
| 7015 | 7.0718
| 7016 | 7.9804
| 7017 | 8.3489
| 7018 | 7.4919
| 7019 | 7.0344
| 7020 | 8.0386
| 7021 | 7.7832
| 7022 | 7.9457
| 7023 | 6.4163
| 7024 | 8.1856
| 7025 | 7.5868
| 7026 | 7.1441
| 7027 | 7.8884
| 7028 | 6.5031
| 7029 | 7.1607
| 7030 | 8.0127
| 7031 | 8.1446
| 7032 | 8.6314
| 7033 | 8.2416
| 7034 | 8.6193
| 7035 | 7.5368
| 7036 | 7.3112
| 7037 | 8.1177
| 7038 | 8.4558
| 7039 | 8.4444
| 7040 | 7.8892
| 7041 | 8.0452
| 7042 | 8.1823
| 7043 | 7.7671
| 7044 | 8.2536
| 7045 | 8.1218
| 7046 | 8.3686
| 7047 | 7.3642
| 7048 | 8.0256
| 7049 | 7.1402
| 7050 | 7.5312
| 7051 | 7.0611
| 7052 | 7.1359
| 7053 | 7.724
| 7054 | 7.7072
| 7055 | 8.2046
| 7056 | 8.3859
| 7057 | 7.9063
| 7058 | 8.0642
| 7059 | 8.0585
| 7060 | 7.6838
| 7061 | 7.9717
| 7062 | 7.0184
| 7063 | 7.66
| 7064 | 8.7943
| 7065 | 8.7816
| 7066 | 7.5678
| 7067 | 8.256
| 7068 | 7.5105
| 7069 | 8.3743
| 7070 | 8.2428
| 7071 | 8.5209
| 7072 | 7.3566
| 7073 | 7.3321
| 7074 | 7.0084
| 7075 | 8.6123
| 7076 | 7.6073
| 7077 | 6.9864
| 7078 | 8.6338
| 7079 | 7.4647
| 7080 | 7.3489
| 7081 | 7.463
| 7082 | 8.021
| 7083 | 7.9956
| 7084 | 7.6381
| 7085 | 8.3629
| 7086 | 7.9938
| 7087 | 8.5832
| 7088 | 7.7533
| 7089 | 8.8692
| 7090 | 7.392
| 7091 | 7.2098
| 7092 | 6.671
| 7093 | 7.4565
| 7094 | 7.8565
| 7095 | 8.5747
| 7096 | 7.3495
| 7097 | 6.9501
| 7098 | 7.2229
| 7099 | 7.9088
| 7100 | 5.8326
| 7101 | 7.2371
| 7102 | 8.6054
| 7103 | 8.5832
| 7104 | 8.4575
| 7105 | 8.1055
| 7106 | 7.1311
| 7107 | 6.8473
| 7108 | 7.7093
| 7109 | 7.6708
| 7110 | 8.0955
| 7111 | 7.8916
| 7112 | 8.4795
| 7113 | 7.2889
| 7114 | 7.6151
| 7115 | 8.5135
| 7116 | 7.4955
| 7117 | 8.4726
| 7118 | 8.0681
| 7119 | 7.2128
| 7120 | 7.9717
| 7121 | 6.2048
| 7122 | 8.0768
| 7123 | 8.0886
| 7124 | 8.7508
| 7125 | 8.2584
| 7126 | 7.8691
| 7127 | 8.1404
| 7128 | 8.3035
| 7129 | 7.6688
| 7130 | 7.101
| 7131 | 7.5805
| 7132 | 8.2882
| 7133 | 8.37
| 7134 | 7.6315
| 7135 | 6.9461
| 7136 | 8.3258
| 7137 | 7.9238
| 7138 | 7.6035
| 7139 | 7.9509
| 7140 | 7.148
| 7141 | 8.048
| 7142 | 8.2806
| 7143 | 6.8666
| 7144 | 7.3864
| 7145 | 7.1631
| 7146 | 7.817
| 7147 | 7.2417
| 7148 | 8.1735
| 7149 | 7.8178
| 7150 | 6.8149
| 7151 | 8.1269
| 7152 | 8.4526
| 7153 | 7.3375
| 7154 | 8.3615
| 7155 | 8.0219
| 7156 | 8.2719
| 7157 | 7.2963
| 7158 | 7.7454
| 7159 | 8.5007
| 7160 | 8.2023
| 7161 | 7.337
| 7162 | 7.1019
| 7163 | 8.1956
| 7164 | 7.6041
| 7165 | 8.1065
| 7166 | 7.8541
| 7167 | 7.7656
| 7168 | 7.7017
| 7169 | 7.2058
| 7170 | 7.1043
| 7171 | 7.9381
| 7172 | 6.8908
| 7173 | 7.908
| 7174 | 7.8385
| 7175 | 7.4328
| 7176 | 8.5247
| 7177 | 8.3643
| 7178 | 8.4332
| 7179 | 7.5269
| 7180 | 8.0965
| 7181 | 7.9415
| 7182 | 8.446
| 7183 | 8.0367
| 7184 | 8.0652
| 7185 | 7.3714
| 7186 | 7.8385
| 7187 | 6.656
| 7188 | 7.5166
| 7189 | 7.8285
| 7190 | 8.5811
| 7191 | 8.1045
| 7192 | 7.3847
| 7193 | 7.5887
| 7194 | 7.148
| 7195 | 8.4575
| 7196 | 8.4428
| 7197 | 7.8285
| 7198 | 7.8262
| 7199 | 7.8707
| 7200 | 8.8033
| 7201 | 7.5227
| 7202 | 7.0362
| 7203 | 7.8747
| 7204 | 8.3615
| 7205 | 8.6363
| 7206 | 8.5622
| 7207 | 7.0802
| 7208 | 7.5647
| 7209 | 8.1478
| 7210 | 7.2905
| 7211 | 8.3978
| 7212 | 8.2882
| 7213 | 8.1025
| 7214 | 7.3262
| 7215 | 8.5622
| 7216 | 8.6241
| 7217 | 8.5964
| 7218 | 7.8155
| 7219 | 7.4443
| 7220 | 7.7368
| 7221 | 6.8959
| 7222 | 8.2584
| 7223 | 7.3892
| 7224 | 8.6009
| 7225 | 6.641
| 7226 | 8.0219
| 7227 | 7.7461
| 7228 | 8.1648
| 7229 | 8.4726
| 7230 | 7.703
| 7231 | 6.8306
| 7232 | 7.2556
| 7233 | 7.3993
| 7234 | 8.8127
| 7235 | 7.703
| 7236 | 8.6839
| 7237 | 8.1488
| 7238 | 8.416
| 7239 | 8.3559
| 7240 | 8.0749
| 7241 | 7.4202
| 7242 | 7.5836
| 7243 | 8.0623
| 7244 | 7.2489
| 7245 | 8.8277
| 7246 | 7.2158
| 7247 | 8.0642
| 7248 | 7.1129
| 7249 | 7.4294
| 7250 | 7.6028
| 7251 | 8.2695
| 7252 | 8.6926
| 7253 | 7.5009
| 7254 | 8.0377
| 7255 | 6.9909
| 7256 | 6.8084
| 7257 | 8.3448
| 7258 | 8.231
| 7259 | 7.7254
| 7260 | 7.9163
| 7261 | 8.7015
| 7262 | 8.0623
| 7263 | 7.3016
| 7264 | 7.0658
| 7265 | 7.9725
| 7266 | 8.2856
| 7267 | 8.1967
| 7268 | 8.7657
| 7269 | 8.0414
| 7270 | 8.2393
| 7271 | 7.5535
| 7272 | 8.1595
| 7273 | 8.4222
| 7274 | 7.6009
| 7275 | 7.7269
| 7276 | 7.5516
| 7277 | 8.1425
| 7278 | 8.5421
| 7279 | 8.7368
| 7280 | 7.0148
| 7281 | 8.0284
| 7282 | 8.0788
| 7283 | 8.2334
| 7284 | 8.4709
| 7285 | 8.3545
| 7286 | 8.2719
| 7287 | 8.6289
| 7288 | 7.9569
| 7289 | 8.1228
| 7290 | 8.1207
| 7291 | 7.2868
| 7292 | 7.2634
| 7293 | 7.5591
| 7294 | 7.9655
| 7295 | 6.5931
| 7296 | 8.1085
| 7297 | 7.654
| 7298 | 8.2091
| 7299 | 8.1126
| 7300 | 7.8876
| 7301 | 8.3166
| 7302 | 8.717
| 7303 | 8.8384
| 7304 | 6.7552
| 7305 | 7.3397
| 7306 | 7.9638
| 7307 | 7.6387
| 7308 | 7.0863
| 7309 | 7.9647
| 7310 | 8.617
| 7311 | 8.4175
| 7312 | 7.9372
| 7313 | 8.2264
| 7314 | 8.0118
| 7315 | 7.5355
| 7316 | 7.9947
| 7317 | 7.8723
| 7318 | 8.3462
| 7319 | 8.069
| 7320 | 8.4316
| 7321 | 8.0925
| 7322 | 6.9846
| 7323 | 8.4625
| 7324 | 6.999
| 7325 | 7.9406
| 7326 | 7.2361
| 7327 | 8.7775
| 7328 | 7.5578
| 7329 | 7.6106
| 7330 | 6.5953
| 7331 | 7.3764
| 7332 | 7.6367
| 7333 | 8.0633
| 7334 | 7.2644
| 7335 | 6.8063
| 7336 | 6.9673
| 7337 | 8.5789
| 7338 | 6.9629
| 7339 | 8.508
| 7340 | 8.3166
| 7341 | 8.0127
| 7342 | 7.4259
| 7343 | 8.1867
| 7344 | 8.4191
| 7345 | 8.4364
| 7346 | 6.9313
| 7347 | 7.17
| 7348 | 8.1573
| 7349 | 7.5622
| 7350 | 7.7368
| 7351 | 7.7649
| 7352 | 7.5497
| 7353 | 8.0935
| 7354 | 7.7693
| 7355 | 8.5135
| 7356 | 8.6955
| 7357 | 7.6947
| 7358 | 7.0934
| 7359 | 7.4168
| 7360 | 7.6171
| 7361 | 6.6205
| 7362 | 7.9526
| 7363 | 7.4225
| 7364 | 7.05
| 7365 | 7.6803
| 7366 | 7.3353
| 7367 | 8.5061
| 7368 | 8.1541
| 7369 | 7.9787
| 7370 | 7.9398
| 7371 | 6.3523
| 7372 | 7.84
| 7373 | 7.7447
| 7374 | 7.4594
| 7375 | 7.6872
| 7376 | 6.4174
| 7377 | 8.2346
| 7378 | 8.8277
| 7379 | 7.2525
| 7380 | 8.483
| 7381 | 8.2252
| 7382 | 8.3772
| 7383 | 6.267
| 7384 | 7.8147
| 7385 | 7.8924
| 7386 | 6.7123
| 7387 | 8.0461
| 7388 | 6.841
| 7389 | 7.35
| 7390 | 7.3091
| 7391 | 7.1383
| 7392 | 8.1627
| 7393 | 7.6003
| 7394 | 8.1659
| 7395 | 8.3874
| 7396 | 7.6197
| 7397 | 8.91
| 7398 | 7.8803
| 7399 | 7.1833
| 7400 | 7.969
| 7401 | 7.8771
| 7402 | 7.2853
| 7403 | 8.5876
| 7404 | 6.8696
| 7405 | 7.7072
| 7406 | 7.8393
| 7407 | 8.2299
| 7408 | 7.3155
| 7409 | 7.8949
| 7410 | 8.4083
| 7411 | 8.1945
| 7412 | 7.6996
| 7413 | 6.2942
| 7414 | 7.2098
| 7415 | 8.2707
| 7416 | 8.6054
| 7417 | 8.6314
| 7418 | 7.6151
| 7419 | 7.9129
| 7420 | 8.2488
| 7421 | 8.1096
| 7422 | 7.2921
| 7423 | 8.5191
| 7424 | 7.1804
| 7425 | 8.0091
| 7426 | 8.1478
| 7427 | 8.7775
| 7428 | 7.3792
| 7429 | 7.1422
| 7430 | 8.1136
| 7431 | 7.8292
| 7432 | 8.1075
| 7433 | 8.7943
| 7434 | 7.7121
| 7435 | 8.1331
| 7436 | 8.7015
| 7437 | 7.48
| 7438 | 7.4322
| 7439 | 7.0915
| 7440 | 8.8225
| 7441 | 7.6688
| 7442 | 7.3692
| 7443 | 7.0275
| 7444 | 8.1005
| 7445 | 8.342
| 7446 | 8.0228
| 7447 | 8.4953
| 7448 | 7.8049
| 7449 | 8.97
| 7450 | 8.0817
| 7451 | 8.1436
| 7452 | 7.8924
| 7453 | 8.1341
| 7454 | 7.5641
| 7455 | 8.224
| 7456 | 7.8064
| 7457 | 7.6553
| 7458 | 8.0965
| 7459 | 7.0648
| 7460 | 7.7892
| 7461 | 8.1383
| 7462 | 8.7437
| 7463 | 8.6783
| 7464 | 7.1504
| 7465 | 8.3393
| 7466 | 8.2794
| 7467 | 8.2609
| 7468 | 7.0849
| 7469 | 7.64
| 7470 | 7.8965
| 7471 | 8.2001
| 7472 | 7.3021
| 7473 | 6.2081
| 7474 | 7.0967
| 7475 | 6.5957
| 7476 | 7.6223
| 7477 | 6.9036
| 7478 | 7.9279
| 7479 | 8.0876
| 7480 | 7.7347
| 7481 | 7.172
| 7482 | 8.4744
| 7483 | 7.5849
| 7484 | 7.9171
| 7485 | 7.9647
| 7486 | 7.8612
| 7487 | 8.4558
| 7488 | 7.5411
| 7489 | 6.5748
| 7490 | 8.5153
| 7491 | 7.6381
| 7492 | 8.1187
| 7493 | 6.7143
| 7494 | 7.814
| 7495 | 8.2831
| 7496 | 7.7892
| 7497 | 7.4265
| 7498 | 7.7707
| 7499 | 7.2428
| 7500 | 8.4008
| 7501 | 6.9704
| 7502 | 7.6009
| 7503 | 7.9509
| 7504 | 7.0344
| 7505 | 8.021
| 7506 | 8.0604
| 7507 | 7.9858
| 7508 | 7.0417
| 7509 | 8.4023
| 7510 | 7.6321
| 7511 | 7.4386
| 7512 | 7.5597
| 7513 | 6.7068
| 7514 | 7.6892
| 7515 | 8.3671
| 7516 | 7.576
| 7517 | 7.8478
| 7518 | 8.3393
| 7519 | 8.4575
| 7520 | 7.0271
| 7521 | 8.4316
| 7522 | 7.9638
| 7523 | 8.07
| 7524 | 8.4412
| 7525 | 7.8102
| 7526 | 7.4225
| 7527 | 8.2334
| 7528 | 8.6955
| 7529 | 8.3126
| 7530 | 7.8541
| 7531 | 7.5337
| 7532 | 7.9875
| 7533 | 7.9822
| 7534 | 8.5209
| 7535 | 8.5191
| 7536 | 7.5466
| 7537 | 8.2894
| 7538 | 7.8208
| 7539 | 7.8659
| 7540 | 8.3629
| 7541 | 6.5645
| 7542 | 8.3671
| 7543 | 8.7015
| 7544 | 7.8117
| 7545 | 8.67
| 7546 | 8.3993
| 7547 | 8.071
| 7548 | 8.3714
| 7549 | 7.899
| 7550 | 8.4592
| 7551 | 8.1116
| 7552 | 6.7329
| 7553 | 8.7508
| 7554 | 8.033
| 7555 | 8.592
| 7556 | 7.2158
| 7557 | 8.5726
| 7558 | 7.703
| 7559 | 8.592
| 7560 | 7.5027
| 7561 | 7.4403
| 7562 | 8.1415
| 7563 | 7.8354
| 7564 | 7.6282
| 7565 | 8.1978
| 7566 | 7.3998
| 7567 | 7.0143
| 7568 | 7.6216
| 7569 | 8.7775
| 7570 | 8.2287
| 7571 | 8.267
| 7572 | 7.3898
| 7573 | 8.0788
| 7574 | 7.2863
| 7575 | 7.4202
| 7576 | 8.8625
| 7577 | 8.2428
| 7578 | 7.7914
| 7579 | 8.4114
| 7580 | 7.3473
| 7581 | 8.4269
| 7582 | 8.8175
| 7583 | 7.992
| 7584 | 8.8079
| 7585 | 7.6913
| 7586 | 7.6742
| 7587 | 8.383
| 7588 | 7.9238
| 7589 | 8.3757
| 7590 | 8.4428
| 7591 | 7.5051
| 7592 | 8.1394
| 7593 | 7.5417
| 7594 | 8.2512
| 7595 | 8.1269
| 7596 | 7.4806
| 7597 | 6.6888
| 7598 | 7.5343
| 7599 | 6.9691
| 7600 | 8.1779
| 7601 | 8.3933
| 7602 | 8.5747
| 7603 | 6.9105
| 7604 | 8.1187
| 7605 | 8.6077
| 7606 | 8.2125
| 7607 | 8.5061
| 7608 | 7.658
| 7609 | 7.9491
| 7610 | 7.1636
| 7611 | 7.8941
| 7612 | 7.7656
| 7613 | 8.7696
| 7614 | 8.5266
| 7615 | 8.7368
| 7616 | 8.6077
| 7617 | 7.6831
| 7618 | 8.483
| 7619 | 8.7402
| 7620 | 7.1033
| 7621 | 8.5811
| 7622 | 8.7581
| 7623 | 8.3587
| 7624 | 8.0349
| 7625 | 7.8269
| 7626 | 6.5053
| 7627 | 8.0671
| 7628 | 7.8254
| 7629 | 7.0184
| 7630 | 7.8779
| 7631 | 8.0905
| 7632 | 7.2275
| 7633 | 7.8932
| 7634 | 7.6851
| 7635 | 7.8795
| 7636 | 8.1856
| 7637 | 8.1702
| 7638 | 7.0202
| 7639 | 7.5894
| 7640 | 7.7959
| 7641 | 8.3048
| 7642 | 8.071
| 7643 | 6.9261
| 7644 | 7.1903
| 7645 | 8.6413
| 7646 | 7.7497
| 7647 | 7.8572
| 7648 | 7.5622
| 7649 | 8.6593
| 7650 | 7.8292
| 7651 | 8.2137
| 7652 | 8.4098
| 7653 | 7.4443
| 7654 | 6.9413
| 7655 | 7.8715
| 7656 | 8.6413
| 7657 | 6.619
| 7658 | 8.1187
| 7659 | 7.0008
| 7660 | 7.3998
| 7661 | 8.1197
| 7662 | 7.168
| 7663 | 8.2597
| 7664 | 8.4542
| 7665 | 8.2907
| 7666 | 8.3978
| 7667 | 7.3123
| 7668 | 8.1834
| 7669 | 7.9813
| 7670 | 8.4847
| 7671 | 8.7138
| 7672 | 7.7744
| 7673 | 7.372
| 7674 | 7.6341
| 7675 | 8.131
| 7676 | 7.9229
| 7677 | 7.0399
| 7678 | 7.0611
| 7679 | 7.4682
| 7680 | 8.8625
| 7681 | 8.4412
| 7682 | 7.7936
| 7683 | 8.1552
| 7684 | 7.2407
| 7685 | 8.3272
| 7686 | 7.9699
| 7687 | 7.9638
| 7688 | 8.1616
| 7689 | 7.7219
| 7690 | 8.97
| 7691 | 8.3573
| 7692 | 7.6414
| 7693 | 8.0896
| 7694 | 7.6407
| 7695 | 7.4397
| 7696 | 7.0348
| 7697 | 6.9954
| 7698 | 8.4989
| 7699 | 7.5653
| 7700 | 7.3413
| 7701 | 7.7475
| 7702 | 7.9595
| 7703 | 7.6295
| 7704 | 7.3959
| 7705 | 7.6961
| 7706 | 8.416
| 7707 | 8.483
| 7708 | 7.3664
| 7709 | 5.6794
| 7710 | 8.4526
| 7711 | 7.7269
| 7712 | 8.0945
| 7713 | 8.8625
| 7714 | 7.4647
| 7715 | 8.2183
| 7716 | 8.0028
| 7717 | 7.5951
| 7718 | 8.9329
| 7719 | 8.5401
| 7720 | 7.6803
| 7721 | 7.2407
| 7722 | 7.8667
| 7723 | 8.2658
| 7724 | 6.2869
| 7725 | 7.5817
| 7726 | 8.2682
| 7727 | 8.6363
| 7728 | 8.2512
| 7729 | 8.2682
| 7730 | 7.6594
| 7731 | 7.4665
| 7732 | 7.3473
| 7733 | 6.9563
| 7734 | 8.6363
| 7735 | 7.9305
| 7736 | 7.9055
| 7737 | 8.5007
| 7738 | 7.4368
| 7739 | 7.3299
| 7740 | 6.6133
| 7741 | 7.7354
| 7742 | 7.033
| 7743 | 7.4818
| 7744 | 8.8384
| 7745 | 7.1422
| 7746 | 7.2148
| 7747 | 6.8244
| 7748 | 8.0788
| 7749 | 8.5362
| 7750 | 6.8373
| 7751 | 7.8439
| 7752 | 7.6533
| 7753 | 8.5854
| 7754 | 7.1388
| 7755 | 8.2707
| 7756 | 8.2682
| 7757 | 7.9022
| 7758 | 8.4284
| 7759 | 8.8918
| 7760 | 7.5093
| 7761 | 7.5069
| 7762 | 7.6197
| 7763 | 7.8262
| 7764 | 7.2649
| 7765 | 8.1156
| 7766 | 7.8691
| 7767 | 7.9769
| 7768 | 7.28
| 7769 | 6.5409
| 7770 | 8.2034
| 7771 | 7.9491
| 7772 | 8.0155
| 7773 | 7.2753
| 7774 | 8.7544
| 7775 | 8.3312
| 7776 | 8.1146
| 7777 | 7.2551
| 7778 | 7.53
| 7779 | 7.5497
| 7780 | 7.749
| 7781 | 8.5601
| 7782 | 7.7862
| 7783 | 8.8384
| 7784 | 7.7781
| 7785 | 8.2057
| 7786 | 8.0633
| 7787 | 8.9005
| 7788 | 7.7693
| 7789 | 7.4806
| 7790 | 7.5672
| 7791 | 7.2738
| 7792 | 8.3714
| 7793 | 7.6742
| 7794 | 8.3889
| 7795 | 6.7341
| 7796 | 7.8463
| 7797 | 7.2556
| 7798 | 8.2488
| 7799 | 8.0613
| 7800 | 8.5007
| 7801 | 6.3701
| 7802 | 7.2811
| 7803 | 8.8441
| 7804 | 7.7389
| 7805 | 8.3407
| 7806 | 8.4692
| 7807 | 8.0768
| 7808 | 7.6783
| 7809 | 7.3224
| 7810 | 8.3503
| 7811 | 7.6216
| 7812 | 7.6171
| 7813 | 8.2945
| 7814 | 7.8908
| 7815 | 8.0807
| 7816 | 7.6009
| 7817 | 6.7924
| 7818 | 8.5266
| 7819 | 7.6769
| 7820 | 7.7869
| 7821 | 8.7368
| 7822 | 8.2287
| 7823 | 6.6179
| 7824 | 8.0613
| 7825 | 8.654
| 7826 | 7.7862
| 7827 | 8.0001
| 7828 | 7.4432
| 7829 | 8.9005
| 7830 | 7.3687
| 7831 | 7.3598
| 7832 | 8.1713
| 7833 | 7.8819
| 7834 | 8.2194
| 7835 | 8.6868
| 7836 | 8.131
| 7837 | 7.6742
| 7838 | 7.3467
| 7839 | 8.2476
| 7840 | 7.597
| 7841 | 6.844
| 7842 | 7.1749
| 7843 | 7.3107
| 7844 | 7.1685
| 7845 | 7.5741
| 7846 | 8.6646
| 7847 | 7.4038
| 7848 | 8.1552
| 7849 | 8.0284
| 7850 | 7.6308
| 7851 | 8.4592
| 7852 | 7.5958
| 7853 | 8.8838
| 7854 | 7.729
| 7855 | 8.0836
| 7856 | 7.9196
| 7857 | 7.4397
| 7858 | 8.4175
| 7859 | 6.6671
| 7860 | 8.2194
| 7861 | 7.9196
| 7862 | 8.3448
| 7863 | 8.2819
| 7864 | 8.4709
| 7865 | 7.858
| 7866 | 7.5202
| 7867 | 8.1933
| 7868 | 7.9708
| 7869 | 8.1659
| 7870 | 7.5208
| 7871 | 7.8087
| 7872 | 7.6975
| 7873 | 7.5221
| 7874 | 8.6054
| 7875 | 8.4847
| 7876 | 7.3687
| 7877 | 7.8981
| 7878 | 8.3339
| 7879 | 7.9063
| 7880 | 7.8277
| 7881 | 7.7944
| 7882 | 7.6433
| 7883 | 7.9831
| 7884 | 7.6048
| 7885 | 7.279
| 7886 | 8.4761
| 7887 | 7.3451
| 7888 | 7.814
| 7889 | 6.8934
| 7890 | 6.9985
| 7891 | 8.508
| 7892 | 8.8763
| 7893 | 7.7914
| 7894 | 7.28
| 7895 | 7.463
| 7896 | 8.717
| 7897 | 8.069
| 7898 | 7.7156
| 7899 | 7.5337
| 7900 | 8.2091
| 7901 | 6.9002
| 7902 | 7.4525
| 7903 | 8.1341
| 7904 | 7.3808
| 7905 | 8.2856
| 7906 | 8.3545
| 7907 | 8.4592
| 7908 | 8.0358
| 7909 | 7.9577
| 7910 | 7.8087
| 7911 | 8.0778
| 7912 | 7.3016
| 7913 | 8.3815
| 7914 | 8.0955
| 7915 | 7.7591
| 7916 | 8.19
| 7917 | 8.67
| 7918 | 8.1126
| 7919 | 7.7051
| 7920 | 6.8994
| 7921 | 8.129
| 7922 | 8.7202
| 7923 | 8.3714
| 7924 | 8.2476
| 7925 | 8.0739
| 7926 | 7.3343
| 7927 | 8.2252
| 7928 | 7.4208
| 7929 | 8.1207
| 7930 | 7.4055
| 7931 | 6.6475
| 7932 | 8.2346
| 7933 | 7.7375
| 7934 | 8.3874
| 7935 | 7.3937
| 7936 | 8.1478
| 7937 | 8.5789
| 7938 | 7.5166
| 7939 | 7.8285
| 7940 | 7.7058
| 7941 | 6.8498
| 7942 | 8.5811
| 7943 | 6.38
| 7944 | 8.7619
| 7945 | 8.2452
| 7946 | 8.2171
| 7947 | 8.0778
| 7948 | 7.8525
| 7949 | 6.3752
| 7950 | 8.6241
| 7951 | 8.3022
| 7952 | 7.7114
| 7953 | 8.3903
| 7954 | 8.0518
| 7955 | 7.1167
| 7956 | 7.82
| 7957 | 8.6811
| 7958 | 8.4316
| 7959 | 7.77
| 7960 | 8.4175
| 7961 | 7.4185
| 7962 | 7.9965
| 7963 | 7.7051
| 7964 | 6.9088
| 7965 | 6.2998
| 7966 | 8.0082
| 7967 | 8.4237
| 7968 | 6.6861
| 7969 | 8.1757
| 7970 | 8.4608
| 7971 | 8.7107
| 7972 | 7.644
| 7973 | 7.4202
| 7974 | 8.5247
| 7975 | 6.6791
| 7976 | 7.2013
| 7977 | 7.4072
| 7978 | 8.4709
| 7979 | 8.1911
| 7980 | 6.822
| 7981 | 7.9263
| 7982 | 8.2334
| 7983 | 7.6203
| 7984 | 7.3698
| 7985 | 8.071
| 7986 | 7.5628
| 7987 | 7.5817
| 7988 | 8.2869
| 7989 | 7.7051
| 7990 | 7.3278
| 7991 | 7.9022
| 7992 | 6.8789
| 7993 | 8.6673
| 7994 | 7.3027
| 7995 | 8.2869
| 7996 | 7.3197
| 7997 | 8.1956
| 7998 | 7.4202
| 7999 | 8.4237
| 8000 | 8.4953
| 8001 | 8.1768
| 8002 | 7.6493
| 8003 | 7.111
| 8004 | 8.6054
| 8005 | 8.0302
| 8006 | 7.9364
| 8007 | 7.817
| 8008 | 8.2103
| 8009 | 8.3061
| 8010 | 7.4455
| 8011 | 6.9704
| 8012 | 8.6077
| 8013 | 8.7696
| 8014 | 8.13
| 8015 | 8.7619
| 8016 | 8.7138
| 8017 | 8.3325
| 8018 | 7.1431
| 8019 | 8.1415
| 8020 | 8.1085
| 8021 | 7.9638
| 8022 | 8.3009
| 8023 | 8.3009
| 8024 | 7.4117
| 8025 | 8.6314
| 8026 | 7.5798
| 8027 | 7.4818
| 8028 | 8.0064
| 8029 | 7.7832
| 8030 | 7.3566
| 8031 | 7.4117
| 8032 | 7.0779
| 8033 | 8.1259
| 8034 | 7.4438
| 8035 | 8.55
| 8036 | 8.4023
| 8037 | 8.4625
| 8038 | 8.0797
| 8039 | 8.5098
| 8040 | 8.1259
| 8041 | 7.6125
| 8042 | 8.0518
| 8043 | 6.5707
| 8044 | 7.6961
| 8045 | 7.0207
| 8046 | 8.554
| 8047 | 6.8968
| 8048 | 7.5703
| 8049 | 7.6249
| 8050 | 8.0749
| 8051 | 8.3874
| 8052 | 6.7632
| 8053 | 7.3337
| 8054 | 7.9629
| 8055 | 7.0098
| 8056 | 7.9246
| 8057 | 7.1412
| 8058 | 8.416
| 8059 | 7.9682
| 8060 | 8.6926
| 8061 | 7.7825
| 8062 | 8.2114
| 8063 | 7.8549
| 8064 | 8.0508
| 8065 | 8.0836
| 8066 | 8.0817
| 8067 | 7.2163
| 8068 | 7.5251
| 8069 | 7.3544
| 8070 | 8.4493
| 8071 | 8.6619
| 8072 | 6.8515
| 8073 | 6.9157
| 8074 | 8.1352
| 8075 | 8.7858
| 8076 | 7.5221
| 8077 | 8.1156
| 8078 | 6.7072
| 8079 | 8.1681
| 8080 | 8.1648
| 8081 | 7.1311
| 8082 | 7.8525
| 8083 | 7.101
| 8084 | 8.3948
| 8085 | 7.9254
| 8086 | 7.0542
| 8087 | 8.5362
| 8088 | 7.908
| 8089 | 8.4316
| 8090 | 8.2609
| 8091 | 8.554
| 8092 | 7.8285
| 8093 | 8.5684
| 8094 | 7.652
| 8095 | 7.2639
| 8096 | 7.7454
| 8097 | 7.9305
| 8098 | 8.0905
| 8099 | 7.6381
| 8100 | 7.1248
| 8101 | 7.1943
| 8102 | 8.1702
| 8103 | 7.6892
| 8104 | 6.7661
| 8105 | 7.95
| 8106 | 7.6394
| 8107 | 7.1287
| 8108 | 8.6955
| 8109 | 8.7657
| 8110 | 8.1146
| 8111 | 8.1383
| 8112 | 8.3786
| 8113 | 8.0247
| 8114 | 8.2057
| 8115 | 6.9691
| 8116 | 7.77
| 8117 | 7.7518
| 8118 | 8.1045
| 8119 | 8.2057
| 8120 | 8.0975
| 8121 | 8.1757
| 8122 | 7.9196
| 8123 | 7.8998
| 8124 | 7.251
| 8125 | 7.5754
| 8126 | 7.8277
| 8127 | 8.4023
| 8128 | 8.292
| 8129 | 8.2068
| 8130 | 8.8918
| 8131 | 7.4866
| 8132 | 8.3272
| 8133 | 8.6463
| 8134 | 8.544
| 8135 | 7.82
| 8136 | 8.2322
| 8137 | 7.6321
| 8138 | 8.3686
| 8139 | 8.6388
| 8140 | 7.8447
| 8141 | 8.2524
| 8142 | 8.6123
| 8143 | 6.8994
| 8144 | 6.6749
| 8145 | 7.4021
| 8146 | 7.9415
| 8147 | 7.6899
| 8148 | 8.2882
| 8149 | 8.7015
| 8150 | 7.8439
| 8151 | 7.8185
| 8152 | 7.4741
| 8153 | 7.7936
| 8154 | 7.2138
| 8155 | 8.1509
| 8156 | 8.1259
| 8157 | 7.0977
| 8158 | 6.3523
| 8159 | 8.1845
| 8160 | 8.5876
| 8161 | 7.6968
| 8162 | 8.7544
| 8163 | 7.2249
| 8164 | 7.5386
| 8165 | 7.9263
| 8166 | 8.3074
| 8167 | 7.9893
| 8168 | 8.2548
| 8169 | 8.1823
| 8170 | 7.8795
| 8171 | 8.8692
| 8172 | 7.9113
| 8173 | 7.8517
| 8174 | 7.5779
| 8175 | 8.256
| 8176 | 7.5836
| 8177 | 7.4197
| 8178 | 7.1306
| 8179 | 8.3035
| 8180 | 6.3303
| 8181 | 7.9664
| 8182 | 8.7619
| 8183 | 7.3987
| 8184 | 8.6009
| 8185 | 6.962
| 8186 | 7.6112
| 8187 | 8.6955
| 8188 | 7.5805
| 8189 | 7.7044
| 8190 | 8.0452
| 8191 | 6.8079
| 8192 | 6.6834
| 8193 | 8.7138
| 8194 | 7.0807
| 8195 | 8.8561
| 8196 | 8.01
| 8197 | 8.3531
| 8198 | 7.8019
| 8199 | 8.1331
| 8200 | 7.5741
| 8201 | 8.2744
| 8202 | 8.5601
| 8203 | 7.4931
| 8204 | 8.3258
| 8205 | 6.9426
| 8206 | 7.9543
| 8207 | 8.256
| 8208 | 7.5423
| 8209 | 8.4144
| 8210 | 8.4412
| 8211 | 7.5063
| 8212 | 8.2476
| 8213 | 6.7916
| 8214 | 7.3364
| 8215 | 8.3573
| 8216 | 8.0228
| 8217 | 7.5051
| 8218 | 8.3587
| 8219 | 6.8469
| 8220 | 6.9731
| 8221 | 8.7437
| 8222 | 8.948
| 8223 | 8.5942
| 8224 | 7.3397
| 8225 | 7.3348
| 8226 | 7.3853
| 8227 | 8.0377
| 8228 | 7.608
| 8229 | 7.5374
| 8230 | 8.7619
| 8231 | 7.9778
| 8232 | 8.4053
| 8233 | 8.2609
| 8234 | 8.6388
| 8235 | 6.7107
| 8236 | 7.4901
| 8237 | 7.1843
| 8238 | 8.1605
| 8239 | 8.5986
| 8240 | 8.2264
| 8241 | 8.5362
| 8242 | 8.216
| 8243 | 7.7269
| 8244 | 8.5135
| 8245 | 8.5854
| 8246 | 7.9491
| 8247 | 7.7555
| 8248 | 7.4089
| 8249 | 8.8441
| 8250 | 8.2091
| 8251 | 8.6811
| 8252 | 7.7877
| 8253 | 7.1263
| 8254 | 7.6447
| 8255 | 6.5329
| 8256 | 7.658
| 8257 | 8.4129
| 8258 | 8.0293
| 8259 | 6.7349
| 8260 | 8.6314
| 8261 | 7.9039
| 8262 | 7.9238
| 8263 | 7.6348
| 8264 | 7.6567
| 8265 | 8.4659
| 8266 | 8.5601
| 8267 | 8.948
| 8268 | 8.1156
| 8269 | 8.0995
| 8270 | 7.3582
| 8271 | 6.8257
| 8272 | 8.7368
| 8273 | 7.2868
| 8274 | 8.1207
| 8275 | 8.7696
| 8276 | 8.6338
| 8277 | 7.5553
| 8278 | 8.6031
| 8279 | 7.8147
| 8280 | 7.6473
| 8281 | 7.2397
| 8282 | 7.7375
| 8283 | 8.2744
| 8284 | 7.908
| 8285 | 7.7598
| 8286 | 7.8949
| 8287 | 7.8239
| 8288 | 7.2874
| 8289 | 7.47
| 8290 | 8.0925
| 8291 | 7.8246
| 8292 | 7.6035
| 8293 | 7.6769
| 8294 | 7.3192
| 8295 | 7.599
| 8296 | 8.0191
| 8297 | 6.6062
| 8298 | 8.1563
| 8299 | 7.406
| 8300 | 7.6473
| 8301 | 7.5516
| 8302 | 8.1933
| 8303 | 8.0623
| 8304 | 6.7576
| 8305 | 6.7552
| 8306 | 7.9121
| 8307 | 8.5747
| 8308 | 7.9006
| 8309 | 7.062
| 8310 | 8.001
| 8311 | 6.5934
| 8312 | 8.97
| 8313 | 7.8447
| 8314 | 8.4493
| 8315 | 8.0623
| 8316 | 7.2868
| 8317 | 7.8193
| 8318 | 8.5285
| 8319 | 7.8998
| 8320 | 7.908
| 8321 | 7.4806
| 8322 | 8.2769
| 8323 | 8.3729
| 8324 | 7.9603
| 8325 | 6.5648
| 8326 | 7.463
| 8327 | 6.7033
| 8328 | 7.7847
| 8329 | 7.5033
| 8330 | 8.0739
| 8331 | 7.8262
| 8332 | 7.1248
| 8333 | 7.1666
| 8334 | 7.7722
| 8335 | 8.37
| 8336 | 7.5653
| 8337 | 6.6096
| 8338 | 6.8088
| 8339 | 7.8667
| 8340 | 7.171
| 8341 | 7.5215
| 8342 | 6.7936
| 8343 | 8.7508
| 8344 | 7.2691
| 8345 | 8.0965
| 8346 | 8.5601
| 8347 | 7.9787
| 8348 | 8.5747
| 8349 | 6.4254
| 8350 | 7.7247
| 8351 | 8.3889
| 8352 | 8.2882
| 8353 | 8.3859
| 8354 | 7.7562
| 8355 | 7.5779
| 8356 | 7.2743
| 8357 | 7.5331
| 8358 | 8.2369
| 8359 | 6.8569
| 8360 | 8.1967
| 8361 | 7.5535
| 8362 | 7.984
| 8363 | 7.5597
| 8364 | 7.2758
| 8365 | 8.0623
| 8366 | 8.3743
| 8367 | 7.3881
| 8368 | 6.746
| 8369 | 7.583
| 8370 | 7.6158
| 8371 | 8.3339
| 8372 | 8.0585
| 8373 | 7.9983
| 8374 | 7.6527
| 8375 | 6.9361
| 8376 | 8.2695
| 8377 | 7.8699
| 8378 | 7.6851
| 8379 | 6.6842
| 8380 | 7.7634
| 8381 | 7.8699
| 8382 | 7.1181
| 8383 | 7.1033
| 8384 | 8.592
| 8385 | 6.6931
| 8386 | 8.6463
| 8387 | 8.1531
| 8388 | 7.5522
| 8389 | 8.1075
| 8390 | 7.9039
| 8391 | 7.5951
| 8392 | 7.9313
| 8393 | 8.2137
| 8394 | 8.7657
| 8395 | 7.1157
| 8396 | 8.1207
| 8397 | 8.0339
| 8398 | 7.8216
| 8399 | 7.7591
| 8400 | 8.3074
| 8401 | 7.2665
| 8402 | 8.1238
| 8403 | 8.6926
| 8404 | 7.8162
| 8405 | 8.1228
| 8406 | 8.2057
| 8407 | 8.4129
| 8408 | 8.2091
| 8409 | 8.244
| 8410 | 8.13
| 8411 | 8.3845
| 8412 | 7.5411
| 8413 | 8.0508
| 8414 | 7.8981
| 8415 | 7.9355
| 8416 | 8.071
| 8417 | 8.4813
| 8418 | 7.8533
| 8419 | 6.9114
| 8420 | 7.4162
| 8421 | 8.4761
| 8422 | 8.5323
| 8423 | 8.0652
| 8424 | 8.67
| 8425 | 8.001
| 8426 | 7.0972
| 8427 | 6.746
| 8428 | 7.3128
| 8429 | 8.1801
| 8430 | 7.7504
| 8431 | 8.0302
| 8432 | 7.8941
| 8433 | 7.903
| 8434 | 8.3845
| 8435 | 7.0035
| 8436 | 8.4023
| 8437 | 7.0939
| 8438 | 8.1055
| 8439 | 7.5423
| 8440 | 7.7744
| 8441 | 8.2001
| 8442 | 8.4971
| 8443 | 8.3657
| 8444 | 8.0729
| 8445 | 8.4269
| 8446 | 6.9909
| 8447 | 7.5448
| 8448 | 8.1394
| 8449 | 7.8747
| 8450 | 7.0062
| 8451 | 8.1218
| 8452 | 7.3283
| 8453 | 8.2428
| 8454 | 7.5276
| 8455 | 7.3256
| 8456 | 6.9248
| 8457 | 7.7404
| 8458 | 8.2464
| 8459 | 6.444
| 8460 | 7.9047
| 8461 | 8.37
| 8462 | 8.7544
| 8463 | 7.7605
| 8464 | 6.9058
| 8465 | 8.5642
| 8466 | 7.4311
| 8467 | 8.1177
| 8468 | 7.7368
| 8469 | 6.6966
| 8470 | 7.4265
| 8471 | 8.5172
| 8472 | 7.3764
| 8473 | 7.9179
| 8474 | 7.4794
| 8475 | 7.2748
| 8476 | 8.4676
| 8477 | 8.1978
| 8478 | 8.5153
| 8479 | 8.7735
| 8480 | 7.654
| 8481 | 7.1514
| 8482 | 7.89
| 8483 | 8.0995
| 8484 | 7.9938
| 8485 | 8.544
| 8486 | 8.6619
| 8487 | 7.7959
| 8488 | 7.5479
| 8489 | 8.1933
| 8490 | 8.0414
| 8491 | 7.5386
| 8492 | 7.5136
| 8493 | 8.4761
| 8494 | 8.1509
| 8495 | 7.652
| 8496 | 8.0073
| 8497 | 8.2464
| 8498 | 8.383
| 8499 | 6.8874
| 8500 | 7.658
| 8501 | 8.25
| 8502 | 7.7247
| 8503 | 7.851
| 8504 | 6.9114
| 8505 | 8.3993
| 8506 | 7.7693
| 8507 | 8.1167
| 8508 | 7.0362
| 8509 | 8.5642
| 8510 | 7.6674
| 8511 | 8.556
| 8512 | 8.3671
| 8513 | 8.7138
| 8514 | 8.4144
| 8515 | 8.0136
| 8516 | 7.9603
| 8517 | 7.5767
| 8518 | 8.3903
| 8519 | 7.4659
| 8520 | 8.0136
| 8521 | 8.5061
| 8522 | 7.6729
| 8523 | 7.338
| 8524 | 7.9612
| 8525 | 7.4848
| 8526 | 7.1938
| 8527 | 7.9039
| 8528 | 7.2551
| 8529 | 7.5142
| 8530 | 7.46
| 8531 | 7.0727
| 8532 | 7.2148
| 8533 | 8.4558
| 8534 | 7.8432
| 8535 | 8.1146
| 8536 | 7.6668
| 8537 | 8.6413
| 8538 | 7.1903
| 8539 | 8.2958
| 8540 | 8.3179
| 8541 | 7.6054
| 8542 | 7.7598
| 8543 | 7.8004
| 8544 | 7.7482
| 8545 | 7.3446
| 8546 | 8.2869
| 8547 | 8.6123
| 8548 | 8.4175
| 8549 | 7.7191
| 8550 | 8.5601
| 8551 | 8.4642
| 8552 | 7.66
| 8553 | 8.5601
| 8554 | 6.873
| 8555 | 8.1362
| 8556 | 7.2764
| 8557 | 8.73
| 8558 | 7.5117
| 8559 | 7.8239
| 8560 | 7.899
| 8561 | 7.3359
| 8562 | 7.762
| 8563 | 6.9878
| 8564 | 7.6607
| 8565 | 8.0575
| 8566 | 6.9593
| 8567 | 7.5111
| 8568 | 7.7855
| 8569 | 7.9491
| 8570 | 7.3954
| 8571 | 6.4377
| 8572 | 8.5228
| 8573 | 7.9305
| 8574 | 8.216
| 8575 | 7.1205
| 8576 | 8.0935
| 8577 | 7.6015
| 8578 | 7.9055
| 8579 | 8.2299
| 8580 | 8.3643
| 8581 | 7.4618
| 8582 | 8.0414
| 8583 | 7.513
| 8584 | 8.267
| 8585 | 7.6865
| 8586 | 8.1605
| 8587 | 7.9974
| 8588 | 8.4744
| 8589 | 8.0508
| 8590 | 8.7202
| 8591 | 7.9664
| 8592 | 8.446
| 8593 | 7.7107
| 8594 | 8.4253
| 8595 | 8.5684
| 8596 | 8.033
| 8597 | 8.1341
| 8598 | 8.4692
| 8599 | 8.3022
| 8600 | 7.0704
| 8601 | 8.3022
| 8602 | 7.8102
| 8603 | 7.8079
| 8604 | 8.1922
| 8605 | 8.1757
| 8606 | 7.6106
| 8607 | 7.6197
| 8608 | 6.7277
| 8609 | 7.1779
| 8610 | 7.6783
| 8611 | 7.0175
| 8612 | 6.982
| 8613 | 7.9682
| 8614 | 6.4528
| 8615 | 8.0995
| 8616 | 8.0386
| 8617 | 8.3339
| 8618 | 7.2863
| 8619 | 7.0225
| 8620 | 7.5215
| 8621 | 7.4718
| 8622 | 8.5964
| 8623 | 8.0778
| 8624 | 8.0201
| 8625 | 7.4706
| 8626 | 7.1172
| 8627 | 8.7202
| 8628 | 7.8285
| 8629 | 7.0896
| 8630 | 8.0719
| 8631 | 8.3299
| 8632 | 7.8723
| 8633 | 8.3022
| 8634 | 6.7002
| 8635 | 6.7989
| 8636 | 8.4364
| 8637 | 7.7318
| 8638 | 7.4242
| 8639 | 8.6514
| 8640 | 7.5786
| 8641 | 7.8731
| 8642 | 7.3478
| 8643 | 7.2779
| 8644 | 7.0316
| 8645 | 7.8932
| 8646 | 7.7354
| 8647 | 7.6879
| 8648 | 8.1692
| 8649 | 6.9931
| 8650 | 8.0433
| 8651 | 7.933
| 8652 | 8.0556
| 8653 | 7.7086
| 8654 | 7.749
| 8655 | 8.4476
| 8656 | 8.6727
| 8657 | 7.3032
| 8658 | 7.8004
| 8659 | 8.4008
| 8660 | 7.3582
| 8661 | 7.6892
| 8662 | 8.3475
| 8663 | 7.0616
| 8664 | 8.1248
| 8665 | 8.2806
| 8666 | 8.0395
| 8667 | 6.7648
| 8668 | 8.0546
| 8669 | 7.3176
| 8670 | 8.7943
| 8671 | 7.2244
| 8672 | 8.2971
| 8673 | 6.9317
| 8674 | 8.0414
| 8675 | 7.4305
| 8676 | 7.5634
| 8677 | 8.0836
| 8678 | 8.3366
| 8679 | 7.7737
| 8680 | 7.6533
| 8681 | 8.3087
| 8682 | 7.1495
| 8683 | 8.3048
| 8684 | 7.1306
| 8685 | 8.2958
| 8686 | 7.7418
| 8687 | 7.6262
| 8688 | 8.5942
| 8689 | 7.65
| 8690 | 8.19
| 8691 | 7.9432
| 8692 | 8.416
| 8693 | 7.9022
| 8694 | 8.1404
| 8695 | 8.6265
| 8696 | 7.5472
| 8697 | 7.9271
| 8698 | 7.4391
| 8699 | 7.5245
| 8700 | 7.3825
| 8701 | 7.5166
| 8702 | 8.2148
| 8703 | 7.2422
| 8704 | 8.1167
| 8705 | 7.3069
| 8706 | 7.4311
| 8707 | 7.9778
| 8708 | 7.9725
| 8709 | 6.7778
| 8710 | 7.5417
| 8711 | 8.6755
| 8712 | 8.2572
| 8713 | 8.3462
| 8714 | 7.7425
| 8715 | 7.6348
| 8716 | 7.7482
| 8717 | 7.8193
| 8718 | 8.3686
| 8719 | 8.4175
| 8720 | 8.5768
| 8721 | 7.9612
| 8722 | 8.6593
| 8723 | 8.1228
| 8724 | 6.7261
| 8725 | 8.1605
| 8726 | 7.1963
| 8727 | 8.1812
| 8728 | 8.5304
| 8729 | 8.1415
| 8730 | 8.342
| 8731 | 8.4676
| 8732 | 7.5932
| 8733 | 7.8502
| 8734 | 8.548
| 8735 | 8.5172
| 8736 | 8.0339
| 8737 | 8.2381
| 8738 | 7.3903
| 8739 | 8.8033
| 8740 | 7.1878
| 8741 | 8.0414
| 8742 | 7.2953
| 8743 | 7.4878
| 8744 | 8.0935
| 8745 | 8.8033
| 8746 | 8.0358
| 8747 | 7.6776
| 8748 | 8.4053
| 8749 | 8.5228
| 8750 | 8.0749
| 8751 | 8.6146
| 8752 | 8.1605
| 8753 | 8.3587
| 8754 | 8.6363
| 8755 | 8.0633
| 8756 | 7.7163
| 8757 | 8.49
| 8758 | 8.1085
| 8759 | 6.9545
| 8760 | 7.6112
| 8761 | 8.0219
| 8762 | 7.6844
| 8763 | 7.0934
| 8764 | 7.2073
| 8765 | 7.4403
| 8766 | 6.9695
| 8767 | 8.4692
| 8768 | 8.7858
| 8769 | 7.9279
| 8770 | 8.7581
| 8771 | 6.8398
| 8772 | 8.3126
| 8773 | 8.8838
| 8774 | 7.6587
| 8775 | 7.8851
| 8776 | 7.9717
| 8777 | 8.833
| 8778 | 7.95
| 8779 | 8.3139
| 8780 | 7.1412
| 8781 | 8.3139
| 8782 | 8.069
| 8783 | 7.6433
| 8784 | 8.2137
| 8785 | 8.5832
| 8786 | 7.0793
| 8787 | 8.6217
| 8788 | 7.9105
| 8789 | 7.538
| 8790 | 8.2217
| 8791 | 7.4925
| 8792 | 8.3475
| 8793 | 8.2572
| 8794 | 7.5051
| 8795 | 6.6349
| 8796 | 7.5938
| 8797 | 8.0265
| 8798 | 7.701
| 8799 | 7.6394
| 8800 | 8.2781
| 8801 | 7.0505
| 8802 | 7.8771
| 8803 | 8.3801
| 8804 | 8.1025
| 8805 | 8.8692
| 8806 | 8.6673
| 8807 | 7.4559
| 8808 | 8.3061
| 8809 | 8.4882
| 8810 | 8.4865
| 8811 | 7.9113
| 8812 | 8.4237
| 8813 | 7.1953
| 8814 | 8.2103
| 8815 | 8.79
| 8816 | 8.5622
| 8817 | 8.9206
| 8818 | 7.976
| 8819 | 7.6328
| 8820 | 8.8225
| 8821 | 7.5063
| 8822 | 7.8339
| 8823 | 8.5025
| 8824 | 7.3954
| 8825 | 7.7325
| 8826 | 7.9483
| 8827 | 7.3775
| 8828 | 8.4882
| 8829 | 7.7396
| 8830 | 7.7576
| 8831 | 8.55
| 8832 | 7.8892
| 8833 | 7.6621
| 8834 | 8.0118
| 8835 | 6.53
| 8836 | 8.1425
| 8837 | 7.3272
| 8838 | 7.1282
| 8839 | 8.2512
| 8840 | 8.6646
| 8841 | 8.1945
| 8842 | 7.1524
| 8843 | 7.7233
| 8844 | 7.7781
| 8845 | 8.4114
| 8846 | 8.654
| 8847 | 7.2033
| 8848 | 7.033
| 8849 | 7.4612
| 8850 | 8.0537
| 8851 | 8.3489
| 8852 | 8.6077
| 8853 | 8.0585
| 8854 | 7.2826
| 8855 | 7.5541
| 8856 | 8.556
| 8857 | 7.7396
| 8858 | 8.2393
| 8859 | 7.9322
| 8860 | 8.7334
| 8861 | 7.9752
| 8862 | 8.6868
| 8863 | 7.2587
| 8864 | 8.0817
| 8865 | 8.1005
| 8866 | 7.9229
| 8867 | 8.6463
| 8868 | 7.9699
| 8869 | 7.1033
| 8870 | 8.6619
| 8871 | 8.0461
| 8872 | 7.9517
| 8873 | 7.9372
| 8874 | 8.1956
| 8875 | 8.5135
| 8876 | 7.3251
| 8877 | 7.8019
| 8878 | 8.1177
| 8879 | 8.4726
| 8880 | 8.0082
| 8881 | 8.3859
| 8882 | 8.1856
| 8883 | 7.4747
| 8884 | 8.3786
| 8885 | 7.2937
| 8886 | 8.6727
| 8887 | 7.2722
| 8888 | 8.1341
| 8889 | 7.3914
| 8890 | 7.8193
| 8891 | 8.3258
| 8892 | 6.9161
| 8893 | 8.3022
| 8894 | 7.8346
| 8895 | 7.266
| 8896 | 7.862
| 8897 | 7.7454
| 8898 | 7.2587
| 8899 | 8.0405
| 8900 | 8.6289
| 8901 | 7.3139
| 8902 | 7.5503
| 8903 | 7.9047
| 8904 | 6.6077
| 8905 | 8.0155
| 8906 | 7.9586
| 8907 | 7.3653
| 8908 | 8.1126
| 8909 | 8.552
| 8910 | 8.6077
| 8911 | 8.6868
| 8912 | 6.6006
| 8913 | 8.6146
| 8914 | 7.0896
| 8915 | 7.5343
| 8916 | 7.9355
| 8917 | 7.9938
| 8918 | 8.7988
| 8919 | 7.9389
| 8920 | 8.3743
| 8921 | 8.13
| 8922 | 8.5007
| 8923 | 8.0046
| 8924 | 7.7613
| 8925 | 8.554
| 8926 | 7.8502
| 8927 | 8.7619
| 8928 | 7.4351
| 8929 | 8.4592
| 8930 | 7.0394
| 8931 | 7.7832
| 8932 | 7.7627
| 8933 | 7.0868
| 8934 | 8.6463
| 8935 | 7.701
| 8936 | 8.2744
| 8937 | 7.89
| 8938 | 7.2093
| 8939 | 7.0802
| 8940 | 7.6321
| 8941 | 8.2548
| 8942 | 8.5343
| 8943 | 8.5642
| 8944 | 6.8182
| 8945 | 7.9956
| 8946 | 8.2381
| 8947 | 8.6241
| 8948 | 8.7107
| 8949 | 8.508
| 8950 | 6.8311
| 8951 | 7.9621
| 8952 | 7.8117
| 8953 | 8.0019
| 8954 | 8.7045
| 8955 | 8.73
| 8956 | 8.5964
| 8957 | 8.338
| 8958 | 7.3825
| 8959 | 8.1595
| 8960 | 8.1383
| 8961 | 8.0518
| 8962 | 7.148
| 8963 | 8.2464
| 8964 | 6.8079
| 8965 | 8.833
| 8966 | 8.3218
| 8967 | 8.8384
| 8968 | 7.8998
| 8969 | 7.1873
| 8970 | 6.6919
| 8971 | 8.0749
| 8972 | 8.0955
| 8973 | 7.4168
| 8974 | 8.7696
| 8975 | 8.0527
| 8976 | 8.4865
| 8977 | 7.6722
| 8978 | 6.9913
| 8979 | 8.3657
| 8980 | 6.6449
| 8981 | 7.6695
| 8982 | 7.1868
| 8983 | 6.5549
| 8984 | 7.076
| 8985 | 8.3393
| 8986 | 7.8292
| 8987 | 8.342
| 8988 | 8.6241
| 8989 | 8.1045
| 8990 | 7.1499
| 8991 | 7.3262
| 8992 | 7.2853
| 8993 | 7.6177
| 8994 | 7.8723
| 8995 | 7.7751
| 8996 | 7.3278
| 8997 | 6.836
| 8998 | 8.0274
| 8999 | 7.3027
| 9000 | 7.5269
| 9001 | 6.8415
| 9002 | 6.4634
| 9003 | 7.817
| 9004 | 7.9947
| 9005 | 8.1106
| 9006 | 8.3559
| 9007 | 8.1724
| 9008 | 7.7974
| 9009 | 7.4259
| 9010 | 7.9682
| 9011 | 8.5581
| 9012 | 8.8225
| 9013 | 8.4625
| 9014 | 5.9493
| 9015 | 7.6735
| 9016 | 7.6989
| 9017 | 7.0991
| 9018 | 8.85
| 9019 | 8.179
| 9020 | 7.5906
| 9021 | 6.9896
| 9022 | 8.2732
| 9023 | 7.8827
| 9024 | 8.0064
| 9025 | 7.6328
| 9026 | 7.5398
| 9027 | 8.1573
| 9028 | 8.5663
| 9029 | 8.4761
| 9030 | 8.4676
| 9031 | 8.0201
| 9032 | 7.2826
| 9033 | 7.1296
| 9034 | 7.251
| 9035 | 8.5401
| 9036 | 8.7619
| 9037 | 7.4872
| 9038 | 8.0846
| 9039 | 7.1243
| 9040 | 8.0182
| 9041 | 7.66
| 9042 | 7.8132
| 9043 | 7.7114
| 9044 | 8.5007
| 9045 | 7.8908
| 9046 | 7.6776
| 9047 | 8.7437
| 9048 | 7.5559
| 9049 | 8.2252
| 9050 | 8.5061
| 9051 | 7.2008
| 9052 | 7.7269
| 9053 | 7.7072
| 9054 | 7.8763
| 9055 | 6.6308
| 9056 | 6.9041
| 9057 | 8.0064
| 9058 | 7.5634
| 9059 | 6.8981
| 9060 | 7.1553
| 9061 | 7.6041
| 9062 | 8.31
| 9063 | 8.033
| 9064 | 7.3016
| 9065 | 7.5913
| 9066 | 7.5964
| 9067 | 7.992
| 9068 | 8.3657
| 9069 | 7.2942
| 9070 | 8.3503
| 9071 | 6.8286
| 9072 | 8.3048
| 9073 | 7.5039
| 9074 | 8.1779
| 9075 | 8.2114
| 9076 | 5.9977
| 9077 | 8.833
| 9078 | 8.3903
| 9079 | 8.1499
| 9080 | 8.5266
| 9081 | 7.4501
| 9082 | 7.5392
| 9083 | 8.3192
| 9084 | 7.5355
| 9085 | 8.6897
| 9086 | 7.4094
| 9087 | 8.6413
| 9088 | 7.5609
| 9089 | 8.1467
| 9090 | 7.2023
| 9091 | 7.3731
| 9092 | 7.6886
| 9093 | 8.7858
| 9094 | 8.3407
| 9095 | 8.5876
| 9096 | 7.6414
| 9097 | 8.2171
| 9098 | 7.9322
| 9099 | 7.9096
| 9100 | 7.2433
| 9101 | 7.8771
| 9102 | 7.2505
| 9103 | 8.1746
| 9104 | 7.516
| 9105 | 8.1404
| 9106 | 6.4977
| 9107 | 8.0019
| 9108 | 6.6152
| 9109 | 6.6951
| 9110 | 7.1602
| 9111 | 7.4294
| 9112 | 7.3648
| 9113 | 7.6374
| 9114 | 8.5043
| 9115 | 6.6594
| 9116 | 7.9096
| 9117 | 8.0228
| 9118 | 7.2826
| 9119 | 8.2794
| 9120 | 8.1867
| 9121 | 8.2512
| 9122 | 7.4083
| 9123 | 7.6824
| 9124 | 8.0349
| 9125 | 7.1359
| 9126 | 7.4985
| 9127 | 8.2645
| 9128 | 7.9673
| 9129 | 8.5421
| 9130 | 8.3126
| 9131 | 7.7142
| 9132 | 7.7297
| 9133 | 6.6772
| 9134 | 7.1282
| 9135 | 8.4269
| 9136 | 7.9039
| 9137 | 8.617
| 9138 | 8.4882
| 9139 | 7.4559
| 9140 | 8.0284
| 9141 | 7.8231
| 9142 | 7.9509
| 9143 | 7.0348
| 9144 | 7.6119
| 9145 | 6.3973
| 9146 | 8.1933
| 9147 | 8.1467
| 9148 | 8.654
| 9149 | 7.6164
| 9150 | 8.5854
| 9151 | 7.7044
| 9152 | 7.4618
| 9153 | 7.6256
| 9154 | 8.2984
| 9155 | 7.7877
| 9156 | 8.6009
| 9157 | 7.4015
| 9158 | 7.8254
| 9159 | 7.4157
| 9160 | 8.0652
| 9161 | 7.9974
| 9162 | 8.2597
| 9163 | 8.2719
| 9164 | 7.2505
| 9165 | 6.8215
| 9166 | 7.3781
| 9167 | 7.4688
| 9168 | 8.8918
| 9169 | 7.6099
| 9170 | 8.4625
| 9171 | 8.1025
| 9172 | 8.1627
| 9173 | 8.5832
| 9174 | 7.3858
| 9175 | 7.5325
| 9176 | 7.654
| 9177 | 8.5876
| 9178 | 6.7794
| 9179 | 8.1259
| 9180 | 7.0234
| 9181 | 8.0499
| 9182 | 8.1005
| 9183 | 8.0856
| 9184 | 6.5187
| 9185 | 7.2654
| 9186 | 8.2645
| 9187 | 7.8517
| 9188 | 7.3937
| 9189 | 7.5276
| 9190 | 7.9743
| 9191 | 7.6838
| 9192 | 7.9322
| 9193 | 7.551
| 9194 | 7.5938
| 9195 | 7.8455
| 9196 | 8.7402
| 9197 | 6.9261
| 9198 | 8.85
| 9199 | 7.8965
| 9200 | 8.4444
| 9201 | 7.7233
| 9202 | 7.4753
| 9203 | 8.2012
| 9204 | 8.5247
| 9205 | 8.0945
| 9206 | 7.8155
| 9207 | 8.552
| 9208 | 7.3332
| 9209 | 8.1573
| 9210 | 8.2405
| 9211 | 8.7402
| 9212 | 7.0189
| 9213 | 7.7368
| 9214 | 8.1228
| 9215 | 7.3571
| 9216 | 7.6607
| 9217 | 7.9406
| 9218 | 7.8723
| 9219 | 8.7619
| 9220 | 8.4269
| 9221 | 7.781
| 9222 | 8.0055
| 9223 | 6.7325
| 9224 | 8.2194
| 9225 | 7.0307
| 9226 | 7.858
| 9227 | 8.6926
| 9228 | 8.5581
| 9229 | 6.7241
| 9230 | 7.8362
| 9231 | 6.4938
| 9232 | 8.6289
| 9233 | 7.0491
| 9234 | 7.71
| 9235 | 8.0311
| 9236 | 8.2217
| 9237 | 7.8208
| 9238 | 8.131
| 9239 | 7.7781
| 9240 | 8.224
| 9241 | 8.7544
| 9242 | 8.1856
| 9243 | 7.9146
| 9244 | 8.5832
| 9245 | 8.3671
| 9246 | 7.9305
| 9247 | 7.1378
| 9248 | 8.1834
| 9249 | 7.5491
| 9250 | 8.0866
| 9251 | 8.0719
| 9252 | 7.899
| 9253 | 8.0749
| 9254 | 8.4709
| 9255 | 7.679
| 9256 | 7.6681
| 9257 | 8.1035
| 9258 | 7.6282
| 9259 | 7.5306
| 9260 | 8.1207
| 9261 | 8.0546
| 9262 | 7.1243
| 9263 | 7.6361
| 9264 | 7.7555
| 9265 | 7.646
| 9266 | 7.2884
| 9267 | 7.7276
| 9268 | 8.0817
| 9269 | 6.878
| 9270 | 7.4824
| 9271 | 8.4953
| 9272 | 7.7184
| 9273 | 8.3166
| 9274 | 8.5116
| 9275 | 6.9166
| 9276 | 7.0514
| 9277 | 7.5269
| 9278 | 7.9875
| 9279 | 7.6607
| 9280 | 8.5705
| 9281 | 7.606
| 9282 | 7.6099
| 9283 | 8.8441
| 9284 | 8.67
| 9285 | 8.91
| 9286 | 8.6783
| 9287 | 7.3993
| 9288 | 7.9526
| 9289 | 8.556
| 9290 | 7.7156
| 9291 | 7.3786
| 9292 | 8.1126
| 9293 | 7.7254
| 9294 | 7.1661
| 9295 | 8.5898
| 9296 | 6.9213
| 9297 | 8.6673
| 9298 | 7.8876
| 9299 | 7.9466
| 9300 | 7.392
| 9301 | 8.3933
| 9302 | 8.1812
| 9303 | 8.5684
| 9304 | 6.7802
| 9305 | 8.2907
| 9306 | 8.446
| 9307 | 8.2068
| 9308 | 8.4971
| 9309 | 7.4027
| 9310 | 8.0265
| 9311 | 7.903
| 9312 | 6.3189
| 9313 | 8.4778
| 9314 | 8.3757
| 9315 | 8.1045
| 9316 | 8.7015
| 9317 | 7.9432
| 9318 | 7.3321
| 9319 | 7.9569
| 9320 | 7.4991
| 9321 | 7.7482
| 9322 | 8.1584
| 9323 | 7.9246
| 9324 | 8.67
| 9325 | 7.5547
| 9326 | 8.5228
| 9327 | 7.9072
| 9328 | 7.4973
| 9329 | 6.3667
| 9330 | 7.387
| 9331 | 6.7368
| 9332 | 8.19
| 9333 | 7.5015
| 9334 | 7.4351
| 9335 | 7.7951
| 9336 | 8.4558
| 9337 | 8.5854
| 9338 | 7.7318
| 9339 | 8.0886
| 9340 | 6.6951
| 9341 | 6.3701
| 9342 | 8.1488
| 9343 | 8.0293
| 9344 | 8.0817
| 9345 | 8.6314
| 9346 | 6.8096
| 9347 | 8.3285
| 9348 | 6.6502
| 9349 | 8.4237
| 9350 | 8.552
| 9351 | 7.8533
| 9352 | 8.1341
| 9353 | 6.859
| 9354 | 8.0955
| 9355 | 8.2001
| 9356 | 8.0585
| 9357 | 7.7226
| 9358 | 7.5541
| 9359 | 6.7504
| 9360 | 7.9138
| 9361 | 6.5589
| 9362 | 7.1239
| 9363 | 8.4847
| 9364 | 7.6028
| 9365 | 7.8109
| 9366 | 7.2821
| 9367 | 7.2937
| 9368 | 6.8511
| 9369 | 8.43
| 9370 | 6.792
| 9371 | 7.362
| 9372 | 8.1362
| 9373 | 7.3283
| 9374 | 7.1651
| 9375 | 8.1768
| 9376 | 8.5116
| 9377 | 8.0886
| 9378 | 8.2621
| 9379 | 7.8517
| 9380 | 8.31
| 9381 | 7.9552
| 9382 | 8.2091
| 9383 | 7.8102
| 9384 | 8.0155
| 9385 | 8.5421
| 9386 | 7.4519
| 9387 | 7.9171
| 9388 | 8.0817
| 9389 | 7.8254
| 9390 | 7.2173
| 9391 | 6.4845
| 9392 | 8.8079
| 9393 | 8.1404
| 9394 | 7.7439
| 9395 | 8.2287
| 9396 | 8.5421
| 9397 | 7.5294
| 9398 | 8.5942
| 9399 | 8.0633
| 9400 | 7.6886
| 9401 | 7.4729
| 9402 | 8.7581
| 9403 | 7.7656
| 9404 | 8.6955
| 9405 | 7.8763
| 9406 | 7.2428
| 9407 | 7.6203
| 9408 | 7.7254
| 9409 | 8.2621
| 9410 | 7.7439
| 9411 | 7.6315
| 9412 | 8.1248
| 9413 | 7.4443
| 9414 | 7.7781
| 9415 | 8.0284
| 9416 | 7.6374
| 9417 | 7.4889
| 9418 | 8.2229
| 9419 | 8.1126
| 9420 | 7.7634
| 9421 | 8.2334
| 9422 | 8.4558
| 9423 | 7.5913
| 9424 | 8.5401
| 9425 | 8.2695
| 9426 | 7.8162
| 9427 | 8.3074
| 9428 | 7.5685
| 9429 | 7.6164
| 9430 | 8.5285
| 9431 | 8.1207
| 9432 | 7.7715
| 9433 | 7.9983
| 9434 | 6.8848
| 9435 | 8.7267
| 9436 | 8.6955
| 9437 | 8.3048
| 9438 | 8.0073
| 9439 | 8.3352
| 9440 | 7.7339
| 9441 | 7.5015
| 9442 | 8.0975
| 9443 | 7.992
| 9444 | 7.6487
| 9445 | 7.6906
| 9446 | 7.7276
| 9447 | 7.7072
| 9448 | 8.4526
| 9449 | 7.2351
| 9450 | 8.3166
| 9451 | 8.338
| 9452 | 7.1749
| 9453 | 8.91
| 9454 | 8.2299
| 9455 | 7.2138
| 9456 | 7.749
| 9457 | 7.5441
| 9458 | 7.7079
| 9459 | 8.4083
| 9460 | 7.3251
| 9461 | 7.2858
| 9462 | 7.5881
| 9463 | 8.1757
| 9464 | 7.3171
| 9465 | 8.3933
| 9466 | 8.1541
| 9467 | 8.8625
| 9468 | 7.6872
| 9469 | 8.13
| 9470 | 8.7619
| 9471 | 8.6463
| 9472 | 7.149
| 9473 | 7.9279
| 9474 | 8.97
| 9475 | 7.2083
| 9476 | 8.2769
| 9477 | 8.4882
| 9478 | 7.8231
| 9479 | 8.4575
| 9480 | 7.4878
| 9481 | 7.0807
| 9482 | 7.2525
| 9483 | 8.244
| 9484 | 8.4129
| 9485 | 8.1779
| 9486 | 8.3545
| 9487 | 8.5323
| 9488 | 7.9902
| 9489 | 8.4608
| 9490 | 6.9392
| 9491 | 8.5622
| 9492 | 7.8262
| 9493 | 8.2299
| 9494 | 8.4348
| 9495 | 8.3192
| 9496 | 8.1015
| 9497 | 7.3631
| 9498 | 7.7382
| 9499 | 8.1341
| 9500 | 8.0182
| 9501 | 7.6989
| 9502 | 7.4254
| 9503 | 8.3801
| 9504 | 7.4753
| 9505 | 7.4276
| 9506 | 6.4212
| 9507 | 6.9904
| 9508 | 7.77
| 9509 | 7.6009
| 9510 | 6.9532
| 9511 | 8.5247
| 9512 | 8.0915
| 9513 | 8.3743
| 9514 | 7.8811
| 9515 | 7.2392
| 9516 | 7.4403
| 9517 | 8.2287
| 9518 | 8.9329
| 9519 | 8.8918
| 9520 | 7.3446
| 9521 | 8.6593
| 9522 | 8.3061
| 9523 | 7.681
| 9524 | 7.5843
| 9525 | 7.7722
| 9526 | 8.0546
| 9527 | 7.9875
| 9528 | 8.0935
| 9529 | 7.6831
| 9530 | 7.7023
| 9531 | 6.9514
| 9532 | 8.5362
| 9533 | 7.7212
| 9534 | 8.0604
| 9535 | 7.7065
| 9536 | 7.29
| 9537 | 8.79
| 9538 | 8.1552
| 9539 | 8.2217
| 9540 | 7.3101
| 9541 | 7.3133
| 9542 | 7.5697
| 9543 | 7.992
| 9544 | 7.762
| 9545 | 8.5811
| 9546 | 7.6627
| 9547 | 7.4973
| 9548 | 7.3181
| 9549 | 8.1499
| 9550 | 7.3847
| 9551 | 7.5184
| 9552 | 8.3061
| 9553 | 7.8393
| 9554 | 7.2484
| 9555 | 7.82
| 9556 | 7.1968
| 9557 | 7.3203
| 9558 | 8.5025
| 9559 | 7.2188
| 9560 | 7.784
| 9561 | 7.8331
| 9562 | 8.3657
| 9563 | 7.0944
| 9564 | 7.5697
| 9565 | 7.7382
| 9566 | 6.9335
| 9567 | 6.9638
| 9568 | 7.2895
| 9569 | 7.6722
| 9570 | 7.9849
| 9571 | 8.0955
| 9572 | 7.8691
| 9573 | 8.7045
| 9574 | 6.6978
| 9575 | 7.5312
| 9576 | 7.656
| 9577 | 8.0284
| 9578 | 7.7497
| 9579 | 7.133
| 9580 | 7.6269
| 9581 | 6.5093
| 9582 | 7.7914
| 9583 | 6.8477
| 9584 | 8.1488
| 9585 | 7.5331
| 9586 | 7.9629
| 9587 | 7.1263
| 9588 | 7.83
| 9589 | 8.6783
| 9590 | 7.944
| 9591 | 7.47
| 9592 | 7.4386
| 9593 | 8.6839
| 9594 | 8.179
| 9595 | 8.2125
| 9596 | 7.749
| 9597 | 7.1725
| 9598 | 7.6513
| 9599 | 7.2093
| 9600 | 8.2171
| 9601 | 7.8178
| 9602 | 8.2322
| 9603 | 6.6807
| 9604 | 7.6695
| 9605 | 7.7332
| 9606 | 7.9734
| 9607 | 8.1746
| 9608 | 7.6125
| 9609 | 7.8557
| 9610 | 8.3009
| 9611 | 7.133
| 9612 | 7.8185
| 9613 | 6.7432
| 9614 | 8.6926
| 9615 | 8.548
| 9616 | 7.7375
| 9617 | 7.8957
| 9618 | 6.9378
| 9619 | 7.2325
| 9620 | 7.6996
| 9621 | 8.3559
| 9622 | 8.544
| 9623 | 8.5209
| 9624 | 7.8707
| 9625 | 7.4055
| 9626 | 8.0055
| 9627 | 8.1116
| 9628 | 7.0189
| 9629 | 7.3631
| 9630 | 6.7416
| 9631 | 8.0866
| 9632 | 7.8998
| 9633 | 8.6619
| 9634 | 8.7334
| 9635 | 7.0723
| 9636 | 7.5081
| 9637 | 8.1085
| 9638 | 8.3743
| 9639 | 7.9831
| 9640 | 7.1621
| 9641 | 7.4191
| 9642 | 8.5622
| 9643 | 7.8525
| 9644 | 8.3743
| 9645 | 8.5811
| 9646 | 8.0719
| 9647 | 8.3126
| 9648 | 8.833
| 9649 | 5.6141
| 9650 | 7.8651
| 9651 | 8.0886
| 9652 | 7.7461
| 9653 | 8.2357
| 9654 | 7.0431
| 9655 | 7.0929
| 9656 | 7.8949
| 9657 | 8.6566
| 9658 | 6.9352
| 9659 | 7.6553
| 9660 | 6.8658
| 9661 | 7.3181
| 9662 | 7.862
| 9663 | 8.6314
| 9664 | 6.5143
| 9665 | 7.7533
| 9666 | 7.729
| 9667 | 8.2945
| 9668 | 7.3155
| 9669 | 8.6783
| 9670 | 8.1415
| 9671 | 8.4989
| 9672 | 7.8675
| 9673 | 8.2945
| 9674 | 7.5824
| 9675 | 8.3126
| 9676 | 7.0532
| 9677 | 7.6934
| 9678 | 7.9708
| 9679 | 8.0856
| 9680 | 6.8789
| 9681 | 7.5202
| 9682 | 7.9129
| 9683 | 6.334
| 9684 | 7.6354
| 9685 | 7.903
| 9686 | 6.6853
| 9687 | 8.0461
| 9688 | 8.3009
| 9689 | 7.1263
| 9690 | 7.7671
| 9691 | 8.1106
| 9692 | 7.84
| 9693 | 7.6022
| 9694 | 7.3549
| 9695 | 8.0518
| 9696 | 6.0953
| 9697 | 7.3593
| 9698 | 8.4364
| 9699 | 7.9423
| 9700 | 7.4559
| 9701 | 7.4374
| 9702 | 7.1769
| 9703 | 6.6842
| 9704 | 8.1238
| 9705 | 8.6593
| 9706 | 7.7562
| 9707 | 7.4979
| 9708 | 7.9534
| 9709 | 7.9171
| 9710 | 7.2505
| 9711 | 8.0228
| 9712 | 8.1279
| 9713 | 7.2361
| 9714 | 8.4098
| 9715 | 7.7212
| 9716 | 8.4865
| 9717 | 7.7773
| 9718 | 8.4316
| 9719 | 7.9647
| 9720 | 7.4197
| 9721 | 7.5361
| 9722 | 8.4412
| 9723 | 7.4741
| 9724 | 8.4396
| 9725 | 7.1014
| 9726 | 8.1922
| 9727 | 6.9788
| 9728 | 8.8763
| 9729 | 6.9994
| 9730 | 8.3601
| 9731 | 8.2416
| 9732 | 7.0774
| 9733 | 8.4813
| 9734 | 7.4391
| 9735 | 6.538
| 9736 | 8.0925
| 9737 | 7.8377
| 9738 | 7.969
| 9739 | 8.546
| 9740 | 8.9005
| 9741 | 8.1218
| 9742 | 7.652
| 9743 | 7.5215
| 9744 | 8.6388
| 9745 | 7.6054
| 9746 | 8.3859
| 9747 | 6.5201
| 9748 | 7.2603
| 9749 | 7.5411
| 9750 | 8.1812
| 9751 | 8.6217
| 9752 | 7.5337
| 9753 | 6.664
| 9754 | 7.9813
| 9755 | 6.5715
| 9756 | 7.2995
| 9757 | 8.5382
| 9758 | 7.9743
| 9759 | 8.4191
| 9760 | 7.944
| 9761 | 8.4744
| 9762 | 7.299
| 9763 | 8.3462
| 9764 | 7.6467
| 9765 | 7.7788
| 9766 | 7.1617
| 9767 | 8.548
| 9768 | 7.6334
| 9769 | 6.8477
| 9770 | 7.1509
| 9771 | 8.4253
| 9772 | 8.0995
| 9773 | 8.3918
| 9774 | 7.6184
| 9775 | 7.5294
| 9776 | 8.4761
| 9777 | 7.5666
| 9778 | 7.5926
| 9779 | 7.4671
| 9780 | 7.7332
| 9781 | 7.0399
| 9782 | 8.2658
| 9783 | 8.2536
| 9784 | 7.1514
| 9785 | 7.7922
| 9786 | 7.3435
| 9787 | 7.7715
| 9788 | 8.4144
| 9789 | 8.0046
| 9790 | 8.2322
| 9791 | 8.5061
| 9792 | 7.9154
| 9793 | 7.063
| 9794 | 8.1989
| 9795 | 7.372
| 9796 | 6.859
| 9797 | 7.1393
| 9798 | 7.0121
| 9799 | 8.6193
| 9800 | 7.9586
| 9801 | 7.8049
| 9802 | 8.2894
| 9803 | 7.5691
| 9804 | 7.7773
| 9805 | 7.3408
| 9806 | 7.9813
| 9807 | 8.8838
| 9808 | 7.8478
| 9809 | 8.3786
| 9810 | 8.6593
| 9811 | 7.9398
| 9812 | 8.3874
| 9813 | 6.6085
| 9814 | 8.338
| 9815 | 7.5105
| 9816 | 8.0499
| 9817 | 8.3245
| 9818 | 8.717
| 9819 | 7.9893
| 9820 | 8.3918
| 9821 | 8.2229
| 9822 | 8.5705
| 9823 | 7.77
| 9824 | 7.1715
| 9825 | 7.8502
| 9826 | 8.0661
| 9827 | 7.4409
| 9828 | 6.7669
| 9829 | 7.7922
| 9830 | 7.0367
| 9831 | 7.6641
| 9832 | 7.9708
| 9833 | 8.1116
| 9834 | 8.49
| 9835 | 7.9893
| 9836 | 7.2392
| 9837 | 8.2428
| 9838 | 8.3475
| 9839 | 8.6646
| 9840 | 8.4191
| 9841 | 6.6502
| 9842 | 7.2123
| 9843 | 7.1918
| 9844 | 6.7665
| 9845 | 8.4509
| 9846 | 8.3601
| 9847 | 7.4111
| 9848 | 8.4935
| 9849 | 8.3772
| 9850 | 7.2884
| 9851 | 7.3931
| 9852 | 7.9014
| 9853 | 8.1922
| 9854 | 8.5898
| 9855 | 7.9595
| 9856 | 7.1427
| 9857 | 7.7996
| 9858 | 8.13
| 9859 | 8.01
| 9860 | 7.9113
| 9861 | 7.4294
| 9862 | 7.0821
| 9863 | 8.2548
| 9864 | 8.4659
| 9865 | 6.8481
| 9866 | 7.0953
| 9867 | 8.416
| 9868 | 7.1799
| 9869 | 7.9965
| 9870 | 7.2018
| 9871 | 8.2229
| 9872 | 8.2932
| 9873 | 7.3213
| 9874 | 8.3245
| 9875 | 8.3048
| 9876 | 8.2346
| 9877 | 7.8949
| 9878 | 7.8755
| 9879 | 8.1177
| 9880 | 8.3061
| 9881 | 8.267
| 9882 | 8.7696
| 9883 | 6.1036
| 9884 | 7.7375
| 9885 | 7.5786
| 9886 | 7.933
| 9887 | 7.8843
| 9888 | 8.4509
| 9889 | 8.0349
| 9890 | 7.3881
| 9891 | 7.5251
| 9892 | 7.9595
| 9893 | 8.3113
| 9894 | 7.5479
| 9895 | 7.3511
| 9896 | 6.7879
| 9897 | 7.77
| 9898 | 7.8478
| 9899 | 6.4226
| 9900 | 6.9344
| 9901 | 7.6282
| 9902 | 8.446
| 9903 | 8.4608
| 9904 | 6.4422
| 9905 | 8.5705
| 9906 | 8.5266
| 9907 | 7.4967
| 9908 | 7.9423
| 9909 | 8.2984
| 9910 | 7.4322
| 9911 | 6.488
| 9912 | 7.7304
| 9913 | 8.3517
| 9914 | 6.9936
| 9915 | 8.8561
| 9916 | 7.8369
| 9917 | 8.3601
| 9918 | 8.0797
| 9919 | 8.7234
| 9920 | 7.4777
| 9921 | 8.5209
| 9922 | 8.8441
| 9923 | 8.1055
| 9924 | 7.6407
| 9925 | 7.228
| 9926 | 8.3434
| 9927 | 7.8819
| 9928 | 8.5228
| 9929 | 7.7311
| 9930 | 8.1015
| 9931 | 7.8707
| 9932 | 7.1048
| 9933 | 8.131
| 9934 | 7.3925
| 9935 | 8.5401
| 9936 | 8.0613
| 9937 | 7.9629
| 9938 | 7.6328
| 9939 | 7.6177
| 9940 | 7.6688
| 9941 | 6.9629
| 9942 | 8.2524
| 9943 | 7.4072
| 9944 | 8.1404
| 9945 | 8.1331
| 9946 | 6.4542
| 9947 | 6.6621
| 9948 | 8.6489
| 9949 | 6.8336
| 9950 | 7.8572
| 9951 | 6.6258
| 9952 | 8.5382
| 9953 | 7.8064
| 9954 | 8.2945
| 9955 | 7.3321
| 9956 | 7.9415
| 9957 | 7.8432
| 9958 | 8.4098
| 9959 | 8.208
| 9960 | 8.0807
| 9961 | 7.9296
| 9962 | 8.0414
| 9963 | 7.5239
| 9964 | 7.5148
| 9965 | 8.4083
| 9966 | 7.3931
| 9967 | 8.8033
| 9968 | 7.8723
| 9969 | 7.3332
| 9970 | 8.7267
| 9971 | 7.7205
| 9972 | 8.179
| 9973 | 7.516
| 9974 | 7.9338
| 9975 | 7.7788
| 9976 | 7.3998
| 9977 | 7.6035
| 9978 | 7.3181
| 9979 | 6.6232
| 9980 | 7.0948
| 9981 | 7.0518
| 9982 | 7.9138
| 9983 | 7.4594
| 9984 | 8.1146
| 9985 | 7.7347
| 9986 | 7.7576
| 9987 | 7.3875
| 9988 | 7.4895
| 9989 | 7.5528
| 9990 | 7.6607
| 9991 | 8.7437
| 9992 | 8.4608
| 9993 | 7.8612
| 9994 | 8.0256
| 9995 | 6.5696
| 9996 | 8.5811
| 9997 | 8.1735
| 9998 | 7.6387
| 9999 | 6.7855
| 10000 | 8.4038
12.7
| 0.66667 | 0.32432 | FALSE | 0
| 0.66667 | 0.7 | FALSE | 0
| 1 | 1.0243 | FALSE | 0 | 0.66667
| 1.3333 | 1.3486 | FALSE | 0 | 1
| 1.6667 | 1.673 | FALSE | 0 | 1.3333
| 2 | 1.9973 | FALSE | 0 | 1.6667
| 2.3333 | 2.3216 | FALSE | 0 | 2
| 2.6667 | 2.6459 | FALSE | 0 | 2.3333
| 3 | 2.9703 | FALSE | 0 | 2.6667
| 3.3333 | 3.2946 | FALSE | 0 | 3
| 3.6667 | 3.6189 | FALSE | 0 | 3.3333
| 4 | 3.9432 | FALSE | 0 | 3.6667
| 4.3333 | 4.2676 | FALSE | 0 | 4
| 4.6667 | 4.5919 | FALSE | 0 | 4.3333
| 5 | 4.9162 | FALSE | 0 | 4.6667
| 5.3333 | 5.2405 | FALSE | 0 | 5
| 5.6667 | 5.5649 | FALSE | 0 | 5.3333 | 7.8571
| 6 | 5.8892 | FALSE | 0 | 5.6667
| 6.3333 | 6.2135 | FALSE | 0 | 6
| 6.6667 | 6.5378 | FALSE | 0 | 6.3333
| 7 | 6.8622 | FALSE | 0 | 6.6667
| 7.3333 | 7.1865 | FALSE | 0 | 7
| 7.6667 | 7.5108 | FALSE | 0.05 | 7.3333
| 8 | 7.8351 | TRUE | 0 | 7.6667
| 8.3333 | 8.1595 | FALSE | 0 | 8
| 8.6667 | 8.4838 | FALSE | 0 | 8.3333
| 9 | 8.8081 | FALSE | 0 | 8.6667
| 9.3333 | 9.1324 | FALSE | 0 | 9
| 9.6667 | 9.4568 | FALSE | 0 | 9.3333
| 10 | 9.7811 | FALSE | 0 | 9.6667
| 10.3333 | 10.1054 | FALSE | 0 | 10
| 10.6667 | 10.4297 | FALSE | 0 | 10.3333
| 11 | 10.7541 | FALSE | 0 | 10.6667
| 11.3333 | 11.0784 | FALSE | 0 | 11
| 11.6667 | 11.4027 | FALSE | 0 | 11.3333
| 12 | 11.727 | FALSE | 0 | 11.6667
| 12.3333 | 12.0514 | FALSE | 0 | 12
| 12.6667 | 12.7 | FALSE | 0 | 12.3333 |  | 0
|  | 0 |  |  | 12.6667 |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0.0001
|  | 0.0001 |  |  |  |  | 0.0005
|  | 0.0005 |  |  |  |  | 0.0023
|  | 0.0023 |  |  |  |  | 0.0122
|  | 0.0122 |  |  |  |  | 0.039
|  | 0.039 |  |  |  |  | 0.0762
|  | 0.0762 |  |  |  |  | 0.133
|  | 0.133 |  |  |  |  | 0.1904
|  | 0.1904 |  |  |  |  | 0.2156
|  | 0.2156 |  |  |  |  | 0.1921
|  | 0.1921 |  |  |  |  | 0.1188
|  | 0.1188 |  |  |  |  | 0.0198
|  | 0.0198 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
|  | 0 |  |  |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0.0001
0.0006
0.0029
0.0151
0.0541
0.1303
0.2633
0.4537
0.6693
0.8614
0.9802
1
1
1
1
1
1
1
1
1
1
1
Data Table
This data table calculates the maximum of the task durations for each trial. The work is actually done in the Model sheet cell H10, pointed to by the data table formula cell C3.